## Read Me
Alex West - underground pipe construction sequence and methodology
Prepared 22 Oct 2026 by Claude for Mohamed. Planning workbook: not a design, temporary-works or construction approval.
What it is
A sequence, methodology and logic-linked activity programme for the 201 pipe packages (45 lines) of the v3 package workbook, re-checked for groundwater at -1.50 and with every pipe carried on piles and a piled slab.
Inputs used
1. Alex-West-Pipe-Execution-Packages-All-Lines.xlsx (v3, 21 Oct 2026): packages, pieces, levels, nearest structures and piles, holds, sequence notes.
2. Alex-West-Combined-Coordination.blend (19 Oct 2026): aeration pile status for 3,672 piles (data date 17 Oct 2026), agreed aeration piling zone order, recorded weekly piling production, structure register (stage and open gaps). Check: pile counts near UG-02-S03 reproduce the package workbook (31 within 15 m, 18 pending).
3. Decisions (Mohamed, 22 Oct 2026): groundwater level -1.50; all pipes need piles and foundations; shoring where needed.
4. The web viewer link could not be opened from this environment (host blocked); the .blend file was used instead.
Sheets
Methodology - step-by-step method, plant, hold points and the sequencing rules.
Inputs - levels, groundwater, slopes, pile layout, gates and productivity (yellow = edit).
Aeration - pile status by zone from the model, actual production rate, forecast zone completion that gates nearby pipe packages.
Structures - enter the date each structure is ready for tie-in (no progress data for these in the model).
Fronts - eight work fronts, crew numbers (yellow; 2 crews by default on fronts over 1.3 km) and front start / finish.
Packages - method (open cut / sheet piles), excavation, slab, backfill, piles, sheet piles, dewatering, flotation check and dates per package.
Activities - 2,211 activities (11 per package) with formula-driven durations and dates; Relationships - the same logic as a P6 / MS Project import list.
Programme - front and line summary with a monthly bar chart and monthly counts of activities and piles. Sensitivity - sheet-piled length under other ground rules.
Piece check - the piece-level method, volume and flotation calculations behind Packages.
How the logic works
Within a package: ladder (start-to-start at LADDER share of the predecessor, finish-to-finish FFLAG). Across packages: crew continuity per front, deeper line first, shared-trench excavation together, tie-in closure after the adjacent run, gates (DLU approval, pile design, crossing identification, structure readiness, aeration zones).
Dates are calendar dates; a finish date is the start of the next free day. Working days convert to calendar days by x 7 / WD.
Six shared-trench backfill holds could not be linked without creating a logic loop; they are marked COORDINATE ON SITE in the Packages "Interactions" column.
What drives the dates now
START is an example (1 Dec 2026). DLU approval, pile design and crossing-identification dates are set equal to START, so they do not constrain yet. Structure readiness is blank. Enter these and the programme recalculates. Productivity values are assumptions except pipe piling, which is calibrated to the site aeration piling.
Holds that apply to every package
All holds of the package workbook remain (vertical datum not verified, envelope levels, interpolated levels, slab basis, missing pile layouts, structures not in the master). New: groundwater design value, slopes below GWL and the depth limit for open cut are assumptions for geotechnical confirmation; pipe pile layout is a placeholder.
Colour key
Blue text = input or source data; black = formula; green = formula pulling from another sheet; yellow fill = edit.

## Methodology
Construction methodology - buried GRP / HDPE pipes on piled slabs, groundwater at -1.50
Planning methodology for sequencing and resourcing. Not a temporary-works design or a method statement for approval.
Step | Activity (code) | Method | Plant / crew | Hold points and checks | Quantity / duration basis
1 | Release (A010) | Package released only when: DLU-002 approved (Rev 03 is Issued for Approval); pile and slab design approved; the connected structure is ready for tie-in packages; aeration piling in the adjacent zone is complete where open aeration piles are within 15 m; unassigned crossing pipes identified (UG-01-S02, UG-02-S04, UG-03-S03). | Planning / engineering | IFC drawing; pile design; permit to dig; structure handover certificate; aeration zone piling complete. | Gates on Inputs, Structures and Aeration sheets.
2 | Set-out and working platform (A020) | Survey pipe axis, slab edges, pile positions and sheet lines. Trial pits / scanning at every crossing listed on Packages. Granular working platform at NG for piling rigs and cranes on very soft clay; platform designed for rig track pressure. | Survey team, dozer, roller | Platform bearing check (plate test) before rig access. | Plan length / R_PLAT.
3 | Pipe-support piling (A030) | All pipes are carried on piles and a piled slab. Install piles from the platform at NG BEFORE excavation (CFA or bored, 600 mm assumed), concreting to above cut-off and leaving the empty-bore length to the slab soffit. Rigs follow the front order; near structures and aeration piles keep the agreed clearances. | 1-2 rigs per front (Fronts sheet); site actual 5.4 piles / rig / day, 5.0 used | Pile records, integrity tests on every pile, preliminary load test before production. | Piles = (length / PILE_SP + 1) x piles per row - placeholder until pile design.
4 | Sheet piles (A040) | Where the Piece check says sheet piles (open cut does not fit beside a structure / pile, or excavation is deeper than MAXOC below GWL): install interlocking steel sheets both sides after piling, with a toe in the soft clay for cut-off and base stability. Press-in (silent) method within 10 m of structures and fresh piles to limit vibration. | Sheet pile gang with vibro / press-in rig and crane | Temporary works design: embedment, struts, base heave, hydraulic cut-off. | Wall = 2 x shored length; sheet length = depth x SHEET_RATIO.
5 | Dewatering (A050) | Groundwater at -1.50 and excavation bottoms down to -7.6 (199 of 201 packages below GWL, up to 6.1 m) mean almost every package is dewatered. Wellpoints along the trench to 0.5 m below formation; deep wells or two-stage wellpoints where drawdown exceeds 4.5 m. Draw down for at least DW_DRAW days before excavation. Monitor levels next to existing structures and fresh piles (settlement / negative skin friction). | Dewatering subcontractor, standby pumps and power | Piezometers; settlement markers on structures within 15 m; discharge permit and silt treatment. | Drawdown = GWL - (R - DD_BELOW); method on Packages.
6 | Excavation and strutting (A060) | Excavate in layers, installing walings and struts as each level is reached. Keep the excavator off the edge in soft clay; stockpile away from the trench. Excavate evenly around the installed piles so they are not pushed sideways. Deeper lines are excavated, laid and backfilled before a shallower line in the same corridor; lines in a shared trench are opened together. | Long-reach excavator / clamshell, trucks | Formation inspection; pile head exposure survey; strut loads. | Shored m3 / R_EXS + open-cut m3 / R_EXO.
7 | Piled slab (A070) | Break down pile heads to cut-off, blinding, reinforcement with pile starter bars, cast the 0.50 m piled slab (pipe cradle or anchor straps cast in where the flotation check needs them). Cure before pipe load. | Concrete gang, pump | Pile head inspection; rebar inspection before pour; cube results. | Length / R_SLAB + SLAB_CURE.
8 | Pipe laying and jointing (A080) | Lay from the downstream end upwards (gravity lines). GRP: bell and spigot joints with a crane and lifting beam; HDPE: butt fusion off-line, lowered in strings. Fittings and thrust restraint as drawn. Tie-in packages are laid last as the closure to the structure, once the structure is ready. | Pipe crew + crane per front; fusion machine for HDPE | Joint test per joint (GRP); fusion records (HDPE); alignment and level survey. | Length / pipe rate by OD + fittings x FIT_D + TIE_D at tie-ins.
9 | Surround and testing (A090) | Granular haunch and surround placed and compacted evenly both sides (flexible pipes). Line test by section. | Pipe crew | Deflection check (GRP); hydrostatic / air test. | TEST_D + length / R_TEST.
10 | Backfill (A100) | Backfill in layers to NG, removing struts progressively as the fill reaches each level. Shared-trench pipes are all laid before backfill starts. Keep dewatering running until the flotation check is met (Packages column "Flotation action"): empty pipes below -1.50 can float. | Excavator, compactors | Compaction tests; flotation check before switching off pumps. | Backfill m3 / R_BF.
11 | Dewatering off, extract sheets (A110) | Switch off and remove dewatering only after the fill is heavy enough (or the pipe is strapped to the slab). Extract sheet piles slowly, grouting voids near pipes and structures. Reinstate the platform / surface. | Crane with vibro extractor | Survey pipe level after pumps off; settlement monitoring. | Wall m / R_EXT.
| Sequencing rules (whole network) | 1) Eight fronts by system (Fronts sheet). A shared-trench corridor that crosses systems is built by one front (the one holding most of its length; 30 packages moved). 2) Within a front: deeper lines first, downstream first; shared-trench packages back to back along the corridor. 3) Deeper-first links between packages within 8 m with excavation bottoms more than 1 m apart. 4) Shared trench (bottoms within 1 m): excavate together, backfill only after all its pipes are laid (6 such holds are site coordination items - see Packages). 5) Set-out runs one package ahead of piling; dewatering is timed so drawdown completes when the excavation crew is free. 6) Tie-ins follow the adjacent run, wait for the structure and close the line. 7) Packages within 15 m of open aeration piles wait for that zone, in the agreed zone order. 8) Pipe piling waits for pile design approval; nothing starts before DLU-002 approval. |  | Pending decisions: GWL design value confirmation; slope and depth-limit rules; pile layout; structure readiness dates.
| Rig planning note | 8 rigs are on aeration piling at about 5.4 piles / rig / working day (measured from the model). 1,587 open aeration piles remain; at that rate they finish around end November 2026 (Aeration sheet). Pipe-support piling (about 5,800 piles on the placeholder layout) peaks at about 13 equivalent rigs in the first months (Programme sheet, row Rigs), so releasing the aeration rigs to the pipe fronts is the natural hand-over.

## Inputs
Inputs - levels, ground, groundwater, piles, programme gates and productivity
Yellow = edit. Every quantity, method flag, duration and date in this workbook recalculates from these cells.
Name | Description | Value | Unit | Source / status
Levels and ground
NG | Adopted natural ground level | -0.7 | m | Package workbook Inputs (D-004, Mohamed 20 Oct 2026). Single site value.
FL | Finished ground level | 1 | m | Package workbook Inputs (D-004; DLU sections FGL +1.00).
GWL | Groundwater level for design of temporary works | -1.5 | m | Mohamed, 22 Oct 2026.
SLAB | Piled slab + blinding below external pipe bottom (excavation bottom R = pipe bottom - SLAB) | 0.5 | m | D-001, user-stated basis. All pipes on piles and a piled slab (Mohamed, 22 Oct 2026). No pile/slab design yet.
SLABOVH | Piled slab overhang beyond pipe outside, each side | 0.5 | m | ASSUMPTION for concrete quantity only.
WS | Working space, pipe outside to trench toe / sheet line | 1 | m | AGREED by Mohamed, 21 Oct 2026.
SLOPE_A | Open-cut side slope above GWL (H per 1 V) | 1.5 | H:V | ASSUMPTION (very soft silty clay). Package workbook value.
SLOPE_B | Open-cut side slope below GWL, dewatered (H per 1 V) | 2 | H:V | ASSUMPTION: flatter below water in soft clay. Geotechnical confirmation needed.
MAXOC | Maximum excavation depth below GWL allowed in open cut (deeper = sheet piles regardless of space) | 2.5 | m | ASSUMPTION: base heave / slope stability limit in soft clay below water. See Sensitivity sheet.
DD_BELOW | Drawdown target below excavation formation | 0.5 | m | Planning rule of thumb.
WP_LIMIT | Maximum drawdown for single-stage wellpoints | 4.5 | m | Planning rule of thumb; deeper needs deep wells / two stages.
GAM_D | Unit weight of backfill above GWL | 18 | kN/m3 | ASSUMPTION.
GAM_S | Saturated unit weight of backfill below GWL | 18 | kN/m3 | ASSUMPTION.
GAM_W | Unit weight of water | 9.81 | kN/m3 | Physical constant.
FOS_FLOT | Required factor of safety against pipe flotation (empty pipe, pipe weight ignored) | 1.1 | - | Planning check value.
Pipe-support piles and sheet piles (no pile design available - layout is a planning placeholder)
PILE_SP | Longitudinal spacing of pile rows under the pipe slab | 3 | m | ASSUMPTION - replace with pile design.
PILE_THR | Outside diameter at or above which two piles per row are used | 1 | m | ASSUMPTION.
PILE_N_SMALL | Piles per row below the threshold | 1 | no. | ASSUMPTION.
PILE_N_LARGE | Piles per row at or above the threshold | 2 | no. | ASSUMPTION.
SHEET_RATIO | Sheet pile length / excavation depth from NG (embedment in soft clay) | 2 | - | ASSUMPTION - temporary works design to confirm.
Programme gates and calendar
START | Pipe works mobilisation (earliest start of any package) | 2026-12-01 | date | EXAMPLE - replace with the planned mobilisation date.
D_DLU | DLU-002 approved / IFC (Rev 03 is Issued for Approval) | 2026-12-01 | date | Not yet known - currently equal to START (not constraining). Enter the forecast approval date.
D_PILEDES | Pipe pile and slab design approved | 2026-12-01 | date | Not yet known - currently equal to START (not constraining). Gates all pipe piling.
D_XING | Unassigned crossing pipes P0114 / P0117 / P0279 identified | 2026-12-01 | date | Not yet known - gates excavation of UG-01-S02, UG-02-S04, UG-03-S03.
WD | Working days per week | 6 | days | Site calendar Sat-Thu (calendar days = working days x 7 / WD).
LADDER | Overlap within a package: successor starts after this share of its predecessor | 0.3 | - | Planning rule (start-to-start ladder). 1.0 = finish-to-start.
FFLAG | Finish-to-finish lag between consecutive activities in a package | 2 | cal. days | Planning rule.
Productivity per crew / rig (per working day)
R_PLAT | Set-out, crossing survey and working platform | 80 | m/day | ASSUMPTION.
R_PILE | Pipe-support piles per rig (600 mm assumed) | 5 | piles/day | Site actual on aeration 600 mm piling = 5.4 (last 4 full weeks, Aeration sheet). 5.0 used for the longer empty bore from NG.
R_SHEET | Sheet pile installation (vibro / press-in near structures) | 25 | m wall/day | ASSUMPTION.
R_DW | Dewatering installation along the trench | 40 | m/day | ASSUMPTION.
DW_DRAW | Drawdown period before excavation | 7 | days | ASSUMPTION - soft silty clay is slow to drain.
R_EXS | Excavation in a strutted sheet-piled trench | 250 | m3/day | ASSUMPTION.
R_EXO | Excavation in dewatered open cut | 450 | m3/day | ASSUMPTION.
R_SLAB | Pile trimming, blinding and piled slab (rebar, form, pour) | 12 | m/day | ASSUMPTION.
SLAB_CURE | Slab cure before pipe loading | 3 | days | ASSUMPTION.
R_PIPE_L | Pipe laying, outside diameter >= PIPE_T1 | 20 | m/day | ASSUMPTION.
R_PIPE_M | Pipe laying, PIPE_T2 <= outside diameter < PIPE_T1 | 30 | m/day | ASSUMPTION.
R_PIPE_S | Pipe laying, outside diameter < PIPE_T2 | 40 | m/day | ASSUMPTION.
PIPE_T1 | Large-diameter threshold | 2 | m | ASSUMPTION.
PIPE_T2 | Medium-diameter threshold | 1.2 | m | ASSUMPTION.
FIT_D | Extra time per fitting (elbow, tee, reducer) | 0.5 | days | ASSUMPTION.
TIE_D | Structure connection (puddle flange / grouting) per tie-in package | 3 | days | ASSUMPTION.
TEST_D | Joint and line test, fixed time per package | 2 | days | ASSUMPTION.
R_TEST | Surround and testing progress | 150 | m/day | ASSUMPTION.
R_BF | Backfill and compaction in layers | 350 | m3/day | ASSUMPTION.
R_EXT | Sheet pile extraction | 50 | m wall/day | ASSUMPTION.

## Aeration
Aeration piling status and zone forecast (from the 3D model)
Source: Alex-West-Combined-Coordination.blend, scene "AW-AER Piles Actual - 2026-10-18"; tracking data date 17 Oct 2026. Done = recorded execution, not acceptance. Agreed piling order (18 Oct 2026): Zones 1, 2, 3, then 5 and 4 together, then 6, then 7, then 8.
Zone | Group order | Done | Pending | Defect | Unknown | Open piles to complete (pending + defect) | Cumulative open piles in agreed order | Forecast zone piling complete | Pipe packages gated
1 | 1 | 470 | 6 | 2 | 0 | 8 | 8 | 2026-10-18 | 0
2 | 2 | 518 | 41 | 2 | 3 | 43 | 51 | 2026-10-19 | 0
3 | 3 | 248 | 236 | 2 | 0 | 238 | 289 | 2026-10-25 | 3
4 | 4 | 221 | 337 | 3 | 0 | 340 | 770 | 2026-11-07 | 1
5 | 4 | 223 | 137 | 4 | 0 | 141 | 770 | 2026-11-07 | 2
6 | 5 | 134 | 279 | 5 | 0 | 284 | 1054 | 2026-11-15 | 0
7 | 6 | 121 | 296 | 1 | 0 | 297 | 1351 | 2026-11-23 | 2
8 | 7 | 144 | 236 | 0 | 3 | 236 | 1587 | 2026-11-29 | 3
Total |  | 2079 | 1568 | 19 | 6 | 1587
Production basis
AER_DATA | Tracking data date |  |  |  |  | 2026-10-17 | From model properties (Tracking_Data_Date).
AER_RIGS | Rigs assumed to stay on aeration piling |  |  |  |  | 8 | Model: 8 rigs active in the last two recorded weeks. Edit if rigs move to pipe piling earlier.
AER_ACT | Actual rate, last 4 full weeks (piles per rig per working day) |  |  |  |  | 5.4286 | Formula from the weekly table below.
AER_OVR | Override rate (blank = use actual) | [5 empty] | Optional.
AER_RATE | Rate used for the forecast |  |  |  |  | 5.4286
Recorded production by week (from execution dates on the pile objects)
Week from | Piles executed | Rigs active | Piles / rig / working day
2026-08-03 | 4 | 2 | 0.33333
2026-08-10 | 46 | 3 | 2.5556
2026-08-17 | 123 | 5 | 4.1
2026-08-24 | 210 | 7 | 5
2026-08-31 | 146 | 7 | 3.4762
2026-09-07 | 229 | 8 | 4.7708
2026-09-14 | 323 | 9 | 5.9815
2026-09-21 | 316 | 9 | 5.8519
2026-09-28 | 246 | 9 | 4.5556
2026-10-05 | 255 | 8 | 5.3125
2026-10-12 | 200 | 8 | 4.1667 | Week to data date (17 Oct) - may be partial; excluded from the rate.
Formulas:
Forecast zone piling complete = AER_DATA+ROUNDUP([Cumulative open piles in agreed order]/(AER_RIGS*AER_RATE)*7/WD,0)

## Structures
Structure readiness for pipe tie-ins
Yellow = enter the date each structure is ready for a pipe tie-in (wall and penetration built, its excavation backfilled to pipe zone). Blank = not constraining. The 3D model holds no construction progress for these structures (only aeration piles), so these dates must come from the master programme.
Code | Structure | In 3D model | Model stage (manifest 19 Oct 2026) | Open gaps (manifest) | Ready for tie-in (date) | Tie-in packages | Date used
AER | aeration tank | Yes | Structural reconstruction | Reconcile new CGD/calculation and held features |  | 3 | 0
CCT | chlorine contact tank | Yes | Civil Guide Rev01 coordination reconstruction | Guide structure; OP01/floor discrepancy; consultant comments and common datum / interfaces unverified |  | 8 | 0
FSTA | FST A | Yes | Typical structural instance | Tank-specific attachments, structural applicability and penetration ports |  | 3 | 0
FSTB | FST B | Yes | Typical structural instance | Tank-specific attachments, structural applicability and penetration ports |  | 3 | 0
FSTC | FST C | Yes | Typical structural instance | Tank-specific attachments, structural applicability and penetration ports |  | 3 | 0
FSTD | FST D | Yes | Typical structural instance | Tank-specific attachments, structural applicability and penetration ports |  | 3 | 0
FSTE | FST E | Yes | Typical structural instance | Tank-specific attachments, structural applicability and penetration ports |  | 3 | 0
FSTF | FST F | Yes | Typical structural instance | Tank-specific attachments, structural applicability and penetration ports |  | 3 | 0
FSTG | FST G | Yes | Typical structural instance | Tank-specific attachments, structural applicability and penetration ports |  | 3 | 0
FSTH | FST H | Yes | Typical structural instance | Tank-specific attachments, structural applicability and penetration ports |  | 3 | 0
FSTI | FST I | Yes | Typical structural instance | Tank-specific attachments, structural applicability and penetration ports |  | 3 | 0
FSTJ | FST J | Yes | Typical structural instance | Tank-specific attachments, structural applicability and penetration ports |  | 6 | 0
FSTK | FST K | Yes | Typical structural instance | Tank-specific attachments, structural applicability and penetration ports |  | 3 | 0
FSTL | FST L | Yes | Typical structural instance | Tank-specific attachments, structural applicability and penetration ports |  | 3 | 0
GRT | grit removal / fine screens | Yes | Civil Guide Rev01 coordination reconstruction | Guide structural/vendor details, comment closure and common datum; grit footprint discrepancy 0.894m |  | 1 | 0
IPS | IPS | Yes | CGD Rev01 civil envelope | Common vertical datum, final structural/vendor interfaces; shared hall grouped AW-IPS-SHARED |  | 6 | 0
PST | PST | Yes | Eight new basins CGD Rev01 | Current approval, guide structural details, outlet throat/baffle dimensions, layout outline differences, common datum and pipe interfaces |  | 1 | 0
PST08 | PST basin 08 | Yes | Eight new basins CGD Rev01 | Current approval, guide structural details, outlet throat/baffle dimensions, layout outline differences, common datum and pipe interfaces |  | 1 | 0
RASPS | RAS/WAS pumping station | Yes | CGD Rev01 civil envelope | Common vertical datum, final structural/vendor interfaces; shared hall grouped AW-IPS-SHARED |  | 2 | 0
SDCA | secondary distribution chamber A | Yes | CGD Rev02 envelope | CGD A centre/orientation discrepancy; baffle and hydraulic levels; common vertical datum and pipe interfaces; B stair difference |  | 5 | 0
SDCB | secondary distribution chamber B | Yes | CGD Rev02 envelope | CGD A centre/orientation discrepancy; baffle and hydraulic levels; common vertical datum and pipe interfaces; B stair difference |  | 5 | 0
SDCC | secondary distribution chamber C | Yes | CGD Rev02 envelope | CGD A centre/orientation discrepancy; baffle and hydraulic levels; common vertical datum and pipe interfaces; B stair difference |  | 6 | 0
WFT | fire & service water structure (AW-FIRE) | Yes | Civil Guide Rev00 coordination reconstruction | Revise and Resubmit; hydraulic/penstock/vendor/structural review comments remain open |  | 7 | 0
WPD | WAS pre-dewatering building | Yes |  |  |  | 1 | 0
BYPCH | overflow bypass chamber (not modelled) | No | Not in master - tie-in position not checked |  |  | 0 | 0
CHUG25 | chamber connecting UG-25 (not modelled) | No | Not in master - tie-in position not checked |  |  | 0 | 0
EXPST | existing PST (not modelled) | No | Not in master - tie-in position not checked |  |  | 0 | 0
OUTF | outfall chamber (not modelled) | No | Not in master - tie-in position not checked |  |  | 0 | 0
TEPS | treated effluent pump station (not modelled) | No | Not in master - tie-in position not checked |  |  | 0 | 0
Formulas:
Date used = IF([Ready for tie-in (date)]="",0,[Ready for tie-in (date)])

## Fronts
Work fronts and crews
Each front runs its run packages in the order on the Activities sheet (deeper lines first, downstream first). Crew numbers (yellow) divide the durations. Tie-in packages are outside the chains and assume a separate tie-in team when the structure is ready. Moving a line to another front needs a rebuild.
Front | Description | Lines | Packages | Length (m) | Piles (no.) | Shored length (m) | Piling rigs | Sheet pile gangs | Excavation gangs | Slab gangs | Pipe crews | Backfill gangs | Start | Finish | Duration (months)
F1 | Headworks & primary (GRT-PST-IPS) | UG-01, UG-02, UG-03, UG-04 | 15 | 800.3519 | 569 | 800.3519 | 1 | 1 | 1 | 1 | 1 | 1 | 2026-12-01 | 2027-06-24 | 6.7434
F2 | Bypass corridor: IPS bypass and outfall twin | UG-05, UG-06, UG-24, UG-25, UG-26 | 14 | 1724.1875 | 1196 | 1567.3564 | 2 | 2 | 2 | 2 | 2 | 2 | 2026-12-01 | 2027-07-22 | 7.6645
F3 | Distribution & FCT risers | UG-08, UG-09, UG-10, UG-11B, UG-13A, UG-13B, UG-14E, UG-14F, UG-16B, UG-27J, UG-27K, UG-27L | 30 | 1094.7783 | 800 | 648.7086 | 1 | 1 | 1 | 1 | 1 | 1 | 2026-12-01 | 2027-07-26 | 7.7961
F4 | FCT effluent A-H to CCT | UG-07, UG-07A, UG-15, UG-15A | 22 | 550.5855 | 436 | 308.432 | 1 | 1 | 1 | 1 | 1 | 1 | 2026-12-01 | 2027-08-22 | 8.6842
F5 | FCT effluent I-L to CCT | UG-07, UG-11, UG-11B, UG-12, UG-12A | 22 | 570.5608 | 452 | 254.1972 | 1 | 1 | 1 | 1 | 1 | 1 | 2026-12-01 | 2027-09-18 | 9.5724
F6 | Sludge A-D,G,H to RAS/WAS + UG-23 | UG-11, UG-11A, UG-11B, UG-14G, UG-14H, UG-16A, UG-16C, UG-16D, UG-23 | 34 | 1164.3496 | 765 | 839.9423 | 1 | 1 | 1 | 1 | 1 | 1 | 2026-12-01 | 2027-08-08 | 8.2237
F7 | Sludge I-L,E,F to RAS/WAS | UG-07A, UG-12, UG-13, UG-13A, UG-13B, UG-23, UG-27I | 38 | 868.0987 | 585 | 816.1554 | 1 | 1 | 1 | 1 | 1 | 1 | 2026-12-01 | 2027-08-07 | 8.1908
F8 | Effluent, outfall & CCT links | UG-11B, UG-15, UG-15A, UG-17, UG-18, UG-19, UG-20, UG-21, UG-22, UG-28, UG-28A | 26 | 1378.4556 | 985 | 1326.4495 | 2 | 2 | 2 | 2 | 2 | 2 | 2026-12-01 | 2027-07-04 | 7.0724
All | All fronts |  | 201 | 8151.3679 | 5788 | 6561.5933 | 10 | 10 | 10 | 10 | 10 | 10 | 2026-12-01 | 2027-09-18 | 9.5724
| Tie-in packages (separate team) |  | 71
Formulas:
Start = MINIFS(Packages!$AL6:AL400,Packages!$C6:C400,[Front])
Start = MIN(N5:[Start, row above])
Finish = MAXIFS(Packages!$AM6:AM400,Packages!$C6:C400,[Front])
Finish = MAX(O5:[Finish, row above])

## Piece check
Piece-level method check with groundwater at GWL
One row per piece from the package workbook (10 m cuts). Open cut only where the dewatered open-cut reach fits short of the nearest other structure or pile AND the excavation is no deeper than MAXOC below GWL; otherwise sheet piles. Black = formula, blue = source data.
Line | Package | Sub-piece | Plan length (m) | Planning OD (m) | Start R (m) | End R (m) | Start crown (m) | End crown (m) | Nearest other structure / pile (m) | R deepest (m) | R average (m) | Excavation depth from NG, avg (m) | Depth below GWL, deepest (m) | Depth NG to GWL used, deepest (m) | Open-cut reach from axis (m) | Method | Shored length (m) | Depth below GWL, avg (m) | Depth NG to GWL, avg (m) | Trench bottom width (m) | Excavation shored (m3) | Excavation open cut (m3) | Piled slab concrete (m3) | Pipe displacement below NG (m3) | Flotation FoS start, backfill to NG | Flotation FoS end, backfill to NG | Flotation FoS start, final to FL | Flotation FoS end, final to FL
UG-01 | UG-01-S01 | P0022-01 | 10 | 2.5864 | -5.3932 | -5.4023 | -2.3068 | -2.3159 | 99 | -5.4023 | -5.3977 | 4.6977 | 3.9023 | 0.8 | 11.2978 | Shoring | 10 | 3.8977 | 0.8 | 4.5864 | 215.4564 | 0 | 17.9319 | 52.5384 | 1.0542 | 1.0579 | 2.5898 | 2.5935
UG-01 | UG-01-S01 | P0022-02 | 1.0054 | 2.5864 | -5.4023 | -5.4032 | -2.3159 | -2.3168 | 99 | -5.4032 | -5.4027 | 4.7027 | 3.9032 | 0.8 | 11.2996 | Shoring | 1.0054 | 3.9027 | 0.8 | 4.5864 | 21.6842 | 0 | 1.8028 | 5.282 | 1.0579 | 1.0583 | 2.5935 | 2.5939
UG-01 | UG-01-S01 | P0428 | 3.9 | 2.5864 | -5.4032 | -5.4305 | -2.3168 | -2.3441 | 99 | -5.4305 | -5.4168 | 4.7168 | 3.9305 | 0.8 | 11.3542 | Shoring | 3.9 | 3.9168 | 0.8 | 4.5864 | 84.3699 | 0 | 6.9935 | 20.49 | 1.0583 | 1.0695 | 2.5939 | 2.6051
UG-01 | UG-01-S01 | P0429 | 3.8998 | 2.556 | -5.4153 | -5.4426 | -2.3593 | -2.3866 | 99 | -5.4426 | -5.429 | 4.729 | 3.9426 | 0.8 | 11.3632 | Shoring | 3.8998 | 3.929 | 0.8 | 4.556 | 84.0217 | 0 | 6.9338 | 20.0103 | 1.0886 | 1.0999 | 2.6424 | 2.6538
UG-01 | UG-01-S02 | P0284-01 | 1.1948 | 2.556 | -5.4426 | -5.451 | -2.3866 | -2.395 | 12.83 | -5.451 | -5.4468 | 4.7468 | 3.951 | 0.8 | 11.38 | Shoring | 1.1948 | 3.9468 | 0.8 | 4.556 | 25.84 | 0 | 2.1244 | 6.1308 | 1.0999 | 1.1034 | 2.6538 | 2.6572
UG-01 | UG-01-S02 | P0284-02 | 10 | 2.556 | -5.451 | -5.521 | -2.395 | -2.465 | 12.83 | -5.521 | -5.486 | 4.786 | 4.021 | 0.8 | 11.52 | Shoring | 10 | 3.986 | 0.8 | 4.556 | 218.0495 | 0 | 17.78 | 51.3111 | 1.1034 | 1.1325 | 2.6572 | 2.6864
UG-01 | UG-01-S02 | P0284-03 | 10 | 2.556 | -5.521 | -5.591 | -2.465 | -2.535 | 12.84 | -5.591 | -5.556 | 4.856 | 4.091 | 0.8 | 11.66 | Shoring | 10 | 4.056 | 0.8 | 4.556 | 221.2396 | 0 | 17.78 | 51.3111 | 1.1325 | 1.1617 | 2.6864 | 2.7155
UG-01 | UG-01-S02 | P0284-04 | 10 | 2.556 | -5.591 | -5.661 | -2.535 | -2.605 | 13.01 | -5.661 | -5.626 | 4.926 | 4.161 | 0.8 | 11.8001 | Shoring | 10 | 4.126 | 0.8 | 4.556 | 224.4297 | 0 | 17.78 | 51.3111 | 1.1617 | 1.1908 | 2.7155 | 2.7446
UG-01 | UG-01-S02 | P0284-05 | 10 | 2.556 | -5.661 | -5.7311 | -2.605 | -2.6751 | 17.64 | -5.7311 | -5.696 | 4.996 | 4.2311 | 0.8 | 11.9401 | Shoring | 10 | 4.196 | 0.8 | 4.556 | 227.6198 | 0 | 17.78 | 51.3111 | 1.1908 | 1.2199 | 2.7446 | 2.7737
UG-01 | UG-01-S02 | P0284-06 | 10 | 2.556 | -5.7311 | -5.8011 | -2.6751 | -2.7451 | 24.9 | -5.8011 | -5.7661 | 5.0661 | 4.3011 | 0.8 | 12.0802 | Shoring | 10 | 4.2661 | 0.8 | 4.556 | 230.8099 | 0 | 17.78 | 51.3111 | 1.2199 | 1.249 | 2.7737 | 2.8028
UG-01 | UG-01-S02 | P0284-07 | 10 | 2.556 | -5.8011 | -5.8711 | -2.7451 | -2.8151 | 99 | -5.8711 | -5.8361 | 5.1361 | 4.3711 | 0.8 | 12.2202 | Shoring | 10 | 4.3361 | 0.8 | 4.556 | 234 | 0 | 17.78 | 51.3111 | 1.249 | 1.2781 | 2.8028 | 2.832
UG-01 | UG-01-S02 | P0284-08 | 10 | 2.556 | -5.8711 | -5.9411 | -2.8151 | -2.8851 | 99 | -5.9411 | -5.9061 | 5.2061 | 4.4411 | 0.8 | 12.3602 | Shoring | 10 | 4.4061 | 0.8 | 4.556 | 237.1901 | 0 | 17.78 | 51.3111 | 1.2781 | 1.3072 | 2.832 | 2.8611
UG-01 | UG-01-S02 | P0284-09 | 10 | 2.556 | -5.9411 | -6.0111 | -2.8851 | -2.9551 | 99 | -6.0111 | -5.9761 | 5.2761 | 4.5111 | 0.8 | 12.5003 | Shoring | 10 | 4.4761 | 0.8 | 4.556 | 240.3802 | 0 | 17.78 | 51.3111 | 1.3072 | 1.3364 | 2.8611 | 2.8902
UG-01 | UG-01-S02 | P0284-10 | 10 | 2.556 | -6.0111 | -6.0812 | -2.9551 | -3.0252 | 99 | -6.0812 | -6.0461 | 5.3461 | 4.5812 | 0.8 | 12.6403 | Shoring | 10 | 4.5461 | 0.8 | 4.556 | 243.5703 | 0 | 17.78 | 51.3111 | 1.3364 | 1.3655 | 2.8902 | 2.9193
UG-01 | UG-01-S02 | P0284-11 | 10 | 2.556 | -6.0812 | -6.1512 | -3.0252 | -3.0952 | 99 | -6.1512 | -6.1162 | 5.4162 | 4.6512 | 0.8 | 12.7804 | Shoring | 10 | 4.6162 | 0.8 | 4.556 | 246.7604 | 0 | 17.78 | 51.3111 | 1.3655 | 1.3946 | 2.9193 | 2.9484
UG-01 | UG-01-S02 | P0284-12 | 1.463 | 2.556 | -6.1512 | -6.1614 | -3.0952 | -3.1054 | 99 | -6.1614 | -6.1563 | 5.4563 | 4.6614 | 0.8 | 12.8008 | Shoring | 1.463 | 4.6563 | 0.8 | 4.556 | 36.3686 | 0 | 2.6012 | 7.5068 | 1.3946 | 1.3989 | 2.9484 | 2.9527
UG-01 | UG-01-S02 | P0427 | 3.7496 | 2.556 | -6.1614 | -6.1877 | -3.1054 | -3.1317 | 99 | -6.1877 | -6.1745 | 5.4745 | 4.6877 | 0.8 | 12.8533 | Shoring | 3.7496 | 4.6745 | 0.8 | 4.556 | 93.5227 | 0 | 6.6668 | 19.2396 | 1.3989 | 1.4098 | 2.9527 | 2.9636
UG-01 | UG-01-S02 | P0426 | 3.7503 | 2.5864 | -6.2029 | -6.2291 | -3.1165 | -3.1427 | 99 | -6.2291 | -6.216 | 5.516 | 4.7291 | 0.8 | 12.9515 | Shoring | 3.7503 | 4.716 | 0.8 | 4.5864 | 94.8772 | 0 | 6.725 | 19.7036 | 1.387 | 1.3978 | 2.9225 | 2.9333
UG-01 | UG-01-S02 | P0023-01 | 1.0371 | 2.5864 | -6.2291 | -6.2364 | -3.1427 | -3.15 | 99 | -6.2364 | -6.2328 | 5.5328 | 4.7364 | 0.8 | 12.966 | Shoring | 1.0371 | 4.7328 | 0.8 | 4.5864 | 26.3167 | 0 | 1.8597 | 5.4488 | 1.3978 | 1.4007 | 2.9333 | 2.9363
UG-01 | UG-01-S02 | P0023-02 | 0.51724 | 2.5864 | -6.2364 | -6.24 | -3.15 | -3.1536 | 99 | -6.24 | -6.2382 | 5.5382 | 4.74 | 0.8 | 12.9732 | Shoring | 0.51724 | 4.7382 | 0.8 | 4.5864 | 13.1381 | 0 | 0.92751 | 2.7175 | 1.4007 | 1.4022 | 2.9363 | 2.9378
UG-01 | UG-01-S02 | P0004 | 3.75 | 2.555 | -6.2243 | -6.2506 | -3.1693 | -3.1956 | 99 | -6.2506 | -6.2374 | 5.5374 | 4.7506 | 0.8 | 12.9786 | Shoring | 3.75 | 4.7374 | 0.8 | 4.555 | 94.5862 | 0 | 6.6656 | 19.2265 | 1.426 | 1.4369 | 2.9804 | 2.9914
UG-01 | UG-01-S02 | P0005 | 3.75 | 2.555 | -6.2506 | -6.2768 | -3.1956 | -3.2218 | 99 | -6.2768 | -6.2637 | 5.5637 | 4.7768 | 0.8 | 13.0311 | Shoring | 3.75 | 4.7637 | 0.8 | 4.555 | 95.0348 | 0 | 6.6656 | 19.2265 | 1.4369 | 1.4479 | 2.9914 | 3.0023
UG-01 | UG-01-S02 | P0001-01 | 1.9828 | 2.5864 | -6.2925 | -6.3064 | -3.2061 | -3.22 | 99 | -6.3064 | -6.2995 | 5.5995 | 4.8064 | 0.8 | 13.106 | Shoring | 1.9828 | 4.7995 | 0.8 | 4.5864 | 50.9199 | 0 | 3.5555 | 10.4171 | 1.4238 | 1.4295 | 2.9594 | 2.9651
UG-01 | UG-01-S02 | P0001-02 | 10 | 2.5864 | -6.3064 | -6.3764 | -3.22 | -3.29 | 99 | -6.3764 | -6.3414 | 5.6414 | 4.8764 | 0.8 | 13.2461 | Shoring | 10 | 4.8414 | 0.8 | 4.5864 | 258.7375 | 0 | 17.932 | 52.5386 | 1.4295 | 1.4583 | 2.9651 | 2.9939
UG-01 | UG-01-S02 | P0001-03 | 10 | 2.5864 | -6.3764 | -6.4464 | -3.29 | -3.3601 | 27.62 | -6.4464 | -6.4114 | 5.7114 | 4.9464 | 0.8 | 13.3861 | Shoring | 10 | 4.9114 | 0.8 | 4.5864 | 261.9489 | 0 | 17.932 | 52.5386 | 1.4583 | 1.4871 | 2.9939 | 3.0226
UG-01 | UG-01-S02 | P0001-04 | 8.1045 | 2.5864 | -6.4464 | -6.5032 | -3.3601 | -3.4168 | 20.24 | -6.5032 | -6.4748 | 5.7748 | 5.0032 | 0.8 | 13.4996 | Shoring | 8.1045 | 4.9748 | 0.8 | 4.5864 | 214.653 | 0 | 14.533 | 42.58 | 1.4871 | 1.5104 | 3.0226 | 3.046
UG-01 | UG-01-S02 | P0006-01 | 1.8955 | 2.555 | -6.4875 | -6.4875 | -3.4325 | -3.4325 | 18.6 | -6.4875 | -6.4875 | 5.7875 | 4.9875 | 0.8 | 13.4525 | Shoring | 1.8955 | 4.9875 | 0.8 | 4.555 | 49.9687 | 0 | 3.3692 | 9.7183 | 1.5355 | 1.5355 | 3.0899 | 3.0899
UG-01 | UG-01-S02 | P0006-02 | 1.8545 | 2.555 | -6.4875 | -6.4875 | -3.4325 | -3.4325 | 17.05 | -6.4875 | -6.4875 | 5.7875 | 4.9875 | 0.8 | 13.4525 | Shoring | 1.8545 | 4.9875 | 0.8 | 4.555 | 48.8889 | 0 | 3.2964 | 9.5083 | 1.5355 | 1.5355 | 3.0899 | 3.0899
UG-01 | UG-01-S02 | P0007 | 3.75 | 2.555 | -6.4875 | -6.4875 | -3.4325 | -3.4325 | 16.79 | -6.4875 | -6.4875 | 5.7875 | 4.9875 | 0.8 | 13.4525 | Shoring | 3.75 | 4.9875 | 0.8 | 4.555 | 98.8574 | 0 | 6.6656 | 19.2265 | 1.5355 | 1.5355 | 3.0899 | 3.0899
UG-01 | UG-01-S02 | P0002-01 | 4.3955 | 2.5864 | -6.5032 | -6.5032 | -3.4168 | -3.4168 | 16.81 | -6.5032 | -6.5032 | 5.8032 | 5.0032 | 0.8 | 13.4996 | Shoring | 4.3955 | 5.0032 | 0.8 | 4.5864 | 116.9892 | 0 | 7.882 | 23.0934 | 1.5104 | 1.5104 | 3.046 | 3.046
UG-01 | UG-01-S02 | P0002-02 | 1.2987 | 2.5864 | -6.5032 | -6.5032 | -3.4168 | -3.4168 | 17.56 | -6.5032 | -6.5032 | 5.8032 | 5.0032 | 0.8 | 13.4996 | Shoring | 1.2987 | 5.0032 | 0.8 | 4.5864 | 34.5658 | 0 | 2.3288 | 6.8232 | 1.5104 | 1.5104 | 3.046 | 3.046
UG-01 | UG-01-S02 | P0008 | 3.75 | 2.555 | -6.4875 | -6.4875 | -3.4325 | -3.4325 | 17.99 | -6.4875 | -6.4875 | 5.7875 | 4.9875 | 0.8 | 13.4525 | Shoring | 3.75 | 4.9875 | 0.8 | 4.555 | 98.8578 | 0 | 6.6656 | 19.2266 | 1.5355 | 1.5355 | 3.0899 | 3.0899
UG-01 | UG-01-S02 | P0009 | 3.75 | 2.555 | -6.4875 | -6.4875 | -3.4325 | -3.4325 | 19.11 | -6.4875 | -6.4875 | 5.7875 | 4.9875 | 0.8 | 13.4525 | Shoring | 3.75 | 4.9875 | 0.8 | 4.555 | 98.8577 | 0 | 6.6656 | 19.2266 | 1.5355 | 1.5355 | 3.0899 | 3.0899
UG-01 | UG-01-S02 | P0003-01 | 1.2013 | 2.5864 | -6.5032 | -6.5049 | -3.4168 | -3.4185 | 19.09 | -6.5049 | -6.504 | 5.804 | 5.0049 | 0.8 | 13.5029 | Shoring | 1.2013 | 5.004 | 0.8 | 4.5864 | 31.9782 | 0 | 2.1542 | 6.3115 | 1.5104 | 1.5111 | 3.046 | 3.0467
UG-01 | UG-01-S02 | P0003-02 | 10 | 2.5864 | -6.5049 | -6.5187 | -3.4185 | -3.4323 | 13.3 | -6.5187 | -6.5118 | 5.8118 | 5.0187 | 0.8 | 13.5305 | Shoring | 10 | 5.0118 | 0.8 | 4.5864 | 266.5499 | 0 | 17.932 | 52.5386 | 1.5111 | 1.5168 | 3.0467 | 3.0523
UG-01 | UG-01-S02 | P0003-03 | 10 | 2.5864 | -6.5187 | -6.5325 | -3.4323 | -3.4461 | 10.38 | -6.5325 | -6.5256 | 5.8256 | 5.0325 | 0.8 | 13.5581 | Shoring | 10 | 5.0256 | 0.8 | 4.5864 | 267.1831 | 0 | 17.932 | 52.5386 | 1.5168 | 1.5224 | 3.0523 | 3.058
UG-01 | UG-01-S02 | P0003-04 | 10 | 2.5864 | -6.5325 | -6.5463 | -3.4461 | -3.4599 | 10.09 | -6.5463 | -6.5394 | 5.8394 | 5.0463 | 0.8 | 13.5857 | Shoring | 10 | 5.0394 | 0.8 | 4.5864 | 267.8163 | 0 | 17.932 | 52.5386 | 1.5224 | 1.5281 | 3.058 | 3.0637
UG-01 | UG-01-S02 | P0003-05 | 10 | 2.5864 | -6.5463 | -6.5601 | -3.4599 | -3.4737 | 10.62 | -6.5601 | -6.5532 | 5.8532 | 5.0601 | 0.8 | 13.6134 | Shoring | 10 | 5.0532 | 0.8 | 4.5864 | 268.4495 | 0 | 17.932 | 52.5386 | 1.5281 | 1.5338 | 3.0637 | 3.0694
UG-01 | UG-01-S02 | P0003-06 | 2.0034 | 2.5864 | -6.5601 | -6.5628 | -3.4737 | -3.4765 | 16.71 | -6.5628 | -6.5615 | 5.8615 | 5.0628 | 0.8 | 13.6189 | Shoring | 2.0034 | 5.0615 | 0.8 | 4.5864 | 53.8583 | 0 | 3.5926 | 10.5258 | 1.5338 | 1.5349 | 3.0694 | 3.0705
UG-01 | UG-01-S02 | P0407 | 3.7509 | 2.5864 | -6.5628 | -6.568 | -3.4765 | -3.4816 | 18.34 | -6.568 | -6.5654 | 5.8654 | 5.068 | 0.8 | 13.6292 | Shoring | 3.7509 | 5.0654 | 0.8 | 4.5864 | 100.903 | 0 | 6.7261 | 19.7066 | 1.5349 | 1.537 | 3.0705 | 3.0726
UG-01 | UG-01-S02 | P0408 | 3.7488 | 2.5864 | -6.568 | -6.5732 | -3.4816 | -3.4868 | 21.57 | -6.5732 | -6.5706 | 5.8706 | 5.0732 | 0.8 | 13.6396 | Shoring | 3.7488 | 5.0706 | 0.8 | 4.5864 | 100.9351 | 0 | 6.7223 | 19.6956 | 1.537 | 1.5392 | 3.0726 | 3.0747
UG-01 | UG-01-S02 | P0285-01 | 0.49693 | 2.5864 | -6.5732 | -6.5816 | -3.4868 | -3.4952 | 22.96 | -6.5816 | -6.5774 | 5.8774 | 5.0816 | 0.8 | 13.6564 | Shoring | 0.49693 | 5.0774 | 0.8 | 4.5864 | 13.3954 | 0 | 0.8911 | 2.6108 | 1.5392 | 1.5426 | 3.0747 | 3.0782
UG-01 | UG-01-S02 | P0285-02 | 10 | 2.5864 | -6.5816 | -6.7507 | -3.4952 | -3.6643 | 23.18 | -6.7507 | -6.6661 | 5.9661 | 5.2507 | 0.8 | 13.9945 | Shoring | 10 | 5.1661 | 0.8 | 4.5864 | 273.6308 | 0 | 17.932 | 52.5391 | 1.5426 | 1.6121 | 3.0782 | 3.1477
UG-01 | UG-01-S02 | P0285-03 | 10 | 2.5864 | -6.7507 | -6.9197 | -3.6643 | -3.8333 | 29.11 | -6.9197 | -6.8352 | 6.1352 | 5.4197 | 0.8 | 14.3326 | Shoring | 10 | 5.3352 | 0.8 | 4.5864 | 281.3843 | 0 | 17.932 | 52.5391 | 1.6121 | 1.6816 | 3.1477 | 3.2171
UG-01 | UG-01-S02 | P0285-04 | 10 | 2.5864 | -6.9197 | -7.0888 | -3.8333 | -4.0024 | 35.86 | -7.0888 | -7.0042 | 6.3042 | 5.5888 | 0.8 | 14.6707 | Shoring | 10 | 5.5042 | 0.8 | 4.5864 | 289.1377 | 0 | 17.932 | 52.5391 | 1.6816 | 1.7511 | 3.2171 | 3.2866
UG-01 | UG-01-S02 | P0285-05 | 10 | 2.5864 | -7.0888 | -7.2578 | -4.0024 | -4.1714 | 99 | -7.2578 | -7.1733 | 6.4733 | 5.7578 | 0.8 | 15.0088 | Shoring | 10 | 5.6733 | 0.8 | 4.5864 | 296.8912 | 0 | 17.932 | 52.5391 | 1.7511 | 1.8205 | 3.2866 | 3.3561
UG-01 | UG-01-S02 | P0285-06 | 6.7196 | 2.5864 | -7.2578 | -7.3714 | -4.1714 | -4.285 | 39.3 | -7.3714 | -7.3146 | 6.6146 | 5.8714 | 0.8 | 15.236 | Shoring | 6.7196 | 5.8146 | 0.8 | 4.5864 | 203.8538 | 0 | 12.0496 | 35.3041 | 1.8205 | 1.8672 | 3.3561 | 3.4028
UG-01 | UG-01-S02 | P0728-01 | 3.2804 | 2.5864 | -7.3714 | -7.4269 | -4.285 | -4.3405 | 36.89 | -7.4269 | -7.3991 | 6.6991 | 5.9269 | 0.8 | 15.3469 | Shoring | 3.2804 | 5.8991 | 0.8 | 4.5864 | 100.7909 | 0 | 5.8825 | 17.235 | 1.8672 | 1.89 | 3.4028 | 3.4256
UG-01 | UG-01-S02 | P0728-02 | 0.61829 | 2.5864 | -7.4269 | -7.4373 | -4.3405 | -4.3509 | 36.44 | -7.4373 | -7.4321 | 6.7321 | 5.9373 | 0.8 | 15.3678 | Shoring | 0.61829 | 5.9321 | 0.8 | 4.5864 | 19.0903 | 0 | 1.1087 | 3.2484 | 1.89 | 1.8943 | 3.4256 | 3.4299
UG-01 | UG-01-S02 | P0727 | 3.897 | 0.61306 | -6.4507 | -6.5165 | -5.3376 | -5.4035 | 31.8 | -6.5165 | -6.4836 | 5.7836 | 5.0165 | 0.8 | 12.5396 | Shoring | 3.897 | 4.9836 | 0.8 | 2.6131 | 58.8954 | 0 | 3.1431 | 1.1504 | 9.7025 | 9.8167 | 16.1807 | 16.2949
UG-01 | UG-01-S02 | P0726 | 0.35042 | 0.61306 | -6.5165 | -6.5165 | -5.4035 | -5.4035 | 31.38 | -6.5165 | -6.5165 | 5.8165 | 5.0165 | 0.8 | 12.5396 | Shoring | 0.35042 | 5.0165 | 0.8 | 2.6131 | 5.326 | 0 | 0.28262 | 0.10344 | 9.8167 | 9.8167 | 16.2949 | 16.2949
UG-01 | UG-01-S03 | P0175-01 | 5.1343 | 0.61306 | -6.5165 | -6.5165 | -5.4035 | -5.4035 | 99 | -6.5165 | -6.5165 | 5.8165 | 5.0165 | 0.8 | 12.5396 | Shoring | 5.1343 | 5.0165 | 0.8 | 2.6131 | 78.0356 | 0 | 4.141 | 1.5156 | 9.8167 | 9.8167 | 16.2949 | 16.2949
UG-01 | UG-01-S03 | P0175-02 | 10 | 0.61306 | -6.5165 | -6.5165 | -5.4035 | -5.4035 | 99 | -6.5165 | -6.5165 | 5.8165 | 5.0165 | 0.8 | 12.5396 | Shoring | 10 | 5.0165 | 0.8 | 2.6131 | 151.9897 | 0 | 8.0653 | 2.9519 | 9.8167 | 9.8167 | 16.2949 | 16.2949
UG-01 | UG-01-S03 | P0175-03 | 10 | 0.61306 | -6.5165 | -6.5165 | -5.4035 | -5.4035 | 99 | -6.5165 | -6.5165 | 5.8165 | 5.0165 | 0.8 | 12.5396 | Shoring | 10 | 5.0165 | 0.8 | 2.6131 | 151.9897 | 0 | 8.0653 | 2.9519 | 9.8167 | 9.8167 | 16.2949 | 16.2949
UG-01 | UG-01-S03 | P0175-04 | 4.2759 | 0.61306 | -6.5165 | -6.5165 | -5.4035 | -5.4035 | 99 | -6.5165 | -6.5165 | 5.8165 | 5.0165 | 0.8 | 12.5396 | Shoring | 4.2759 | 5.0165 | 0.8 | 2.6131 | 64.9893 | 0 | 3.4487 | 1.2622 | 9.8167 | 9.8167 | 16.2949 | 16.2949
UG-02 | UG-02-S01 | P0132 | 4.5179 | 1.5518 | -5.0959 | -5.0959 | -3.0441 | -3.0441 | 21.39 | -5.0959 | -5.0959 | 4.3959 | 3.5959 | 0.8 | 10.1677 | Shoring | 4.5179 | 3.5959 | 0.8 | 3.5518 | 70.5395 | 0 | 5.7644 | 8.5447 | 2.2621 | 2.2621 | 4.8214 | 4.8214
UG-02 | UG-02-S01 | P0131 | 0.75 | 2.0412 | -5.3406 | -5.3406 | -2.7994 | -2.7994 | 20.66 | -5.3406 | -5.3406 | 4.6406 | 3.8406 | 0.8 | 10.9018 | Shoring | 0.75 | 3.8406 | 0.8 | 4.0412 | 14.0652 | 0 | 1.1404 | 2.4543 | 1.5923 | 1.5923 | 3.538 | 3.538
UG-02 | UG-02-S01 | P0130 | 3.7841 | 2.0696 | -5.3548 | -5.3548 | -2.7852 | -2.7852 | 16.99 | -5.3548 | -5.3548 | 4.6548 | 3.8548 | 0.8 | 10.9444 | Shoring | 3.7841 | 3.8548 | 0.8 | 4.0696 | 71.6834 | 0 | 5.8079 | 12.73 | 1.5632 | 1.5632 | 3.4822 | 3.4822
UG-02 | UG-02-S01 | P0486-01 | 0.94798 | 2.0696 | -5.3548 | -5.36 | -2.7852 | -2.7904 | 16.08 | -5.36 | -5.3574 | 4.6574 | 3.86 | 0.8 | 10.9549 | Shoring | 0.94798 | 3.8574 | 0.8 | 4.0696 | 17.9679 | 0 | 1.455 | 3.1891 | 1.5632 | 1.5659 | 3.4822 | 3.4849
UG-02 | UG-02-S01 | P0486-02 | 1.0525 | 2.0696 | -5.36 | -5.3658 | -2.7904 | -2.7963 | 15.08 | -5.3658 | -5.3629 | 4.6629 | 3.8658 | 0.8 | 10.9665 | Shoring | 1.0525 | 3.8629 | 0.8 | 4.0696 | 19.9729 | 0 | 1.6154 | 3.5407 | 1.5659 | 1.5688 | 3.4849 | 3.4878
UG-02 | UG-02-S01 | P0487 | 2 | 2.0696 | -5.3659 | -5.3769 | -2.7962 | -2.8073 | 14.59 | -5.3769 | -5.3714 | 4.6714 | 3.8769 | 0.8 | 10.9886 | Shoring | 2 | 3.8714 | 0.8 | 4.0696 | 38.0209 | 0 | 3.0696 | 6.7281 | 1.5688 | 1.5745 | 3.4878 | 3.4935
UG-02 | UG-02-S02 | P0282-01 | 6.9475 | 2.0696 | -5.3769 | -5.4153 | -2.8073 | -2.8457 | 14.31 | -5.4153 | -5.3961 | 4.6961 | 3.9153 | 0.8 | 11.0654 | Shoring | 6.9475 | 3.8961 | 0.8 | 4.0696 | 132.7757 | 0 | 10.6631 | 23.372 | 1.5745 | 1.5942 | 3.4935 | 3.5132
UG-02 | UG-02-S02 | P0282-02 | 10 | 2.0696 | -5.4153 | -5.4705 | -2.8457 | -2.9009 | 11.17 | -5.4705 | -5.4429 | 4.7429 | 3.9705 | 0.8 | 11.1759 | Shoring | 10 | 3.9429 | 0.8 | 4.0696 | 193.018 | 0 | 15.348 | 33.6408 | 1.5942 | 1.6226 | 3.5132 | 3.5416
UG-02 | UG-02-S02 | P0282-03 | 10 | 2.0696 | -5.4705 | -5.5258 | -2.9009 | -2.9562 | 11.29 | -5.5258 | -5.4982 | 4.7982 | 4.0258 | 0.8 | 11.2864 | Shoring | 10 | 3.9982 | 0.8 | 4.0696 | 195.2664 | 0 | 15.348 | 33.6408 | 1.6226 | 1.651 | 3.5416 | 3.57
UG-02 | UG-02-S02 | P0282-04 | 10 | 2.0696 | -5.5258 | -5.581 | -2.9562 | -3.0114 | 11.42 | -5.581 | -5.5534 | 4.8534 | 4.081 | 0.8 | 11.3969 | Shoring | 10 | 4.0534 | 0.8 | 4.0696 | 197.5147 | 0 | 15.348 | 33.6408 | 1.651 | 1.6793 | 3.57 | 3.5983
UG-02 | UG-02-S02 | P0282-05 | 10 | 2.0696 | -5.581 | -5.6363 | -3.0114 | -3.0667 | 11.54 | -5.6363 | -5.6087 | 4.9087 | 4.1363 | 0.8 | 11.5074 | Shoring | 10 | 4.1087 | 0.8 | 4.0696 | 199.7631 | 0 | 15.348 | 33.6408 | 1.6793 | 1.7077 | 3.5983 | 3.6267
UG-02 | UG-02-S02 | P0282-06 | 10 | 2.0696 | -5.6363 | -5.6915 | -3.0667 | -3.1219 | 11.66 | -5.6915 | -5.6639 | 4.9639 | 4.1915 | 0.8 | 11.6179 | Shoring | 10 | 4.1639 | 0.8 | 4.0696 | 202.0115 | 0 | 15.348 | 33.6408 | 1.7077 | 1.7361 | 3.6267 | 3.6551
UG-02 | UG-02-S02 | P0282-07 | 10 | 2.0696 | -5.6915 | -5.7468 | -3.1219 | -3.1772 | 11.79 | -5.7468 | -5.7192 | 5.0192 | 4.2468 | 0.8 | 11.7284 | Shoring | 10 | 4.2192 | 0.8 | 4.0696 | 204.2598 | 0 | 15.348 | 33.6408 | 1.7361 | 1.7645 | 3.6551 | 3.6835
UG-02 | UG-02-S02 | P0282-08 | 10 | 2.0696 | -5.7468 | -5.802 | -3.1772 | -3.2324 | 11.91 | -5.802 | -5.7744 | 5.0744 | 4.302 | 0.8 | 11.8388 | Shoring | 10 | 4.2744 | 0.8 | 4.0696 | 206.5082 | 0 | 15.348 | 33.6408 | 1.7645 | 1.7928 | 3.6835 | 3.7118
UG-02 | UG-02-S02 | P0282-09 | 1.1 | 2.0696 | -5.802 | -5.8081 | -3.2324 | -3.2385 | 12.04 | -5.8081 | -5.8051 | 5.1051 | 4.3081 | 0.8 | 11.851 | Shoring | 1.1 | 4.3051 | 0.8 | 4.0696 | 22.8532 | 0 | 1.6883 | 3.7005 | 1.7928 | 1.796 | 3.7118 | 3.715
UG-02 | UG-02-S03 | P0282-10 | 8.9 | 2.0696 | -5.8081 | -5.8573 | -3.2385 | -3.2877 | 11.97 | -5.8573 | -5.8327 | 5.1327 | 4.3573 | 0.8 | 11.9493 | Shoring | 8.9 | 4.3327 | 0.8 | 4.0696 | 185.9034 | 0 | 13.6598 | 29.9403 | 1.796 | 1.8212 | 3.715 | 3.7402
UG-02 | UG-02-S03 | P0282-11 | 10 | 2.0696 | -5.8573 | -5.9125 | -3.2877 | -3.3429 | 11.9 | -5.9125 | -5.8849 | 5.1849 | 4.4125 | 0.8 | 12.0598 | Shoring | 10 | 4.3849 | 0.8 | 4.0696 | 211.0049 | 0 | 15.348 | 33.6408 | 1.8212 | 1.8496 | 3.7402 | 3.7686
UG-02 | UG-02-S03 | P0282-12 | 10 | 2.0696 | -5.9125 | -5.9678 | -3.3429 | -3.3982 | 11.82 | -5.9678 | -5.9401 | 5.2401 | 4.4678 | 0.8 | 12.1703 | Shoring | 10 | 4.4401 | 0.8 | 4.0696 | 213.2533 | 0 | 15.348 | 33.6408 | 1.8496 | 1.878 | 3.7686 | 3.797
UG-02 | UG-02-S03 | P0282-13 | 10 | 2.0696 | -5.9678 | -6.023 | -3.3982 | -3.4534 | 10.75 | -6.023 | -5.9954 | 5.2954 | 4.523 | 0.8 | 12.2808 | Shoring | 10 | 4.4954 | 0.8 | 4.0696 | 215.5017 | 0 | 15.348 | 33.6408 | 1.878 | 1.9064 | 3.797 | 3.8253
UG-02 | UG-02-S03 | P0282-14 | 10 | 2.0696 | -6.023 | -6.0783 | -3.4534 | -3.5087 | 10.68 | -6.0783 | -6.0506 | 5.3506 | 4.5783 | 0.8 | 12.3913 | Shoring | 10 | 4.5506 | 0.8 | 4.0696 | 217.75 | 0 | 15.348 | 33.6408 | 1.9064 | 1.9347 | 3.8253 | 3.8537
UG-02 | UG-02-S03 | P0282-15 | 10 | 2.0696 | -6.0783 | -6.1335 | -3.5087 | -3.5639 | 10.6 | -6.1335 | -6.1059 | 5.4059 | 4.6335 | 0.8 | 12.5018 | Shoring | 10 | 4.6059 | 0.8 | 4.0696 | 219.9984 | 0 | 15.348 | 33.6408 | 1.9347 | 1.9631 | 3.8537 | 3.8821
UG-02 | UG-02-S03 | P0282-16 | 6.2 | 2.0696 | -6.1335 | -6.1678 | -3.5639 | -3.5982 | 10.56 | -6.1678 | -6.1506 | 5.4506 | 4.6678 | 0.8 | 12.5703 | Shoring | 6.2 | 4.6506 | 0.8 | 4.0696 | 137.5281 | 0 | 9.5158 | 20.8573 | 1.9631 | 1.9807 | 3.8821 | 3.8997
UG-02 | UG-02-S04 | P0282-17 | 3.8 | 2.0696 | -6.1678 | -6.1888 | -3.5982 | -3.6191 | 10.53 | -6.1888 | -6.1783 | 5.4783 | 4.6888 | 0.8 | 12.6123 | Shoring | 3.8 | 4.6783 | 0.8 | 4.0696 | 84.7186 | 0 | 5.8323 | 12.7835 | 1.9807 | 1.9915 | 3.8997 | 3.9105
UG-02 | UG-02-S04 | P0282-18 | 10 | 2.0696 | -6.1888 | -6.244 | -3.6191 | -3.6744 | 10.45 | -6.244 | -6.2164 | 5.5164 | 4.744 | 0.8 | 12.7228 | Shoring | 10 | 4.7164 | 0.8 | 4.0696 | 224.4951 | 0 | 15.348 | 33.6408 | 1.9915 | 2.0199 | 3.9105 | 3.9389
UG-02 | UG-02-S04 | P0282-19 | 10 | 2.0696 | -6.244 | -6.2993 | -3.6744 | -3.7296 | 10.3 | -6.2993 | -6.2716 | 5.5716 | 4.7993 | 0.8 | 12.8333 | Shoring | 10 | 4.7716 | 0.8 | 4.0696 | 226.7435 | 0 | 15.348 | 33.6408 | 2.0199 | 2.0482 | 3.9389 | 3.9672
UG-02 | UG-02-S04 | P0282-20 | 10 | 2.0696 | -6.2993 | -6.3545 | -3.7296 | -3.7849 | 9.31 | -6.3545 | -6.3269 | 5.6269 | 4.8545 | 0.8 | 12.9438 | Shoring | 10 | 4.8269 | 0.8 | 4.0696 | 228.9919 | 0 | 15.348 | 33.6408 | 2.0482 | 2.0766 | 3.9672 | 3.9956
UG-02 | UG-02-S04 | P0282-21 | 10 | 2.0696 | -6.3545 | -6.4097 | -3.7849 | -3.8401 | 9.23 | -6.4097 | -6.3821 | 5.6821 | 4.9097 | 0.8 | 13.0543 | Shoring | 10 | 4.8821 | 0.8 | 4.0696 | 231.2402 | 0 | 15.348 | 33.6408 | 2.0766 | 2.105 | 3.9956 | 4.024
UG-02 | UG-02-S04 | P0282-22 | 10 | 2.0696 | -6.4097 | -6.465 | -3.8401 | -3.8954 | 9.16 | -6.465 | -6.4374 | 5.7374 | 4.965 | 0.8 | 13.1648 | Shoring | 10 | 4.9374 | 0.8 | 4.0696 | 233.4886 | 0 | 15.348 | 33.6408 | 2.105 | 2.1334 | 4.024 | 4.0524
UG-02 | UG-02-S04 | P0282-23 | 10 | 2.0696 | -6.465 | -6.5202 | -3.8954 | -3.9506 | 9.09 | -6.5202 | -6.4926 | 5.7926 | 5.0202 | 0.8 | 13.2753 | Shoring | 10 | 4.9926 | 0.8 | 4.0696 | 235.737 | 0 | 15.348 | 33.6408 | 2.1334 | 2.1617 | 4.0524 | 4.0807
UG-02 | UG-02-S04 | P0282-24 | 10 | 2.0696 | -6.5202 | -6.5755 | -3.9506 | -4.0059 | 9.01 | -6.5755 | -6.5479 | 5.8479 | 5.0755 | 0.8 | 13.3858 | Shoring | 10 | 5.0479 | 0.8 | 4.0696 | 237.9853 | 0 | 15.348 | 33.6408 | 2.1617 | 2.1901 | 4.0807 | 4.1091
UG-02 | UG-02-S04 | P0282-25 | 10 | 2.0696 | -6.5755 | -6.6307 | -4.0059 | -4.0611 | 8.94 | -6.6307 | -6.6031 | 5.9031 | 5.1307 | 0.8 | 13.4963 | Shoring | 10 | 5.1031 | 0.8 | 4.0696 | 240.2337 | 0 | 15.348 | 33.6408 | 2.1901 | 2.2185 | 4.1091 | 4.1375
UG-02 | UG-02-S04 | P0282-26 | 10 | 2.0696 | -6.6307 | -6.686 | -4.0611 | -4.1164 | 8.91 | -6.686 | -6.6584 | 5.9584 | 5.186 | 0.8 | 13.6068 | Shoring | 10 | 5.1584 | 0.8 | 4.0696 | 242.4821 | 0 | 15.348 | 33.6408 | 2.2185 | 2.2469 | 4.1375 | 4.1659
UG-02 | UG-02-S04 | P0282-27 | 5.2164 | 2.0696 | -6.686 | -6.7148 | -4.1164 | -4.1452 | 9.8 | -6.7148 | -6.7004 | 6.0004 | 5.2148 | 0.8 | 13.6644 | Shoring | 5.2164 | 5.2004 | 0.8 | 4.0696 | 127.3796 | 0 | 8.0061 | 17.5483 | 2.2469 | 2.2617 | 4.1659 | 4.1807
UG-02 | UG-02-S04 | P0481 | 3.1 | 2.0696 | -6.7148 | -6.7199 | -4.1452 | -4.1503 | 12.41 | -6.7199 | -6.7174 | 6.0174 | 5.2199 | 0.8 | 13.6746 | Shoring | 3.1 | 5.2174 | 0.8 | 4.0696 | 75.9144 | 0 | 4.7579 | 10.4288 | 2.2617 | 2.2643 | 4.1807 | 4.1833
UG-02 | UG-02-S04 | P0480-01 | 1.6836 | 2.0696 | -6.7199 | -6.7227 | -4.1503 | -4.1531 | 13.64 | -6.7227 | -6.7213 | 6.0213 | 5.2227 | 0.8 | 13.6801 | Shoring | 1.6836 | 5.2213 | 0.8 | 4.0696 | 41.2557 | 0 | 2.584 | 5.6638 | 2.2643 | 2.2657 | 4.1833 | 4.1847
UG-02 | UG-02-S04 | P0480-02 | 1.3941 | 2.0696 | -6.7227 | -6.725 | -4.1531 | -4.1554 | 12.92 | -6.725 | -6.7238 | 6.0238 | 5.225 | 0.8 | 13.6847 | Shoring | 1.3941 | 5.2238 | 0.8 | 4.0696 | 34.1751 | 0 | 2.1396 | 4.6897 | 2.2657 | 2.2669 | 4.1847 | 4.1859
UG-02 | UG-02-S05 | P0188 | 5.9679 | 2.0696 | -6.725 | -6.7348 | -4.1554 | -4.1652 | 11.31 | -6.7348 | -6.7299 | 6.0299 | 5.2348 | 0.8 | 13.7044 | Shoring | 5.9679 | 5.2299 | 0.8 | 4.0696 | 146.4466 | 0 | 9.1595 | 20.0762 | 2.2669 | 2.272 | 4.1859 | 4.191
UG-03 | UG-03-S01 | P0134 | 3.6907 | 1.5518 | -5.0959 | -5.0959 | -3.0441 | -3.0441 | 16.53 | -5.0959 | -5.0959 | 4.3959 | 3.5959 | 0.8 | 10.1677 | Shoring | 3.6907 | 3.5959 | 0.8 | 3.5518 | 57.6244 | 0 | 4.709 | 6.9803 | 2.2621 | 2.2621 | 4.8214 | 4.8214
UG-03 | UG-03-S01 | P0133 | 0.75 | 2.0412 | -5.3406 | -5.3468 | -2.7994 | -2.8056 | 17.12 | -5.3468 | -5.3437 | 4.6437 | 3.8468 | 0.8 | 10.9143 | Shoring | 0.75 | 3.8437 | 0.8 | 4.0412 | 14.0747 | 0 | 1.1405 | 2.4543 | 1.5923 | 1.5955 | 3.538 | 3.5412
UG-03 | UG-03-S01 | P0484 | 1.9999 | 2.0412 | -5.3468 | -5.3634 | -2.8056 | -2.8222 | 17.09 | -5.3634 | -5.3551 | 4.6551 | 3.8634 | 0.8 | 10.9474 | Shoring | 1.9999 | 3.8551 | 0.8 | 4.0412 | 37.6217 | 0 | 3.041 | 6.5443 | 1.5955 | 1.6042 | 3.5412 | 3.5499
UG-03 | UG-03-S01 | P0485 | 2.0001 | 2.0412 | -5.3634 | -5.38 | -2.8222 | -2.8388 | 17.07 | -5.38 | -5.3717 | 4.6717 | 3.88 | 0.8 | 10.9806 | Shoring | 2.0001 | 3.8717 | 0.8 | 4.0412 | 37.7608 | 0 | 3.0414 | 6.5451 | 1.6042 | 1.6128 | 3.5499 | 3.5585
UG-03 | UG-03-S01 | P0278-01 | 1.5593 | 2.0412 | -5.38 | -5.3929 | -2.8388 | -2.8517 | 17.06 | -5.3929 | -5.3865 | 4.6865 | 3.8929 | 0.8 | 11.0064 | Shoring | 1.5593 | 3.8865 | 0.8 | 4.0412 | 29.5318 | 0 | 2.3711 | 5.1026 | 1.6128 | 1.6196 | 3.5585 | 3.5653
UG-03 | UG-03-S01 | P0278-02 | 10 | 2.0412 | -5.3929 | -5.4758 | -2.8517 | -2.9346 | 16.99 | -5.4758 | -5.4344 | 4.7344 | 3.9758 | 0.8 | 11.1723 | Shoring | 10 | 3.9344 | 0.8 | 4.0412 | 191.3258 | 0 | 15.206 | 32.7236 | 1.6196 | 1.6627 | 3.5653 | 3.6084
UG-03 | UG-03-S01 | P0278-03 | 10 | 2.0412 | -5.4758 | -5.5588 | -2.9346 | -3.0176 | 16.49 | -5.5588 | -5.5173 | 4.8173 | 4.0588 | 0.8 | 11.3381 | Shoring | 10 | 4.0173 | 0.8 | 4.0412 | 194.6768 | 0 | 15.206 | 32.7236 | 1.6627 | 1.7059 | 3.6084 | 3.6516
UG-03 | UG-03-S01 | P0278-04 | 10 | 2.0412 | -5.5588 | -5.6417 | -3.0176 | -3.1005 | 15.83 | -5.6417 | -5.6002 | 4.9002 | 4.1417 | 0.8 | 11.504 | Shoring | 10 | 4.1002 | 0.8 | 4.0412 | 198.0277 | 0 | 15.206 | 32.7236 | 1.7059 | 1.7491 | 3.6516 | 3.6948
UG-03 | UG-03-S01 | P0278-05 | 10 | 2.0412 | -5.6417 | -5.7246 | -3.1005 | -3.1834 | 15.76 | -5.7246 | -5.6831 | 4.9831 | 4.2246 | 0.8 | 11.6698 | Shoring | 10 | 4.1831 | 0.8 | 4.0412 | 201.3787 | 0 | 15.206 | 32.7236 | 1.7491 | 1.7923 | 3.6948 | 3.738
UG-03 | UG-03-S01 | P0278-06 | 10 | 2.0412 | -5.7246 | -5.8075 | -3.1834 | -3.2663 | 15.68 | -5.8075 | -5.7661 | 5.0661 | 4.3075 | 0.8 | 11.8356 | Shoring | 10 | 4.2661 | 0.8 | 4.0412 | 204.7297 | 0 | 15.206 | 32.7236 | 1.7923 | 1.8355 | 3.738 | 3.7812
UG-03 | UG-03-S01 | P0278-07 | 6 | 2.0412 | -5.8075 | -5.8573 | -3.2663 | -3.3161 | 15.63 | -5.8573 | -5.8324 | 5.1324 | 4.3573 | 0.8 | 11.9351 | Shoring | 6 | 4.3324 | 0.8 | 4.0412 | 124.4463 | 0 | 9.1236 | 19.6342 | 1.8355 | 1.8614 | 3.7812 | 3.8071
UG-03 | UG-03-S02 | P0278-08 | 4 | 2.0412 | -5.8573 | -5.8904 | -3.3161 | -3.3492 | 15.6 | -5.8904 | -5.8739 | 5.1739 | 4.3904 | 0.8 | 12.0015 | Shoring | 4 | 4.3739 | 0.8 | 4.0412 | 83.6344 | 0 | 6.0824 | 13.0894 | 1.8614 | 1.8786 | 3.8071 | 3.8243
UG-03 | UG-03-S02 | P0278-09 | 10 | 2.0412 | -5.8904 | -5.9734 | -3.3492 | -3.4322 | 15.52 | -5.9734 | -5.9319 | 5.2319 | 4.4734 | 0.8 | 12.1673 | Shoring | 10 | 4.4319 | 0.8 | 4.0412 | 211.4316 | 0 | 15.206 | 32.7236 | 1.8786 | 1.9218 | 3.8243 | 3.8675
UG-03 | UG-03-S02 | P0278-10 | 2 | 2.0412 | -5.9734 | -5.9899 | -3.4322 | -3.4487 | 15.51 | -5.9899 | -5.9817 | 5.2817 | 4.4899 | 0.8 | 12.2005 | Shoring | 2 | 4.4817 | 0.8 | 4.0412 | 42.6884 | 0 | 3.0412 | 6.5447 | 1.9218 | 1.9305 | 3.8675 | 3.8762
UG-03 | UG-03-S03 | P0278-11 | 8 | 2.0412 | -5.9899 | -6.0563 | -3.4487 | -3.5151 | 14.94 | -6.0563 | -6.0231 | 5.3231 | 4.5563 | 0.8 | 12.3332 | Shoring | 8 | 4.5231 | 0.8 | 4.0412 | 172.0942 | 0 | 12.1648 | 26.1789 | 1.9305 | 1.965 | 3.8762 | 3.9107
UG-03 | UG-03-S03 | P0278-12 | 10 | 2.0412 | -6.0563 | -6.1392 | -3.5151 | -3.598 | 14.37 | -6.1392 | -6.0977 | 5.3977 | 4.6392 | 0.8 | 12.499 | Shoring | 10 | 4.5977 | 0.8 | 4.0412 | 218.1336 | 0 | 15.206 | 32.7236 | 1.965 | 2.0082 | 3.9107 | 3.9539
UG-03 | UG-03-S03 | P0278-13 | 10 | 2.0412 | -6.1392 | -6.2221 | -3.598 | -3.6809 | 14.29 | -6.2221 | -6.1807 | 5.4807 | 4.7221 | 0.8 | 12.6648 | Shoring | 10 | 4.6807 | 0.8 | 4.0412 | 221.4846 | 0 | 15.206 | 32.7236 | 2.0082 | 2.0514 | 3.9539 | 3.9971
UG-03 | UG-03-S03 | P0278-14 | 10 | 2.0412 | -6.2221 | -6.305 | -3.6809 | -3.7638 | 14.22 | -6.305 | -6.2636 | 5.5636 | 4.805 | 0.8 | 12.8307 | Shoring | 10 | 4.7636 | 0.8 | 4.0412 | 224.8356 | 0 | 15.206 | 32.7236 | 2.0514 | 2.0946 | 3.9971 | 4.0403
UG-03 | UG-03-S03 | P0278-15 | 10 | 2.0412 | -6.305 | -6.388 | -3.7638 | -3.8468 | 14.14 | -6.388 | -6.3465 | 5.6465 | 4.888 | 0.8 | 12.9965 | Shoring | 10 | 4.8465 | 0.8 | 4.0412 | 228.1865 | 0 | 15.206 | 32.7236 | 2.0946 | 2.1377 | 4.0403 | 4.0834
UG-03 | UG-03-S03 | P0278-16 | 10 | 2.0412 | -6.388 | -6.4709 | -3.8468 | -3.9297 | 14.06 | -6.4709 | -6.4294 | 5.7294 | 4.9709 | 0.8 | 13.1624 | Shoring | 10 | 4.9294 | 0.8 | 4.0412 | 231.5375 | 0 | 15.206 | 32.7236 | 2.1377 | 2.1809 | 4.0834 | 4.1266
UG-03 | UG-03-S03 | P0278-17 | 10 | 2.0412 | -6.4709 | -6.5538 | -3.9297 | -4.0126 | 13.99 | -6.5538 | -6.5123 | 5.8123 | 5.0538 | 0.8 | 13.3282 | Shoring | 10 | 5.0123 | 0.8 | 4.0412 | 234.8885 | 0 | 15.206 | 32.7236 | 2.1809 | 2.2241 | 4.1266 | 4.1698
UG-03 | UG-03-S03 | P0278-18 | 10 | 2.0412 | -6.5538 | -6.6367 | -4.0126 | -4.0955 | 13.96 | -6.6367 | -6.5953 | 5.8953 | 5.1367 | 0.8 | 13.4941 | Shoring | 10 | 5.0953 | 0.8 | 4.0412 | 238.2395 | 0 | 15.206 | 32.7236 | 2.2241 | 2.2673 | 4.1698 | 4.213
UG-03 | UG-03-S03 | P0278-19 | 8.1 | 2.0412 | -6.6367 | -6.7039 | -4.0955 | -4.1627 | 14.52 | -6.7039 | -6.6703 | 5.9703 | 5.2039 | 0.8 | 13.6284 | Shoring | 8.1 | 5.1703 | 0.8 | 4.0412 | 195.4304 | 0 | 12.3169 | 26.5061 | 2.2673 | 2.3023 | 4.213 | 4.248
UG-03 | UG-03-S04 | P0278-20 | 0.80903 | 2.0412 | -6.7039 | -6.7106 | -4.1627 | -4.1694 | 14.51 | -6.7106 | -6.7072 | 6.0072 | 5.2106 | 0.8 | 13.6418 | Shoring | 0.80903 | 5.2072 | 0.8 | 4.0412 | 19.6404 | 0 | 1.2302 | 2.6474 | 2.3023 | 2.3057 | 4.248 | 4.2515
UG-03 | UG-03-S04 | P0483-01 | 1.091 | 2.0412 | -6.7106 | -6.7112 | -4.1694 | -4.17 | 14.5 | -6.7112 | -6.7109 | 6.0109 | 5.2112 | 0.8 | 13.6431 | Shoring | 1.091 | 5.2109 | 0.8 | 4.0412 | 26.5011 | 0 | 1.6589 | 3.57 | 2.3057 | 2.3061 | 4.2515 | 4.2518
UG-03 | UG-03-S04 | P0483-02 | 2.0149 | 2.0412 | -6.7112 | -6.7124 | -4.17 | -4.1712 | 19.65 | -6.7124 | -6.7118 | 6.0118 | 5.2124 | 0.8 | 13.6454 | Shoring | 2.0149 | 5.2118 | 0.8 | 4.0412 | 48.9518 | 0 | 3.0639 | 6.5935 | 2.3061 | 2.3067 | 4.2518 | 4.2524
UG-03 | UG-03-S04 | P0482 | 3.0655 | 2.0696 | -6.7266 | -6.7284 | -4.157 | -4.1588 | 19.14 | -6.7284 | -6.7275 | 6.0275 | 5.2284 | 0.8 | 13.6916 | Shoring | 3.0655 | 5.2275 | 0.8 | 4.0696 | 75.195 | 0 | 4.7049 | 10.3125 | 2.2677 | 2.2687 | 4.1868 | 4.1877
UG-03 | UG-03-S05 | P0189-01 | 4.9196 | 2.0696 | -6.7284 | -6.7313 | -4.1588 | -4.1617 | 16.76 | -6.7313 | -6.7298 | 6.0298 | 5.2313 | 0.8 | 13.6973 | Shoring | 4.9196 | 5.2298 | 0.8 | 4.0696 | 120.7224 | 0 | 7.5506 | 16.5498 | 2.2687 | 2.2701 | 4.1877 | 4.1891
UG-03 | UG-03-S05 | P0189-02 | 6.0592 | 2.0696 | -6.7313 | -6.7348 | -4.1617 | -4.1652 | 15.41 | -6.7348 | -6.733 | 6.033 | 5.2348 | 0.8 | 13.7044 | Shoring | 6.0592 | 5.233 | 0.8 | 4.0696 | 148.7648 | 0 | 9.2996 | 20.3833 | 2.2701 | 2.272 | 4.1891 | 4.191
UG-04 | UG-04-S01 | P0269 | 3.1319 | 1.5316 | -5.0858 | -5.0858 | -3.0542 | -3.0542 | 19.08 | -5.0858 | -5.0858 | 4.3858 | 3.5858 | 0.8 | 10.1374 | Shoring | 3.1319 | 3.5858 | 0.8 | 3.5316 | 48.51 | 0 | 3.9644 | 5.7702 | 2.2989 | 2.2989 | 4.892 | 4.892
UG-04 | UG-04-S01 | P0123 | 0.75 | 2.0412 | -5.3406 | -5.3936 | -2.7994 | -2.8524 | 18.33 | -5.3936 | -5.3671 | 4.6671 | 3.8936 | 0.8 | 11.0078 | Shoring | 0.75 | 3.8671 | 0.8 | 4.0412 | 14.1456 | 0 | 1.1405 | 2.4543 | 1.5923 | 1.6199 | 3.538 | 3.5656
UG-04 | UG-04-S01 | P0704 | 0.89998 | 2.0412 | -5.3936 | -5.4572 | -2.8524 | -2.916 | 17.43 | -5.4572 | -5.4254 | 4.7254 | 3.9572 | 0.8 | 11.1351 | Shoring | 0.89998 | 3.9254 | 0.8 | 4.0412 | 17.1864 | 0 | 1.3685 | 2.9451 | 1.6199 | 1.653 | 3.5656 | 3.5987
UG-04 | UG-04-S01 | P0705 | 0.90002 | 2.0696 | -5.4714 | -5.535 | -2.9018 | -2.9655 | 16.65 | -5.535 | -5.5032 | 4.8032 | 4.035 | 0.8 | 11.3049 | Shoring | 0.90002 | 4.0032 | 0.8 | 4.0696 | 17.5928 | 0 | 1.3813 | 3.0277 | 1.6231 | 1.6557 | 3.5421 | 3.5748
UG-04 | UG-04-S01 | P0125 | 2.8278 | 2.0696 | -5.535 | -5.7349 | -2.9655 | -3.1653 | 21.34 | -5.7349 | -5.635 | 4.935 | 4.2349 | 0.8 | 11.7046 | Shoring | 2.8278 | 4.135 | 0.8 | 4.0696 | 56.7911 | 0 | 4.34 | 9.5127 | 1.6557 | 1.7584 | 3.5748 | 3.6774
UG-04 | UG-04-S01 | P0711 | 0.89999 | 2.0696 | -5.7349 | -5.7985 | -3.1653 | -3.229 | 23.13 | -5.7985 | -5.7667 | 5.0667 | 4.2985 | 0.8 | 11.8319 | Shoring | 0.89999 | 4.2667 | 0.8 | 4.0696 | 18.5575 | 0 | 1.3813 | 3.0276 | 1.7584 | 1.7911 | 3.6774 | 3.7101
UG-04 | UG-04-S01 | P0710-01 | 0.59031 | 2.0696 | -5.7985 | -5.8403 | -3.229 | -3.2707 | 23.39 | -5.8403 | -5.8194 | 5.1194 | 4.3403 | 0.8 | 11.9154 | Shoring | 0.59031 | 4.3194 | 0.8 | 4.0696 | 12.2985 | 0 | 0.90601 | 1.9858 | 1.7911 | 1.8125 | 3.7101 | 3.7315
UG-04 | UG-04-S01 | P0710-02 | 0.30969 | 2.0696 | -5.8403 | -5.8622 | -3.2707 | -3.2926 | 23.23 | -5.8622 | -5.8512 | 5.1512 | 4.3622 | 0.8 | 11.9591 | Shoring | 0.30969 | 4.3512 | 0.8 | 4.0696 | 6.4922 | 0 | 0.47531 | 1.0418 | 1.8125 | 1.8238 | 3.7315 | 3.7428
UG-04 | UG-04-S02 | P0124 | 0.33017 | 2.0696 | -5.8622 | -5.8855 | -3.2926 | -3.3159 | 23.06 | -5.8855 | -5.8738 | 5.1738 | 4.3855 | 0.8 | 12.0058 | Shoring | 0.33017 | 4.3738 | 0.8 | 4.0696 | 6.9519 | 0 | 0.50674 | 1.1107 | 1.8238 | 1.8357 | 3.7428 | 3.7548
UG-04 | UG-04-S02 | P0187-01 | 9.3601 | 2.0696 | -5.8855 | -6.5471 | -3.3159 | -3.9775 | 19.94 | -6.5471 | -6.2163 | 5.5163 | 5.0471 | 0.8 | 13.3291 | Shoring | 9.3601 | 4.7163 | 0.8 | 4.0696 | 210.1278 | 0 | 14.3659 | 31.4879 | 1.8357 | 2.1756 | 3.7548 | 4.0946
UG-04 | UG-04-S02 | P0187-02 | 2.6549 | 2.0696 | -6.5471 | -6.7348 | -3.9775 | -4.1652 | 19.53 | -6.7348 | -6.641 | 5.941 | 5.2348 | 0.8 | 13.7044 | Shoring | 2.6549 | 5.141 | 0.8 | 4.0696 | 64.1882 | 0 | 4.0747 | 8.9312 | 2.1756 | 2.272 | 4.0946 | 4.191
UG-05 | UG-05-S01 | P0042-01 | 6 | 2.2764 | -3.6382 | -3.6603 | -0.8618 | -0.88396 | 17.96 | -3.6603 | -3.6493 | 2.9493 | 2.1603 | 0.8 | 7.6589 | Open cut | 0 | 2.1493 | 0.8 | 4.2764 | 0 | 178.132 | 9.8292 | 24.4194 | 0.16606 | 0.18879 | 1.9107 | 1.9335
UG-05 | UG-05-S02 | P0042-02 | 4 | 2.2764 | -3.6603 | -3.6751 | -0.88396 | -0.89872 | 15.4 | -3.6751 | -3.6677 | 2.9677 | 2.1751 | 0.8 | 7.6884 | Open cut | 0 | 2.1677 | 0.8 | 4.2764 | 0 | 119.9443 | 6.5528 | 16.2796 | 0.18879 | 0.20395 | 1.9335 | 1.9486
UG-05 | UG-05-S02 | P0042-03 | 10 | 2.2764 | -3.6751 | -3.712 | -0.89872 | -0.93565 | 12.71 | -3.712 | -3.6936 | 2.9936 | 2.212 | 0.8 | 7.7623 | Open cut | 0 | 2.1936 | 0.8 | 4.2764 | 0 | 304.0472 | 16.382 | 40.699 | 0.20395 | 0.24184 | 1.9486 | 1.9865
UG-05 | UG-05-S02 | P0042-04 | 10 | 2.2764 | -3.712 | -3.749 | -0.93565 | -0.97257 | 12.78 | -3.749 | -3.7305 | 3.0305 | 2.249 | 0.8 | 7.8361 | Open cut | 0 | 2.2305 | 0.8 | 4.2764 | 0 | 310.0743 | 16.382 | 40.699 | 0.24184 | 0.27973 | 1.9865 | 2.0244
UG-05 | UG-05-S02 | P0042-05 | 9.2489 | 2.2764 | -3.749 | -3.7831 | -0.97257 | -1.0067 | 16.91 | -3.7831 | -3.766 | 3.066 | 2.2831 | 0.8 | 7.9044 | Open cut | 0 | 2.266 | 0.8 | 4.2764 | 0 | 292.1987 | 15.1516 | 37.6423 | 0.27973 | 0.31477 | 2.0244 | 2.0595
UG-05 | UG-05-S02 | P0528-01 | 0.75106 | 2.2764 | -3.7831 | -3.7859 | -1.0067 | -1.0095 | 23.62 | -3.7859 | -3.7845 | 3.0845 | 2.2859 | 0.8 | 7.91 | Open cut | 0 | 2.2845 | 0.8 | 4.2764 | 0 | 23.9578 | 1.2304 | 3.0567 | 0.31477 | 0.31762 | 2.0595 | 2.0623
UG-05 | UG-05-S02 | P0528-02 | 2.6489 | 2.2764 | -3.7859 | -3.7957 | -1.0095 | -1.0193 | 24.24 | -3.7957 | -3.7908 | 3.0908 | 2.2957 | 0.8 | 7.9295 | Open cut | 0 | 2.2908 | 0.8 | 4.2764 | 0 | 84.7744 | 4.3395 | 10.781 | 0.31762 | 0.32765 | 2.0623 | 2.0723
UG-05 | UG-05-S02 | P0529 | 3.3955 | 2.249 | -3.782 | -3.7945 | -1.033 | -1.0455 | 24.91 | -3.7945 | -3.7882 | 3.0882 | 2.2945 | 0.8 | 7.9135 | Open cut | 0 | 2.2882 | 0.8 | 4.249 | 0 | 108.2364 | 5.516 | 13.4889 | 0.34587 | 0.3589 | 2.1118 | 2.1248
UG-05 | UG-05-S02 | P0334-01 | 3.9555 | 2.249 | -3.7945 | -3.8081 | -1.0455 | -1.0591 | 23.57 | -3.8081 | -3.8013 | 3.1013 | 2.3081 | 0.8 | 7.9406 | Open cut | 0 | 2.3013 | 0.8 | 4.249 | 0 | 126.9462 | 6.4258 | 15.7136 | 0.3589 | 0.37299 | 2.1248 | 2.1389
UG-05 | UG-05-S02 | P0334-02 | 4.1 | 2.249 | -3.8081 | -3.8221 | -1.0591 | -1.0731 | 22.83 | -3.8221 | -3.8151 | 3.1151 | 2.3221 | 0.8 | 7.9688 | Open cut | 0 | 2.3151 | 0.8 | 4.249 | 0 | 132.5274 | 6.6605 | 16.2875 | 0.37299 | 0.38759 | 2.1389 | 2.1535
UG-05 | UG-05-S03 | P0334-03 | 5.9 | 2.249 | -3.8221 | -3.8424 | -1.0731 | -1.0934 | 22.73 | -3.8424 | -3.8322 | 3.1322 | 2.3424 | 0.8 | 8.0092 | Open cut | 0 | 2.3322 | 0.8 | 4.249 | 0 | 192.4041 | 9.5846 | 23.4381 | 0.38759 | 0.40861 | 2.1535 | 2.1745
UG-05 | UG-05-S03 | P0334-04 | 10 | 2.249 | -3.8424 | -3.8767 | -1.0934 | -1.1277 | 23.04 | -3.8767 | -3.8595 | 3.1595 | 2.3767 | 0.8 | 8.0778 | Open cut | 0 | 2.3595 | 0.8 | 4.249 | 0 | 330.6981 | 16.245 | 39.7256 | 0.40861 | 0.44424 | 2.1745 | 2.2102
UG-05 | UG-05-S03 | P0334-05 | 10 | 2.249 | -3.8767 | -3.911 | -1.1277 | -1.162 | 26.58 | -3.911 | -3.8938 | 3.1938 | 2.411 | 0.8 | 8.1464 | Open cut | 0 | 2.3938 | 0.8 | 4.249 | 0 | 336.5131 | 16.245 | 39.7256 | 0.44424 | 0.47986 | 2.2102 | 2.2458
UG-05 | UG-05-S03 | P0334-06 | 10 | 2.249 | -3.911 | -3.9453 | -1.162 | -1.1962 | 45.94 | -3.9453 | -3.9281 | 3.2281 | 2.4453 | 0.8 | 8.215 | Open cut | 0 | 2.4281 | 0.8 | 4.249 | 0 | 342.3752 | 16.245 | 39.7256 | 0.47986 | 0.51549 | 2.2458 | 2.2814
UG-05 | UG-05-S03 | P0334-07 | 10 | 2.249 | -3.9453 | -3.9795 | -1.1962 | -1.2305 | 36.31 | -3.9795 | -3.9624 | 3.2624 | 2.4795 | 0.8 | 8.2836 | Open cut | 0 | 2.4624 | 0.8 | 4.249 | 0 | 348.2844 | 16.245 | 39.7256 | 0.51549 | 0.55112 | 2.2814 | 2.317
UG-05 | UG-05-S03 | P0334-08 | 10 | 2.249 | -3.9795 | -4.0138 | -1.2305 | -1.2648 | 26.81 | -4.0138 | -3.9967 | 3.2967 | 2.5138 | 0.8 | 8.3522 | Shoring | 10 | 2.4967 | 0.8 | 4.249 | 140.0767 | 0 | 16.245 | 39.7256 | 0.55112 | 0.58674 | 2.317 | 2.3527
UG-05 | UG-05-S03 | P0334-09 | 2.6476 | 2.249 | -4.0138 | -4.0229 | -1.2648 | -1.2739 | 24.33 | -4.0229 | -4.0184 | 3.3184 | 2.5229 | 0.8 | 8.3703 | Shoring | 2.6476 | 2.5184 | 0.8 | 4.249 | 37.3313 | 0 | 4.3011 | 10.5179 | 0.58674 | 0.59617 | 2.3527 | 2.3621
UG-05 | UG-05-S03 | P0609 | 3.4004 | 2.249 | -4.0229 | -4.0346 | -1.2739 | -1.2856 | 21.16 | -4.0346 | -4.0288 | 3.3288 | 2.5346 | 0.8 | 8.3937 | Shoring | 3.4004 | 2.5288 | 0.8 | 4.249 | 48.095 | 0 | 5.524 | 13.5083 | 0.59617 | 0.6083 | 2.3621 | 2.3742
UG-05 | UG-05-S03 | P0608 | 3.396 | 2.249 | -4.0346 | -4.0462 | -1.2856 | -1.2972 | 21.16 | -4.0462 | -4.0404 | 3.3404 | 2.5462 | 0.8 | 8.417 | Shoring | 3.396 | 2.5404 | 0.8 | 4.249 | 48.201 | 0 | 5.5168 | 13.4908 | 0.6083 | 0.6204 | 2.3742 | 2.3863
UG-05 | UG-05-S03 | P0331-01 | 0.55593 | 2.249 | -4.0462 | -4.0481 | -1.2972 | -1.2991 | 22.54 | -4.0481 | -4.0472 | 3.3472 | 2.5481 | 0.8 | 8.4208 | Shoring | 0.55593 | 2.5472 | 0.8 | 4.249 | 7.9065 | 0 | 0.9031 | 2.2084 | 0.6204 | 0.62238 | 2.3863 | 2.3883
UG-05 | UG-05-S03 | P0331-02 | 10 | 2.249 | -4.0481 | -4.0824 | -1.2991 | -1.3334 | 22.78 | -4.0824 | -4.0653 | 3.3653 | 2.5824 | 0.8 | 8.4894 | Shoring | 10 | 2.5653 | 0.8 | 4.249 | 142.9907 | 0 | 16.245 | 39.7253 | 0.62238 | 0.65801 | 2.3883 | 2.4239
UG-05 | UG-05-S03 | P0331-03 | 2.5524 | 2.249 | -4.0824 | -4.0912 | -1.3334 | -1.3422 | 27.9 | -4.0912 | -4.0868 | 3.3868 | 2.5912 | 0.8 | 8.5069 | Shoring | 2.5524 | 2.5868 | 0.8 | 4.249 | 36.7297 | 0 | 4.1463 | 10.1393 | 0.65801 | 0.6671 | 2.4239 | 2.433
UG-05 | UG-05-S03 | P0611 | 3.4 | 2.249 | -4.0912 | -4.1028 | -1.3422 | -1.3539 | 29.4 | -4.1028 | -4.097 | 3.397 | 2.6028 | 0.8 | 8.5302 | Shoring | 3.4 | 2.597 | 0.8 | 4.249 | 49.0752 | 0 | 5.5233 | 13.5066 | 0.6671 | 0.67921 | 2.433 | 2.4451
UG-05 | UG-05-S03 | P0610 | 3.397 | 2.249 | -4.1029 | -4.1145 | -1.3538 | -1.3655 | 99 | -4.1145 | -4.1087 | 3.4087 | 2.6145 | 0.8 | 8.5535 | Shoring | 3.397 | 2.6087 | 0.8 | 4.249 | 49.1999 | 0 | 5.5184 | 13.4946 | 0.67921 | 0.69131 | 2.4451 | 2.4572
UG-05 | UG-05-S03 | P0330-01 | 0.65069 | 2.249 | -4.1145 | -4.1145 | -1.3655 | -1.3655 | 99 | -4.1145 | -4.1145 | 3.4145 | 2.6145 | 0.8 | 8.5536 | Shoring | 0.65069 | 2.6145 | 0.8 | 4.249 | 9.4403 | 0 | 1.057 | 2.5849 | 0.69131 | 0.69135 | 2.4572 | 2.4573
UG-05 | UG-05-S03 | P0330-02 | 10 | 2.249 | -4.1145 | -4.1151 | -1.3655 | -1.3661 | 21.54 | -4.1151 | -4.1148 | 3.4148 | 2.6151 | 0.8 | 8.5548 | Shoring | 10 | 2.6148 | 0.8 | 4.249 | 145.0965 | 0 | 16.245 | 39.7255 | 0.69135 | 0.69197 | 2.4573 | 2.4579
UG-05 | UG-05-S03 | P0330-03 | 8.3 | 2.249 | -4.1151 | -4.1156 | -1.3661 | -1.3666 | 16.66 | -4.1156 | -4.1154 | 3.4154 | 2.6156 | 0.8 | 8.5558 | Shoring | 8.3 | 2.6154 | 0.8 | 4.249 | 120.4494 | 0 | 13.4834 | 32.9721 | 0.69197 | 0.69249 | 2.4579 | 2.4584
UG-05 | UG-05-S04 | P0330-04 | 1.7 | 2.249 | -4.1156 | -4.1157 | -1.3666 | -1.3667 | 15.78 | -4.1157 | -4.1157 | 3.4157 | 2.6157 | 0.8 | 8.556 | Shoring | 1.7 | 2.6157 | 0.8 | 4.249 | 24.6725 | 0 | 2.7617 | 6.7533 | 0.69249 | 0.69259 | 2.4584 | 2.4585
UG-05 | UG-05-S04 | P0330-05 | 10 | 2.249 | -4.1157 | -4.1163 | -1.3667 | -1.3673 | 11.7 | -4.1163 | -4.116 | 3.416 | 2.6163 | 0.8 | 8.5572 | Shoring | 10 | 2.616 | 0.8 | 4.249 | 145.1473 | 0 | 16.245 | 39.7255 | 0.69259 | 0.69321 | 2.4585 | 2.4591
UG-05 | UG-05-S04 | P0330-06 | 10 | 2.249 | -4.1163 | -4.1169 | -1.3673 | -1.3679 | 9.83 | -4.1169 | -4.1166 | 3.4166 | 2.6169 | 0.8 | 8.5584 | Shoring | 10 | 2.6166 | 0.8 | 4.249 | 145.1727 | 0 | 16.245 | 39.7255 | 0.69321 | 0.69383 | 2.4591 | 2.4598
UG-05 | UG-05-S04 | P0330-07 | 10 | 2.249 | -4.1169 | -4.1175 | -1.3679 | -1.3685 | 9.75 | -4.1175 | -4.1172 | 3.4172 | 2.6175 | 0.8 | 8.5596 | Shoring | 10 | 2.6172 | 0.8 | 4.249 | 145.1982 | 0 | 16.245 | 39.7255 | 0.69383 | 0.69446 | 2.4598 | 2.4604
UG-05 | UG-05-S04 | P0330-08 | 10 | 2.249 | -4.1175 | -4.1181 | -1.3685 | -1.3691 | 10.48 | -4.1181 | -4.1178 | 3.4178 | 2.6181 | 0.8 | 8.5608 | Shoring | 10 | 2.6178 | 0.8 | 4.249 | 145.2236 | 0 | 16.245 | 39.7255 | 0.69446 | 0.69508 | 2.4604 | 2.461
UG-05 | UG-05-S04 | P0330-09 | 10 | 2.249 | -4.1181 | -4.1187 | -1.3691 | -1.3697 | 13.55 | -4.1187 | -4.1184 | 3.4184 | 2.6187 | 0.8 | 8.562 | Shoring | 10 | 2.6184 | 0.8 | 4.249 | 145.249 | 0 | 16.245 | 39.7255 | 0.69508 | 0.6957 | 2.461 | 2.4616
UG-05 | UG-05-S04 | P0330-10 | 10 | 2.249 | -4.1187 | -4.1193 | -1.3697 | -1.3703 | 18.55 | -4.1193 | -4.119 | 3.419 | 2.6193 | 0.8 | 8.5631 | Shoring | 10 | 2.619 | 0.8 | 4.249 | 145.2744 | 0 | 16.245 | 39.7255 | 0.6957 | 0.69632 | 2.4616 | 2.4622
UG-05 | UG-05-S04 | P0330-11 | 10 | 2.249 | -4.1193 | -4.1199 | -1.3703 | -1.3709 | 15.21 | -4.1199 | -4.1196 | 3.4196 | 2.6199 | 0.8 | 8.5643 | Shoring | 10 | 2.6196 | 0.8 | 4.249 | 145.2998 | 0 | 16.245 | 39.7255 | 0.69632 | 0.69694 | 2.4622 | 2.4629
UG-05 | UG-05-S04 | P0330-12 | 10 | 2.249 | -4.1199 | -4.1205 | -1.3709 | -1.3715 | 11.07 | -4.1205 | -4.1202 | 3.4202 | 2.6205 | 0.8 | 8.5655 | Shoring | 10 | 2.6202 | 0.8 | 4.249 | 145.3252 | 0 | 16.245 | 39.7255 | 0.69694 | 0.69756 | 2.4629 | 2.4635
UG-05 | UG-05-S04 | P0330-13 | 10 | 2.249 | -4.1205 | -4.1211 | -1.3715 | -1.3721 | 9.17 | -4.1211 | -4.1208 | 3.4208 | 2.6211 | 0.8 | 8.5667 | Shoring | 10 | 2.6208 | 0.8 | 4.249 | 145.3507 | 0 | 16.245 | 39.7255 | 0.69756 | 0.69818 | 2.4635 | 2.4641
UG-05 | UG-05-S04 | P0330-14 | 10 | 2.249 | -4.1211 | -4.1217 | -1.3721 | -1.3727 | 9.09 | -4.1217 | -4.1214 | 3.4214 | 2.6217 | 0.8 | 8.5679 | Shoring | 10 | 2.6214 | 0.8 | 4.249 | 145.3761 | 0 | 16.245 | 39.7255 | 0.69818 | 0.69881 | 2.4641 | 2.4647
UG-05 | UG-05-S04 | P0330-15 | 10 | 2.249 | -4.1217 | -4.1223 | -1.3727 | -1.3733 | 9.83 | -4.1223 | -4.122 | 3.422 | 2.6223 | 0.8 | 8.5691 | Shoring | 10 | 2.622 | 0.8 | 4.249 | 145.4015 | 0 | 16.245 | 39.7255 | 0.69881 | 0.69943 | 2.4647 | 2.4654
UG-05 | UG-05-S04 | P0330-16 | 10 | 2.249 | -4.1223 | -4.1229 | -1.3733 | -1.3739 | 12.94 | -4.1229 | -4.1226 | 3.4226 | 2.6229 | 0.8 | 8.5703 | Shoring | 10 | 2.6226 | 0.8 | 4.249 | 145.4269 | 0 | 16.245 | 39.7255 | 0.69943 | 0.70005 | 2.4654 | 2.466
UG-05 | UG-05-S04 | P0330-17 | 1.5 | 2.249 | -4.1229 | -4.123 | -1.3739 | -1.374 | 18.02 | -4.123 | -4.123 | 3.423 | 2.623 | 0.8 | 8.5705 | Shoring | 1.5 | 2.623 | 0.8 | 4.249 | 21.8162 | 0 | 2.4368 | 5.9588 | 0.70005 | 0.70014 | 2.466 | 2.4661
UG-05 | UG-05-S05 | P0330-18 | 8.5 | 2.249 | -4.123 | -4.1235 | -1.374 | -1.3745 | 18.91 | -4.1235 | -4.1233 | 3.4233 | 2.6235 | 0.8 | 8.5715 | Shoring | 8.5 | 2.6233 | 0.8 | 4.249 | 123.6361 | 0 | 13.8083 | 33.7666 | 0.70014 | 0.70067 | 2.4661 | 2.4666
UG-05 | UG-05-S05 | P0330-19 | 10 | 2.249 | -4.1235 | -4.1241 | -1.3745 | -1.3751 | 24.5 | -4.1241 | -4.1238 | 3.4238 | 2.6241 | 0.8 | 8.5727 | Shoring | 10 | 2.6238 | 0.8 | 4.249 | 145.4778 | 0 | 16.245 | 39.7255 | 0.70067 | 0.70129 | 2.4666 | 2.4672
UG-05 | UG-05-S05 | P0330-20 | 6.5174 | 2.249 | -4.1241 | -4.1245 | -1.3751 | -1.3755 | 99 | -4.1245 | -4.1243 | 3.4243 | 2.6245 | 0.8 | 8.5735 | Shoring | 6.5174 | 2.6243 | 0.8 | 4.249 | 94.8278 | 0 | 10.5876 | 25.8908 | 0.70129 | 0.7017 | 2.4672 | 2.4676
UG-06 | UG-06-S01 | P0360 | 8.8526 | 2.2764 | -4.0682 | -4.0682 | -1.2918 | -1.2918 | 18.37 | -4.0682 | -4.0682 | 3.3682 | 2.5682 | 0.8 | 8.4746 | Shoring | 8.8526 | 2.5682 | 0.8 | 4.2764 | 127.5102 | 0 | 14.5023 | 36.0289 | 0.60737 | 0.60737 | 2.3521 | 2.3521
UG-06 | UG-06-S01 | P0601-01 | 1.1474 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 18.22 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 1.1474 | 2.5545 | 0.8 | 4.249 | 16.3537 | 0 | 1.8639 | 4.558 | 0.62898 | 0.62898 | 2.3949 | 2.3949
UG-06 | UG-06-S01 | P0601-02 | 0.2767 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 18.2 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 0.2767 | 2.5545 | 0.8 | 4.249 | 3.9438 | 0 | 0.44949 | 1.0992 | 0.62898 | 0.62898 | 2.3949 | 2.3949
UG-06 | UG-06-S01 | P0602 | 2.7921 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 16.16 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 2.7921 | 2.5545 | 0.8 | 4.249 | 39.7964 | 0 | 4.5358 | 11.0917 | 0.62898 | 0.62898 | 2.3949 | 2.3949
UG-06 | UG-06-S01 | P0603 | 1.4216 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 14.74 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 1.4216 | 2.5545 | 0.8 | 4.249 | 20.2624 | 0 | 2.3094 | 5.6474 | 0.62898 | 0.62898 | 2.3949 | 2.3949
UG-06 | UG-06-S01 | P0757-01 | 5.5096 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 9.24 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 5.5096 | 2.5545 | 0.8 | 4.249 | 78.5299 | 0 | 8.9504 | 21.8871 | 0.62899 | 0.62899 | 2.3949 | 2.3949
UG-06 | UG-06-S01 | P0757-02 | 1.1846 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 8.05 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 1.1846 | 2.5545 | 0.8 | 4.249 | 16.8845 | 0 | 1.9244 | 4.7059 | 0.62899 | 0.62899 | 2.3949 | 2.3949
UG-06 | UG-06-S02 | P0359-01 | 8.8154 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 0 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 8.8154 | 2.5545 | 0.8 | 4.249 | 125.648 | 0 | 14.3206 | 35.0194 | 0.62899 | 0.62899 | 2.3949 | 2.3949
UG-06 | UG-06-S02 | P0359-02 | 10 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 0 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 10 | 2.5545 | 0.8 | 4.249 | 142.5325 | 0 | 16.245 | 39.7253 | 0.62899 | 0.62899 | 2.3949 | 2.3949
UG-06 | UG-06-S02 | P0359-03 | 9.1 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 6.87 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 9.1 | 2.5545 | 0.8 | 4.249 | 129.7046 | 0 | 14.7829 | 36.15 | 0.62899 | 0.62899 | 2.3949 | 2.3949
UG-06 | UG-06-S03 | P0359-04 | 0.9 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 15 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 0.9 | 2.5545 | 0.8 | 4.249 | 12.8279 | 0 | 1.462 | 3.5753 | 0.62899 | 0.62899 | 2.3949 | 2.3949
UG-06 | UG-06-S03 | P0359-05 | 0.34587 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 15.86 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 0.34587 | 2.5545 | 0.8 | 4.249 | 4.9298 | 0 | 0.56186 | 1.374 | 0.62899 | 0.62899 | 2.3949 | 2.3949
UG-06 | UG-06-S03 | P0605 | 3.4 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 16.19 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 3.4 | 2.5545 | 0.8 | 4.249 | 48.461 | 0 | 5.5233 | 13.5066 | 0.62899 | 0.62899 | 2.3949 | 2.3949
UG-06 | UG-06-S03 | P0604 | 3.3998 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 19.48 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 3.3998 | 2.5545 | 0.8 | 4.249 | 48.4585 | 0 | 5.523 | 13.5059 | 0.62899 | 0.62899 | 2.3949 | 2.3949
UG-06 | UG-06-S03 | P0328-01 | 2.8543 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 20.54 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 2.8543 | 2.5545 | 0.8 | 4.249 | 40.6833 | 0 | 4.6368 | 11.3389 | 0.62899 | 0.62899 | 2.3949 | 2.3949
UG-06 | UG-06-S03 | P0328-02 | 10 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 21.8 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 10 | 2.5545 | 0.8 | 4.249 | 142.5325 | 0 | 16.245 | 39.7253 | 0.62899 | 0.62899 | 2.3949 | 2.3949
UG-06 | UG-06-S03 | P0328-03 | 10 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 99 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 10 | 2.5545 | 0.8 | 4.249 | 142.5325 | 0 | 16.245 | 39.7253 | 0.62899 | 0.62899 | 2.3949 | 2.3949
UG-06 | UG-06-S03 | P0328-04 | 10 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 38.24 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 10 | 2.5545 | 0.8 | 4.249 | 142.5325 | 0 | 16.245 | 39.7253 | 0.62899 | 0.62899 | 2.3949 | 2.3949
UG-06 | UG-06-S03 | P0328-05 | 10 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 28.54 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 10 | 2.5545 | 0.8 | 4.249 | 142.5325 | 0 | 16.245 | 39.7253 | 0.62899 | 0.62899 | 2.3949 | 2.3949
UG-06 | UG-06-S03 | P0328-06 | 9.3937 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 19.53 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 9.3937 | 2.5545 | 0.8 | 4.249 | 133.8908 | 0 | 15.2601 | 37.3168 | 0.62899 | 0.62899 | 2.3949 | 2.3949
UG-06 | UG-06-S03 | P0053-01 | 0.60629 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 18.96 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 0.60629 | 2.5545 | 0.8 | 4.249 | 8.6417 | 0 | 0.98492 | 2.4085 | 0.62899 | 0.62899 | 2.3949 | 2.3949
UG-06 | UG-06-S03 | P0053-02 | 2.7937 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 16.32 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 2.7937 | 2.5545 | 0.8 | 4.249 | 39.8194 | 0 | 4.5384 | 11.0981 | 0.62899 | 0.62899 | 2.3949 | 2.3949
UG-06 | UG-06-S03 | P0052 | 3.4 | 2.249 | -4.0545 | -4.0545 | -1.3055 | -1.3055 | 16.32 | -4.0545 | -4.0545 | 3.3545 | 2.5545 | 0.8 | 8.4335 | Shoring | 3.4 | 2.5545 | 0.8 | 4.249 | 48.4611 | 0 | 5.5233 | 13.5067 | 0.62898 | 0.62898 | 2.3949 | 2.3949
UG-06 | UG-06-S03 | P0164-01 | 3.8063 | 2.249 | -4.0545 | -4.0694 | -1.3055 | -1.3204 | 17.56 | -4.0694 | -4.0619 | 3.3619 | 2.5694 | 0.8 | 8.4632 | Shoring | 3.8063 | 2.5619 | 0.8 | 4.249 | 54.3721 | 0 | 6.1833 | 15.1205 | 0.62899 | 0.64442 | 2.3949 | 2.4104
UG-06 | UG-06-S03 | P0164-02 | 9.8885 | 2.249 | -4.0694 | -4.108 | -1.3204 | -1.359 | 19.19 | -4.108 | -4.0887 | 3.3887 | 2.608 | 0.8 | 8.5404 | Shoring | 9.8885 | 2.5887 | 0.8 | 4.249 | 142.378 | 0 | 16.0638 | 39.2822 | 0.64442 | 0.68452 | 2.4104 | 2.4505
UG-06 | UG-06-S03 | P0606-01 | 0.11152 | 2.249 | -4.108 | -4.1084 | -1.359 | -1.3594 | 24.48 | -4.1084 | -4.1082 | 3.4082 | 2.6084 | 0.8 | 8.5413 | Shoring | 0.11152 | 2.6082 | 0.8 | 4.249 | 1.6149 | 0 | 0.18116 | 0.44301 | 0.68452 | 0.68497 | 2.4505 | 2.4509
UG-06 | UG-06-S03 | P0606-02 | 3.2885 | 2.249 | -4.1084 | -4.1212 | -1.3594 | -1.3722 | 24.55 | -4.1212 | -4.1148 | 3.4148 | 2.6212 | 0.8 | 8.5669 | Shoring | 3.2885 | 2.6148 | 0.8 | 4.249 | 47.7142 | 0 | 5.3421 | 13.0635 | 0.68497 | 0.69831 | 2.4509 | 2.4642
UG-06 | UG-06-S03 | P0607 | 3.3987 | 2.249 | -4.1212 | -4.1345 | -1.3722 | -1.3855 | 24.03 | -4.1345 | -4.1279 | 3.4279 | 2.6345 | 0.8 | 8.5935 | Shoring | 3.3987 | 2.6279 | 0.8 | 4.249 | 49.5021 | 0 | 5.5212 | 13.5015 | 0.6983 | 0.71208 | 2.4642 | 2.478
UG-06 | UG-06-S03 | P0329-01 | 3.3128 | 2.249 | -4.1345 | -4.1343 | -1.3855 | -1.3853 | 21.62 | -4.1345 | -4.1344 | 3.4344 | 2.6345 | 0.8 | 8.5935 | Shoring | 3.3128 | 2.6344 | 0.8 | 4.249 | 48.3432 | 0 | 5.3817 | 13.1603 | 0.71208 | 0.71187 | 2.478 | 2.4778
UG-06 | UG-06-S03 | P0329-02 | 7.4 | 2.249 | -4.1343 | -4.1338 | -1.3853 | -1.3848 | 16.65 | -4.1343 | -4.1341 | 3.4341 | 2.6343 | 0.8 | 8.5931 | Shoring | 7.4 | 2.6341 | 0.8 | 4.249 | 107.9761 | 0 | 12.0213 | 29.3968 | 0.71187 | 0.7114 | 2.4778 | 2.4773
UG-06 | UG-06-S04 | P0329-03 | 2.6 | 2.249 | -4.1338 | -4.1337 | -1.3848 | -1.3847 | 15.06 | -4.1338 | -4.1338 | 3.4338 | 2.6338 | 0.8 | 8.5922 | Shoring | 2.6 | 2.6338 | 0.8 | 4.249 | 37.9342 | 0 | 4.2237 | 10.3286 | 0.7114 | 0.71124 | 2.4773 | 2.4772
UG-06 | UG-06-S04 | P0329-04 | 10 | 2.249 | -4.1337 | -4.1331 | -1.3847 | -1.3841 | 10 | -4.1337 | -4.1334 | 3.4334 | 2.6337 | 0.8 | 8.5919 | Shoring | 10 | 2.6334 | 0.8 | 4.249 | 145.8843 | 0 | 16.245 | 39.7255 | 0.71124 | 0.7106 | 2.4772 | 2.4765
UG-06 | UG-06-S04 | P0329-05 | 10 | 2.249 | -4.1331 | -4.1325 | -1.3841 | -1.3835 | 7.07 | -4.1331 | -4.1328 | 3.4328 | 2.6331 | 0.8 | 8.5906 | Shoring | 10 | 2.6328 | 0.8 | 4.249 | 145.8582 | 0 | 16.245 | 39.7255 | 0.7106 | 0.70996 | 2.4765 | 2.4759
UG-06 | UG-06-S04 | P0329-06 | 10 | 2.249 | -4.1325 | -4.1318 | -1.3835 | -1.3828 | 6.56 | -4.1325 | -4.1322 | 3.4322 | 2.6325 | 0.8 | 8.5894 | Shoring | 10 | 2.6322 | 0.8 | 4.249 | 145.8322 | 0 | 16.245 | 39.7255 | 0.70996 | 0.70933 | 2.4759 | 2.4753
UG-06 | UG-06-S04 | P0329-07 | 10 | 2.249 | -4.1318 | -4.1312 | -1.3828 | -1.3822 | 6.78 | -4.1318 | -4.1315 | 3.4315 | 2.6318 | 0.8 | 8.5882 | Shoring | 10 | 2.6315 | 0.8 | 4.249 | 145.8062 | 0 | 16.245 | 39.7255 | 0.70933 | 0.70869 | 2.4753 | 2.4746
UG-06 | UG-06-S04 | P0329-08 | 10 | 2.249 | -4.1312 | -4.1306 | -1.3822 | -1.3816 | 9.21 | -4.1312 | -4.1309 | 3.4309 | 2.6312 | 0.8 | 8.587 | Shoring | 10 | 2.6309 | 0.8 | 4.249 | 145.7801 | 0 | 16.245 | 39.7255 | 0.70869 | 0.70805 | 2.4746 | 2.474
UG-06 | UG-06-S04 | P0329-09 | 10 | 2.249 | -4.1306 | -4.13 | -1.3816 | -1.381 | 13.89 | -4.1306 | -4.1303 | 3.4303 | 2.6306 | 0.8 | 8.5857 | Shoring | 10 | 2.6303 | 0.8 | 4.249 | 145.7541 | 0 | 16.245 | 39.7255 | 0.70805 | 0.70742 | 2.474 | 2.4733
UG-06 | UG-06-S04 | P0329-10 | 10 | 2.249 | -4.13 | -4.1294 | -1.381 | -1.3804 | 14.53 | -4.13 | -4.1297 | 3.4297 | 2.63 | 0.8 | 8.5845 | Shoring | 10 | 2.6297 | 0.8 | 4.249 | 145.7281 | 0 | 16.245 | 39.7255 | 0.70742 | 0.70678 | 2.4733 | 2.4727
UG-06 | UG-06-S04 | P0329-11 | 10 | 2.249 | -4.1294 | -4.1288 | -1.3804 | -1.3798 | 9.4 | -4.1294 | -4.1291 | 3.4291 | 2.6294 | 0.8 | 8.5833 | Shoring | 10 | 2.6291 | 0.8 | 4.249 | 145.702 | 0 | 16.245 | 39.7255 | 0.70678 | 0.70615 | 2.4727 | 2.4721
UG-06 | UG-06-S04 | P0329-12 | 10 | 2.249 | -4.1288 | -4.1282 | -1.3798 | -1.3792 | 6.41 | -4.1288 | -4.1285 | 3.4285 | 2.6288 | 0.8 | 8.5821 | Shoring | 10 | 2.6285 | 0.8 | 4.249 | 145.676 | 0 | 16.245 | 39.7255 | 0.70615 | 0.70551 | 2.4721 | 2.4714
UG-06 | UG-06-S04 | P0329-13 | 10 | 2.249 | -4.1282 | -4.1276 | -1.3792 | -1.3786 | 5.9 | -4.1282 | -4.1279 | 3.4279 | 2.6282 | 0.8 | 8.5808 | Shoring | 10 | 2.6279 | 0.8 | 4.249 | 145.65 | 0 | 16.245 | 39.7255 | 0.70551 | 0.70487 | 2.4714 | 2.4708
UG-06 | UG-06-S04 | P0329-14 | 10 | 2.249 | -4.1276 | -4.1269 | -1.3786 | -1.3779 | 6.12 | -4.1276 | -4.1273 | 3.4273 | 2.6276 | 0.8 | 8.5796 | Shoring | 10 | 2.6273 | 0.8 | 4.249 | 145.6239 | 0 | 16.245 | 39.7255 | 0.70487 | 0.70424 | 2.4708 | 2.4702
UG-06 | UG-06-S04 | P0329-15 | 10 | 2.249 | -4.1269 | -4.1263 | -1.3779 | -1.3773 | 8.59 | -4.1269 | -4.1266 | 3.4266 | 2.6269 | 0.8 | 8.5784 | Shoring | 10 | 2.6266 | 0.8 | 4.249 | 145.5979 | 0 | 16.245 | 39.7255 | 0.70424 | 0.7036 | 2.4702 | 2.4695
UG-06 | UG-06-S04 | P0329-16 | 7.8 | 2.249 | -4.1263 | -4.1259 | -1.3773 | -1.3769 | 13.34 | -4.1263 | -4.1261 | 3.4261 | 2.6263 | 0.8 | 8.5772 | Shoring | 7.8 | 2.6261 | 0.8 | 4.249 | 113.5483 | 0 | 12.6711 | 30.9859 | 0.7036 | 0.7031 | 2.4695 | 2.469
UG-06 | UG-06-S05 | P0329-17 | 2.2 | 2.249 | -4.1259 | -4.1257 | -1.3769 | -1.3767 | 18.2 | -4.1259 | -4.1258 | 3.4258 | 2.6259 | 0.8 | 8.5762 | Shoring | 2.2 | 2.6258 | 0.8 | 4.249 | 32.0236 | 0 | 3.5739 | 8.7396 | 0.7031 | 0.70296 | 2.469 | 2.4689
UG-06 | UG-06-S05 | P0329-18 | 10 | 2.249 | -4.1257 | -4.1251 | -1.3767 | -1.3761 | 19.71 | -4.1257 | -4.1254 | 3.4254 | 2.6257 | 0.8 | 8.5759 | Shoring | 10 | 2.6254 | 0.8 | 4.249 | 145.5458 | 0 | 16.245 | 39.7255 | 0.70296 | 0.70233 | 2.4689 | 2.4683
UG-06 | UG-06-S05 | P0329-19 | 9.9072 | 2.249 | -4.1251 | -4.1245 | -1.3761 | -1.3755 | 99 | -4.1251 | -4.1248 | 3.4248 | 2.6251 | 0.8 | 8.5747 | Shoring | 9.9072 | 2.6248 | 0.8 | 4.249 | 144.1695 | 0 | 16.0943 | 39.3568 | 0.70233 | 0.7017 | 2.4683 | 2.4676
UG-07 | UG-07-S01 | P0090 | 0.6 | 2.0412 | -3.2195 | -3.2264 | -0.67828 | -0.68521 | 8.3 | -3.2264 | -3.223 | 2.523 | 1.7264 | 0.8 | 6.6735 | Open cut | 0 | 1.723 | 0.8 | 4.0412 | 0 | 13.5639 | 0.91236 | 1.9634 | 0 | 0 | 1.9208 | 1.9288
UG-07 | UG-07-S01 | P0626 | 2.0145 | 2.0412 | -3.2264 | -3.2497 | -0.68521 | -0.70849 | 7.78 | -3.2497 | -3.2381 | 2.5381 | 1.7497 | 0.8 | 6.72 | Open cut | 0 | 1.7381 | 0.8 | 4.0412 | 0 | 45.9722 | 3.0633 | 6.5923 | 0 | 0.0097201 | 1.9288 | 1.9554
UG-07 | UG-07-S01 | P0627 | 1.9749 | 2.0696 | -3.2639 | -3.2867 | -0.69429 | -0.71711 | 7.78 | -3.2867 | -3.2753 | 2.5753 | 1.7867 | 0.8 | 6.8083 | Open cut | 0 | 1.7753 | 0.8 | 4.0696 | 0 | 46.2632 | 3.0312 | 6.6439 | 0 | 0.019318 | 1.9126 | 1.9383
UG-07 | UG-07-S01 | P0230-01 | 5.4105 | 2.0696 | -3.2867 | -3.3493 | -0.71711 | -0.77964 | 8.85 | -3.3493 | -3.318 | 2.618 | 1.8493 | 0.8 | 6.9333 | Open cut | 0 | 1.818 | 0.8 | 4.0696 | 0 | 130.0799 | 8.3041 | 18.2016 | 0.019318 | 0.0899 | 1.9383 | 2.0089
UG-07 | UG-07-S01 | P0230-02 | 4.7231 | 2.0696 | -3.3493 | -3.4038 | -0.77964 | -0.83422 | 12.13 | -3.4038 | -3.3765 | 2.6765 | 1.9038 | 0.8 | 7.0425 | Open cut | 0 | 1.8765 | 0.8 | 4.0696 | 0 | 117.6058 | 7.249 | 15.8889 | 0.0899 | 0.15151 | 2.0089 | 2.0705
UG-07 | UG-07-S01 | P0786 | 3.545 | 2.0696 | -3.4038 | -3.4448 | -0.83422 | -0.87519 | 14.86 | -3.4448 | -3.4243 | 2.7243 | 1.9448 | 0.8 | 7.1244 | Open cut | 0 | 1.9243 | 0.8 | 4.0696 | 0 | 90.7905 | 5.4409 | 11.9257 | 0.15151 | 0.19776 | 2.0705 | 2.1168
UG-07 | UG-07-S01 | P0625-01 | 1.7319 | 2.0696 | -3.4448 | -3.5966 | -0.87519 | -1.0269 | 14.48 | -3.5966 | -3.5207 | 2.8207 | 2.0966 | 0.8 | 7.4279 | Open cut | 0 | 2.0207 | 0.8 | 4.0696 | 0 | 46.8859 | 2.6582 | 5.8264 | 0.19776 | 0.36906 | 2.1168 | 2.2881
UG-07 | UG-07-S01 | P0625-02 | 0.23418 | 2.0696 | -3.5966 | -3.6171 | -1.0269 | -1.0475 | 14.44 | -3.6171 | -3.6068 | 2.9068 | 2.1171 | 0.8 | 7.469 | Open cut | 0 | 2.1068 | 0.8 | 4.0696 | 0 | 6.6529 | 0.35943 | 0.78782 | 0.36906 | 0.39222 | 2.2881 | 2.3112
UG-07 | UG-07-S02 | P0624 | 2.0272 | 2.0696 | -3.6171 | -3.7947 | -1.0475 | -1.2251 | 12.87 | -3.7947 | -3.7059 | 3.0059 | 2.2947 | 0.8 | 7.8242 | Open cut | 0 | 2.2059 | 0.8 | 4.0696 | 0 | 60.7813 | 3.1113 | 6.8195 | 0.39223 | 0.59274 | 2.3112 | 2.5117
UG-07 | UG-07-S02 | P0208 | 2.7927 | 2.0696 | -3.7947 | -4.0394 | -1.2251 | -1.4698 | 10.95 | -4.0394 | -3.917 | 3.217 | 2.5394 | 0.8 | 8.3136 | Shoring | 2.7927 | 2.417 | 0.8 | 4.0696 | 36.5621 | 0 | 4.2862 | 9.3948 | 0.59274 | 0.86895 | 2.5117 | 2.788
UG-07 | UG-07-S02 | P0785-01 | 4.9459 | 2.0696 | -4.0394 | -4.1272 | -1.4698 | -1.5576 | 8.78 | -4.1272 | -4.0833 | 3.3833 | 2.6272 | 0.8 | 8.4893 | Shoring | 4.9459 | 2.5833 | 0.8 | 4.0696 | 68.0992 | 0 | 7.591 | 16.6384 | 0.86895 | 0.93266 | 2.788 | 2.8517
UG-07 | UG-07-S02 | P0785-02 | 10 | 2.0696 | -4.1272 | -4.3048 | -1.5576 | -1.7352 | 8.53 | -4.3048 | -4.216 | 3.516 | 2.8048 | 0.8 | 8.8445 | Shoring | 10 | 2.716 | 0.8 | 4.0696 | 143.0885 | 0 | 15.348 | 33.6405 | 0.93266 | 1.0239 | 2.8517 | 2.9429
UG-07 | UG-07-S02 | P0785-03 | 10 | 2.0696 | -4.3048 | -4.4825 | -1.7352 | -1.9129 | 8.48 | -4.4825 | -4.3937 | 3.6937 | 2.9825 | 0.8 | 9.1997 | Shoring | 10 | 2.8937 | 0.8 | 4.0696 | 150.3168 | 0 | 15.348 | 33.6405 | 1.0239 | 1.1151 | 2.9429 | 3.0341
UG-07 | UG-07-S02 | P0785-04 | 5.5 | 2.0696 | -4.4825 | -4.5801 | -1.9129 | -2.0106 | 8.45 | -4.5801 | -4.5313 | 3.8313 | 3.0801 | 0.8 | 9.3951 | Shoring | 5.5 | 3.0313 | 0.8 | 4.0696 | 85.7553 | 0 | 8.4414 | 18.5023 | 1.1151 | 1.1653 | 3.0341 | 3.0843
UG-07 | UG-07-S03 | P0785-05 | 4.5 | 2.0696 | -4.5801 | -4.6601 | -2.0106 | -2.0905 | 8.43 | -4.6601 | -4.6201 | 3.9201 | 3.1601 | 0.8 | 9.555 | Shoring | 4.5 | 3.1201 | 0.8 | 4.0696 | 71.7898 | 0 | 6.9066 | 15.1382 | 1.1653 | 1.2063 | 3.0843 | 3.1253
UG-07 | UG-07-S03 | P0785-06 | 10 | 2.0696 | -4.6601 | -4.8377 | -2.0905 | -2.2681 | 8.44 | -4.8377 | -4.7489 | 4.0489 | 3.3377 | 0.8 | 9.9102 | Shoring | 10 | 3.2489 | 0.8 | 4.0696 | 164.7734 | 0 | 15.348 | 33.6405 | 1.2063 | 1.2976 | 3.1253 | 3.2166
UG-07 | UG-07-S03 | P0785-07 | 10 | 2.0696 | -4.8377 | -5.0153 | -2.2681 | -2.4457 | 9.65 | -5.0153 | -4.9265 | 4.2265 | 3.5153 | 0.8 | 10.2654 | Shoring | 10 | 3.4265 | 0.8 | 4.0696 | 172.0017 | 0 | 15.348 | 33.6405 | 1.2976 | 1.3888 | 3.2166 | 3.3078
UG-07 | UG-07-S03 | P0785-08 | 0.727 | 2.0696 | -5.0153 | -5.0282 | -2.4457 | -2.4586 | 9.65 | -5.0282 | -5.0218 | 4.3218 | 3.5282 | 0.8 | 10.2912 | Shoring | 0.727 | 3.5218 | 0.8 | 4.0696 | 12.7864 | 0 | 1.1158 | 2.4457 | 1.3888 | 1.3954 | 3.3078 | 3.3144
UG-07 | UG-07-S04 | P0785-09 | 6.0003 | 2.0696 | -5.0282 | -5.1348 | -2.4586 | -2.5652 | 9.67 | -5.1348 | -5.0815 | 4.3815 | 3.6348 | 0.8 | 10.5044 | Shoring | 6.0003 | 3.5815 | 0.8 | 4.0696 | 106.9917 | 0 | 9.2093 | 20.1854 | 1.3954 | 1.4502 | 3.3144 | 3.3692
UG-07A | UG-07A-S01 | P0035-01 | 10 | 1.2 | -2.5 | -2.5 | -0.80001 | -0.80001 | 13.38 | -2.5 | -2.5 | 1.8 | 0.99999 | 0.8 | 4.8 | Open cut | 0 | 0.99999 | 0.8 | 3.2 | 0 | 119.1992 | 10.9999 | 11.3095 | 0.1947 | 0.1947 | 3.5044 | 3.5044
UG-07A | UG-07A-S01 | P0035-02 | 6.6867 | 1.2 | -2.5 | -2.5 | -0.80001 | -0.80001 | 20.05 | -2.5 | -2.5 | 1.8 | 0.99999 | 0.8 | 4.8 | Open cut | 0 | 0.99999 | 0.8 | 3.2 | 0 | 79.7046 | 7.3553 | 7.5623 | 0.1947 | 0.1947 | 3.5044 | 3.5044
UG-07A | UG-07A-S01 | P0054 | 1.005 | 1.2 | -2.5 | -2.4998 | -0.8 | -0.79984 | 20.62 | -2.5 | -2.4999 | 1.7999 | 1 | 0.8 | 4.8 | Open cut | 0 | 0.99992 | 0.8 | 3.2 | 0 | 11.9785 | 1.1055 | 1.1366 | 0.19469 | 0.19438 | 3.5044 | 3.504
UG-07A | UG-07A-S01 | P0055 | 1.005 | 1.2 | -2.4998 | -2.4997 | -0.79984 | -0.79967 | 19.89 | -2.4998 | -2.4998 | 1.7998 | 0.99984 | 0.8 | 4.7997 | Open cut | 0 | 0.99975 | 0.8 | 3.2 | 0 | 11.977 | 1.1055 | 1.1366 | 0.19438 | 0.19405 | 3.504 | 3.5037
UG-07A | UG-07A-S02 | P0096-01 | 1.3033 | 1.2 | -2.4997 | -2.4995 | -0.79967 | -0.79946 | 18.95 | -2.4997 | -2.4996 | 1.7996 | 0.99967 | 0.8 | 4.7993 | Open cut | 0 | 0.99956 | 0.8 | 3.2 | 0 | 15.5299 | 1.4337 | 1.474 | 0.19405 | 0.19364 | 3.5037 | 3.5033
UG-07A | UG-07A-S02 | P0096-02 | 10 | 1.2 | -2.4995 | -2.4978 | -0.79946 | -0.79785 | 12.42 | -2.4995 | -2.4987 | 1.7987 | 0.99946 | 0.8 | 4.7989 | Open cut | 0 | 0.99865 | 0.8 | 3.2 | 0 | 119.0597 | 11 | 11.3097 | 0.19364 | 0.1905 | 3.5033 | 3.5001
UG-07A | UG-07A-S02 | P0096-03 | 10 | 1.2 | -2.4978 | -2.4962 | -0.79785 | -0.79624 | 7.49 | -2.4978 | -2.497 | 1.797 | 0.99784 | 0.8 | 4.7957 | Open cut | 0 | 0.99704 | 0.8 | 3.2 | 0 | 118.8921 | 11 | 11.3097 | 0.1905 | 0.18736 | 3.5001 | 3.497
UG-07A | UG-07A-S02 | P0096-04 | 0.20643 | 1.2 | -2.4962 | -2.4962 | -0.79624 | -0.7962 | 7.41 | -2.4962 | -2.4962 | 1.7962 | 0.99623 | 0.8 | 4.7925 | Open cut | 0 | 0.99621 | 0.8 | 3.2 | 0 | 2.4525 | 0.22707 | 0.23346 | 0.18736 | 0.18729 | 3.497 | 3.4969
UG-07A | UG-07A-S02 | P0033 | 1.005 | 1.2 | -2.4962 | -2.496 | -0.7962 | -0.79603 | 7.03 | -2.4962 | -2.4961 | 1.7961 | 0.9962 | 0.8 | 4.7924 | Open cut | 0 | 0.99611 | 0.8 | 3.2 | 0 | 11.9389 | 1.1055 | 1.1366 | 0.18729 | 0.18696 | 3.4969 | 3.4966
UG-07A | UG-07A-S02 | P0034 | 1.005 | 1.2 | -2.496 | -2.4959 | -0.79603 | -0.79587 | 6.6 | -2.496 | -2.496 | 1.796 | 0.99603 | 0.8 | 4.7921 | Open cut | 0 | 0.99595 | 0.8 | 3.2 | 0 | 11.9373 | 1.1055 | 1.1366 | 0.18695 | 0.18664 | 3.4966 | 3.4963
UG-07A | UG-07A-S02 | P0095-01 | 7.7836 | 1.2 | -2.4959 | -2.4946 | -0.79587 | -0.79461 | 4.07 | -2.4959 | -2.4952 | 1.7952 | 0.99587 | 0.8 | 4.7917 | Shoring | 7.7836 | 0.99524 | 0.8 | 3.2 | 44.715 | 0 | 8.5619 | 8.8031 | 0.18664 | 0.18419 | 3.4963 | 3.4938
UG-07A | UG-07A-S02 | P0095-02 | 10 | 1.2 | -2.4946 | -2.493 | -0.79461 | -0.793 | 3.26 | -2.4946 | -2.4938 | 1.7938 | 0.99461 | 0.8 | 4.7892 | Shoring | 10 | 0.99381 | 0.8 | 3.2 | 57.4018 | 0 | 11 | 11.3098 | 0.18419 | 0.18105 | 3.4938 | 3.4907
UG-07A | UG-07A-S02 | P0095-03 | 10 | 1.2 | -2.493 | -2.4914 | -0.793 | -0.79138 | 3.37 | -2.493 | -2.4922 | 1.7922 | 0.993 | 0.8 | 4.786 | Shoring | 10 | 0.99219 | 0.8 | 3.2 | 57.3501 | 0 | 11 | 11.3098 | 0.18105 | 0.17791 | 3.4907 | 3.4875
UG-07A | UG-07A-S02 | P0095-04 | 6.5138 | 1.2 | -2.4914 | -2.4903 | -0.79138 | -0.79033 | 5.68 | -2.4914 | -2.4909 | 1.7909 | 0.99138 | 0.8 | 4.7828 | Open cut | 0 | 0.99086 | 0.8 | 3.2 | 0 | 77.0261 | 7.1652 | 7.3669 | 0.17791 | 0.17586 | 3.4875 | 3.4855
UG-07A | UG-07A-S02 | P0470 | 1.0051 | 1.2 | -2.4903 | -2.4902 | -0.79033 | -0.79016 | 6.57 | -2.4903 | -2.4902 | 1.7902 | 0.99033 | 0.8 | 4.7807 | Open cut | 0 | 0.99025 | 0.8 | 3.2 | 0 | 11.879 | 1.1056 | 1.1367 | 0.17586 | 0.17553 | 3.4855 | 3.4852
UG-07A | UG-07A-S02 | P0471 | 1.0049 | 1.2 | -2.4902 | -2.49 | -0.79016 | -0.79 | 6.57 | -2.4902 | -2.4901 | 1.7901 | 0.99016 | 0.8 | 4.7803 | Open cut | 0 | 0.99008 | 0.8 | 3.2 | 0 | 11.8743 | 1.1053 | 1.1364 | 0.17553 | 0.17522 | 3.4852 | 3.4849
UG-07A | UG-07A-S02 | P0238-01 | 1.4763 | 1.2 | -2.49 | -2.49 | -0.79 | -0.79 | 7.15 | -2.49 | -2.49 | 1.79 | 0.99 | 0.8 | 4.78 | Open cut | 0 | 0.99 | 0.8 | 3.2 | 0 | 17.4437 | 1.6239 | 1.6696 | 0.17522 | 0.17522 | 3.4849 | 3.4849
UG-07A | UG-07A-S02 | P0238-02 | 10 | 1.2 | -2.49 | -2.49 | -0.79 | -0.79 | 8.13 | -2.49 | -2.49 | 1.79 | 0.99 | 0.8 | 4.78 | Open cut | 0 | 0.99 | 0.8 | 3.2 | 0 | 118.1616 | 11 | 11.3096 | 0.17522 | 0.17522 | 3.4849 | 3.4849
UG-07A | UG-07A-S02 | P0238-03 | 10 | 1.2 | -2.49 | -2.49 | -0.79 | -0.79 | 8.34 | -2.49 | -2.49 | 1.79 | 0.99 | 0.8 | 4.78 | Open cut | 0 | 0.99 | 0.8 | 3.2 | 0 | 118.1616 | 11 | 11.3096 | 0.17522 | 0.17522 | 3.4849 | 3.4849
UG-07A | UG-07A-S02 | P0238-04 | 6.6334 | 1.2 | -2.49 | -2.49 | -0.79 | -0.79 | 3.69 | -2.49 | -2.49 | 1.79 | 0.99 | 0.8 | 4.78 | Shoring | 6.6334 | 0.99 | 0.8 | 3.2 | 37.9962 | 0 | 7.2968 | 7.5022 | 0.17522 | 0.17522 | 3.4849 | 3.4849
UG-07A | UG-07A-S02 | P0473 | 0.96327 | 1.2 | -2.49 | -2.49 | -0.79 | -0.79 | 2.99 | -2.49 | -2.49 | 1.79 | 0.99 | 0.8 | 4.78 | Shoring | 0.96327 | 0.99 | 0.8 | 3.2 | 5.5176 | 0 | 1.0596 | 1.0894 | 0.17522 | 0.17522 | 3.4849 | 3.4849
UG-07A | UG-07A-S02 | P0472 | 1.0349 | 1.2 | -2.49 | -2.49 | -0.79 | -0.79 | 2.94 | -2.49 | -2.49 | 1.79 | 0.99 | 0.8 | 4.78 | Shoring | 1.0349 | 0.99 | 0.8 | 3.2 | 5.9281 | 0 | 1.1384 | 1.1705 | 0.17521 | 0.17521 | 3.4848 | 3.4848
UG-07A | UG-07A-S02 | P0237-01 | 1.3684 | 1.2 | -2.49 | -2.4903 | -0.79 | -0.79029 | 2.86 | -2.4903 | -2.4901 | 1.7901 | 0.9903 | 0.8 | 4.7806 | Shoring | 1.3684 | 0.99015 | 0.8 | 3.2 | 7.8386 | 0 | 1.5052 | 1.5476 | 0.17521 | 0.17579 | 3.4848 | 3.4854
UG-07A | UG-07A-S02 | P0237-02 | 10 | 1.2 | -2.4903 | -2.4925 | -0.79029 | -0.79245 | 2.34 | -2.4925 | -2.4914 | 1.7914 | 0.99245 | 0.8 | 4.7849 | Shoring | 10 | 0.99137 | 0.8 | 3.2 | 57.324 | 0 | 11 | 11.3098 | 0.17579 | 0.17998 | 3.4854 | 3.4896
UG-07A | UG-07A-S02 | P0237-03 | 10 | 1.2 | -2.4925 | -2.4946 | -0.79245 | -0.7946 | 1.91 | -2.4946 | -2.4935 | 1.7935 | 0.99461 | 0.8 | 4.7892 | Shoring | 10 | 0.99353 | 0.8 | 3.2 | 57.3929 | 0 | 11 | 11.3098 | 0.17998 | 0.18418 | 3.4896 | 3.4938
UG-07A | UG-07A-S02 | P0237-04 | 10 | 1.2 | -2.4946 | -2.4968 | -0.7946 | -0.79676 | 2.55 | -2.4968 | -2.4957 | 1.7957 | 0.99676 | 0.8 | 4.7935 | Shoring | 10 | 0.99568 | 0.8 | 3.2 | 57.4619 | 0 | 11 | 11.3098 | 0.18418 | 0.18837 | 3.4938 | 3.498
UG-07A | UG-07A-S02 | P0237-05 | 1.3531 | 1.2 | -2.4968 | -2.4971 | -0.79676 | -0.79705 | 11.84 | -2.4971 | -2.4969 | 1.7969 | 0.99705 | 0.8 | 4.7941 | Open cut | 0 | 0.99691 | 0.8 | 3.2 | 0 | 16.085 | 1.4884 | 1.5303 | 0.18837 | 0.18894 | 3.498 | 3.4986
UG-07A | UG-07A-S02 | P0094 | 0.21 | 1.2 | -2.497 | -2.4971 | -0.79706 | -0.7971 | 13.18 | -2.4971 | -2.4971 | 1.7971 | 0.99708 | 0.8 | 4.7942 | Open cut | 0 | 0.99706 | 0.8 | 3.2 | 0 | 2.4968 | 0.231 | 0.2375 | 0.18896 | 0.18903 | 3.4986 | 3.4987
UG-07A | UG-07A-S02 | P0093 | 0.2 | 1.4 | -2.5971 | -2.5971 | -0.6971 | -0.69715 | 13.39 | -2.5971 | -2.5971 | 1.8971 | 1.0971 | 0.8 | 5.0943 | Open cut | 0 | 1.0971 | 0.8 | 3.4 | 0 | 2.6656 | 0.24 | 0.30787 | 0 | 0 | 2.832 | 2.8321
UG-07A | UG-07A-S02 | P0207-01 | 8.2369 | 1.6 | -2.6971 | -2.6989 | -0.59714 | -0.59891 | 13.58 | -2.6989 | -2.698 | 1.998 | 1.1989 | 0.8 | 5.3978 | Open cut | 0 | 1.198 | 0.8 | 3.6 | 0 | 122.377 | 10.708 | 16.5614 | 0 | 0 | 2.332 | 2.3346
UG-07A | UG-07A-S02 | P0207-02 | 1.0736 | 1.6 | -2.6989 | -2.6991 | -0.59891 | -0.59914 | 21.77 | -2.6991 | -2.699 | 1.999 | 1.1991 | 0.8 | 5.3983 | Open cut | 0 | 1.199 | 0.8 | 3.6 | 0 | 15.9636 | 1.3957 | 2.1587 | 0 | 0 | 2.3346 | 2.335
UG-07A | UG-07A-S03 | P0784-01 | 6.1264 | 1.6 | -2.6991 | -2.6983 | -0.59914 | -0.59831 | 17.11 | -2.6991 | -2.6987 | 1.9987 | 1.1991 | 0.8 | 5.3983 | Open cut | 0 | 1.1987 | 0.8 | 3.6 | 0 | 91.0697 | 7.9643 | 12.3178 | 0 | 0 | 2.335 | 2.3337
UG-07A | UG-07A-S04 | P0784-02 | 2.8 | 1.6 | -2.6983 | -2.6979 | -0.59831 | -0.59793 | 14.45 | -2.6983 | -2.6981 | 1.9981 | 1.1983 | 0.8 | 5.3966 | Open cut | 0 | 1.1981 | 0.8 | 3.6 | 0 | 41.603 | 3.64 | 5.6297 | 0 | 0 | 2.3337 | 2.3332
UG-07A | UG-07A-S04 | P0784-03 | 10 | 1.6 | -2.6979 | -2.6966 | -0.59793 | -0.59658 | 4.77 | -2.6979 | -2.6973 | 1.9973 | 1.1979 | 0.8 | 5.3959 | Shoring | 10 | 1.1973 | 0.8 | 3.6 | 71.9012 | 0 | 13 | 20.1062 | 0 | 0 | 2.3332 | 2.3312
UG-07A | UG-07A-S04 | P0784-04 | 10 | 1.6 | -2.6966 | -2.6952 | -0.59658 | -0.59522 | 0 | -2.6966 | -2.6959 | 1.9959 | 1.1966 | 0.8 | 5.3932 | Shoring | 10 | 1.1959 | 0.8 | 3.6 | 71.8525 | 0 | 13 | 20.1062 | 0 | 0 | 2.3312 | 2.3292
UG-07A | UG-07A-S04 | P0784-05 | 10 | 1.6 | -2.6952 | -2.6939 | -0.59522 | -0.59387 | 3.6 | -2.6952 | -2.6945 | 1.9945 | 1.1952 | 0.8 | 5.3904 | Shoring | 10 | 1.1945 | 0.8 | 3.6 | 71.8037 | 0 | 13 | 20.1062 | 0 | 0 | 2.3292 | 2.3273
UG-07A | UG-07A-S04 | P0784-06 | 0.88438 | 1.6 | -2.6939 | -2.6938 | -0.59387 | -0.59375 | 8.35 | -2.6939 | -2.6938 | 1.9938 | 1.1939 | 0.8 | 5.3877 | Open cut | 0 | 1.1938 | 0.8 | 3.6 | 0 | 13.0961 | 1.1497 | 1.7782 | 0 | 0 | 2.3273 | 2.3271
UG-07A | UG-07A-S04 | P0092-01 | 9.1156 | 1.6 | -2.6937 | -2.6925 | -0.59375 | -0.59252 | 8.43 | -2.6937 | -2.6931 | 1.9931 | 1.1937 | 0.8 | 5.3875 | Open cut | 0 | 1.1931 | 0.8 | 3.6 | 0 | 134.915 | 11.8503 | 18.328 | 0 | 0 | 2.3271 | 2.3253
UG-07A | UG-07A-S04 | P0092-02 | 10 | 1.6 | -2.6925 | -2.6912 | -0.59252 | -0.59117 | 10.38 | -2.6925 | -2.6918 | 1.9918 | 1.1925 | 0.8 | 5.385 | Open cut | 0 | 1.1918 | 0.8 | 3.6 | 0 | 147.8547 | 13 | 20.1061 | 0 | 0 | 2.3253 | 2.3233
UG-07A | UG-07A-S04 | P0092-03 | 8.6128 | 1.6 | -2.6912 | -2.69 | -0.59117 | -0.59 | 9.91 | -2.6912 | -2.6906 | 1.9906 | 1.1912 | 0.8 | 5.3823 | Open cut | 0 | 1.1906 | 0.8 | 3.6 | 0 | 127.2186 | 11.1966 | 17.317 | 0 | 0 | 2.3233 | 2.3216
UG-07A | UG-07A-S04 | P0540-01 | 1.3872 | 1.6 | -2.69 | -2.706 | -0.59 | -0.60603 | 8.52 | -2.706 | -2.698 | 1.998 | 1.206 | 0.8 | 5.4121 | Open cut | 0 | 1.198 | 0.8 | 3.6 | 0 | 20.6099 | 1.8034 | 2.7892 | 0 | 0 | 2.3216 | 2.345
UG-07A | UG-07A-S04 | P0540-02 | 1.0628 | 1.6 | -2.706 | -2.7183 | -0.60603 | -0.61831 | 7.47 | -2.7183 | -2.7122 | 2.0122 | 1.2183 | 0.8 | 5.4366 | Open cut | 0 | 1.2122 | 0.8 | 3.6 | 0 | 15.9647 | 1.3816 | 2.1369 | 0 | 0 | 2.345 | 2.363
UG-07A | UG-07A-S04 | P0541-01 | 1.2372 | 1.6 | -2.7183 | -2.7326 | -0.61831 | -0.63261 | 7.47 | -2.7326 | -2.7255 | 2.0255 | 1.2326 | 0.8 | 5.4652 | Open cut | 0 | 1.2255 | 0.8 | 3.6 | 0 | 18.7766 | 1.6084 | 2.4876 | 0 | 0 | 2.363 | 2.3838
UG-07A | UG-07A-S05 | P0541-02 | 1.2126 | 1.6 | -2.7326 | -2.7466 | -0.63261 | -0.64662 | 7.63 | -2.7466 | -2.7396 | 2.0396 | 1.2466 | 0.8 | 5.4932 | Open cut | 0 | 1.2396 | 0.8 | 3.6 | 0 | 18.6042 | 1.5764 | 2.438 | 0 | 0 | 2.3838 | 2.4043
UG-07A | UG-07A-S05 | P0236-01 | 6.4874 | 1.6 | -2.7466 | -2.8216 | -0.64662 | -0.72159 | 7.97 | -2.8216 | -2.7841 | 2.0841 | 1.3216 | 0.8 | 5.6432 | Open cut | 0 | 1.2841 | 0.8 | 3.6 | 0 | 102.9538 | 8.4336 | 13.0437 | 0 | 0.031527 | 2.4043 | 2.5138
UG-07A | UG-07A-S05 | P0236-02 | 10 | 1.6 | -2.8216 | -2.9372 | -0.72159 | -0.83716 | 10.38 | -2.9372 | -2.8794 | 2.1794 | 1.4372 | 0.8 | 5.8743 | Open cut | 0 | 1.3794 | 0.8 | 3.6 | 0 | 170.2507 | 13 | 20.1062 | 0.031527 | 0.20027 | 2.5138 | 2.6825
UG-07A | UG-07A-S05 | P0236-03 | 2.6863 | 1.6 | -2.9372 | -2.9682 | -0.83716 | -0.8682 | 9.34 | -2.9682 | -2.9527 | 2.2527 | 1.4682 | 0.8 | 5.9364 | Open cut | 0 | 1.4527 | 0.8 | 3.6 | 0 | 48.1894 | 3.4922 | 5.4012 | 0.20027 | 0.2456 | 2.6825 | 2.7278
UG-07A | UG-07A-S05 | P0398 | 0.655 | 1.6 | -2.9682 | -2.9758 | -0.8682 | -0.87577 | 9.11 | -2.9758 | -2.972 | 2.272 | 1.4758 | 0.8 | 5.9515 | Open cut | 0 | 1.472 | 0.8 | 3.6 | 0 | 11.9099 | 0.8515 | 1.317 | 0.2456 | 0.25665 | 2.7278 | 2.7389
UG-07A | UG-07A-S05 | P0235 | 2 | 1.6552 | -3.0034 | -3.0265 | -0.84817 | -0.87129 | 8.47 | -3.0265 | -3.0149 | 2.3149 | 1.5265 | 0.8 | 6.0806 | Open cut | 0 | 1.5149 | 0.8 | 3.6552 | 0 | 37.7187 | 2.6552 | 4.3035 | 0.20913 | 0.24176 | 2.6086 | 2.6412
UG-07A | UG-07A-S06 | P0041 | 5.1538 | 1.2 | -2.5 | -2.5 | -0.8 | -0.8 | 19.07 | -2.5 | -2.5 | 1.8 | 1 | 0.8 | 4.8 | Open cut | 0 | 1 | 0.8 | 3.2 | 0 | 61.4331 | 5.6692 | 5.8288 | 0.19468 | 0.19468 | 3.5043 | 3.5043
UG-07A | UG-07A-S06 | P0523 | 0.10201 | 1.2 | -2.5 | -2.5 | -0.8 | -0.8 | 19.02 | -2.5 | -2.5 | 1.8 | 1 | 0.8 | 4.8 | Open cut | 0 | 1 | 0.8 | 3.2 | 0 | 1.216 | 0.11221 | 0.11537 | 0.19468 | 0.19468 | 3.5043 | 3.5043
UG-07A | UG-07A-S06 | P0524 | 0.10196 | 1.2 | -2.5 | -2.5 | -0.8 | -0.8 | 18.97 | -2.5 | -2.5 | 1.8 | 1 | 0.8 | 4.8 | Open cut | 0 | 1 | 0.8 | 3.2 | 0 | 1.2154 | 0.11216 | 0.11532 | 0.19468 | 0.19468 | 3.5043 | 3.5043
UG-07A | UG-07A-S07 | P0204-01 | 4.6422 | 1.2 | -2.5 | -2.5 | -0.8 | -0.8 | 17.61 | -2.5 | -2.5 | 1.8 | 1 | 0.8 | 4.8 | Open cut | 0 | 1 | 0.8 | 3.2 | 0 | 55.3354 | 5.1065 | 5.2502 | 0.19469 | 0.19469 | 3.5043 | 3.5043
UG-07A | UG-07A-S07 | P0204-02 | 5.3861 | 1.2 | -2.5 | -2.5 | -0.8 | -0.8 | 17.35 | -2.5 | -2.5 | 1.8 | 1 | 0.8 | 4.8 | Open cut | 0 | 1 | 0.8 | 3.2 | 0 | 64.2018 | 5.9247 | 6.0915 | 0.19469 | 0.19469 | 3.5043 | 3.5043
UG-07A | UG-07A-S07 | P0203-01 | 4.6139 | 1.2 | -2.5 | -2.5 | -0.8 | -0.8 | 12.32 | -2.5 | -2.5 | 1.8 | 1 | 0.8 | 4.8 | Open cut | 0 | 1 | 0.8 | 3.2 | 0 | 54.9981 | 5.0753 | 5.2182 | 0.19468 | 0.19468 | 3.5043 | 3.5043
UG-07A | UG-07A-S07 | P0203-02 | 4.619 | 1.2 | -2.5 | -2.5 | -0.8 | -0.8 | 16.89 | -2.5 | -2.5 | 1.8 | 1 | 0.8 | 4.8 | Open cut | 0 | 1 | 0.8 | 3.2 | 0 | 55.0583 | 5.0809 | 5.224 | 0.19468 | 0.19468 | 3.5043 | 3.5043
UG-07A | UG-07A-S07 | P0384 | 0.17 | 1.2 | -2.5 | -2.5 | -0.8 | -0.8 | 20.82 | -2.5 | -2.5 | 1.8 | 1 | 0.8 | 4.8 | Open cut | 0 | 1 | 0.8 | 3.2 | 0 | 2.0264 | 0.187 | 0.19227 | 0.19468 | 0.19468 | 3.5043 | 3.5043
UG-07A | UG-07A-S07 | P0250 | 0.62936 | 1.2 | -2.5 | -2.5 | -0.8 | -0.8 | 20.91 | -2.5 | -2.5 | 1.8 | 1 | 0.8 | 4.8 | Open cut | 0 | 1 | 0.8 | 3.2 | 0 | 7.502 | 0.6923 | 0.71179 | 0.19468 | 0.19468 | 3.5043 | 3.5043
UG-07A | UG-07A-S07 | P0251 | 2.4486 | 1.2 | -2.5 | -2.4991 | -0.8 | -0.79914 | 21.27 | -2.5 | -2.4996 | 1.7996 | 1 | 0.8 | 4.8 | Open cut | 0 | 0.99957 | 0.8 | 3.2 | 0 | 29.1767 | 2.6935 | 2.7693 | 0.19469 | 0.19301 | 3.5043 | 3.5027
UG-07A | UG-07A-S05 | P0091 | 0.45 | 1.6 | -2.9682 | -2.9682 | -0.8682 | -0.8682 | 9.18 | -2.9682 | -2.9682 | 2.2682 | 1.4682 | 0.8 | 5.9364 | Open cut | 0 | 1.4682 | 0.8 | 3.6 | 0 | 8.1607 | 0.585 | 0.90478 | 0.2456 | 0.2456 | 2.7278 | 2.7278
UG-07A | UG-07A-S08 | P0046 | 2.8061 | 1.2 | -2.969 | -2.969 | -1.269 | -1.269 | 99 | -2.969 | -2.969 | 2.269 | 1.469 | 0.8 | 5.738 | Open cut | 0 | 1.469 | 0.8 | 3.2 | 0 | 48.3706 | 3.0867 | 3.1736 | 1.1078 | 1.1078 | 4.4175 | 4.4175
UG-07A | UG-07A-S08 | P0629 | 0.094613 | 1.2 | -2.969 | -2.969 | -1.269 | -1.269 | 99 | -2.969 | -2.969 | 2.269 | 1.469 | 0.8 | 5.738 | Open cut | 0 | 1.469 | 0.8 | 3.2 | 0 | 1.6309 | 0.10407 | 0.107 | 1.1078 | 1.1078 | 4.4175 | 4.4175
UG-07A | UG-07A-S09 | P0231 | 6.0561 | 1.2 | -2.969 | -2.969 | -1.269 | -1.269 | 22.06 | -2.969 | -2.969 | 2.269 | 1.469 | 0.8 | 5.7381 | Open cut | 0 | 1.469 | 0.8 | 3.2 | 0 | 104.3946 | 6.6617 | 6.8494 | 1.1078 | 1.1078 | 4.4174 | 4.4174
UG-07A | UG-07A-S09 | P0393 | 0.17365 | 1.2 | -2.969 | -2.969 | -1.269 | -1.269 | 21.9 | -2.969 | -2.969 | 2.269 | 1.469 | 0.8 | 5.7381 | Open cut | 0 | 1.469 | 0.8 | 3.2 | 0 | 2.9933 | 0.19101 | 0.19639 | 1.1078 | 1.1078 | 4.4174 | 4.4174
UG-07A | UG-07A-S09 | P0297-01 | 0.86958 | 1.2259 | -2.982 | -2.982 | -1.2561 | -1.2561 | 21.05 | -2.982 | -2.982 | 2.282 | 1.482 | 0.8 | 5.7769 | Open cut | 0 | 1.482 | 0.8 | 3.2259 | 0 | 15.1794 | 0.96779 | 1.0263 | 1.0598 | 1.0598 | 4.2996 | 4.2996
UG-07A | UG-07A-S09 | P0297-02 | 5.0663 | 1.2259 | -2.982 | -2.982 | -1.2561 | -1.2561 | 16.2 | -2.982 | -2.982 | 2.282 | 1.482 | 0.8 | 5.7769 | Open cut | 0 | 1.482 | 0.8 | 3.2259 | 0 | 88.4379 | 5.6385 | 5.9796 | 1.0598 | 1.0598 | 4.2996 | 4.2996
UG-07A | UG-07A-S08 | P0628 | 0.031716 | 1.2 | -2.969 | -2.969 | -1.269 | -1.269 | 99 | -2.969 | -2.969 | 2.269 | 1.469 | 0.8 | 5.738 | Open cut | 0 | 1.469 | 0.8 | 3.2 | 0 | 0.54671 | 0.034887 | 0.035869 | 1.1078 | 1.1078 | 4.4175 | 4.4175
UG-07A | UG-07A-S10 | P0357 | 8.8102 | 1.2 | -2.7 | -2.7 | -1 | -1 | 28.8 | -2.7 | -2.7 | 2 | 1.2 | 0.8 | 5.2 | Open cut | 0 | 1.2 | 0.8 | 3.2 | 0 | 124.0473 | 9.6912 | 9.964 | 0.58406 | 0.58406 | 3.8937 | 3.8937
UG-07A | UG-07A-S10 | P0740 | 0.48972 | 1.2 | -2.7 | -2.892 | -1 | -1.1921 | 28.69 | -2.892 | -2.796 | 2.096 | 1.392 | 0.8 | 5.5841 | Open cut | 0 | 1.296 | 0.8 | 3.2 | 0 | 7.4309 | 0.53869 | 0.55386 | 0.58406 | 0.95795 | 3.8937 | 4.2676
UG-07A | UG-07A-S11 | P0298-01 | 0.70007 | 1.2 | -2.892 | -3.1666 | -1.1921 | -1.4666 | 28.53 | -3.1666 | -3.0293 | 2.3293 | 1.6666 | 0.8 | 6.1332 | Open cut | 0 | 1.5293 | 0.8 | 3.2 | 0 | 12.591 | 0.77008 | 0.79175 | 0.95796 | 1.4925 | 4.2676 | 4.8021
UG-07A | UG-07A-S11 | P0298-02 | 0.59602 | 1.2 | -3.1666 | -3.4003 | -1.4666 | -1.7003 | 28.41 | -3.4003 | -3.2835 | 2.5835 | 1.9003 | 0.8 | 6.6006 | Open cut | 0 | 1.7835 | 0.8 | 3.2 | 0 | 12.6925 | 0.65562 | 0.67407 | 1.4925 | 1.7349 | 4.8021 | 5.0446
UG-07A | UG-07A-S11 | P0738 | 1.6421 | 1.2 | -3.4003 | -4.0443 | -1.7003 | -2.3443 | 28.15 | -4.0443 | -3.7223 | 3.0223 | 2.5443 | 0.8 | 7.8886 | Shoring | 1.6421 | 2.2223 | 0.8 | 3.2 | 15.8813 | 0 | 1.8063 | 1.8571 | 1.7349 | 2.3054 | 5.0446 | 5.6151
UG-07A | UG-07A-S11 | P0739 | 1.978 | 1.2 | -4.0443 | -4.82 | -2.3443 | -3.12 | 26.19 | -4.82 | -4.4322 | 3.7322 | 3.32 | 0.8 | 9.44 | Shoring | 1.978 | 2.9322 | 0.8 | 3.2 | 23.6231 | 0 | 2.1758 | 2.2371 | 2.3054 | 2.9925 | 5.615 | 6.3021
UG-07A | UG-07A-S11 | P0299-01 | 5.7839 | 1.2 | -4.82 | -4.8067 | -3.12 | -3.1067 | 20.48 | -4.82 | -4.8134 | 4.1134 | 3.32 | 0.8 | 9.44 | Shoring | 5.7839 | 3.3134 | 0.8 | 3.2 | 76.132 | 0 | 6.3623 | 6.5415 | 2.9925 | 2.9807 | 6.3021 | 6.2904
UG-07A | UG-07A-S11 | P0299-02 | 10 | 1.2 | -4.8067 | -4.7838 | -3.1067 | -3.0838 | 10.8 | -4.8067 | -4.7952 | 4.0952 | 3.3067 | 0.8 | 9.4134 | Shoring | 10 | 3.2952 | 0.8 | 3.2 | 131.048 | 0 | 11 | 11.3098 | 2.9807 | 2.9604 | 6.2904 | 6.27
UG-07A | UG-07A-S11 | P0299-03 | 10 | 1.2 | -4.7838 | -4.7608 | -3.0838 | -3.0608 | 2.09 | -4.7838 | -4.7723 | 4.0723 | 3.2838 | 0.8 | 9.3675 | Shoring | 10 | 3.2723 | 0.8 | 3.2 | 130.3134 | 0 | 11 | 11.3098 | 2.9604 | 2.9401 | 6.27 | 6.2497
UG-07A | UG-07A-S11 | P0299-04 | 10 | 1.2 | -4.7608 | -4.7379 | -3.0608 | -3.0379 | 0 | -4.7608 | -4.7493 | 4.0493 | 3.2608 | 0.8 | 9.3216 | Shoring | 10 | 3.2493 | 0.8 | 3.2 | 129.5788 | 0 | 11 | 11.3098 | 2.9401 | 2.9197 | 6.2497 | 6.2294
UG-07A | UG-07A-S11 | P0299-05 | 0.1 | 1.2 | -4.7379 | -4.7376 | -3.0379 | -3.0376 | 4.79 | -4.7379 | -4.7377 | 4.0377 | 3.2379 | 0.8 | 9.2757 | Shoring | 0.1 | 3.2377 | 0.8 | 3.2 | 1.2921 | 0 | 0.11 | 0.1131 | 2.9197 | 2.9195 | 6.2294 | 6.2292
UG-07A | UG-07A-S12 | P0299-06 | 9.9 | 1.2 | -4.7376 | -4.7149 | -3.0376 | -3.0149 | 4.89 | -4.7376 | -4.7263 | 4.0263 | 3.2376 | 0.8 | 9.2752 | Shoring | 9.9 | 3.2263 | 0.8 | 3.2 | 127.5521 | 0 | 10.89 | 11.1967 | 2.9195 | 2.8994 | 6.2292 | 6.209
UG-07A | UG-07A-S12 | P0299-07 | 6.4884 | 1.2 | -4.7149 | -4.7 | -3.0149 | -3 | 14.74 | -4.7149 | -4.7074 | 4.0074 | 3.2149 | 0.8 | 9.2298 | Shoring | 6.4884 | 3.2074 | 0.8 | 3.2 | 83.206 | 0 | 7.1372 | 7.3382 | 2.8994 | 2.8862 | 6.209 | 6.1958
UG-07A | UG-07A-S12 | P0632 | 1.0001 | 1.2 | -4.7 | -4.6301 | -3 | -2.9301 | 16.15 | -4.7 | -4.6651 | 3.9651 | 3.2 | 0.8 | 9.2 | Shoring | 1.0001 | 3.1651 | 0.8 | 3.2 | 12.6895 | 0 | 1.1001 | 1.1311 | 2.8862 | 2.8243 | 6.1958 | 6.1339
UG-07A | UG-07A-S12 | P0631 | 1.0132 | 1.2 | -4.6301 | -4.5594 | -2.9301 | -2.8594 | 16.15 | -4.6301 | -4.5947 | 3.8947 | 3.1301 | 0.8 | 9.0603 | Shoring | 1.0132 | 3.0947 | 0.8 | 3.2 | 12.6275 | 0 | 1.1145 | 1.1459 | 2.8244 | 2.7617 | 6.134 | 6.0713
UG-07A | UG-07A-S12 | P0057-01 | 1.4983 | 1.2 | -4.5594 | -4.4547 | -2.8594 | -2.7547 | 16.61 | -4.5594 | -4.507 | 3.807 | 3.0594 | 0.8 | 8.9187 | Shoring | 1.4983 | 3.007 | 0.8 | 3.2 | 18.2533 | 0 | 1.6482 | 1.6945 | 2.7617 | 2.6689 | 6.0713 | 5.9786
UG-07A | UG-07A-S12 | P0057-02 | 5.6711 | 1.2 | -4.4547 | -4.0585 | -2.7547 | -2.3585 | 16.41 | -4.4547 | -4.2566 | 3.5566 | 2.9547 | 0.8 | 8.7094 | Shoring | 5.6711 | 2.7566 | 0.8 | 3.2 | 64.5435 | 0 | 6.2382 | 6.4138 | 2.6689 | 2.318 | 5.9786 | 5.6277
UG-07A | UG-07A-S12 | P0394 | 0.17501 | 1.2 | -4.0585 | -4.0463 | -2.3585 | -2.3463 | 16.33 | -4.0585 | -4.0524 | 3.3524 | 2.5585 | 0.8 | 7.917 | Shoring | 0.17501 | 2.5524 | 0.8 | 3.2 | 1.8774 | 0 | 0.1925 | 0.19792 | 2.318 | 2.3072 | 5.6277 | 5.6168
UG-07A | UG-07A-S12 | P0239-01 | 4.1539 | 1.2258 | -4.0592 | -3.769 | -2.3334 | -2.0432 | 13.11 | -4.0592 | -3.9141 | 3.2141 | 2.5592 | 0.8 | 7.9313 | Shoring | 4.1539 | 2.4141 | 0.8 | 3.2258 | 43.0674 | 0 | 4.6228 | 4.9021 | 2.2474 | 1.9958 | 5.4874 | 5.2357
UG-07A | UG-07A-S12 | P0239-02 | 2.169 | 1.2258 | -3.769 | -3.6175 | -2.0432 | -1.8917 | 10.95 | -3.769 | -3.6932 | 2.9932 | 2.269 | 0.8 | 7.3509 | Open cut | 0 | 2.1932 | 0.8 | 3.2258 | 0 | 59.1164 | 2.4139 | 2.5597 | 1.9958 | 1.8644 | 5.2357 | 5.1043
UG-12 | UG-12-S01 | P0089 | 0.6 | 2.0412 | -3.0514 | -3.0516 | -0.51017 | -0.51037 | 99 | -3.0516 | -3.0515 | 2.3515 | 1.5516 | 0.8 | 6.3238 | Open cut | 0 | 1.5515 | 0.8 | 4.0412 | 0 | 12.145 | 0.91236 | 1.9634 | 0 | 0 | 1.7284 | 1.7287
UG-12 | UG-12-S01 | P0788-01 | 9.4 | 2.0696 | -3.0658 | -3.0689 | -0.49617 | -0.49931 | 23.53 | -3.0689 | -3.0673 | 2.3673 | 1.5689 | 0.8 | 6.3726 | Open cut | 0 | 1.5673 | 0.8 | 4.0696 | 0 | 192.9135 | 14.4271 | 31.6221 | 0 | 0 | 1.6889 | 1.6925
UG-12 | UG-12-S01 | P0788-02 | 1.4468 | 2.0696 | -3.0689 | -3.0694 | -0.49931 | -0.49979 | 22.78 | -3.0694 | -3.0691 | 2.3691 | 1.5694 | 0.8 | 6.3736 | Open cut | 0 | 1.5691 | 0.8 | 4.0696 | 0 | 29.727 | 2.2205 | 4.867 | 0 | 0 | 1.6925 | 1.693
UG-12 | UG-12-S01 | P0787-01 | 8.5532 | 2.0696 | -3.0694 | -3.0722 | -0.49979 | -0.50265 | 19.01 | -3.0722 | -3.0708 | 2.3708 | 1.5722 | 0.8 | 6.3793 | Open cut | 0 | 1.5708 | 0.8 | 4.0696 | 0 | 175.9389 | 13.1275 | 28.7736 | 0 | 0 | 1.693 | 1.6962
UG-12 | UG-12-S01 | P0787-02 | 10 | 2.0696 | -3.0722 | -3.0756 | -0.50265 | -0.50599 | 16.28 | -3.0756 | -3.0739 | 2.3739 | 1.5756 | 0.8 | 6.386 | Open cut | 0 | 1.5739 | 0.8 | 4.0696 | 0 | 206.119 | 15.348 | 33.6406 | 0 | 0 | 1.6962 | 1.7
UG-12 | UG-12-S01 | P0787-03 | 0.1 | 2.0696 | -3.0756 | -3.0756 | -0.50599 | -0.50602 | 16.26 | -3.0756 | -3.0756 | 2.3756 | 1.5756 | 0.8 | 6.386 | Open cut | 0 | 1.5756 | 0.8 | 4.0696 | 0 | 2.0635 | 0.15348 | 0.33641 | 0 | 0 | 1.7 | 1.7
UG-12 | UG-12-S02 | P0787-04 | 7.5911 | 2.0696 | -3.0756 | -3.0782 | -0.50602 | -0.50856 | 15.61 | -3.0782 | -3.0769 | 2.3769 | 1.5782 | 0.8 | 6.3911 | Open cut | 0 | 1.5769 | 0.8 | 4.0696 | 0 | 156.7733 | 11.6508 | 25.5369 | 0 | 0 | 1.7 | 1.7029
UG-12 | UG-12-S02 | P0255-01 | 2.3089 | 2.0696 | -3.0782 | -3.0789 | -0.50856 | -0.50933 | 15.61 | -3.0789 | -3.0785 | 2.3785 | 1.5789 | 0.8 | 6.3927 | Open cut | 0 | 1.5785 | 0.8 | 4.0696 | 0 | 47.7357 | 3.5437 | 7.7672 | 0 | 0 | 1.7029 | 1.7038
UG-12 | UG-12-S02 | P0255-02 | 6.1 | 2.0696 | -3.0789 | -3.081 | -0.50933 | -0.51137 | 15.67 | -3.081 | -3.0799 | 2.3799 | 1.581 | 0.8 | 6.3967 | Open cut | 0 | 1.5799 | 0.8 | 4.0696 | 0 | 126.232 | 9.3623 | 20.5207 | 0 | 0 | 1.7038 | 1.7061
UG-12 | UG-12-S03 | P0255-03 | 3.9 | 2.0696 | -3.081 | -3.0823 | -0.51137 | -0.51267 | 16.39 | -3.0823 | -3.0816 | 2.3816 | 1.5823 | 0.8 | 6.3993 | Open cut | 0 | 1.5816 | 0.8 | 4.0696 | 0 | 80.7942 | 5.9857 | 13.1198 | 0 | 0 | 1.7061 | 1.7075
UG-12 | UG-12-S03 | P0255-04 | 7.5791 | 2.0696 | -3.0823 | -3.0848 | -0.51267 | -0.5152 | 17.27 | -3.0848 | -3.0835 | 2.3835 | 1.5848 | 0.8 | 6.4044 | Open cut | 0 | 1.5835 | 0.8 | 4.0696 | 0 | 157.2096 | 11.6324 | 25.4965 | 0 | 0 | 1.7075 | 1.7104
UG-12 | UG-12-S03 | P0696 | 0.89963 | 2.0696 | -3.0848 | -3.3826 | -0.5152 | -0.81296 | 19.83 | -3.3826 | -3.2337 | 2.5337 | 1.8826 | 0.8 | 6.9999 | Open cut | 0 | 1.7337 | 0.8 | 4.0696 | 0 | 20.5387 | 1.3808 | 3.0264 | 0 | 0.12751 | 1.7104 | 2.0465
UG-12 | UG-12-S03 | P0695 | 0.83594 | 2.0697 | -3.3826 | -3.6593 | -0.81293 | -1.0896 | 20.2 | -3.6593 | -3.5209 | 2.8209 | 2.1593 | 0.8 | 7.5534 | Open cut | 0 | 2.0209 | 0.8 | 4.0697 | 0 | 22.6335 | 1.283 | 2.8123 | 0.12747 | 0.43979 | 2.0464 | 2.3587
UG-12 | UG-12-S03 | P0254-01 | 0.68533 | 2.0697 | -3.6593 | -3.8861 | -1.0896 | -1.3164 | 20.74 | -3.8861 | -3.7727 | 3.0727 | 2.3861 | 0.8 | 8.007 | Open cut | 0 | 2.2727 | 0.8 | 4.0697 | 0 | 21.2915 | 1.0519 | 2.3056 | 0.43979 | 0.69583 | 2.3587 | 2.6148
UG-12 | UG-12-S03 | P0254-02 | 6.0585 | 2.0697 | -3.8861 | -5.8913 | -1.3164 | -3.3217 | 21.2 | -5.8913 | -4.8887 | 4.1887 | 4.3913 | 0.8 | 12.0175 | Shoring | 6.0585 | 3.3887 | 0.8 | 4.0697 | 103.2776 | 0 | 9.2988 | 20.3824 | 0.69583 | 1.8386 | 2.6148 | 3.7576
UG-12 | UG-12-S03 | P0694 | 0.83307 | 2.0697 | -5.8913 | -6.1671 | -3.3217 | -3.5974 | 99 | -6.1671 | -6.0292 | 5.3292 | 4.6671 | 0.8 | 12.569 | Shoring | 0.83307 | 4.5292 | 0.8 | 4.0697 | 18.0677 | 0 | 1.2786 | 2.8027 | 1.8386 | 1.9803 | 3.7576 | 3.8992
UG-12 | UG-12-S03 | P0693 | 0.89966 | 2.0696 | -6.167 | -6.4648 | -3.5974 | -3.8952 | 99 | -6.4648 | -6.3159 | 5.6159 | 4.9648 | 0.8 | 13.1644 | Shoring | 0.89966 | 4.8159 | 0.8 | 4.0696 | 20.5613 | 0 | 1.3808 | 3.0265 | 1.9803 | 2.1333 | 3.8993 | 4.0523
UG-12 | UG-12-S03 | P0253-01 | 2.2087 | 2.0696 | -6.4648 | -6.4564 | -3.8952 | -3.8868 | 99 | -6.4648 | -6.4606 | 5.7606 | 4.9648 | 0.8 | 13.1644 | Shoring | 2.2087 | 4.9606 | 0.8 | 4.0696 | 51.7807 | 0 | 3.39 | 7.4304 | 2.1333 | 2.129 | 4.0523 | 4.048
UG-12 | UG-12-S03 | P0253-02 | 10 | 2.0696 | -6.4564 | -6.4186 | -3.8868 | -3.849 | 25.85 | -6.4564 | -6.4375 | 5.7375 | 4.9564 | 0.8 | 13.1477 | Shoring | 10 | 4.9375 | 0.8 | 4.0696 | 233.4952 | 0 | 15.348 | 33.6406 | 2.129 | 2.1096 | 4.048 | 4.0286
UG-12 | UG-12-S03 | P0253-03 | 10 | 2.0696 | -6.4186 | -6.3808 | -3.849 | -3.8112 | 21.49 | -6.4186 | -6.3997 | 5.6997 | 4.9186 | 0.8 | 13.0721 | Shoring | 10 | 4.8997 | 0.8 | 4.0696 | 231.9564 | 0 | 15.348 | 33.6406 | 2.1096 | 2.0901 | 4.0286 | 4.0091
UG-12 | UG-12-S03 | P0253-04 | 10 | 2.0696 | -6.3808 | -6.343 | -3.8112 | -3.7734 | 18.86 | -6.3808 | -6.3619 | 5.6619 | 4.8808 | 0.8 | 12.9964 | Shoring | 10 | 4.8619 | 0.8 | 4.0696 | 230.4175 | 0 | 15.348 | 33.6406 | 2.0901 | 2.0707 | 4.0091 | 3.9897
UG-12 | UG-12-S03 | P0253-05 | 1.3 | 2.0696 | -6.343 | -6.3381 | -3.7734 | -3.7685 | 18.66 | -6.343 | -6.3406 | 5.6406 | 4.843 | 0.8 | 12.9208 | Shoring | 1.3 | 4.8406 | 0.8 | 4.0696 | 29.8412 | 0 | 1.9952 | 4.3733 | 2.0707 | 2.0682 | 3.9897 | 3.9872
UG-12 | UG-12-S04 | P0253-06 | 8.7 | 2.0696 | -6.3381 | -6.3052 | -3.7685 | -3.7356 | 18.2 | -6.3381 | -6.3216 | 5.6216 | 4.8381 | 0.8 | 12.911 | Shoring | 8.7 | 4.8216 | 0.8 | 4.0696 | 199.0374 | 0 | 13.3528 | 29.2673 | 2.0682 | 2.0513 | 3.9872 | 3.9703
UG-12 | UG-12-S04 | P0253-07 | 10 | 2.0696 | -6.3052 | -6.2674 | -3.7356 | -3.6978 | 15.97 | -6.3052 | -6.2863 | 5.5863 | 4.8052 | 0.8 | 12.8452 | Shoring | 10 | 4.7863 | 0.8 | 4.0696 | 227.3398 | 0 | 15.348 | 33.6406 | 2.0513 | 2.0319 | 3.9703 | 3.9509
UG-12 | UG-12-S04 | P0253-08 | 10 | 2.0696 | -6.2674 | -6.2296 | -3.6978 | -3.66 | 6.04 | -6.2674 | -6.2485 | 5.5485 | 4.7674 | 0.8 | 12.7696 | Shoring | 10 | 4.7485 | 0.8 | 4.0696 | 225.8009 | 0 | 15.348 | 33.6406 | 2.0319 | 2.0125 | 3.9509 | 3.9315
UG-12 | UG-12-S04 | P0253-09 | 10 | 2.0696 | -6.2296 | -6.1918 | -3.66 | -3.6222 | 0.43 | -6.2296 | -6.2107 | 5.5107 | 4.7296 | 0.8 | 12.6939 | Shoring | 10 | 4.7107 | 0.8 | 4.0696 | 224.2621 | 0 | 15.348 | 33.6406 | 2.0125 | 1.993 | 3.9315 | 3.912
UG-12 | UG-12-S04 | P0253-10 | 3.4 | 2.0696 | -6.1918 | -6.1789 | -3.6222 | -3.6093 | 2.6 | -6.1918 | -6.1853 | 5.4853 | 4.6918 | 0.8 | 12.6183 | Shoring | 3.4 | 4.6853 | 0.8 | 4.0696 | 75.8985 | 0 | 5.2183 | 11.4378 | 1.993 | 1.9864 | 3.912 | 3.9054
UG-12 | UG-12-S05 | P0253-11 | 6.6 | 2.0696 | -6.1789 | -6.1539 | -3.6093 | -3.5843 | 5.44 | -6.1789 | -6.1664 | 5.4664 | 4.6789 | 0.8 | 12.5926 | Shoring | 6.6 | 4.6664 | 0.8 | 4.0696 | 146.8246 | 0 | 10.1297 | 22.2028 | 1.9864 | 1.9736 | 3.9054 | 3.8926
UG-12 | UG-12-S05 | P0253-12 | 9.4647 | 2.0696 | -6.1539 | -6.1182 | -3.5843 | -3.5485 | 10.63 | -6.1539 | -6.136 | 5.436 | 4.6539 | 0.8 | 12.5427 | Shoring | 9.4647 | 4.636 | 0.8 | 4.0696 | 209.3823 | 0 | 14.5264 | 31.8397 | 1.9736 | 1.9552 | 3.8926 | 3.8742
UG-12 | UG-12-S05 | P0692-01 | 0.53535 | 2.0696 | -6.1182 | -6.1161 | -3.5485 | -3.5465 | 16.4 | -6.1182 | -6.1171 | 5.4171 | 4.6182 | 0.8 | 12.4711 | Shoring | 0.53535 | 4.6171 | 0.8 | 4.0696 | 11.8021 | 0 | 0.82165 | 1.8009 | 1.9552 | 1.9542 | 3.8742 | 3.8732
UG-12 | UG-12-S05 | P0692-02 | 2.5645 | 2.0696 | -6.1161 | -6.1064 | -3.5465 | -3.5368 | 16.35 | -6.1161 | -6.1113 | 5.4113 | 4.6161 | 0.8 | 12.4671 | Shoring | 2.5645 | 4.6113 | 0.8 | 4.0696 | 56.4744 | 0 | 3.936 | 8.6271 | 1.9542 | 1.9492 | 3.8732 | 3.8682
UG-12 | UG-12-S05 | P0691 | 3.0744 | 2.0696 | -6.1064 | -6.0948 | -3.5368 | -3.5252 | 14.23 | -6.1064 | -6.1006 | 5.4006 | 4.6064 | 0.8 | 12.4477 | Shoring | 3.0744 | 4.6006 | 0.8 | 4.0696 | 67.5704 | 0 | 4.7186 | 10.3425 | 1.9492 | 1.9432 | 3.8682 | 3.8622
UG-12 | UG-12-S05 | P0252-01 | 1.8611 | 2.0696 | -6.0948 | -6.0682 | -3.5252 | -3.4986 | 13.11 | -6.0948 | -6.0815 | 5.3815 | 4.5948 | 0.8 | 12.4244 | Shoring | 1.8611 | 4.5815 | 0.8 | 4.0696 | 40.7592 | 0 | 2.8564 | 6.2609 | 1.9432 | 1.9296 | 3.8622 | 3.8486
UG-12 | UG-12-S06 | P0252-02 | 2.4724 | 2.0696 | -6.0682 | -6.0328 | -3.4986 | -3.4632 | 11.91 | -6.0682 | -6.0505 | 5.3505 | 4.5682 | 0.8 | 12.3711 | Shoring | 2.4724 | 4.5505 | 0.8 | 4.0696 | 53.8344 | 0 | 3.7946 | 8.3172 | 1.9296 | 1.9114 | 3.8486 | 3.8304
UG-12 | UG-12-S06 | P0690 | 3.0807 | 2.0696 | -6.0328 | -5.9887 | -3.4632 | -3.4191 | 11.02 | -6.0328 | -6.0107 | 5.3107 | 4.5328 | 0.8 | 12.3003 | Shoring | 3.0807 | 4.5107 | 0.8 | 4.0696 | 66.5823 | 0 | 4.7283 | 10.3637 | 1.9114 | 1.8887 | 3.8304 | 3.8077
UG-12 | UG-12-S06 | P0689 | 3.1 | 2.0696 | -5.9887 | -5.9443 | -3.4191 | -3.3747 | 8.69 | -5.9887 | -5.9665 | 5.2665 | 4.4887 | 0.8 | 12.2122 | Shoring | 3.1 | 4.4665 | 0.8 | 4.0696 | 66.4409 | 0 | 4.7579 | 10.4286 | 1.8887 | 1.8659 | 3.8077 | 3.7849
UG-12 | UG-12-S06 | P0209-01 | 3.8469 | 2.0696 | -5.9443 | -5.8892 | -3.3747 | -3.3196 | 6.74 | -5.9443 | -5.9168 | 5.2168 | 4.4443 | 0.8 | 12.1234 | Shoring | 3.8469 | 4.4168 | 0.8 | 4.0696 | 81.6696 | 0 | 5.9042 | 12.941 | 1.8659 | 1.8377 | 3.7849 | 3.7567
UG-12 | UG-12-S06 | P0209-02 | 10 | 2.0696 | -5.8892 | -5.7461 | -3.3196 | -3.1765 | 6.44 | -5.8892 | -5.8177 | 5.1177 | 4.3892 | 0.8 | 12.0133 | Shoring | 10 | 4.3177 | 0.8 | 4.0696 | 208.2685 | 0 | 15.348 | 33.6404 | 1.8377 | 1.7641 | 3.7567 | 3.6832
UG-12 | UG-12-S06 | P0209-03 | 10 | 2.0696 | -5.7461 | -5.603 | -3.1765 | -3.0334 | 6.44 | -5.7461 | -5.6745 | 4.9745 | 4.2461 | 0.8 | 11.727 | Shoring | 10 | 4.1745 | 0.8 | 4.0696 | 202.4435 | 0 | 15.348 | 33.6404 | 1.7641 | 1.6906 | 3.6832 | 3.6096
UG-12 | UG-12-S06 | P0209-04 | 9.6 | 2.0696 | -5.603 | -5.4656 | -3.0334 | -2.896 | 5.57 | -5.603 | -5.5343 | 4.8343 | 4.103 | 0.8 | 11.4407 | Shoring | 9.6 | 4.0343 | 0.8 | 4.0696 | 188.8656 | 0 | 14.7341 | 32.2948 | 1.6906 | 1.6201 | 3.6096 | 3.5391
UG-12 | UG-12-S07 | P0209-05 | 0.4 | 2.0696 | -5.4656 | -5.4598 | -2.896 | -2.8902 | 5.58 | -5.4656 | -5.4627 | 4.7627 | 3.9656 | 0.8 | 11.1659 | Shoring | 0.4 | 3.9627 | 0.8 | 4.0696 | 7.7529 | 0 | 0.61392 | 1.3456 | 1.6201 | 1.6171 | 3.5391 | 3.5361
UG-12 | UG-12-S07 | P0209-06 | 10 | 2.0696 | -5.4598 | -5.3167 | -2.8902 | -2.7471 | 5.58 | -5.4598 | -5.3883 | 4.6883 | 3.9598 | 0.8 | 11.1545 | Shoring | 10 | 3.8883 | 0.8 | 4.0696 | 190.7935 | 0 | 15.348 | 33.6404 | 1.6171 | 1.5436 | 3.5361 | 3.4626
UG-12 | UG-12-S07 | P0209-07 | 6.708 | 2.0696 | -5.3167 | -5.2207 | -2.7471 | -2.6511 | 6.05 | -5.3167 | -5.2687 | 4.5687 | 3.8167 | 0.8 | 10.8682 | Shoring | 6.708 | 3.7687 | 0.8 | 4.0696 | 124.72 | 0 | 10.2954 | 22.566 | 1.5436 | 1.4943 | 3.4626 | 3.4133
UG-12 | UG-12-S08 | P0209-08 | 3.292 | 2.0696 | -5.2207 | -5.1736 | -2.6511 | -2.604 | 6.08 | -5.2207 | -5.1971 | 4.4971 | 3.7207 | 0.8 | 10.6762 | Shoring | 3.292 | 3.6971 | 0.8 | 4.0696 | 60.2485 | 0 | 5.0526 | 11.0744 | 1.4943 | 1.4701 | 3.4133 | 3.3891
UG-12 | UG-12-S08 | P0209-09 | 2.7084 | 2.0696 | -5.1736 | -5.1348 | -2.604 | -2.5652 | 7.18 | -5.1736 | -5.1542 | 4.4542 | 3.6736 | 0.8 | 10.5819 | Shoring | 2.7084 | 3.6542 | 0.8 | 4.0696 | 49.0942 | 0 | 4.1568 | 9.1111 | 1.4701 | 1.4502 | 3.3891 | 3.3692
UG-12A | UG-12A-S01 | P0358-01 | 10 | 1.2 | -2.7 | -2.7 | -1 | -1 | 99 | -2.7 | -2.7 | 2 | 1.2 | 0.8 | 5.2 | Open cut | 0 | 1.2 | 0.8 | 3.2 | 0 | 140.7997 | 11 | 11.3097 | 0.58406 | 0.58406 | 3.8937 | 3.8937
UG-12A | UG-12A-S01 | P0358-02 | 1.2982 | 1.2 | -2.7 | -2.7 | -1 | -1 | 99 | -2.7 | -2.7 | 2 | 1.2 | 0.8 | 5.2 | Open cut | 0 | 1.2 | 0.8 | 3.2 | 0 | 18.2786 | 1.428 | 1.4682 | 0.58406 | 0.58406 | 3.8937 | 3.8937
UG-12A | UG-12A-S01 | P0742 | 1.978 | 1.2 | -2.7 | -2.6979 | -1 | -0.99788 | 99 | -2.7 | -2.6989 | 1.9989 | 1.2 | 0.8 | 5.2 | Open cut | 0 | 1.1989 | 0.8 | 3.2 | 0 | 27.8266 | 2.1758 | 2.237 | 0.58406 | 0.57993 | 3.8937 | 3.8896
UG-12A | UG-12A-S01 | P0741 | 1.978 | 1.2 | -2.6979 | -2.6958 | -0.99788 | -0.99577 | 24.18 | -2.6979 | -2.6968 | 1.9968 | 1.1979 | 0.8 | 5.1958 | Open cut | 0 | 1.1968 | 0.8 | 3.2 | 0 | 27.7799 | 2.1758 | 2.2371 | 0.57993 | 0.57582 | 3.8896 | 3.8855
UG-12A | UG-12A-S02 | P0300-01 | 4.7458 | 1.2 | -2.6958 | -2.6907 | -0.99577 | -0.99069 | 15.11 | -2.6958 | -2.6932 | 1.9932 | 1.1958 | 0.8 | 5.1915 | Open cut | 0 | 1.1932 | 0.8 | 3.2 | 0 | 66.4615 | 5.2204 | 5.3674 | 0.57582 | 0.56593 | 3.8855 | 3.8756
UG-12A | UG-12A-S02 | P0300-02 | 10 | 1.2 | -2.6907 | -2.68 | -0.99069 | -0.97999 | 13.95 | -2.6907 | -2.6853 | 1.9853 | 1.1907 | 0.8 | 5.1814 | Open cut | 0 | 1.1853 | 0.8 | 3.2 | 0 | 139.1624 | 11 | 11.3097 | 0.56593 | 0.5451 | 3.8756 | 3.8547
UG-12A | UG-12A-S02 | P0300-03 | 10 | 1.2 | -2.68 | -2.6693 | -0.97999 | -0.96929 | 8.75 | -2.68 | -2.6746 | 1.9746 | 1.18 | 0.8 | 5.16 | Open cut | 0 | 1.1746 | 0.8 | 3.2 | 0 | 137.9725 | 11 | 11.3097 | 0.5451 | 0.52427 | 3.8547 | 3.8339
UG-12A | UG-12A-S02 | P0300-04 | 10 | 1.2 | -2.6693 | -2.6586 | -0.96929 | -0.95859 | 5.71 | -2.6693 | -2.6639 | 1.9639 | 1.1693 | 0.8 | 5.1386 | Open cut | 0 | 1.1639 | 0.8 | 3.2 | 0 | 136.7871 | 11 | 11.3097 | 0.52427 | 0.50343 | 3.8339 | 3.8131
UG-12A | UG-12A-S02 | P0300-05 | 10 | 1.2 | -2.6586 | -2.6479 | -0.95859 | -0.94789 | 5.19 | -2.6586 | -2.6532 | 1.9532 | 1.1586 | 0.8 | 5.1172 | Open cut | 0 | 1.1532 | 0.8 | 3.2 | 0 | 135.6064 | 11 | 11.3097 | 0.50343 | 0.4826 | 3.8131 | 3.7922
UG-12A | UG-12A-S02 | P0300-06 | 10 | 1.2 | -2.6479 | -2.6372 | -0.94789 | -0.93719 | 5.42 | -2.6479 | -2.6425 | 1.9425 | 1.1479 | 0.8 | 5.0958 | Open cut | 0 | 1.1425 | 0.8 | 3.2 | 0 | 134.4302 | 11 | 11.3097 | 0.4826 | 0.46177 | 3.7922 | 3.7714
UG-12A | UG-12A-S02 | P0300-07 | 6.7162 | 1.2 | -2.6372 | -2.63 | -0.93719 | -0.93 | 7.95 | -2.6372 | -2.6336 | 1.9336 | 1.1372 | 0.8 | 5.0744 | Open cut | 0 | 1.1336 | 0.8 | 3.2 | 0 | 89.6278 | 7.3878 | 7.5958 | 0.46177 | 0.44778 | 3.7714 | 3.7574
UG-12A | UG-12A-S02 | P0634 | 0.99255 | 1.2 | -2.63 | -2.63 | -0.93 | -0.93 | 10.98 | -2.63 | -2.63 | 1.93 | 1.13 | 0.8 | 5.06 | Open cut | 0 | 1.13 | 0.8 | 3.2 | 0 | 13.2067 | 1.0918 | 1.1225 | 0.44778 | 0.44778 | 3.7574 | 3.7574
UG-12A | UG-12A-S02 | P0633 | 1.0227 | 1.2 | -2.63 | -2.63 | -0.93 | -0.93 | 11.28 | -2.63 | -2.63 | 1.93 | 1.13 | 0.8 | 5.06 | Open cut | 0 | 1.13 | 0.8 | 3.2 | 0 | 13.6079 | 1.125 | 1.1567 | 0.44778 | 0.44778 | 3.7574 | 3.7574
UG-12A | UG-12A-S02 | P0064-01 | 1.2686 | 1.2 | -2.63 | -2.63 | -0.93 | -0.93 | 11.04 | -2.63 | -2.63 | 1.93 | 1.13 | 0.8 | 5.06 | Open cut | 0 | 1.13 | 0.8 | 3.2 | 0 | 16.8792 | 1.3954 | 1.4347 | 0.44778 | 0.44778 | 3.7574 | 3.7574
UG-12A | UG-12A-S02 | P0064-02 | 5.2 | 1.2 | -2.63 | -2.63 | -0.93 | -0.93 | 10.46 | -2.63 | -2.63 | 1.93 | 1.13 | 0.8 | 5.06 | Open cut | 0 | 1.13 | 0.8 | 3.2 | 0 | 69.1901 | 5.72 | 5.881 | 0.44778 | 0.44778 | 3.7574 | 3.7574
UG-12A | UG-12A-S03 | P0064-03 | 4.8 | 1.2 | -2.63 | -2.63 | -0.93 | -0.93 | 10.42 | -2.63 | -2.63 | 1.93 | 1.13 | 0.8 | 5.06 | Open cut | 0 | 1.13 | 0.8 | 3.2 | 0 | 63.8678 | 5.28 | 5.4287 | 0.44778 | 0.44778 | 3.7574 | 3.7574
UG-12A | UG-12A-S03 | P0064-04 | 0.5967 | 1.2 | -2.63 | -2.63 | -0.93 | -0.93 | 10.53 | -2.63 | -2.63 | 1.93 | 1.13 | 0.8 | 5.06 | Open cut | 0 | 1.13 | 0.8 | 3.2 | 0 | 7.9395 | 0.65637 | 0.67485 | 0.44778 | 0.44778 | 3.7574 | 3.7574
UG-12A | UG-12A-S03 | P0062 | 1.005 | 1.2 | -2.63 | -2.631 | -0.93 | -0.93101 | 10.58 | -2.631 | -2.6305 | 1.9305 | 1.131 | 0.8 | 5.062 | Open cut | 0 | 1.1305 | 0.8 | 3.2 | 0 | 13.3777 | 1.1055 | 1.1366 | 0.44778 | 0.44975 | 3.7574 | 3.7594
UG-12A | UG-12A-S03 | P0063 | 1.005 | 1.2 | -2.631 | -2.632 | -0.93101 | -0.93201 | 10.06 | -2.632 | -2.6315 | 1.9315 | 1.132 | 0.8 | 5.064 | Open cut | 0 | 1.1315 | 0.8 | 3.2 | 0 | 13.3889 | 1.1055 | 1.1366 | 0.44975 | 0.45169 | 3.7594 | 3.7613
UG-12A | UG-12A-S03 | P0087-01 | 7.3933 | 1.2 | -2.632 | -2.6394 | -0.93201 | -0.93941 | 6.09 | -2.6394 | -2.6357 | 1.9357 | 1.1394 | 0.8 | 5.0788 | Open cut | 0 | 1.1357 | 0.8 | 3.2 | 0 | 98.8353 | 8.1326 | 8.3616 | 0.45169 | 0.4661 | 3.7613 | 3.7757
UG-12A | UG-12A-S03 | P0087-02 | 10 | 1.2 | -2.6394 | -2.6494 | -0.93941 | -0.94942 | 2.73 | -2.6494 | -2.6444 | 1.9444 | 1.1494 | 0.8 | 5.0988 | Shoring | 10 | 1.1444 | 0.8 | 3.2 | 62.2212 | 0 | 11 | 11.3097 | 0.4661 | 0.48559 | 3.7757 | 3.7952
UG-12A | UG-12A-S03 | P0087-03 | 10 | 1.2 | -2.6494 | -2.6594 | -0.94942 | -0.95943 | 2.11 | -2.6594 | -2.6544 | 1.9544 | 1.1594 | 0.8 | 5.1189 | Shoring | 10 | 1.1544 | 0.8 | 3.2 | 62.5415 | 0 | 11 | 11.3097 | 0.48559 | 0.50507 | 3.7952 | 3.8147
UG-12A | UG-12A-S03 | P0087-04 | 10 | 1.2 | -2.6594 | -2.6694 | -0.95943 | -0.96944 | 2.33 | -2.6694 | -2.6644 | 1.9644 | 1.1694 | 0.8 | 5.1389 | Shoring | 10 | 1.1644 | 0.8 | 3.2 | 62.8618 | 0 | 11 | 11.3097 | 0.50507 | 0.52456 | 3.8147 | 3.8342
UG-12A | UG-12A-S03 | P0087-05 | 10 | 1.2 | -2.6694 | -2.6794 | -0.96944 | -0.97945 | 5.02 | -2.6794 | -2.6744 | 1.9744 | 1.1794 | 0.8 | 5.1589 | Shoring | 10 | 1.1744 | 0.8 | 3.2 | 63.1821 | 0 | 11 | 11.3097 | 0.52456 | 0.54405 | 3.8342 | 3.8537
UG-12A | UG-12A-S03 | P0087-06 | 0.47096 | 1.2 | -2.6794 | -2.6799 | -0.97945 | -0.97992 | 10.14 | -2.6799 | -2.6797 | 1.9797 | 1.1799 | 0.8 | 5.1598 | Open cut | 0 | 1.1797 | 0.8 | 3.2 | 0 | 6.5244 | 0.51806 | 0.53265 | 0.54405 | 0.54496 | 3.8537 | 3.8546
UG-12A | UG-12A-S03 | P0160 | 1.4197 | 1.2 | -2.6799 | -2.6813 | -0.97992 | -0.98134 | 10.43 | -2.6813 | -2.6806 | 1.9806 | 1.1813 | 0.8 | 5.1627 | Open cut | 0 | 1.1806 | 0.8 | 3.2 | 0 | 19.6831 | 1.5617 | 1.6057 | 0.54496 | 0.54773 | 3.8546 | 3.8574
UG-12A | UG-12A-S03 | P0159 | 0.21 | 1.2 | -2.6813 | -2.6816 | -0.98134 | -0.98155 | 11.32 | -2.6816 | -2.6814 | 1.9814 | 1.1816 | 0.8 | 5.1631 | Open cut | 0 | 1.1814 | 0.8 | 3.2 | 0 | 2.9133 | 0.231 | 0.2375 | 0.54773 | 0.54813 | 3.8574 | 3.8578
UG-12A | UG-12A-S03 | P0158 | 0.2 | 1.4 | -2.7815 | -2.7817 | -0.88155 | -0.88175 | 11.45 | -2.7817 | -2.7816 | 2.0816 | 1.2817 | 0.8 | 5.4635 | Open cut | 0 | 1.2816 | 0.8 | 3.4 | 0 | 3.0848 | 0.24 | 0.30787 | 0.30296 | 0.3033 | 3.1398 | 3.1401
UG-12A | UG-12A-S03 | P0794 | 7.4253 | 1.6 | -2.8818 | -2.8892 | -0.78175 | -0.78918 | 11.58 | -2.8892 | -2.8855 | 2.1855 | 1.3892 | 0.8 | 5.7784 | Open cut | 0 | 1.3855 | 0.8 | 3.6 | 0 | 126.9739 | 9.6529 | 14.9294 | 0.11937 | 0.13021 | 2.6016 | 2.6124
UG-12A | UG-12A-S04 | P0315-01 | 0.274 | 1.6 | -2.8892 | -2.8889 | -0.78918 | -0.78889 | 16.71 | -2.8892 | -2.889 | 2.189 | 1.3892 | 0.8 | 5.7784 | Open cut | 0 | 1.389 | 0.8 | 3.6 | 0 | 4.6976 | 0.3562 | 0.55091 | 0.13021 | 0.12979 | 2.6124 | 2.612
UG-12A | UG-12A-S04 | P0315-02 | 10 | 1.6 | -2.8889 | -2.8784 | -0.78889 | -0.7784 | 11.97 | -2.8889 | -2.8836 | 2.1836 | 1.3889 | 0.8 | 5.7778 | Open cut | 0 | 1.3836 | 0.8 | 3.6 | 0 | 170.7773 | 13 | 20.1062 | 0.12979 | 0.11447 | 2.612 | 2.5967
UG-12A | UG-12A-S04 | P0315-03 | 10 | 1.6 | -2.8784 | -2.8679 | -0.7784 | -0.7679 | 6.41 | -2.8784 | -2.8731 | 2.1731 | 1.3784 | 0.8 | 5.7568 | Open cut | 0 | 1.3731 | 0.8 | 3.6 | 0 | 169.4848 | 13 | 20.1062 | 0.11447 | 0.099143 | 2.5967 | 2.5814
UG-12A | UG-12A-S04 | P0315-04 | 10 | 1.6 | -2.8679 | -2.8574 | -0.7679 | -0.7574 | 3.08 | -2.8679 | -2.8627 | 2.1627 | 1.3679 | 0.8 | 5.7358 | Shoring | 10 | 1.3627 | 0.8 | 3.6 | 77.8555 | 0 | 13 | 20.1062 | 0.099143 | 0.083817 | 2.5814 | 2.566
UG-12A | UG-12A-S04 | P0315-05 | 10 | 1.6 | -2.8574 | -2.8469 | -0.7574 | -0.74691 | 2.47 | -2.8574 | -2.8522 | 2.1522 | 1.3574 | 0.8 | 5.7148 | Shoring | 10 | 1.3522 | 0.8 | 3.6 | 77.4776 | 0 | 13 | 20.1062 | 0.083817 | 0.06849 | 2.566 | 2.5507
UG-12A | UG-12A-S04 | P0315-06 | 10 | 1.6 | -2.8469 | -2.8364 | -0.74691 | -0.73641 | 2.69 | -2.8469 | -2.8417 | 2.1417 | 1.3469 | 0.8 | 5.6938 | Shoring | 10 | 1.3417 | 0.8 | 3.6 | 77.0997 | 0 | 13 | 20.1062 | 0.06849 | 0.053164 | 2.5507 | 2.5354
UG-12A | UG-12A-S04 | P0315-07 | 6.1076 | 1.6 | -2.8364 | -2.83 | -0.73641 | -0.73 | 5.35 | -2.8364 | -2.8332 | 2.1332 | 1.3364 | 0.8 | 5.6728 | Shoring | 6.1076 | 1.3332 | 0.8 | 3.6 | 46.9038 | 0 | 7.9399 | 12.2801 | 0.053164 | 0.043804 | 2.5354 | 2.526
UG-12A | UG-12A-S04 | P0061 | 0.975 | 1.6 | -2.83 | -2.83 | -0.73001 | -0.73001 | 8.22 | -2.83 | -2.83 | 2.13 | 1.33 | 0.8 | 5.66 | Open cut | 0 | 1.33 | 0.8 | 3.6 | 0 | 16.0112 | 1.2675 | 1.9603 | 0.043813 | 0.043813 | 2.5261 | 2.5261
UG-12A | UG-12A-S04 | P0060 | 0.975 | 1.6 | -2.83 | -2.83 | -0.73 | -0.73 | 8.57 | -2.83 | -2.83 | 2.13 | 1.33 | 0.8 | 5.66 | Open cut | 0 | 1.33 | 0.8 | 3.6 | 0 | 16.0112 | 1.2675 | 1.9603 | 0.043812 | 0.043812 | 2.5261 | 2.5261
UG-12A | UG-12A-S04 | P0161-01 | 1.9424 | 1.6 | -2.83 | -2.83 | -0.73 | -0.73 | 8.28 | -2.83 | -2.83 | 2.13 | 1.33 | 0.8 | 5.66 | Open cut | 0 | 1.33 | 0.8 | 3.6 | 0 | 31.897 | 2.5251 | 3.9053 | 0.043809 | 0.043809 | 2.5261 | 2.5261
UG-12A | UG-12A-S04 | P0161-02 | 10 | 1.6 | -2.83 | -2.83 | -0.73 | -0.73 | 7.99 | -2.83 | -2.83 | 2.13 | 1.33 | 0.8 | 5.66 | Open cut | 0 | 1.33 | 0.8 | 3.6 | 0 | 164.2175 | 13 | 20.106 | 0.043809 | 0.043809 | 2.5261 | 2.5261
UG-12A | UG-12A-S04 | P0161-03 | 6.4 | 1.6 | -2.83 | -2.83 | -0.73 | -0.73 | 8.39 | -2.83 | -2.83 | 2.13 | 1.33 | 0.8 | 5.66 | Open cut | 0 | 1.33 | 0.8 | 3.6 | 0 | 105.0992 | 8.32 | 12.8679 | 0.043809 | 0.043809 | 2.5261 | 2.5261
UG-12A | UG-12A-S05 | P0161-04 | 3.6 | 1.6 | -2.83 | -2.83 | -0.73 | -0.73 | 9.83 | -2.83 | -2.83 | 2.13 | 1.33 | 0.8 | 5.66 | Open cut | 0 | 1.33 | 0.8 | 3.6 | 0 | 59.1183 | 4.68 | 7.2382 | 0.043809 | 0.043809 | 2.5261 | 2.5261
UG-12A | UG-12A-S05 | P0161-05 | 9.3085 | 1.6 | -2.83 | -2.83 | -0.73 | -0.73 | 11.07 | -2.83 | -2.83 | 2.13 | 1.33 | 0.8 | 5.66 | Open cut | 0 | 1.33 | 0.8 | 3.6 | 0 | 152.8621 | 12.101 | 18.7157 | 0.043809 | 0.043809 | 2.5261 | 2.5261
UG-12A | UG-12A-S05 | P0058-01 | 0.69148 | 1.6 | -2.83 | -2.83 | -0.73 | -0.73 | 15.49 | -2.83 | -2.83 | 2.13 | 1.33 | 0.8 | 5.66 | Open cut | 0 | 1.33 | 0.8 | 3.6 | 0 | 11.3554 | 0.89893 | 1.3903 | 0.043801 | 0.043801 | 2.526 | 2.526
UG-12A | UG-12A-S05 | P0058-02 | 0.28353 | 1.6 | -2.83 | -2.83 | -0.73 | -0.73 | 15.88 | -2.83 | -2.83 | 2.13 | 1.33 | 0.8 | 5.66 | Open cut | 0 | 1.33 | 0.8 | 3.6 | 0 | 4.656 | 0.36859 | 0.57007 | 0.043801 | 0.043801 | 2.526 | 2.526
UG-12A | UG-12A-S05 | P0059 | 0.97499 | 1.6 | -2.83 | -2.83 | -0.73 | -0.73 | 15.88 | -2.83 | -2.83 | 2.13 | 1.33 | 0.8 | 5.66 | Open cut | 0 | 1.33 | 0.8 | 3.6 | 0 | 16.0111 | 1.2675 | 1.9603 | 0.043804 | 0.043804 | 2.526 | 2.526
UG-12A | UG-12A-S05 | P0162-01 | 0.24148 | 1.6 | -2.83 | -2.83 | -0.73 | -0.73 | 15.84 | -2.83 | -2.83 | 2.13 | 1.33 | 0.8 | 5.66 | Open cut | 0 | 1.33 | 0.8 | 3.6 | 0 | 3.9656 | 0.31393 | 0.48553 | 0.04381 | 0.04381 | 2.5261 | 2.5261
UG-12A | UG-12A-S06 | P0162-02 | 8.5 | 1.6 | -2.83 | -2.83 | -0.73 | -0.73 | 15.32 | -2.83 | -2.83 | 2.13 | 1.33 | 0.8 | 5.66 | Open cut | 0 | 1.33 | 0.8 | 3.6 | 0 | 139.5847 | 11.05 | 17.0901 | 0.04381 | 0.04381 | 2.5261 | 2.5261
UG-12A | UG-12A-S06 | P0162-03 | 10 | 1.6 | -2.83 | -2.83 | -0.73 | -0.73 | 15.36 | -2.83 | -2.83 | 2.13 | 1.33 | 0.8 | 5.66 | Open cut | 0 | 1.33 | 0.8 | 3.6 | 0 | 164.2173 | 13 | 20.106 | 0.04381 | 0.04381 | 2.5261 | 2.5261
UG-12A | UG-12A-S06 | P0162-04 | 10 | 1.6 | -2.83 | -2.83 | -0.73 | -0.73 | 16.85 | -2.83 | -2.83 | 2.13 | 1.33 | 0.8 | 5.66 | Open cut | 0 | 1.33 | 0.8 | 3.6 | 0 | 164.2173 | 13 | 20.106 | 0.04381 | 0.04381 | 2.5261 | 2.5261
UG-12A | UG-12A-S06 | P0162-05 | 8.2375 | 1.6 | -2.83 | -2.83 | -0.73 | -0.73 | 20.36 | -2.83 | -2.83 | 2.13 | 1.33 | 0.8 | 5.66 | Open cut | 0 | 1.33 | 0.8 | 3.6 | 0 | 135.2742 | 10.7087 | 16.5623 | 0.04381 | 0.04381 | 2.5261 | 2.5261
UG-12A | UG-12A-S06 | P0397 | 0.205 | 1.6 | -2.83 | -2.8301 | -0.73 | -0.73007 | 24.5 | -2.8301 | -2.83 | 2.13 | 1.3301 | 0.8 | 5.6601 | Open cut | 0 | 1.33 | 0.8 | 3.6 | 0 | 3.3665 | 0.2665 | 0.41217 | 0.04381 | 0.043913 | 2.5261 | 2.5262
UG-12A | UG-12A-S06 | P0317-01 | 1.5575 | 1.6334 | -2.8468 | -2.8473 | -0.71337 | -0.71389 | 24.61 | -2.8473 | -2.847 | 2.147 | 1.3473 | 0.8 | 5.7113 | Open cut | 0 | 1.347 | 0.8 | 3.6334 | 0 | 26.0108 | 2.0507 | 3.2636 | 0.019126 | 0.019868 | 2.4506 | 2.4513
UG-12A | UG-12A-S06 | P0317-02 | 0.54351 | 1.6334 | -2.8473 | -2.8475 | -0.71389 | -0.71407 | 99 | -2.8475 | -2.8474 | 2.1474 | 1.3475 | 0.8 | 5.7116 | Open cut | 0 | 1.3474 | 0.8 | 3.6334 | 0 | 9.0792 | 0.71564 | 1.1389 | 0.019868 | 0.020127 | 2.4513 | 2.4516
UG-12A | UG-12A-S07 | P0083-01 | 10 | 1.2 | -2.7 | -2.7 | -1 | -1 | 21.24 | -2.7 | -2.7 | 2 | 1.2 | 0.8 | 5.2 | Open cut | 0 | 1.2 | 0.8 | 3.2 | 0 | 140.7998 | 11 | 11.3097 | 0.58406 | 0.58406 | 3.8937 | 3.8937
UG-12A | UG-12A-S07 | P0083-02 | 0.90835 | 1.2 | -2.7 | -2.7 | -1 | -1 | 21.07 | -2.7 | -2.7 | 2 | 1.2 | 0.8 | 5.2 | Open cut | 0 | 1.2 | 0.8 | 3.2 | 0 | 12.7896 | 0.99918 | 1.0273 | 0.58406 | 0.58406 | 3.8937 | 3.8937
UG-12A | UG-12A-S07 | P0754 | 0.10822 | 1.2 | -2.7 | -2.7 | -1 | -1 | 21.04 | -2.7 | -2.7 | 2 | 1.2 | 0.8 | 5.2 | Open cut | 0 | 1.2 | 0.8 | 3.2 | 0 | 1.5237 | 0.11904 | 0.12239 | 0.58406 | 0.58406 | 3.8937 | 3.8937
UG-12A | UG-12A-S07 | P0755 | 0.1082 | 1.2 | -2.7 | -2.7 | -1 | -1 | 21.01 | -2.7 | -2.7 | 2 | 1.2 | 0.8 | 5.2 | Open cut | 0 | 1.2 | 0.8 | 3.2 | 0 | 1.5234 | 0.11902 | 0.12237 | 0.58406 | 0.58406 | 3.8937 | 3.8937
UG-12A | UG-12A-S08 | P0316 | 5.2744 | 1.2 | -2.7 | -2.6892 | -1 | -0.98918 | 19.2 | -2.7 | -2.6946 | 1.9946 | 1.2 | 0.8 | 5.2 | Open cut | 0 | 1.1946 | 0.8 | 3.2 | 0 | 73.9439 | 5.8018 | 5.9651 | 0.58406 | 0.563 | 3.8937 | 3.8727
UG-12A | UG-12A-S09 | P0088-01 | 6 | 1.2 | -2.6346 | -2.6346 | -0.93459 | -0.93459 | 23.49 | -2.6346 | -2.6346 | 1.9346 | 1.1346 | 0.8 | 5.0692 | Open cut | 0 | 1.1346 | 0.8 | 3.2 | 0 | 80.1357 | 6.6 | 6.7858 | 0.45671 | 0.45671 | 3.7664 | 3.7664
UG-12A | UG-12A-S10 | P0088-02 | 4 | 1.2 | -2.6346 | -2.6346 | -0.93459 | -0.93459 | 22.38 | -2.6346 | -2.6346 | 1.9346 | 1.1346 | 0.8 | 5.0692 | Open cut | 0 | 1.1346 | 0.8 | 3.2 | 0 | 53.4238 | 4.4 | 4.5239 | 0.45671 | 0.45671 | 3.7664 | 3.7664
UG-12A | UG-12A-S10 | P0088-03 | 10 | 1.2 | -2.6346 | -2.6346 | -0.93459 | -0.93459 | 20.94 | -2.6346 | -2.6346 | 1.9346 | 1.1346 | 0.8 | 5.0692 | Open cut | 0 | 1.1346 | 0.8 | 3.2 | 0 | 133.5595 | 11 | 11.3097 | 0.45671 | 0.45671 | 3.7664 | 3.7664
UG-12A | UG-12A-S10 | P0088-04 | 4.3885 | 1.2 | -2.6346 | -2.6346 | -0.93459 | -0.93459 | 18 | -2.6346 | -2.6346 | 1.9346 | 1.1346 | 0.8 | 5.0692 | Open cut | 0 | 1.1346 | 0.8 | 3.2 | 0 | 58.6131 | 4.8274 | 4.9633 | 0.45671 | 0.45671 | 3.7664 | 3.7664
UG-12A | UG-12A-S10 | P0395 | 0.175 | 1.2 | -2.6346 | -2.6346 | -0.93459 | -0.93459 | 20.93 | -2.6346 | -2.6346 | 1.9346 | 1.1346 | 0.8 | 5.0692 | Open cut | 0 | 1.1346 | 0.8 | 3.2 | 0 | 2.3373 | 0.1925 | 0.19792 | 0.45671 | 0.45671 | 3.7664 | 3.7664
UG-12A | UG-12A-S10 | P0296-01 | 5.4365 | 1.2258 | -2.6475 | -2.6475 | -0.92169 | -0.92169 | 20.94 | -2.6475 | -2.6475 | 1.9475 | 1.1475 | 0.8 | 5.1079 | Open cut | 0 | 1.1475 | 0.8 | 3.2258 | 0 | 73.6513 | 6.0502 | 6.4157 | 0.42251 | 0.42251 | 3.6625 | 3.6625
UG-12A | UG-12A-S10 | P0296-02 | 5.2588 | 1.2258 | -2.6475 | -2.6475 | -0.92169 | -0.92169 | 21.6 | -2.6475 | -2.6475 | 1.9475 | 1.1475 | 0.8 | 5.1079 | Open cut | 0 | 1.1475 | 0.8 | 3.2258 | 0 | 71.2449 | 5.8526 | 6.2061 | 0.42251 | 0.42251 | 3.6625 | 3.6625
UG-12A | UG-12A-S11 | P0355-01 | 6 | 1.2 | -2.6434 | -2.6434 | -0.94336 | -0.94336 | 99 | -2.6434 | -2.6434 | 1.9434 | 1.1434 | 0.8 | 5.0867 | Open cut | 0 | 1.1434 | 0.8 | 3.2 | 0 | 80.7122 | 6.6 | 6.7858 | 0.47379 | 0.47379 | 3.7834 | 3.7834
UG-12A | UG-12A-S12 | P0355-02 | 3.8735 | 1.2 | -2.6434 | -2.6434 | -0.94336 | -0.94336 | 99 | -2.6434 | -2.6434 | 1.9434 | 1.1434 | 0.8 | 5.0867 | Open cut | 0 | 1.1434 | 0.8 | 3.2 | 0 | 52.1069 | 4.2609 | 4.3808 | 0.47379 | 0.47379 | 3.7834 | 3.7834
UG-12A | UG-12A-S12 | P0396 | 0.175 | 1.2258 | -2.6563 | -2.6563 | -0.93046 | -0.93046 | 99 | -2.6563 | -2.6563 | 1.9563 | 1.1563 | 0.8 | 5.1254 | Open cut | 0 | 1.1563 | 0.8 | 3.2258 | 0 | 2.3878 | 0.19476 | 0.20653 | 0.43923 | 0.43923 | 3.6792 | 3.6792
UG-12A | UG-12A-S12 | P0295 | 4.1212 | 1.2258 | -2.6563 | -2.6563 | -0.93046 | -0.93046 | 99 | -2.6563 | -2.6563 | 1.9563 | 1.1563 | 0.8 | 5.1254 | Open cut | 0 | 1.1563 | 0.8 | 3.2258 | 0 | 56.2307 | 4.5864 | 4.8635 | 0.43923 | 0.43923 | 3.6792 | 3.6792
UG-15 | UG-15-S01 | P0527 | 0.59999 | 1.6552 | -5.033 | -5.0383 | -2.8778 | -2.8831 | 8.82 | -5.0383 | -5.0356 | 4.3356 | 3.5383 | 0.8 | 10.1042 | Shoring | 0.59999 | 3.5356 | 0.8 | 3.6552 | 9.5084 | 0 | 0.79655 | 1.291 | 2.014 | 2.0174 | 4.4134 | 4.4168
UG-15 | UG-15-S01 | P0792 | 1.6131 | 2.0696 | -5.2455 | -5.2598 | -2.6759 | -2.6902 | 8.8 | -5.2598 | -5.2526 | 4.5526 | 3.7598 | 0.8 | 10.7544 | Shoring | 1.6131 | 3.7526 | 0.8 | 4.0696 | 29.8864 | 0 | 2.4758 | 5.4265 | 1.507 | 1.5144 | 3.426 | 3.4334
UG-15 | UG-15-S01 | P0309-01 | 7.7869 | 2.0696 | -5.2598 | -5.3288 | -2.6902 | -2.7591 | 8.8 | -5.3288 | -5.2943 | 4.5943 | 3.8288 | 0.8 | 10.8923 | Shoring | 7.7869 | 3.7943 | 0.8 | 4.0696 | 145.5911 | 0 | 11.9514 | 26.1958 | 1.5144 | 1.5498 | 3.4334 | 3.4688
UG-15 | UG-15-S01 | P0309-02 | 1.8126 | 2.0696 | -5.3288 | -5.3448 | -2.7591 | -2.7752 | 9.7 | -5.3448 | -5.3368 | 4.6368 | 3.8448 | 0.8 | 10.9244 | Shoring | 1.8126 | 3.8368 | 0.8 | 4.0696 | 34.2031 | 0 | 2.782 | 6.0976 | 1.5498 | 1.558 | 3.4688 | 3.477
UG-15 | UG-15-S01 | P0746 | 1.9543 | 2.0696 | -5.3448 | -5.3447 | -2.7752 | -2.7751 | 10.13 | -5.3448 | -5.3447 | 4.6447 | 3.8448 | 0.8 | 10.9244 | Shoring | 1.9543 | 3.8447 | 0.8 | 4.0696 | 36.9406 | 0 | 2.9995 | 6.5744 | 1.558 | 1.5579 | 3.477 | 3.4769
UG-15 | UG-15-S01 | P0745 | 2.0634 | 2.0412 | -5.3305 | -5.3303 | -2.7893 | -2.7891 | 9.74 | -5.3305 | -5.3304 | 4.6304 | 3.8305 | 0.8 | 10.8815 | Shoring | 2.0634 | 3.8304 | 0.8 | 4.0412 | 38.6109 | 0 | 3.1376 | 6.7522 | 1.587 | 1.5869 | 3.5327 | 3.5326
UG-15 | UG-15-S01 | P0308-01 | 4.1697 | 2.0412 | -5.3303 | -5.33 | -2.7891 | -2.7888 | 8.11 | -5.3303 | -5.3302 | 4.6302 | 3.8303 | 0.8 | 10.8812 | Shoring | 4.1697 | 3.8302 | 0.8 | 4.0412 | 78.0218 | 0 | 6.3405 | 13.645 | 1.5869 | 1.5868 | 3.5326 | 3.5325
UG-15 | UG-15-S01 | P0308-02 | 10 | 2.0412 | -5.33 | -5.3293 | -2.7888 | -2.7881 | 5.98 | -5.33 | -5.3296 | 4.6296 | 3.83 | 0.8 | 10.8806 | Shoring | 10 | 3.8296 | 0.8 | 4.0412 | 187.0937 | 0 | 15.206 | 32.7239 | 1.5868 | 1.5864 | 3.5325 | 3.5321
UG-15 | UG-15-S01 | P0308-03 | 10 | 2.0412 | -5.3293 | -5.3285 | -2.7881 | -2.7873 | 5.88 | -5.3293 | -5.3289 | 4.6289 | 3.8293 | 0.8 | 10.8792 | Shoring | 10 | 3.8289 | 0.8 | 4.0412 | 187.0642 | 0 | 15.206 | 32.7239 | 1.5864 | 1.586 | 3.5321 | 3.5317
UG-15 | UG-15-S01 | P0308-04 | 9.3 | 2.0412 | -5.3285 | -5.3279 | -2.7873 | -2.7867 | 6.64 | -5.3285 | -5.3282 | 4.6282 | 3.8285 | 0.8 | 10.8777 | Shoring | 9.3 | 3.8282 | 0.8 | 4.0412 | 173.9432 | 0 | 14.1416 | 30.4332 | 1.586 | 1.5857 | 3.5317 | 3.5314
UG-15 | UG-15-S02 | P0308-05 | 0.7 | 2.0412 | -5.3279 | -5.3278 | -2.7867 | -2.7866 | 9.63 | -5.3279 | -5.3278 | 4.6278 | 3.8279 | 0.8 | 10.8763 | Shoring | 0.7 | 3.8278 | 0.8 | 4.0412 | 13.0915 | 0 | 1.0644 | 2.2907 | 1.5857 | 1.5856 | 3.5314 | 3.5313
UG-15 | UG-15-S02 | P0308-06 | 10 | 2.0412 | -5.3278 | -5.3271 | -2.7866 | -2.7859 | 9.94 | -5.3278 | -5.3275 | 4.6275 | 3.8278 | 0.8 | 10.8762 | Shoring | 10 | 3.8275 | 0.8 | 4.0412 | 187.0051 | 0 | 15.206 | 32.7239 | 1.5856 | 1.5853 | 3.5313 | 3.531
UG-15 | UG-15-S02 | P0308-07 | 5.4 | 2.0412 | -5.3271 | -5.3267 | -2.7859 | -2.7855 | 14.47 | -5.3271 | -5.3269 | 4.6269 | 3.8271 | 0.8 | 10.8748 | Shoring | 5.4 | 3.8269 | 0.8 | 4.0412 | 100.9705 | 0 | 8.2113 | 17.6709 | 1.5853 | 1.5851 | 3.531 | 3.5307
UG-15 | UG-15-S03 | P0308-08 | 4.6 | 2.0412 | -5.3267 | -5.3264 | -2.7855 | -2.7851 | 14.45 | -5.3267 | -5.3265 | 4.6265 | 3.8267 | 0.8 | 10.874 | Shoring | 4.6 | 3.8265 | 0.8 | 4.0412 | 86.0051 | 0 | 6.9948 | 15.053 | 1.5851 | 1.5849 | 3.5307 | 3.5306
UG-15 | UG-15-S03 | P0308-09 | 10 | 2.0412 | -5.3264 | -5.3256 | -2.7851 | -2.7844 | 13.12 | -5.3264 | -5.326 | 4.626 | 3.8264 | 0.8 | 10.8733 | Shoring | 10 | 3.826 | 0.8 | 4.0412 | 186.9461 | 0 | 15.206 | 32.7239 | 1.5849 | 1.5845 | 3.5306 | 3.5302
UG-15 | UG-15-S03 | P0308-10 | 10 | 2.0412 | -5.3256 | -5.3249 | -2.7844 | -2.7837 | 8.73 | -5.3256 | -5.3253 | 4.6253 | 3.8256 | 0.8 | 10.8719 | Shoring | 10 | 3.8253 | 0.8 | 4.0412 | 186.9166 | 0 | 15.206 | 32.7239 | 1.5845 | 1.5841 | 3.5302 | 3.5298
UG-15 | UG-15-S03 | P0308-11 | 10 | 2.0412 | -5.3249 | -5.3242 | -2.7837 | -2.783 | 6.69 | -5.3249 | -5.3245 | 4.6245 | 3.8249 | 0.8 | 10.8704 | Shoring | 10 | 3.8245 | 0.8 | 4.0412 | 186.8871 | 0 | 15.206 | 32.7239 | 1.5841 | 1.5837 | 3.5298 | 3.5294
UG-15 | UG-15-S03 | P0308-12 | 10 | 2.0412 | -5.3242 | -5.3234 | -2.783 | -2.7822 | 6.6 | -5.3242 | -5.3238 | 4.6238 | 3.8242 | 0.8 | 10.8689 | Shoring | 10 | 3.8238 | 0.8 | 4.0412 | 186.8575 | 0 | 15.206 | 32.7239 | 1.5837 | 1.5834 | 3.5294 | 3.529
UG-15 | UG-15-S03 | P0308-13 | 10 | 2.0412 | -5.3234 | -5.3227 | -2.7822 | -2.7815 | 7.39 | -5.3234 | -5.3231 | 4.6231 | 3.8234 | 0.8 | 10.8675 | Shoring | 10 | 3.8231 | 0.8 | 4.0412 | 186.828 | 0 | 15.206 | 32.7239 | 1.5834 | 1.583 | 3.529 | 3.5287
UG-15 | UG-15-S03 | P0308-14 | 2.7 | 2.0412 | -5.3227 | -5.3225 | -2.7815 | -2.7813 | 10.67 | -5.3227 | -5.3226 | 4.6226 | 3.8227 | 0.8 | 10.866 | Shoring | 2.7 | 3.8226 | 0.8 | 4.0412 | 50.4385 | 0 | 4.1056 | 8.8355 | 1.583 | 1.5829 | 3.5287 | 3.5286
UG-15 | UG-15-S04 | P0308-15 | 7.3 | 2.0412 | -5.3225 | -5.322 | -2.7813 | -2.7808 | 11.93 | -5.3225 | -5.3222 | 4.6222 | 3.8225 | 0.8 | 10.8656 | Shoring | 7.3 | 3.8222 | 0.8 | 4.0412 | 136.36 | 0 | 11.1004 | 23.8885 | 1.5829 | 1.5826 | 3.5286 | 3.5283
UG-15 | UG-15-S04 | P0308-16 | 0.97503 | 2.0412 | -5.322 | -5.3219 | -2.7808 | -2.7807 | 14.26 | -5.322 | -5.3219 | 4.6219 | 3.822 | 0.8 | 10.8646 | Shoring | 0.97503 | 3.8219 | 0.8 | 4.0412 | 18.2118 | 0 | 1.4826 | 3.1907 | 1.5826 | 1.5826 | 3.5283 | 3.5283
UG-15 | UG-15-S04 | P0791-01 | 7.825 | 2.0412 | -5.3219 | -5.3213 | -2.7807 | -2.7801 | 14.23 | -5.3219 | -5.3216 | 4.6216 | 3.8219 | 0.8 | 10.8644 | Shoring | 7.825 | 3.8216 | 0.8 | 4.0412 | 146.1465 | 0 | 11.8987 | 25.6064 | 1.5826 | 1.5823 | 3.5283 | 3.528
UG-15 | UG-15-S05 | P0791-02 | 1.2 | 2.0412 | -5.3213 | -5.3212 | -2.7801 | -2.78 | 14.23 | -5.3213 | -5.3213 | 4.6213 | 3.8213 | 0.8 | 10.8633 | Shoring | 1.2 | 3.8213 | 0.8 | 4.0412 | 22.4107 | 0 | 1.8247 | 3.9269 | 1.5823 | 1.5822 | 3.528 | 3.5279
UG-15 | UG-15-S05 | P0791-03 | 8.8311 | 2.0412 | -5.3212 | -5.3206 | -2.78 | -2.7794 | 14.2 | -5.3212 | -5.3209 | 4.6209 | 3.8212 | 0.8 | 10.8631 | Shoring | 8.8311 | 3.8209 | 0.8 | 4.0412 | 164.9138 | 0 | 13.4287 | 28.8989 | 1.5822 | 1.5819 | 3.5279 | 3.5276
UG-15 | UG-15-S05 | P0535-01 | 1.1689 | 2.0412 | -5.3206 | -5.3206 | -2.7794 | -2.7794 | 14.19 | -5.3206 | -5.3206 | 4.6206 | 3.8206 | 0.8 | 10.8618 | Shoring | 1.1689 | 3.8206 | 0.8 | 4.0412 | 21.826 | 0 | 1.7774 | 3.825 | 1.5819 | 1.5819 | 3.5276 | 3.5276
UG-15 | UG-15-S05 | P0535-02 | 1.9318 | 2.0412 | -5.3206 | -5.3206 | -2.7794 | -2.7794 | 14.19 | -5.3206 | -5.3206 | 4.6206 | 3.8206 | 0.8 | 10.8618 | Shoring | 1.9318 | 3.8206 | 0.8 | 4.0412 | 36.0713 | 0 | 2.9374 | 6.3215 | 1.5819 | 1.5819 | 3.5276 | 3.5276
UG-15 | UG-15-S05 | P0534 | 3.0962 | 2.0696 | -5.3348 | -5.3348 | -2.7652 | -2.7652 | 33.71 | -5.3348 | -5.3348 | 4.6348 | 3.8348 | 0.8 | 10.9044 | Shoring | 3.0962 | 3.8348 | 0.8 | 4.0696 | 58.4007 | 0 | 4.7521 | 10.416 | 1.5529 | 1.5529 | 3.4719 | 3.4719
UG-15 | UG-15-S06 | P0076-01 | 4.972 | 2.0696 | -5.3348 | -5.3348 | -2.7652 | -2.7652 | 23.41 | -5.3348 | -5.3348 | 4.6348 | 3.8348 | 0.8 | 10.9044 | Shoring | 4.972 | 3.8348 | 0.8 | 4.0696 | 93.781 | 0 | 7.631 | 16.7262 | 1.5529 | 1.5529 | 3.4719 | 3.4719
UG-15 | UG-15-S06 | P0076-02 | 7.9976 | 2.0696 | -5.3348 | -5.3348 | -2.7652 | -2.7652 | 15.82 | -5.3348 | -5.3348 | 4.6348 | 3.8348 | 0.8 | 10.9044 | Shoring | 7.9976 | 3.8348 | 0.8 | 4.0696 | 150.8495 | 0 | 12.2748 | 26.9045 | 1.5529 | 1.5529 | 3.4719 | 3.4719
UG-15A | UG-15A-S01 | P0026 | 5.5876 | 1.2 | -4.9013 | -4.9013 | -3.2013 | -3.2013 | 25.21 | -4.9013 | -4.9013 | 4.2013 | 3.4013 | 0.8 | 9.6026 | Shoring | 5.5876 | 3.4013 | 0.8 | 3.2 | 75.1208 | 0 | 6.1464 | 6.3194 | 3.0645 | 3.0645 | 6.3742 | 6.3742
UG-15A | UG-15A-S01 | P0554 | 0.44543 | 1.1652 | -4.8839 | -4.8839 | -3.2187 | -3.2187 | 24.89 | -4.8839 | -4.8839 | 4.1839 | 3.3839 | 0.8 | 9.5505 | Shoring | 0.44543 | 3.3839 | 0.8 | 3.1652 | 5.8988 | 0 | 0.48223 | 0.47501 | 3.1718 | 3.1718 | 6.5801 | 6.5801
UG-15A | UG-15A-S02 | P0212 | 3.4273 | 1.2 | -4.9013 | -4.9013 | -3.2013 | -3.2013 | 22.46 | -4.9013 | -4.9013 | 4.2013 | 3.4013 | 0.8 | 9.6026 | Shoring | 3.4273 | 3.4013 | 0.8 | 3.2 | 46.0778 | 0 | 3.7701 | 3.8763 | 3.0645 | 3.0645 | 6.3741 | 6.3741
UG-15A | UG-15A-S02 | P0555 | 0.48001 | 1.1591 | -4.8809 | -4.8809 | -3.2217 | -3.2217 | 22.12 | -4.8809 | -4.8809 | 4.1809 | 3.3809 | 0.8 | 9.5413 | Shoring | 0.48001 | 3.3809 | 0.8 | 3.1591 | 6.3398 | 0 | 0.51819 | 0.50651 | 3.1914 | 3.1914 | 6.6178 | 6.6178
UG-15A | UG-15A-S02 | P0024-01 | 0.059607 | 1.2 | -4.9013 | -4.9013 | -3.2013 | -3.2013 | 22.08 | -4.9013 | -4.9013 | 4.2013 | 3.4013 | 0.8 | 9.6026 | Shoring | 0.059607 | 3.4013 | 0.8 | 3.2 | 0.80136 | 0 | 0.065567 | 0.067413 | 3.0645 | 3.0645 | 6.3742 | 6.3742
UG-15A | UG-15A-S02 | P0024-02 | 0.94539 | 1.2 | -4.9013 | -4.9013 | -3.2013 | -3.2013 | 21.41 | -4.9013 | -4.9013 | 4.2013 | 3.4013 | 0.8 | 9.6026 | Shoring | 0.94539 | 3.4013 | 0.8 | 3.2 | 12.71 | 0 | 1.0399 | 1.0692 | 3.0645 | 3.0645 | 6.3742 | 6.3742
UG-15A | UG-15A-S02 | P0025 | 1.005 | 1.2 | -4.9013 | -4.9013 | -3.2013 | -3.2013 | 20.4 | -4.9013 | -4.9013 | 4.2013 | 3.4013 | 0.8 | 9.6026 | Shoring | 1.005 | 3.4013 | 0.8 | 3.2 | 13.5114 | 0 | 1.1055 | 1.1366 | 3.0645 | 3.0645 | 6.3742 | 6.3742
UG-15A | UG-15A-S02 | P0075 | 1.3415 | 1.2 | -4.9013 | -4.9013 | -3.2013 | -3.2013 | 19.06 | -4.9013 | -4.9013 | 4.2013 | 3.4013 | 0.8 | 9.6026 | Shoring | 1.3415 | 3.4013 | 0.8 | 3.2 | 18.0348 | 0 | 1.4756 | 1.5171 | 3.0645 | 3.0645 | 6.3742 | 6.3742
UG-15A | UG-15A-S02 | P0386 | 0.17501 | 1.2 | -4.9013 | -4.9013 | -3.2013 | -3.2013 | 18.89 | -4.9013 | -4.9013 | 4.2013 | 3.4013 | 0.8 | 9.6026 | Shoring | 0.17501 | 3.4013 | 0.8 | 3.2 | 2.3528 | 0 | 0.19251 | 0.19793 | 3.0645 | 3.0645 | 6.3742 | 6.3742
UG-15A | UG-15A-S02 | P0310 | 4.6325 | 1.2258 | -4.9142 | -4.9142 | -3.1884 | -3.1884 | 14.26 | -4.9142 | -4.9142 | 4.2142 | 3.4142 | 0.8 | 9.6414 | Shoring | 4.6325 | 3.4142 | 0.8 | 3.2258 | 62.9757 | 0 | 5.1556 | 5.4672 | 2.9887 | 2.9887 | 6.2286 | 6.2286
UG-15A | UG-15A-S03 | P0140 | 2.2225 | 1.2 | -2.72 | -2.72 | -1.02 | -1.02 | 24.39 | -2.72 | -2.72 | 2.02 | 1.22 | 0.8 | 5.24 | Open cut | 0 | 1.22 | 0.8 | 3.2 | 0 | 31.7925 | 2.4448 | 2.5136 | 0.62299 | 0.62299 | 3.9326 | 3.9326
UG-15A | UG-15A-S03 | P0180-01 | 7.7775 | 1.2 | -2.72 | -2.72 | -1.02 | -1.02 | 22.27 | -2.72 | -2.72 | 2.02 | 1.22 | 0.8 | 5.24 | Open cut | 0 | 1.22 | 0.8 | 3.2 | 0 | 111.2555 | 8.5552 | 8.7961 | 0.62299 | 0.62299 | 3.9326 | 3.9326
UG-15A | UG-15A-S03 | P0180-02 | 1.2544 | 1.2 | -2.72 | -2.72 | -1.02 | -1.02 | 22.03 | -2.72 | -2.72 | 2.02 | 1.22 | 0.8 | 5.24 | Open cut | 0 | 1.22 | 0.8 | 3.2 | 0 | 17.9438 | 1.3798 | 1.4187 | 0.62299 | 0.62299 | 3.9326 | 3.9326
UG-15A | UG-15A-S03 | P0228 | 4.1848 | 1.2 | -2.72 | -2.72 | -1.02 | -1.02 | 21.45 | -2.72 | -2.72 | 2.02 | 1.22 | 0.8 | 5.24 | Open cut | 0 | 1.22 | 0.8 | 3.2 | 0 | 59.8632 | 4.6033 | 4.7329 | 0.62299 | 0.62299 | 3.9326 | 3.9326
UG-15A | UG-15A-S03 | P0594 | 1.0086 | 1.2 | -2.72 | -2.72 | -1.02 | -1.02 | 21.36 | -2.72 | -2.72 | 2.02 | 1.22 | 0.8 | 5.24 | Open cut | 0 | 1.22 | 0.8 | 3.2 | 0 | 14.4283 | 1.1095 | 1.1407 | 0.62299 | 0.62299 | 3.9326 | 3.9326
UG-15A | UG-15A-S03 | P0595 | 1.0026 | 1.2 | -2.72 | -2.72 | -1.02 | -1.02 | 20.6 | -2.72 | -2.72 | 2.02 | 1.22 | 0.8 | 5.24 | Open cut | 0 | 1.22 | 0.8 | 3.2 | 0 | 14.3417 | 1.1028 | 1.1339 | 0.62298 | 0.62298 | 3.9326 | 3.9326
UG-15A | UG-15A-S04 | P0291 | 1.2327 | 1.2 | -2.72 | -2.72 | -1.02 | -1.02 | 16.79 | -2.72 | -2.72 | 2.02 | 1.22 | 0.8 | 5.24 | Open cut | 0 | 1.22 | 0.8 | 3.2 | 0 | 17.6333 | 1.356 | 1.3941 | 0.62298 | 0.62298 | 3.9326 | 3.9326
UG-15A | UG-15A-S04 | P0598 | 0.11637 | 1.2 | -2.72 | -2.72 | -1.02 | -1.02 | 17.68 | -2.72 | -2.72 | 2.02 | 1.22 | 0.8 | 5.24 | Open cut | 0 | 1.22 | 0.8 | 3.2 | 0 | 1.6647 | 0.12801 | 0.13162 | 0.62299 | 0.62299 | 3.9326 | 3.9326
UG-15A | UG-15A-S04 | P0597 | 0.31574 | 1.2 | -2.72 | -2.8883 | -1.02 | -1.1883 | 17.76 | -2.8883 | -2.8042 | 2.1042 | 1.3883 | 0.8 | 5.5766 | Open cut | 0 | 1.3042 | 0.8 | 3.2 | 0 | 4.8208 | 0.34731 | 0.35709 | 0.62299 | 0.95065 | 3.9326 | 4.2603
UG-15A | UG-15A-S04 | P0289-01 | 0.88478 | 1.2 | -2.8883 | -3.3599 | -1.1883 | -1.6599 | 17.99 | -3.3599 | -3.1241 | 2.4241 | 1.8599 | 0.8 | 6.5198 | Open cut | 0 | 1.6241 | 0.8 | 3.2 | 0 | 16.9787 | 0.97326 | 1.0007 | 0.95065 | 1.6991 | 4.2603 | 5.0088
UG-15A | UG-15A-S04 | P0289-02 | 1.9606 | 1.2 | -3.3599 | -4.405 | -1.6599 | -2.705 | 17.31 | -4.405 | -3.8825 | 3.1825 | 2.905 | 0.8 | 8.61 | Shoring | 1.9606 | 2.3825 | 0.8 | 3.2 | 19.9664 | 0 | 2.1567 | 2.2174 | 1.6991 | 2.6249 | 5.0088 | 5.9345
UG-15A | UG-15A-S04 | P0596 | 0.47841 | 1.1591 | -4.3845 | -4.6395 | -2.7254 | -2.9805 | 16.97 | -4.6395 | -4.512 | 3.812 | 3.1395 | 0.8 | 9.0586 | Shoring | 0.47841 | 3.012 | 0.8 | 3.1591 | 5.7613 | 0 | 0.51646 | 0.50481 | 2.7363 | 2.9701 | 6.1627 | 6.3966
UG-15A | UG-15A-S04 | P0290-01 | 4.661 | 1.2 | -4.66 | -4.6624 | -2.96 | -2.9624 | 13.82 | -4.6624 | -4.6612 | 3.9612 | 3.1624 | 0.8 | 9.1248 | Shoring | 4.661 | 3.1612 | 0.8 | 3.2 | 59.0818 | 0 | 5.1271 | 5.2714 | 2.8508 | 2.8529 | 6.1604 | 6.1626
UG-15A | UG-15A-S05 | P0290-02 | 2.9 | 1.2 | -4.6624 | -4.6639 | -2.9624 | -2.9639 | 12.01 | -4.6639 | -4.6631 | 3.9631 | 3.1639 | 0.8 | 9.1277 | Shoring | 2.9 | 3.1631 | 0.8 | 3.2 | 36.7778 | 0 | 3.19 | 3.2798 | 2.8529 | 2.8542 | 6.1626 | 6.1639
UG-15A | UG-15A-S05 | P0290-03 | 10 | 1.2 | -4.6639 | -4.669 | -2.9639 | -2.969 | 6.88 | -4.669 | -4.6664 | 3.9664 | 3.169 | 0.8 | 9.138 | Shoring | 10 | 3.1664 | 0.8 | 3.2 | 126.9259 | 0 | 11 | 11.3097 | 2.8542 | 2.8588 | 6.1639 | 6.1684
UG-15A | UG-15A-S05 | P0290-04 | 10 | 1.2 | -4.669 | -4.6741 | -2.969 | -2.9741 | 4.05 | -4.6741 | -4.6716 | 3.9716 | 3.1741 | 0.8 | 9.1483 | Shoring | 10 | 3.1716 | 0.8 | 3.2 | 127.0899 | 0 | 11 | 11.3097 | 2.8588 | 2.8633 | 6.1684 | 6.173
UG-15A | UG-15A-S05 | P0290-05 | 10 | 1.2 | -4.6741 | -4.6793 | -2.9741 | -2.9793 | 3.71 | -4.6793 | -4.6767 | 3.9767 | 3.1793 | 0.8 | 9.1585 | Shoring | 10 | 3.1767 | 0.8 | 3.2 | 127.254 | 0 | 11 | 11.3097 | 2.8633 | 2.8678 | 6.173 | 6.1775
UG-15A | UG-15A-S05 | P0290-06 | 10 | 1.2 | -4.6793 | -4.6844 | -2.9793 | -2.9844 | 4.13 | -4.6844 | -4.6818 | 3.9818 | 3.1844 | 0.8 | 9.1688 | Shoring | 10 | 3.1818 | 0.8 | 3.2 | 127.4181 | 0 | 11 | 11.3097 | 2.8678 | 2.8724 | 6.1775 | 6.182
UG-15A | UG-15A-S05 | P0290-07 | 2.2117 | 1.2 | -4.6844 | -4.6855 | -2.9844 | -2.9855 | 7.1 | -4.6855 | -4.685 | 3.985 | 3.1855 | 0.8 | 9.171 | Shoring | 2.2117 | 3.185 | 0.8 | 3.2 | 28.2038 | 0 | 2.4329 | 2.5014 | 2.8724 | 2.8734 | 6.182 | 6.183
UG-15A | UG-15A-S05 | P0431 | 1.005 | 1.2 | -4.6855 | -4.686 | -2.9855 | -2.986 | 8.09 | -4.686 | -4.6858 | 3.9858 | 3.186 | 0.8 | 9.1721 | Shoring | 1.005 | 3.1858 | 0.8 | 3.2 | 12.8185 | 0 | 1.1055 | 1.1366 | 2.8734 | 2.8738 | 6.183 | 6.1835
UG-15A | UG-15A-S05 | P0430 | 1.005 | 1.2 | -4.686 | -4.6865 | -2.986 | -2.9866 | 8.32 | -4.6865 | -4.6863 | 3.9863 | 3.1865 | 0.8 | 9.1731 | Shoring | 1.005 | 3.1863 | 0.8 | 3.2 | 12.8196 | 0 | 1.1055 | 1.1366 | 2.8739 | 2.8743 | 6.1835 | 6.184
UG-15A | UG-15A-S05 | P0021-01 | 5.7783 | 1.2 | -4.6865 | -4.6895 | -2.9866 | -2.9895 | 7.35 | -4.6895 | -4.688 | 3.988 | 3.1895 | 0.8 | 9.179 | Shoring | 5.7783 | 3.188 | 0.8 | 3.2 | 73.74 | 0 | 6.356 | 6.5349 | 2.8743 | 2.8769 | 6.184 | 6.1866
UG-15A | UG-15A-S05 | P0021-02 | 10 | 1.2 | -4.6895 | -4.6946 | -2.9895 | -2.9946 | 7.2 | -4.6946 | -4.6921 | 3.9921 | 3.1946 | 0.8 | 9.1893 | Shoring | 10 | 3.1921 | 0.8 | 3.2 | 127.7459 | 0 | 10.9999 | 11.3095 | 2.8769 | 2.8815 | 6.1866 | 6.1912
UG-15A | UG-15A-S05 | P0021-03 | 6.4848 | 1.2 | -4.6946 | -4.698 | -2.9946 | -2.998 | 7.82 | -4.698 | -4.6963 | 3.9963 | 3.198 | 0.8 | 9.1959 | Shoring | 6.4848 | 3.1963 | 0.8 | 3.2 | 82.9278 | 0 | 7.1332 | 7.3339 | 2.8815 | 2.8844 | 6.1912 | 6.1941
UG-15A | UG-15A-S05 | P0028 | 1.978 | 1.2 | -4.698 | -4.699 | -2.998 | -2.999 | 9.54 | -4.699 | -4.6985 | 3.9985 | 3.199 | 0.8 | 9.198 | Shoring | 1.978 | 3.1985 | 0.8 | 3.2 | 25.3088 | 0 | 2.1758 | 2.2371 | 2.8844 | 2.8853 | 6.1941 | 6.195
UG-15A | UG-15A-S05 | P0027-01 | 1.5372 | 1.2 | -4.699 | -4.6998 | -2.999 | -2.9998 | 9.69 | -4.6998 | -4.6994 | 3.9994 | 3.1998 | 0.8 | 9.1995 | Shoring | 1.5372 | 3.1994 | 0.8 | 3.2 | 19.6736 | 0 | 1.691 | 1.7386 | 2.8853 | 2.886 | 6.195 | 6.1957
UG-15A | UG-15A-S05 | P0027-02 | 0.44076 | 1.2 | -4.6998 | -4.7 | -2.9998 | -3 | 9.54 | -4.7 | -4.6999 | 3.9999 | 3.2 | 0.8 | 9.2 | Shoring | 0.44076 | 3.1999 | 0.8 | 3.2 | 5.6416 | 0 | 0.48483 | 0.49848 | 2.886 | 2.8862 | 6.1957 | 6.1959
UG-15A | UG-15A-S05 | P0107-01 | 9.5592 | 1.2 | -4.7 | -4.7 | -3 | -3 | 7.44 | -4.7 | -4.7 | 4 | 3.2 | 0.8 | 9.2 | Shoring | 9.5592 | 3.2 | 0.8 | 3.2 | 122.3582 | 0 | 10.5152 | 10.8112 | 2.8862 | 2.8862 | 6.1959 | 6.1959
UG-15A | UG-15A-S05 | P0107-02 | 10 | 1.2 | -4.7 | -4.7 | -3 | -3 | 7.27 | -4.7 | -4.7 | 4 | 3.2 | 0.8 | 9.2 | Shoring | 10 | 3.2 | 0.8 | 3.2 | 127.9999 | 0 | 11 | 11.3097 | 2.8862 | 2.8862 | 6.1959 | 6.1959
UG-15A | UG-15A-S05 | P0107-03 | 10 | 1.2 | -4.7 | -4.7 | -3 | -3 | 7.85 | -4.7 | -4.7 | 4 | 3.2 | 0.8 | 9.2 | Shoring | 10 | 3.2 | 0.8 | 3.2 | 127.9999 | 0 | 11 | 11.3097 | 2.8862 | 2.8862 | 6.1959 | 6.1959
UG-15A | UG-15A-S05 | P0107-04 | 10 | 1.2 | -4.7 | -4.7 | -3 | -3 | 10.86 | -4.7 | -4.7 | 4 | 3.2 | 0.8 | 9.2 | Shoring | 10 | 3.2 | 0.8 | 3.2 | 127.9999 | 0 | 11 | 11.3097 | 2.8862 | 2.8862 | 6.1959 | 6.1959
UG-15A | UG-15A-S05 | P0107-05 | 4.5294 | 1.2 | -4.7 | -4.7 | -3 | -3 | 15.93 | -4.7 | -4.7 | 4 | 3.2 | 0.8 | 9.2 | Shoring | 4.5294 | 3.2 | 0.8 | 3.2 | 57.9757 | 0 | 4.9823 | 5.1226 | 2.8862 | 2.8862 | 6.1959 | 6.1959
UG-15A | UG-15A-S05 | P0106 | 0.21 | 1.2 | -4.7 | -4.7 | -3 | -3 | 18.74 | -4.7 | -4.7 | 4 | 3.2 | 0.8 | 9.2 | Shoring | 0.21 | 3.2 | 0.8 | 3.2 | 2.688 | 0 | 0.231 | 0.2375 | 2.8862 | 2.8862 | 6.1959 | 6.1959
UG-15A | UG-15A-S05 | P0105 | 0.2 | 1.4 | -4.8 | -4.8 | -2.9 | -2.9 | 18.88 | -4.8 | -4.8 | 4.1 | 3.3 | 0.8 | 9.5 | Shoring | 0.2 | 3.3 | 0.8 | 3.4 | 2.788 | 0 | 0.24 | 0.30787 | 2.398 | 2.398 | 5.2348 | 5.2348
UG-15A | UG-15A-S05 | P0782 | 4.2805 | 1.6 | -4.9 | -4.9 | -2.8 | -2.8 | 19.01 | -4.9 | -4.9 | 4.2 | 3.4 | 0.8 | 9.8 | Shoring | 4.2805 | 3.4 | 0.8 | 3.6 | 64.7207 | 0 | 5.5646 | 8.6064 | 2.0318 | 2.0318 | 4.514 | 4.514
UG-15A | UG-15A-S06 | P0176-01 | 0.78017 | 1.6 | -4.9 | -4.9 | -2.8 | -2.8 | 20.41 | -4.9 | -4.9 | 4.2 | 3.4 | 0.8 | 9.8 | Shoring | 0.78017 | 3.4 | 0.8 | 3.6 | 11.7962 | 0 | 1.0142 | 1.5686 | 2.0318 | 2.0318 | 4.514 | 4.514
UG-15A | UG-15A-S06 | P0176-02 | 10 | 1.6 | -4.9 | -4.9 | -2.8 | -2.8 | 14.21 | -4.9 | -4.9 | 4.2 | 3.4 | 0.8 | 9.8 | Shoring | 10 | 3.4 | 0.8 | 3.6 | 151.2001 | 0 | 13 | 20.1062 | 2.0318 | 2.0318 | 4.514 | 4.514
UG-15A | UG-15A-S06 | P0176-03 | 10 | 1.6 | -4.9 | -4.9 | -2.8 | -2.8 | 9.62 | -4.9 | -4.9 | 4.2 | 3.4 | 0.8 | 9.8 | Shoring | 10 | 3.4 | 0.8 | 3.6 | 151.2001 | 0 | 13 | 20.1062 | 2.0318 | 2.0318 | 4.514 | 4.514
UG-15A | UG-15A-S06 | P0176-04 | 10 | 1.6 | -4.9 | -4.9 | -2.8 | -2.8 | 7.29 | -4.9 | -4.9 | 4.2 | 3.4 | 0.8 | 9.8 | Shoring | 10 | 3.4 | 0.8 | 3.6 | 151.2001 | 0 | 13 | 20.1062 | 2.0318 | 2.0318 | 4.514 | 4.514
UG-15A | UG-15A-S06 | P0176-05 | 10 | 1.6 | -4.9 | -4.9 | -2.8 | -2.8 | 7.09 | -4.9 | -4.9 | 4.2 | 3.4 | 0.8 | 9.8 | Shoring | 10 | 3.4 | 0.8 | 3.6 | 151.2001 | 0 | 13 | 20.1062 | 2.0318 | 2.0318 | 4.514 | 4.514
UG-15A | UG-15A-S06 | P0176-06 | 5.5543 | 1.6 | -4.9 | -4.9 | -2.8 | -2.8 | 7.63 | -4.9 | -4.9 | 4.2 | 3.4 | 0.8 | 9.8 | Shoring | 5.5543 | 3.4 | 0.8 | 3.6 | 83.9808 | 0 | 7.2206 | 11.1676 | 2.0318 | 2.0318 | 4.514 | 4.514
UG-15A | UG-15A-S06 | P0139 | 4.2912 | 1.6 | -4.9 | -4.9 | -2.8 | -2.8 | 8.97 | -4.9 | -4.9 | 4.2 | 3.4 | 0.8 | 9.8 | Shoring | 4.2912 | 3.4 | 0.8 | 3.6 | 64.883 | 0 | 5.5786 | 8.6279 | 2.0318 | 2.0318 | 4.514 | 4.514
UG-15A | UG-15A-S06 | P0138-01 | 0.15451 | 1.6 | -4.9 | -4.9014 | -2.8 | -2.8014 | 10.52 | -4.9014 | -4.9007 | 4.2007 | 3.4014 | 0.8 | 9.8027 | Shoring | 0.15451 | 3.4007 | 0.8 | 3.6 | 2.3365 | 0 | 0.20086 | 0.31066 | 2.0318 | 2.0327 | 4.514 | 4.5149
UG-15A | UG-15A-S06 | P0138-02 | 0.8205 | 1.6 | -4.9014 | -4.9086 | -2.8014 | -2.8086 | 10.58 | -4.9086 | -4.905 | 4.205 | 3.4086 | 0.8 | 9.8173 | Shoring | 0.8205 | 3.405 | 0.8 | 3.6 | 12.4207 | 0 | 1.0666 | 1.6497 | 2.0327 | 2.0375 | 4.5149 | 4.5197
UG-15A | UG-15A-S06 | P0137 | 0.97499 | 1.6 | -4.9086 | -4.9173 | -2.8086 | -2.8173 | 10.62 | -4.9173 | -4.9129 | 4.2129 | 3.4173 | 0.8 | 9.8345 | Shoring | 0.97499 | 3.4129 | 0.8 | 3.6 | 14.7873 | 0 | 1.2675 | 1.9603 | 2.0375 | 2.0433 | 4.5198 | 4.5255
UG-15A | UG-15A-S06 | P0136 | 3.2532 | 1.6 | -4.9173 | -4.9461 | -2.8173 | -2.8461 | 9.77 | -4.9461 | -4.9317 | 4.2317 | 3.4461 | 0.8 | 9.8921 | Shoring | 3.2532 | 3.4317 | 0.8 | 3.6 | 49.5592 | 0 | 4.2291 | 6.5408 | 2.0433 | 2.0624 | 4.5255 | 4.5447
UG-15A | UG-15A-S06 | P0399 | 0.205 | 1.6 | -4.9461 | -4.9479 | -2.8461 | -2.8479 | 9.73 | -4.9479 | -4.947 | 4.247 | 3.4479 | 0.8 | 9.8958 | Shoring | 0.205 | 3.447 | 0.8 | 3.6 | 3.1343 | 0 | 0.2665 | 0.41218 | 2.0624 | 2.0636 | 4.5447 | 4.5459
UG-15A | UG-15A-S06 | P0286-01 | 4.7463 | 1.6552 | -4.9755 | -5.0175 | -2.8203 | -2.8623 | 8.98 | -5.0175 | -4.9965 | 4.2965 | 3.5175 | 0.8 | 10.0626 | Shoring | 4.7463 | 3.4965 | 0.8 | 3.6552 | 74.5387 | 0 | 6.3012 | 10.2128 | 1.9771 | 2.004 | 4.3765 | 4.4035
UG-15A | UG-15A-S06 | P0286-02 | 1.7465 | 1.6552 | -5.0175 | -5.033 | -2.8623 | -2.8778 | 8.85 | -5.033 | -5.0253 | 4.3253 | 3.533 | 0.8 | 10.0936 | Shoring | 1.7465 | 3.5253 | 0.8 | 3.6552 | 27.6119 | 0 | 2.3187 | 3.7581 | 2.004 | 2.014 | 4.4035 | 4.4134
UG-15A | UG-15A-S07 | P0019 | 5.9406 | 1.2 | -4.7 | -4.7 | -3 | -3 | 23.01 | -4.7 | -4.7 | 4 | 3.2 | 0.8 | 9.2 | Shoring | 5.9406 | 3.2 | 0.8 | 3.2 | 76.0394 | 0 | 6.5346 | 6.7186 | 2.8862 | 2.8862 | 6.1959 | 6.1959
UG-15A | UG-15A-S07 | P0142-01 | 4.0594 | 1.2 | -4.7 | -4.7 | -3 | -3 | 22.02 | -4.7 | -4.7 | 4 | 3.2 | 0.8 | 9.2 | Shoring | 4.0594 | 3.2 | 0.8 | 3.2 | 51.9605 | 0 | 4.4654 | 4.5911 | 2.8862 | 2.8862 | 6.1959 | 6.1959
UG-15A | UG-15A-S07 | P0142-02 | 0.53938 | 1.2 | -4.7 | -4.7 | -3 | -3 | 21.91 | -4.7 | -4.7 | 4 | 3.2 | 0.8 | 9.2 | Shoring | 0.53938 | 3.2 | 0.8 | 3.2 | 6.904 | 0 | 0.59332 | 0.61002 | 2.8862 | 2.8862 | 6.1959 | 6.1959
UG-15A | UG-15A-S07 | P0736 | 0.17347 | 1.195 | -4.6975 | -4.6975 | -3.0025 | -3.0025 | 21.87 | -4.6975 | -4.6975 | 3.9975 | 3.1975 | 0.8 | 9.1926 | Shoring | 0.17347 | 3.1975 | 0.8 | 3.195 | 2.2156 | 0 | 0.19039 | 0.19457 | 2.9004 | 2.9004 | 6.2237 | 6.2237
UG-15A | UG-15A-S08 | P0283-01 | 9.2872 | 1.2 | -4.7 | -4.7 | -3 | -3 | 20.94 | -4.7 | -4.7 | 4 | 3.2 | 0.8 | 9.2 | Shoring | 9.2872 | 3.2 | 0.8 | 3.2 | 118.8756 | 0 | 10.2159 | 10.5035 | 2.8862 | 2.8862 | 6.1958 | 6.1958
UG-15A | UG-15A-S08 | P0283-02 | 1.6947 | 1.2 | -4.7 | -4.7 | -3 | -3 | 20.23 | -4.7 | -4.7 | 4 | 3.2 | 0.8 | 9.2 | Shoring | 1.6947 | 3.2 | 0.8 | 3.2 | 21.6916 | 0 | 1.8641 | 1.9166 | 2.8862 | 2.8862 | 6.1958 | 6.1958
UG-15A | UG-15A-S09 | P0141 | 0.56028 | 1.2 | -4.825 | -4.825 | -3.125 | -3.125 | 34.24 | -4.825 | -4.825 | 4.125 | 3.325 | 0.8 | 9.45 | Shoring | 0.56028 | 3.325 | 0.8 | 3.2 | 7.3957 | 0 | 0.61631 | 0.63366 | 2.9969 | 2.9969 | 6.3066 | 6.3066
UG-15A | UG-15A-S09 | P0737 | 0.32054 | 1.1827 | -4.8163 | -4.8163 | -3.1337 | -3.1337 | 34.07 | -4.8163 | -4.8163 | 4.1163 | 3.3163 | 0.8 | 9.424 | Shoring | 0.32054 | 3.3163 | 0.8 | 3.1827 | 4.1993 | 0 | 0.34981 | 0.35212 | 3.0487 | 3.0487 | 6.4069 | 6.4069
UG-15A | UG-15A-S10 | P0292 | 2.5488 | 1.2 | -4.825 | -4.825 | -3.125 | -3.125 | 32.85 | -4.825 | -4.825 | 4.125 | 3.325 | 0.8 | 9.45 | Shoring | 2.5488 | 3.325 | 0.8 | 3.2 | 33.6434 | 0 | 2.8036 | 2.8826 | 2.9969 | 2.9969 | 6.3066 | 6.3066
UG-15A | UG-15A-S10 | P0293 | 0.57651 | 1.2 | -4.825 | -4.825 | -3.125 | -3.125 | 32.59 | -4.825 | -4.825 | 4.125 | 3.325 | 0.8 | 9.45 | Shoring | 0.57651 | 3.325 | 0.8 | 3.2 | 7.6099 | 0 | 0.63416 | 0.65202 | 2.9969 | 2.9969 | 6.3065 | 6.3065
UG-15A | UG-15A-S10 | P0400 | 0.16814 | 1.2 | -4.825 | -4.825 | -3.125 | -3.125 | 32.52 | -4.825 | -4.825 | 4.125 | 3.325 | 0.8 | 9.45 | Shoring | 0.16814 | 3.325 | 0.8 | 3.2 | 2.2195 | 0 | 0.18496 | 0.19017 | 2.9969 | 2.9969 | 6.3065 | 6.3065
UG-15A | UG-15A-S10 | P0294 | 3.0191 | 1.2258 | -4.8379 | -4.8379 | -3.1121 | -3.1121 | 31.33 | -4.8379 | -4.8379 | 4.1379 | 3.3379 | 0.8 | 9.4887 | Shoring | 3.0191 | 3.3379 | 0.8 | 3.2258 | 40.2991 | 0 | 3.36 | 3.5631 | 2.9226 | 2.9226 | 6.1624 | 6.1624
UG-08 | UG-08-S01 | P0032-01 | 10 | 2.69 | -3.175 | -3.175 | 0.014997 | 0.014997 | 12.49 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 235.3894 | 18.45 | 56.8319 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S01 | P0032-02 | 5.3211 | 2.69 | -3.175 | -3.175 | 0.014997 | 0.014997 | 12.49 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 125.2537 | 9.8175 | 30.241 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S01 | P0466 | 2.6 | 2.69 | -3.175 | -3.175 | 0.014997 | 0.014997 | 12.59 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 61.2002 | 4.7969 | 14.7761 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S01 | P0467-01 | 2.0789 | 2.657 | -3.1585 | -3.1585 | -0.0015011 | -0.0015011 | 10.88 | -3.1585 | -3.1585 | 2.4585 | 1.6585 | 0.8 | 6.8455 | Open cut | 0 | 1.6585 | 0.8 | 4.657 | 0 | 48.2675 | 3.8013 | 11.5268 | 0 | 0 | 0.88059 | 0.88059
UG-08 | UG-08-S01 | P0467-02 | 0.5211 | 2.657 | -3.1585 | -3.1585 | -0.0015011 | -0.0015011 | 10.38 | -3.1585 | -3.1585 | 2.4585 | 1.6585 | 0.8 | 6.8455 | Open cut | 0 | 1.6585 | 0.8 | 4.657 | 0 | 12.0986 | 0.95282 | 2.8893 | 0 | 0 | 0.88059 | 0.88059
UG-08 | UG-08-S02 | P0099-01 | 9.4789 | 2.657 | -3.1585 | -3.1585 | -0.0015011 | -0.0015011 | 2.89 | -3.1585 | -3.1585 | 2.4585 | 1.6585 | 0.8 | 6.8455 | Shoring | 9.4789 | 1.6585 | 0.8 | 4.657 | 108.5261 | 0 | 17.3322 | 52.557 | 0 | 0 | 0.88059 | 0.88059
UG-08 | UG-08-S02 | P0099-02 | 8 | 2.657 | -3.1585 | -3.1585 | -0.0015011 | -0.0015011 | 2.83 | -3.1585 | -3.1585 | 2.4585 | 1.6585 | 0.8 | 6.8455 | Shoring | 8 | 1.6585 | 0.8 | 4.657 | 91.5938 | 0 | 14.628 | 44.357 | 0 | 0 | 0.88059 | 0.88059
UG-08 | UG-08-S03 | P0099-03 | 2 | 2.657 | -3.1585 | -3.1585 | -0.0015011 | -0.0015011 | 3.49 | -3.1585 | -3.1585 | 2.4585 | 1.6585 | 0.8 | 6.8455 | Shoring | 2 | 1.6585 | 0.8 | 4.657 | 22.8984 | 0 | 3.657 | 11.0893 | 0 | 0 | 0.88059 | 0.88059
UG-08 | UG-08-S03 | P0099-04 | 10 | 2.657 | -3.1585 | -3.1585 | -0.0015011 | -0.0015011 | 4.94 | -3.1585 | -3.1585 | 2.4585 | 1.6585 | 0.8 | 6.8455 | Shoring | 10 | 1.6585 | 0.8 | 4.657 | 114.4922 | 0 | 18.285 | 55.4463 | 0 | 0 | 0.88059 | 0.88059
UG-08 | UG-08-S03 | P0099-05 | 6.908 | 2.657 | -3.1585 | -3.1585 | -0.0015011 | -0.0015011 | 6.76 | -3.1585 | -3.1585 | 2.4585 | 1.6585 | 0.8 | 6.8455 | Shoring | 6.908 | 1.6585 | 0.8 | 4.657 | 79.0917 | 0 | 12.6313 | 38.3025 | 0 | 0 | 0.88059 | 0.88059
UG-08 | UG-08-S03 | P0457 | 2.6 | 2.657 | -3.1585 | -3.1585 | -0.0015011 | -0.0015011 | 10.21 | -3.1585 | -3.1585 | 2.4585 | 1.6585 | 0.8 | 6.8455 | Open cut | 0 | 1.6585 | 0.8 | 4.657 | 0 | 60.3669 | 4.7542 | 14.4163 | 0 | 0 | 0.88059 | 0.88059
UG-08 | UG-08-S03 | P0456-01 | 0.49192 | 2.69 | -3.175 | -3.175 | 0.014995 | 0.014995 | 12.29 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 11.5793 | 0.90759 | 2.7957 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S04 | P0456-02 | 2.108 | 2.69 | -3.175 | -3.175 | 0.014995 | 0.014995 | 12.77 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 49.6202 | 3.8893 | 11.9802 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S04 | P0045-01 | 7.892 | 2.69 | -3.175 | -3.175 | 0.014995 | 0.014995 | 14.85 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 185.7689 | 14.5607 | 44.8516 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S04 | P0045-02 | 2.9717 | 2.69 | -3.175 | -3.175 | 0.014995 | 0.014995 | 15.1 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 69.9498 | 5.4827 | 16.8885 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S04 | P0539 | 2.6 | 2.69 | -3.175 | -3.175 | 0.014995 | 0.014995 | 14.13 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 61.2011 | 4.797 | 14.7763 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S04 | P0538 | 2.6 | 2.69 | -3.175 | -3.175 | 0.015 | 0.015 | 14.13 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 61.2014 | 4.797 | 14.7764 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S04 | P0031-01 | 1.8283 | 2.69 | -3.175 | -3.175 | 0.015 | 0.015 | 15.56 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 43.0372 | 3.3733 | 10.3908 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S04 | P0031-02 | 10 | 2.69 | -3.175 | -3.175 | 0.015 | 0.015 | 16.73 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 235.3901 | 18.45 | 56.8322 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S04 | P0031-03 | 10 | 2.69 | -3.175 | -3.175 | 0.015 | 0.015 | 23.07 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 235.3901 | 18.45 | 56.8322 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S04 | P0031-04 | 8 | 2.69 | -3.175 | -3.175 | 0.015 | 0.015 | 69.23 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 188.3121 | 14.76 | 45.4658 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S05 | P0031-05 | 2 | 2.69 | -3.175 | -3.175 | 0.015 | 0.015 | 99 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 47.078 | 3.69 | 11.3664 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S05 | P0031-06 | 10 | 2.69 | -3.175 | -3.175 | 0.015 | 0.015 | 99 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 235.3901 | 18.45 | 56.8322 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S05 | P0031-07 | 10 | 2.69 | -3.175 | -3.175 | 0.015 | 0.015 | 99 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 235.3901 | 18.45 | 56.8322 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S05 | P0031-08 | 10 | 2.69 | -3.175 | -3.175 | 0.015 | 0.015 | 24.65 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 235.3901 | 18.45 | 56.8322 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S05 | P0031-09 | 10 | 2.69 | -3.175 | -3.175 | 0.015 | 0.015 | 16.63 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 235.3901 | 18.45 | 56.8322 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S05 | P0031-10 | 3.7315 | 2.69 | -3.175 | -3.175 | 0.015 | 0.015 | 13.84 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 87.8347 | 6.8845 | 21.2067 | 0 | 0 | 0.85546 | 0.85546
UG-08 | UG-08-S05 | P0458 | 1.7386 | 2.657 | -3.1585 | -3.172 | -0.0015009 | -0.015001 | 12.6 | -3.172 | -3.1652 | 2.4652 | 1.672 | 0.8 | 6.8725 | Open cut | 0 | 1.6652 | 0.8 | 4.657 | 0 | 40.5355 | 3.179 | 9.6397 | 0 | 0 | 0.88059 | 0.89246
UG-08 | UG-08-S05 | P0459 | 0.81145 | 2.606 | -3.1465 | -3.1528 | -0.040523 | -0.046833 | 12.15 | -3.1528 | -3.1496 | 2.4496 | 1.6528 | 0.8 | 6.8086 | Open cut | 0 | 1.6496 | 0.8 | 4.606 | 0 | 18.6344 | 1.463 | 4.328 | 0 | 0 | 0.93282 | 0.93848
UG-08 | UG-08-S05 | P0460 | 0.81157 | 2.6059 | -3.1528 | -3.1591 | -0.046836 | -0.053136 | 12.02 | -3.1591 | -3.1559 | 2.4559 | 1.6591 | 0.8 | 6.8211 | Open cut | 0 | 1.6559 | 0.8 | 4.6059 | 0 | 18.7109 | 1.4632 | 4.3286 | 0 | 0 | 0.93848 | 0.94413
UG-08 | UG-08-S05 | P0461 | 1.7384 | 2.657 | -3.1846 | -3.1981 | -0.027609 | -0.041109 | 12.02 | -3.1981 | -3.1914 | 2.4914 | 1.6981 | 0.8 | 6.9247 | Open cut | 0 | 1.6914 | 0.8 | 4.657 | 0 | 41.1942 | 3.1787 | 9.639 | 0 | 0 | 0.90355 | 0.91542
UG-08 | UG-08-S05 | P0463-01 | 1.1685 | 2.657 | -3.1981 | -3.2072 | -0.041109 | -0.050186 | 12.12 | -3.2072 | -3.2026 | 2.5026 | 1.7072 | 0.8 | 6.9429 | Open cut | 0 | 1.7026 | 0.8 | 4.657 | 0 | 27.8824 | 2.1366 | 6.479 | 0 | 0 | 0.91542 | 0.9234
UG-08 | UG-08-S05 | P0463-02 | 1.4333 | 2.657 | -3.2072 | -3.2183 | -0.050186 | -0.061319 | 12.22 | -3.2183 | -3.2128 | 2.5128 | 1.7183 | 0.8 | 6.9651 | Open cut | 0 | 1.7128 | 0.8 | 4.657 | 0 | 34.4142 | 2.6209 | 7.9474 | 0 | 0 | 0.9234 | 0.93319
UG-08 | UG-08-S05 | P0462 | 2.5976 | 2.657 | -3.2183 | -3.2385 | -0.06132 | -0.0815 | 10.9 | -3.2385 | -3.2284 | 2.5284 | 1.7385 | 0.8 | 7.0055 | Open cut | 0 | 1.7284 | 0.8 | 4.657 | 0 | 62.9672 | 4.7497 | 14.4027 | 0 | 0 | 0.93319 | 0.95093
UG-08 | UG-08-S05 | P0246-01 | 5.9691 | 2.657 | -3.2385 | -3.416 | -0.0815 | -0.25899 | 7.91 | -3.416 | -3.3272 | 2.6272 | 1.916 | 0.8 | 7.3605 | Open cut | 0 | 1.8272 | 0.8 | 4.657 | 0 | 153.5238 | 10.9144 | 33.0963 | 0 | 0 | 0.95093 | 1.107
UG-08 | UG-08-S05 | P0246-02 | 10 | 2.657 | -3.416 | -3.7133 | -0.25899 | -0.55635 | 4.73 | -3.7133 | -3.5647 | 2.8647 | 2.2133 | 0.8 | 7.9552 | Shoring | 10 | 2.0647 | 0.8 | 4.657 | 133.4077 | 0 | 18.285 | 55.4464 | 0 | 0 | 1.107 | 1.3684
UG-08 | UG-08-S05 | P0246-03 | 10 | 2.657 | -3.7133 | -4.0107 | -0.55635 | -0.8537 | 4.14 | -4.0107 | -3.862 | 3.162 | 2.5107 | 0.8 | 8.5499 | Shoring | 10 | 2.362 | 0.8 | 4.657 | 147.2554 | 0 | 18.285 | 55.4464 | 0 | 0.13514 | 1.3684 | 1.6299
UG-08 | UG-08-S05 | P0246-04 | 10 | 2.657 | -4.0107 | -4.3081 | -0.8537 | -1.1511 | 4.36 | -4.3081 | -4.1594 | 3.4594 | 2.8081 | 0.8 | 9.1446 | Shoring | 10 | 2.6594 | 0.8 | 4.657 | 161.1032 | 0 | 18.285 | 55.4464 | 0.13514 | 0.3966 | 1.6299 | 1.8914
UG-08 | UG-08-S05 | P0246-05 | 10 | 2.657 | -4.3081 | -4.6054 | -1.1511 | -1.4484 | 6.88 | -4.6054 | -4.4567 | 3.7567 | 3.1054 | 0.8 | 9.7393 | Shoring | 10 | 2.9567 | 0.8 | 4.657 | 174.951 | 0 | 18.285 | 55.4464 | 0.3966 | 0.65805 | 1.8914 | 2.1528
UG-08 | UG-08-S05 | P0246-06 | 7.6845 | 2.657 | -4.6054 | -4.8339 | -1.4484 | -1.6769 | 11.78 | -4.8339 | -4.7197 | 4.0197 | 3.3339 | 0.8 | 10.1963 | Shoring | 7.6845 | 3.2197 | 0.8 | 4.657 | 143.8501 | 0 | 14.0511 | 42.6076 | 0.65805 | 0.77419 | 2.1528 | 2.2689
UG-08 | UG-08-S05 | P0465-01 | 2.3155 | 2.657 | -4.8339 | -4.9028 | -1.6769 | -1.7458 | 16.68 | -4.9028 | -4.8683 | 4.1683 | 3.4028 | 0.8 | 10.334 | Shoring | 2.3155 | 3.3683 | 0.8 | 4.657 | 44.9488 | 0 | 4.2339 | 12.8387 | 0.77419 | 0.80174 | 2.2689 | 2.2965
UG-08 | UG-08-S05 | P0465-02 | 0.28322 | 2.657 | -4.9028 | -4.9112 | -1.7458 | -1.7542 | 18.31 | -4.9112 | -4.907 | 4.207 | 3.4112 | 0.8 | 10.3509 | Shoring | 0.28322 | 3.407 | 0.8 | 4.657 | 5.5489 | 0 | 0.51787 | 1.5704 | 0.80174 | 0.80511 | 2.2965 | 2.2999
UG-08 | UG-08-S05 | P0464 | 2.5999 | 2.657 | -4.9112 | -4.9885 | -1.7542 | -1.8315 | 16.73 | -4.9885 | -4.9498 | 4.2498 | 3.4885 | 0.8 | 10.5055 | Shoring | 2.5999 | 3.4498 | 0.8 | 4.657 | 51.4568 | 0 | 4.754 | 14.4157 | 0.80511 | 0.83604 | 2.2999 | 2.3308
UG-08 | UG-08-S05 | P0109-01 | 1.2168 | 2.657 | -4.9885 | -4.9885 | -1.8315 | -1.8315 | 15.93 | -4.9885 | -4.9885 | 4.2885 | 3.4885 | 0.8 | 10.5055 | Shoring | 1.2168 | 3.4885 | 0.8 | 4.657 | 24.3021 | 0 | 2.225 | 6.7469 | 0.83604 | 0.83604 | 2.3308 | 2.3308
UG-08 | UG-08-S06 | P0109-02 | 5.9 | 2.657 | -4.9885 | -4.9885 | -1.8315 | -1.8315 | 12.32 | -4.9885 | -4.9885 | 4.2885 | 3.4885 | 0.8 | 10.5055 | Shoring | 5.9 | 3.4885 | 0.8 | 4.657 | 117.8321 | 0 | 10.7881 | 32.7133 | 0.83604 | 0.83604 | 2.3308 | 2.3308
UG-08 | UG-08-S06 | P0109-03 | 10 | 2.657 | -4.9885 | -4.9885 | -1.8315 | -1.8315 | 7.59 | -4.9885 | -4.9885 | 4.2885 | 3.4885 | 0.8 | 10.5055 | Shoring | 10 | 3.4885 | 0.8 | 4.657 | 199.7154 | 0 | 18.285 | 55.4463 | 0.83604 | 0.83604 | 2.3308 | 2.3308
UG-08 | UG-08-S06 | P0109-04 | 10 | 2.657 | -4.9885 | -4.9885 | -1.8315 | -1.8315 | 5.21 | -4.9885 | -4.9885 | 4.2885 | 3.4885 | 0.8 | 10.5055 | Shoring | 10 | 3.4885 | 0.8 | 4.657 | 199.7154 | 0 | 18.285 | 55.4463 | 0.83604 | 0.83604 | 2.3308 | 2.3308
UG-08 | UG-08-S06 | P0109-05 | 10 | 2.657 | -4.9885 | -4.9885 | -1.8315 | -1.8315 | 5.04 | -4.9885 | -4.9885 | 4.2885 | 3.4885 | 0.8 | 10.5055 | Shoring | 10 | 3.4885 | 0.8 | 4.657 | 199.7154 | 0 | 18.285 | 55.4463 | 0.83604 | 0.83604 | 2.3308 | 2.3308
UG-08 | UG-08-S06 | P0109-06 | 10 | 2.657 | -4.9885 | -4.9885 | -1.8315 | -1.8315 | 5.67 | -4.9885 | -4.9885 | 4.2885 | 3.4885 | 0.8 | 10.5055 | Shoring | 10 | 3.4885 | 0.8 | 4.657 | 199.7154 | 0 | 18.285 | 55.4463 | 0.83604 | 0.83604 | 2.3308 | 2.3308
UG-08 | UG-08-S06 | P0109-07 | 7.114 | 2.657 | -4.9885 | -4.9885 | -1.8315 | -1.8315 | 8.86 | -4.9885 | -4.9885 | 4.2885 | 3.4885 | 0.8 | 10.5055 | Shoring | 7.114 | 3.4885 | 0.8 | 4.657 | 142.0775 | 0 | 13.0079 | 39.4445 | 0.83604 | 0.83604 | 2.3308 | 2.3308
UG-08 | UG-08-S07 | P0109-08 | 2.886 | 2.657 | -4.9885 | -4.9885 | -1.8315 | -1.8315 | 12.47 | -4.9885 | -4.9885 | 4.2885 | 3.4885 | 0.8 | 10.5055 | Shoring | 2.886 | 3.4885 | 0.8 | 4.657 | 57.6379 | 0 | 5.277 | 16.0018 | 0.83604 | 0.83604 | 2.3308 | 2.3308
UG-08 | UG-08-S07 | P0109-09 | 0.62014 | 2.657 | -4.9885 | -4.9885 | -1.8315 | -1.8315 | 14.18 | -4.9885 | -4.9885 | 4.2885 | 3.4885 | 0.8 | 10.5055 | Shoring | 0.62014 | 3.4885 | 0.8 | 4.657 | 12.3852 | 0 | 1.1339 | 3.4385 | 0.83604 | 0.83604 | 2.3308 | 2.3308
UG-08 | UG-08-S07 | P0143 | 2.4938 | 2.657 | -4.9885 | -4.9885 | -1.8315 | -1.8315 | 14.57 | -4.9885 | -4.9885 | 4.2885 | 3.4885 | 0.8 | 10.5055 | Shoring | 2.4938 | 3.4885 | 0.8 | 4.657 | 49.8049 | 0 | 4.5599 | 13.8271 | 0.83604 | 0.83604 | 2.3308 | 2.3308
UG-09 | UG-09-S01 | P0029-01 | 10 | 2.69 | -3.175 | -3.175 | 0.015004 | 0.015004 | 18.93 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 235.3907 | 18.45 | 56.8325 | 0 | 0 | 0.85545 | 0.85545
UG-09 | UG-09-S01 | P0029-02 | 8.6629 | 2.69 | -3.175 | -3.175 | 0.015004 | 0.015004 | 18.92 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 203.9166 | 15.9831 | 49.2334 | 0 | 0 | 0.85545 | 0.85545
UG-09 | UG-09-S01 | P0446-01 | 1.3371 | 2.69 | -3.175 | -3.175 | 0.015004 | 0.015004 | 19.35 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 31.4741 | 2.467 | 7.5991 | 0 | 0 | 0.85545 | 0.85545
UG-09 | UG-09-S01 | P0446-02 | 1.2629 | 2.69 | -3.175 | -3.175 | 0.015004 | 0.015004 | 19.65 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 29.7271 | 2.33 | 7.1773 | 0 | 0 | 0.85545 | 0.85545
UG-09 | UG-09-S01 | P0447 | 2.6 | 2.657 | -3.1585 | -3.1585 | -0.0015018 | -0.0015018 | 17.54 | -3.1585 | -3.1585 | 2.4585 | 1.6585 | 0.8 | 6.8455 | Open cut | 0 | 1.6585 | 0.8 | 4.657 | 0 | 60.3658 | 4.7541 | 14.416 | 0 | 0 | 0.88059 | 0.88059
UG-09 | UG-09-S02 | P0100-01 | 6.1371 | 2.657 | -3.1585 | -3.1585 | -0.0015018 | -0.0015018 | 12 | -3.1585 | -3.1585 | 2.4585 | 1.6585 | 0.8 | 6.8455 | Open cut | 0 | 1.6585 | 0.8 | 4.657 | 0 | 142.4895 | 11.2217 | 34.028 | 0 | 0 | 0.88059 | 0.88059
UG-09 | UG-09-S02 | P0100-02 | 10 | 2.657 | -3.1585 | -3.1585 | -0.0015018 | -0.0015018 | 6.19 | -3.1585 | -3.1585 | 2.4585 | 1.6585 | 0.8 | 6.8455 | Shoring | 10 | 1.6585 | 0.8 | 4.657 | 114.4922 | 0 | 18.285 | 55.4462 | 0 | 0 | 0.88059 | 0.88059
UG-09 | UG-09-S02 | P0100-03 | 4.1 | 2.657 | -3.1585 | -3.1585 | -0.0015018 | -0.0015018 | 6.18 | -3.1585 | -3.1585 | 2.4585 | 1.6585 | 0.8 | 6.8455 | Shoring | 4.1 | 1.6585 | 0.8 | 4.657 | 46.9418 | 0 | 7.4968 | 22.7329 | 0 | 0 | 0.88059 | 0.88059
UG-09 | UG-09-S03 | P0100-04 | 5.9 | 2.657 | -3.1585 | -3.1585 | -0.0015018 | -0.0015018 | 6.18 | -3.1585 | -3.1585 | 2.4585 | 1.6585 | 0.8 | 6.8455 | Shoring | 5.9 | 1.6585 | 0.8 | 4.657 | 67.5504 | 0 | 10.7881 | 32.7133 | 0 | 0 | 0.88059 | 0.88059
UG-09 | UG-09-S03 | P0100-05 | 10 | 2.657 | -3.1585 | -3.1585 | -0.0015018 | -0.0015018 | 7.51 | -3.1585 | -3.1585 | 2.4585 | 1.6585 | 0.8 | 6.8455 | Open cut | 0 | 1.6585 | 0.8 | 4.657 | 0 | 232.1764 | 18.285 | 55.4462 | 0 | 0 | 0.88059 | 0.88059
UG-09 | UG-09-S03 | P0100-06 | 5.0058 | 2.657 | -3.1585 | -3.1585 | -0.0015018 | -0.0015018 | 10.11 | -3.1585 | -3.1585 | 2.4585 | 1.6585 | 0.8 | 6.8455 | Open cut | 0 | 1.6585 | 0.8 | 4.657 | 0 | 116.2238 | 9.1532 | 27.7555 | 0 | 0 | 0.88059 | 0.88059
UG-09 | UG-09-S03 | P0449-01 | 2.1942 | 2.657 | -3.1585 | -3.1585 | -0.0015018 | -0.0015018 | 11.72 | -3.1585 | -3.1585 | 2.4585 | 1.6585 | 0.8 | 6.8455 | Open cut | 0 | 1.6585 | 0.8 | 4.657 | 0 | 50.9433 | 4.012 | 12.1658 | 0 | 0 | 0.88059 | 0.88059
UG-09 | UG-09-S04 | P0449-02 | 0.40585 | 2.657 | -3.1585 | -3.1585 | -0.0015018 | -0.0015018 | 12.98 | -3.1585 | -3.1585 | 2.4585 | 1.6585 | 0.8 | 6.8455 | Open cut | 0 | 1.6585 | 0.8 | 4.657 | 0 | 9.423 | 0.7421 | 2.2503 | 0 | 0 | 0.88059 | 0.88059
UG-09 | UG-09-S04 | P0448-01 | 2.3941 | 2.69 | -3.175 | -3.175 | 0.014995 | 0.014995 | 13.24 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 56.3556 | 4.4172 | 13.6064 | 0 | 0 | 0.85546 | 0.85546
UG-09 | UG-09-S04 | P0448-02 | 0.20583 | 2.69 | -3.175 | -3.175 | 0.014995 | 0.014995 | 15.63 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 4.845 | 0.37975 | 1.1698 | 0 | 0 | 0.85546 | 0.85546
UG-09 | UG-09-S04 | P0044 | 7.3881 | 2.69 | -3.175 | -3.175 | 0.014995 | 0.014995 | 15.84 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 173.9083 | 13.631 | 41.988 | 0 | 0 | 0.85546 | 0.85546
UG-09 | UG-09-S04 | P0537-01 | 2.4061 | 2.69 | -3.175 | -3.175 | 0.014995 | 0.014995 | 18.36 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 56.6358 | 4.4392 | 13.674 | 0 | 0 | 0.85546 | 0.85546
UG-09 | UG-09-S04 | P0537-02 | 0.19395 | 2.69 | -3.175 | -3.175 | 0.014995 | 0.014995 | 18.29 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 4.5654 | 0.35784 | 1.1023 | 0 | 0 | 0.85546 | 0.85546
UG-09 | UG-09-S04 | P0536 | 2.6 | 2.69 | -3.175 | -3.175 | 0.014996 | 0.014996 | 18.29 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 61.2012 | 4.797 | 14.7763 | 0 | 0 | 0.85546 | 0.85546
UG-09 | UG-09-S04 | P0030-01 | 7.206 | 2.69 | -3.175 | -3.175 | 0.014996 | 0.014996 | 19.55 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 169.6226 | 13.2951 | 40.9533 | 0 | 0 | 0.85546 | 0.85546
UG-09 | UG-09-S04 | P0030-02 | 10 | 2.69 | -3.175 | -3.175 | 0.014996 | 0.014996 | 24.19 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 235.3892 | 18.45 | 56.8319 | 0 | 0 | 0.85546 | 0.85546
UG-09 | UG-09-S04 | P0030-03 | 10 | 2.69 | -3.175 | -3.175 | 0.014996 | 0.014996 | 65.54 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 235.3892 | 18.45 | 56.8319 | 0 | 0 | 0.85546 | 0.85546
UG-09 | UG-09-S04 | P0030-04 | 10 | 2.69 | -3.175 | -3.175 | 0.014996 | 0.014996 | 99 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 235.3892 | 18.45 | 56.8319 | 0 | 0 | 0.85546 | 0.85546
UG-09 | UG-09-S04 | P0030-05 | 10 | 2.69 | -3.175 | -3.175 | 0.014996 | 0.014996 | 99 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 235.3892 | 18.45 | 56.8319 | 0 | 0 | 0.85546 | 0.85546
UG-09 | UG-09-S04 | P0030-06 | 10 | 2.69 | -3.175 | -3.175 | 0.014996 | 0.014996 | 99 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 235.3892 | 18.45 | 56.8319 | 0 | 0 | 0.85546 | 0.85546
UG-09 | UG-09-S04 | P0030-07 | 10 | 2.69 | -3.175 | -3.175 | 0.014996 | 0.014996 | 22.08 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 235.3892 | 18.45 | 56.8319 | 0 | 0 | 0.85546 | 0.85546
UG-09 | UG-09-S04 | P0030-08 | 0.4 | 2.69 | -3.175 | -3.175 | 0.014996 | 0.014996 | 21.78 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 9.4156 | 0.738 | 2.2733 | 0 | 0 | 0.85546 | 0.85546
UG-09 | UG-09-S05 | P0030-09 | 5.2239 | 2.69 | -3.175 | -3.175 | 0.014996 | 0.014996 | 17.99 | -3.175 | -3.175 | 2.475 | 1.675 | 0.8 | 6.895 | Open cut | 0 | 1.675 | 0.8 | 4.69 | 0 | 122.9655 | 9.6381 | 29.6885 | 0 | 0 | 0.85546 | 0.85546
UG-09 | UG-09-S05 | P0450 | 1.7386 | 2.657 | -3.1585 | -3.1703 | -0.0015009 | -0.013321 | 16.79 | -3.1703 | -3.1644 | 2.4644 | 1.6703 | 0.8 | 6.8691 | Open cut | 0 | 1.6644 | 0.8 | 4.657 | 0 | 40.5144 | 3.179 | 9.6397 | 0 | 0 | 0.88059 | 0.89098
UG-09 | UG-09-S05 | P0451 | 0.81145 | 2.606 | -3.1448 | -3.1503 | -0.038843 | -0.044353 | 16.37 | -3.1503 | -3.1476 | 2.4476 | 1.6503 | 0.8 | 6.8036 | Open cut | 0 | 1.6476 | 0.8 | 4.606 | 0 | 18.6101 | 1.463 | 4.328 | 0 | 0 | 0.93131 | 0.93625
UG-09 | UG-09-S05 | P0452 | 0.81157 | 2.6059 | -3.1503 | -3.1558 | -0.044356 | -0.049876 | 16.26 | -3.1558 | -3.1531 | 2.4531 | 1.6558 | 0.8 | 6.8146 | Open cut | 0 | 1.6531 | 0.8 | 4.6059 | 0 | 18.6773 | 1.4632 | 4.3286 | 0 | 0 | 0.93626 | 0.94121
UG-09 | UG-09-S05 | P0453-01 | 1.0145 | 2.657 | -3.1814 | -3.1882 | -0.024349 | -0.031247 | 16.26 | -3.1882 | -3.1848 | 2.4848 | 1.6882 | 0.8 | 6.905 | Open cut | 0 | 1.6848 | 0.8 | 4.657 | 0 | 23.9422 | 1.855 | 5.625 | 0 | 0 | 0.90068 | 0.90674
UG-09 | UG-09-S05 | P0453-02 | 0.72395 | 2.657 | -3.1882 | -3.1932 | -0.031247 | -0.036169 | 16.34 | -3.1932 | -3.1907 | 2.4907 | 1.6932 | 0.8 | 6.9148 | Open cut | 0 | 1.6907 | 0.8 | 4.657 | 0 | 17.1478 | 1.3237 | 4.014 | 0 | 0 | 0.90674 | 0.91107
UG-09 | UG-09-S05 | P0455 | 2.5973 | 2.657 | -3.1932 | -3.2108 | -0.036169 | -0.053819 | 14.53 | -3.2108 | -3.202 | 2.502 | 1.7108 | 0.8 | 6.9501 | Open cut | 0 | 1.702 | 0.8 | 4.657 | 0 | 61.9508 | 4.7492 | 14.4013 | 0 | 0 | 0.91107 | 0.92659
UG-09 | UG-09-S05 | P0454 | 2.6011 | 2.657 | -3.2108 | -3.2285 | -0.053821 | -0.071501 | 12.86 | -3.2285 | -3.2197 | 2.5197 | 1.7285 | 0.8 | 6.9855 | Open cut | 0 | 1.7197 | 0.8 | 4.657 | 0 | 62.7159 | 4.7561 | 14.4221 | 0 | 0 | 0.92659 | 0.94214
UG-09 | UG-09-S05 | P0245-01 | 2.5776 | 2.657 | -3.2285 | -3.2982 | -0.071501 | -0.14123 | 11.3 | -3.2982 | -3.2634 | 2.5634 | 1.7982 | 0.8 | 7.1249 | Open cut | 0 | 1.7634 | 0.8 | 4.657 | 0 | 63.8202 | 4.7132 | 14.292 | 0 | 0 | 0.94214 | 1.0034
UG-09 | UG-09-S06 | P0245-02 | 1.5 | 2.657 | -3.2982 | -3.3388 | -0.14123 | -0.1818 | 10.44 | -3.3388 | -3.3185 | 2.6185 | 1.8388 | 0.8 | 7.2061 | Open cut | 0 | 1.8185 | 0.8 | 4.657 | 0 | 38.3814 | 2.7427 | 8.3169 | 0 | 0 | 1.0034 | 1.0391
UG-09 | UG-09-S06 | P0245-03 | 10 | 2.657 | -3.3388 | -3.6093 | -0.1818 | -0.4523 | 5.83 | -3.6093 | -3.4741 | 2.7741 | 2.1093 | 0.8 | 7.7471 | Shoring | 10 | 1.9741 | 0.8 | 4.657 | 129.1875 | 0 | 18.285 | 55.4463 | 0 | 0 | 1.0391 | 1.277
UG-09 | UG-09-S06 | P0245-04 | 10 | 2.657 | -3.6093 | -3.8798 | -0.4523 | -0.7228 | 3.73 | -3.8798 | -3.7446 | 3.0446 | 2.3798 | 0.8 | 8.2881 | Shoring | 10 | 2.2446 | 0.8 | 4.657 | 141.7847 | 0 | 18.285 | 55.4463 | 0 | 0.020052 | 1.277 | 1.5148
UG-09 | UG-09-S06 | P0245-05 | 10 | 2.657 | -3.8798 | -4.1503 | -0.7228 | -0.99331 | 3.67 | -4.1503 | -4.0151 | 3.3151 | 2.6503 | 0.8 | 8.8291 | Shoring | 10 | 2.5151 | 0.8 | 4.657 | 154.382 | 0 | 18.285 | 55.4463 | 0.020052 | 0.2579 | 1.5148 | 1.7527
UG-09 | UG-09-S06 | P0245-06 | 10 | 2.657 | -4.1503 | -4.4208 | -0.99331 | -1.2638 | 4.61 | -4.4208 | -4.2856 | 3.5856 | 2.9208 | 0.8 | 9.3701 | Shoring | 10 | 2.7856 | 0.8 | 4.657 | 166.9792 | 0 | 18.285 | 55.4463 | 0.2579 | 0.49574 | 1.7527 | 1.9905
UG-09 | UG-09-S06 | P0245-07 | 10 | 2.657 | -4.4208 | -4.6913 | -1.2638 | -1.5343 | 8.25 | -4.6913 | -4.5561 | 3.8561 | 3.1913 | 0.8 | 9.9111 | Shoring | 10 | 3.0561 | 0.8 | 4.657 | 179.5765 | 0 | 18.285 | 55.4463 | 0.49574 | 0.71714 | 1.9905 | 2.2119
UG-09 | UG-09-S06 | P0245-08 | 5.4181 | 2.657 | -4.6913 | -4.8379 | -1.5343 | -1.6809 | 13.96 | -4.8379 | -4.7646 | 4.0646 | 3.3379 | 0.8 | 10.2042 | Shoring | 5.4181 | 3.2646 | 0.8 | 4.657 | 102.5587 | 0 | 9.9071 | 30.0415 | 0.71714 | 0.77578 | 2.2119 | 2.2705
UG-09 | UG-09-S06 | P0469 | 2.599 | 2.657 | -4.8379 | -4.9082 | -1.6809 | -1.7512 | 16.6 | -4.9082 | -4.873 | 4.173 | 3.4082 | 0.8 | 10.3448 | Shoring | 2.599 | 3.373 | 0.8 | 4.657 | 50.5075 | 0 | 4.7522 | 14.4103 | 0.77578 | 0.8039 | 2.2705 | 2.2987
UG-09 | UG-09-S06 | P0468-01 | 1.9829 | 2.657 | -4.9082 | -4.9618 | -1.7512 | -1.8048 | 15.31 | -4.9618 | -4.935 | 4.235 | 3.4618 | 0.8 | 10.4521 | Shoring | 1.9829 | 3.435 | 0.8 | 4.657 | 39.1074 | 0 | 3.6257 | 10.9944 | 0.8039 | 0.82536 | 2.2987 | 2.3201
UG-09 | UG-09-S06 | P0468-02 | 0.61715 | 2.657 | -4.9618 | -4.9785 | -1.8048 | -1.8215 | 14.91 | -4.9785 | -4.9702 | 4.2702 | 3.4785 | 0.8 | 10.4855 | Shoring | 0.61715 | 3.4702 | 0.8 | 4.657 | 12.2726 | 0 | 1.1285 | 3.4218 | 0.82536 | 0.83204 | 2.3201 | 2.3268
UG-09 | UG-09-S07 | P0144-01 | 9.3829 | 2.657 | -4.9785 | -4.9785 | -1.8215 | -1.8215 | 9.68 | -4.9785 | -4.9785 | 4.2785 | 3.4785 | 0.8 | 10.4855 | Shoring | 9.3829 | 3.4785 | 0.8 | 4.657 | 186.9527 | 0 | 17.1565 | 52.0243 | 0.83204 | 0.83204 | 2.3268 | 2.3268
UG-09 | UG-09-S07 | P0144-02 | 10 | 2.657 | -4.9785 | -4.9785 | -1.8215 | -1.8215 | 6.05 | -4.9785 | -4.9785 | 4.2785 | 3.4785 | 0.8 | 10.4855 | Shoring | 10 | 3.4785 | 0.8 | 4.657 | 199.2494 | 0 | 18.285 | 55.4461 | 0.83204 | 0.83204 | 2.3268 | 2.3268
UG-09 | UG-09-S07 | P0144-03 | 10 | 2.657 | -4.9785 | -4.9785 | -1.8215 | -1.8215 | 5.04 | -4.9785 | -4.9785 | 4.2785 | 3.4785 | 0.8 | 10.4855 | Shoring | 10 | 3.4785 | 0.8 | 4.657 | 199.2494 | 0 | 18.285 | 55.4461 | 0.83204 | 0.83204 | 2.3268 | 2.3268
UG-09 | UG-09-S07 | P0144-04 | 10 | 2.657 | -4.9785 | -4.9785 | -1.8215 | -1.8215 | 5.08 | -4.9785 | -4.9785 | 4.2785 | 3.4785 | 0.8 | 10.4855 | Shoring | 10 | 3.4785 | 0.8 | 4.657 | 199.2494 | 0 | 18.285 | 55.4461 | 0.83204 | 0.83204 | 2.3268 | 2.3268
UG-09 | UG-09-S07 | P0144-05 | 10 | 2.657 | -4.9785 | -4.9785 | -1.8215 | -1.8215 | 6.97 | -4.9785 | -4.9785 | 4.2785 | 3.4785 | 0.8 | 10.4855 | Shoring | 10 | 3.4785 | 0.8 | 4.657 | 199.2494 | 0 | 18.285 | 55.4461 | 0.83204 | 0.83204 | 2.3268 | 2.3268
UG-09 | UG-09-S07 | P0144-06 | 1.799 | 2.657 | -4.9785 | -4.9785 | -1.8215 | -1.8215 | 11.33 | -4.9785 | -4.9785 | 4.2785 | 3.4785 | 0.8 | 10.4855 | Shoring | 1.799 | 3.4785 | 0.8 | 4.657 | 35.845 | 0 | 3.2895 | 9.9748 | 0.83204 | 0.83204 | 2.3268 | 2.3268
UG-09 | UG-09-S08 | P0144-07 | 6 | 2.657 | -4.9785 | -4.9785 | -1.8215 | -1.8215 | 12.33 | -4.9785 | -4.9785 | 4.2785 | 3.4785 | 0.8 | 10.4855 | Shoring | 6 | 3.4785 | 0.8 | 4.657 | 119.5492 | 0 | 10.9709 | 33.2675 | 0.83204 | 0.83204 | 2.3268 | 2.3268
UG-10 | UG-10-S01 | P0043 | 2.2441 | 2.69 | -3.205 | -3.205 | -0.015002 | -0.015002 | 8.93 | -3.205 | -3.205 | 2.505 | 1.705 | 0.8 | 6.955 | Open cut | 0 | 1.705 | 0.8 | 4.69 | 0 | 53.8096 | 4.1403 | 12.7536 | 0 | 0 | 0.88151 | 0.88151
UG-10 | UG-10-S01 | P0530 | 2.6 | 2.69 | -3.205 | -3.205 | -0.015002 | -0.015002 | 6.33 | -3.205 | -3.205 | 2.505 | 1.705 | 0.8 | 6.955 | Shoring | 2.6 | 1.705 | 0.8 | 4.69 | 30.5458 | 0 | 4.797 | 14.7763 | 0 | 0 | 0.88151 | 0.88151
UG-10 | UG-10-S01 | P0531 | 2.6 | 2.657 | -3.1885 | -3.1885 | -0.031502 | -0.031502 | 6.32 | -3.1885 | -3.1885 | 2.4885 | 1.6885 | 0.8 | 6.9055 | Shoring | 2.6 | 1.6885 | 0.8 | 4.657 | 30.1313 | 0 | 4.7541 | 14.4161 | 0 | 0 | 0.90697 | 0.90697
UG-10 | UG-10-S02 | P0098-01 | 2.5559 | 2.657 | -3.1885 | -3.1885 | -0.031502 | -0.031502 | 6.32 | -3.1885 | -3.1885 | 2.4885 | 1.6885 | 0.8 | 6.9055 | Shoring | 2.5559 | 1.6885 | 0.8 | 4.657 | 29.6204 | 0 | 4.6735 | 14.1716 | 0 | 0 | 0.90697 | 0.90697
UG-10 | UG-10-S02 | P0098-02 | 10 | 2.657 | -3.1885 | -3.1885 | -0.031502 | -0.031502 | 6.3 | -3.1885 | -3.1885 | 2.4885 | 1.6885 | 0.8 | 6.9055 | Shoring | 10 | 1.6885 | 0.8 | 4.657 | 115.8892 | 0 | 18.285 | 55.4462 | 0 | 0 | 0.90697 | 0.90697
UG-10 | UG-10-S02 | P0098-03 | 10 | 2.657 | -3.1885 | -3.1885 | -0.031502 | -0.031502 | 3.73 | -3.1885 | -3.1885 | 2.4885 | 1.6885 | 0.8 | 6.9055 | Shoring | 10 | 1.6885 | 0.8 | 4.657 | 115.8892 | 0 | 18.285 | 55.4462 | 0 | 0 | 0.90697 | 0.90697
UG-10 | UG-10-S02 | P0098-04 | 10 | 2.657 | -3.1885 | -3.1885 | -0.031502 | -0.031502 | 3.74 | -3.1885 | -3.1885 | 2.4885 | 1.6885 | 0.8 | 6.9055 | Shoring | 10 | 1.6885 | 0.8 | 4.657 | 115.8892 | 0 | 18.285 | 55.4462 | 0 | 0 | 0.90697 | 0.90697
UG-10 | UG-10-S02 | P0098-05 | 10 | 2.657 | -3.1885 | -3.1885 | -0.031502 | -0.031502 | 2.8 | -3.1885 | -3.1885 | 2.4885 | 1.6885 | 0.8 | 6.9055 | Shoring | 10 | 1.6885 | 0.8 | 4.657 | 115.8892 | 0 | 18.285 | 55.4462 | 0 | 0 | 0.90697 | 0.90697
UG-10 | UG-10-S02 | P0098-06 | 10 | 2.657 | -3.1885 | -3.1885 | -0.031502 | -0.031502 | 2.8 | -3.1885 | -3.1885 | 2.4885 | 1.6885 | 0.8 | 6.9055 | Shoring | 10 | 1.6885 | 0.8 | 4.657 | 115.8892 | 0 | 18.285 | 55.4462 | 0 | 0 | 0.90697 | 0.90697
UG-10 | UG-10-S02 | P0098-07 | 10 | 2.657 | -3.1885 | -3.1885 | -0.031502 | -0.031502 | 3.76 | -3.1885 | -3.1885 | 2.4885 | 1.6885 | 0.8 | 6.9055 | Shoring | 10 | 1.6885 | 0.8 | 4.657 | 115.8892 | 0 | 18.285 | 55.4462 | 0 | 0 | 0.90697 | 0.90697
UG-10 | UG-10-S02 | P0098-08 | 3.0605 | 2.657 | -3.1885 | -3.1885 | -0.031502 | -0.031502 | 3.76 | -3.1885 | -3.1885 | 2.4885 | 1.6885 | 0.8 | 6.9055 | Shoring | 3.0605 | 1.6885 | 0.8 | 4.657 | 35.4683 | 0 | 5.5962 | 16.9695 | 0 | 0 | 0.90697 | 0.90697
UG-10 | UG-10-S02 | P0532 | 2.6 | 2.657 | -3.1885 | -3.1885 | -0.031502 | -0.031502 | 3.77 | -3.1885 | -3.1885 | 2.4885 | 1.6885 | 0.8 | 6.9055 | Shoring | 2.6 | 1.6885 | 0.8 | 4.657 | 30.1312 | 0 | 4.7541 | 14.416 | 0 | 0 | 0.90697 | 0.90697
UG-10 | UG-10-S02 | P0533 | 2.6 | 2.657 | -3.1885 | -3.1885 | -0.031502 | -0.031502 | 3.77 | -3.1885 | -3.1885 | 2.4885 | 1.6885 | 0.8 | 6.9055 | Shoring | 2.6 | 1.6885 | 0.8 | 4.657 | 30.1312 | 0 | 4.7541 | 14.416 | 0 | 0 | 0.90697 | 0.90697
UG-10 | UG-10-S02 | P0101-01 | 1.7395 | 2.657 | -3.1885 | -3.1967 | -0.031502 | -0.039703 | 5.17 | -3.1967 | -3.1926 | 2.4926 | 1.6967 | 0.8 | 6.9219 | Shoring | 1.7395 | 1.6926 | 0.8 | 4.657 | 20.1917 | 0 | 3.1806 | 9.6447 | 0 | 0 | 0.90697 | 0.91418
UG-10 | UG-10-S02 | P0101-02 | 10 | 2.657 | -3.1967 | -3.2438 | -0.039703 | -0.08685 | 4.68 | -3.2438 | -3.2203 | 2.5203 | 1.7438 | 0.8 | 7.0162 | Shoring | 10 | 1.7203 | 0.8 | 4.657 | 117.3689 | 0 | 18.285 | 55.4462 | 0 | 0 | 0.91418 | 0.95564
UG-10 | UG-10-S02 | P0101-03 | 10 | 2.657 | -3.2438 | -3.291 | -0.08685 | -0.134 | 4.5 | -3.291 | -3.2674 | 2.5674 | 1.791 | 0.8 | 7.1105 | Shoring | 10 | 1.7674 | 0.8 | 4.657 | 119.5646 | 0 | 18.285 | 55.4462 | 0 | 0 | 0.95564 | 0.99709
UG-10 | UG-10-S02 | P0101-04 | 10 | 2.657 | -3.291 | -3.3381 | -0.134 | -0.18114 | 2.47 | -3.3381 | -3.3146 | 2.6146 | 1.8381 | 0.8 | 7.2048 | Shoring | 10 | 1.8146 | 0.8 | 4.657 | 121.7602 | 0 | 18.285 | 55.4462 | 0 | 0 | 0.99709 | 1.0385
UG-10 | UG-10-S02 | P0101-05 | 4.3 | 2.657 | -3.3381 | -3.3584 | -0.18114 | -0.20142 | 2.46 | -3.3584 | -3.3483 | 2.6483 | 1.8584 | 0.8 | 7.2453 | Shoring | 4.3 | 1.8483 | 0.8 | 4.657 | 53.0319 | 0 | 7.8625 | 23.8419 | 0 | 0 | 1.0385 | 1.0564
UG-10 | UG-10-S03 | P0101-06 | 5.7 | 2.657 | -3.3584 | -3.3853 | -0.20142 | -0.22829 | 2.45 | -3.3853 | -3.3718 | 2.6718 | 1.8853 | 0.8 | 7.2991 | Shoring | 5.7 | 1.8718 | 0.8 | 4.657 | 70.9239 | 0 | 10.4224 | 31.6043 | 0 | 0 | 1.0564 | 1.08
UG-10 | UG-10-S03 | P0101-07 | 10 | 2.657 | -3.3853 | -3.4324 | -0.22829 | -0.27544 | 2.73 | -3.4324 | -3.4089 | 2.7089 | 1.9324 | 0.8 | 7.3934 | Shoring | 10 | 1.9089 | 0.8 | 4.657 | 126.1514 | 0 | 18.285 | 55.4462 | 0 | 0 | 1.08 | 1.1215
UG-10 | UG-10-S03 | P0101-08 | 8.8335 | 2.657 | -3.4324 | -3.4741 | -0.27544 | -0.31708 | 8.66 | -3.4741 | -3.4533 | 2.7533 | 1.9741 | 0.8 | 7.4767 | Open cut | 0 | 1.9533 | 0.8 | 4.657 | 0 | 244.3585 | 16.152 | 48.9784 | 0 | 0 | 1.1215 | 1.1581
UG-10 | UG-10-S03 | P0686-01 | 1.1665 | 2.657 | -3.4741 | -3.4796 | -0.31708 | -0.32258 | 11.68 | -3.4796 | -3.4768 | 2.7768 | 1.9796 | 0.8 | 7.4877 | Open cut | 0 | 1.9768 | 0.8 | 4.657 | 0 | 32.7008 | 2.1329 | 6.4678 | 0 | 0 | 1.1581 | 1.1629
UG-10 | UG-10-S03 | P0686-02 | 1.4335 | 2.657 | -3.4796 | -3.4863 | -0.32258 | -0.32934 | 10.56 | -3.4863 | -3.483 | 2.783 | 1.9863 | 0.8 | 7.5012 | Open cut | 0 | 1.983 | 0.8 | 4.657 | 0 | 40.3238 | 2.6211 | 7.9481 | 0 | 0 | 1.1629 | 1.1689
UG-10 | UG-10-S03 | P0687 | 2.5787 | 2.69 | -3.5028 | -3.515 | -0.31284 | -0.325 | 10.35 | -3.515 | -3.5089 | 2.8089 | 2.015 | 0.8 | 7.575 | Open cut | 0 | 2.0089 | 0.8 | 4.69 | 0 | 73.8367 | 4.7576 | 14.655 | 0 | 0 | 1.1402 | 1.1507
UG-10 | UG-10-S03 | P0244-01 | 2.3879 | 2.69 | -3.515 | -3.761 | -0.325 | -0.57104 | 10.31 | -3.761 | -3.638 | 2.938 | 2.261 | 0.8 | 8.0671 | Open cut | 0 | 2.138 | 0.8 | 4.69 | 0 | 73.3628 | 4.4056 | 13.5707 | 0 | 0 | 1.1507 | 1.3644
UG-10 | UG-10-S04 | P0244-02 | 3.6 | 2.69 | -3.761 | -4.132 | -0.57104 | -0.94197 | 10.32 | -4.132 | -3.9465 | 3.2465 | 2.632 | 0.8 | 8.8089 | Shoring | 3.6 | 2.4465 | 0.8 | 4.69 | 54.8139 | 0 | 6.642 | 20.4595 | 0 | 0.21015 | 1.3644 | 1.6866
UG-10 | UG-10-S04 | P0244-03 | 3.2927 | 2.69 | -4.132 | -4.4712 | -0.94197 | -1.2812 | 10.53 | -4.4712 | -4.3016 | 3.6016 | 2.9712 | 0.8 | 9.4875 | Shoring | 3.2927 | 2.8016 | 0.8 | 4.69 | 55.6183 | 0 | 6.075 | 18.713 | 0.21015 | 0.5048 | 1.6866 | 1.9812
UG-10 | UG-10-S04 | P0685 | 2.5803 | 2.69 | -4.4712 | -4.7371 | -1.2812 | -1.5471 | 11.02 | -4.7371 | -4.6042 | 3.9042 | 3.2371 | 0.8 | 10.0192 | Shoring | 2.5803 | 3.1042 | 0.8 | 4.69 | 47.2471 | 0 | 4.7607 | 14.6645 | 0.5048 | 0.7134 | 1.9812 | 2.1898
UG-10 | UG-10-S04 | P0684 | 2.6 | 2.69 | -4.7371 | -5.005 | -1.5471 | -1.815 | 10.33 | -5.005 | -4.8711 | 4.1711 | 3.505 | 0.8 | 10.555 | Shoring | 2.6 | 3.3711 | 0.8 | 4.69 | 50.8618 | 0 | 4.797 | 14.7764 | 0.7134 | 0.81926 | 2.1898 | 2.2957
UG-10 | UG-10-S04 | P0108-01 | 1.527 | 2.69 | -5.005 | -5.005 | -1.815 | -1.815 | 9.66 | -5.005 | -5.005 | 4.305 | 3.505 | 0.8 | 10.555 | Shoring | 1.527 | 3.505 | 0.8 | 4.69 | 30.8306 | 0 | 2.8173 | 8.6782 | 0.81926 | 0.81926 | 2.2957 | 2.2957
UG-10 | UG-10-S04 | P0108-02 | 10 | 2.69 | -5.005 | -5.005 | -1.815 | -1.815 | 6.44 | -5.005 | -5.005 | 4.305 | 3.505 | 0.8 | 10.555 | Shoring | 10 | 3.505 | 0.8 | 4.69 | 201.9046 | 0 | 18.45 | 56.8322 | 0.81926 | 0.81926 | 2.2957 | 2.2957
UG-10 | UG-10-S04 | P0108-03 | 10 | 2.69 | -5.005 | -5.005 | -1.815 | -1.815 | 5.75 | -5.005 | -5.005 | 4.305 | 3.505 | 0.8 | 10.555 | Shoring | 10 | 3.505 | 0.8 | 4.69 | 201.9046 | 0 | 18.45 | 56.8322 | 0.81926 | 0.81926 | 2.2957 | 2.2957
UG-10 | UG-10-S04 | P0108-04 | 10 | 2.69 | -5.005 | -5.005 | -1.815 | -1.815 | 5.89 | -5.005 | -5.005 | 4.305 | 3.505 | 0.8 | 10.555 | Shoring | 10 | 3.505 | 0.8 | 4.69 | 201.9046 | 0 | 18.45 | 56.8322 | 0.81926 | 0.81926 | 2.2957 | 2.2957
UG-10 | UG-10-S04 | P0108-05 | 9.599 | 2.69 | -5.005 | -5.005 | -1.815 | -1.815 | 8.13 | -5.005 | -5.005 | 4.305 | 3.505 | 0.8 | 10.555 | Shoring | 9.599 | 3.505 | 0.8 | 4.69 | 193.8082 | 0 | 17.7102 | 54.5533 | 0.81926 | 0.81926 | 2.2957 | 2.2957
UG-10 | UG-10-S05 | P0108-06 | 0.401 | 2.69 | -5.005 | -5.005 | -1.815 | -1.815 | 12.49 | -5.005 | -5.005 | 4.305 | 3.505 | 0.8 | 10.555 | Shoring | 0.401 | 3.505 | 0.8 | 4.69 | 8.0964 | 0 | 0.73985 | 2.279 | 0.81926 | 0.81926 | 2.2957 | 2.2957
UG-10 | UG-10-S05 | P0108-07 | 5.5987 | 2.69 | -5.005 | -5.005 | -1.815 | -1.815 | 12.71 | -5.005 | -5.005 | 4.305 | 3.505 | 0.8 | 10.555 | Shoring | 5.5987 | 3.505 | 0.8 | 4.69 | 113.0409 | 0 | 10.3297 | 31.8188 | 0.81926 | 0.81926 | 2.2957 | 2.2957
UG-11 | UG-11-S01 | P0259 | 5.0632 | 2.0696 | -4.6248 | -4.6248 | -2.0552 | -2.0552 | 9.65 | -4.6248 | -4.6248 | 3.9248 | 3.1248 | 0.8 | 9.4844 | Shoring | 5.0632 | 3.1248 | 0.8 | 4.0696 | 80.8705 | 0 | 7.7709 | 17.0327 | 1.1882 | 1.1882 | 3.1072 | 3.1072
UG-11 | UG-11-S01 | P0697 | 1.4722 | 2.045 | -4.6125 | -4.6125 | -2.0675 | -2.0675 | 9.68 | -4.6125 | -4.6125 | 3.9125 | 3.1125 | 0.8 | 9.4475 | Shoring | 1.4722 | 3.1125 | 0.8 | 4.045 | 23.2998 | 0 | 2.2415 | 4.8357 | 1.2089 | 1.2089 | 3.151 | 3.151
UG-11 | UG-11-S01 | P0698 | 0.25049 | 2.045 | -4.6125 | -4.6125 | -2.0675 | -2.0675 | 9.68 | -4.6125 | -4.6125 | 3.9125 | 3.1125 | 0.8 | 9.4475 | Shoring | 0.25049 | 3.1125 | 0.8 | 4.045 | 3.9642 | 0 | 0.38137 | 0.82274 | 1.2089 | 1.2089 | 3.151 | 3.151
UG-11 | UG-11-S01 | P0258-01 | 3.2141 | 2.0696 | -4.6248 | -4.6248 | -2.0552 | -2.0552 | 9.68 | -4.6248 | -4.6248 | 3.9248 | 3.1248 | 0.8 | 9.4844 | Shoring | 3.2141 | 3.1248 | 0.8 | 4.0696 | 51.337 | 0 | 4.933 | 10.8125 | 1.1882 | 1.1882 | 3.1072 | 3.1072
UG-11 | UG-11-S01 | P0258-02 | 10 | 2.0696 | -4.6248 | -4.6248 | -2.0552 | -2.0552 | 9.92 | -4.6248 | -4.6248 | 3.9248 | 3.1248 | 0.8 | 9.4844 | Shoring | 10 | 3.1248 | 0.8 | 4.0696 | 159.7238 | 0 | 15.348 | 33.6406 | 1.1882 | 1.1882 | 3.1072 | 3.1072
UG-11 | UG-11-S01 | P0258-03 | 10 | 2.0696 | -4.6248 | -4.6248 | -2.0552 | -2.0552 | 15.53 | -4.6248 | -4.6248 | 3.9248 | 3.1248 | 0.8 | 9.4844 | Shoring | 10 | 3.1248 | 0.8 | 4.0696 | 159.7238 | 0 | 15.348 | 33.6406 | 1.1882 | 1.1882 | 3.1072 | 3.1072
UG-11 | UG-11-S01 | P0258-04 | 1.7511 | 2.0696 | -4.6248 | -4.6248 | -2.0552 | -2.0552 | 22.66 | -4.6248 | -4.6248 | 3.9248 | 3.1248 | 0.8 | 9.4844 | Shoring | 1.7511 | 3.1248 | 0.8 | 4.0696 | 27.969 | 0 | 2.6876 | 5.8908 | 1.1882 | 1.1882 | 3.1072 | 3.1072
UG-11 | UG-11-S01 | P0547 | 3.1 | 2.0696 | -4.6248 | -4.6248 | -2.0552 | -2.0552 | 23.77 | -4.6248 | -4.6248 | 3.9248 | 3.1248 | 0.8 | 9.4844 | Shoring | 3.1 | 3.1248 | 0.8 | 4.0696 | 49.5142 | 0 | 4.7579 | 10.4285 | 1.1882 | 1.1882 | 3.1072 | 3.1072
UG-11 | UG-11-S01 | P0546-01 | 2.5489 | 2.0696 | -4.6248 | -4.6248 | -2.0552 | -2.0552 | 25.91 | -4.6248 | -4.6248 | 3.9248 | 3.1248 | 0.8 | 9.4844 | Shoring | 2.5489 | 3.1248 | 0.8 | 4.0696 | 40.7123 | 0 | 3.9121 | 8.5747 | 1.1882 | 1.1882 | 3.1072 | 3.1072
UG-11 | UG-11-S02 | P0546-02 | 0.55109 | 2.0696 | -4.6248 | -4.6248 | -2.0552 | -2.0552 | 26.09 | -4.6248 | -4.6248 | 3.9248 | 3.1248 | 0.8 | 9.4844 | Shoring | 0.55109 | 3.1248 | 0.8 | 4.0696 | 8.8022 | 0 | 0.84581 | 1.8539 | 1.1882 | 1.1882 | 3.1072 | 3.1072
UG-11 | UG-11-S02 | P0234-01 | 2.0489 | 2.0696 | -4.6248 | -4.6248 | -2.0552 | -2.0552 | 26.17 | -4.6248 | -4.6248 | 3.9248 | 3.1248 | 0.8 | 9.4844 | Shoring | 2.0489 | 3.1248 | 0.8 | 4.0696 | 32.726 | 0 | 3.1447 | 6.8926 | 1.1882 | 1.1882 | 3.1072 | 3.1072
UG-11 | UG-11-S02 | P0234-02 | 3.2857 | 2.0696 | -4.6248 | -4.6248 | -2.0552 | -2.0552 | 26.53 | -4.6248 | -4.6248 | 3.9248 | 3.1248 | 0.8 | 9.4844 | Shoring | 3.2857 | 3.1248 | 0.8 | 4.0696 | 52.4809 | 0 | 5.0429 | 11.0534 | 1.1882 | 1.1882 | 3.1072 | 3.1072
UG-11 | UG-11-S02 | P0549 | 3.1 | 2.0696 | -4.6248 | -4.6248 | -2.0552 | -2.0552 | 27.43 | -4.6248 | -4.6248 | 3.9248 | 3.1248 | 0.8 | 9.4844 | Shoring | 3.1 | 3.1248 | 0.8 | 4.0696 | 49.5141 | 0 | 4.7579 | 10.4285 | 1.1882 | 1.1882 | 3.1072 | 3.1072
UG-11 | UG-11-S02 | P0548 | 3.1 | 2.0696 | -4.6248 | -4.6248 | -2.0552 | -2.0552 | 27.69 | -4.6248 | -4.6248 | 3.9248 | 3.1248 | 0.8 | 9.4844 | Shoring | 3.1 | 3.1248 | 0.8 | 4.0696 | 49.5146 | 0 | 4.7579 | 10.4286 | 1.1882 | 1.1882 | 3.1072 | 3.1072
UG-11 | UG-11-S02 | P0210-01 | 0.51426 | 2.0696 | -4.6248 | -4.6248 | -2.0552 | -2.0552 | 27.57 | -4.6248 | -4.6248 | 3.9248 | 3.1248 | 0.8 | 9.4844 | Shoring | 0.51426 | 3.1248 | 0.8 | 4.0696 | 8.214 | 0 | 0.78929 | 1.73 | 1.1882 | 1.1882 | 3.1072 | 3.1072
UG-11 | UG-11-S02 | P0210-02 | 4.1214 | 2.0696 | -4.6248 | -4.6248 | -2.0552 | -2.0552 | 26.95 | -4.6248 | -4.6248 | 3.9248 | 3.1248 | 0.8 | 9.4844 | Shoring | 4.1214 | 3.1248 | 0.8 | 4.0696 | 65.8284 | 0 | 6.3255 | 13.8646 | 1.1882 | 1.1882 | 3.1072 | 3.1072
UG-11 | UG-11-S02 | P0409 | 1.5 | 1.42 | -4.3 | -4.3 | -2.38 | -2.38 | 26.88 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.51 | Shoring | 1.5 | 2.8 | 0.8 | 3.42 | 18.4681 | 0 | 1.815 | 2.3755 | 1.9749 | 1.9749 | 4.7718 | 4.7718
UG-11 | UG-11-S02 | P0179-01 | 4.3786 | 1.42 | -4.3 | -4.3 | -2.38 | -2.38 | 26.84 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.51 | Shoring | 4.3786 | 2.8 | 0.8 | 3.42 | 53.9096 | 0 | 5.2981 | 6.9344 | 1.9749 | 1.9749 | 4.7718 | 4.7718
UG-11 | UG-11-S02 | P0179-02 | 3.646 | 1.42 | -4.3 | -4.3 | -2.38 | -2.38 | 26.81 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.51 | Shoring | 3.646 | 2.8 | 0.8 | 3.42 | 44.8902 | 0 | 4.4117 | 5.7742 | 1.9749 | 1.9749 | 4.7718 | 4.7718
UG-11 | UG-11-S03 | P0771 | 6.0782 | 2.0696 | -7.5748 | -7.5748 | -5.0052 | -5.0052 | 10.31 | -7.5748 | -7.5748 | 6.8748 | 6.0748 | 0.8 | 15.3844 | Shoring | 6.0782 | 6.0748 | 0.8 | 4.0696 | 170.054 | 0 | 9.3288 | 20.4474 | 2.7034 | 2.7034 | 4.6224 | 4.6224
UG-11 | UG-11-S03 | P0781 | 2.2332 | 2.0696 | -7.5748 | -7.5754 | -5.0052 | -5.0058 | 15.53 | -7.5754 | -7.5751 | 6.8751 | 6.0754 | 0.8 | 15.3855 | Shoring | 2.2332 | 6.0751 | 0.8 | 4.0696 | 62.4835 | 0 | 3.4276 | 7.5127 | 2.7034 | 2.7037 | 4.6224 | 4.6227
UG-11 | UG-11-S03 | P0780 | 0.80769 | 2.0696 | -7.5754 | -7.5756 | -5.0058 | -5.006 | 14.75 | -7.5756 | -7.5755 | 6.8755 | 6.0756 | 0.8 | 15.3859 | Shoring | 0.80769 | 6.0755 | 0.8 | 4.0696 | 22.5996 | 0 | 1.2397 | 2.7171 | 2.7037 | 2.7038 | 4.6227 | 4.6228
UG-11 | UG-11-S03 | P0779 | 0.80768 | 2.0696 | -7.5756 | -7.5758 | -5.006 | -5.0062 | 14.06 | -7.5758 | -7.5757 | 6.8757 | 6.0758 | 0.8 | 15.3863 | Shoring | 0.80768 | 6.0757 | 0.8 | 4.0696 | 22.5999 | 0 | 1.2396 | 2.7171 | 2.7038 | 2.7039 | 4.6228 | 4.6229
UG-11 | UG-11-S03 | P0778-01 | 0.073183 | 2.0696 | -7.5758 | -7.5758 | -5.0062 | -5.0062 | 14 | -7.5758 | -7.5758 | 6.8758 | 6.0758 | 0.8 | 15.3864 | Shoring | 0.073183 | 6.0758 | 0.8 | 4.0696 | 2.0478 | 0 | 0.11232 | 0.24619 | 2.7039 | 2.7039 | 4.6229 | 4.6229
UG-11 | UG-11-S03 | P0778-02 | 2.1149 | 2.0696 | -7.5758 | -7.5763 | -5.0062 | -5.0067 | 12.48 | -7.5763 | -7.5761 | 6.8761 | 6.0763 | 0.8 | 15.3874 | Shoring | 2.1149 | 6.0761 | 0.8 | 4.0696 | 59.1805 | 0 | 3.2459 | 7.1146 | 2.7039 | 2.7042 | 4.6229 | 4.6232
UG-11 | UG-11-S03 | P0777-01 | 7.8851 | 2.0696 | -7.5763 | -7.5783 | -5.0067 | -5.0087 | 6.93 | -7.5783 | -7.5773 | 6.8773 | 6.0783 | 0.8 | 15.3914 | Shoring | 7.8851 | 6.0773 | 0.8 | 4.0696 | 220.6878 | 0 | 12.1021 | 26.5259 | 2.7042 | 2.7052 | 4.6232 | 4.6242
UG-11 | UG-11-S03 | P0777-02 | 3.1 | 2.0696 | -7.5783 | -7.5791 | -5.0087 | -5.0095 | 5.11 | -7.5791 | -7.5787 | 6.8787 | 6.0791 | 0.8 | 15.393 | Shoring | 3.1 | 6.0787 | 0.8 | 4.0696 | 86.7799 | 0 | 4.7579 | 10.4286 | 2.7052 | 2.7056 | 4.6242 | 4.6246
UG-11 | UG-11-S04 | P0777-03 | 6.9 | 2.0696 | -7.5791 | -7.5808 | -5.0095 | -5.0112 | 4.69 | -7.5808 | -7.5799 | 6.8799 | 6.0808 | 0.8 | 15.3964 | Shoring | 6.9 | 6.0799 | 0.8 | 4.0696 | 193.1906 | 0 | 10.5901 | 23.212 | 2.7056 | 2.7065 | 4.6246 | 4.6255
UG-11 | UG-11-S04 | P0777-04 | 10 | 2.0696 | -7.5808 | -7.5833 | -5.0112 | -5.0137 | 6.77 | -7.5833 | -7.5821 | 6.8821 | 6.0833 | 0.8 | 15.4015 | Shoring | 10 | 6.0821 | 0.8 | 4.0696 | 280.0727 | 0 | 15.348 | 33.6405 | 2.7065 | 2.7078 | 4.6255 | 4.6268
UG-11 | UG-11-S04 | P0777-05 | 1.2 | 2.0696 | -7.5833 | -7.5836 | -5.0137 | -5.014 | 11.71 | -7.5836 | -7.5835 | 6.8835 | 6.0836 | 0.8 | 15.4021 | Shoring | 1.2 | 6.0835 | 0.8 | 4.0696 | 33.6156 | 0 | 1.8418 | 4.0369 | 2.7078 | 2.7079 | 4.6268 | 4.6269
UG-11 | UG-11-S05 | P0777-06 | 8.8 | 2.0696 | -7.5836 | -7.5858 | -5.014 | -5.0162 | 12.05 | -7.5858 | -7.5847 | 6.8847 | 6.0858 | 0.8 | 15.4065 | Shoring | 8.8 | 6.0847 | 0.8 | 4.0696 | 246.5594 | 0 | 13.5062 | 29.6037 | 2.7079 | 2.7091 | 4.6269 | 4.6281
UG-11 | UG-11-S05 | P0777-07 | 0.40198 | 2.0696 | -7.5858 | -7.5859 | -5.0162 | -5.0163 | 17.09 | -7.5859 | -7.5859 | 6.8859 | 6.0859 | 0.8 | 15.4067 | Shoring | 0.40198 | 6.0859 | 0.8 | 4.0696 | 11.2645 | 0 | 0.61695 | 1.3523 | 2.7091 | 2.7091 | 4.6281 | 4.6281
UG-11 | UG-11-S05 | P0553 | 2.2333 | 0.99415 | -7.0482 | -7.0488 | -5.5541 | -5.5546 | 17.38 | -7.0488 | -7.0485 | 6.3485 | 5.5488 | 0.8 | 13.7946 | Shoring | 2.2333 | 5.5485 | 0.8 | 2.9941 | 42.4504 | 0 | 2.2267 | 1.7335 | 6.2147 | 6.2153 | 10.2097 | 10.2103
UG-11 | UG-11-S05 | P0552 | 0.80768 | 0.99414 | -7.0488 | -7.049 | -5.5546 | -5.5548 | 18.96 | -7.049 | -7.0489 | 6.3489 | 5.549 | 0.8 | 13.795 | Shoring | 0.80768 | 5.5489 | 0.8 | 2.9941 | 15.3536 | 0 | 0.80532 | 0.62694 | 6.2154 | 6.2156 | 10.2103 | 10.2105
UG-11 | UG-11-S05 | P0551 | 0.80769 | 0.99416 | -7.049 | -7.0492 | -5.5548 | -5.555 | 19.37 | -7.0492 | -7.0491 | 6.3491 | 5.5492 | 0.8 | 13.7955 | Shoring | 0.80769 | 5.5491 | 0.8 | 2.9942 | 15.3543 | 0 | 0.80533 | 0.62697 | 6.2155 | 6.2157 | 10.2104 | 10.2106
UG-11 | UG-11-S05 | P0550 | 2.2332 | 0.99415 | -7.0492 | -7.0497 | -5.555 | -5.5556 | 19.58 | -7.0497 | -7.0495 | 6.3495 | 5.5497 | 0.8 | 13.7966 | Shoring | 2.2332 | 5.5495 | 0.8 | 2.9942 | 42.4567 | 0 | 2.2267 | 1.7335 | 6.2157 | 6.2163 | 10.2107 | 10.2113
UG-11 | UG-11-S05 | P0260-01 | 3.5162 | 2.0696 | -7.5875 | -7.5884 | -5.0179 | -5.0188 | 19.62 | -7.5884 | -7.5879 | 6.8879 | 6.0884 | 0.8 | 15.4115 | Shoring | 3.5162 | 6.0879 | 0.8 | 4.0696 | 98.5617 | 0 | 5.3966 | 11.8286 | 2.7099 | 2.7103 | 4.6289 | 4.6294
UG-11 | UG-11-S05 | P0260-02 | 10 | 2.0696 | -7.5884 | -7.5909 | -5.0188 | -5.0213 | 20.13 | -7.5909 | -7.5896 | 6.8896 | 6.0909 | 0.8 | 15.4165 | Shoring | 10 | 6.0896 | 0.8 | 4.0696 | 280.3797 | 0 | 15.348 | 33.6406 | 2.7103 | 2.7116 | 4.6294 | 4.6306
UG-11 | UG-11-S05 | P0260-03 | 10 | 2.0696 | -7.5909 | -7.5934 | -5.0213 | -5.0238 | 19.47 | -7.5934 | -7.5921 | 6.8921 | 6.0934 | 0.8 | 15.4216 | Shoring | 10 | 6.0921 | 0.8 | 4.0696 | 280.482 | 0 | 15.348 | 33.6406 | 2.7116 | 2.7129 | 4.6306 | 4.6319
UG-11 | UG-11-S05 | P0260-04 | 2.5 | 2.0696 | -7.5934 | -7.594 | -5.0238 | -5.0244 | 17.04 | -7.594 | -7.5937 | 6.8937 | 6.094 | 0.8 | 15.4228 | Shoring | 2.5 | 6.0937 | 0.8 | 4.0696 | 70.1365 | 0 | 3.837 | 8.4101 | 2.7129 | 2.7133 | 4.6319 | 4.6323
UG-11 | UG-11-S06 | P0260-05 | 7.5 | 2.0696 | -7.594 | -7.5959 | -5.0244 | -5.0263 | 9.62 | -7.5959 | -7.595 | 6.895 | 6.0959 | 0.8 | 15.4266 | Shoring | 7.5 | 6.095 | 0.8 | 4.0696 | 210.4477 | 0 | 11.511 | 25.2304 | 2.7133 | 2.7142 | 4.6323 | 4.6332
UG-11 | UG-11-S06 | P0260-06 | 10 | 2.0696 | -7.5959 | -7.5984 | -5.0263 | -5.0288 | 0.91 | -7.5984 | -7.5971 | 6.8971 | 6.0984 | 0.8 | 15.4316 | Shoring | 10 | 6.0971 | 0.8 | 4.0696 | 280.6865 | 0 | 15.348 | 33.6406 | 2.7142 | 2.7155 | 4.6332 | 4.6345
UG-11 | UG-11-S06 | P0260-07 | 10 | 2.0696 | -7.5984 | -7.6009 | -5.0288 | -5.0313 | 0 | -7.6009 | -7.5997 | 6.8997 | 6.1009 | 0.8 | 15.4366 | Shoring | 10 | 6.0997 | 0.8 | 4.0696 | 280.7887 | 0 | 15.348 | 33.6406 | 2.7155 | 2.7168 | 4.6345 | 4.6358
UG-11 | UG-11-S06 | P0260-08 | 10 | 2.0696 | -7.6009 | -7.6034 | -5.0313 | -5.0338 | 0 | -7.6034 | -7.6022 | 6.9022 | 6.1034 | 0.8 | 15.4417 | Shoring | 10 | 6.1022 | 0.8 | 4.0696 | 280.891 | 0 | 15.348 | 33.6406 | 2.7168 | 2.7181 | 4.6358 | 4.6371
UG-11 | UG-11-S06 | P0260-09 | 5.4539 | 2.0696 | -7.6034 | -7.6048 | -5.0338 | -5.0352 | 6.31 | -7.6048 | -7.6041 | 6.9041 | 6.1048 | 0.8 | 15.4444 | Shoring | 5.4539 | 6.1041 | 0.8 | 4.0696 | 153.2382 | 0 | 8.3706 | 18.3472 | 2.7181 | 2.7188 | 4.6371 | 4.6378
UG-11 | UG-11-S06 | P0699 | 0.2503 | 0.99415 | -7.0671 | -7.0671 | -5.5729 | -5.5729 | 9.64 | -7.0671 | -7.0671 | 6.3671 | 5.5671 | 0.8 | 13.8312 | Shoring | 0.2503 | 5.5671 | 0.8 | 2.9942 | 4.7717 | 0 | 0.24957 | 0.19429 | 6.2349 | 6.2349 | 10.2298 | 10.2298
UG-11A | UG-11A-S01 | P0348-01 | 6 | 0.99999 | -4.09 | -4.09 | -2.59 | -2.59 | 12.5 | -4.09 | -4.09 | 3.39 | 2.59 | 0.8 | 7.88 | Shoring | 6 | 2.59 | 0.8 | 3 | 61.0196 | 0 | 6 | 4.7123 | 3.0277 | 3.0277 | 6.9993 | 6.9993
UG-11A | UG-11A-S02 | P0348-02 | 4 | 0.99999 | -4.09 | -4.09 | -2.59 | -2.59 | 18 | -4.09 | -4.09 | 3.39 | 2.59 | 0.8 | 7.88 | Shoring | 4 | 2.59 | 0.8 | 3 | 40.6797 | 0 | 4 | 3.1415 | 3.0277 | 3.0277 | 6.9993 | 6.9993
UG-11A | UG-11A-S02 | P0348-03 | 10 | 0.99999 | -4.09 | -4.09 | -2.59 | -2.59 | 21.81 | -4.09 | -4.09 | 3.39 | 2.59 | 0.8 | 7.88 | Shoring | 10 | 2.59 | 0.8 | 3 | 101.6993 | 0 | 9.9999 | 7.8538 | 3.0277 | 3.0277 | 6.9993 | 6.9993
UG-11A | UG-11A-S02 | P0348-04 | 10 | 0.99999 | -4.09 | -4.09 | -2.59 | -2.59 | 0 | -4.09 | -4.09 | 3.39 | 2.59 | 0.8 | 7.88 | Shoring | 10 | 2.59 | 0.8 | 3 | 101.6993 | 0 | 9.9999 | 7.8538 | 3.0277 | 3.0277 | 6.9993 | 6.9993
UG-11A | UG-11A-S02 | P0348-05 | 5.6895 | 0.99999 | -4.09 | -4.09 | -2.59 | -2.59 | 1 | -4.09 | -4.09 | 3.39 | 2.59 | 0.8 | 7.88 | Shoring | 5.6895 | 2.59 | 0.8 | 3 | 57.8619 | 0 | 5.6895 | 4.4684 | 3.0277 | 3.0277 | 6.9993 | 6.9993
UG-11A | UG-11A-S02 | P0020 | 0.30085 | 1 | -4.09 | -4.09 | -2.59 | -2.59 | 6.69 | -4.09 | -4.09 | 3.39 | 2.59 | 0.8 | 7.88 | Shoring | 0.30085 | 2.59 | 0.8 | 3 | 3.0596 | 0 | 0.30085 | 0.23629 | 3.0276 | 3.0276 | 6.9992 | 6.9992
UG-11A | UG-11A-S02 | P0226-01 | 4.0096 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 6.99 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.4801 | Shoring | 4.0096 | 2.79 | 0.8 | 3.4 | 48.9425 | 0 | 4.8116 | 6.1727 | 2.0107 | 2.0107 | 4.8474 | 4.8474
UG-11A | UG-11A-S02 | P0226-02 | 10 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 11 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.4801 | Shoring | 10 | 2.79 | 0.8 | 3.4 | 122.0618 | 0 | 12.0002 | 15.3946 | 2.0107 | 2.0107 | 4.8474 | 4.8474
UG-11A | UG-11A-S02 | P0226-03 | 4.3 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 10.95 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.4801 | Shoring | 4.3 | 2.79 | 0.8 | 3.4 | 52.4866 | 0 | 5.1601 | 6.6197 | 2.0107 | 2.0107 | 4.8474 | 4.8474
UG-11A | UG-11A-S03 | P0226-04 | 5.7 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 10.83 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.4801 | Shoring | 5.7 | 2.79 | 0.8 | 3.4 | 69.5752 | 0 | 6.8401 | 8.7749 | 2.0107 | 2.0107 | 4.8474 | 4.8474
UG-11A | UG-11A-S03 | P0226-05 | 10 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 2.25 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.4801 | Shoring | 10 | 2.79 | 0.8 | 3.4 | 122.0618 | 0 | 12.0002 | 15.3946 | 2.0107 | 2.0107 | 4.8474 | 4.8474
UG-11A | UG-11A-S03 | P0226-06 | 3.2423 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 0 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.4801 | Shoring | 3.2423 | 2.79 | 0.8 | 3.4 | 39.5758 | 0 | 3.8908 | 4.9913 | 2.0107 | 2.0107 | 4.8474 | 4.8474
UG-11A | UG-11A-S03 | P0592 | 1.0431 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 0 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.4801 | Shoring | 1.0431 | 2.79 | 0.8 | 3.4 | 12.7324 | 0 | 1.2518 | 1.6058 | 2.0107 | 2.0107 | 4.8474 | 4.8474
UG-11A | UG-11A-S03 | P0593 | 0.97419 | 1.3989 | -4.2895 | -4.2895 | -2.3905 | -2.3905 | 0.19 | -4.2895 | -4.2895 | 3.5895 | 2.7895 | 0.8 | 8.4784 | Shoring | 0.97419 | 2.7895 | 0.8 | 3.3989 | 11.8854 | 0 | 1.1685 | 1.4974 | 2.0127 | 2.0127 | 4.8516 | 4.8516
UG-11A | UG-11A-S03 | P0248-01 | 4.7404 | 1.3989 | -4.2895 | -4.2895 | -2.3905 | -2.3905 | 1.13 | -4.2895 | -4.2895 | 3.5895 | 2.7895 | 0.8 | 8.4784 | Shoring | 4.7404 | 2.7895 | 0.8 | 3.3989 | 57.8351 | 0 | 5.686 | 7.2863 | 2.0127 | 2.0127 | 4.8516 | 4.8516
UG-11A | UG-11A-S03 | P0248-02 | 2.9956 | 1.3989 | -4.2895 | -4.2895 | -2.3905 | -2.3905 | 5.74 | -4.2895 | -4.2895 | 3.5895 | 2.7895 | 0.8 | 8.4784 | Shoring | 2.9956 | 2.7895 | 0.8 | 3.3989 | 36.5477 | 0 | 3.5931 | 4.6044 | 2.0127 | 2.0127 | 4.8516 | 4.8516
UG-11A | UG-11A-S03 | P0421 | 1.0324 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 8.66 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.48 | Shoring | 1.0324 | 2.79 | 0.8 | 3.4 | 12.601 | 0 | 1.2388 | 1.5892 | 2.0107 | 2.0107 | 4.8476 | 4.8476
UG-11A | UG-11A-S04 | P0420 | 0.99563 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 9.68 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.48 | Shoring | 0.99563 | 2.79 | 0.8 | 3.4 | 12.1526 | 0 | 1.1948 | 1.5327 | 2.0107 | 2.0107 | 4.8476 | 4.8476
UG-11A | UG-11A-S04 | P0249-01 | 4.9764 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 10.66 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.48 | Shoring | 4.9764 | 2.79 | 0.8 | 3.4 | 60.7421 | 0 | 5.9717 | 7.6606 | 2.0107 | 2.0107 | 4.8476 | 4.8476
UG-11A | UG-11A-S04 | P0249-02 | 10 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 13.53 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.48 | Shoring | 10 | 2.79 | 0.8 | 3.4 | 122.0602 | 0 | 12 | 15.3939 | 2.0107 | 2.0107 | 4.8476 | 4.8476
UG-11A | UG-11A-S04 | P0249-03 | 10 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 16.13 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.48 | Shoring | 10 | 2.79 | 0.8 | 3.4 | 122.0602 | 0 | 12 | 15.3939 | 2.0107 | 2.0107 | 4.8476 | 4.8476
UG-11A | UG-11A-S04 | P0249-04 | 10 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 6.79 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.48 | Shoring | 10 | 2.79 | 0.8 | 3.4 | 122.0602 | 0 | 12 | 15.3939 | 2.0107 | 2.0107 | 4.8476 | 4.8476
UG-11A | UG-11A-S04 | P0249-05 | 3.7 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 3.09 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.48 | Shoring | 3.7 | 2.79 | 0.8 | 3.4 | 45.1623 | 0 | 4.44 | 5.6957 | 2.0107 | 2.0107 | 4.8476 | 4.8476
UG-11A | UG-11A-S05 | P0249-06 | 6.3 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 0 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.48 | Shoring | 6.3 | 2.79 | 0.8 | 3.4 | 76.8979 | 0 | 7.56 | 9.6981 | 2.0107 | 2.0107 | 4.8476 | 4.8476
UG-11A | UG-11A-S05 | P0249-07 | 10 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 1.01 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.48 | Shoring | 10 | 2.79 | 0.8 | 3.4 | 122.0602 | 0 | 12 | 15.3939 | 2.0107 | 2.0107 | 4.8476 | 4.8476
UG-11A | UG-11A-S05 | P0249-08 | 10 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 11.01 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.48 | Shoring | 10 | 2.79 | 0.8 | 3.4 | 122.0602 | 0 | 12 | 15.3939 | 2.0107 | 2.0107 | 4.8476 | 4.8476
UG-11A | UG-11A-S05 | P0249-09 | 10 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 21 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.48 | Shoring | 10 | 2.79 | 0.8 | 3.4 | 122.0602 | 0 | 12 | 15.3939 | 2.0107 | 2.0107 | 4.8476 | 4.8476
UG-11A | UG-11A-S05 | P0249-10 | 3.6856 | 1.4 | -4.29 | -4.29 | -2.39 | -2.39 | 26.78 | -4.29 | -4.29 | 3.59 | 2.79 | 0.8 | 8.48 | Shoring | 3.6856 | 2.79 | 0.8 | 3.4 | 44.9868 | 0 | 4.4228 | 5.6736 | 2.0107 | 2.0107 | 4.8476 | 4.8476
UG-11A | UG-11A-S05 | P0361 | 0.205 | 1.42 | -4.3 | -4.3 | -2.38 | -2.38 | 26.81 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.51 | Shoring | 0.205 | 2.8 | 0.8 | 3.42 | 2.524 | 0 | 0.24806 | 0.32466 | 1.9749 | 1.9749 | 4.7718 | 4.7718
UG-11A | UG-11A-S06 | P0347-01 | 6 | 0.99999 | -4.09 | -4.09 | -2.59 | -2.59 | 99 | -4.09 | -4.09 | 3.39 | 2.59 | 0.8 | 7.88 | Shoring | 6 | 2.59 | 0.8 | 3 | 61.0198 | 0 | 6 | 4.7123 | 3.0277 | 3.0277 | 6.9993 | 6.9993
UG-11A | UG-11A-S07 | P0347-02 | 4 | 0.99999 | -4.09 | -4.09 | -2.59 | -2.59 | 99 | -4.09 | -4.09 | 3.39 | 2.59 | 0.8 | 7.88 | Shoring | 4 | 2.59 | 0.8 | 3 | 40.6798 | 0 | 4 | 3.1415 | 3.0277 | 3.0277 | 6.9993 | 6.9993
UG-11A | UG-11A-S07 | P0347-03 | 10 | 0.99999 | -4.09 | -4.09 | -2.59 | -2.59 | 18.71 | -4.09 | -4.09 | 3.39 | 2.59 | 0.8 | 7.88 | Shoring | 10 | 2.59 | 0.8 | 3 | 101.6996 | 0 | 10 | 7.8538 | 3.0277 | 3.0277 | 6.9993 | 6.9993
UG-11A | UG-11A-S07 | P0347-04 | 2.9534 | 0.99999 | -4.09 | -4.09 | -2.59 | -2.59 | 0 | -4.09 | -4.09 | 3.39 | 2.59 | 0.8 | 7.88 | Shoring | 2.9534 | 2.59 | 0.8 | 3 | 30.036 | 0 | 2.9534 | 2.3196 | 3.0277 | 3.0277 | 6.9993 | 6.9993
UG-11A | UG-11A-S07 | P0229-01 | 7.0466 | 1 | -4.09 | -4.09 | -2.59 | -2.59 | 0 | -4.09 | -4.09 | 3.39 | 2.59 | 0.8 | 7.88 | Shoring | 7.0466 | 2.59 | 0.8 | 3 | 71.6641 | 0 | 7.0466 | 5.5345 | 3.0276 | 3.0276 | 6.9991 | 6.9991
UG-11A | UG-11A-S07 | P0229-02 | 9.2729 | 1 | -4.09 | -4.09 | -2.59 | -2.59 | 1.11 | -4.09 | -4.09 | 3.39 | 2.59 | 0.8 | 7.88 | Shoring | 9.2729 | 2.59 | 0.8 | 3 | 94.3054 | 0 | 9.2729 | 7.283 | 3.0276 | 3.0276 | 6.9991 | 6.9991
UG-11A | UG-11A-S07 | P0526 | 0.19174 | 1 | -4.09 | -4.09 | -2.59 | -2.59 | 9.25 | -4.09 | -4.09 | 3.39 | 2.59 | 0.8 | 7.88 | Shoring | 0.19174 | 2.59 | 0.8 | 3 | 1.95 | 0 | 0.19174 | 0.15059 | 3.0276 | 3.0276 | 6.9991 | 6.9991
UG-11A | UG-11A-S07 | P0247-01 | 0.53539 | 1.2 | -4.19 | -4.19 | -2.49 | -2.49 | 9.28 | -4.19 | -4.19 | 3.49 | 2.69 | 0.8 | 8.18 | Shoring | 0.53539 | 2.69 | 0.8 | 3.2 | 5.9793 | 0 | 0.58893 | 0.60552 | 2.4344 | 2.4344 | 5.7441 | 5.7441
UG-11A | UG-11A-S07 | P0247-02 | 0.52599 | 1.2 | -4.19 | -4.19 | -2.49 | -2.49 | 9.35 | -4.19 | -4.19 | 3.49 | 2.69 | 0.8 | 8.18 | Shoring | 0.52599 | 2.69 | 0.8 | 3.2 | 5.8742 | 0 | 0.57859 | 0.59488 | 2.4344 | 2.4344 | 5.7441 | 5.7441
UG-11A | UG-11A-S07 | P0419 | 1.4168 | 1.2 | -4.19 | -4.19 | -2.49 | -2.49 | 9.43 | -4.19 | -4.19 | 3.49 | 2.69 | 0.8 | 8.18 | Shoring | 1.4168 | 2.69 | 0.8 | 3.2 | 15.8226 | 0 | 1.5585 | 1.6023 | 2.4344 | 2.4344 | 5.7441 | 5.7441
UG-11A | UG-11A-S07 | P0688 | 0.19752 | 1.2 | -4.19 | -4.19 | -2.49 | -2.49 | 9.43 | -4.19 | -4.19 | 3.49 | 2.69 | 0.8 | 8.18 | Shoring | 0.19752 | 2.69 | 0.8 | 3.2 | 2.2059 | 0 | 0.21727 | 0.22339 | 2.4344 | 2.4344 | 5.7441 | 5.7441
UG-11B | UG-11B-S01 | P0346-01 | 6 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 49.92 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 6 | 2.6 | 0.8 | 3 | 61.1998 | 0 | 6 | 4.7123 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-11B | UG-11B-S02 | P0346-02 | 4 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 49.91 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 4 | 2.6 | 0.8 | 3 | 40.7999 | 0 | 4 | 3.1416 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-11B | UG-11B-S02 | P0346-03 | 10 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 41.68 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 10 | 2.6 | 0.8 | 3 | 101.9997 | 0 | 10 | 7.8539 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-11B | UG-11B-S02 | P0346-04 | 10 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 0 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 10 | 2.6 | 0.8 | 3 | 101.9997 | 0 | 10 | 7.8539 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-11B | UG-11B-S02 | P0346-05 | 10 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 1 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 10 | 2.6 | 0.8 | 3 | 101.9997 | 0 | 10 | 7.8539 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-11B | UG-11B-S02 | P0346-06 | 9.0189 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 11 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 9.0189 | 2.6 | 0.8 | 3 | 91.9923 | 0 | 9.0189 | 7.0833 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-11B | UG-11B-S02 | P0390 | 0.18001 | 1.0222 | -4.1111 | -4.1111 | -2.5889 | -2.5889 | 20.02 | -4.1111 | -4.1111 | 3.4111 | 2.6111 | 0.8 | 7.9332 | Shoring | 0.18001 | 2.6111 | 0.8 | 3.0222 | 1.8557 | 0 | 0.182 | 0.14771 | 2.9609 | 2.9609 | 6.8464 | 6.8464
UG-11B | UG-11B-S02 | P0257-01 | 0.80111 | 1.0222 | -4.1111 | -4.1111 | -2.5889 | -2.5889 | 20.2 | -4.1111 | -4.1111 | 3.4111 | 2.6111 | 0.8 | 7.9332 | Shoring | 0.80111 | 2.6111 | 0.8 | 3.0222 | 8.2585 | 0 | 0.80999 | 0.65738 | 2.9609 | 2.9609 | 6.8464 | 6.8464
UG-11B | UG-11B-S02 | P0257-02 | 5.6291 | 1.0222 | -4.1111 | -4.1111 | -2.5889 | -2.5889 | 21 | -4.1111 | -4.1111 | 3.4111 | 2.6111 | 0.8 | 7.9332 | Shoring | 5.6291 | 2.6111 | 0.8 | 3.0222 | 58.029 | 0 | 5.6914 | 4.6191 | 2.9609 | 2.9609 | 6.8464 | 6.8464
UG-11B | UG-11B-S03 | P0783 | 2.3656 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 26.63 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 2.3656 | 3.1348 | 0.8 | 4.0696 | 37.8798 | 0 | 3.6307 | 7.9578 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-11B | UG-11B-S03 | P0320-01 | 2.0054 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 26.69 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 2.0054 | 3.1348 | 0.8 | 4.0696 | 32.112 | 0 | 3.0778 | 6.7461 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-11B | UG-11B-S03 | P0320-02 | 10 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 26.81 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 10 | 3.1348 | 0.8 | 4.0696 | 160.1304 | 0 | 15.348 | 33.6404 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-11B | UG-11B-S03 | P0320-03 | 10 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 28.47 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 10 | 3.1348 | 0.8 | 4.0696 | 160.1304 | 0 | 15.348 | 33.6404 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-11B | UG-11B-S03 | P0320-04 | 10 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 31.75 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 10 | 3.1348 | 0.8 | 4.0696 | 160.1304 | 0 | 15.348 | 33.6404 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-11B | UG-11B-S03 | P0320-05 | 10 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 99 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 10 | 3.1348 | 0.8 | 4.0696 | 160.1304 | 0 | 15.348 | 33.6404 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-11B | UG-11B-S03 | P0320-06 | 10 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 99 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 10 | 3.1348 | 0.8 | 4.0696 | 160.1304 | 0 | 15.348 | 33.6404 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-11B | UG-11B-S03 | P0320-07 | 10 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 21.07 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 10 | 3.1348 | 0.8 | 4.0696 | 160.1304 | 0 | 15.348 | 33.6404 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-11B | UG-11B-S03 | P0320-08 | 5.8443 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 17.77 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 5.8443 | 3.1348 | 0.8 | 4.0696 | 93.5849 | 0 | 8.9698 | 19.6604 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-11B | UG-11B-S04 | P0795-01 | 4.1557 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 16.31 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 4.1557 | 3.1348 | 0.8 | 4.0696 | 66.5454 | 0 | 6.3782 | 13.98 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-11B | UG-11B-S04 | P0795-02 | 5.8753 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 15.84 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 5.8753 | 3.1348 | 0.8 | 4.0696 | 94.0817 | 0 | 9.0174 | 19.7648 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-11B | UG-11B-S04 | P0410 | 1.5 | 1.4296 | -4.3148 | -4.3148 | -2.3852 | -2.3852 | 15.83 | -4.3148 | -4.3148 | 3.6148 | 2.8148 | 0.8 | 8.5444 | Shoring | 1.5 | 2.8148 | 0.8 | 3.4296 | 18.596 | 0 | 1.8222 | 2.4078 | 1.9655 | 1.9655 | 4.7436 | 4.7436
UG-11B | UG-11B-S04 | P0318 | 1.9664 | 1.4296 | -4.3148 | -4.3148 | -2.3852 | -2.3852 | 15.83 | -4.3148 | -4.3148 | 3.6148 | 2.8148 | 0.8 | 8.5444 | Shoring | 1.9664 | 2.8148 | 0.8 | 3.4296 | 24.3781 | 0 | 2.3888 | 3.1564 | 1.9655 | 1.9655 | 4.7436 | 4.7436
UG-11B | UG-11B-S04 | P0389 | 0.20501 | 1.4296 | -4.3148 | -4.3148 | -2.3852 | -2.3852 | 15.83 | -4.3148 | -4.3148 | 3.6148 | 2.8148 | 0.8 | 8.5444 | Shoring | 0.20501 | 2.8148 | 0.8 | 3.4296 | 2.5416 | 0 | 0.24905 | 0.32907 | 1.9655 | 1.9655 | 4.7436 | 4.7436
UG-11B | UG-11B-S04 | P0319-01 | 0.45327 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 15.83 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 0.45327 | 2.8 | 0.8 | 3.4 | 5.548 | 0 | 0.54392 | 0.69775 | 2.0183 | 2.0183 | 4.8552 | 4.8552
UG-11B | UG-11B-S04 | P0319-02 | 10 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 15.83 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 10 | 2.8 | 0.8 | 3.4 | 122.4002 | 0 | 12 | 15.3939 | 2.0183 | 2.0183 | 4.8552 | 4.8552
UG-11B | UG-11B-S04 | P0319-03 | 2.0039 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 15.83 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 2.0039 | 2.8 | 0.8 | 3.4 | 24.5276 | 0 | 2.4047 | 3.0848 | 2.0183 | 2.0183 | 4.8552 | 4.8552
UG-11B | UG-11B-S04 | P0545 | 1.8507 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 15.83 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 1.8507 | 2.8 | 0.8 | 3.4 | 22.6524 | 0 | 2.2208 | 2.8489 | 2.0183 | 2.0183 | 4.8552 | 4.8552
UG-11B | UG-11B-S04 | P0544 | 1.8486 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 15.83 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 1.8486 | 2.8 | 0.8 | 3.4 | 22.6273 | 0 | 2.2184 | 2.8458 | 2.0183 | 2.0183 | 4.8552 | 4.8552
UG-11B | UG-11B-S04 | P0049-01 | 4.2968 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 17.43 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 4.2968 | 2.8 | 0.8 | 3.4 | 52.5929 | 0 | 5.1562 | 6.6144 | 2.0183 | 2.0183 | 4.8552 | 4.8552
UG-11B | UG-11B-S04 | P0049-02 | 6.1 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 21.15 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 6.1 | 2.8 | 0.8 | 3.4 | 74.6641 | 0 | 7.32 | 9.3902 | 2.0183 | 2.0183 | 4.8552 | 4.8552
UG-11B | UG-11B-S05 | P0049-03 | 0.65758 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 26.44 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 0.65758 | 2.8 | 0.8 | 3.4 | 8.0488 | 0 | 0.7891 | 1.0123 | 2.0183 | 2.0183 | 4.8552 | 4.8552
UG-11B | UG-11B-S05 | P0542 | 0.33534 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 27.02 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 0.33534 | 2.8 | 0.8 | 3.4 | 4.1046 | 0 | 0.40241 | 0.51622 | 2.0183 | 2.0183 | 4.8552 | 4.8552
UG-11B | UG-11B-S05 | P0543 | 0.33479 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 26.87 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 0.33479 | 2.8 | 0.8 | 3.4 | 4.0978 | 0 | 0.40175 | 0.51537 | 2.0183 | 2.0183 | 4.8551 | 4.8551
UG-11B | UG-11B-S05 | P0227-01 | 2.5723 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 24.89 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 2.5723 | 2.8 | 0.8 | 3.4 | 31.4849 | 0 | 3.0868 | 3.9598 | 2.0183 | 2.0183 | 4.8551 | 4.8551
UG-11B | UG-11B-S05 | P0227-02 | 10 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 17.71 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 10 | 2.8 | 0.8 | 3.4 | 122.4003 | 0 | 12 | 15.3939 | 2.0183 | 2.0183 | 4.8551 | 4.8551
UG-11B | UG-11B-S05 | P0227-03 | 10 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 11.74 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 10 | 2.8 | 0.8 | 3.4 | 122.4003 | 0 | 12 | 15.3939 | 2.0183 | 2.0183 | 4.8551 | 4.8551
UG-11B | UG-11B-S05 | P0227-04 | 10 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 7.57 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 10 | 2.8 | 0.8 | 3.4 | 122.4003 | 0 | 12 | 15.3939 | 2.0183 | 2.0183 | 4.8551 | 4.8551
UG-11B | UG-11B-S05 | P0227-05 | 10 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 5.87 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 10 | 2.8 | 0.8 | 3.4 | 122.4003 | 0 | 12 | 15.3939 | 2.0183 | 2.0183 | 4.8551 | 4.8551
UG-11B | UG-11B-S05 | P0227-06 | 10 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 5.85 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 10 | 2.8 | 0.8 | 3.4 | 122.4003 | 0 | 12 | 15.3939 | 2.0183 | 2.0183 | 4.8551 | 4.8551
UG-11B | UG-11B-S05 | P0227-07 | 10 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 6.97 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 10 | 2.8 | 0.8 | 3.4 | 122.4003 | 0 | 12 | 15.3939 | 2.0183 | 2.0183 | 4.8551 | 4.8551
UG-11B | UG-11B-S05 | P0227-08 | 7.3734 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 10.65 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 7.3734 | 2.8 | 0.8 | 3.4 | 90.2505 | 0 | 8.8481 | 11.3505 | 2.0183 | 2.0183 | 4.8551 | 4.8551
UG-11B | UG-11B-S05 | P0102 | 1.3552 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 14.64 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 1.3552 | 2.8 | 0.8 | 3.4 | 16.5877 | 0 | 1.6262 | 2.0862 | 2.0183 | 2.0183 | 4.8552 | 4.8552
UG-11B | UG-11B-S05 | P0103 | 1.005 | 1.425 | -4.3125 | -4.3125 | -2.3875 | -2.3875 | 15.47 | -4.3125 | -4.3125 | 3.6125 | 2.8125 | 0.8 | 8.5375 | Shoring | 1.005 | 2.8125 | 0.8 | 3.425 | 12.4347 | 0 | 1.2186 | 1.6028 | 1.9736 | 1.9736 | 4.7607 | 4.7607
UG-11B | UG-11B-S05 | P0104-01 | 0.2664 | 1.425 | -4.3125 | -4.3125 | -2.3875 | -2.3875 | 16.08 | -4.3125 | -4.3125 | 3.6125 | 2.8125 | 0.8 | 8.5375 | Shoring | 0.2664 | 2.8125 | 0.8 | 3.425 | 3.2961 | 0 | 0.32301 | 0.42486 | 1.9736 | 1.9736 | 4.7607 | 4.7607
UG-11B | UG-11B-S05 | P0104-02 | 0.7386 | 1.425 | -4.3125 | -4.3125 | -2.3875 | -2.3875 | 16.02 | -4.3125 | -4.3125 | 3.6125 | 2.8125 | 0.8 | 8.5375 | Shoring | 0.7386 | 2.8125 | 0.8 | 3.425 | 9.1386 | 0 | 0.89556 | 1.178 | 1.9736 | 1.9736 | 4.7607 | 4.7607
UG-11B | UG-11B-S05 | P0256-01 | 0.4614 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 15.99 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 0.4614 | 2.8 | 0.8 | 3.4 | 5.6475 | 0 | 0.55367 | 0.71026 | 2.0183 | 2.0183 | 4.8552 | 4.8552
UG-11B | UG-11B-S06 | P0256-02 | 8.6197 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 15.38 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 8.6197 | 2.8 | 0.8 | 3.4 | 105.5054 | 0 | 10.3437 | 13.269 | 2.0183 | 2.0183 | 4.8552 | 4.8552
UG-11B | UG-11B-S06 | P0048-01 | 0.18027 | 1.425 | -4.3125 | -4.3125 | -2.3875 | -2.3875 | 15.2 | -4.3125 | -4.3125 | 3.6125 | 2.8125 | 0.8 | 8.5375 | Shoring | 0.18027 | 2.8125 | 0.8 | 3.425 | 2.2304 | 0 | 0.21857 | 0.2875 | 1.9736 | 1.9736 | 4.7607 | 4.7607
UG-11B | UG-11B-S06 | P0048-02 | 0.82473 | 1.425 | -4.3125 | -4.3125 | -2.3875 | -2.3875 | 14.38 | -4.3125 | -4.3125 | 3.6125 | 2.8125 | 0.8 | 8.5375 | Shoring | 0.82473 | 2.8125 | 0.8 | 3.425 | 10.2042 | 0 | 0.99999 | 1.3153 | 1.9736 | 1.9736 | 4.7607 | 4.7607
UG-11B | UG-11B-S06 | P0047 | 1.005 | 1.425 | -4.3125 | -4.3125 | -2.3875 | -2.3875 | 13.75 | -4.3125 | -4.3125 | 3.6125 | 2.8125 | 0.8 | 8.5375 | Shoring | 1.005 | 2.8125 | 0.8 | 3.425 | 12.4347 | 0 | 1.2186 | 1.6028 | 1.9736 | 1.9736 | 4.7607 | 4.7607
UG-11B | UG-11B-S06 | P0263 | 7.057 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 9.76 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 7.057 | 2.8 | 0.8 | 3.4 | 86.3777 | 0 | 8.4684 | 10.8634 | 2.0183 | 2.0183 | 4.8552 | 4.8552
UG-11B | UG-11B-S07 | P0789-01 | 1.1133 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 9.21 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 1.1133 | 2.8 | 0.8 | 3.4 | 13.6263 | 0 | 1.3359 | 1.7137 | 2.0183 | 2.0183 | 4.8552 | 4.8552
UG-11B | UG-11B-S07 | P0789-02 | 10 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 5.54 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 10 | 2.8 | 0.8 | 3.4 | 122.3999 | 0 | 12 | 15.3938 | 2.0183 | 2.0183 | 4.8552 | 4.8552
UG-11B | UG-11B-S07 | P0789-03 | 2.4056 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 5.03 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 2.4056 | 2.8 | 0.8 | 3.4 | 29.4451 | 0 | 2.8868 | 3.7032 | 2.0183 | 2.0183 | 4.8552 | 4.8552
UG-11B | UG-11B-S07 | P0712 | 0.3 | 1.4 | -4.3 | -4.3 | -2.4 | -2.4 | 4.98 | -4.3 | -4.3 | 3.6 | 2.8 | 0.8 | 8.5 | Shoring | 0.3 | 2.8 | 0.8 | 3.4 | 3.672 | 0 | 0.36 | 0.46181 | 2.0183 | 2.0183 | 4.8552 | 4.8552
UG-11B | UG-11B-S07 | P0273-01 | 7.2944 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 4.57 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 7.2944 | 2.6 | 0.8 | 3 | 74.4024 | 0 | 7.2944 | 5.729 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S07 | P0273-02 | 10 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 4.63 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 10 | 2.6 | 0.8 | 3 | 101.9999 | 0 | 10 | 7.854 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S07 | P0273-03 | 2.4434 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 6.65 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 2.4434 | 2.6 | 0.8 | 3 | 24.9225 | 0 | 2.4434 | 1.919 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S07 | P0701 | 1.3063 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 7.54 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 1.3063 | 2.6 | 0.8 | 3 | 13.3242 | 0 | 1.3063 | 1.026 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S07 | P0700 | 1.3419 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 7.63 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 1.3419 | 2.6 | 0.8 | 3 | 13.6874 | 0 | 1.3419 | 1.0539 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-11B | UG-11B-S07 | P0112-01 | 4.9084 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 6.37 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 4.9084 | 2.6 | 0.8 | 3 | 50.0657 | 0 | 4.9084 | 3.855 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-11B | UG-11B-S07 | P0112-02 | 0.49386 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 6.23 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.49386 | 2.6 | 0.8 | 3 | 5.0374 | 0 | 0.49386 | 0.38788 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-11B | UG-11B-S07 | P0262-01 | 9.5061 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 4.66 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 9.5061 | 2.6 | 0.8 | 3 | 96.9627 | 0 | 9.5062 | 7.4662 | 3.0382 | 3.0382 | 7.0098 | 7.0098
UG-11B | UG-11B-S07 | P0262-02 | 10 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 4.65 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 10 | 2.6 | 0.8 | 3 | 102.0002 | 0 | 10 | 7.854 | 3.0382 | 3.0382 | 7.0098 | 7.0098
UG-11B | UG-11B-S07 | P0262-03 | 0.41198 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 8.17 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.41198 | 2.6 | 0.8 | 3 | 4.2022 | 0 | 0.41198 | 0.32357 | 3.0382 | 3.0382 | 7.0098 | 7.0098
UG-11B | UG-11B-S07 | P0126 | 0.63268 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 8.32 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.63268 | 2.6 | 0.8 | 3 | 6.4533 | 0 | 0.63268 | 0.4969 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-11B | UG-11B-S07 | P0713 | 0.37256 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 8.56 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.37256 | 2.6 | 0.8 | 3 | 3.8001 | 0 | 0.37256 | 0.29261 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-11B | UG-11B-S07 | P0714 | 0.37259 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 8.56 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.37259 | 2.6 | 0.8 | 3 | 3.8004 | 0 | 0.37259 | 0.29263 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S07 | P0127 | 0.63224 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 8.33 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.63224 | 2.6 | 0.8 | 3 | 6.4489 | 0 | 0.63224 | 0.49656 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S07 | P0122 | 7.4249 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 6.4 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 7.4249 | 2.6 | 0.8 | 3 | 75.7344 | 0 | 7.4249 | 5.8315 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S07 | P0706-01 | 0.15299 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 6.38 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.15299 | 2.6 | 0.8 | 3 | 1.5605 | 0 | 0.15299 | 0.12016 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S07 | P0706-02 | 1.2399 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 6.2 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 1.2399 | 2.6 | 0.8 | 3 | 12.6474 | 0 | 1.2399 | 0.97384 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S07 | P0707 | 1.2714 | 0.99887 | -4.0994 | -4.0994 | -2.6006 | -2.6006 | 5.58 | -4.0994 | -4.0994 | 3.3994 | 2.5994 | 0.8 | 7.8983 | Shoring | 1.2714 | 2.5994 | 0.8 | 2.9989 | 12.9607 | 0 | 1.2706 | 0.99626 | 3.0423 | 3.0423 | 7.0183 | 7.0183
UG-11B | UG-11B-S07 | P0274 | 5.5655 | 0.99887 | -4.0994 | -4.0994 | -2.6006 | -2.6006 | 1.31 | -4.0994 | -4.0994 | 3.3994 | 2.5994 | 0.8 | 7.8983 | Shoring | 5.5655 | 2.5994 | 0.8 | 2.9989 | 56.7371 | 0 | 5.5623 | 4.3613 | 3.0423 | 3.0423 | 7.0183 | 7.0183
UG-11B | UG-11B-S07 | P0703 | 0.39486 | 0.99887 | -4.0994 | -4.0994 | -2.6006 | -2.6006 | 1.02 | -4.0994 | -4.0994 | 3.3994 | 2.5994 | 0.8 | 7.8983 | Shoring | 0.39486 | 2.5994 | 0.8 | 2.9989 | 4.0254 | 0 | 0.39464 | 0.30943 | 3.0423 | 3.0423 | 7.0183 | 7.0183
UG-11B | UG-11B-S07 | P0702 | 0.34633 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 0.68 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.34633 | 2.6 | 0.8 | 3 | 3.5326 | 0 | 0.34633 | 0.27201 | 3.0382 | 3.0382 | 7.0098 | 7.0098
UG-11B | UG-11B-S08 | P0113-01 | 1.182 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 11.6 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 1.182 | 2.6 | 0.8 | 3 | 12.0568 | 0 | 1.182 | 0.92837 | 3.0382 | 3.0382 | 7.0098 | 7.0098
UG-11B | UG-11B-S08 | P0113-02 | 10 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 12.78 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 10 | 2.6 | 0.8 | 3 | 102.0002 | 0 | 10 | 7.854 | 3.0382 | 3.0382 | 7.0098 | 7.0098
UG-11B | UG-11B-S08 | P0113-03 | 10 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 22.78 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 10 | 2.6 | 0.8 | 3 | 102.0002 | 0 | 10 | 7.854 | 3.0382 | 3.0382 | 7.0098 | 7.0098
UG-11B | UG-11B-S08 | P0113-04 | 8.275 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 32.78 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 8.275 | 2.6 | 0.8 | 3 | 84.4052 | 0 | 8.275 | 6.4992 | 3.0382 | 3.0382 | 7.0098 | 7.0098
UG-11B | UG-11B-S09 | P0345-01 | 6 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 99 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 6 | 2.6 | 0.8 | 3 | 61.1999 | 0 | 6 | 4.7124 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S10 | P0345-02 | 4 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 99 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 4 | 2.6 | 0.8 | 3 | 40.8 | 0 | 4 | 3.1416 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S10 | P0345-03 | 10 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 99 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 10 | 2.6 | 0.8 | 3 | 101.9999 | 0 | 10 | 7.854 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S10 | P0345-04 | 10 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 0 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 10 | 2.6 | 0.8 | 3 | 101.9999 | 0 | 10 | 7.854 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S10 | P0345-05 | 10 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 1.02 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 10 | 2.6 | 0.8 | 3 | 101.9999 | 0 | 10 | 7.854 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S10 | P0345-06 | 3.6676 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 11.01 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 3.6676 | 2.6 | 0.8 | 3 | 37.4099 | 0 | 3.6676 | 2.8805 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S10 | P0321 | 5.1679 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 14.68 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 5.1679 | 2.6 | 0.8 | 3 | 52.7125 | 0 | 5.1679 | 4.0589 | 3.0382 | 3.0382 | 7.0098 | 7.0098
UG-11B | UG-11B-S10 | P0402 | 0.18002 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 19.85 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.18002 | 2.6 | 0.8 | 3 | 1.8362 | 0 | 0.18002 | 0.14139 | 3.0382 | 3.0382 | 7.0098 | 7.0098
UG-11B | UG-11B-S10 | P0322-01 | 0.98446 | 1.0219 | -4.111 | -4.111 | -2.589 | -2.589 | 20.03 | -4.111 | -4.111 | 3.411 | 2.611 | 0.8 | 7.9329 | Shoring | 0.98446 | 2.611 | 0.8 | 3.0219 | 10.1474 | 0 | 0.99525 | 0.80746 | 2.9617 | 2.9617 | 6.848 | 6.848
UG-11B | UG-11B-S10 | P0322-02 | 5.4448 | 1.0219 | -4.111 | -4.111 | -2.589 | -2.589 | 17.77 | -4.111 | -4.111 | 3.411 | 2.611 | 0.8 | 7.9329 | Shoring | 5.4448 | 2.611 | 0.8 | 3.0219 | 56.1228 | 0 | 5.5044 | 4.4659 | 2.9617 | 2.9617 | 6.848 | 6.848
UG-11B | UG-11B-S11 | P0773-01 | 6 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 99 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 6 | 2.6 | 0.8 | 3 | 61.2 | 0 | 6 | 4.7124 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S12 | P0773-02 | 4 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 99 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 4 | 2.6 | 0.8 | 3 | 40.8 | 0 | 4 | 3.1416 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S12 | P0773-03 | 10 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 24.58 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 10 | 2.6 | 0.8 | 3 | 102 | 0 | 10 | 7.854 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S12 | P0773-04 | 10 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 0 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 10 | 2.6 | 0.8 | 3 | 102 | 0 | 10 | 7.854 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S12 | P0773-05 | 6.3311 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 1 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 6.3311 | 2.6 | 0.8 | 3 | 64.5777 | 0 | 6.3311 | 4.9725 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S12 | P0268 | 2.4318 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 7.33 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 2.4318 | 2.6 | 0.8 | 3 | 24.8042 | 0 | 2.4318 | 1.9099 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-11B | UG-11B-S13 | P0206-01 | 10 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 26.63 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 10 | 3.1348 | 0.8 | 4.0696 | 160.1306 | 0 | 15.348 | 33.6405 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-11B | UG-11B-S13 | P0206-02 | 8.1 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 27.52 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 8.1 | 3.1348 | 0.8 | 4.0696 | 129.7058 | 0 | 12.4319 | 27.2488 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-11B | UG-11B-S14 | P0206-03 | 1.9 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 99 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 1.9 | 3.1348 | 0.8 | 4.0696 | 30.4248 | 0 | 2.9161 | 6.3917 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-11B | UG-11B-S14 | P0206-04 | 3.2462 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 26.88 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 3.2462 | 3.1348 | 0.8 | 4.0696 | 51.9817 | 0 | 4.9823 | 10.9204 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-11B | UG-11B-S14 | P0708 | 3.1 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 23.8 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 3.1 | 3.1348 | 0.8 | 4.0696 | 49.64 | 0 | 4.7578 | 10.4285 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-11B | UG-11B-S14 | P0709 | 3.1 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 21.55 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 3.1 | 3.1348 | 0.8 | 4.0696 | 49.641 | 0 | 4.7579 | 10.4287 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-11B | UG-11B-S14 | P0267-01 | 0.5538 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 21.17 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 0.5538 | 3.1348 | 0.8 | 4.0696 | 8.868 | 0 | 0.84997 | 1.863 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-11B | UG-11B-S14 | P0267-02 | 8.2538 | 2.0696 | -4.6348 | -4.6348 | -2.0652 | -2.0652 | 16.68 | -4.6348 | -4.6348 | 3.9348 | 3.1348 | 0.8 | 9.5044 | Shoring | 8.2538 | 3.1348 | 0.8 | 4.0696 | 132.1694 | 0 | 12.668 | 27.7664 | 1.1934 | 1.1934 | 3.1124 | 3.1124
UG-13 | UG-13-S01 | P0311 | 1.3069 | 1.4296 | -5.6148 | -5.6148 | -3.6852 | -3.6852 | 6.37 | -5.6148 | -5.6148 | 4.9148 | 4.1148 | 0.8 | 11.1444 | Shoring | 1.3069 | 4.1148 | 0.8 | 3.4296 | 22.0297 | 0 | 1.5877 | 2.0979 | 2.9321 | 2.9321 | 5.7102 | 5.7102
UG-13 | UG-13-S01 | P0747 | 1.5 | 1.4296 | -5.6148 | -5.6148 | -3.6852 | -3.6852 | 6.47 | -5.6148 | -5.6148 | 4.9148 | 4.1148 | 0.8 | 11.1444 | Shoring | 1.5 | 4.1148 | 0.8 | 3.4296 | 25.2837 | 0 | 1.8222 | 2.4077 | 2.9321 | 2.9321 | 5.7102 | 5.7102
UG-13 | UG-13-S01 | P0314-01 | 7.193 | 2.0412 | -5.9206 | -5.9206 | -3.3794 | -3.3794 | 6.65 | -5.9206 | -5.9206 | 5.2206 | 4.4206 | 0.8 | 12.0618 | Shoring | 7.193 | 4.4206 | 0.8 | 4.0412 | 151.7553 | 0 | 10.9378 | 23.5383 | 1.8943 | 1.8943 | 3.84 | 3.84
UG-13 | UG-13-S01 | P0314-02 | 2.5591 | 2.0412 | -5.9206 | -5.9206 | -3.3794 | -3.3794 | 8.34 | -5.9206 | -5.9206 | 5.2206 | 4.4206 | 0.8 | 12.0618 | Shoring | 2.5591 | 4.4206 | 0.8 | 4.0412 | 53.9909 | 0 | 3.8914 | 8.3744 | 1.8943 | 1.8943 | 3.84 | 3.84
UG-13 | UG-13-S01 | P0793 | 0.95902 | 2.0412 | -5.9206 | -5.9206 | -3.3794 | -3.3794 | 9.25 | -5.9206 | -5.9206 | 5.2206 | 4.4206 | 0.8 | 12.0618 | Shoring | 0.95902 | 4.4206 | 0.8 | 4.0412 | 20.233 | 0 | 1.4583 | 3.1383 | 1.8943 | 1.8943 | 3.84 | 3.84
UG-13 | UG-13-S01 | P0156 | 3.1 | 2.045 | -5.9225 | -5.9225 | -3.3775 | -3.3775 | 9.63 | -5.9225 | -5.9225 | 5.2225 | 4.4225 | 0.8 | 12.0675 | Shoring | 3.1 | 4.4225 | 0.8 | 4.045 | 65.4875 | 0 | 4.7197 | 10.1821 | 1.8898 | 1.8898 | 3.8319 | 3.8319
UG-13 | UG-13-S01 | P0155 | 3.1 | 2.045 | -5.9225 | -5.9225 | -3.3775 | -3.3775 | 10.19 | -5.9225 | -5.9225 | 5.2225 | 4.4225 | 0.8 | 12.0675 | Shoring | 3.1 | 4.4225 | 0.8 | 4.045 | 65.4875 | 0 | 4.7197 | 10.1821 | 1.8898 | 1.8898 | 3.8319 | 3.8319
UG-13 | UG-13-S02 | P0154-01 | 0.28186 | 2.0696 | -5.9348 | -5.9348 | -3.3652 | -3.3652 | 10.13 | -5.9348 | -5.9348 | 5.2348 | 4.4348 | 0.8 | 12.1044 | Shoring | 0.28186 | 4.4348 | 0.8 | 4.0696 | 6.0047 | 0 | 0.4326 | 0.9482 | 1.8611 | 1.8611 | 3.7801 | 3.7801
UG-13 | UG-13-S02 | P0154-02 | 5.5826 | 2.0696 | -5.9348 | -5.9348 | -3.3652 | -3.3652 | 9.33 | -5.9348 | -5.9348 | 5.2348 | 4.4348 | 0.8 | 12.1044 | Shoring | 5.5826 | 4.4348 | 0.8 | 4.0696 | 118.9297 | 0 | 8.5682 | 18.7802 | 1.8611 | 1.8611 | 3.7801 | 3.7801
UG-13 | UG-13-S02 | P0790 | 2.4823 | 2.0696 | -5.9348 | -5.9348 | -3.3652 | -3.3652 | 9.24 | -5.9348 | -5.9348 | 5.2348 | 4.4348 | 0.8 | 12.1044 | Shoring | 2.4823 | 4.4348 | 0.8 | 4.0696 | 52.8828 | 0 | 3.8099 | 8.3507 | 1.8611 | 1.8611 | 3.7801 | 3.7801
UG-13 | UG-13-S02 | P0301-01 | 1.935 | 2.0696 | -5.9348 | -5.9348 | -3.3652 | -3.3652 | 9.23 | -5.9348 | -5.9348 | 5.2348 | 4.4348 | 0.8 | 12.1044 | Shoring | 1.935 | 4.4348 | 0.8 | 4.0696 | 41.223 | 0 | 2.9699 | 6.5095 | 1.8611 | 1.8611 | 3.7801 | 3.7801
UG-13 | UG-13-S02 | P0301-02 | 10 | 2.0696 | -5.9348 | -5.9348 | -3.3652 | -3.3652 | 9.27 | -5.9348 | -5.9348 | 5.2348 | 4.4348 | 0.8 | 12.1044 | Shoring | 10 | 4.4348 | 0.8 | 4.0696 | 213.0355 | 0 | 15.348 | 33.6405 | 1.8611 | 1.8611 | 3.7801 | 3.7801
UG-13 | UG-13-S02 | P0301-03 | 3.3175 | 2.0696 | -5.9348 | -5.9348 | -3.3652 | -3.3652 | 10.98 | -5.9348 | -5.9348 | 5.2348 | 4.4348 | 0.8 | 12.1044 | Shoring | 3.3175 | 4.4348 | 0.8 | 4.0696 | 70.6738 | 0 | 5.0916 | 11.1601 | 1.8611 | 1.8611 | 3.7801 | 3.7801
UG-13 | UG-13-S02 | P0146 | 3.1 | 2.045 | -5.9225 | -5.9225 | -3.3775 | -3.3775 | 12.07 | -5.9225 | -5.9225 | 5.2225 | 4.4225 | 0.8 | 12.0675 | Shoring | 3.1 | 4.4225 | 0.8 | 4.045 | 65.4875 | 0 | 4.7198 | 10.1821 | 1.8898 | 1.8898 | 3.8319 | 3.8319
UG-13 | UG-13-S02 | P0145 | 3.1 | 2.045 | -5.9225 | -5.9225 | -3.3775 | -3.3775 | 12.37 | -5.9225 | -5.9225 | 5.2225 | 4.4225 | 0.8 | 12.0675 | Shoring | 3.1 | 4.4225 | 0.8 | 4.045 | 65.4875 | 0 | 4.7197 | 10.1821 | 1.8898 | 1.8898 | 3.8319 | 3.8319
UG-13 | UG-13-S02 | P0326-01 | 0.48253 | 2.0411 | -5.9205 | -5.9205 | -3.3795 | -3.3795 | 12.24 | -5.9205 | -5.9205 | 5.2205 | 4.4205 | 0.8 | 12.0616 | Shoring | 0.48253 | 4.4205 | 0.8 | 4.0411 | 10.1798 | 0 | 0.73371 | 1.5788 | 1.8945 | 1.8945 | 3.8403 | 3.8403
UG-13 | UG-13-S02 | P0326-02 | 2.4 | 2.0411 | -5.9205 | -5.9205 | -3.3795 | -3.3795 | 11.68 | -5.9205 | -5.9205 | 5.2205 | 4.4205 | 0.8 | 12.0616 | Shoring | 2.4 | 4.4205 | 0.8 | 4.0411 | 50.6317 | 0 | 3.6493 | 7.8527 | 1.8945 | 1.8945 | 3.8403 | 3.8403
UG-13 | UG-13-S03 | P0326-03 | 7.6 | 2.0411 | -5.9205 | -5.9205 | -3.3795 | -3.3795 | 10.84 | -5.9205 | -5.9205 | 5.2205 | 4.4205 | 0.8 | 12.0616 | Shoring | 7.6 | 4.4205 | 0.8 | 4.0411 | 160.3339 | 0 | 11.5561 | 24.8668 | 1.8945 | 1.8945 | 3.8403 | 3.8403
UG-13 | UG-13-S03 | P0326-04 | 10 | 2.0411 | -5.9205 | -5.9205 | -3.3795 | -3.3795 | 10.84 | -5.9205 | -5.9205 | 5.2205 | 4.4205 | 0.8 | 12.0616 | Shoring | 10 | 4.4205 | 0.8 | 4.0411 | 210.9656 | 0 | 15.2054 | 32.7195 | 1.8945 | 1.8945 | 3.8403 | 3.8403
UG-13 | UG-13-S03 | P0326-05 | 10 | 2.0411 | -5.9205 | -5.9205 | -3.3795 | -3.3795 | 11.92 | -5.9205 | -5.9205 | 5.2205 | 4.4205 | 0.8 | 12.0616 | Shoring | 10 | 4.4205 | 0.8 | 4.0411 | 210.9656 | 0 | 15.2054 | 32.7195 | 1.8945 | 1.8945 | 3.8403 | 3.8403
UG-13 | UG-13-S03 | P0326-06 | 1.9873 | 2.0411 | -5.9205 | -5.9205 | -3.3795 | -3.3795 | 15.29 | -5.9205 | -5.9205 | 5.2205 | 4.4205 | 0.8 | 12.0616 | Shoring | 1.9873 | 4.4205 | 0.8 | 4.0411 | 41.9251 | 0 | 3.0218 | 6.5023 | 1.8945 | 1.8945 | 3.8403 | 3.8403
UG-13 | UG-13-S03 | P0037 | 0.9 | 2.0412 | -5.9206 | -5.9206 | -3.3794 | -3.3794 | 16.19 | -5.9206 | -5.9206 | 5.2206 | 4.4206 | 0.8 | 12.0618 | Shoring | 0.9 | 4.4206 | 0.8 | 4.0412 | 18.9878 | 0 | 1.3685 | 2.9451 | 1.8943 | 1.8943 | 3.84 | 3.84
UG-13 | UG-13-S03 | P0205 | 1.5773 | 1.42 | -5.61 | -5.61 | -3.69 | -3.69 | 16.62 | -5.61 | -5.61 | 4.91 | 4.11 | 0.8 | 11.13 | Shoring | 1.5773 | 4.11 | 0.8 | 3.42 | 26.4864 | 0 | 1.9085 | 2.4979 | 2.9556 | 2.9556 | 5.7525 | 5.7525
UG-13 | UG-13-S03 | P0385 | 0.205 | 1.42 | -5.61 | -5.61 | -3.69 | -3.69 | 17.41 | -5.61 | -5.61 | 4.91 | 4.11 | 0.8 | 11.13 | Shoring | 0.205 | 4.11 | 0.8 | 3.42 | 3.4425 | 0 | 0.24806 | 0.32466 | 2.9556 | 2.9556 | 5.7525 | 5.7525
UG-13 | UG-13-S04 | P0327-01 | 10 | 2.0412 | -5.9206 | -5.9206 | -3.3794 | -3.3794 | 15.36 | -5.9206 | -5.9206 | 5.2206 | 4.4206 | 0.8 | 12.0618 | Shoring | 10 | 4.4206 | 0.8 | 4.0412 | 210.9752 | 0 | 15.206 | 32.7237 | 1.8943 | 1.8943 | 3.84 | 3.84
UG-13 | UG-13-S04 | P0327-02 | 10 | 2.0412 | -5.9206 | -5.9206 | -3.3794 | -3.3794 | 24.52 | -5.9206 | -5.9206 | 5.2206 | 4.4206 | 0.8 | 12.0618 | Shoring | 10 | 4.4206 | 0.8 | 4.0412 | 210.9752 | 0 | 15.206 | 32.7237 | 1.8943 | 1.8943 | 3.84 | 3.84
UG-13 | UG-13-S04 | P0327-03 | 10 | 2.0412 | -5.9206 | -5.9206 | -3.3794 | -3.3794 | 99 | -5.9206 | -5.9206 | 5.2206 | 4.4206 | 0.8 | 12.0618 | Shoring | 10 | 4.4206 | 0.8 | 4.0412 | 210.9752 | 0 | 15.206 | 32.7237 | 1.8943 | 1.8943 | 3.84 | 3.84
UG-13 | UG-13-S04 | P0327-04 | 7.2 | 2.0412 | -5.9206 | -5.9206 | -3.3794 | -3.3794 | 99 | -5.9206 | -5.9206 | 5.2206 | 4.4206 | 0.8 | 12.0618 | Shoring | 7.2 | 4.4206 | 0.8 | 4.0412 | 151.9022 | 0 | 10.9483 | 23.5611 | 1.8943 | 1.8943 | 3.84 | 3.84
UG-13 | UG-13-S05 | P0327-05 | 2.8 | 2.0412 | -5.9206 | -5.9206 | -3.3794 | -3.3794 | 32.42 | -5.9206 | -5.9206 | 5.2206 | 4.4206 | 0.8 | 12.0618 | Shoring | 2.8 | 4.4206 | 0.8 | 4.0412 | 59.0731 | 0 | 4.2577 | 9.1626 | 1.8943 | 1.8943 | 3.84 | 3.84
UG-13 | UG-13-S05 | P0327-06 | 10 | 2.0412 | -5.9206 | -5.9206 | -3.3794 | -3.3794 | 23.09 | -5.9206 | -5.9206 | 5.2206 | 4.4206 | 0.8 | 12.0618 | Shoring | 10 | 4.4206 | 0.8 | 4.0412 | 210.9752 | 0 | 15.206 | 32.7237 | 1.8943 | 1.8943 | 3.84 | 3.84
UG-13 | UG-13-S05 | P0327-07 | 10 | 2.0412 | -5.9206 | -5.9206 | -3.3794 | -3.3794 | 14.68 | -5.9206 | -5.9206 | 5.2206 | 4.4206 | 0.8 | 12.0618 | Shoring | 10 | 4.4206 | 0.8 | 4.0412 | 210.9752 | 0 | 15.206 | 32.7237 | 1.8943 | 1.8943 | 3.84 | 3.84
UG-13 | UG-13-S05 | P0327-08 | 10 | 2.0412 | -5.9206 | -5.9206 | -3.3794 | -3.3794 | 23.88 | -5.9206 | -5.9206 | 5.2206 | 4.4206 | 0.8 | 12.0618 | Shoring | 10 | 4.4206 | 0.8 | 4.0412 | 210.9752 | 0 | 15.206 | 32.7237 | 1.8943 | 1.8943 | 3.84 | 3.84
UG-13 | UG-13-S05 | P0327-09 | 7.5386 | 2.0412 | -5.9206 | -5.9206 | -3.3794 | -3.3794 | 23.8 | -5.9206 | -5.9206 | 5.2206 | 4.4206 | 0.8 | 12.0618 | Shoring | 7.5386 | 4.4206 | 0.8 | 4.0412 | 159.0453 | 0 | 11.4632 | 24.6691 | 1.8943 | 1.8943 | 3.84 | 3.84
UG-13 | UG-13-S05 | P0599 | 2 | 2.0412 | -5.9206 | -5.9206 | -3.3794 | -3.3794 | 23.83 | -5.9206 | -5.9206 | 5.2206 | 4.4206 | 0.8 | 12.0618 | Shoring | 2 | 4.4206 | 0.8 | 4.0412 | 42.1948 | 0 | 3.0412 | 6.5447 | 1.8943 | 1.8943 | 3.84 | 3.84
UG-13 | UG-13-S05 | P0600-01 | 0.46143 | 2.0696 | -5.9348 | -5.9348 | -3.3652 | -3.3652 | 23.38 | -5.9348 | -5.9348 | 5.2348 | 4.4348 | 0.8 | 12.1044 | Shoring | 0.46143 | 4.4348 | 0.8 | 4.0696 | 9.8301 | 0 | 0.7082 | 1.5523 | 1.8611 | 1.8611 | 3.7801 | 3.7801
UG-13 | UG-13-S05 | P0600-02 | 1.5431 | 2.0696 | -5.9348 | -5.9348 | -3.3652 | -3.3652 | 21.83 | -5.9348 | -5.9348 | 5.2348 | 4.4348 | 0.8 | 12.1044 | Shoring | 1.5431 | 4.4348 | 0.8 | 4.0696 | 32.8736 | 0 | 2.3684 | 5.1911 | 1.8611 | 1.8611 | 3.7801 | 3.7801
UG-13A | UG-13A-S01 | P0350-01 | 6 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 99 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 6 | 3.9 | 0.8 | 3 | 84.5999 | 0 | 6 | 4.7124 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13A | UG-13A-S02 | P0350-02 | 4 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 34.19 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 4 | 3.9 | 0.8 | 3 | 56.3999 | 0 | 4 | 3.1416 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13A | UG-13A-S02 | P0350-03 | 10 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 28.31 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 10 | 3.9 | 0.8 | 3 | 140.9998 | 0 | 10 | 7.8539 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13A | UG-13A-S02 | P0350-04 | 10 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 0 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 10 | 3.9 | 0.8 | 3 | 140.9998 | 0 | 10 | 7.8539 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13A | UG-13A-S02 | P0350-05 | 1.4925 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 1 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 1.4925 | 3.9 | 0.8 | 3 | 21.0441 | 0 | 1.4925 | 1.1722 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13A | UG-13A-S02 | P0743 | 0.6364 | 0.98079 | -5.3904 | -5.3904 | -3.9096 | -3.9096 | 2.49 | -5.3904 | -5.3904 | 4.6904 | 3.8904 | 0.8 | 10.4712 | Shoring | 0.6364 | 3.8904 | 0.8 | 2.9808 | 8.8975 | 0 | 0.63028 | 0.48081 | 4.5171 | 4.5171 | 8.5665 | 8.5665
UG-13A | UG-13A-S02 | P0303 | 0.78329 | 0.99999 | -5.4 | -5.4 | -3.9 | -3.9 | 3.13 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 0.78329 | 3.9 | 0.8 | 3 | 11.0444 | 0 | 0.78329 | 0.61519 | 4.4202 | 4.4202 | 8.3918 | 8.3918
UG-13A | UG-13A-S02 | P0744 | 0.6364 | 0.99999 | -5.4 | -5.4 | -3.9 | -3.9 | 3.91 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 0.6364 | 3.9 | 0.8 | 3 | 8.9731 | 0 | 0.63639 | 0.49981 | 4.4202 | 4.4202 | 8.3918 | 8.3918
UG-13A | UG-13A-S02 | P0147 | 2.6008 | 0.99999 | -5.4 | -5.4 | -3.9 | -3.9 | 4.54 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 2.6008 | 3.9 | 0.8 | 3 | 36.6711 | 0 | 2.6008 | 2.0426 | 4.4202 | 4.4202 | 8.3918 | 8.3918
UG-13A | UG-13A-S02 | P0401 | 0.18 | 0.99999 | -5.4 | -5.4 | -3.9 | -3.9 | 7.14 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 0.18 | 3.9 | 0.8 | 3 | 2.538 | 0 | 0.18 | 0.14137 | 4.4202 | 4.4202 | 8.3918 | 8.3918
UG-13A | UG-13A-S02 | P0302 | 1.9145 | 1.022 | -5.411 | -5.411 | -3.889 | -3.889 | 7.32 | -5.411 | -5.411 | 4.711 | 3.911 | 0.8 | 10.5329 | Shoring | 1.9145 | 3.911 | 0.8 | 3.022 | 27.2556 | 0 | 1.9355 | 1.5704 | 4.3138 | 4.3138 | 8.2 | 8.2
UG-13A | UG-13A-S03 | P0351-01 | 6 | 1 | -4.15 | -4.15 | -2.65 | -2.65 | 99 | -4.15 | -4.15 | 3.45 | 2.65 | 0.8 | 8 | Shoring | 6 | 2.65 | 0.8 | 3 | 62.0999 | 0 | 6 | 4.7124 | 3.0914 | 3.0914 | 7.063 | 7.063
UG-13A | UG-13A-S04 | P0351-02 | 4 | 1 | -4.15 | -4.15 | -2.65 | -2.65 | 30.9 | -4.15 | -4.15 | 3.45 | 2.65 | 0.8 | 8 | Shoring | 4 | 2.65 | 0.8 | 3 | 41.4 | 0 | 4 | 3.1416 | 3.0914 | 3.0914 | 7.063 | 7.063
UG-13A | UG-13A-S04 | P0351-03 | 10 | 1 | -4.15 | -4.15 | -2.65 | -2.65 | 20.9 | -4.15 | -4.15 | 3.45 | 2.65 | 0.8 | 8 | Shoring | 10 | 2.65 | 0.8 | 3 | 103.4999 | 0 | 10 | 7.8539 | 3.0914 | 3.0914 | 7.063 | 7.063
UG-13A | UG-13A-S04 | P0351-04 | 10 | 1 | -4.15 | -4.15 | -2.65 | -2.65 | 0 | -4.15 | -4.15 | 3.45 | 2.65 | 0.8 | 8 | Shoring | 10 | 2.65 | 0.8 | 3 | 103.4999 | 0 | 10 | 7.8539 | 3.0914 | 3.0914 | 7.063 | 7.063
UG-13A | UG-13A-S04 | P0351-05 | 1.9627 | 1 | -4.15 | -4.15 | -2.65 | -2.65 | 1.1 | -4.15 | -4.15 | 3.45 | 2.65 | 0.8 | 8 | Shoring | 1.9627 | 2.65 | 0.8 | 3 | 20.3134 | 0 | 1.9626 | 1.5415 | 3.0914 | 3.0914 | 7.063 | 7.063
UG-13A | UG-13A-S04 | P0716 | 0.37133 | 1 | -4.15 | -4.15 | -2.65 | -2.65 | 3.06 | -4.15 | -4.15 | 3.45 | 2.65 | 0.8 | 8 | Shoring | 0.37133 | 2.65 | 0.8 | 3 | 3.8432 | 0 | 0.37133 | 0.29164 | 3.0914 | 3.0914 | 7.063 | 7.063
UG-13A | UG-13A-S04 | P0715 | 0.37488 | 0.99999 | -4.15 | -4.15 | -2.65 | -2.65 | 3.44 | -4.15 | -4.15 | 3.45 | 2.65 | 0.8 | 8 | Shoring | 0.37488 | 2.65 | 0.8 | 3 | 3.88 | 0 | 0.37488 | 0.29443 | 3.0914 | 3.0914 | 7.063 | 7.063
UG-13A | UG-13A-S04 | P0129 | 3.1713 | 0.99999 | -4.15 | -4.15 | -2.65 | -2.65 | 3.7 | -4.15 | -4.15 | 3.45 | 2.65 | 0.8 | 8 | Shoring | 3.1713 | 2.65 | 0.8 | 3 | 32.8228 | 0 | 3.1713 | 2.4907 | 3.0914 | 3.0914 | 7.063 | 7.063
UG-13A | UG-13A-S04 | P0717 | 0.3728 | 0.99999 | -4.15 | -4.15 | -2.65 | -2.65 | 5.84 | -4.15 | -4.15 | 3.45 | 2.65 | 0.8 | 8 | Shoring | 0.3728 | 2.65 | 0.8 | 3 | 3.8585 | 0 | 0.3728 | 0.29279 | 3.0914 | 3.0914 | 7.063 | 7.063
UG-13A | UG-13A-S04 | P0718 | 0.37085 | 0.99999 | -4.15 | -4.15 | -2.65 | -2.65 | 5.84 | -4.15 | -4.15 | 3.45 | 2.65 | 0.8 | 8 | Shoring | 0.37085 | 2.65 | 0.8 | 3 | 3.8383 | 0 | 0.37085 | 0.29126 | 3.0914 | 3.0914 | 7.063 | 7.063
UG-13A | UG-13A-S04 | P0277-01 | 3.3762 | 0.99999 | -4.15 | -4.4799 | -2.65 | -2.9799 | 5.86 | -4.4799 | -4.315 | 3.615 | 2.9799 | 0.8 | 8.6599 | Shoring | 3.3762 | 2.815 | 0.8 | 3 | 36.6144 | 0 | 3.3762 | 2.6516 | 3.0914 | 3.4421 | 7.063 | 7.4137
UG-13A | UG-13A-S04 | P0277-02 | 4.9833 | 0.99999 | -4.4799 | -4.9669 | -2.9799 | -3.4669 | 6.24 | -4.9669 | -4.7234 | 4.0234 | 3.4669 | 0.8 | 9.6338 | Shoring | 4.9833 | 3.2234 | 0.8 | 3 | 60.1501 | 0 | 4.9833 | 3.9138 | 3.4421 | 3.9598 | 7.4137 | 7.9314
UG-13A | UG-13A-S04 | P0719 | 0.37606 | 0.99999 | -4.9669 | -5.0037 | -3.4669 | -3.5037 | 7.36 | -5.0037 | -4.9853 | 4.2853 | 3.5037 | 0.8 | 9.7074 | Shoring | 0.37606 | 3.4853 | 0.8 | 3 | 4.8346 | 0 | 0.37606 | 0.29535 | 3.9598 | 3.9989 | 7.9314 | 7.9705
UG-13A | UG-13A-S04 | P0720 | 0.36551 | 1.4 | -5.2037 | -5.2394 | -3.3037 | -3.3394 | 7.31 | -5.2394 | -5.2215 | 4.5215 | 3.7394 | 0.8 | 10.3788 | Shoring | 0.36551 | 3.7215 | 0.8 | 3.4 | 5.619 | 0 | 0.43861 | 0.56265 | 2.7045 | 2.7316 | 5.5413 | 5.5684
UG-13A | UG-13A-S04 | P0519 | 0.3023 | 1.4 | -5.2394 | -5.269 | -3.3394 | -3.3689 | 7.17 | -5.269 | -5.2542 | 4.5542 | 3.769 | 0.8 | 10.4379 | Shoring | 0.3023 | 3.7542 | 0.8 | 3.4 | 4.6809 | 0 | 0.36276 | 0.46536 | 2.7316 | 2.754 | 5.5684 | 5.5908
UG-13A | UG-13A-S04 | P0288 | 0.93818 | 1.4 | -5.269 | -5.3606 | -3.3689 | -3.4606 | 6.76 | -5.3606 | -5.3148 | 4.6148 | 3.8606 | 0.8 | 10.6213 | Shoring | 0.93818 | 3.8148 | 0.8 | 3.4 | 14.7203 | 0 | 1.1258 | 1.4442 | 2.754 | 2.8236 | 5.5908 | 5.6605
UG-13A | UG-13A-S04 | P0516 | 1.2462 | 1.4 | -5.3606 | -5.4824 | -3.4606 | -3.5824 | 6.25 | -5.4824 | -5.4215 | 4.7215 | 3.9824 | 0.8 | 10.8648 | Shoring | 1.2462 | 3.9215 | 0.8 | 3.4 | 20.0058 | 0 | 1.4955 | 1.9184 | 2.8236 | 2.9161 | 5.6605 | 5.7529
UG-13A | UG-13A-S05 | P0517 | 1.2538 | 1.4 | -5.4824 | -5.4871 | -3.5824 | -3.587 | 5.77 | -5.4871 | -5.4847 | 4.7847 | 3.9871 | 0.8 | 10.8741 | Shoring | 1.2538 | 3.9847 | 0.8 | 3.4 | 20.3967 | 0 | 1.5045 | 1.9301 | 2.9161 | 2.9196 | 5.7529 | 5.7564
UG-13A | UG-13A-S05 | P0172 | 0.55607 | 1.4 | -5.487 | -5.4891 | -3.5871 | -3.5891 | 5.57 | -5.4891 | -5.4881 | 4.7881 | 3.9891 | 0.8 | 10.8782 | Shoring | 0.55607 | 3.9881 | 0.8 | 3.4 | 9.0525 | 0 | 0.66728 | 0.856 | 2.9196 | 2.9212 | 5.7565 | 5.758
UG-13A | UG-13A-S05 | P0335-01 | 3.3785 | 1.4 | -5.4891 | -5.5016 | -3.5891 | -3.6016 | 4.53 | -5.5016 | -5.4954 | 4.7954 | 4.0016 | 0.8 | 10.9032 | Shoring | 3.3785 | 3.9954 | 0.8 | 3.4 | 55.0844 | 0 | 4.0542 | 5.2008 | 2.9212 | 2.9307 | 5.7581 | 5.7676
UG-13A | UG-13A-S06 | P0335-02 | 6.6 | 1.4 | -5.5016 | -5.526 | -3.6016 | -3.626 | 3.43 | -5.526 | -5.5138 | 4.8138 | 4.026 | 0.8 | 10.952 | Shoring | 6.6 | 4.0138 | 0.8 | 3.4 | 108.0213 | 0 | 7.92 | 10.1598 | 2.9307 | 2.9492 | 5.7676 | 5.7861
UG-13A | UG-13A-S06 | P0335-03 | 9.5 | 1.4 | -5.526 | -5.5611 | -3.626 | -3.6611 | 3.35 | -5.5611 | -5.5436 | 4.8436 | 4.0611 | 0.8 | 11.0223 | Shoring | 9.5 | 4.0436 | 0.8 | 3.4 | 156.4467 | 0 | 11.4 | 14.6239 | 2.9492 | 2.9759 | 5.7861 | 5.8128
UG-13A | UG-13A-S07 | P0335-04 | 0.5 | 1.4 | -5.5611 | -5.563 | -3.6611 | -3.663 | 4.17 | -5.563 | -5.5621 | 4.8621 | 4.063 | 0.8 | 11.0259 | Shoring | 0.5 | 4.0621 | 0.8 | 3.4 | 8.2655 | 0 | 0.6 | 0.76968 | 2.9759 | 2.9773 | 5.8128 | 5.8142
UG-13A | UG-13A-S07 | P0335-05 | 8.0212 | 1.4 | -5.563 | -5.5926 | -3.663 | -3.6926 | 8.58 | -5.5926 | -5.5778 | 4.8778 | 4.0926 | 0.8 | 11.0853 | Shoring | 8.0212 | 4.0778 | 0.8 | 3.4 | 133.0268 | 0 | 9.6253 | 12.3474 | 2.9773 | 2.9998 | 5.8142 | 5.8367
UG-13A | UG-13A-S07 | P0723 | 1.0133 | 1.4 | -5.5926 | -5.5964 | -3.6926 | -3.6964 | 7.69 | -5.5964 | -5.5945 | 4.8945 | 4.0964 | 0.8 | 11.0927 | Shoring | 1.0133 | 4.0945 | 0.8 | 3.4 | 16.8618 | 0 | 1.2159 | 1.5598 | 2.9998 | 3.0027 | 5.8367 | 5.8395
UG-13A | UG-13A-S07 | P0724 | 0.97801 | 1.4 | -5.5964 | -5.6 | -3.6964 | -3.7 | 7.43 | -5.6 | -5.5982 | 4.8982 | 4.1 | 0.8 | 11.1 | Shoring | 0.97801 | 4.0982 | 0.8 | 3.4 | 16.2875 | 0 | 1.1736 | 1.5055 | 3.0027 | 3.0054 | 5.8395 | 5.8423
UG-13A | UG-13A-S07 | P0725 | 0.023596 | 1.4 | -5.6 | -5.6 | -3.7 | -3.7 | 7.43 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 11.1 | Shoring | 0.023596 | 4.1 | 0.8 | 3.4 | 0.3931 | 0 | 0.028315 | 0.036322 | 3.0054 | 3.0054 | 5.8423 | 5.8423
UG-13A | UG-13A-S08 | P0312-01 | 9.964 | 1.4 | -5.6 | -5.6 | -3.7 | -3.7 | 6.28 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 11.1 | Shoring | 9.964 | 4.1 | 0.8 | 3.4 | 166.0001 | 0 | 11.9568 | 15.3384 | 3.0054 | 3.0054 | 5.8422 | 5.8422
UG-13A | UG-13A-S08 | P0312-02 | 1.6065 | 1.4 | -5.6 | -5.6 | -3.7 | -3.7 | 6.29 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 11.1 | Shoring | 1.6065 | 4.1 | 0.8 | 3.4 | 26.7644 | 0 | 1.9278 | 2.473 | 3.0054 | 3.0054 | 5.8422 | 5.8422
UG-13A | UG-13A-S09 | P0521 | 0.6364 | 0.98078 | -5.3904 | -5.3904 | -3.9096 | -3.9096 | 7.01 | -5.3904 | -5.3904 | 4.6904 | 3.8904 | 0.8 | 10.4712 | Shoring | 0.6364 | 3.8904 | 0.8 | 2.9808 | 8.8975 | 0 | 0.63028 | 0.4808 | 4.5171 | 4.5171 | 8.5665 | 8.5665
UG-13A | UG-13A-S10 | P0323-01 | 9.3636 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 7.02 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 9.3636 | 3.9 | 0.8 | 3 | 132.027 | 0 | 9.3636 | 7.3542 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13A | UG-13A-S10 | P0323-02 | 0.69875 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 8.46 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 0.69875 | 3.9 | 0.8 | 3 | 9.8523 | 0 | 0.69875 | 0.5488 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13A | UG-13A-S10 | P0520 | 0.30019 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 8.66 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 0.30019 | 3.9 | 0.8 | 3 | 4.2326 | 0 | 0.30019 | 0.23577 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13A | UG-13A-S10 | P0336 | 4.2126 | 1.4001 | -5.6001 | -5.6001 | -3.6999 | -3.6999 | 7.4 | -5.6001 | -5.6001 | 4.9001 | 4.1001 | 0.8 | 11.1002 | Shoring | 4.2126 | 4.1001 | 0.8 | 3.4001 | 70.1858 | 0 | 5.0554 | 6.486 | 3.0051 | 3.0051 | 5.8417 | 5.8417
UG-13A | UG-13A-S10 | P0518 | 1.2505 | 1.4001 | -5.6001 | -5.4825 | -3.6999 | -3.5824 | 6.25 | -5.6001 | -5.5413 | 4.8413 | 4.1001 | 0.8 | 11.1002 | Shoring | 1.2505 | 4.0413 | 0.8 | 3.4001 | 20.5847 | 0 | 1.5007 | 1.9254 | 3.0051 | 2.9158 | 5.8417 | 5.7524
UG-13A | UG-13A-S11 | P0339-01 | 6 | 1.4 | -5.6 | -5.6 | -3.7 | -3.7 | 6.28 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 11.1 | Shoring | 6 | 4.1 | 0.8 | 3.4 | 99.9597 | 0 | 7.2 | 9.2362 | 3.0054 | 3.0054 | 5.8423 | 5.8423
UG-13A | UG-13A-S12 | P0339-02 | 4 | 1.4 | -5.6 | -5.6 | -3.7 | -3.7 | 6.49 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 11.1 | Shoring | 4 | 4.1 | 0.8 | 3.4 | 66.6398 | 0 | 4.8 | 6.1574 | 3.0054 | 3.0054 | 5.8423 | 5.8423
UG-13A | UG-13A-S12 | P0339-03 | 1.2637 | 1.4 | -5.6 | -5.6 | -3.7 | -3.7 | 7.13 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 11.1 | Shoring | 1.2637 | 4.1 | 0.8 | 3.4 | 21.0528 | 0 | 1.5164 | 1.9453 | 3.0054 | 3.0054 | 5.8423 | 5.8423
UG-13A | UG-13A-S13 | P0356-01 | 10 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 31.05 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 10 | 2.6 | 0.8 | 3 | 101.9999 | 0 | 10 | 7.854 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-13A | UG-13A-S13 | P0356-02 | 10 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 21.06 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 10 | 2.6 | 0.8 | 3 | 101.9999 | 0 | 10 | 7.854 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-13A | UG-13A-S13 | P0356-03 | 9.617 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 11.45 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 9.617 | 2.6 | 0.8 | 3 | 98.0938 | 0 | 9.617 | 7.5532 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-13A | UG-13A-S13 | P0722 | 0.3703 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 11.08 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.3703 | 2.6 | 0.8 | 3 | 3.777 | 0 | 0.3703 | 0.29083 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-13A | UG-13A-S13 | P0721 | 0.3792 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 10.8 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.3792 | 2.6 | 0.8 | 3 | 3.8678 | 0 | 0.3792 | 0.29782 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13A | UG-13A-S14 | P0325 | 1.0121 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 1.2 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 1.0121 | 2.6 | 0.8 | 3 | 10.3236 | 0 | 1.0121 | 0.7949 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13A | UG-13A-S14 | P0173 | 1.9053 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 1.92 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 1.9053 | 2.6 | 0.8 | 3 | 19.4341 | 0 | 1.9053 | 1.4964 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13A | UG-13A-S14 | P0767 | 0.36819 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 3.31 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.36819 | 2.6 | 0.8 | 3 | 3.7555 | 0 | 0.36819 | 0.28917 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13A | UG-13A-S14 | P0768 | 0.37607 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 3.59 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.37607 | 2.6 | 0.8 | 3 | 3.8359 | 0 | 0.37607 | 0.29536 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13A | UG-13A-S14 | P0337-01 | 5.9718 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 3.62 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 5.9718 | 2.6 | 0.8 | 3 | 60.9119 | 0 | 5.9718 | 4.6902 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13A | UG-13A-S14 | P0337-02 | 5.1139 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 4.65 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 5.1139 | 2.6 | 0.8 | 3 | 52.1613 | 0 | 5.1139 | 4.0164 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13A | UG-13A-S14 | P0730 | 0.37101 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 6.31 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.37101 | 2.6 | 0.8 | 3 | 3.7843 | 0 | 0.37101 | 0.29139 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13A | UG-13A-S14 | P0729 | 0.36976 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 6.46 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.36976 | 2.6 | 0.8 | 3 | 3.7715 | 0 | 0.36976 | 0.29041 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13A | UG-13A-S14 | P0324-01 | 4.1454 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 6.8 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 4.1454 | 2.6 | 0.8 | 3 | 42.2827 | 0 | 4.1454 | 3.2557 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13A | UG-13A-S14 | P0324-02 | 10 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 7.08 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 10 | 2.6 | 0.8 | 3 | 101.9998 | 0 | 10 | 7.8539 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13A | UG-13A-S14 | P0324-03 | 1.2278 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 7.02 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 1.2278 | 2.6 | 0.8 | 3 | 12.5239 | 0 | 1.2278 | 0.96433 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13A | UG-13A-S14 | P0522 | 0.6364 | 0.98079 | -4.0904 | -4.0904 | -2.6096 | -2.6096 | 7.01 | -4.0904 | -4.0904 | 3.3904 | 2.5904 | 0.8 | 7.8712 | Shoring | 0.6364 | 2.5904 | 0.8 | 2.9808 | 6.4315 | 0 | 0.63029 | 0.4808 | 3.1082 | 3.1082 | 7.1576 | 7.1576
UG-13A | UG-13A-S15 | P0352-01 | 10 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 99 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 10 | 3.9 | 0.8 | 3 | 140.9999 | 0 | 10 | 7.854 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13A | UG-13A-S15 | P0352-02 | 10 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 24.6 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 10 | 3.9 | 0.8 | 3 | 140.9999 | 0 | 10 | 7.854 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13A | UG-13A-S15 | P0352-03 | 8.6908 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 18.35 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 8.6908 | 3.9 | 0.8 | 3 | 122.5402 | 0 | 8.6908 | 6.8257 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13A | UG-13A-S15 | P0770 | 0.26284 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 18.17 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 0.26284 | 3.9 | 0.8 | 3 | 3.7061 | 0 | 0.26284 | 0.20643 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13A | UG-13A-S15 | P0769 | 0.24219 | 0.99999 | -5.4 | -5.4 | -3.9 | -3.9 | 17.94 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 0.24219 | 3.9 | 0.8 | 3 | 3.4148 | 0 | 0.24219 | 0.19021 | 4.4202 | 4.4202 | 8.3917 | 8.3917
UG-13A | UG-13A-S16 | P0338-01 | 0.80417 | 0.99999 | -5.4 | -5.4 | -3.9 | -3.9 | 0.16 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 0.80417 | 3.9 | 0.8 | 3 | 11.3388 | 0 | 0.80417 | 0.63159 | 4.4202 | 4.4202 | 8.3917 | 8.3917
UG-13A | UG-13A-S16 | P0338-02 | 6.1315 | 0.99999 | -5.4 | -5.4 | -3.9 | -3.9 | 0.87 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 6.1315 | 3.9 | 0.8 | 3 | 86.4547 | 0 | 6.1315 | 4.8157 | 4.4202 | 4.4202 | 8.3917 | 8.3917
UG-13A | UG-13A-S16 | P0406 | 0.27347 | 0.99999 | -5.4 | -5.4 | -3.9 | -3.9 | 6.37 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 0.27347 | 3.9 | 0.8 | 3 | 3.8559 | 0 | 0.27347 | 0.21478 | 4.4202 | 4.4202 | 8.3917 | 8.3917
UG-13A | UG-13A-S16 | P0341 | 2.0652 | 1.0221 | -5.411 | -5.411 | -3.889 | -3.889 | 6.62 | -5.411 | -5.411 | 4.711 | 3.911 | 0.8 | 10.5331 | Shoring | 2.0652 | 3.911 | 0.8 | 3.0221 | 29.4021 | 0 | 2.088 | 1.6944 | 4.3132 | 4.3132 | 8.1991 | 8.1991
UG-13B | UG-13B-S01 | P0354-01 | 10 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 9.86 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 10 | 2.6 | 0.8 | 3 | 101.9997 | 0 | 10 | 7.8539 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13B | UG-13B-S01 | P0354-02 | 10 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 4.05 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 10 | 2.6 | 0.8 | 3 | 101.9997 | 0 | 10 | 7.8539 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13B | UG-13B-S01 | P0354-03 | 9.9624 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 4.05 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 9.9624 | 2.6 | 0.8 | 3 | 101.616 | 0 | 9.9624 | 7.8243 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13B | UG-13B-S01 | P0353 | 0.03666 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 4.33 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.03666 | 2.6 | 0.8 | 3 | 0.37393 | 0 | 0.03666 | 0.028792 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13B | UG-13B-S01 | P0749 | 0.37638 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 4.01 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.37638 | 2.6 | 0.8 | 3 | 3.839 | 0 | 0.37637 | 0.2956 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13B | UG-13B-S01 | P0748 | 0.36776 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 3.96 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.36776 | 2.6 | 0.8 | 3 | 3.7512 | 0 | 0.36776 | 0.28884 | 3.0382 | 3.0382 | 7.0098 | 7.0098
UG-13B | UG-13B-S02 | P0157 | 2.8628 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 1.65 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 2.8628 | 2.6 | 0.8 | 3 | 29.2002 | 0 | 2.8628 | 2.2484 | 3.0382 | 3.0382 | 7.0098 | 7.0098
UG-13B | UG-13B-S02 | P0750 | 0.3519 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 3.77 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.3519 | 2.6 | 0.8 | 3 | 3.5894 | 0 | 0.3519 | 0.27639 | 3.0382 | 3.0382 | 7.0098 | 7.0098
UG-13B | UG-13B-S02 | P0751 | 0.38784 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 4.04 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.38784 | 2.6 | 0.8 | 3 | 3.956 | 0 | 0.38784 | 0.30461 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-13B | UG-13B-S02 | P0313-01 | 5.6543 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 4.09 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 5.6543 | 2.6 | 0.8 | 3 | 57.674 | 0 | 5.6543 | 4.4409 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-13B | UG-13B-S02 | P0313-02 | 9.0949 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 5.31 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 9.0949 | 2.6 | 0.8 | 3 | 92.7684 | 0 | 9.0949 | 7.1431 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-13B | UG-13B-S02 | P0753 | 0.32944 | 1 | -4.1 | -4.1 | -2.6 | -2.6 | 8.69 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.32944 | 2.6 | 0.8 | 3 | 3.3602 | 0 | 0.32943 | 0.25874 | 3.0383 | 3.0383 | 7.0098 | 7.0098
UG-13B | UG-13B-S02 | P0752 | 0.26102 | 1.0018 | -4.1009 | -4.1009 | -2.5991 | -2.5991 | 8.67 | -4.1009 | -4.1009 | 3.4009 | 2.6009 | 0.8 | 7.9027 | Shoring | 0.26102 | 2.6009 | 0.8 | 3.0018 | 2.6647 | 0 | 0.26125 | 0.20573 | 3.0319 | 3.0319 | 6.9965 | 6.9965
UG-13B | UG-13B-S02 | P0281-01 | 0.31459 | 1.0018 | -4.1009 | -4.1009 | -2.5991 | -2.5991 | 8.56 | -4.1009 | -4.1009 | 3.4009 | 2.6009 | 0.8 | 7.9027 | Shoring | 0.31459 | 2.6009 | 0.8 | 3.0018 | 3.2116 | 0 | 0.31487 | 0.24796 | 3.0319 | 3.0319 | 6.9965 | 6.9965
UG-13B | UG-13B-S02 | P0281-02 | 7 | 1.0018 | -4.1009 | -4.1009 | -2.5991 | -2.5991 | 5.4 | -4.1009 | -4.1009 | 3.4009 | 2.6009 | 0.8 | 7.9027 | Shoring | 7 | 2.6009 | 0.8 | 3.0018 | 71.4608 | 0 | 7.0062 | 5.5173 | 3.0319 | 3.0319 | 6.9965 | 6.9965
UG-13B | UG-13B-S03 | P0281-03 | 3 | 1.0018 | -4.1009 | -4.1009 | -2.5991 | -2.5991 | 3.29 | -4.1009 | -4.1009 | 3.4009 | 2.6009 | 0.8 | 7.9027 | Shoring | 3 | 2.6009 | 0.8 | 3.0018 | 30.626 | 0 | 3.0027 | 2.3645 | 3.0319 | 3.0319 | 6.9965 | 6.9965
UG-13B | UG-13B-S03 | P0281-04 | 10 | 1.0018 | -4.1009 | -4.1009 | -2.5991 | -2.5991 | 2.28 | -4.1009 | -4.1009 | 3.4009 | 2.6009 | 0.8 | 7.9027 | Shoring | 10 | 2.6009 | 0.8 | 3.0018 | 102.0868 | 0 | 10.0089 | 7.8818 | 3.0319 | 3.0319 | 6.9965 | 6.9965
UG-13B | UG-13B-S03 | P0281-05 | 2 | 1.0018 | -4.1009 | -4.1009 | -2.5991 | -2.5991 | 6.11 | -4.1009 | -4.1009 | 3.4009 | 2.6009 | 0.8 | 7.9027 | Shoring | 2 | 2.6009 | 0.8 | 3.0018 | 20.4174 | 0 | 2.0018 | 1.5764 | 3.0319 | 3.0319 | 6.9965 | 6.9965
UG-13B | UG-13B-S04 | P0281-06 | 0.23454 | 1.0018 | -4.1009 | -4.1009 | -2.5991 | -2.5991 | 7.21 | -4.1009 | -4.1009 | 3.4009 | 2.6009 | 0.8 | 7.9027 | Shoring | 0.23454 | 2.6009 | 0.8 | 3.0018 | 2.3943 | 0 | 0.23475 | 0.18486 | 3.0319 | 3.0319 | 6.9965 | 6.9965
UG-13B | UG-13B-S04 | P0732 | 0.37182 | 1.0018 | -4.1009 | -4.1009 | -2.5991 | -2.5991 | 7.27 | -4.1009 | -4.1009 | 3.4009 | 2.6009 | 0.8 | 7.9027 | Shoring | 0.37182 | 2.6009 | 0.8 | 3.0018 | 3.7958 | 0 | 0.37215 | 0.29306 | 3.0319 | 3.0319 | 6.9965 | 6.9965
UG-13B | UG-13B-S04 | P0731 | 0.37433 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 7.36 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.37433 | 2.6 | 0.8 | 3 | 3.8182 | 0 | 0.37433 | 0.29399 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13B | UG-13B-S04 | P0135 | 2.2486 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 7.68 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 2.2486 | 2.6 | 0.8 | 3 | 22.9351 | 0 | 2.2485 | 1.766 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13B | UG-13B-S04 | P0733 | 0.37279 | 0.99999 | -4.1 | -4.1 | -2.6 | -2.6 | 7.82 | -4.1 | -4.1 | 3.4 | 2.6 | 0.8 | 7.9 | Shoring | 0.37279 | 2.6 | 0.8 | 3 | 3.8025 | 0 | 0.37279 | 0.29279 | 3.0383 | 3.0383 | 7.0099 | 7.0099
UG-13B | UG-13B-S04 | P0734 | 0.33737 | 0.99623 | -4.0981 | -4.0981 | -2.6019 | -2.6019 | 7.58 | -4.0981 | -4.0981 | 3.3981 | 2.5981 | 0.8 | 7.8944 | Shoring | 0.33737 | 2.5981 | 0.8 | 2.9962 | 3.4349 | 0 | 0.33673 | 0.26298 | 3.0517 | 3.0517 | 7.0383 | 7.0383
UG-13B | UG-13B-S04 | P0735 | 0.035415 | 0.99623 | -4.0981 | -4.0981 | -2.6019 | -2.6019 | 7.56 | -4.0981 | -4.0981 | 3.3981 | 2.5981 | 0.8 | 7.8944 | Shoring | 0.035415 | 2.5981 | 0.8 | 2.9962 | 0.36058 | 0 | 0.035348 | 0.027606 | 3.0517 | 3.0517 | 7.0383 | 7.0383
UG-13B | UG-13B-S04 | P0287-01 | 4.0252 | 0.99623 | -4.0981 | -4.0999 | -2.6019 | -2.6037 | 4.72 | -4.0999 | -4.099 | 3.399 | 2.5999 | 0.8 | 7.8979 | Shoring | 4.0252 | 2.599 | 0.8 | 2.9962 | 40.9934 | 0 | 4.0176 | 3.1376 | 3.0517 | 3.0536 | 7.0383 | 7.0402
UG-13B | UG-13B-S04 | P0287-02 | 10 | 0.99623 | -4.0999 | -4.1043 | -2.6037 | -2.6081 | 1.75 | -4.1043 | -4.1021 | 3.4021 | 2.6043 | 0.8 | 7.9067 | Shoring | 10 | 2.6021 | 0.8 | 2.9962 | 101.9348 | 0 | 9.9812 | 7.7949 | 3.0536 | 3.0583 | 7.0402 | 7.0449
UG-13B | UG-13B-S04 | P0287-03 | 6 | 0.99623 | -4.1043 | -4.107 | -2.6081 | -2.6107 | 1.77 | -4.107 | -4.1056 | 3.4056 | 2.607 | 0.8 | 7.912 | Shoring | 6 | 2.6056 | 0.8 | 2.9962 | 61.2244 | 0 | 5.9887 | 4.677 | 3.0583 | 3.0612 | 7.0449 | 7.0478
UG-13B | UG-13B-S05 | P0287-04 | 1.8943 | 0.99623 | -4.107 | -4.1078 | -2.6107 | -2.6116 | 4.96 | -4.1078 | -4.1074 | 3.4074 | 2.6078 | 0.8 | 7.9137 | Shoring | 1.8943 | 2.6074 | 0.8 | 2.9962 | 19.3398 | 0 | 1.8908 | 1.4766 | 3.0612 | 3.0621 | 7.0478 | 7.0487
UG-13B | UG-13B-S05 | P0475 | 0.37135 | 0.99623 | -4.1078 | -4.1079 | -2.6116 | -2.6117 | 6.31 | -4.1079 | -4.1079 | 3.4079 | 2.6079 | 0.8 | 7.914 | Shoring | 0.37135 | 2.6079 | 0.8 | 2.9962 | 3.7917 | 0 | 0.37065 | 0.28946 | 3.0621 | 3.0622 | 7.0487 | 7.0488
UG-13B | UG-13B-S05 | P0474 | 0.37494 | 1 | -4.1098 | -4.11 | -2.6098 | -2.61 | 6.57 | -4.11 | -4.1099 | 3.4099 | 2.61 | 0.8 | 7.92 | Shoring | 0.37494 | 2.6099 | 0.8 | 3 | 3.8355 | 0 | 0.37494 | 0.29448 | 3.0487 | 3.0489 | 7.0203 | 7.0205
UG-13B | UG-13B-S05 | P0233-01 | 1.3594 | 1 | -4.11 | -4.143 | -2.61 | -2.643 | 6.95 | -4.143 | -4.1265 | 3.4265 | 2.643 | 0.8 | 7.9859 | Shoring | 1.3594 | 2.6265 | 0.8 | 3 | 13.9737 | 0 | 1.3594 | 1.0677 | 3.0489 | 3.0839 | 7.0205 | 7.0555
UG-13B | UG-13B-S05 | P0233-02 | 10 | 1 | -4.143 | -4.3855 | -2.643 | -2.8855 | 6.85 | -4.3855 | -4.2642 | 3.5642 | 2.8855 | 0.8 | 8.471 | Shoring | 10 | 2.7642 | 0.8 | 3 | 106.9271 | 0 | 10 | 7.854 | 3.0839 | 3.3417 | 7.0555 | 7.3133
UG-13B | UG-13B-S05 | P0233-03 | 10 | 1 | -4.3855 | -4.628 | -2.8855 | -3.128 | 5.96 | -4.628 | -4.5068 | 3.8068 | 3.128 | 0.8 | 8.9561 | Shoring | 10 | 3.0068 | 0.8 | 3 | 114.2031 | 0 | 10 | 7.854 | 3.3417 | 3.5995 | 7.3133 | 7.5711
UG-13B | UG-13B-S05 | P0233-04 | 10 | 1 | -4.628 | -4.8706 | -3.128 | -3.3706 | 6.02 | -4.8706 | -4.7493 | 4.0493 | 3.3706 | 0.8 | 9.4411 | Shoring | 10 | 3.2493 | 0.8 | 3 | 121.4792 | 0 | 10 | 7.854 | 3.5995 | 3.8574 | 7.5711 | 7.8289
UG-13B | UG-13B-S05 | P0233-05 | 10 | 1 | -4.8706 | -5.1131 | -3.3706 | -3.6131 | 7.93 | -5.1131 | -4.9918 | 4.2918 | 3.6131 | 0.8 | 9.9262 | Shoring | 10 | 3.4918 | 0.8 | 3 | 128.7552 | 0 | 10 | 7.854 | 3.8574 | 4.1152 | 7.8289 | 8.0867
UG-13B | UG-13B-S05 | P0233-06 | 10 | 1 | -5.1131 | -5.3556 | -3.6131 | -3.8556 | 9.28 | -5.3556 | -5.2344 | 4.5344 | 3.8556 | 0.8 | 10.4113 | Shoring | 10 | 3.7344 | 0.8 | 3 | 136.0312 | 0 | 10 | 7.854 | 4.1152 | 4.373 | 8.0867 | 8.3446
UG-13B | UG-13B-S05 | P0233-07 | 1.4166 | 1 | -5.3556 | -5.39 | -3.8556 | -3.89 | 7.96 | -5.39 | -5.3728 | 4.6728 | 3.89 | 0.8 | 10.48 | Shoring | 1.4166 | 3.8728 | 0.8 | 3 | 19.8591 | 0 | 1.4166 | 1.1126 | 4.373 | 4.4095 | 8.3446 | 8.3811
UG-13B | UG-13B-S05 | P0477 | 0.37264 | 1 | -5.39 | -5.3904 | -3.89 | -3.8904 | 7.61 | -5.3904 | -5.3902 | 4.6902 | 3.8904 | 0.8 | 10.4807 | Shoring | 0.37264 | 3.8902 | 0.8 | 3 | 5.2432 | 0 | 0.37264 | 0.29267 | 4.4095 | 4.4099 | 8.3811 | 8.3815
UG-13B | UG-13B-S05 | P0476 | 0.37295 | 0.99999 | -5.3904 | -5.3907 | -3.8904 | -3.8907 | 7.27 | -5.3907 | -5.3905 | 4.6905 | 3.8907 | 0.8 | 10.4814 | Shoring | 0.37295 | 3.8905 | 0.8 | 3 | 5.248 | 0 | 0.37295 | 0.29291 | 4.4099 | 4.4103 | 8.3815 | 8.3819
UG-13B | UG-13B-S05 | P0038-01 | 7.8378 | 0.99999 | -5.3907 | -5.3983 | -3.8907 | -3.8983 | 2.8 | -5.3983 | -5.3945 | 4.6945 | 3.8983 | 0.8 | 10.4966 | Shoring | 7.8378 | 3.8945 | 0.8 | 3 | 110.383 | 0 | 7.8378 | 6.1557 | 4.4103 | 4.4183 | 8.3819 | 8.3899
UG-13B | UG-13B-S05 | P0038-02 | 0.1 | 0.99999 | -5.3983 | -5.3984 | -3.8983 | -3.8984 | 2.86 | -5.3984 | -5.3983 | 4.6983 | 3.8984 | 0.8 | 10.4967 | Shoring | 0.1 | 3.8983 | 0.8 | 3 | 1.4095 | 0 | 0.1 | 0.078539 | 4.4183 | 4.4184 | 8.3899 | 8.39
UG-13B | UG-13B-S06 | P0038-03 | 0.93727 | 0.99999 | -5.3984 | -5.3993 | -3.8984 | -3.8993 | 2.87 | -5.3993 | -5.3988 | 4.6988 | 3.8993 | 0.8 | 10.4986 | Shoring | 0.93727 | 3.8988 | 0.8 | 3 | 13.2121 | 0 | 0.93726 | 0.73612 | 4.4184 | 4.4194 | 8.39 | 8.391
UG-13B | UG-13B-S06 | P0478 | 0.37276 | 0.99999 | -5.3993 | -5.3996 | -3.8993 | -3.8996 | 2.96 | -5.3996 | -5.3995 | 4.6995 | 3.8996 | 0.8 | 10.4993 | Shoring | 0.37276 | 3.8995 | 0.8 | 3 | 5.2553 | 0 | 0.37276 | 0.29276 | 4.4194 | 4.4198 | 8.391 | 8.3914
UG-13B | UG-13B-S06 | P0479 | 0.37282 | 1 | -5.3996 | -5.4 | -3.8996 | -3.9 | 3 | -5.4 | -5.3998 | 4.6998 | 3.9 | 0.8 | 10.5 | Shoring | 0.37282 | 3.8998 | 0.8 | 3 | 5.2566 | 0 | 0.37282 | 0.29281 | 4.4197 | 4.4201 | 8.3913 | 8.3917
UG-13B | UG-13B-S06 | P0211-01 | 8.2172 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 3.3 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 8.2172 | 3.9 | 0.8 | 3 | 115.8618 | 0 | 8.2172 | 6.4537 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13B | UG-13B-S06 | P0211-02 | 10 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 10.11 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 10 | 3.9 | 0.8 | 3 | 141 | 0 | 10 | 7.854 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13B | UG-13B-S06 | P0211-03 | 10 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 11.25 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 10 | 3.9 | 0.8 | 3 | 141 | 0 | 10 | 7.854 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13B | UG-13B-S06 | P0211-04 | 7.1 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 11.25 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 7.1 | 3.9 | 0.8 | 3 | 100.11 | 0 | 7.1 | 5.5763 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13B | UG-13B-S07 | P0211-05 | 2.9 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 11.94 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 2.9 | 3.9 | 0.8 | 3 | 40.89 | 0 | 2.9 | 2.2777 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13B | UG-13B-S07 | P0211-06 | 10 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 12.56 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 10 | 3.9 | 0.8 | 3 | 141 | 0 | 10 | 7.854 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13B | UG-13B-S07 | P0211-07 | 8.5405 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 16.11 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 8.5405 | 3.9 | 0.8 | 3 | 120.4216 | 0 | 8.5405 | 6.7077 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13B | UG-13B-S07 | P0036 | 0.3 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 20.55 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 0.3 | 3.9 | 0.8 | 3 | 4.23 | 0 | 0.3 | 0.23562 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13B | UG-13B-S07 | P0039-01 | 1.1595 | 1.4 | -5.6 | -5.6 | -3.7 | -3.7 | 20.73 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 11.1 | Shoring | 1.1595 | 4.1 | 0.8 | 3.4 | 19.3165 | 0 | 1.3913 | 1.7848 | 3.0054 | 3.0054 | 5.8422 | 5.8422
UG-13B | UG-13B-S07 | P0039-02 | 0.080312 | 1.4 | -5.6 | -5.6 | -3.7 | -3.7 | 21.42 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 11.1 | Shoring | 0.080312 | 4.1 | 0.8 | 3.4 | 1.338 | 0 | 0.096374 | 0.12363 | 3.0054 | 3.0054 | 5.8422 | 5.8422
UG-13B | UG-13B-S07 | P0510 | 1.012 | 1.4 | -5.6 | -5.6 | -3.7 | -3.7 | 21.46 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 11.1 | Shoring | 1.012 | 4.1 | 0.8 | 3.4 | 16.8597 | 0 | 1.2144 | 1.5578 | 3.0054 | 3.0054 | 5.8422 | 5.8422
UG-13B | UG-13B-S07 | P0512 | 1.6728 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 20.77 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 1.6728 | 3.9 | 0.8 | 3 | 23.5862 | 0 | 1.6728 | 1.3138 | 4.4202 | 4.4202 | 8.3917 | 8.3917
UG-13B | UG-13B-S08 | P0040 | 6.3864 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 16 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 6.3864 | 3.9 | 0.8 | 3 | 90.0483 | 0 | 6.3864 | 5.0158 | 4.4202 | 4.4202 | 8.3917 | 8.3917
UG-13B | UG-13B-S08 | P0513 | 0.36965 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 15.74 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 0.36965 | 3.9 | 0.8 | 3 | 5.2121 | 0 | 0.36965 | 0.29032 | 4.4202 | 4.4202 | 8.3917 | 8.3917
UG-13B | UG-13B-S08 | P0514 | 0.37501 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 15.37 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 0.37501 | 3.9 | 0.8 | 3 | 5.2877 | 0 | 0.37501 | 0.29454 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13B | UG-13B-S08 | P0349-01 | 0.10383 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 15.26 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 0.10383 | 3.9 | 0.8 | 3 | 1.464 | 0 | 0.10383 | 0.081546 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13B | UG-13B-S08 | P0349-02 | 8.1 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 7.16 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 8.1 | 3.9 | 0.8 | 3 | 114.21 | 0 | 8.1 | 6.3617 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13B | UG-13B-S09 | P0349-03 | 1.9 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 5.26 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 1.9 | 3.9 | 0.8 | 3 | 26.79 | 0 | 1.9 | 1.4923 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13B | UG-13B-S09 | P0349-04 | 10 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 0 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 10 | 3.9 | 0.8 | 3 | 141 | 0 | 10 | 7.854 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13B | UG-13B-S09 | P0349-05 | 10 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 26.56 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 10 | 3.9 | 0.8 | 3 | 141 | 0 | 10 | 7.854 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13B | UG-13B-S09 | P0349-06 | 8.138 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 31.76 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 8.138 | 3.9 | 0.8 | 3 | 114.7458 | 0 | 8.138 | 6.3916 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13B | UG-13B-S10 | P0349-07 | 1.862 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 99 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 1.862 | 3.9 | 0.8 | 3 | 26.2542 | 0 | 1.862 | 1.4624 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13B | UG-13B-S10 | P0349-08 | 4.1381 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 99 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 4.1381 | 3.9 | 0.8 | 3 | 58.3465 | 0 | 4.1381 | 3.25 | 4.4201 | 4.4201 | 8.3917 | 8.3917
UG-13B | UG-13B-S11 | P0511 | 1.012 | 1.4 | -5.6 | -5.6 | -3.7 | -3.7 | 22.08 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 11.1 | Shoring | 1.012 | 4.1 | 0.8 | 3.4 | 16.86 | 0 | 1.2144 | 1.5579 | 3.0054 | 3.0054 | 5.8422 | 5.8422
UG-13B | UG-13B-S11 | P0174 | 2.559 | 1.4 | -5.6 | -5.6 | -3.7 | -3.7 | 22.71 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 11.1 | Shoring | 2.559 | 4.1 | 0.8 | 3.4 | 42.6327 | 0 | 3.0708 | 3.9392 | 3.0054 | 3.0054 | 5.8423 | 5.8423
UG-13B | UG-13B-S11 | P0340-01 | 6.429 | 1.4 | -5.6 | -5.6 | -3.7 | -3.7 | 20.01 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 11.1 | Shoring | 6.429 | 4.1 | 0.8 | 3.4 | 107.1071 | 0 | 7.7148 | 9.8967 | 3.0054 | 3.0054 | 5.8422 | 5.8422
UG-13B | UG-13B-S11 | P0340-02 | 4.5305 | 1.4 | -5.6 | -5.6 | -3.7 | -3.7 | 17.52 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 11.1 | Shoring | 4.5305 | 4.1 | 0.8 | 3.4 | 75.4779 | 0 | 5.4366 | 6.9741 | 3.0054 | 3.0054 | 5.8422 | 5.8422
UG-13B | UG-13B-S08 | P0515 | 0.63639 | 0.98078 | -5.3904 | -5.3904 | -3.9096 | -3.9096 | 20.77 | -5.3904 | -5.3904 | 4.6904 | 3.8904 | 0.8 | 10.4712 | Shoring | 0.63639 | 3.8904 | 0.8 | 2.9808 | 8.8974 | 0 | 0.63028 | 0.4808 | 4.5171 | 4.5171 | 8.5665 | 8.5665
UG-13B | UG-13B-S08 | P0202 | 0.17019 | 1 | -5.4 | -5.4 | -3.9 | -3.9 | 21.27 | -5.4 | -5.4 | 4.7 | 3.9 | 0.8 | 10.5 | Shoring | 0.17019 | 3.9 | 0.8 | 3 | 2.3997 | 0 | 0.17019 | 0.13367 | 4.4202 | 4.4202 | 8.3917 | 8.3917
UG-13B | UG-13B-S12 | P0343 | 4.8319 | 2.0696 | -5.9348 | -5.9348 | -3.3652 | -3.3652 | 16.91 | -5.9348 | -5.9348 | 5.2348 | 4.4348 | 0.8 | 12.1044 | Shoring | 4.8319 | 4.4348 | 0.8 | 4.0696 | 102.9371 | 0 | 7.416 | 16.2549 | 1.8611 | 1.8611 | 3.7801 | 3.7801
UG-13B | UG-13B-S12 | P0342 | 0.09087 | 2.0696 | -5.9348 | -5.9348 | -3.3652 | -3.3652 | 21.74 | -5.9348 | -5.9348 | 5.2348 | 4.4348 | 0.8 | 12.1044 | Shoring | 0.09087 | 4.4348 | 0.8 | 4.0696 | 1.9359 | 0 | 0.13947 | 0.30569 | 1.8611 | 1.8611 | 3.7801 | 3.7801
UG-14E | UG-14E-S01 | P0370 | 0.05001 | 1.6 | 0.8 | 0.7762 | 2.9 | 2.8762 | 21.38 | 0.7762 | 0.7881 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14E | UG-14E-S01 | P0371 | 0.20399 | 1.6 | 0.7762 | 0.67912 | 2.8762 | 2.7791 | 21.39 | 0.67912 | 0.72766 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14E | UG-14E-S01 | P0190 | 1.1551 | 1.6 | 0.67912 | 0.12938 | 2.7791 | 2.2294 | 21.42 | 0.12938 | 0.40425 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14E | UG-14E-S01 | P0580 | 0.8431 | 1.6 | 0.12938 | -0.27186 | 2.2294 | 1.8281 | 21.63 | -0.27186 | -0.071241 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14E | UG-14E-S01 | P0581 | 0.23993 | 1.6 | -0.27186 | -0.38605 | 1.8281 | 1.714 | 21.79 | -0.38605 | -0.32896 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14E | UG-14E-S01 | P0579 | 0.69043 | 1.6 | -0.38605 | -0.71464 | 1.714 | 1.3854 | 21.85 | -0.71464 | -0.55035 | 0 | 0 | 0.014642 | 1.822 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14E | UG-14E-S01 | P0221 | 5.1416 | 1.6 | -0.71464 | -3.1616 | 1.3854 | -1.0616 | 22.02 | -3.1616 | -1.9381 | 1.2381 | 1.6616 | 0.8 | 6.3232 | Open cut | 0 | 0.43812 | 0.8 | 3.6 | 0 | 37.0356 | 6.6841 | 10.3378 | 99 | 0.52798 | 99 | 3.0102
UG-14E | UG-14E-S01 | P0488 | 0.67818 | 1.6 | -3.1616 | -3.4843 | -1.0616 | -1.3844 | 23.53 | -3.4843 | -3.323 | 2.623 | 1.9843 | 0.8 | 6.9687 | Open cut | 0 | 1.823 | 0.8 | 3.6 | 0 | 15.5186 | 0.88163 | 1.3636 | 0.52799 | 0.99925 | 3.0102 | 3.4815
UG-14E | UG-14E-S01 | P0490 | 0.24346 | 1.6 | -3.4843 | -3.6002 | -1.3844 | -1.5002 | 23.78 | -3.6002 | -3.5423 | 2.8423 | 2.1002 | 0.8 | 7.2004 | Open cut | 0 | 2.0423 | 0.8 | 3.6 | 0 | 6.3468 | 0.31649 | 0.4895 | 0.99925 | 1.1683 | 3.4815 | 3.6505
UG-14E | UG-14E-S01 | P0489-01 | 0.7542 | 1.6 | -3.6002 | -3.9592 | -1.5002 | -1.8592 | 23.87 | -3.9592 | -3.7797 | 3.0797 | 2.4592 | 0.8 | 7.9183 | Open cut | 0 | 2.2797 | 0.8 | 3.6 | 0 | 22.4266 | 0.98046 | 1.5164 | 1.1683 | 1.4067 | 3.6505 | 3.889
UG-14E | UG-14E-S01 | P0489-02 | 0.085833 | 1.6 | -3.9592 | -4 | -1.8592 | -1.9 | 24.14 | -4 | -3.9796 | 3.2796 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.4796 | 0.8 | 3.6 | 0 | 2.8323 | 0.11158 | 0.17258 | 1.4067 | 1.4339 | 3.889 | 3.9161
UG-14E | UG-14E-S01 | P0128-01 | 9.9142 | 1.6 | -4 | -4 | -1.9 | -1.9 | 20.41 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.5 | 0.8 | 3.6 | 0 | 330.5382 | 12.8884 | 19.9336 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-14E | UG-14E-S01 | P0128-02 | 10 | 1.6 | -4 | -4 | -1.9 | -1.9 | 17.32 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.5 | 0.8 | 3.6 | 0 | 333.3999 | 13 | 20.1062 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-14E | UG-14E-S01 | P0128-03 | 7.5876 | 1.6 | -4 | -4 | -1.9 | -1.9 | 17.3 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.5 | 0.8 | 3.6 | 0 | 252.9696 | 9.8638 | 15.2557 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-14F | UG-14F-S01 | P0374 | 0.05001 | 1.6 | 0.8 | 0.77612 | 2.9 | 2.8761 | 21.27 | 0.77612 | 0.78806 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14F | UG-14F-S01 | P0375 | 0.20399 | 1.6 | 0.77612 | 0.6787 | 2.8761 | 2.7787 | 21.27 | 0.6787 | 0.72741 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14F | UG-14F-S01 | P0193 | 1.3707 | 1.6 | 0.6787 | 0.024081 | 2.7787 | 2.1241 | 21.32 | 0.024081 | 0.35139 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14F | UG-14F-S01 | P0571 | 0.83864 | 1.6 | 0.024081 | -0.37642 | 2.1241 | 1.7236 | 21.6 | -0.37642 | -0.17617 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14F | UG-14F-S01 | P0572 | 0.24601 | 1.6 | -0.37642 | -0.49391 | 1.7236 | 1.6061 | 21.8 | -0.49391 | -0.43516 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14F | UG-14F-S01 | P0570 | 0.67582 | 1.6 | -0.49391 | -0.81666 | 1.6061 | 1.2833 | 21.86 | -0.81666 | -0.65529 | 0 | 0 | 0.11666 | 1.975 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14F | UG-14F-S01 | P0218 | 4.9083 | 1.6 | -0.81666 | -3.1607 | 1.2833 | -1.0607 | 22.02 | -3.1607 | -1.9887 | 1.2887 | 1.6607 | 0.8 | 6.3214 | Open cut | 0 | 0.48867 | 0.8 | 3.6 | 0 | 37.5022 | 6.3808 | 9.8687 | 99 | 0.52666 | 99 | 3.0089
UG-14F | UG-14F-S01 | P0494 | 0.67449 | 1.6 | -3.1607 | -3.4828 | -1.0607 | -1.3828 | 23.45 | -3.4828 | -3.3217 | 2.6217 | 1.9828 | 0.8 | 6.9656 | Open cut | 0 | 1.8217 | 0.8 | 3.6 | 0 | 15.4224 | 0.87684 | 1.3561 | 0.52666 | 0.99698 | 3.0089 | 3.4792
UG-14F | UG-14F-S01 | P0496 | 0.24297 | 1.6 | -3.4828 | -3.5988 | -1.3828 | -1.4988 | 23.67 | -3.5988 | -3.5408 | 2.8408 | 2.0988 | 0.8 | 7.1977 | Open cut | 0 | 2.0408 | 0.8 | 3.6 | 0 | 6.3287 | 0.31586 | 0.48852 | 0.99698 | 1.1664 | 3.4792 | 3.6486
UG-14F | UG-14F-S01 | P0495-01 | 0.78905 | 1.6 | -3.5988 | -3.9757 | -1.4988 | -1.8757 | 23.76 | -3.9757 | -3.7872 | 3.0872 | 2.4757 | 0.8 | 7.9513 | Open cut | 0 | 2.2872 | 0.8 | 3.6 | 0 | 23.5579 | 1.0258 | 1.5865 | 1.1664 | 1.4177 | 3.6486 | 3.8999
UG-14F | UG-14F-S01 | P0495-02 | 0.050981 | 1.6 | -3.9757 | -4 | -1.8757 | -1.9 | 24.04 | -4 | -3.9878 | 3.2878 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.4878 | 0.8 | 3.6 | 0 | 1.6893 | 0.066275 | 0.1025 | 1.4177 | 1.4339 | 3.8999 | 3.9161
UG-14F | UG-14F-S01 | P0200-01 | 9.949 | 1.6 | -4 | -4 | -1.9 | -1.9 | 24.06 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Shoring | 9.949 | 2.5 | 0.8 | 3.6 | 118.1944 | 0 | 12.9337 | 20.0037 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-14F | UG-14F-S01 | P0200-02 | 10 | 1.6 | -4 | -4 | -1.9 | -1.9 | 28.92 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Shoring | 10 | 2.5 | 0.8 | 3.6 | 118.8001 | 0 | 13 | 20.1062 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-14F | UG-14F-S01 | P0200-03 | 8.0885 | 1.6 | -4 | -4 | -1.9 | -1.9 | 34.62 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Shoring | 8.0885 | 2.5 | 0.8 | 3.6 | 96.0912 | 0 | 10.515 | 16.2629 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-14G | UG-14G-S01 | P0376 | 0.05001 | 1.6 | 0.81 | 0.81 | 2.91 | 2.91 | 21.34 | 0.81 | 0.81 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14G | UG-14G-S01 | P0377 | 0.204 | 1.6 | 0.81 | 0.81 | 2.91 | 2.91 | 21.35 | 0.81 | 0.81 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14G | UG-14G-S01 | P0194 | 1.5967 | 1.6 | 0.81 | 0.81 | 2.91 | 2.91 | 21.39 | 0.81 | 0.81 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14G | UG-14G-S01 | P0577 | 0.84055 | 1.6 | 0.81 | 0.33758 | 2.91 | 2.4376 | 21.7 | 0.33758 | 0.57379 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14G | UG-14G-S01 | P0578 | 0.24334 | 1.6 | 0.33758 | 0.20082 | 2.4376 | 2.3008 | 21.88 | 0.20082 | 0.2692 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14G | UG-14G-S01 | P0576 | 0.68081 | 1.6 | 0.20082 | -0.18182 | 2.3008 | 1.9182 | 21.94 | -0.18182 | 0.0094966 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14G | UG-14G-S01 | P0220 | 5.0007 | 1.6 | -0.18182 | -2.9924 | 1.9182 | -0.89236 | 22.11 | -2.9924 | -1.5871 | 0.88709 | 1.4924 | 0.8 | 5.9847 | Open cut | 0 | 0.087089 | 0.8 | 3.6 | 0 | 22.24 | 6.5009 | 10.0545 | 99 | 0.28087 | 99 | 2.7631
UG-14G | UG-14G-S01 | P0497 | 0.67429 | 1.6 | -2.9924 | -3.3713 | -0.89236 | -1.2713 | 23.58 | -3.3713 | -3.1818 | 2.4818 | 1.8713 | 0.8 | 6.7427 | Open cut | 0 | 1.6818 | 0.8 | 3.6 | 0 | 14.1154 | 0.87657 | 1.3557 | 0.28087 | 0.83421 | 2.7631 | 3.3164
UG-14G | UG-14G-S01 | P0499 | 0.24296 | 1.6 | -3.3713 | -3.5079 | -1.2713 | -1.4079 | 23.82 | -3.5079 | -3.4396 | 2.7396 | 2.0079 | 0.8 | 7.0158 | Open cut | 0 | 1.9396 | 0.8 | 3.6 | 0 | 5.9654 | 0.31584 | 0.48849 | 0.83422 | 1.0336 | 3.3165 | 3.5158
UG-14G | UG-14G-S01 | P0498-01 | 0.46666 | 1.6 | -3.5079 | -3.7702 | -1.4079 | -1.6702 | 23.91 | -3.7702 | -3.639 | 2.939 | 2.2702 | 0.8 | 7.5403 | Open cut | 0 | 2.139 | 0.8 | 3.6 | 0 | 12.8501 | 0.60666 | 0.93828 | 1.0336 | 1.2812 | 3.5158 | 3.7634
UG-14G | UG-14G-S01 | P0498-02 | 0.37335 | 1.6 | -3.7702 | -3.98 | -1.6702 | -1.88 | 24.08 | -3.98 | -3.8751 | 3.1751 | 2.48 | 0.8 | 7.96 | Open cut | 0 | 2.3751 | 0.8 | 3.6 | 0 | 11.6757 | 0.48536 | 0.75067 | 1.2812 | 1.4206 | 3.7634 | 3.9028
UG-14G | UG-14G-S01 | P0201-01 | 9.6266 | 1.6 | -3.98 | -3.98 | -1.88 | -1.88 | 19.76 | -3.98 | -3.98 | 3.28 | 2.48 | 0.8 | 7.96 | Open cut | 0 | 2.48 | 0.8 | 3.6 | 0 | 317.7254 | 12.5146 | 19.3555 | 1.4206 | 1.4206 | 3.9028 | 3.9028
UG-14G | UG-14G-S01 | P0201-02 | 10 | 1.6 | -3.98 | -3.98 | -1.88 | -1.88 | 13.23 | -3.98 | -3.98 | 3.28 | 2.48 | 0.8 | 7.96 | Open cut | 0 | 2.48 | 0.8 | 3.6 | 0 | 330.0479 | 13 | 20.1062 | 1.4206 | 1.4206 | 3.9028 | 3.9028
UG-14G | UG-14G-S01 | P0201-03 | 8.2988 | 1.6 | -3.98 | -3.98 | -1.88 | -1.88 | 11.66 | -3.98 | -3.98 | 3.28 | 2.48 | 0.8 | 7.96 | Open cut | 0 | 2.48 | 0.8 | 3.6 | 0 | 273.9009 | 10.7885 | 16.6858 | 1.4206 | 1.4206 | 3.9028 | 3.9028
UG-14H | UG-14H-S01 | P0372 | 0.05001 | 1.6 | 0.81 | 0.81 | 2.91 | 2.91 | 21.16 | 0.81 | 0.81 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14H | UG-14H-S01 | P0373 | 0.20399 | 1.6 | 0.81 | 0.81 | 2.91 | 2.91 | 21.17 | 0.81 | 0.81 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14H | UG-14H-S01 | P0192 | 1.5019 | 1.6 | 0.81 | 0.81 | 2.91 | 2.91 | 21.21 | 0.81 | 0.81 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14H | UG-14H-S01 | P0574 | 0.84 | 1.6 | 0.81 | 0.33632 | 2.91 | 2.4363 | 21.53 | 0.33632 | 0.57316 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14H | UG-14H-S01 | P0575 | 0.24413 | 1.6 | 0.33632 | 0.19865 | 2.4363 | 2.2987 | 21.72 | 0.19865 | 0.26748 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14H | UG-14H-S01 | P0573 | 0.67911 | 1.6 | 0.19865 | -0.1843 | 2.2987 | 1.9157 | 21.78 | -0.1843 | 0.0071745 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-14H | UG-14H-S01 | P0219 | 4.9744 | 1.6 | -0.1843 | -2.9894 | 1.9157 | -0.88942 | 21.94 | -2.9894 | -1.5869 | 0.88686 | 1.4894 | 0.8 | 5.9788 | Open cut | 0 | 0.086862 | 0.8 | 3.6 | 0 | 22.1151 | 6.4668 | 10.0017 | 99 | 0.27658 | 99 | 2.7588
UG-14H | UG-14H-S01 | P0491 | 0.6736 | 1.6 | -2.9894 | -3.3693 | -0.88942 | -1.2693 | 23.41 | -3.3693 | -3.1793 | 2.4793 | 1.8693 | 0.8 | 6.7385 | Open cut | 0 | 1.6793 | 0.8 | 3.6 | 0 | 14.0781 | 0.87567 | 1.3543 | 0.27659 | 0.83122 | 2.7588 | 3.3135
UG-14H | UG-14H-S01 | P0493 | 0.243 | 1.6 | -3.3693 | -3.5063 | -1.2693 | -1.4063 | 23.64 | -3.5063 | -3.4378 | 2.7378 | 2.0063 | 0.8 | 7.0126 | Open cut | 0 | 1.9378 | 0.8 | 3.6 | 0 | 5.9601 | 0.3159 | 0.48858 | 0.83121 | 1.0313 | 3.3134 | 3.5135
UG-14H | UG-14H-S01 | P0492-01 | 0.58988 | 1.6 | -3.5063 | -3.8389 | -1.4063 | -1.7389 | 23.73 | -3.8389 | -3.6726 | 2.9726 | 2.3389 | 0.8 | 7.6779 | Open cut | 0 | 2.1726 | 0.8 | 3.6 | 0 | 16.5486 | 0.76684 | 1.186 | 1.0313 | 1.3269 | 3.5135 | 3.8091
UG-14H | UG-14H-S01 | P0492-02 | 0.25016 | 1.6 | -3.8389 | -3.98 | -1.7389 | -1.88 | 23.94 | -3.98 | -3.9095 | 3.2095 | 2.48 | 0.8 | 7.96 | Open cut | 0 | 2.4095 | 0.8 | 3.6 | 0 | 7.9639 | 0.3252 | 0.50297 | 1.3269 | 1.4206 | 3.8091 | 3.9028
UG-14H | UG-14H-S01 | P0191-01 | 9.7498 | 1.6 | -3.98 | -3.98 | -1.88 | -1.88 | 24.04 | -3.98 | -3.98 | 3.28 | 2.48 | 0.8 | 7.96 | Open cut | 0 | 2.48 | 0.8 | 3.6 | 0 | 321.7914 | 12.6748 | 19.6032 | 1.4206 | 1.4206 | 3.9028 | 3.9028
UG-14H | UG-14H-S01 | P0191-02 | 10 | 1.6 | -3.98 | -3.98 | -1.88 | -1.88 | 28.78 | -3.98 | -3.98 | 3.28 | 2.48 | 0.8 | 7.96 | Open cut | 0 | 2.48 | 0.8 | 3.6 | 0 | 330.0478 | 13 | 20.1061 | 1.4206 | 1.4206 | 3.9028 | 3.9028
UG-14H | UG-14H-S01 | P0191-03 | 8.1766 | 1.6 | -3.98 | -3.98 | -1.88 | -1.88 | 34.46 | -3.98 | -3.98 | 3.28 | 2.48 | 0.8 | 7.96 | Open cut | 0 | 2.48 | 0.8 | 3.6 | 0 | 269.8667 | 10.6296 | 16.44 | 1.4206 | 1.4206 | 3.9028 | 3.9028
UG-16A | UG-16A-S01 | P0362 | 0.05001 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.61 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16A | UG-16A-S01 | P0363 | 0.204 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.62 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16A | UG-16A-S01 | P0181 | 1.1081 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.66 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16A | UG-16A-S01 | P0583 | 0.84545 | 1.6 | 0.79 | 0.329 | 2.89 | 2.429 | 21.86 | 0.329 | 0.5595 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16A | UG-16A-S01 | P0584 | 0.23622 | 1.6 | 0.329 | 0.2002 | 2.429 | 2.3002 | 22.03 | 0.2002 | 0.2646 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16A | UG-16A-S01 | P0582 | 0.69594 | 1.6 | 0.2002 | -0.17927 | 2.3002 | 1.9207 | 22.08 | -0.17927 | 0.010464 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16A | UG-16A-S01 | P0222 | 5.2491 | 1.6 | -0.17927 | -3.0414 | 1.9207 | -0.94144 | 22.25 | -3.0414 | -1.6104 | 0.91036 | 1.5414 | 0.8 | 6.0829 | Open cut | 0 | 0.11036 | 0.8 | 3.6 | 0 | 24.2237 | 6.8239 | 10.5541 | 99 | 0.35253 | 99 | 2.8348
UG-16A | UG-16A-S01 | P0432 | 0.67494 | 1.6 | -3.0414 | -3.4095 | -0.94144 | -1.3095 | 23.78 | -3.4095 | -3.2254 | 2.5254 | 1.9095 | 0.8 | 6.8189 | Open cut | 0 | 1.7254 | 0.8 | 3.6 | 0 | 14.5297 | 0.87742 | 1.357 | 0.35254 | 0.8899 | 2.8348 | 3.3721
UG-16A | UG-16A-S01 | P0434 | 0.24298 | 1.6 | -3.4095 | -3.5419 | -1.3095 | -1.442 | 24.02 | -3.5419 | -3.4757 | 2.7757 | 2.0419 | 0.8 | 7.0839 | Open cut | 0 | 1.9757 | 0.8 | 3.6 | 0 | 6.0943 | 0.31587 | 0.48854 | 0.8899 | 1.0834 | 3.3721 | 3.5656
UG-16A | UG-16A-S01 | P0433-01 | 0.69318 | 1.6 | -3.542 | -3.9199 | -1.4419 | -1.8199 | 24.1 | -3.9199 | -3.7309 | 3.0309 | 2.4199 | 0.8 | 7.8398 | Open cut | 0 | 2.2309 | 0.8 | 3.6 | 0 | 20.0777 | 0.90114 | 1.3937 | 1.0833 | 1.3806 | 3.5656 | 3.8629
UG-16A | UG-16A-S01 | P0433-02 | 0.14686 | 1.6 | -3.9199 | -4 | -1.8199 | -1.9 | 24.35 | -4 | -3.96 | 3.26 | 2.5 | 0.8 | 8 | Shoring | 0.14686 | 2.46 | 0.8 | 3.6 | 1.7236 | 0 | 0.19092 | 0.29529 | 1.3806 | 1.4339 | 3.8629 | 3.9161
UG-16A | UG-16A-S01 | P0186-01 | 9.8531 | 1.6 | -4 | -4 | -1.9 | -1.9 | 24.41 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Shoring | 9.8531 | 2.5 | 0.8 | 3.6 | 117.0554 | 0 | 12.8091 | 19.811 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-16A | UG-16A-S01 | P0186-02 | 10 | 1.6 | -4 | -4 | -1.9 | -1.9 | 28.72 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Shoring | 10 | 2.5 | 0.8 | 3.6 | 118.8002 | 0 | 13 | 20.1063 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-16A | UG-16A-S01 | P0186-03 | 7.7775 | 1.6 | -4 | -4 | -1.9 | -1.9 | 34.33 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Shoring | 7.7775 | 2.5 | 0.8 | 3.6 | 92.3972 | 0 | 10.1108 | 15.6377 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-16B | UG-16B-S01 | P0366 | 0.05001 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.08 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16B | UG-16B-S01 | P0367 | 0.204 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.09 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16B | UG-16B-S01 | P0183 | 1.4686 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.13 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16B | UG-16B-S01 | P0589 | 0.83807 | 1.6 | 0.79 | 0.31192 | 2.89 | 2.4119 | 21.45 | 0.31192 | 0.55096 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16B | UG-16B-S01 | P0590 | 0.24696 | 1.6 | 0.31192 | 0.17104 | 2.4119 | 2.271 | 21.65 | 0.17104 | 0.24148 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16B | UG-16B-S01 | P0588 | 0.67336 | 1.6 | 0.17104 | -0.21308 | 2.271 | 1.8869 | 21.71 | -0.21308 | -0.021019 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16B | UG-16B-S01 | P0224 | 4.8813 | 1.6 | -0.21308 | -2.9977 | 1.8869 | -0.89767 | 21.88 | -2.9977 | -1.6054 | 0.90538 | 1.4977 | 0.8 | 5.9953 | Open cut | 0 | 0.10538 | 0.8 | 3.6 | 0 | 22.3504 | 6.3457 | 9.8145 | 99 | 0.28862 | 99 | 2.7709
UG-16B | UG-16B-S01 | P0437 | 0.67397 | 1.6 | -2.9977 | -3.3821 | -0.89767 | -1.2821 | 23.31 | -3.3821 | -3.1899 | 2.4899 | 1.8821 | 0.8 | 6.7643 | Open cut | 0 | 1.6899 | 0.8 | 3.6 | 0 | 14.1823 | 0.87616 | 1.3551 | 0.28862 | 0.85 | 2.7708 | 3.3322
UG-16B | UG-16B-S01 | P0439 | 0.24308 | 1.6 | -3.3821 | -3.5208 | -1.2821 | -1.4208 | 23.53 | -3.5208 | -3.4515 | 2.7515 | 2.0208 | 0.8 | 7.0416 | Open cut | 0 | 1.9515 | 0.8 | 3.6 | 0 | 6.0105 | 0.316 | 0.48874 | 0.85 | 1.0525 | 3.3322 | 3.5347
UG-16B | UG-16B-S01 | P0438-01 | 0.7206 | 1.6 | -3.5208 | -3.9319 | -1.4208 | -1.8319 | 23.62 | -3.9319 | -3.7263 | 3.0263 | 2.4319 | 0.8 | 7.8638 | Open cut | 0 | 2.2263 | 0.8 | 3.6 | 0 | 20.8199 | 0.93678 | 1.4489 | 1.0525 | 1.3886 | 3.5347 | 3.8708
UG-16B | UG-16B-S01 | P0438-02 | 0.11942 | 1.6 | -3.9319 | -4 | -1.8319 | -1.9 | 23.88 | -4 | -3.9659 | 3.2659 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.4659 | 0.8 | 3.6 | 0 | 3.9132 | 0.15524 | 0.2401 | 1.3886 | 1.4339 | 3.8708 | 3.9161
UG-16B | UG-16B-S01 | P0280-01 | 9.8806 | 1.6 | -4 | -4 | -1.9 | -1.9 | 23.92 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Shoring | 9.8806 | 2.5 | 0.8 | 3.6 | 117.3814 | 0 | 12.8448 | 19.8661 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-16B | UG-16B-S01 | P0280-02 | 10 | 1.6 | -4 | -4 | -1.9 | -1.9 | 28.3 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Shoring | 10 | 2.5 | 0.8 | 3.6 | 118.8 | 0 | 13 | 20.1062 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-16B | UG-16B-S01 | P0280-03 | 8.1234 | 1.6 | -4 | -4 | -1.9 | -1.9 | 34.02 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Shoring | 8.1234 | 2.5 | 0.8 | 3.6 | 96.5062 | 0 | 10.5604 | 16.3331 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-16C | UG-16C-S01 | P0368 | 0.05001 | 1.6 | 0.8 | 0.8 | 2.9 | 2.9 | 21.09 | 0.8 | 0.8 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16C | UG-16C-S01 | P0369 | 0.20399 | 1.6 | 0.8 | 0.8 | 2.9 | 2.9 | 21.1 | 0.8 | 0.8 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16C | UG-16C-S01 | P0184 | 0.95946 | 1.6 | 0.8 | 0.8 | 2.9 | 2.9 | 21.14 | 0.8 | 0.8 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16C | UG-16C-S01 | P0591 | 1.7802 | 1.6 | 0.8 | -0.16004 | 2.9 | 1.94 | 21.33 | -0.16004 | 0.31998 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16C | UG-16C-S01 | P0225 | 5.3639 | 1.6 | -0.16004 | -3.0527 | 1.94 | -0.9527 | 21.73 | -3.0527 | -1.6064 | 0.90637 | 1.5527 | 0.8 | 6.1054 | Open cut | 0 | 0.10637 | 0.8 | 3.6 | 0 | 24.5988 | 6.9731 | 10.7849 | 99 | 0.36897 | 99 | 2.8512
UG-16C | UG-16C-S01 | P0440 | 0.91654 | 1.6 | -3.0527 | -3.547 | -0.9527 | -1.447 | 23.28 | -3.547 | -3.2998 | 2.5998 | 2.047 | 0.8 | 7.094 | Open cut | 0 | 1.7998 | 0.8 | 3.6 | 0 | 20.6752 | 1.1915 | 1.8428 | 0.36897 | 1.0907 | 2.8512 | 3.5729
UG-16C | UG-16C-S01 | P0441-01 | 0.72586 | 1.6 | -3.547 | -3.9384 | -1.447 | -1.8384 | 23.6 | -3.9384 | -3.7427 | 3.0427 | 2.4384 | 0.8 | 7.8768 | Open cut | 0 | 2.2427 | 0.8 | 3.6 | 0 | 21.1587 | 0.94362 | 1.4594 | 1.0907 | 1.3929 | 3.5729 | 3.8752
UG-16C | UG-16C-S01 | P0441-02 | 0.11419 | 1.6 | -3.9384 | -4 | -1.8384 | -1.9 | 23.86 | -4 | -3.9692 | 3.2692 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.4692 | 0.8 | 3.6 | 0 | 3.7482 | 0.14845 | 0.22959 | 1.3929 | 1.4339 | 3.8752 | 3.9161
UG-16C | UG-16C-S01 | P0185-01 | 9.8858 | 1.6 | -4 | -4 | -1.9 | -1.9 | 23.91 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.5 | 0.8 | 3.6 | 0 | 329.5926 | 12.8515 | 19.8765 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-16C | UG-16C-S01 | P0185-02 | 10 | 1.6 | -4 | -4 | -1.9 | -1.9 | 28.4 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.5 | 0.8 | 3.6 | 0 | 333.3996 | 13 | 20.1061 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-16C | UG-16C-S01 | P0185-03 | 8.3838 | 1.6 | -4 | -4 | -1.9 | -1.9 | 34.12 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.5 | 0.8 | 3.6 | 0 | 279.5159 | 10.8989 | 16.8566 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-16D | UG-16D-S01 | P0364 | 0.05001 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.66 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16D | UG-16D-S01 | P0365 | 0.20399 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.67 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16D | UG-16D-S01 | P0182 | 1.3557 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.7 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16D | UG-16D-S01 | P0586 | 0.84004 | 1.6 | 0.79 | 0.31638 | 2.89 | 2.4164 | 21.96 | 0.31638 | 0.55319 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16D | UG-16D-S01 | P0587 | 0.24407 | 1.6 | 0.31638 | 0.17878 | 2.4164 | 2.2788 | 22.14 | 0.17878 | 0.24758 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16D | UG-16D-S01 | P0585 | 0.67923 | 1.6 | 0.17878 | -0.20418 | 2.2788 | 1.8958 | 22.19 | -0.20418 | -0.012701 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-16D | UG-16D-S01 | P0223 | 4.9755 | 1.6 | -0.20418 | -3.0094 | 1.8958 | -0.90936 | 22.36 | -3.0094 | -1.6068 | 0.90677 | 1.5094 | 0.8 | 6.0187 | Open cut | 0 | 0.10677 | 0.8 | 3.6 | 0 | 22.8315 | 6.4681 | 10.0037 | 99 | 0.3057 | 99 | 2.7879
UG-16D | UG-16D-S01 | P0435 | 0.917 | 1.5999 | -3.0093 | -3.5264 | -0.90939 | -1.4264 | 23.78 | -3.5264 | -3.2678 | 2.5678 | 2.0264 | 0.8 | 7.0527 | Open cut | 0 | 1.7678 | 0.8 | 3.5999 | 0 | 20.2766 | 1.1921 | 1.8436 | 0.30574 | 1.0607 | 2.7881 | 3.543
UG-16D | UG-16D-S01 | P0436-01 | 0.73445 | 1.6 | -3.5264 | -3.9405 | -1.4264 | -1.8405 | 24.09 | -3.9405 | -3.7334 | 3.0334 | 2.4405 | 0.8 | 7.8809 | Open cut | 0 | 2.2334 | 0.8 | 3.6 | 0 | 21.3018 | 0.95479 | 1.4767 | 1.0606 | 1.3943 | 3.5428 | 3.8765
UG-16D | UG-16D-S01 | P0436-02 | 0.1056 | 1.6 | -3.9405 | -4 | -1.8405 | -1.9 | 24.36 | -4 | -3.9702 | 3.2702 | 2.5 | 0.8 | 8 | Shoring | 0.1056 | 2.4702 | 0.8 | 3.6 | 1.2432 | 0 | 0.13728 | 0.21233 | 1.3943 | 1.4339 | 3.8765 | 3.9161
UG-16D | UG-16D-S01 | P0261-01 | 9.8944 | 1.6 | -4 | -4 | -1.9 | -1.9 | 24.39 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Shoring | 9.8944 | 2.5 | 0.8 | 3.6 | 117.5457 | 0 | 12.8627 | 19.894 | 1.4338 | 1.4338 | 3.9161 | 3.9161
UG-16D | UG-16D-S01 | P0261-02 | 10 | 1.6 | -4 | -4 | -1.9 | -1.9 | 28.74 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Shoring | 10 | 2.5 | 0.8 | 3.6 | 118.8002 | 0 | 13 | 20.1063 | 1.4338 | 1.4338 | 3.9161 | 3.9161
UG-16D | UG-16D-S01 | P0261-03 | 6.3001 | 1.6 | -4 | -4 | -1.9 | -1.9 | 34.41 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Shoring | 6.3001 | 2.5 | 0.8 | 3.6 | 74.8457 | 0 | 8.1902 | 12.6672 | 1.4338 | 1.4338 | 3.9161 | 3.9161
UG-27I | UG-27I-S01 | P0391 | 0.05001 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.28 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27I | UG-27I-S01 | P0392 | 0.20399 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.29 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27I | UG-27I-S01 | P0213 | 1.1891 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.33 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27I | UG-27I-S01 | P0565 | 0.83943 | 1.6 | 0.79 | 0.31528 | 2.89 | 2.4153 | 21.58 | 0.31528 | 0.55264 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27I | UG-27I-S01 | P0566 | 0.24487 | 1.6 | 0.31528 | 0.17679 | 2.4153 | 2.2768 | 21.78 | 0.17679 | 0.24603 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27I | UG-27I-S01 | P0564 | 0.67931 | 1.6 | 0.17679 | -0.20738 | 2.2768 | 1.8926 | 21.84 | -0.20738 | -0.015299 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27I | UG-27I-S01 | P0216 | 4.9478 | 1.6 | -0.20738 | -3.0055 | 1.8926 | -0.90553 | 22.03 | -3.0055 | -1.6065 | 0.90645 | 1.5055 | 0.8 | 6.0111 | Open cut | 0 | 0.10645 | 0.8 | 3.6 | 0 | 22.6935 | 6.4322 | 9.9482 | 99 | 0.3001 | 99 | 2.7823
UG-27I | UG-27I-S01 | P0556 | 0.67568 | 1.5999 | -3.0055 | -3.3876 | -0.90559 | -1.2877 | 23.55 | -3.3876 | -3.1965 | 2.4965 | 1.8876 | 0.8 | 6.7751 | Open cut | 0 | 1.6965 | 0.8 | 3.5999 | 0 | 14.2788 | 0.87834 | 1.3583 | 0.30022 | 0.85821 | 2.7826 | 3.3406
UG-27I | UG-27I-S01 | P0558 | 0.24281 | 1.6 | -3.3877 | -3.525 | -1.2876 | -1.425 | 23.76 | -3.525 | -3.4563 | 2.7563 | 2.025 | 0.8 | 7.0499 | Open cut | 0 | 1.9563 | 0.8 | 3.6 | 0 | 6.0211 | 0.31566 | 0.48821 | 0.85805 | 1.0586 | 3.3403 | 3.5408
UG-27I | UG-27I-S01 | P0557 | 0.83997 | 1.6 | -3.525 | -4 | -1.425 | -1.9 | 23.84 | -4 | -3.7625 | 3.0625 | 2.5 | 0.8 | 8 | Shoring | 0.83997 | 2.2625 | 0.8 | 3.6 | 9.2607 | 0 | 1.092 | 1.6889 | 1.0585 | 1.4338 | 3.5408 | 3.9161
UG-27I | UG-27I-S01 | P0275-01 | 0.086931 | 1.6 | -4 | -4 | -1.9 | -1.9 | 24.14 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.5 | 0.8 | 3.6 | 0 | 2.8983 | 0.11301 | 0.17478 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-27I | UG-27I-S01 | P0275-02 | 10 | 1.6 | -4 | -4 | -1.9 | -1.9 | 24.18 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.5 | 0.8 | 3.6 | 0 | 333.3997 | 13 | 20.1061 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-27I | UG-27I-S01 | P0275-03 | 10 | 1.6 | -4 | -4 | -1.9 | -1.9 | 28.6 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.5 | 0.8 | 3.6 | 0 | 333.3997 | 13 | 20.1061 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-27I | UG-27I-S01 | P0275-04 | 7.5872 | 1.6 | -4 | -4 | -1.9 | -1.9 | 34.31 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.5 | 0.8 | 3.6 | 0 | 252.9566 | 9.8633 | 15.2549 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-27J | UG-27J-S01 | P0380 | 0.05001 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.27 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27J | UG-27J-S01 | P0381 | 0.20399 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.28 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27J | UG-27J-S01 | P0196 | 1.4139 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.32 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27J | UG-27J-S01 | P0563 | 0.83919 | 1.6 | 0.79 | 0.31449 | 2.89 | 2.4145 | 21.62 | 0.31449 | 0.55225 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27J | UG-27J-S01 | P0562 | 0.92142 | 1.6 | 0.31449 | -0.20761 | 2.4145 | 1.8924 | 21.81 | -0.20761 | 0.053439 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27J | UG-27J-S01 | P0215 | 4.9363 | 1.6 | -0.20761 | -3.0046 | 1.8924 | -0.90461 | 22.04 | -3.0046 | -1.6061 | 0.90611 | 1.5046 | 0.8 | 6.0092 | Open cut | 0 | 0.10611 | 0.8 | 3.6 | 0 | 22.6281 | 6.4171 | 9.9249 | 99 | 0.29876 | 99 | 2.781
UG-27J | UG-27J-S01 | P0504 | 0.91666 | 1.6 | -3.0046 | -3.524 | -0.90461 | -1.424 | 23.53 | -3.524 | -3.2643 | 2.5643 | 2.024 | 0.8 | 7.048 | Open cut | 0 | 1.7643 | 0.8 | 3.6 | 0 | 20.2241 | 1.1917 | 1.8431 | 0.29876 | 1.0572 | 2.781 | 3.5394
UG-27J | UG-27J-S01 | P0503 | 0.42021 | 1.6 | -3.524 | -3.7621 | -1.424 | -1.6621 | 23.85 | -3.7621 | -3.6431 | 2.9431 | 2.2621 | 0.8 | 7.5242 | Open cut | 0 | 2.1431 | 0.8 | 3.6 | 0 | 11.5971 | 0.54627 | 0.84488 | 1.0572 | 1.2758 | 3.5394 | 3.758
UG-27J | UG-27J-S01 | P0505-01 | 0.2984 | 1.6 | -3.7621 | -3.9312 | -1.6621 | -1.8312 | 24.01 | -3.9312 | -3.8466 | 3.1466 | 2.4312 | 0.8 | 7.8624 | Open cut | 0 | 2.3466 | 0.8 | 3.6 | 0 | 9.1938 | 0.38792 | 0.59996 | 1.2758 | 1.3881 | 3.758 | 3.8704
UG-27J | UG-27J-S01 | P0505-02 | 0.12144 | 1.6 | -3.9312 | -4 | -1.8312 | -1.9 | 24.12 | -4 | -3.9656 | 3.2656 | 2.5 | 0.8 | 8 | Shoring | 0.12144 | 2.4656 | 0.8 | 3.6 | 1.4277 | 0 | 0.15787 | 0.24417 | 1.3881 | 1.4339 | 3.8704 | 3.9161
UG-27J | UG-27J-S01 | P0199-01 | 5.8786 | 1.6 | -4 | -4 | -1.9 | -1.9 | 24.16 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.5 | 0.8 | 3.6 | 0 | 195.991 | 7.6421 | 11.8195 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-27J | UG-27J-S02 | P0199-02 | 4 | 1.6 | -4 | -4 | -1.9 | -1.9 | 26.84 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.5 | 0.8 | 3.6 | 0 | 133.3599 | 5.2 | 8.0425 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-27J | UG-27J-S02 | P0199-03 | 10 | 1.6 | -4 | -4 | -1.9 | -1.9 | 28.78 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.5 | 0.8 | 3.6 | 0 | 333.3998 | 13 | 20.1061 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-27J | UG-27J-S02 | P0199-04 | 8.0646 | 1.6 | -4 | -4 | -1.9 | -1.9 | 34.46 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.5 | 0.8 | 3.6 | 0 | 268.8723 | 10.4839 | 16.2147 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-27K | UG-27K-S01 | P0382 | 0.05001 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.3 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27K | UG-27K-S01 | P0383 | 0.20399 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.3 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27K | UG-27K-S01 | P0197 | 1.0427 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.34 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27K | UG-27K-S01 | P0568 | 0.84922 | 1.6 | 0.79 | 0.33788 | 2.89 | 2.4379 | 21.54 | 0.33788 | 0.56394 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27K | UG-27K-S01 | P0569 | 0.23022 | 1.6 | 0.33788 | 0.21531 | 2.4379 | 2.3153 | 21.71 | 0.21531 | 0.2766 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27K | UG-27K-S01 | P0567 | 0.70868 | 1.6 | 0.21531 | -0.16198 | 2.3153 | 1.938 | 21.77 | -0.16198 | 0.026667 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27K | UG-27K-S01 | P0217 | 5.4495 | 1.6 | -0.16198 | -3.0633 | 1.938 | -0.96325 | 21.96 | -3.0633 | -1.6126 | 0.91262 | 1.5633 | 0.8 | 6.1265 | Open cut | 0 | 0.11262 | 0.8 | 3.6 | 0 | 25.2375 | 7.0844 | 10.9569 | 99 | 0.38438 | 99 | 2.8666
UG-27K | UG-27K-S01 | P0507 | 0.67673 | 1.6 | -3.0632 | -3.4235 | -0.96325 | -1.3235 | 23.62 | -3.4235 | -3.2434 | 2.5434 | 1.9235 | 0.8 | 6.8471 | Open cut | 0 | 1.7434 | 0.8 | 3.6 | 0 | 14.735 | 0.87975 | 1.3606 | 0.38438 | 0.91044 | 2.8666 | 3.3927
UG-27K | UG-27K-S01 | P0509 | 0.24282 | 1.6 | -3.4235 | -3.5528 | -1.3235 | -1.4528 | 23.88 | -3.5528 | -3.4882 | 2.7882 | 2.0528 | 0.8 | 7.1056 | Open cut | 0 | 1.9882 | 0.8 | 3.6 | 0 | 6.1349 | 0.31567 | 0.48822 | 0.91044 | 1.0992 | 3.3927 | 3.5814
UG-27K | UG-27K-S01 | P0508-01 | 0.54615 | 1.6 | -3.5528 | -3.8436 | -1.4528 | -1.7436 | 23.97 | -3.8436 | -3.6982 | 2.9982 | 2.3436 | 0.8 | 7.6871 | Open cut | 0 | 2.1982 | 0.8 | 3.6 | 0 | 15.5388 | 0.70999 | 1.0981 | 1.0992 | 1.3299 | 3.5814 | 3.8122
UG-27K | UG-27K-S01 | P0508-02 | 0.29383 | 1.6 | -3.8436 | -4 | -1.7436 | -1.9 | 24.17 | -4 | -3.9218 | 3.2218 | 2.5 | 0.8 | 8 | Shoring | 0.29383 | 2.4218 | 0.8 | 3.6 | 3.4079 | 0 | 0.38198 | 0.59078 | 1.3299 | 1.4339 | 3.8122 | 3.9161
UG-27K | UG-27K-S01 | P0276-01 | 9.7062 | 1.6 | -4 | -4 | -1.9 | -1.9 | 24.28 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Shoring | 9.7062 | 2.5 | 0.8 | 3.6 | 115.3095 | 0 | 12.618 | 19.5155 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-27K | UG-27K-S01 | P0276-02 | 10 | 1.6 | -4 | -4 | -1.9 | -1.9 | 28.63 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Shoring | 10 | 2.5 | 0.8 | 3.6 | 118.8001 | 0 | 13 | 20.1063 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-27K | UG-27K-S01 | P0276-03 | 7.7244 | 1.6 | -4 | -4 | -1.9 | -1.9 | 34.3 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Shoring | 7.7244 | 2.5 | 0.8 | 3.6 | 91.7656 | 0 | 10.0417 | 15.5308 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-27L | UG-27L-S01 | P0378 | 0.05 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.16 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27L | UG-27L-S01 | P0379 | 0.204 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.17 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27L | UG-27L-S01 | P0195 | 1.4781 | 1.6 | 0.79 | 0.79 | 2.89 | 2.89 | 21.21 | 0.79 | 0.79 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27L | UG-27L-S01 | P0560 | 0.83942 | 1.6 | 0.79 | 0.31528 | 2.89 | 2.4153 | 21.52 | 0.31528 | 0.55264 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27L | UG-27L-S01 | P0561 | 0.24523 | 1.6 | 0.31528 | 0.1766 | 2.4153 | 2.2766 | 21.72 | 0.1766 | 0.24594 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27L | UG-27L-S01 | P0559 | 0.67896 | 1.6 | 0.1766 | -0.20737 | 2.2766 | 1.8926 | 21.78 | -0.20737 | -0.015382 | 0 | 0 | 0 | 1.8 | Open cut | 0 | 0 | 0 | 3.6 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-27L | UG-27L-S01 | P0214 | 4.9478 | 1.6 | -0.20737 | -3.0055 | 1.8926 | -0.90553 | 21.93 | -3.0055 | -1.6064 | 0.90645 | 1.5055 | 0.8 | 6.0111 | Open cut | 0 | 0.10645 | 0.8 | 3.6 | 0 | 22.6933 | 6.4322 | 9.9482 | 99 | 0.30011 | 99 | 2.7823
UG-27L | UG-27L-S01 | P0500 | 0.67568 | 1.6 | -3.0055 | -3.3877 | -0.90552 | -1.2876 | 23.33 | -3.3877 | -3.1966 | 2.4966 | 1.8877 | 0.8 | 6.7753 | Open cut | 0 | 1.6966 | 0.8 | 3.6 | 0 | 14.2798 | 0.87839 | 1.3586 | 0.30008 | 0.85802 | 2.7823 | 3.3402
UG-27L | UG-27L-S01 | P0502 | 0.24282 | 1.6 | -3.3876 | -3.525 | -1.2877 | -1.425 | 23.54 | -3.525 | -3.4563 | 2.7563 | 2.025 | 0.8 | 7.0499 | Open cut | 0 | 1.9563 | 0.8 | 3.6 | 0 | 6.0211 | 0.31566 | 0.48821 | 0.85805 | 1.0586 | 3.3403 | 3.5408
UG-27L | UG-27L-S01 | P0501-01 | 0.63795 | 1.6 | -3.525 | -3.8857 | -1.425 | -1.7857 | 23.63 | -3.8857 | -3.7054 | 3.0054 | 2.3857 | 0.8 | 7.7715 | Open cut | 0 | 2.2054 | 0.8 | 3.6 | 0 | 18.2221 | 0.82933 | 1.2827 | 1.0586 | 1.358 | 3.5408 | 3.8402
UG-27L | UG-27L-S01 | P0501-02 | 0.20203 | 1.6 | -3.8857 | -4 | -1.7857 | -1.9 | 23.86 | -4 | -3.9429 | 3.2429 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.4429 | 0.8 | 3.6 | 0 | 6.543 | 0.26263 | 0.4062 | 1.358 | 1.4339 | 3.8402 | 3.9161
UG-27L | UG-27L-S01 | P0198-01 | 9.798 | 1.6 | -4 | -4 | -1.9 | -1.9 | 23.94 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.5 | 0.8 | 3.6 | 0 | 326.6642 | 12.7374 | 19.6999 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-27L | UG-27L-S01 | P0198-02 | 10 | 1.6 | -4 | -4 | -1.9 | -1.9 | 28.84 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.5 | 0.8 | 3.6 | 0 | 333.3997 | 13 | 20.1061 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-27L | UG-27L-S01 | P0198-03 | 8.1115 | 1.6 | -4 | -4 | -1.9 | -1.9 | 34.5 | -4 | -4 | 3.3 | 2.5 | 0.8 | 8 | Open cut | 0 | 2.5 | 0.8 | 3.6 | 0 | 270.4367 | 10.5449 | 16.3091 | 1.4339 | 1.4339 | 3.9161 | 3.9161
UG-17 | UG-17-S01 | P0073 | 6.0173 | 2.2764 | -3.9282 | -3.9282 | -1.1518 | -1.1518 | 15.9 | -3.9282 | -3.9282 | 3.2282 | 2.4282 | 0.8 | 8.1946 | Open cut | 0 | 2.4282 | 0.8 | 4.2764 | 0 | 206.5599 | 9.8576 | 24.49 | 0.46367 | 0.46367 | 2.2083 | 2.2083
UG-17 | UG-17-S01 | P0651 | 2.2 | 2.2764 | -3.9282 | -3.9282 | -1.1518 | -1.1518 | 15.98 | -3.9282 | -3.9282 | 3.2282 | 2.4282 | 0.8 | 8.1946 | Open cut | 0 | 2.4282 | 0.8 | 4.2764 | 0 | 75.5207 | 3.604 | 8.9538 | 0.46367 | 0.46367 | 2.2083 | 2.2083
UG-17 | UG-17-S01 | P0652-01 | 1.7827 | 2.249 | -3.9145 | -3.9145 | -1.1655 | -1.1655 | 14.45 | -3.9145 | -3.9145 | 3.2145 | 2.4145 | 0.8 | 8.1535 | Open cut | 0 | 2.4145 | 0.8 | 4.249 | 0 | 60.6192 | 2.896 | 7.0818 | 0.48356 | 0.48356 | 2.2495 | 2.2495
UG-17 | UG-17-S01 | P0652-02 | 0.41731 | 2.249 | -3.9145 | -3.9145 | -1.1655 | -1.1655 | 14.09 | -3.9145 | -3.9145 | 3.2145 | 2.4145 | 0.8 | 8.1535 | Open cut | 0 | 2.4145 | 0.8 | 4.249 | 0 | 14.1902 | 0.67791 | 1.6578 | 0.48356 | 0.48356 | 2.2495 | 2.2495
UG-17 | UG-17-S01 | P0650 | 1.471 | 2.249 | -3.9145 | -3.9145 | -1.1655 | -1.1655 | 12.85 | -3.9145 | -3.9145 | 3.2145 | 2.4145 | 0.8 | 8.1535 | Open cut | 0 | 2.4145 | 0.8 | 4.249 | 0 | 50.0199 | 2.3896 | 5.8435 | 0.48356 | 0.48356 | 2.2495 | 2.2495
UG-17 | UG-17-S01 | P0649 | 0.68672 | 2.2058 | -3.8929 | -3.8929 | -1.1871 | -1.1871 | 12.36 | -3.8929 | -3.8929 | 3.1929 | 2.3929 | 0.8 | 8.0887 | Open cut | 0 | 2.3929 | 0.8 | 4.2058 | 0 | 23.0035 | 1.1007 | 2.6242 | 0.51591 | 0.51591 | 2.3164 | 2.3164
UG-17 | UG-17-S01 | P0648 | 0.68657 | 2.2058 | -3.8929 | -3.8929 | -1.1871 | -1.1871 | 12.09 | -3.8929 | -3.8929 | 3.1929 | 2.3929 | 0.8 | 8.0887 | Open cut | 0 | 2.3929 | 0.8 | 4.2058 | 0 | 22.9985 | 1.1005 | 2.6236 | 0.51591 | 0.51591 | 2.3164 | 2.3164
UG-17 | UG-17-S01 | P0647 | 1.471 | 2.249 | -3.9145 | -3.9145 | -1.1655 | -1.1655 | 11.84 | -3.9145 | -3.9145 | 3.2145 | 2.4145 | 0.8 | 8.1535 | Open cut | 0 | 2.4145 | 0.8 | 4.249 | 0 | 50.0199 | 2.3896 | 5.8435 | 0.48355 | 0.48355 | 2.2495 | 2.2495
UG-17 | UG-17-S02 | P0240-01 | 5.2674 | 2.2764 | -3.9282 | -3.9889 | -1.1518 | -1.2125 | 11.37 | -3.9889 | -3.9585 | 3.2585 | 2.4889 | 0.8 | 8.316 | Open cut | 0 | 2.4585 | 0.8 | 4.2764 | 0 | 183.5759 | 8.6291 | 21.4381 | 0.46367 | 0.52596 | 2.2084 | 2.2706
UG-17 | UG-17-S02 | P0240-02 | 10 | 2.2764 | -3.9889 | -4.1041 | -1.2125 | -1.3277 | 11.36 | -4.1041 | -4.0465 | 3.3465 | 2.6041 | 0.8 | 8.5464 | Shoring | 10 | 2.5465 | 0.8 | 4.2764 | 143.1095 | 0 | 16.382 | 40.6992 | 0.52596 | 0.64421 | 2.2706 | 2.3889
UG-17 | UG-17-S02 | P0240-03 | 10 | 2.2764 | -4.1041 | -4.2193 | -1.3277 | -1.4429 | 11.66 | -4.2193 | -4.1617 | 3.4617 | 2.7193 | 0.8 | 8.7768 | Shoring | 10 | 2.6617 | 0.8 | 4.2764 | 148.0366 | 0 | 16.382 | 40.6992 | 0.64421 | 0.76245 | 2.3889 | 2.5071
UG-17 | UG-17-S02 | P0240-04 | 1.8812 | 2.2764 | -4.2193 | -4.241 | -1.4429 | -1.4646 | 14.9 | -4.241 | -4.2302 | 3.5302 | 2.741 | 0.8 | 8.8202 | Shoring | 1.8812 | 2.7302 | 0.8 | 4.2764 | 28.3992 | 0 | 3.0818 | 7.6563 | 0.76245 | 0.7847 | 2.5071 | 2.5294
UG-17 | UG-17-S02 | P0638 | 3.3494 | 2.2764 | -4.241 | -4.2796 | -1.4646 | -1.5032 | 16.14 | -4.2796 | -4.2603 | 3.5603 | 2.7796 | 0.8 | 8.8974 | Shoring | 3.3494 | 2.7603 | 0.8 | 4.2764 | 50.9955 | 0 | 5.487 | 13.6318 | 0.7847 | 0.82252 | 2.5294 | 2.5672
UG-17 | UG-17-S02 | P0637 | 3.3505 | 2.2764 | -4.2796 | -4.3182 | -1.5032 | -1.5418 | 17.39 | -4.3182 | -4.2989 | 3.5989 | 2.8182 | 0.8 | 8.9746 | Shoring | 3.3505 | 2.7989 | 0.8 | 4.2764 | 51.5647 | 0 | 5.4887 | 13.6361 | 0.82252 | 0.84054 | 2.5672 | 2.5852
UG-17 | UG-17-S02 | P0082-01 | 1.4189 | 2.2764 | -4.3182 | -4.3182 | -1.5418 | -1.5418 | 17.16 | -4.3182 | -4.3182 | 3.6182 | 2.8182 | 0.8 | 8.9746 | Shoring | 1.4189 | 2.8182 | 0.8 | 4.2764 | 21.955 | 0 | 2.3245 | 5.775 | 0.84054 | 0.84054 | 2.5852 | 2.5852
UG-17 | UG-17-S02 | P0082-02 | 10 | 2.2764 | -4.3182 | -4.3182 | -1.5418 | -1.5418 | 16.69 | -4.3182 | -4.3182 | 3.6182 | 2.8182 | 0.8 | 8.9746 | Shoring | 10 | 2.8182 | 0.8 | 4.2764 | 154.7286 | 0 | 16.382 | 40.6992 | 0.84054 | 0.84054 | 2.5852 | 2.5852
UG-17 | UG-17-S03 | P0082-03 | 3.9993 | 2.2764 | -4.3182 | -4.3182 | -1.5418 | -1.5418 | 16.81 | -4.3182 | -4.3182 | 3.6182 | 2.8182 | 0.8 | 8.9746 | Shoring | 3.9993 | 2.8182 | 0.8 | 4.2764 | 61.8811 | 0 | 6.5517 | 16.277 | 0.84054 | 0.84054 | 2.5852 | 2.5852
UG-17 | UG-17-S03 | P0081 | 3.35 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 17.28 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 3.35 | 2.8045 | 0.8 | 4.249 | 51.3068 | 0 | 5.4421 | 13.3079 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0080-01 | 2.6507 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 16.59 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 2.6507 | 2.8045 | 0.8 | 4.249 | 40.5962 | 0 | 4.306 | 10.5298 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0080-02 | 0.69933 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 16.25 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 0.69933 | 2.8045 | 0.8 | 4.249 | 10.7106 | 0 | 1.1361 | 2.7781 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0111-01 | 9.3007 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 12.67 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 9.3007 | 2.8045 | 0.8 | 4.249 | 142.4441 | 0 | 15.1089 | 36.947 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0111-02 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 10.94 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1547 | 0 | 16.245 | 39.7251 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0111-03 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 10.89 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1547 | 0 | 16.245 | 39.7251 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0111-04 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 11.67 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1547 | 0 | 16.245 | 39.7251 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0111-05 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 14.73 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1547 | 0 | 16.245 | 39.7251 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0111-06 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 19.69 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1547 | 0 | 16.245 | 39.7251 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0111-07 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 16.87 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1547 | 0 | 16.245 | 39.7251 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0111-08 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 12.92 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1547 | 0 | 16.245 | 39.7251 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0111-09 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 11.13 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1547 | 0 | 16.245 | 39.7251 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0111-10 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 11.07 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1547 | 0 | 16.245 | 39.7251 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0111-11 | 5.13 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 11.79 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 5.13 | 2.8045 | 0.8 | 4.249 | 78.568 | 0 | 8.3336 | 20.3789 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0069 | 3.35 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 13.06 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 3.35 | 2.8045 | 0.8 | 4.249 | 51.3068 | 0 | 5.4421 | 13.3079 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0068-01 | 1.52 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 13.62 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 1.52 | 2.8045 | 0.8 | 4.249 | 23.2801 | 0 | 2.4693 | 6.0384 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0068-02 | 1.83 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 13 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 1.83 | 2.8045 | 0.8 | 4.249 | 28.0269 | 0 | 2.9728 | 7.2696 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0085-01 | 8.17 | 2.2764 | -4.3182 | -4.3182 | -1.5418 | -1.5418 | 11.11 | -4.3182 | -4.3182 | 3.6182 | 2.8182 | 0.8 | 8.9746 | Shoring | 8.17 | 2.8182 | 0.8 | 4.2764 | 126.4137 | 0 | 13.3841 | 33.2514 | 0.84054 | 0.84054 | 2.5852 | 2.5852
UG-17 | UG-17-S03 | P0085-02 | 10 | 2.2764 | -4.3182 | -4.3182 | -1.5418 | -1.5418 | 10.74 | -4.3182 | -4.3182 | 3.6182 | 2.8182 | 0.8 | 8.9746 | Shoring | 10 | 2.8182 | 0.8 | 4.2764 | 154.7286 | 0 | 16.382 | 40.6992 | 0.84054 | 0.84054 | 2.5852 | 2.5852
UG-17 | UG-17-S03 | P0085-03 | 4.361 | 2.2764 | -4.3182 | -4.3182 | -1.5418 | -1.5418 | 11.01 | -4.3182 | -4.3182 | 3.6182 | 2.8182 | 0.8 | 8.9746 | Shoring | 4.361 | 2.8182 | 0.8 | 4.2764 | 67.4772 | 0 | 7.1442 | 17.7489 | 0.84054 | 0.84054 | 2.5852 | 2.5852
UG-17 | UG-17-S03 | P0658 | 3.35 | 2.2764 | -4.3182 | -4.3182 | -1.5418 | -1.5418 | 11.74 | -4.3182 | -4.3182 | 3.6182 | 2.8182 | 0.8 | 8.9746 | Shoring | 3.35 | 2.8182 | 0.8 | 4.2764 | 51.8338 | 0 | 5.4879 | 13.6342 | 0.84054 | 0.84054 | 2.5852 | 2.5852
UG-17 | UG-17-S03 | P0659-01 | 2.289 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 11.69 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 2.289 | 2.8045 | 0.8 | 4.249 | 35.0576 | 0 | 3.7185 | 9.0933 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0659-02 | 1.061 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 11.3 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 1.061 | 2.8045 | 0.8 | 4.249 | 16.2497 | 0 | 1.7236 | 4.2149 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0271-01 | 8.939 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 9.03 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 8.939 | 2.8045 | 0.8 | 4.249 | 136.9058 | 0 | 14.5214 | 35.5108 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0271-02 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 8.64 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1555 | 0 | 16.245 | 39.7256 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0271-03 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 8.92 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1555 | 0 | 16.245 | 39.7256 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0271-04 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 11.36 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1555 | 0 | 16.245 | 39.7256 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0271-05 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 15.95 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1555 | 0 | 16.245 | 39.7256 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S03 | P0271-06 | 7.1 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 20.33 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 7.1 | 2.8045 | 0.8 | 4.249 | 108.7404 | 0 | 11.534 | 28.2052 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S04 | P0271-07 | 2.9 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 18.72 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 2.9 | 2.8045 | 0.8 | 4.249 | 44.4151 | 0 | 4.7111 | 11.5204 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S04 | P0271-08 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 14.24 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1555 | 0 | 16.245 | 39.7256 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S04 | P0271-09 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 11.77 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1555 | 0 | 16.245 | 39.7256 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S04 | P0271-10 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 11.41 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1555 | 0 | 16.245 | 39.7256 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S04 | P0271-11 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 11.68 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1555 | 0 | 16.245 | 39.7256 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S04 | P0271-12 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 13.97 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1555 | 0 | 16.245 | 39.7256 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S04 | P0271-13 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 18.32 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1555 | 0 | 16.245 | 39.7256 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S04 | P0271-14 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 24.21 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1555 | 0 | 16.245 | 39.7256 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S04 | P0271-15 | 3.1 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 99 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 3.1 | 2.8045 | 0.8 | 4.249 | 47.4782 | 0 | 5.036 | 12.3149 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S05 | P0271-16 | 6.9 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 20.78 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 6.9 | 2.8045 | 0.8 | 4.249 | 105.6773 | 0 | 11.2091 | 27.4107 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S05 | P0271-17 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 12.97 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1555 | 0 | 16.245 | 39.7256 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-17 | UG-17-S05 | P0271-18 | 8.0735 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 10.05 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 8.0735 | 2.8045 | 0.8 | 4.249 | 123.6496 | 0 | 13.1154 | 32.0724 | 0.85725 | 0.85725 | 2.6232 | 2.6232
UG-18 | UG-18-S01 | P0072 | 1.8039 | 2.2764 | -3.9282 | -3.9282 | -1.1518 | -1.1518 | 19.95 | -3.9282 | -3.9282 | 3.2282 | 2.4282 | 0.8 | 8.1946 | Open cut | 0 | 2.4282 | 0.8 | 4.2764 | 0 | 61.9243 | 2.9552 | 7.3418 | 0.46367 | 0.46367 | 2.2083 | 2.2083
UG-18 | UG-18-S01 | P0645 | 2.2 | 2.2764 | -3.9282 | -3.9282 | -1.1518 | -1.1518 | 19.23 | -3.9282 | -3.9282 | 3.2282 | 2.4282 | 0.8 | 8.1946 | Open cut | 0 | 2.4282 | 0.8 | 4.2764 | 0 | 75.5204 | 3.604 | 8.9538 | 0.46367 | 0.46367 | 2.2083 | 2.2083
UG-18 | UG-18-S01 | P0646 | 2.2 | 2.249 | -3.9145 | -3.9145 | -1.1655 | -1.1655 | 17.47 | -3.9145 | -3.9145 | 3.2145 | 2.4145 | 0.8 | 8.1535 | Open cut | 0 | 2.4145 | 0.8 | 4.249 | 0 | 74.8102 | 3.5739 | 8.7396 | 0.48356 | 0.48356 | 2.2495 | 2.2495
UG-18 | UG-18-S01 | P0644 | 1.471 | 2.249 | -3.9145 | -3.9145 | -1.1655 | -1.1655 | 16.31 | -3.9145 | -3.9145 | 3.2145 | 2.4145 | 0.8 | 8.1535 | Open cut | 0 | 2.4145 | 0.8 | 4.249 | 0 | 50.0196 | 2.3896 | 5.8435 | 0.48356 | 0.48356 | 2.2495 | 2.2495
UG-18 | UG-18-S01 | P0643 | 0.68672 | 2.2058 | -3.8929 | -3.8929 | -1.1871 | -1.1871 | 15.87 | -3.8929 | -3.8929 | 3.1929 | 2.3929 | 0.8 | 8.0887 | Open cut | 0 | 2.3929 | 0.8 | 4.2058 | 0 | 23.0036 | 1.1007 | 2.6242 | 0.51591 | 0.51591 | 2.3164 | 2.3164
UG-18 | UG-18-S01 | P0642 | 0.68656 | 2.2058 | -3.8929 | -3.8929 | -1.1871 | -1.1871 | 15.68 | -3.8929 | -3.8929 | 3.1929 | 2.3929 | 0.8 | 8.0887 | Open cut | 0 | 2.3929 | 0.8 | 4.2058 | 0 | 22.9983 | 1.1005 | 2.6236 | 0.51591 | 0.51591 | 2.3164 | 2.3164
UG-18 | UG-18-S01 | P0641-01 | 0.95181 | 2.249 | -3.9145 | -3.9145 | -1.1655 | -1.1655 | 15.61 | -3.9145 | -3.9145 | 3.2145 | 2.4145 | 0.8 | 8.1535 | Open cut | 0 | 2.4145 | 0.8 | 4.249 | 0 | 32.3658 | 1.5462 | 3.7811 | 0.48355 | 0.48355 | 2.2495 | 2.2495
UG-18 | UG-18-S01 | P0641-02 | 0.51914 | 2.249 | -3.9145 | -3.9145 | -1.1655 | -1.1655 | 15.58 | -3.9145 | -3.9145 | 3.2145 | 2.4145 | 0.8 | 8.1535 | Open cut | 0 | 2.4145 | 0.8 | 4.249 | 0 | 17.653 | 0.84334 | 2.0623 | 0.48355 | 0.48355 | 2.2495 | 2.2495
UG-18 | UG-18-S02 | P0241-01 | 9.4809 | 2.2764 | -3.9282 | -4.044 | -1.1518 | -1.2676 | 15.53 | -4.044 | -3.9861 | 3.2861 | 2.544 | 0.8 | 8.4262 | Shoring | 9.4809 | 2.4861 | 0.8 | 4.2764 | 133.2312 | 0 | 15.5315 | 38.5864 | 0.46367 | 0.58251 | 2.2083 | 2.3272
UG-18 | UG-18-S02 | P0241-02 | 10 | 2.2764 | -4.044 | -4.1661 | -1.2676 | -1.3897 | 7.49 | -4.1661 | -4.1051 | 3.4051 | 2.6661 | 0.8 | 8.6704 | Shoring | 10 | 2.6051 | 0.8 | 4.2764 | 145.6138 | 0 | 16.382 | 40.6992 | 0.58251 | 0.70785 | 2.3272 | 2.4525
UG-18 | UG-18-S02 | P0241-03 | 4.9329 | 2.2764 | -4.1661 | -4.2264 | -1.3897 | -1.45 | 10.64 | -4.2264 | -4.1962 | 3.4962 | 2.7264 | 0.8 | 8.7909 | Shoring | 4.9329 | 2.6962 | 0.8 | 4.2764 | 73.7533 | 0 | 8.0811 | 20.0765 | 0.70785 | 0.76968 | 2.4525 | 2.5144
UG-18 | UG-18-S02 | P0640 | 3.3493 | 2.2764 | -4.2264 | -4.2673 | -1.45 | -1.4909 | 13.34 | -4.2673 | -4.2468 | 3.5468 | 2.7673 | 0.8 | 8.8728 | Shoring | 3.3493 | 2.7468 | 0.8 | 4.2764 | 50.8009 | 0 | 5.4868 | 13.6314 | 0.76968 | 0.81166 | 2.5144 | 2.5563
UG-18 | UG-18-S02 | P0639-01 | 1.7178 | 2.2764 | -4.2673 | -4.2883 | -1.4909 | -1.5119 | 15.47 | -4.2883 | -4.2778 | 3.5778 | 2.7883 | 0.8 | 8.9147 | Shoring | 1.7178 | 2.7778 | 0.8 | 4.2764 | 26.2826 | 0 | 2.8141 | 6.9914 | 0.81166 | 0.82656 | 2.5563 | 2.5712
UG-18 | UG-18-S02 | P0639-02 | 1.6327 | 2.2764 | -4.2883 | -4.3082 | -1.5119 | -1.5318 | 16.59 | -4.3082 | -4.2982 | 3.5982 | 2.8082 | 0.8 | 8.9546 | Shoring | 1.6327 | 2.7982 | 0.8 | 4.2764 | 25.1238 | 0 | 2.6748 | 6.6452 | 0.82656 | 0.83587 | 2.5712 | 2.5805
UG-18 | UG-18-S02 | P0079-01 | 8.3673 | 2.2764 | -4.3082 | -4.3082 | -1.5318 | -1.5318 | 17.74 | -4.3082 | -4.3082 | 3.6082 | 2.8082 | 0.8 | 8.9546 | Shoring | 8.3673 | 2.8082 | 0.8 | 4.2764 | 129.1081 | 0 | 13.7073 | 34.0544 | 0.83587 | 0.83587 | 2.5805 | 2.5805
UG-18 | UG-18-S02 | P0079-02 | 10 | 2.2764 | -4.3082 | -4.3082 | -1.5318 | -1.5318 | 20.57 | -4.3082 | -4.3082 | 3.6082 | 2.8082 | 0.8 | 8.9546 | Shoring | 10 | 2.8082 | 0.8 | 4.2764 | 154.3015 | 0 | 16.382 | 40.6996 | 0.83587 | 0.83587 | 2.5805 | 2.5805
UG-18 | UG-18-S02 | P0079-03 | 2.9156 | 2.2764 | -4.3082 | -4.3082 | -1.5318 | -1.5318 | 21.26 | -4.3082 | -4.3082 | 3.6082 | 2.8082 | 0.8 | 8.9546 | Shoring | 2.9156 | 2.8082 | 0.8 | 4.2764 | 44.988 | 0 | 4.7763 | 11.8663 | 0.83587 | 0.83587 | 2.5805 | 2.5805
UG-18 | UG-18-S02 | P0077 | 3.35 | 2.249 | -4.2945 | -4.2945 | -1.5455 | -1.5455 | 21.82 | -4.2945 | -4.2945 | 3.5945 | 2.7945 | 0.8 | 8.9135 | Shoring | 3.35 | 2.7945 | 0.8 | 4.249 | 51.1646 | 0 | 5.4421 | 13.308 | 0.85253 | 0.85253 | 2.6185 | 2.6185
UG-18 | UG-18-S02 | P0078 | 3.35 | 2.249 | -4.2945 | -4.2945 | -1.5455 | -1.5455 | 21.15 | -4.2945 | -4.2945 | 3.5945 | 2.7945 | 0.8 | 8.9135 | Shoring | 3.35 | 2.7945 | 0.8 | 4.249 | 51.1645 | 0 | 5.4421 | 13.3079 | 0.85253 | 0.85253 | 2.6185 | 2.6185
UG-18 | UG-18-S02 | P0084-01 | 0.38441 | 2.2764 | -4.3082 | -4.3082 | -1.5318 | -1.5318 | 20.98 | -4.3082 | -4.3082 | 3.6082 | 2.8082 | 0.8 | 8.9546 | Shoring | 0.38441 | 2.8082 | 0.8 | 4.2764 | 5.9315 | 0 | 0.62974 | 1.5645 | 0.83587 | 0.83587 | 2.5805 | 2.5805
UG-18 | UG-18-S02 | P0084-02 | 10 | 2.2764 | -4.3082 | -4.3082 | -1.5318 | -1.5318 | 17.67 | -4.3082 | -4.3082 | 3.6082 | 2.8082 | 0.8 | 8.9546 | Shoring | 10 | 2.8082 | 0.8 | 4.2764 | 154.301 | 0 | 16.382 | 40.6993 | 0.83587 | 0.83587 | 2.5805 | 2.5805
UG-18 | UG-18-S02 | P0084-03 | 10 | 2.2764 | -4.3082 | -4.3082 | -1.5318 | -1.5318 | 16.37 | -4.3082 | -4.3082 | 3.6082 | 2.8082 | 0.8 | 8.9546 | Shoring | 10 | 2.8082 | 0.8 | 4.2764 | 154.301 | 0 | 16.382 | 40.6993 | 0.83587 | 0.83587 | 2.5805 | 2.5805
UG-18 | UG-18-S02 | P0084-04 | 10 | 2.2764 | -4.3082 | -4.3082 | -1.5318 | -1.5318 | 16.36 | -4.3082 | -4.3082 | 3.6082 | 2.8082 | 0.8 | 8.9546 | Shoring | 10 | 2.8082 | 0.8 | 4.2764 | 154.301 | 0 | 16.382 | 40.6993 | 0.83587 | 0.83587 | 2.5805 | 2.5805
UG-18 | UG-18-S02 | P0084-05 | 10 | 2.2764 | -4.3082 | -4.3082 | -1.5318 | -1.5318 | 17.24 | -4.3082 | -4.3082 | 3.6082 | 2.8082 | 0.8 | 8.9546 | Shoring | 10 | 2.8082 | 0.8 | 4.2764 | 154.301 | 0 | 16.382 | 40.6993 | 0.83587 | 0.83587 | 2.5805 | 2.5805
UG-18 | UG-18-S02 | P0084-06 | 10 | 2.2764 | -4.3082 | -4.3082 | -1.5318 | -1.5318 | 20.17 | -4.3082 | -4.3082 | 3.6082 | 2.8082 | 0.8 | 8.9546 | Shoring | 10 | 2.8082 | 0.8 | 4.2764 | 154.301 | 0 | 16.382 | 40.6993 | 0.83587 | 0.83587 | 2.5805 | 2.5805
UG-18 | UG-18-S02 | P0084-07 | 10 | 2.2764 | -4.3082 | -4.3082 | -1.5318 | -1.5318 | 24.83 | -4.3082 | -4.3082 | 3.6082 | 2.8082 | 0.8 | 8.9546 | Shoring | 10 | 2.8082 | 0.8 | 4.2764 | 154.301 | 0 | 16.382 | 40.6993 | 0.83587 | 0.83587 | 2.5805 | 2.5805
UG-18 | UG-18-S02 | P0084-08 | 10 | 2.2764 | -4.3082 | -4.3082 | -1.5318 | -1.5318 | 21.26 | -4.3082 | -4.3082 | 3.6082 | 2.8082 | 0.8 | 8.9546 | Shoring | 10 | 2.8082 | 0.8 | 4.2764 | 154.301 | 0 | 16.382 | 40.6993 | 0.83587 | 0.83587 | 2.5805 | 2.5805
UG-18 | UG-18-S02 | P0084-09 | 10 | 2.2764 | -4.3082 | -4.3082 | -1.5318 | -1.5318 | 17.91 | -4.3082 | -4.3082 | 3.6082 | 2.8082 | 0.8 | 8.9546 | Shoring | 10 | 2.8082 | 0.8 | 4.2764 | 154.301 | 0 | 16.382 | 40.6993 | 0.83587 | 0.83587 | 2.5805 | 2.5805
UG-18 | UG-18-S02 | P0084-10 | 10 | 2.2764 | -4.3082 | -4.3082 | -1.5318 | -1.5318 | 16.55 | -4.3082 | -4.3082 | 3.6082 | 2.8082 | 0.8 | 8.9546 | Shoring | 10 | 2.8082 | 0.8 | 4.2764 | 154.301 | 0 | 16.382 | 40.6993 | 0.83587 | 0.83587 | 2.5805 | 2.5805
UG-18 | UG-18-S02 | P0084-11 | 10 | 2.2764 | -4.3082 | -4.3082 | -1.5318 | -1.5318 | 16.53 | -4.3082 | -4.3082 | 3.6082 | 2.8082 | 0.8 | 8.9546 | Shoring | 10 | 2.8082 | 0.8 | 4.2764 | 154.301 | 0 | 16.382 | 40.6993 | 0.83587 | 0.83587 | 2.5805 | 2.5805
UG-18 | UG-18-S02 | P0084-12 | 6.2213 | 2.2764 | -4.3082 | -4.3082 | -1.5318 | -1.5318 | 17.36 | -4.3082 | -4.3082 | 3.6082 | 2.8082 | 0.8 | 8.9546 | Shoring | 6.2213 | 2.8082 | 0.8 | 4.2764 | 95.9951 | 0 | 10.1917 | 25.3202 | 0.83587 | 0.83587 | 2.5805 | 2.5805
UG-18 | UG-18-S02 | P0071 | 3.35 | 2.249 | -4.2945 | -4.2945 | -1.5455 | -1.5455 | 18.93 | -4.2945 | -4.2945 | 3.5945 | 2.7945 | 0.8 | 8.9135 | Shoring | 3.35 | 2.7945 | 0.8 | 4.249 | 51.1645 | 0 | 5.4421 | 13.3079 | 0.85253 | 0.85253 | 2.6185 | 2.6185
UG-18 | UG-18-S02 | P0070-01 | 0.42871 | 2.249 | -4.2945 | -4.2945 | -1.5455 | -1.5455 | 19.91 | -4.2945 | -4.2945 | 3.5945 | 2.7945 | 0.8 | 8.9135 | Shoring | 0.42871 | 2.7945 | 0.8 | 4.249 | 6.5477 | 0 | 0.69644 | 1.7031 | 0.85253 | 0.85253 | 2.6185 | 2.6185
UG-18 | UG-18-S02 | P0070-02 | 2.9213 | 2.249 | -4.2945 | -4.2945 | -1.5455 | -1.5455 | 18.86 | -4.2945 | -4.2945 | 3.5945 | 2.7945 | 0.8 | 8.9135 | Shoring | 2.9213 | 2.7945 | 0.8 | 4.249 | 44.6168 | 0 | 4.7456 | 11.6049 | 0.85253 | 0.85253 | 2.6185 | 2.6185
UG-18 | UG-18-S02 | P0086-01 | 7.0787 | 2.2764 | -4.3082 | -4.3105 | -1.5318 | -1.5341 | 16.99 | -4.3105 | -4.3093 | 3.6093 | 2.8105 | 0.8 | 8.9591 | Shoring | 7.0787 | 2.8093 | 0.8 | 4.2764 | 109.2594 | 0 | 11.5963 | 28.8098 | 0.83587 | 0.83693 | 2.5805 | 2.5816
UG-18 | UG-18-S02 | P0086-02 | 10 | 2.2764 | -4.3105 | -4.3137 | -1.5341 | -1.5373 | 16.14 | -4.3137 | -4.3121 | 3.6121 | 2.8137 | 0.8 | 8.9655 | Shoring | 10 | 2.8121 | 0.8 | 4.2764 | 154.4659 | 0 | 16.382 | 40.6992 | 0.83693 | 0.83842 | 2.5816 | 2.5831
UG-18 | UG-18-S02 | P0086-03 | 7.5352 | 2.2764 | -4.3137 | -4.3161 | -1.5373 | -1.5397 | 16.15 | -4.3161 | -4.3149 | 3.6149 | 2.8161 | 0.8 | 8.9703 | Shoring | 7.5352 | 2.8149 | 0.8 | 4.2764 | 116.4833 | 0 | 12.3441 | 30.6677 | 0.83842 | 0.83954 | 2.5831 | 2.5842
UG-18 | UG-18-S02 | P0660-01 | 2.4648 | 2.2764 | -4.3161 | -4.3168 | -1.5397 | -1.5404 | 16.97 | -4.3168 | -4.3165 | 3.6165 | 2.8168 | 0.8 | 8.9719 | Shoring | 2.4648 | 2.8165 | 0.8 | 4.2764 | 38.1192 | 0 | 4.0378 | 10.0316 | 0.83954 | 0.83991 | 2.5842 | 2.5846
UG-18 | UG-18-S02 | P0660-02 | 0.8852 | 2.2764 | -4.3168 | -4.3171 | -1.5404 | -1.5407 | 17.5 | -4.3171 | -4.317 | 3.617 | 2.8171 | 0.8 | 8.9725 | Shoring | 0.8852 | 2.817 | 0.8 | 4.2764 | 13.692 | 0 | 1.4501 | 3.6027 | 0.83991 | 0.84004 | 2.5846 | 2.5847
UG-18 | UG-18-S02 | P0661 | 3.35 | 2.249 | -4.3034 | -4.3045 | -1.5544 | -1.5555 | 16.27 | -4.3045 | -4.304 | 3.604 | 2.8045 | 0.8 | 8.9335 | Shoring | 3.35 | 2.804 | 0.8 | 4.249 | 51.2993 | 0 | 5.4421 | 13.308 | 0.85675 | 0.85726 | 2.6227 | 2.6232
UG-18 | UG-18-S02 | P0270-01 | 5.7648 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 14.27 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 5.7648 | 2.8045 | 0.8 | 4.249 | 88.2908 | 0 | 9.3649 | 22.9009 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-18 | UG-18-S02 | P0270-02 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 12.51 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1551 | 0 | 16.245 | 39.7254 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-18 | UG-18-S02 | P0270-03 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 12.43 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1551 | 0 | 16.245 | 39.7254 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-18 | UG-18-S02 | P0270-04 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 13.11 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1551 | 0 | 16.245 | 39.7254 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-18 | UG-18-S02 | P0270-05 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 15.99 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1551 | 0 | 16.245 | 39.7254 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-18 | UG-18-S02 | P0270-06 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 20.75 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1551 | 0 | 16.245 | 39.7254 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-18 | UG-18-S02 | P0270-07 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 20.52 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1551 | 0 | 16.245 | 39.7254 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-18 | UG-18-S02 | P0270-08 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 16.86 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1551 | 0 | 16.245 | 39.7254 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-18 | UG-18-S02 | P0270-09 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 15.22 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1551 | 0 | 16.245 | 39.7254 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-18 | UG-18-S02 | P0270-10 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 15.15 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1551 | 0 | 16.245 | 39.7254 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-18 | UG-18-S02 | P0270-11 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 15.79 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1551 | 0 | 16.245 | 39.7254 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-18 | UG-18-S02 | P0270-12 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 18.52 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1551 | 0 | 16.245 | 39.7254 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-18 | UG-18-S02 | P0270-13 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 23.06 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1551 | 0 | 16.245 | 39.7254 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-18 | UG-18-S02 | P0270-14 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 99 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1551 | 0 | 16.245 | 39.7254 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-18 | UG-18-S02 | P0270-15 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 20.49 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1551 | 0 | 16.245 | 39.7254 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-18 | UG-18-S02 | P0270-16 | 10 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 14.69 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 10 | 2.8045 | 0.8 | 4.249 | 153.1551 | 0 | 16.245 | 39.7254 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-18 | UG-18-S02 | P0270-17 | 5.0609 | 2.249 | -4.3045 | -4.3045 | -1.5555 | -1.5555 | 13.73 | -4.3045 | -4.3045 | 3.6045 | 2.8045 | 0.8 | 8.9335 | Shoring | 5.0609 | 2.8045 | 0.8 | 4.249 | 77.5109 | 0 | 8.2215 | 20.1048 | 0.85726 | 0.85726 | 2.6232 | 2.6232
UG-19 | UG-19-S01 | P0014 | 0.81068 | 1.8626 | -4.0313 | -4.0313 | -1.6687 | -1.6687 | 11.67 | -4.0313 | -4.0313 | 3.3313 | 2.5313 | 0.8 | 8.1939 | Shoring | 0.81068 | 2.5313 | 0.8 | 3.8626 | 10.4314 | 0 | 1.1603 | 2.2089 | 1.0997 | 1.0997 | 3.232 | 3.232
UG-19 | UG-19-S01 | P0668 | 0.81471 | 1.8626 | -4.0313 | -4.0313 | -1.6687 | -1.6687 | 10.85 | -4.0313 | -4.0313 | 3.3313 | 2.5313 | 0.8 | 8.1939 | Shoring | 0.81471 | 2.5313 | 0.8 | 3.8626 | 10.4833 | 0 | 1.1661 | 2.2199 | 1.0997 | 1.0997 | 3.232 | 3.232
UG-19 | UG-19-S01 | P0669 | 0.8807 | 1.8626 | -4.0313 | -4.0313 | -1.6687 | -1.6687 | 10.08 | -4.0313 | -4.0313 | 3.3313 | 2.5313 | 0.8 | 8.1939 | Shoring | 0.8807 | 2.5313 | 0.8 | 3.8626 | 11.3324 | 0 | 1.2605 | 2.3997 | 1.0997 | 1.0997 | 3.232 | 3.232
UG-19 | UG-19-S02 | P0242-01 | 7.4939 | 1.8626 | -4.0313 | -4.0952 | -1.6687 | -1.7326 | 4.61 | -4.0952 | -4.0633 | 3.3633 | 2.5952 | 0.8 | 8.3217 | Shoring | 7.4939 | 2.5633 | 0.8 | 3.8626 | 97.3526 | 0 | 10.726 | 20.4191 | 1.0997 | 1.1362 | 3.232 | 3.2685
UG-19 | UG-19-S02 | P0242-02 | 10 | 1.8626 | -4.0952 | -4.1805 | -1.7326 | -1.8179 | 4.31 | -4.1805 | -4.1379 | 3.4379 | 2.6805 | 0.8 | 8.4923 | Shoring | 10 | 2.6379 | 0.8 | 3.8626 | 132.7904 | 0 | 14.313 | 27.2476 | 1.1362 | 1.1848 | 3.2685 | 3.3171
UG-19 | UG-19-S02 | P0242-03 | 10 | 1.8626 | -4.1805 | -4.2658 | -1.8179 | -1.9032 | 7.83 | -4.2658 | -4.2231 | 3.5231 | 2.7658 | 0.8 | 8.6629 | Shoring | 10 | 2.7231 | 0.8 | 3.8626 | 136.0846 | 0 | 14.313 | 27.2476 | 1.1848 | 1.2335 | 3.3171 | 3.3658
UG-19 | UG-19-S02 | P0242-04 | 1.4644 | 1.8626 | -4.2658 | -4.2783 | -1.9032 | -1.9157 | 12.7 | -4.2783 | -4.272 | 3.572 | 2.7783 | 0.8 | 8.6878 | Shoring | 1.4644 | 2.772 | 0.8 | 3.8626 | 20.2041 | 0 | 2.0959 | 3.99 | 1.2335 | 1.2406 | 3.3658 | 3.3729
UG-19 | UG-19-S02 | P0670 | 0.10869 | 1.841 | -4.2675 | -4.2684 | -1.9265 | -1.9274 | 13.42 | -4.2684 | -4.2679 | 3.5679 | 2.7684 | 0.8 | 8.6573 | Shoring | 0.10869 | 2.7679 | 0.8 | 3.841 | 1.4895 | 0 | 0.15439 | 0.28931 | 1.2614 | 1.262 | 3.4187 | 3.4193
UG-19 | UG-19-S02 | P0672 | 0.02969 | 1.8264 | -4.2611 | -4.2612 | -1.9347 | -1.9348 | 13.47 | -4.2612 | -4.2611 | 3.5611 | 2.7612 | 0.8 | 8.6356 | Shoring | 0.02969 | 2.7611 | 0.8 | 3.8264 | 0.40456 | 0 | 0.041958 | 0.077782 | 1.2763 | 1.2764 | 3.4509 | 3.451
UG-19 | UG-19-S02 | P0673 | 0.69459 | 1.8264 | -4.2612 | -4.2671 | -1.9348 | -1.9408 | 13.49 | -4.2671 | -4.2642 | 3.5642 | 2.7671 | 0.8 | 8.6475 | Shoring | 0.69459 | 2.7642 | 0.8 | 3.8264 | 9.4727 | 0 | 0.98159 | 1.8197 | 1.2764 | 1.2799 | 3.451 | 3.4544
UG-19 | UG-19-S02 | P0674 | 0.69469 | 1.8264 | -4.2671 | -4.2731 | -1.9408 | -1.9467 | 13.77 | -4.2731 | -4.2701 | 3.5701 | 2.7731 | 0.8 | 8.6593 | Shoring | 0.69469 | 2.7701 | 0.8 | 3.8264 | 9.4898 | 0 | 0.98173 | 1.82 | 1.2799 | 1.2833 | 3.4544 | 3.4579
UG-19 | UG-19-S03 | P0676 | 0.02982 | 1.841 | -4.2804 | -4.2805 | -1.9394 | -1.9395 | 13.92 | -4.2805 | -4.2804 | 3.5804 | 2.7805 | 0.8 | 8.6815 | Shoring | 0.02982 | 2.7804 | 0.8 | 3.841 | 0.4101 | 0 | 0.042359 | 0.079379 | 1.2689 | 1.269 | 3.4262 | 3.4263
UG-19 | UG-19-S03 | P0677 | 0.10826 | 1.841 | -4.2805 | -4.2805 | -1.9395 | -1.9395 | 13.92 | -4.2805 | -4.2805 | 3.5805 | 2.7805 | 0.8 | 8.6815 | Shoring | 0.10826 | 2.7805 | 0.8 | 3.841 | 1.4889 | 0 | 0.15379 | 0.28819 | 1.269 | 1.269 | 3.4263 | 3.4263
UG-19 | UG-19-S03 | P0774-01 | 6.8699 | 1.8626 | -4.2913 | -4.3255 | -1.9287 | -1.9629 | 13.94 | -4.3255 | -4.3084 | 3.6084 | 2.8255 | 0.8 | 8.7823 | Shoring | 6.8699 | 2.8084 | 0.8 | 3.8626 | 95.751 | 0 | 9.8328 | 18.7185 | 1.2481 | 1.2676 | 3.3804 | 3.3999
UG-19 | UG-19-S03 | P0774-02 | 10 | 1.8626 | -4.3255 | -4.3753 | -1.9629 | -2.0127 | 15.29 | -4.3753 | -4.3504 | 3.6504 | 2.8753 | 0.8 | 8.8819 | Shoring | 10 | 2.8504 | 0.8 | 3.8626 | 141.0003 | 0 | 14.3129 | 27.2471 | 1.2676 | 1.2961 | 3.3999 | 3.4284
UG-19 | UG-19-S03 | P0774-03 | 10 | 1.8626 | -4.3753 | -4.4251 | -2.0127 | -2.0626 | 13.16 | -4.4251 | -4.4002 | 3.7002 | 2.9251 | 0.8 | 8.9816 | Shoring | 10 | 2.9002 | 0.8 | 3.8626 | 142.9244 | 0 | 14.3129 | 27.2471 | 1.2961 | 1.3245 | 3.4284 | 3.4568
UG-19 | UG-19-S03 | P0774-04 | 10 | 1.8626 | -4.4251 | -4.475 | -2.0626 | -2.1124 | 13.15 | -4.475 | -4.45 | 3.75 | 2.975 | 0.8 | 9.0812 | Shoring | 10 | 2.95 | 0.8 | 3.8626 | 144.8485 | 0 | 14.3129 | 27.2471 | 1.3245 | 1.3529 | 3.4568 | 3.4852
UG-19 | UG-19-S03 | P0774-05 | 10 | 1.8626 | -4.475 | -4.5248 | -2.1124 | -2.1622 | 13.68 | -4.5248 | -4.4999 | 3.7999 | 3.0248 | 0.8 | 9.1808 | Shoring | 10 | 2.9999 | 0.8 | 3.8626 | 146.7727 | 0 | 14.3129 | 27.2471 | 1.3529 | 1.3813 | 3.4852 | 3.5136
UG-19 | UG-19-S03 | P0774-06 | 10 | 1.8626 | -4.5248 | -4.5746 | -2.1622 | -2.212 | 12.96 | -4.5746 | -4.5497 | 3.8497 | 3.0746 | 0.8 | 9.2805 | Shoring | 10 | 3.0497 | 0.8 | 3.8626 | 148.6968 | 0 | 14.3129 | 27.2471 | 1.3813 | 1.4098 | 3.5136 | 3.5421
UG-19 | UG-19-S03 | P0774-07 | 10 | 1.8626 | -4.5746 | -4.6244 | -2.212 | -2.2618 | 12.96 | -4.6244 | -4.5995 | 3.8995 | 3.1244 | 0.8 | 9.3801 | Shoring | 10 | 3.0995 | 0.8 | 3.8626 | 150.6209 | 0 | 14.3129 | 27.2471 | 1.4098 | 1.4382 | 3.5421 | 3.5705
UG-19 | UG-19-S03 | P0774-08 | 2.4079 | 1.8626 | -4.6244 | -4.6364 | -2.2618 | -2.2738 | 13.48 | -4.6364 | -4.6304 | 3.9304 | 3.1364 | 0.8 | 9.4041 | Shoring | 2.4079 | 3.1304 | 0.8 | 3.8626 | 36.5555 | 0 | 3.4464 | 6.5608 | 1.4382 | 1.445 | 3.5705 | 3.5773
UG-19 | UG-19-S03 | P0414 | 0.35973 | 1.841 | -4.6256 | -4.6274 | -2.2846 | -2.2864 | 13.67 | -4.6274 | -4.6265 | 3.9265 | 3.1274 | 0.8 | 9.3753 | Shoring | 0.35973 | 3.1265 | 0.8 | 3.841 | 5.4253 | 0 | 0.511 | 0.95757 | 1.4682 | 1.4693 | 3.6255 | 3.6266
UG-19 | UG-19-S03 | P0413 | 1.1021 | 1.7009 | -4.5573 | -4.5628 | -2.3565 | -2.3619 | 13.73 | -4.5628 | -4.5601 | 3.8601 | 3.0628 | 0.8 | 9.1761 | Shoring | 1.1021 | 3.0601 | 0.8 | 3.7009 | 15.7446 | 0 | 1.4884 | 2.5042 | 1.6341 | 1.6375 | 3.9691 | 3.9725
UG-19 | UG-19-S03 | P0412 | 1.1021 | 1.7009 | -4.5628 | -4.5683 | -2.362 | -2.3674 | 14.37 | -4.5683 | -4.5656 | 3.8656 | 3.0683 | 0.8 | 9.187 | Shoring | 1.1021 | 3.0656 | 0.8 | 3.7009 | 15.7659 | 0 | 1.4882 | 2.504 | 1.6375 | 1.641 | 3.9726 | 3.976
UG-19 | UG-19-S03 | P0411 | 0.36008 | 1.841 | -4.6384 | -4.6402 | -2.2974 | -2.2992 | 15.46 | -4.6402 | -4.6393 | 3.9393 | 3.1402 | 0.8 | 9.4008 | Shoring | 0.36008 | 3.1393 | 0.8 | 3.841 | 5.4483 | 0 | 0.51149 | 0.9585 | 1.4756 | 1.4766 | 3.6329 | 3.6339
UG-19 | UG-19-S03 | P0010-01 | 4.6681 | 1.8626 | -4.651 | -4.6742 | -2.2884 | -2.3116 | 15.81 | -4.6742 | -4.6626 | 3.9626 | 3.1742 | 0.8 | 9.4797 | Shoring | 4.6681 | 3.1626 | 0.8 | 3.8626 | 71.4495 | 0 | 6.6814 | 12.7195 | 1.4533 | 1.4666 | 3.5856 | 3.5989
UG-19 | UG-19-S03 | P0010-02 | 1.4214 | 1.8626 | -4.6742 | -4.6813 | -2.3116 | -2.3187 | 20.36 | -4.6813 | -4.6778 | 3.9778 | 3.1813 | 0.8 | 9.4939 | Shoring | 1.4214 | 3.1778 | 0.8 | 3.8626 | 21.8387 | 0 | 2.0344 | 3.8729 | 1.4666 | 1.4707 | 3.5989 | 3.6029
UG-19 | UG-19-S03 | P0011 | 3.7613 | 1.8626 | -4.6813 | -4.6813 | -2.3187 | -2.3187 | 21.75 | -4.6813 | -4.6813 | 3.9813 | 3.1813 | 0.8 | 9.4939 | Shoring | 3.7613 | 3.1813 | 0.8 | 3.8626 | 57.8413 | 0 | 5.3835 | 10.2486 | 1.4707 | 1.4707 | 3.6029 | 3.6029
UG-19 | UG-19-S03 | P0675 | 0.02982 | 1.8264 | -4.2731 | -4.2732 | -1.9467 | -1.9468 | 13.92 | -4.2732 | -4.2731 | 3.5731 | 2.7732 | 0.8 | 8.6596 | Shoring | 0.02982 | 2.7731 | 0.8 | 3.8264 | 0.4077 | 0 | 0.042141 | 0.078123 | 1.2833 | 1.2834 | 3.4579 | 3.4579
UG-19 | UG-19-S02 | P0671 | 0.02969 | 1.841 | -4.2684 | -4.2685 | -1.9274 | -1.9275 | 13.47 | -4.2685 | -4.2685 | 3.5685 | 2.7685 | 0.8 | 8.6575 | Shoring | 0.02969 | 2.7685 | 0.8 | 3.841 | 0.40694 | 0 | 0.042175 | 0.079033 | 1.262 | 1.262 | 3.4193 | 3.4193
UG-20 | UG-20-S01 | P0015 | 1.0228 | 1.8626 | -4.3113 | -4.3113 | -1.9487 | -1.9487 | 11.77 | -4.3113 | -4.3113 | 3.6113 | 2.8113 | 0.8 | 8.7539 | Shoring | 1.0228 | 2.8113 | 0.8 | 3.8626 | 14.2663 | 0 | 1.4639 | 2.7867 | 1.2595 | 1.2595 | 3.3918 | 3.3918
UG-20 | UG-20-S01 | P0678 | 0.81705 | 1.8626 | -4.3113 | -4.3113 | -1.9487 | -1.9487 | 10.98 | -4.3113 | -4.3113 | 3.6113 | 2.8113 | 0.8 | 8.7539 | Shoring | 0.81705 | 2.8113 | 0.8 | 3.8626 | 11.397 | 0 | 1.1694 | 2.2263 | 1.2595 | 1.2595 | 3.3918 | 3.3918
UG-20 | UG-20-S01 | P0679 | 0.87866 | 1.8626 | -4.3113 | -4.3113 | -1.9487 | -1.9487 | 10.35 | -4.3113 | -4.3113 | 3.6113 | 2.8113 | 0.8 | 8.7539 | Shoring | 0.87866 | 2.8113 | 0.8 | 3.8626 | 12.2564 | 0 | 1.2576 | 2.3941 | 1.2595 | 1.2595 | 3.3918 | 3.3918
UG-20 | UG-20-S02 | P0243-01 | 7.2815 | 1.8626 | -4.3113 | -4.3113 | -1.9487 | -1.9487 | 7.46 | -4.3113 | -4.3113 | 3.6113 | 2.8113 | 0.8 | 8.7539 | Shoring | 7.2815 | 2.8113 | 0.8 | 3.8626 | 101.5703 | 0 | 10.4221 | 19.8405 | 1.2595 | 1.2595 | 3.3918 | 3.3918
UG-20 | UG-20-S02 | P0243-02 | 10 | 1.8626 | -4.3113 | -4.3113 | -1.9487 | -1.9487 | 7.46 | -4.3113 | -4.3113 | 3.6113 | 2.8113 | 0.8 | 8.7539 | Shoring | 10 | 2.8113 | 0.8 | 3.8626 | 139.4901 | 0 | 14.313 | 27.2477 | 1.2595 | 1.2595 | 3.3918 | 3.3918
UG-20 | UG-20-S02 | P0243-03 | 10 | 1.8626 | -4.3113 | -4.3113 | -1.9487 | -1.9487 | 11.45 | -4.3113 | -4.3113 | 3.6113 | 2.8113 | 0.8 | 8.7539 | Shoring | 10 | 2.8113 | 0.8 | 3.8626 | 139.4901 | 0 | 14.313 | 27.2477 | 1.2595 | 1.2595 | 3.3918 | 3.3918
UG-20 | UG-20-S02 | P0243-04 | 2.1867 | 1.8626 | -4.3113 | -4.3113 | -1.9487 | -1.9487 | 16.33 | -4.3113 | -4.3113 | 3.6113 | 2.8113 | 0.8 | 8.7539 | Shoring | 2.1867 | 2.8113 | 0.8 | 3.8626 | 30.5023 | 0 | 3.1298 | 5.9582 | 1.2595 | 1.2595 | 3.3918 | 3.3918
UG-20 | UG-20-S02 | P0680 | 0.1366 | 1.841 | -4.3005 | -4.3005 | -1.9595 | -1.9595 | 17.4 | -4.3005 | -4.3005 | 3.6005 | 2.8005 | 0.8 | 8.7215 | Shoring | 0.1366 | 2.8005 | 0.8 | 3.841 | 1.8892 | 0 | 0.19405 | 0.36363 | 1.2805 | 1.2805 | 3.4378 | 3.4378
UG-20 | UG-20-S02 | P0681 | 0.69625 | 1.8263 | -4.2932 | -4.2932 | -1.9668 | -1.9668 | 17.48 | -4.2932 | -4.2932 | 3.5932 | 2.7932 | 0.8 | 8.6995 | Shoring | 0.69625 | 2.7932 | 0.8 | 3.8263 | 9.5724 | 0 | 0.98391 | 1.8239 | 1.2951 | 1.2951 | 3.4697 | 3.4697
UG-20 | UG-20-S02 | P0682 | 0.69637 | 1.8263 | -4.2932 | -4.2932 | -1.9668 | -1.9668 | 17.78 | -4.2932 | -4.2932 | 3.5932 | 2.7932 | 0.8 | 8.6995 | Shoring | 0.69637 | 2.7932 | 0.8 | 3.8263 | 9.574 | 0 | 0.98408 | 1.8242 | 1.2951 | 1.2951 | 3.4697 | 3.4697
UG-20 | UG-20-S02 | P0683 | 0.1365 | 1.841 | -4.3005 | -4.3005 | -1.9595 | -1.9595 | 17.94 | -4.3005 | -4.3005 | 3.6005 | 2.8005 | 0.8 | 8.7215 | Shoring | 0.1365 | 2.8005 | 0.8 | 3.841 | 1.8878 | 0 | 0.1939 | 0.36336 | 1.2805 | 1.2805 | 3.4378 | 3.4378
UG-20 | UG-20-S02 | P0775-01 | 6.1476 | 1.8625 | -4.3113 | -4.3346 | -1.9487 | -1.972 | 17.96 | -4.3346 | -4.3229 | 3.6229 | 2.8346 | 0.8 | 8.8004 | Shoring | 6.1476 | 2.8229 | 0.8 | 3.8626 | 86.0273 | 0 | 8.7989 | 16.7498 | 1.2595 | 1.2728 | 3.3919 | 3.4052
UG-20 | UG-20-S02 | P0775-02 | 10 | 1.8625 | -4.3346 | -4.3724 | -1.972 | -2.0099 | 18.84 | -4.3724 | -4.3535 | 3.6535 | 2.8724 | 0.8 | 8.8761 | Shoring | 10 | 2.8535 | 0.8 | 3.8626 | 141.1181 | 0 | 14.3128 | 27.2462 | 1.2728 | 1.2944 | 3.4052 | 3.4268
UG-20 | UG-20-S02 | P0775-03 | 10 | 1.8625 | -4.3724 | -4.4103 | -2.0099 | -2.0478 | 16.82 | -4.4103 | -4.3914 | 3.6914 | 2.9103 | 0.8 | 8.9519 | Shoring | 10 | 2.8914 | 0.8 | 3.8626 | 142.5811 | 0 | 14.3127 | 27.2462 | 1.2944 | 1.3161 | 3.4268 | 3.4484
UG-20 | UG-20-S02 | P0775-04 | 10 | 1.8625 | -4.4103 | -4.4482 | -2.0478 | -2.0856 | 16.79 | -4.4482 | -4.4292 | 3.7292 | 2.9482 | 0.8 | 9.0276 | Shoring | 10 | 2.9292 | 0.8 | 3.8626 | 144.0441 | 0 | 14.3128 | 27.2462 | 1.3161 | 1.3377 | 3.4484 | 3.47
UG-20 | UG-20-S02 | P0775-05 | 10 | 1.8625 | -4.4482 | -4.4861 | -2.0856 | -2.1235 | 17.19 | -4.4861 | -4.4671 | 3.7671 | 2.9861 | 0.8 | 9.1034 | Shoring | 10 | 2.9671 | 0.8 | 3.8626 | 145.507 | 0 | 14.3127 | 27.2462 | 1.3377 | 1.3593 | 3.47 | 3.4916
UG-20 | UG-20-S02 | P0775-06 | 10 | 1.8625 | -4.4861 | -4.5239 | -2.1235 | -2.1614 | 16.25 | -4.5239 | -4.505 | 3.805 | 3.0239 | 0.8 | 9.1791 | Shoring | 10 | 3.005 | 0.8 | 3.8626 | 146.97 | 0 | 14.3128 | 27.2462 | 1.3593 | 1.3809 | 3.4916 | 3.5132
UG-20 | UG-20-S02 | P0775-07 | 9.0397 | 1.8625 | -4.5239 | -4.5582 | -2.1614 | -2.1956 | 16.25 | -4.5582 | -4.5411 | 3.8411 | 3.0582 | 0.8 | 9.2476 | Shoring | 9.0397 | 3.0411 | 0.8 | 3.8626 | 134.1149 | 0 | 12.9382 | 24.6296 | 1.3809 | 1.4005 | 3.5132 | 3.5328
UG-20 | UG-20-S02 | P0418 | 0.35974 | 1.841 | -4.5474 | -4.5488 | -2.2064 | -2.2078 | 16.68 | -4.5488 | -4.5481 | 3.8481 | 3.0488 | 0.8 | 9.218 | Shoring | 0.35974 | 3.0481 | 0.8 | 3.841 | 5.3171 | 0 | 0.51101 | 0.9576 | 1.4231 | 1.4239 | 3.5804 | 3.5812
UG-20 | UG-20-S02 | P0417-01 | 0.6006 | 1.7009 | -4.4787 | -4.481 | -2.2778 | -2.2801 | 16.68 | -4.481 | -4.4798 | 3.7798 | 2.981 | 0.8 | 9.0124 | Shoring | 0.6006 | 2.9798 | 0.8 | 3.7009 | 8.4016 | 0 | 0.81107 | 1.3646 | 1.5849 | 1.5864 | 3.92 | 3.9214
UG-20 | UG-20-S02 | P0417-02 | 0.50153 | 1.7009 | -4.481 | -4.4829 | -2.2801 | -2.282 | 16.89 | -4.4829 | -4.4819 | 3.7819 | 2.9829 | 0.8 | 9.0162 | Shoring | 0.50153 | 2.9819 | 0.8 | 3.7009 | 7.0197 | 0 | 0.67729 | 1.1396 | 1.5864 | 1.5876 | 3.9214 | 3.9226
UG-20 | UG-20-S02 | P0416 | 1.1021 | 1.7009 | -4.4829 | -4.487 | -2.282 | -2.2862 | 17.08 | -4.487 | -4.485 | 3.785 | 2.987 | 0.8 | 9.0245 | Shoring | 1.1021 | 2.985 | 0.8 | 3.7009 | 15.4371 | 0 | 1.4882 | 2.504 | 1.5876 | 1.5902 | 3.9226 | 3.9252
UG-20 | UG-20-S02 | P0415 | 0.36008 | 1.841 | -4.5571 | -4.5585 | -2.2161 | -2.2175 | 18.1 | -4.5585 | -4.5578 | 3.8578 | 3.0585 | 0.8 | 9.2374 | Shoring | 0.36008 | 3.0578 | 0.8 | 3.841 | 5.3356 | 0 | 0.51149 | 0.9585 | 1.4287 | 1.4295 | 3.586 | 3.5868
UG-20 | UG-20-S02 | P0012 | 3.1754 | 1.8626 | -4.5693 | -4.5813 | -2.2067 | -2.2187 | 18.46 | -4.5813 | -4.5753 | 3.8753 | 3.0813 | 0.8 | 9.2939 | Shoring | 3.1754 | 3.0753 | 0.8 | 3.8626 | 47.531 | 0 | 4.5449 | 8.6521 | 1.4067 | 1.4136 | 3.539 | 3.5459
UG-20 | UG-20-S02 | P0013 | 4.5863 | 1.8626 | -4.5813 | -4.5813 | -2.2187 | -2.2187 | 21.64 | -4.5813 | -4.5813 | 3.8813 | 3.0813 | 0.8 | 9.2939 | Shoring | 4.5863 | 3.0813 | 0.8 | 3.8626 | 68.7573 | 0 | 6.5644 | 12.4965 | 1.4136 | 1.4136 | 3.5459 | 3.5459
UG-21 | UG-21-S01 | P0178-01 | 10 | 2.2764 | -6.2382 | -6.2382 | -3.4618 | -3.4618 | 33.79 | -6.2382 | -6.2382 | 5.5382 | 4.7382 | 0.8 | 12.8146 | Shoring | 10 | 4.7382 | 0.8 | 4.2764 | 236.8354 | 0 | 16.382 | 40.6992 | 1.7371 | 1.7371 | 3.4818 | 3.4818
UG-21 | UG-21-S01 | P0178-02 | 2.2026 | 2.2764 | -6.2382 | -6.2382 | -3.4618 | -3.4618 | 33.22 | -6.2382 | -6.2382 | 5.5382 | 4.7382 | 0.8 | 12.8146 | Shoring | 2.2026 | 4.7382 | 0.8 | 4.2764 | 52.1651 | 0 | 3.6083 | 8.9644 | 1.7371 | 1.7371 | 3.4818 | 3.4818
UG-22 | UG-22-S01 | P0177-01 | 10 | 2.2764 | -6.2382 | -6.2382 | -3.4618 | -3.4618 | 30.68 | -6.2382 | -6.2382 | 5.5382 | 4.7382 | 0.8 | 12.8146 | Shoring | 10 | 4.7382 | 0.8 | 4.2764 | 236.8354 | 0 | 16.382 | 40.6992 | 1.7371 | 1.7371 | 3.4818 | 3.4818
UG-22 | UG-22-S01 | P0177-02 | 2.2104 | 2.2764 | -6.2382 | -6.2382 | -3.4618 | -3.4618 | 30.08 | -6.2382 | -6.2382 | 5.5382 | 4.7382 | 0.8 | 12.8146 | Shoring | 2.2104 | 4.7382 | 0.8 | 4.2764 | 52.3499 | 0 | 3.6211 | 8.9961 | 1.7371 | 1.7371 | 3.4818 | 3.4818
UG-23 | UG-23-S01 | P0051 | 8.7967 | 0.63 | -5.075 | -5.075 | -3.945 | -3.945 | 17.55 | -5.075 | -5.075 | 4.375 | 3.575 | 0.8 | 9.665 | Shoring | 8.7967 | 3.575 | 0.8 | 2.63 | 101.2169 | 0 | 7.1693 | 2.7421 | 7.0921 | 7.0921 | 13.3962 | 13.3962
UG-23 | UG-23-S01 | P0148-01 | 1.2033 | 0.63 | -5.075 | -5.075 | -3.945 | -3.945 | 25.69 | -5.075 | -5.075 | 4.375 | 3.575 | 0.8 | 9.665 | Shoring | 1.2033 | 3.575 | 0.8 | 2.63 | 13.8453 | 0 | 0.98068 | 0.37509 | 7.0921 | 7.0921 | 13.3962 | 13.3962
UG-23 | UG-23-S01 | P0148-02 | 0.09171 | 0.63 | -5.075 | -5.075 | -3.945 | -3.945 | 25.6 | -5.075 | -5.075 | 4.375 | 3.575 | 0.8 | 9.665 | Shoring | 0.09171 | 3.575 | 0.8 | 2.63 | 1.0552 | 0 | 0.074743 | 0.028588 | 7.0921 | 7.0921 | 13.3962 | 13.3962
UG-23 | UG-23-S01 | P0149 | 1.295 | 0.63 | -5.075 | -5.075 | -3.945 | -3.945 | 25.6 | -5.075 | -5.075 | 4.375 | 3.575 | 0.8 | 9.665 | Shoring | 1.295 | 3.575 | 0.8 | 2.63 | 14.9006 | 0 | 1.0554 | 0.40369 | 7.092 | 7.092 | 13.396 | 13.396
UG-23 | UG-23-S02 | P0097-01 | 3.6133 | 0.63 | -5.075 | -5.075 | -3.945 | -3.945 | 25.9 | -5.075 | -5.075 | 4.375 | 3.575 | 0.8 | 9.665 | Shoring | 3.6133 | 3.575 | 0.8 | 2.63 | 41.5753 | 0 | 2.9448 | 1.1263 | 7.0921 | 7.0921 | 13.3962 | 13.3962
UG-23 | UG-23-S03 | P0097-02 | 0.1077 | 0.63 | -5.075 | -5.075 | -3.945 | -3.945 | 9.14 | -5.075 | -5.075 | 4.375 | 3.575 | 0.8 | 9.665 | Shoring | 0.1077 | 3.575 | 0.8 | 2.63 | 1.2392 | 0 | 0.087776 | 0.033573 | 7.0921 | 7.0921 | 13.3962 | 13.3962
UG-23 | UG-23-S03 | P0150 | 1.295 | 0.62999 | -5.075 | -5.075 | -3.945 | -3.945 | 9.14 | -5.075 | -5.075 | 4.375 | 3.575 | 0.8 | 9.665 | Shoring | 1.295 | 3.575 | 0.8 | 2.63 | 14.9005 | 0 | 1.0554 | 0.40367 | 7.0921 | 7.0921 | 13.3963 | 13.3963
UG-23 | UG-23-S03 | P0151 | 1.295 | 0.63 | -5.075 | -5.075 | -3.945 | -3.945 | 9.14 | -5.075 | -5.075 | 4.375 | 3.575 | 0.8 | 9.665 | Shoring | 1.295 | 3.575 | 0.8 | 2.63 | 14.9006 | 0 | 1.0554 | 0.40368 | 7.0921 | 7.0921 | 13.3962 | 13.3962
UG-23 | UG-23-S03 | P0307-01 | 2.3023 | 0.63 | -5.075 | -5.075 | -3.945 | -3.945 | 10.44 | -5.075 | -5.075 | 4.375 | 3.575 | 0.8 | 9.665 | Shoring | 2.3023 | 3.575 | 0.8 | 2.63 | 26.4908 | 0 | 1.8764 | 0.71768 | 7.092 | 7.092 | 13.3961 | 13.3961
UG-23 | UG-23-S03 | P0307-02 | 10 | 0.63 | -5.075 | -5.075 | -3.945 | -3.945 | 12.74 | -5.075 | -5.075 | 4.375 | 3.575 | 0.8 | 9.665 | Shoring | 10 | 3.575 | 0.8 | 2.63 | 115.0624 | 0 | 8.15 | 3.1172 | 7.092 | 7.092 | 13.3961 | 13.3961
UG-23 | UG-23-S03 | P0307-03 | 5 | 0.63 | -5.075 | -5.075 | -3.945 | -3.945 | 13.35 | -5.075 | -5.075 | 4.375 | 3.575 | 0.8 | 9.665 | Shoring | 5 | 3.575 | 0.8 | 2.63 | 57.5312 | 0 | 4.075 | 1.5586 | 7.092 | 7.092 | 13.3961 | 13.3961
UG-23 | UG-23-S04 | P0307-04 | 5 | 0.63 | -5.075 | -5.075 | -3.945 | -3.945 | 11.78 | -5.075 | -5.075 | 4.375 | 3.575 | 0.8 | 9.665 | Shoring | 5 | 3.575 | 0.8 | 2.63 | 57.5312 | 0 | 4.075 | 1.5586 | 7.092 | 7.092 | 13.3961 | 13.3961
UG-23 | UG-23-S04 | P0307-05 | 10 | 0.63 | -5.075 | -5.075 | -3.945 | -3.945 | 9.12 | -5.075 | -5.075 | 4.375 | 3.575 | 0.8 | 9.665 | Shoring | 10 | 3.575 | 0.8 | 2.63 | 115.0624 | 0 | 8.15 | 3.1172 | 7.092 | 7.092 | 13.3961 | 13.3961
UG-23 | UG-23-S04 | P0307-06 | 8 | 0.63 | -5.075 | -5.075 | -3.945 | -3.945 | 7.82 | -5.075 | -5.075 | 4.375 | 3.575 | 0.8 | 9.665 | Shoring | 8 | 3.575 | 0.8 | 2.63 | 92.0499 | 0 | 6.52 | 2.4938 | 7.092 | 7.092 | 13.3961 | 13.3961
UG-23 | UG-23-S05 | P0307-07 | 2 | 0.63 | -5.075 | -5.075 | -3.945 | -3.945 | 7.83 | -5.075 | -5.075 | 4.375 | 3.575 | 0.8 | 9.665 | Shoring | 2 | 3.575 | 0.8 | 2.63 | 23.0125 | 0 | 1.63 | 0.62345 | 7.092 | 7.092 | 13.3961 | 13.3961
UG-23 | UG-23-S05 | P0307-08 | 10 | 0.63 | -5.075 | -5.075 | -3.945 | -3.945 | 7.83 | -5.075 | -5.075 | 4.375 | 3.575 | 0.8 | 9.665 | Shoring | 10 | 3.575 | 0.8 | 2.63 | 115.0624 | 0 | 8.15 | 3.1172 | 7.092 | 7.092 | 13.3961 | 13.3961
UG-23 | UG-23-S05 | P0307-09 | 10 | 0.63 | -5.075 | -5.075 | -3.945 | -3.945 | 12.59 | -5.075 | -5.075 | 4.375 | 3.575 | 0.8 | 9.665 | Shoring | 10 | 3.575 | 0.8 | 2.63 | 115.0624 | 0 | 8.15 | 3.1172 | 7.092 | 7.092 | 13.3961 | 13.3961
UG-23 | UG-23-S05 | P0307-10 | 6.4549 | 0.63 | -5.075 | -5.075 | -3.945 | -3.945 | 12.7 | -5.075 | -5.075 | 4.375 | 3.575 | 0.8 | 9.665 | Shoring | 6.4549 | 3.575 | 0.8 | 2.63 | 74.2714 | 0 | 5.2607 | 2.0121 | 7.092 | 7.092 | 13.3961 | 13.3961
UG-23 | UG-23-S05 | P0664 | 0.17481 | 0.63 | -5.075 | -4.9447 | -3.945 | -3.8147 | 12.52 | -5.075 | -5.0098 | 4.3098 | 3.575 | 0.8 | 9.665 | Shoring | 0.17481 | 3.5098 | 0.8 | 2.63 | 1.9815 | 0 | 0.14247 | 0.054493 | 7.0919 | 6.8721 | 13.396 | 13.1761
UG-23 | UG-23-S05 | P0667 | 0.84296 | 0.6179 | -4.9386 | -4.6244 | -3.8207 | -3.5065 | 11.69 | -4.9386 | -4.7815 | 4.0815 | 3.4386 | 0.8 | 9.3862 | Shoring | 0.84296 | 3.2815 | 0.8 | 2.6179 | 9.007 | 0 | 0.68191 | 0.25277 | 7.0172 | 6.4766 | 13.4447 | 12.9042
UG-23 | UG-23-S05 | P0662 | 0.12363 | 0.63 | -4.6305 | -4.5383 | -3.5005 | -3.4083 | 11.56 | -4.6305 | -4.5844 | 3.8844 | 3.1305 | 0.8 | 8.776 | Shoring | 0.12363 | 3.0844 | 0.8 | 2.63 | 1.263 | 0 | 0.10076 | 0.038539 | 6.3419 | 6.1864 | 12.646 | 12.4905
UG-23 | UG-23-S05 | P0665 | 0.12363 | 0.63 | -4.5383 | -4.4462 | -3.4083 | -3.3162 | 11.44 | -4.5383 | -4.4922 | 3.7922 | 3.0383 | 0.8 | 8.5916 | Shoring | 0.12363 | 2.9922 | 0.8 | 2.63 | 1.233 | 0 | 0.10075 | 0.038537 | 6.1865 | 6.031 | 12.4906 | 12.3351
UG-23 | UG-23-S05 | P0306 | 1.9926 | 0.63 | -4.4462 | -2.9607 | -3.3162 | -1.8307 | 9.46 | -4.4462 | -3.7034 | 3.0034 | 2.9462 | 0.8 | 8.4073 | Shoring | 1.9926 | 2.2034 | 0.8 | 2.63 | 15.7398 | 0 | 1.624 | 0.62116 | 6.0309 | 3.5246 | 12.335 | 9.8286
UG-23 | UG-23-S06 | P0422-01 | 0.28747 | 0.63 | -2.9607 | -2.7464 | -1.8307 | -1.6164 | 9.18 | -2.9607 | -2.8536 | 2.1536 | 1.4607 | 0.8 | 5.4364 | Open cut | 0 | 1.3536 | 0.8 | 2.63 | 0 | 4.2027 | 0.23429 | 0.089613 | 3.5246 | 3.163 | 9.8286 | 9.4671
UG-23 | UG-23-S06 | P0422-02 | 0.69858 | 0.63 | -2.7464 | -2.2256 | -1.6164 | -1.0956 | 8.49 | -2.7464 | -2.486 | 1.786 | 1.2464 | 0.8 | 5.0078 | Open cut | 0 | 0.98603 | 0.8 | 2.63 | 0 | 7.5147 | 0.56934 | 0.21777 | 3.163 | 1.4671 | 9.4671 | 7.7712
UG-23 | UG-23-S06 | P0423 | 0.34963 | 0.63 | -2.2256 | -1.965 | -1.0956 | -0.835 | 8.14 | -2.2256 | -2.0953 | 1.3953 | 0.72564 | 0.8 | 3.9663 | Open cut | 0 | 0.59532 | 0.8 | 2.63 | 0 | 2.5325 | 0.28495 | 0.10899 | 1.4671 | 99 | 7.7712 | 99
UG-23 | UG-23-S06 | P0304 | 2.6015 | 0.63 | -1.965 | -1.965 | -0.835 | -0.835 | 5.59 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 16.1487 | 2.1202 | 0.81096 | 99 | 99 | 99 | 99
UG-23 | UG-23-S06 | P0425 | 1.2951 | 0.63 | -1.965 | -1.965 | -0.835 | -0.835 | 4.34 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 8.0389 | 1.0555 | 0.4037 | 99 | 99 | 99 | 99
UG-23 | UG-23-S06 | P0424 | 1.3054 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 4.34 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 8.1034 | 1.0639 | 0.40693 | 99 | 99 | 99 | 99
UG-23 | UG-23-S06 | P0152-01 | 3.7498 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 4.88 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 23.2762 | 3.056 | 1.1689 | 99 | 99 | 99 | 99
UG-23 | UG-23-S06 | P0152-02 | 5.8356 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 7.57 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 36.2233 | 4.7559 | 1.819 | 99 | 99 | 99 | 99
UG-23 | UG-23-S06 | P0442 | 0.74099 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 9.27 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 4.5996 | 0.6039 | 0.23098 | 99 | 99 | 99 | 99
UG-23 | UG-23-S06 | P0443 | 0.741 | 0.63 | -1.965 | -1.965 | -0.835 | -0.835 | 8.96 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 4.5997 | 0.60392 | 0.23099 | 99 | 99 | 99 | 99
UG-23 | UG-23-S06 | P0163-01 | 2.6825 | 0.63 | -1.965 | -1.965 | -0.835 | -0.835 | 7.89 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 16.6511 | 2.1862 | 0.83619 | 99 | 99 | 99 | 99
UG-23 | UG-23-S06 | P0163-02 | 4.5289 | 0.63 | -1.965 | -1.965 | -0.835 | -0.835 | 6.06 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 28.1126 | 3.691 | 1.4118 | 99 | 99 | 99 | 99
UG-23 | UG-23-S06 | P0445 | 0.74121 | 0.63 | -1.965 | -1.965 | -0.835 | -0.835 | 5.32 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 4.601 | 0.60409 | 0.23106 | 99 | 99 | 99 | 99
UG-23 | UG-23-S06 | P0444 | 0.74085 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 4.79 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 4.5987 | 0.60379 | 0.23094 | 99 | 99 | 99 | 99
UG-23 | UG-23-S06 | P0153-01 | 3.9891 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 1.95 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Shoring | 3.9891 | 0.465 | 0.8 | 2.63 | 13.2713 | 0 | 3.2511 | 1.2435 | 99 | 99 | 99 | 99
UG-23 | UG-23-S06 | P0153-02 | 10 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 0 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Shoring | 10 | 0.465 | 0.8 | 2.63 | 33.2694 | 0 | 8.15 | 3.1172 | 99 | 99 | 99 | 99
UG-23 | UG-23-S06 | P0153-03 | 5.1 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 3.58 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 31.6576 | 4.1565 | 1.5898 | 99 | 99 | 99 | 99
UG-23 | UG-23-S07 | P0153-04 | 4.9 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 7.21 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 30.4161 | 3.9935 | 1.5274 | 99 | 99 | 99 | 99
UG-23 | UG-23-S07 | P0153-05 | 10 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 9.67 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 62.0737 | 8.15 | 3.1172 | 99 | 99 | 99 | 99
UG-23 | UG-23-S07 | P0153-06 | 1.1 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 12.25 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 6.8281 | 0.8965 | 0.34289 | 99 | 99 | 99 | 99
UG-23 | UG-23-S08 | P0153-07 | 8.9 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 12.2 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 55.2456 | 7.2535 | 2.7743 | 99 | 99 | 99 | 99
UG-23 | UG-23-S08 | P0153-08 | 10 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 12.19 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 62.0737 | 8.15 | 3.1172 | 99 | 99 | 99 | 99
UG-23 | UG-23-S08 | P0153-09 | 10 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 14.49 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 62.0737 | 8.15 | 3.1172 | 99 | 99 | 99 | 99
UG-23 | UG-23-S08 | P0153-10 | 10 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 21.6 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 62.0737 | 8.15 | 3.1172 | 99 | 99 | 99 | 99
UG-23 | UG-23-S08 | P0153-11 | 7.1 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 30.39 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 44.0723 | 5.7865 | 2.2132 | 99 | 99 | 99 | 99
UG-23 | UG-23-S09 | P0153-12 | 2.9 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 99 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 18.0014 | 2.3635 | 0.90398 | 99 | 99 | 99 | 99
UG-23 | UG-23-S09 | P0153-13 | 10 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 99 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 62.0737 | 8.15 | 3.1172 | 99 | 99 | 99 | 99
UG-23 | UG-23-S09 | P0153-14 | 10 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 38.95 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 62.0737 | 8.15 | 3.1172 | 99 | 99 | 99 | 99
UG-23 | UG-23-S09 | P0153-15 | 3.7917 | 0.62999 | -1.965 | -1.965 | -0.835 | -0.835 | 40.55 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 23.5367 | 3.0902 | 1.182 | 99 | 99 | 99 | 99
UG-23 | UG-23-S09 | P0018 | 1.295 | 0.62999 | -1.965 | -1.965 | -0.83501 | -0.83501 | 41.51 | -1.965 | -1.965 | 1.265 | 0.46499 | 0.8 | 3.445 | Open cut | 0 | 0.46499 | 0.8 | 2.63 | 0 | 8.0385 | 1.0554 | 0.40367 | 99 | 99 | 99 | 99
UG-23 | UG-23-S09 | P0017 | 1.295 | 0.63 | -1.965 | -1.965 | -0.835 | -0.835 | 41.89 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 8.0386 | 1.0554 | 0.40369 | 99 | 99 | 99 | 99
UG-23 | UG-23-S09 | P0016-01 | 3.6183 | 0.63 | -1.965 | -1.965 | -0.835 | -0.835 | 43.12 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 22.4601 | 2.9489 | 1.1279 | 99 | 99 | 99 | 99
UG-23 | UG-23-S09 | P0016-02 | 10 | 0.63 | -1.965 | -1.965 | -0.835 | -0.835 | 99 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 62.0742 | 8.15 | 3.1173 | 99 | 99 | 99 | 99
UG-23 | UG-23-S09 | P0016-03 | 10 | 0.63 | -1.965 | -1.965 | -0.835 | -0.835 | 41.55 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 62.0742 | 8.15 | 3.1173 | 99 | 99 | 99 | 99
UG-23 | UG-23-S09 | P0016-04 | 10 | 0.63 | -1.965 | -1.965 | -0.835 | -0.835 | 31.61 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 62.0742 | 8.15 | 3.1173 | 99 | 99 | 99 | 99
UG-23 | UG-23-S09 | P0016-05 | 10 | 0.63 | -1.965 | -1.965 | -0.835 | -0.835 | 19.91 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 62.0742 | 8.15 | 3.1173 | 99 | 99 | 99 | 99
UG-23 | UG-23-S09 | P0016-06 | 10 | 0.63 | -1.965 | -1.965 | -0.835 | -0.835 | 17.06 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 62.0742 | 8.15 | 3.1173 | 99 | 99 | 99 | 99
UG-23 | UG-23-S09 | P0016-07 | 7.179 | 0.63 | -1.965 | -1.965 | -0.835 | -0.835 | 17.06 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 44.5631 | 5.8509 | 2.2379 | 99 | 99 | 99 | 99
UG-23 | UG-23-S10 | P0016-08 | 2.821 | 0.63 | -1.965 | -1.965 | -0.835 | -0.835 | 17.75 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 17.5111 | 2.2991 | 0.87939 | 99 | 99 | 99 | 99
UG-23 | UG-23-S10 | P0016-09 | 3.1789 | 0.63 | -1.965 | -1.965 | -0.835 | -0.835 | 18.69 | -1.965 | -1.965 | 1.265 | 0.465 | 0.8 | 3.445 | Open cut | 0 | 0.465 | 0.8 | 2.63 | 0 | 19.733 | 2.5908 | 0.99097 | 99 | 99 | 99 | 99
UG-23 | UG-23-S05 | P0663 | 0.84296 | 0.63 | -4.6305 | -4.9447 | -3.5005 | -3.8147 | 11.69 | -4.9447 | -4.7876 | 4.0876 | 3.4447 | 0.8 | 9.4044 | Shoring | 0.84296 | 3.2876 | 0.8 | 2.63 | 9.0621 | 0 | 0.68701 | 0.26277 | 6.3419 | 6.8721 | 12.646 | 13.1761
UG-23 | UG-23-S05 | P0305 | 0.07071 | 0.63 | -2.9607 | -2.9607 | -1.8307 | -1.8307 | 9.39 | -2.9607 | -2.9607 | 2.2607 | 1.4607 | 0.8 | 5.4364 | Open cut | 0 | 1.4607 | 0.8 | 2.63 | 0 | 1.1206 | 0.057629 | 0.022042 | 3.5246 | 3.5246 | 9.8286 | 9.8286
UG-24 | UG-24-S01 | P0121 | 3.46 | 1.2 | -2.6 | -2.6 | -0.9 | -0.9 | 16.37 | -2.6 | -2.6 | 1.9 | 1.1 | 0.8 | 5 | Open cut | 0 | 1.1 | 0.8 | 3.2 | 0 | 44.9111 | 3.806 | 3.9132 | 0.38938 | 0.38938 | 3.699 | 3.699
UG-24 | UG-24-S01 | P0120 | 0.21 | 1.2 | -2.6 | -2.6 | -0.9 | -0.9 | 16.16 | -2.6 | -2.6 | 1.9 | 1.1 | 0.8 | 5 | Open cut | 0 | 1.1 | 0.8 | 3.2 | 0 | 2.7258 | 0.231 | 0.2375 | 0.38938 | 0.38938 | 3.699 | 3.699
UG-24 | UG-24-S01 | P0119 | 0.2 | 1.4 | -2.7 | -2.7 | -0.8 | -0.8 | 15.96 | -2.7 | -2.7 | 2 | 1.2 | 0.8 | 5.3 | Open cut | 0 | 1.2 | 0.8 | 3.4 | 0 | 2.896 | 0.24 | 0.30787 | 0.16688 | 0.16688 | 3.0037 | 3.0037
UG-24 | UG-24-S01 | P0118 | 3.4312 | 1.6 | -2.8 | -2.8 | -0.7 | -0.7 | 12.53 | -2.8 | -2.8 | 2.1 | 1.3 | 0.8 | 5.6 | Open cut | 0 | 1.3 | 0.8 | 3.6 | 0 | 55.1047 | 4.4605 | 6.8988 | 2.6041e-06 | 2.6041e-06 | 2.4822 | 2.4822
UG-24 | UG-24-S01 | P0388 | 0.205 | 1.6 | -2.8 | -2.8 | -0.7 | -0.7 | 12.32 | -2.8 | -2.8 | 2.1 | 1.3 | 0.8 | 5.6 | Open cut | 0 | 1.3 | 0.8 | 3.6 | 0 | 3.2922 | 0.26649 | 0.41217 | 2.6041e-06 | 2.6041e-06 | 2.4822 | 2.4822
UG-24 | UG-24-S01 | P0264-01 | 2.4938 | 1.6334 | -2.8167 | -2.8167 | -0.6833 | -0.6833 | 9.83 | -2.8167 | -2.8167 | 2.1167 | 1.3167 | 0.8 | 5.6501 | Open cut | 0 | 1.3167 | 0.8 | 3.6334 | 0 | 40.7276 | 3.2836 | 5.2256 | 0 | 0 | 2.4076 | 2.4076
UG-24 | UG-24-S01 | P0264-02 | 0.37678 | 1.6334 | -2.8167 | -2.8167 | -0.6833 | -0.6833 | 9.45 | -2.8167 | -2.8167 | 2.1167 | 1.3167 | 0.8 | 5.6501 | Open cut | 0 | 1.3167 | 0.8 | 3.6334 | 0 | 6.1535 | 0.49611 | 0.78952 | 0 | 0 | 2.4076 | 2.4076
UG-24 | UG-24-S01 | P0067 | 0.6 | 2.0412 | -3.0206 | -3.0206 | -0.4794 | -0.4794 | 8.85 | -3.0206 | -3.0206 | 2.3206 | 1.5206 | 0.8 | 6.2618 | Open cut | 0 | 1.5206 | 0.8 | 4.0412 | 0 | 11.8971 | 0.91236 | 1.9634 | 0 | 0 | 1.6932 | 1.6932
UG-24 | UG-24-S01 | P0635 | 2 | 2.0412 | -3.0206 | -3.0206 | -0.4794 | -0.4794 | 6.85 | -3.0206 | -3.0206 | 2.3206 | 1.5206 | 0.8 | 6.2618 | Open cut | 0 | 1.5206 | 0.8 | 4.0412 | 0 | 39.6568 | 3.0412 | 6.5448 | 0 | 0 | 1.6932 | 1.6932
UG-24 | UG-24-S01 | P0636 | 2 | 2.0411 | -3.0206 | -3.0206 | -0.47945 | -0.47945 | 6.85 | -3.0206 | -3.0206 | 2.3206 | 1.5206 | 0.8 | 6.2617 | Open cut | 0 | 1.5206 | 0.8 | 4.0411 | 0 | 39.655 | 3.0411 | 6.5441 | 0 | 0 | 1.6933 | 1.6933
UG-24 | UG-24-S01 | P0265-01 | 5.0232 | 2.0411 | -3.0206 | -3.0206 | -0.47945 | -0.47945 | 6.85 | -3.0206 | -3.0206 | 2.3206 | 1.5206 | 0.8 | 6.2617 | Open cut | 0 | 1.5206 | 0.8 | 4.0411 | 0 | 99.5983 | 7.6381 | 16.4363 | 0 | 0 | 1.6933 | 1.6933
UG-24 | UG-24-S01 | P0265-02 | 10 | 2.0411 | -3.0206 | -3.0206 | -0.47945 | -0.47945 | 6.51 | -3.0206 | -3.0206 | 2.3206 | 1.5206 | 0.8 | 6.2617 | Open cut | 0 | 1.5206 | 0.8 | 4.0411 | 0 | 198.2756 | 15.2055 | 32.7207 | 0 | 0 | 1.6933 | 1.6933
UG-24 | UG-24-S01 | P0265-03 | 10 | 2.0411 | -3.0206 | -3.0206 | -0.47945 | -0.47945 | 5.85 | -3.0206 | -3.0206 | 2.3206 | 1.5206 | 0.8 | 6.2617 | Shoring | 10 | 1.5206 | 0.8 | 4.0411 | 93.7761 | 0 | 15.2055 | 32.7207 | 0 | 0 | 1.6933 | 1.6933
UG-24 | UG-24-S01 | P0265-04 | 10 | 2.0411 | -3.0206 | -3.0206 | -0.47945 | -0.47945 | 5.85 | -3.0206 | -3.0206 | 2.3206 | 1.5206 | 0.8 | 6.2617 | Shoring | 10 | 1.5206 | 0.8 | 4.0411 | 93.7761 | 0 | 15.2055 | 32.7207 | 0 | 0 | 1.6933 | 1.6933
UG-24 | UG-24-S01 | P0265-05 | 10 | 2.0411 | -3.0206 | -3.0206 | -0.47945 | -0.47945 | 5.85 | -3.0206 | -3.0206 | 2.3206 | 1.5206 | 0.8 | 6.2617 | Shoring | 10 | 1.5206 | 0.8 | 4.0411 | 93.7761 | 0 | 15.2055 | 32.7207 | 0 | 0 | 1.6933 | 1.6933
UG-24 | UG-24-S01 | P0265-06 | 10 | 2.0411 | -3.0206 | -3.0206 | -0.47945 | -0.47945 | 5.85 | -3.0206 | -3.0206 | 2.3206 | 1.5206 | 0.8 | 6.2617 | Shoring | 10 | 1.5206 | 0.8 | 4.0411 | 93.7761 | 0 | 15.2055 | 32.7207 | 0 | 0 | 1.6933 | 1.6933
UG-24 | UG-24-S01 | P0265-07 | 10 | 2.0411 | -3.0206 | -3.0206 | -0.47945 | -0.47945 | 5.85 | -3.0206 | -3.0206 | 2.3206 | 1.5206 | 0.8 | 6.2617 | Shoring | 10 | 1.5206 | 0.8 | 4.0411 | 93.7761 | 0 | 15.2055 | 32.7207 | 0 | 0 | 1.6933 | 1.6933
UG-24 | UG-24-S01 | P0265-08 | 10 | 2.0411 | -3.0206 | -3.0206 | -0.47945 | -0.47945 | 5.85 | -3.0206 | -3.0206 | 2.3206 | 1.5206 | 0.8 | 6.2617 | Shoring | 10 | 1.5206 | 0.8 | 4.0411 | 93.7761 | 0 | 15.2055 | 32.7207 | 0 | 0 | 1.6933 | 1.6933
UG-24 | UG-24-S01 | P0265-09 | 10 | 2.0411 | -3.0206 | -3.0206 | -0.47945 | -0.47945 | 5.85 | -3.0206 | -3.0206 | 2.3206 | 1.5206 | 0.8 | 6.2617 | Shoring | 10 | 1.5206 | 0.8 | 4.0411 | 93.7761 | 0 | 15.2055 | 32.7207 | 0 | 0 | 1.6933 | 1.6933
UG-24 | UG-24-S01 | P0265-10 | 10 | 2.0411 | -3.0206 | -3.0206 | -0.47945 | -0.47945 | 6.52 | -3.0206 | -3.0206 | 2.3206 | 1.5206 | 0.8 | 6.2617 | Open cut | 0 | 1.5206 | 0.8 | 4.0411 | 0 | 198.2756 | 15.2055 | 32.7207 | 0 | 0 | 1.6933 | 1.6933
UG-24 | UG-24-S01 | P0265-11 | 7.5455 | 2.0411 | -3.0206 | -3.0206 | -0.47945 | -0.47945 | 15.75 | -3.0206 | -3.0206 | 2.3206 | 1.5206 | 0.8 | 6.2617 | Open cut | 0 | 1.5206 | 0.8 | 4.0411 | 0 | 149.609 | 11.4734 | 24.6894 | 0 | 0 | 1.6933 | 1.6933
UG-24 | UG-24-S01 | P0066-01 | 2.4545 | 2.045 | -3.0225 | -3.0225 | -0.4775 | -0.4775 | 22.26 | -3.0225 | -3.0225 | 2.3225 | 1.5225 | 0.8 | 6.2675 | Open cut | 0 | 1.5225 | 0.8 | 4.045 | 0 | 48.7524 | 3.737 | 8.0619 | 0 | 0 | 1.6879 | 1.6879
UG-24 | UG-24-S01 | P0066-02 | 0.64551 | 2.045 | -3.0225 | -3.0225 | -0.4775 | -0.4775 | 21.73 | -3.0225 | -3.0225 | 2.3225 | 1.5225 | 0.8 | 6.2675 | Open cut | 0 | 1.5225 | 0.8 | 4.045 | 0 | 12.8216 | 0.9828 | 2.1202 | 0 | 0 | 1.6879 | 1.6879
UG-24 | UG-24-S01 | P0065 | 3.1 | 2.045 | -3.0225 | -3.0225 | -0.4775 | -0.4775 | 21.73 | -3.0225 | -3.0225 | 2.3225 | 1.5225 | 0.8 | 6.2675 | Open cut | 0 | 1.5225 | 0.8 | 4.045 | 0 | 61.5735 | 4.7197 | 10.182 | 0 | 0 | 1.6879 | 1.6879
UG-24 | UG-24-S02 | P0050 | 3.0856 | 2.0696 | -3.0348 | -3.0348 | -0.4652 | -0.4652 | 22.14 | -3.0348 | -3.0348 | 2.3348 | 1.5348 | 0.8 | 6.3044 | Open cut | 0 | 1.5348 | 0.8 | 4.0696 | 0 | 61.972 | 4.7358 | 10.3801 | 0 | 0 | 1.654 | 1.654
UG-25 | UG-25-S01 | P0344-01 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 24.72 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6994 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0344-02 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 99 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6994 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0344-03 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 31.23 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6994 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0344-04 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 31.11 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6994 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0344-05 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 31.42 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6994 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0344-06 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 33.25 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6994 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0344-07 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 17.82 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6994 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0344-08 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 10.6 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6994 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0344-09 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 9.2 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6994 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0344-10 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 9.6 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6994 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0344-11 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 15.59 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6994 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0344-12 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 24.37 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6994 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0344-13 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 32.68 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6994 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0344-14 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 36.02 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6994 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0344-15 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 99 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6994 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0344-16 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 99 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6994 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0344-17 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 30.06 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6994 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0344-18 | 1.5961 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 29.98 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 1.5961 | 3.0518 | 0.8 | 4.4836 | 27.5647 | 0 | 2.7801 | 7.7324 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0616 | 2.5714 | 2.453 | -4.5365 | -4.5365 | -1.5835 | -1.5835 | 29.92 | -4.5365 | -4.5365 | 3.8365 | 3.0365 | 0.8 | 9.4995 | Shoring | 2.5714 | 3.0365 | 0.8 | 4.453 | 43.9291 | 0 | 4.4395 | 12.1521 | 0.7981 | 0.7981 | 2.4172 | 2.4172
UG-25 | UG-25-S01 | P0617 | 0.96883 | 2.453 | -4.5365 | -4.5365 | -1.5835 | -1.5835 | 29.92 | -4.5365 | -4.5365 | 3.8365 | 3.0365 | 0.8 | 9.4995 | Shoring | 0.96883 | 3.0365 | 0.8 | 4.453 | 16.5515 | 0 | 1.6727 | 4.5786 | 0.79809 | 0.79809 | 2.4172 | 2.4172
UG-25 | UG-25-S01 | P0618 | 0.96883 | 2.453 | -4.5365 | -4.5365 | -1.5835 | -1.5835 | 30.19 | -4.5365 | -4.5365 | 3.8365 | 3.0365 | 0.8 | 9.4995 | Shoring | 0.96883 | 3.0365 | 0.8 | 4.453 | 16.5514 | 0 | 1.6727 | 4.5786 | 0.7981 | 0.7981 | 2.4172 | 2.4172
UG-25 | UG-25-S01 | P0619 | 2.5603 | 2.453 | -4.5365 | -4.5365 | -1.5835 | -1.5835 | 30.69 | -4.5365 | -4.5365 | 3.8365 | 3.0365 | 0.8 | 9.4995 | Shoring | 2.5603 | 3.0365 | 0.8 | 4.453 | 43.7398 | 0 | 4.4203 | 12.0997 | 0.7981 | 0.7981 | 2.4172 | 2.4172
UG-25 | UG-25-S01 | P0772-01 | 1.3346 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 30.33 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 1.3346 | 3.0518 | 0.8 | 4.4836 | 23.0479 | 0 | 2.3246 | 6.4654 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0772-02 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 25.92 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6993 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0772-03 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 24.82 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6993 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0772-04 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 24.82 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6993 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0772-05 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 99 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6993 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0772-06 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 30.6 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6993 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0772-07 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 24.83 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6993 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0772-08 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 20.99 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6993 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0772-09 | 10 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 13.85 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 10 | 3.0518 | 0.8 | 4.4836 | 172.6993 | 0 | 17.418 | 48.4455 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0772-10 | 1.3636 | 2.4836 | -4.5518 | -4.5518 | -1.5682 | -1.5682 | 12.54 | -4.5518 | -4.5518 | 3.8518 | 3.0518 | 0.8 | 9.5454 | Shoring | 1.3636 | 3.0518 | 0.8 | 4.4836 | 23.5494 | 0 | 2.3751 | 6.6061 | 0.78172 | 0.78172 | 2.3808 | 2.3808
UG-25 | UG-25-S01 | P0623 | 2.5594 | 2.453 | -4.5365 | -4.5369 | -1.5835 | -1.5839 | 10.11 | -4.5369 | -4.5367 | 3.8367 | 3.0369 | 0.8 | 9.5002 | Shoring | 2.5594 | 3.0367 | 0.8 | 4.453 | 43.7273 | 0 | 4.4189 | 12.0956 | 0.7981 | 0.79826 | 2.4172 | 2.4173
UG-25 | UG-25-S01 | P0622 | 0.96883 | 2.453 | -4.5369 | -4.537 | -1.5839 | -1.584 | 9.34 | -4.537 | -4.5369 | 3.8369 | 3.037 | 0.8 | 9.5005 | Shoring | 0.96883 | 3.0369 | 0.8 | 4.453 | 16.5533 | 0 | 1.6727 | 4.5786 | 0.79826 | 0.79832 | 2.4173 | 2.4174
UG-25 | UG-25-S01 | P0621 | 0.96882 | 2.453 | -4.537 | -4.5372 | -1.584 | -1.5841 | 8.8 | -4.5372 | -4.5371 | 3.8371 | 3.0372 | 0.8 | 9.5008 | Shoring | 0.96882 | 3.0371 | 0.8 | 4.453 | 16.5538 | 0 | 1.6727 | 4.5786 | 0.79832 | 0.79838 | 2.4174 | 2.4174
UG-25 | UG-25-S01 | P0620 | 2.5603 | 2.453 | -4.5372 | -4.5375 | -1.5841 | -1.5845 | 8.35 | -4.5375 | -4.5373 | 3.8373 | 3.0375 | 0.8 | 9.5015 | Shoring | 2.5603 | 3.0373 | 0.8 | 4.453 | 43.7498 | 0 | 4.4204 | 12.0999 | 0.79838 | 0.79853 | 2.4174 | 2.4176
UG-25 | UG-25-S01 | P0110-01 | 1.579 | 2.4836 | -4.5528 | -4.553 | -1.5692 | -1.5694 | 8.12 | -4.553 | -4.5529 | 3.8529 | 3.053 | 0.8 | 9.5479 | Shoring | 1.579 | 3.0529 | 0.8 | 4.4836 | 27.2768 | 0 | 2.7503 | 7.6494 | 0.78215 | 0.78225 | 2.3813 | 2.3814
UG-25 | UG-25-S01 | P0110-02 | 10 | 2.4836 | -4.553 | -4.5545 | -1.5694 | -1.5709 | 8.06 | -4.5545 | -4.5538 | 3.8538 | 3.0545 | 0.8 | 9.5507 | Shoring | 10 | 3.0538 | 0.8 | 4.4836 | 172.7864 | 0 | 17.4179 | 48.4451 | 0.78225 | 0.78287 | 2.3814 | 2.382
UG-25 | UG-25-S01 | P0110-03 | 10 | 2.4836 | -4.5545 | -4.5559 | -1.5709 | -1.5723 | 10.89 | -4.5559 | -4.5552 | 3.8552 | 3.0559 | 0.8 | 9.5536 | Shoring | 10 | 3.0552 | 0.8 | 4.4836 | 172.8508 | 0 | 17.4179 | 48.4451 | 0.78287 | 0.78348 | 2.382 | 2.3826
UG-25 | UG-25-S01 | P0110-04 | 10 | 2.4836 | -4.5559 | -4.5573 | -1.5723 | -1.5738 | 14.93 | -4.5573 | -4.5566 | 3.8566 | 3.0573 | 0.8 | 9.5565 | Shoring | 10 | 3.0566 | 0.8 | 4.4836 | 172.9152 | 0 | 17.4179 | 48.4451 | 0.78348 | 0.7841 | 2.3826 | 2.3832
UG-25 | UG-25-S01 | P0110-05 | 10 | 2.4836 | -4.5573 | -4.5588 | -1.5738 | -1.5752 | 5.25 | -4.5588 | -4.5581 | 3.8581 | 3.0588 | 0.8 | 9.5594 | Shoring | 10 | 3.0581 | 0.8 | 4.4836 | 172.9797 | 0 | 17.4179 | 48.4451 | 0.7841 | 0.78471 | 2.3832 | 2.3838
UG-25 | UG-25-S01 | P0110-06 | 10 | 2.4836 | -4.5588 | -4.5602 | -1.5752 | -1.5766 | 0.42 | -4.5602 | -4.5595 | 3.8595 | 3.0602 | 0.8 | 9.5622 | Shoring | 10 | 3.0595 | 0.8 | 4.4836 | 173.0441 | 0 | 17.4179 | 48.4451 | 0.78471 | 0.78533 | 2.3838 | 2.3845
UG-25 | UG-25-S01 | P0110-07 | 10 | 2.4836 | -4.5602 | -4.5617 | -1.5766 | -1.5781 | 0.91 | -4.5617 | -4.5609 | 3.8609 | 3.0617 | 0.8 | 9.5651 | Shoring | 10 | 3.0609 | 0.8 | 4.4836 | 173.1086 | 0 | 17.4179 | 48.4451 | 0.78533 | 0.78594 | 2.3845 | 2.3851
UG-25 | UG-25-S01 | P0110-08 | 0.96851 | 2.4836 | -4.5617 | -4.5618 | -1.5781 | -1.5782 | 1.93 | -4.5618 | -4.5617 | 3.8617 | 3.0618 | 0.8 | 9.5654 | Shoring | 0.96851 | 3.0617 | 0.8 | 4.4836 | 16.7692 | 0 | 1.687 | 4.692 | 0.78594 | 0.786 | 2.3851 | 2.3851
UG-25 | UG-25-S01 | P0653 | 1.5446 | 2.453 | -4.5465 | -4.5478 | -1.5935 | -1.5948 | 2.03 | -4.5478 | -4.5472 | 3.8472 | 3.0478 | 0.8 | 9.5221 | Shoring | 1.5446 | 3.0472 | 0.8 | 4.453 | 26.461 | 0 | 2.6667 | 7.2996 | 0.80243 | 0.803 | 2.4215 | 2.4221
UG-25 | UG-25-S01 | P0654 | 3.0482 | 2.453 | -4.5478 | -4.5504 | -1.5948 | -1.5974 | 2.25 | -4.5504 | -4.5491 | 3.8491 | 3.0504 | 0.8 | 9.5273 | Shoring | 3.0482 | 3.0491 | 0.8 | 4.453 | 52.2463 | 0 | 5.2627 | 14.4055 | 0.803 | 0.80413 | 2.4221 | 2.4232
UG-25 | UG-25-S01 | P0655 | 1.5446 | 2.4531 | -4.5505 | -4.5518 | -1.5974 | -1.5987 | 4.71 | -4.5518 | -4.5511 | 3.8511 | 3.0518 | 0.8 | 9.5301 | Shoring | 1.5446 | 3.0511 | 0.8 | 4.4531 | 26.4891 | 0 | 2.6668 | 7.3003 | 0.80407 | 0.80464 | 2.4231 | 2.4236
UG-25 | UG-25-S01 | P0776-01 | 2.8941 | 2.4836 | -4.567 | -4.5695 | -1.5834 | -1.5859 | 6.23 | -4.5695 | -4.5683 | 3.8683 | 3.0695 | 0.8 | 9.5808 | Shoring | 2.8941 | 3.0683 | 0.8 | 4.4836 | 50.1946 | 0 | 5.0409 | 14.0206 | 0.78823 | 0.78929 | 2.3874 | 2.3884
UG-25 | UG-25-S01 | P0776-02 | 10 | 2.4836 | -4.5695 | -4.578 | -1.5859 | -1.5944 | 9.07 | -4.578 | -4.5738 | 3.8738 | 3.078 | 0.8 | 9.5978 | Shoring | 10 | 3.0738 | 0.8 | 4.4836 | 173.6838 | 0 | 17.418 | 48.4455 | 0.78929 | 0.79294 | 2.3884 | 2.3921
UG-25 | UG-25-S01 | P0776-03 | 10 | 2.4836 | -4.578 | -4.5865 | -1.5944 | -1.6029 | 9.24 | -4.5865 | -4.5823 | 3.8823 | 3.0865 | 0.8 | 9.6149 | Shoring | 10 | 3.0823 | 0.8 | 4.4836 | 174.066 | 0 | 17.418 | 48.4455 | 0.79294 | 0.79659 | 2.3921 | 2.3957
UG-25 | UG-25-S01 | P0776-04 | 10 | 2.4836 | -4.5865 | -4.5951 | -1.6029 | -1.6115 | 8.97 | -4.5951 | -4.5908 | 3.8908 | 3.0951 | 0.8 | 9.6319 | Shoring | 10 | 3.0908 | 0.8 | 4.4836 | 174.4482 | 0 | 17.418 | 48.4455 | 0.79659 | 0.80024 | 2.3957 | 2.3994
UG-25 | UG-25-S01 | P0776-05 | 10 | 2.4836 | -4.5951 | -4.6036 | -1.6115 | -1.62 | 9.85 | -4.6036 | -4.5993 | 3.8993 | 3.1036 | 0.8 | 9.649 | Shoring | 10 | 3.0993 | 0.8 | 4.4836 | 174.8304 | 0 | 17.418 | 48.4455 | 0.80024 | 0.80388 | 2.3994 | 2.403
UG-25 | UG-25-S01 | P0776-06 | 10 | 2.4836 | -4.6036 | -4.6121 | -1.62 | -1.6285 | 10.77 | -4.6121 | -4.6079 | 3.9079 | 3.1121 | 0.8 | 9.666 | Shoring | 10 | 3.1079 | 0.8 | 4.4836 | 175.2125 | 0 | 17.418 | 48.4455 | 0.80388 | 0.80753 | 2.403 | 2.4067
UG-25 | UG-25-S01 | P0776-07 | 10 | 2.4836 | -4.6121 | -4.6206 | -1.6285 | -1.637 | 9.62 | -4.6206 | -4.6164 | 3.9164 | 3.1206 | 0.8 | 9.6831 | Shoring | 10 | 3.1164 | 0.8 | 4.4836 | 175.5947 | 0 | 17.418 | 48.4455 | 0.80753 | 0.81118 | 2.4067 | 2.4103
UG-25 | UG-25-S01 | P0776-08 | 10 | 2.4836 | -4.6206 | -4.6292 | -1.637 | -1.6456 | 9.75 | -4.6292 | -4.6249 | 3.9249 | 3.1292 | 0.8 | 9.7001 | Shoring | 10 | 3.1249 | 0.8 | 4.4836 | 175.9769 | 0 | 17.418 | 48.4455 | 0.81118 | 0.81483 | 2.4103 | 2.4139
UG-25 | UG-25-S01 | P0776-09 | 10 | 2.4836 | -4.6292 | -4.6377 | -1.6456 | -1.6541 | 12.66 | -4.6377 | -4.6334 | 3.9334 | 3.1377 | 0.8 | 9.7172 | Shoring | 10 | 3.1334 | 0.8 | 4.4836 | 176.359 | 0 | 17.418 | 48.4455 | 0.81483 | 0.81848 | 2.4139 | 2.4176
UG-25 | UG-25-S01 | P0776-10 | 10 | 2.4836 | -4.6377 | -4.6462 | -1.6541 | -1.6626 | 18.47 | -4.6462 | -4.6419 | 3.9419 | 3.1462 | 0.8 | 9.7342 | Shoring | 10 | 3.1419 | 0.8 | 4.4836 | 176.7412 | 0 | 17.418 | 48.4455 | 0.81848 | 0.82212 | 2.4176 | 2.4212
UG-25 | UG-25-S01 | P0776-11 | 10 | 2.4836 | -4.6462 | -4.6547 | -1.6626 | -1.6711 | 17.38 | -4.6547 | -4.6505 | 3.9505 | 3.1547 | 0.8 | 9.7513 | Shoring | 10 | 3.1505 | 0.8 | 4.4836 | 177.1234 | 0 | 17.418 | 48.4455 | 0.82212 | 0.82577 | 2.4212 | 2.4249
UG-25 | UG-25-S01 | P0776-12 | 10 | 2.4836 | -4.6547 | -4.6633 | -1.6711 | -1.6797 | 8.07 | -4.6633 | -4.659 | 3.959 | 3.1633 | 0.8 | 9.7683 | Shoring | 10 | 3.159 | 0.8 | 4.4836 | 177.5056 | 0 | 17.418 | 48.4455 | 0.82577 | 0.82942 | 2.4249 | 2.4285
UG-25 | UG-25-S01 | P0776-13 | 10 | 2.4836 | -4.6633 | -4.6718 | -1.6797 | -1.6882 | 3.48 | -4.6718 | -4.6675 | 3.9675 | 3.1718 | 0.8 | 9.7854 | Shoring | 10 | 3.1675 | 0.8 | 4.4836 | 177.8877 | 0 | 17.418 | 48.4455 | 0.82942 | 0.83307 | 2.4285 | 2.4322
UG-25 | UG-25-S01 | P0776-14 | 10 | 2.4836 | -4.6718 | -4.6803 | -1.6882 | -1.6967 | 3.44 | -4.6803 | -4.676 | 3.976 | 3.1803 | 0.8 | 9.8024 | Shoring | 10 | 3.176 | 0.8 | 4.4836 | 178.2699 | 0 | 17.418 | 48.4455 | 0.83307 | 0.83672 | 2.4322 | 2.4358
UG-25 | UG-25-S01 | P0776-15 | 10 | 2.4836 | -4.6803 | -4.6888 | -1.6967 | -1.7052 | 10.05 | -4.6888 | -4.6846 | 3.9846 | 3.1888 | 0.8 | 9.8195 | Shoring | 10 | 3.1846 | 0.8 | 4.4836 | 178.6521 | 0 | 17.418 | 48.4455 | 0.83672 | 0.84036 | 2.4358 | 2.4395
UG-25 | UG-25-S01 | P0776-16 | 10 | 2.4836 | -4.6888 | -4.6974 | -1.7052 | -1.7138 | 19.73 | -4.6974 | -4.6931 | 3.9931 | 3.1974 | 0.8 | 9.8365 | Shoring | 10 | 3.1931 | 0.8 | 4.4836 | 179.0342 | 0 | 17.418 | 48.4455 | 0.84036 | 0.84401 | 2.4395 | 2.4431
UG-25 | UG-25-S01 | P0776-17 | 5.2172 | 2.4836 | -4.6974 | -4.7018 | -1.7138 | -1.7182 | 99 | -4.7018 | -4.6996 | 3.9996 | 3.2018 | 0.8 | 9.8454 | Shoring | 5.2172 | 3.1996 | 0.8 | 4.4836 | 93.5571 | 0 | 9.0873 | 25.2749 | 0.84401 | 0.84592 | 2.4431 | 2.445
UG-26 | UG-26-S01 | P0056-01 | 10 | 2.4836 | -4.1918 | -4.1901 | -1.2082 | -1.2065 | 99 | -4.1918 | -4.1909 | 3.4909 | 2.6918 | 0.8 | 8.8254 | Shoring | 10 | 2.6909 | 0.8 | 4.4836 | 156.5195 | 0 | 17.418 | 48.4451 | 0.47805 | 0.47644 | 2.0772 | 2.0756
UG-26 | UG-26-S01 | P0056-02 | 10 | 2.4836 | -4.1901 | -4.1884 | -1.2065 | -1.2048 | 99 | -4.1901 | -4.1892 | 3.4892 | 2.6901 | 0.8 | 8.822 | Shoring | 10 | 2.6892 | 0.8 | 4.4836 | 156.443 | 0 | 17.418 | 48.4451 | 0.47644 | 0.47484 | 2.0756 | 2.074
UG-26 | UG-26-S01 | P0056-03 | 10 | 2.4836 | -4.1884 | -4.1867 | -1.2048 | -1.2031 | 27.41 | -4.1884 | -4.1875 | 3.4875 | 2.6884 | 0.8 | 8.8186 | Shoring | 10 | 2.6875 | 0.8 | 4.4836 | 156.3664 | 0 | 17.418 | 48.4451 | 0.47484 | 0.47323 | 2.074 | 2.0724
UG-26 | UG-26-S01 | P0056-04 | 10 | 2.4836 | -4.1867 | -4.185 | -1.2031 | -1.2014 | 27.26 | -4.1867 | -4.1858 | 3.4858 | 2.6867 | 0.8 | 8.8151 | Shoring | 10 | 2.6858 | 0.8 | 4.4836 | 156.2898 | 0 | 17.418 | 48.4451 | 0.47323 | 0.47162 | 2.0724 | 2.0707
UG-26 | UG-26-S01 | P0056-05 | 10 | 2.4836 | -4.185 | -4.1833 | -1.2014 | -1.1997 | 27.58 | -4.185 | -4.1841 | 3.4841 | 2.685 | 0.8 | 8.8117 | Shoring | 10 | 2.6841 | 0.8 | 4.4836 | 156.2132 | 0 | 17.418 | 48.4451 | 0.47162 | 0.47002 | 2.0707 | 2.0691
UG-26 | UG-26-S01 | P0056-06 | 10 | 2.4836 | -4.1833 | -4.1815 | -1.1997 | -1.198 | 29.49 | -4.1833 | -4.1824 | 3.4824 | 2.6833 | 0.8 | 8.8083 | Shoring | 10 | 2.6824 | 0.8 | 4.4836 | 156.1366 | 0 | 17.418 | 48.4451 | 0.47002 | 0.46841 | 2.0691 | 2.0675
UG-26 | UG-26-S01 | P0056-07 | 10 | 2.4836 | -4.1815 | -4.1798 | -1.198 | -1.1962 | 20.23 | -4.1815 | -4.1807 | 3.4807 | 2.6815 | 0.8 | 8.8049 | Shoring | 10 | 2.6807 | 0.8 | 4.4836 | 156.0601 | 0 | 17.418 | 48.4451 | 0.46841 | 0.4668 | 2.0675 | 2.0659
UG-26 | UG-26-S01 | P0056-08 | 10 | 2.4836 | -4.1798 | -4.1781 | -1.1962 | -1.1945 | 14.14 | -4.1798 | -4.179 | 3.479 | 2.6798 | 0.8 | 8.8015 | Shoring | 10 | 2.679 | 0.8 | 4.4836 | 155.9835 | 0 | 17.418 | 48.4451 | 0.4668 | 0.4652 | 2.0659 | 2.0643
UG-26 | UG-26-S01 | P0056-09 | 10 | 2.4836 | -4.1781 | -4.1764 | -1.1945 | -1.1928 | 13.05 | -4.1781 | -4.1773 | 3.4773 | 2.6781 | 0.8 | 8.7981 | Shoring | 10 | 2.6773 | 0.8 | 4.4836 | 155.9069 | 0 | 17.418 | 48.4451 | 0.4652 | 0.46359 | 2.0643 | 2.0627
UG-26 | UG-26-S01 | P0056-10 | 10 | 2.4836 | -4.1764 | -4.1747 | -1.1928 | -1.1911 | 13.31 | -4.1764 | -4.1756 | 3.4756 | 2.6764 | 0.8 | 8.7946 | Shoring | 10 | 2.6756 | 0.8 | 4.4836 | 155.8303 | 0 | 17.418 | 48.4451 | 0.46359 | 0.46198 | 2.0627 | 2.0611
UG-26 | UG-26-S01 | P0056-11 | 10 | 2.4836 | -4.1747 | -4.173 | -1.1911 | -1.1894 | 18 | -4.1747 | -4.1739 | 3.4739 | 2.6747 | 0.8 | 8.7912 | Shoring | 10 | 2.6739 | 0.8 | 4.4836 | 155.7537 | 0 | 17.418 | 48.4451 | 0.46198 | 0.46038 | 2.0611 | 2.0595
UG-26 | UG-26-S01 | P0056-12 | 10 | 2.4836 | -4.173 | -4.1713 | -1.1894 | -1.1877 | 25.9 | -4.173 | -4.1722 | 3.4722 | 2.673 | 0.8 | 8.7878 | Shoring | 10 | 2.6722 | 0.8 | 4.4836 | 155.6771 | 0 | 17.418 | 48.4451 | 0.46038 | 0.45877 | 2.0595 | 2.0579
UG-26 | UG-26-S01 | P0056-13 | 10 | 2.4836 | -4.1713 | -4.1696 | -1.1877 | -1.186 | 28.92 | -4.1713 | -4.1704 | 3.4704 | 2.6713 | 0.8 | 8.7844 | Shoring | 10 | 2.6704 | 0.8 | 4.4836 | 155.6006 | 0 | 17.418 | 48.4451 | 0.45877 | 0.45716 | 2.0579 | 2.0563
UG-26 | UG-26-S01 | P0056-14 | 10 | 2.4836 | -4.1696 | -4.1679 | -1.186 | -1.1843 | 32.44 | -4.1696 | -4.1687 | 3.4687 | 2.6696 | 0.8 | 8.781 | Shoring | 10 | 2.6687 | 0.8 | 4.4836 | 155.524 | 0 | 17.418 | 48.4451 | 0.45716 | 0.45556 | 2.0563 | 2.0547
UG-26 | UG-26-S01 | P0056-15 | 10 | 2.4836 | -4.1679 | -4.1662 | -1.1843 | -1.1826 | 99 | -4.1679 | -4.167 | 3.467 | 2.6679 | 0.8 | 8.7776 | Shoring | 10 | 2.667 | 0.8 | 4.4836 | 155.4474 | 0 | 17.418 | 48.4451 | 0.45556 | 0.45395 | 2.0547 | 2.0531
UG-26 | UG-26-S01 | P0056-16 | 10 | 2.4836 | -4.1662 | -4.1645 | -1.1826 | -1.1809 | 99 | -4.1662 | -4.1653 | 3.4653 | 2.6662 | 0.8 | 8.7741 | Shoring | 10 | 2.6653 | 0.8 | 4.4836 | 155.3708 | 0 | 17.418 | 48.4451 | 0.45395 | 0.45234 | 2.0531 | 2.0515
UG-26 | UG-26-S01 | P0056-17 | 10 | 2.4836 | -4.1645 | -4.1628 | -1.1809 | -1.1792 | 26.24 | -4.1645 | -4.1636 | 3.4636 | 2.6645 | 0.8 | 8.7707 | Shoring | 10 | 2.6636 | 0.8 | 4.4836 | 155.2942 | 0 | 17.418 | 48.4451 | 0.45234 | 0.45074 | 2.0515 | 2.0499
UG-26 | UG-26-S01 | P0056-18 | 5.641 | 2.4836 | -4.1628 | -4.1618 | -1.1792 | -1.1782 | 26.09 | -4.1628 | -4.1623 | 3.4623 | 2.6628 | 0.8 | 8.7673 | Shoring | 5.641 | 2.6623 | 0.8 | 4.4836 | 87.5677 | 0 | 9.8255 | 27.3279 | 0.45074 | 0.44983 | 2.0499 | 2.049
UG-26 | UG-26-S01 | P0612 | 3.6 | 2.4836 | -4.1618 | -4.1765 | -1.1782 | -1.1929 | 26.12 | -4.1765 | -4.1692 | 3.4692 | 2.6765 | 0.8 | 8.7949 | Shoring | 3.6 | 2.6692 | 0.8 | 4.4836 | 55.9962 | 0 | 6.2705 | 17.4405 | 0.44983 | 0.46369 | 2.049 | 2.0628
UG-26 | UG-26-S01 | P0613-01 | 0.75896 | 2.4836 | -4.1765 | -4.1796 | -1.1929 | -1.196 | 26.34 | -4.1796 | -4.1781 | 3.4781 | 2.6796 | 0.8 | 8.8011 | Shoring | 0.75896 | 2.6781 | 0.8 | 4.4836 | 11.8355 | 0 | 1.322 | 3.6768 | 0.46369 | 0.46661 | 2.0628 | 2.0657
UG-26 | UG-26-S01 | P0613-02 | 2.841 | 2.4836 | -4.1796 | -4.1913 | -1.196 | -1.2077 | 26.93 | -4.1913 | -4.1855 | 3.4855 | 2.6913 | 0.8 | 8.8244 | Shoring | 2.841 | 2.6855 | 0.8 | 4.4836 | 44.3971 | 0 | 4.9484 | 13.7632 | 0.46661 | 0.47756 | 2.0657 | 2.0767
UG-26 | UG-26-S01 | P0232-01 | 7.159 | 2.4836 | -4.1913 | -4.2206 | -1.2077 | -1.237 | 22.61 | -4.2206 | -4.2059 | 3.5059 | 2.7206 | 0.8 | 8.883 | Shoring | 7.159 | 2.7059 | 0.8 | 4.4836 | 112.5347 | 0 | 12.4696 | 34.6822 | 0.47756 | 0.50514 | 2.0767 | 2.1043
UG-26 | UG-26-S01 | P0232-02 | 10 | 2.4836 | -4.2206 | -4.2616 | -1.237 | -1.278 | 19.48 | -4.2616 | -4.2411 | 3.5411 | 2.7616 | 0.8 | 8.9649 | Shoring | 10 | 2.7411 | 0.8 | 4.4836 | 158.7681 | 0 | 17.418 | 48.4454 | 0.50514 | 0.54367 | 2.1043 | 2.1428
UG-26 | UG-26-S01 | P0232-03 | 10 | 2.4836 | -4.2616 | -4.3025 | -1.278 | -1.3189 | 19.4 | -4.3025 | -4.282 | 3.582 | 2.8025 | 0.8 | 9.0468 | Shoring | 10 | 2.782 | 0.8 | 4.4836 | 160.6043 | 0 | 17.418 | 48.4454 | 0.54367 | 0.58219 | 2.1428 | 2.1813
UG-26 | UG-26-S01 | P0232-04 | 10 | 2.4836 | -4.3025 | -4.3435 | -1.3189 | -1.3599 | 19.89 | -4.3435 | -4.323 | 3.623 | 2.8435 | 0.8 | 9.1287 | Shoring | 10 | 2.823 | 0.8 | 4.4836 | 162.4405 | 0 | 17.418 | 48.4454 | 0.58219 | 0.62071 | 2.1813 | 2.2198
UG-26 | UG-26-S01 | P0232-05 | 10 | 2.4836 | -4.3435 | -4.3844 | -1.3599 | -1.4008 | 24.16 | -4.3844 | -4.3639 | 3.6639 | 2.8844 | 0.8 | 9.2107 | Shoring | 10 | 2.8639 | 0.8 | 4.4836 | 164.2768 | 0 | 17.418 | 48.4454 | 0.62071 | 0.65924 | 2.2198 | 2.2584
UG-26 | UG-26-S01 | P0232-06 | 10 | 2.4836 | -4.3844 | -4.4254 | -1.4008 | -1.4418 | 22.71 | -4.4254 | -4.4049 | 3.7049 | 2.9254 | 0.8 | 9.2926 | Shoring | 10 | 2.9049 | 0.8 | 4.4836 | 166.113 | 0 | 17.418 | 48.4454 | 0.65924 | 0.69776 | 2.2584 | 2.2969
UG-26 | UG-26-S01 | P0232-07 | 10 | 2.4836 | -4.4254 | -4.4663 | -1.4418 | -1.4827 | 17.33 | -4.4663 | -4.4459 | 3.7459 | 2.9663 | 0.8 | 9.3745 | Shoring | 10 | 2.9459 | 0.8 | 4.4836 | 167.9492 | 0 | 17.418 | 48.4454 | 0.69776 | 0.73629 | 2.2969 | 2.3354
UG-26 | UG-26-S01 | P0232-08 | 10 | 2.4836 | -4.4663 | -4.5073 | -1.4827 | -1.5237 | 14.53 | -4.5073 | -4.4868 | 3.7868 | 3.0073 | 0.8 | 9.4564 | Shoring | 10 | 2.9868 | 0.8 | 4.4836 | 169.7854 | 0 | 17.418 | 48.4454 | 0.73629 | 0.76267 | 2.3354 | 2.3618
UG-26 | UG-26-S01 | P0232-09 | 8.427 | 2.4836 | -4.5073 | -4.5418 | -1.5237 | -1.5582 | 9.23 | -4.5418 | -4.5245 | 3.8245 | 3.0418 | 0.8 | 9.5254 | Shoring | 8.427 | 3.0245 | 0.8 | 4.4836 | 144.5034 | 0 | 14.6781 | 40.8248 | 0.76267 | 0.77744 | 2.3618 | 2.3766
UG-26 | UG-26-S01 | P0615-01 | 1.573 | 2.4836 | -4.5418 | -4.5423 | -1.5582 | -1.5587 | 7.72 | -4.5423 | -4.542 | 3.842 | 3.0423 | 0.8 | 9.5263 | Shoring | 1.573 | 3.042 | 0.8 | 4.4836 | 27.0972 | 0 | 2.7399 | 7.6206 | 0.77744 | 0.77764 | 2.3766 | 2.3768
UG-26 | UG-26-S01 | P0615-02 | 2.0269 | 2.4836 | -4.5423 | -4.5429 | -1.5587 | -1.5593 | 5.79 | -4.5429 | -4.5426 | 3.8426 | 3.0429 | 0.8 | 9.5275 | Shoring | 2.0269 | 3.0426 | 0.8 | 4.4836 | 34.9205 | 0 | 3.5305 | 9.8194 | 0.77764 | 0.77789 | 2.3768 | 2.377
UG-26 | UG-26-S01 | P0614 | 3.6 | 2.4836 | -4.5429 | -4.5439 | -1.5593 | -1.5603 | 3.07 | -4.5439 | -4.5434 | 3.8434 | 3.0439 | 0.8 | 9.5297 | Shoring | 3.6 | 3.0434 | 0.8 | 4.4836 | 62.0369 | 0 | 6.2706 | 17.4406 | 0.7779 | 0.77835 | 2.377 | 2.3775
UG-26 | UG-26-S01 | P0074-01 | 4.373 | 2.4836 | -4.5439 | -4.5452 | -1.5603 | -1.5616 | 2.19 | -4.5452 | -4.5446 | 3.8446 | 3.0452 | 0.8 | 9.5322 | Shoring | 4.373 | 3.0446 | 0.8 | 4.4836 | 75.3805 | 0 | 7.617 | 21.1854 | 0.77835 | 0.7789 | 2.3775 | 2.378
UG-26 | UG-26-S01 | P0074-02 | 10 | 2.4836 | -4.5452 | -4.5482 | -1.5616 | -1.5646 | 2.19 | -4.5482 | -4.5467 | 3.8467 | 3.0482 | 0.8 | 9.5382 | Shoring | 10 | 3.0467 | 0.8 | 4.4836 | 172.4706 | 0 | 17.418 | 48.4453 | 0.7789 | 0.78017 | 2.378 | 2.3793
UG-26 | UG-26-S01 | P0074-03 | 10 | 2.4836 | -4.5482 | -4.5511 | -1.5646 | -1.5675 | 5.83 | -4.5511 | -4.5497 | 3.8497 | 3.0511 | 0.8 | 9.5441 | Shoring | 10 | 3.0497 | 0.8 | 4.4836 | 172.6033 | 0 | 17.418 | 48.4453 | 0.78017 | 0.78144 | 2.3793 | 2.3806
UG-26 | UG-26-S01 | P0074-04 | 10 | 2.4836 | -4.5511 | -4.5541 | -1.5675 | -1.5705 | 9.03 | -4.5541 | -4.5526 | 3.8526 | 3.0541 | 0.8 | 9.55 | Shoring | 10 | 3.0526 | 0.8 | 4.4836 | 172.736 | 0 | 17.418 | 48.4453 | 0.78144 | 0.7827 | 2.3806 | 2.3818
UG-26 | UG-26-S01 | P0074-05 | 10 | 2.4836 | -4.5541 | -4.5571 | -1.5705 | -1.5735 | 7.59 | -4.5571 | -4.5556 | 3.8556 | 3.0571 | 0.8 | 9.5559 | Shoring | 10 | 3.0556 | 0.8 | 4.4836 | 172.8687 | 0 | 17.418 | 48.4453 | 0.7827 | 0.78397 | 2.3818 | 2.3831
UG-26 | UG-26-S01 | P0074-06 | 10 | 2.4836 | -4.5571 | -4.56 | -1.5735 | -1.5764 | 6.3 | -4.56 | -4.5585 | 3.8585 | 3.06 | 0.8 | 9.5618 | Shoring | 10 | 3.0585 | 0.8 | 4.4836 | 173.0014 | 0 | 17.418 | 48.4453 | 0.78397 | 0.78524 | 2.3831 | 2.3844
UG-26 | UG-26-S01 | P0074-07 | 5.9999 | 2.4836 | -4.56 | -4.5618 | -1.5764 | -1.5782 | 6.85 | -4.5618 | -4.5609 | 3.8609 | 3.0618 | 0.8 | 9.5654 | Shoring | 5.9999 | 3.0609 | 0.8 | 4.4836 | 103.863 | 0 | 10.4506 | 29.0668 | 0.78524 | 0.786 | 2.3844 | 2.3851
UG-26 | UG-26-S01 | P0656 | 3.884 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 7.47 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 3.884 | 3.0618 | 0.8 | 4.4836 | 67.25 | 0 | 6.7651 | 18.816 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-26 | UG-26-S01 | P0657-01 | 0.11611 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 7.86 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 0.11611 | 3.0618 | 0.8 | 4.4836 | 2.0105 | 0 | 0.20225 | 0.56251 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-26 | UG-26-S01 | P0657-02 | 3.7675 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 7.98 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 3.7675 | 3.0618 | 0.8 | 4.4836 | 65.2334 | 0 | 6.5622 | 18.2518 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-26 | UG-26-S01 | P0272-01 | 6.2325 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 9.93 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 6.2325 | 3.0618 | 0.8 | 4.4836 | 107.914 | 0 | 10.8557 | 30.1935 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-26 | UG-26-S01 | P0272-02 | 10 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 5.89 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 10 | 3.0618 | 0.8 | 4.4836 | 173.1473 | 0 | 17.418 | 48.4453 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-26 | UG-26-S01 | P0272-03 | 10 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 5.48 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 10 | 3.0618 | 0.8 | 4.4836 | 173.1473 | 0 | 17.418 | 48.4453 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-26 | UG-26-S01 | P0272-04 | 10 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 6.35 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 10 | 3.0618 | 0.8 | 4.4836 | 173.1473 | 0 | 17.418 | 48.4453 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-26 | UG-26-S01 | P0272-05 | 10 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 7.54 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 10 | 3.0618 | 0.8 | 4.4836 | 173.1473 | 0 | 17.418 | 48.4453 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-26 | UG-26-S01 | P0272-06 | 10 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 6.02 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 10 | 3.0618 | 0.8 | 4.4836 | 173.1473 | 0 | 17.418 | 48.4453 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-26 | UG-26-S01 | P0272-07 | 10 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 6.12 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 10 | 3.0618 | 0.8 | 4.4836 | 173.1473 | 0 | 17.418 | 48.4453 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-26 | UG-26-S01 | P0272-08 | 10 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 9.25 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 10 | 3.0618 | 0.8 | 4.4836 | 173.1473 | 0 | 17.418 | 48.4453 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-26 | UG-26-S01 | P0272-09 | 10 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 15.56 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 10 | 3.0618 | 0.8 | 4.4836 | 173.1473 | 0 | 17.418 | 48.4453 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-26 | UG-26-S01 | P0272-10 | 10 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 17.31 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 10 | 3.0618 | 0.8 | 4.4836 | 173.1473 | 0 | 17.418 | 48.4453 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-26 | UG-26-S01 | P0272-11 | 10 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 7.32 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 10 | 3.0618 | 0.8 | 4.4836 | 173.1473 | 0 | 17.418 | 48.4453 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-26 | UG-26-S01 | P0272-12 | 10 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 0 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 10 | 3.0618 | 0.8 | 4.4836 | 173.1473 | 0 | 17.418 | 48.4453 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-26 | UG-26-S01 | P0272-13 | 10 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 0 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 10 | 3.0618 | 0.8 | 4.4836 | 173.1473 | 0 | 17.418 | 48.4453 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-26 | UG-26-S01 | P0272-14 | 10 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 8.69 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 10 | 3.0618 | 0.8 | 4.4836 | 173.1473 | 0 | 17.418 | 48.4453 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-26 | UG-26-S01 | P0272-15 | 10 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 18.44 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 10 | 3.0618 | 0.8 | 4.4836 | 173.1473 | 0 | 17.418 | 48.4453 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-26 | UG-26-S01 | P0272-16 | 5.7146 | 2.4836 | -4.5618 | -4.5618 | -1.5782 | -1.5782 | 28.32 | -4.5618 | -4.5618 | 3.8618 | 3.0618 | 0.8 | 9.5654 | Shoring | 5.7146 | 3.0618 | 0.8 | 4.4836 | 98.9464 | 0 | 9.9536 | 27.6844 | 0.786 | 0.786 | 2.3851 | 2.3851
UG-28 | UG-28-S01 | P0171 | 0.5 | 0.5 | -0.63898 | -0.63917 | 0.36102 | 0.36083 | 11.22 | -0.63917 | -0.63908 | 0 | 0 | 0 | 1.25 | Open cut | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-28 | UG-28-S01 | P0761 | 0.6 | 0.5 | -0.63917 | -0.63941 | 0.36083 | 0.36059 | 11.21 | -0.63941 | -0.63929 | 0 | 0 | 0 | 1.25 | Open cut | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-28 | UG-28-S02 | P0333 | 4.4306 | 0.5 | -5.6 | -5.6 | -4.6 | -4.6 | 34.93 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 10.65 | Shoring | 4.4306 | 4.1 | 0.8 | 2.5 | 54.2751 | 0 | 3.323 | 0.86996 | 10.3284 | 10.3284 | 18.2715 | 18.2715
UG-28 | UG-28-S02 | P0766 | 0.66496 | 0.5 | -5.6 | -5.6 | -4.6 | -4.6 | 34.95 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 10.65 | Shoring | 0.66496 | 4.1 | 0.8 | 2.5 | 8.1458 | 0 | 0.49872 | 0.13057 | 10.3284 | 10.3284 | 18.2715 | 18.2715
UG-28 | UG-28-S02 | P0765 | 0.66502 | 0.5 | -5.6 | -5.6 | -4.6 | -4.6 | 34.98 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 10.65 | Shoring | 0.66502 | 4.1 | 0.8 | 2.5 | 8.1465 | 0 | 0.49877 | 0.13058 | 10.3284 | 10.3284 | 18.2715 | 18.2715
UG-28 | UG-28-S02 | P0169 | 0.48595 | 0.5 | -5.6 | -5.6 | -4.6 | -4.6 | 35.48 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 10.65 | Shoring | 0.48595 | 4.1 | 0.8 | 2.5 | 5.9529 | 0 | 0.36446 | 0.095416 | 10.3284 | 10.3284 | 18.2715 | 18.2715
UG-28 | UG-28-S02 | P0764 | 0.66499 | 0.5 | -5.6 | -5.6 | -4.6 | -4.6 | 35.85 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 10.65 | Shoring | 0.66499 | 4.1 | 0.8 | 2.5 | 8.1461 | 0 | 0.49874 | 0.13057 | 10.3284 | 10.3284 | 18.2715 | 18.2715
UG-28 | UG-28-S02 | P0763 | 0.665 | 0.5 | -5.6 | -5.6 | -4.6 | -4.6 | 36.35 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 10.65 | Shoring | 0.665 | 4.1 | 0.8 | 2.5 | 8.1462 | 0 | 0.49875 | 0.13057 | 10.3285 | 10.3285 | 18.2717 | 18.2717
UG-28 | UG-28-S02 | P0168 | 0.122 | 0.5 | -5.6 | -5.6 | -4.6 | -4.6 | 36.42 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 10.65 | Shoring | 0.122 | 4.1 | 0.8 | 2.5 | 1.4945 | 0 | 0.091498 | 0.023954 | 10.3285 | 10.3285 | 18.2717 | 18.2717
UG-28 | UG-28-S02 | P0167-01 | 2.3015 | 0.5 | -5.6 | -5.6 | -4.6 | -4.6 | 36.43 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 10.65 | Shoring | 2.3015 | 4.1 | 0.8 | 2.5 | 28.193 | 0 | 1.7261 | 0.45189 | 10.3285 | 10.3285 | 18.2717 | 18.2717
UG-28 | UG-28-S02 | P0167-02 | 2.4094 | 0.5 | -5.6 | -5.6 | -4.6 | -4.6 | 25.25 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 10.65 | Shoring | 2.4094 | 4.1 | 0.8 | 2.5 | 29.5154 | 0 | 1.8071 | 0.47308 | 10.3285 | 10.3285 | 18.2717 | 18.2717
UG-28 | UG-28-S02 | P0405 | 0.036 | 0.5 | -5.6 | -5.6 | -4.6 | -4.6 | 25.23 | -5.6 | -5.6 | 4.9 | 4.1 | 0.8 | 10.65 | Shoring | 0.036 | 4.1 | 0.8 | 2.5 | 0.441 | 0 | 0.027 | 0.0070685 | 10.3285 | 10.3285 | 18.2717 | 18.2717
UG-28A | UG-28A-S01 | P0404 | 0.0455 | 0.31499 | -0.5475 | -0.5475 | 0.2675 | 0.2675 | 14.08 | -0.5475 | -0.5475 | 0 | 0 | 0 | 1.1575 | Open cut | 0 | 0 | 0 | 2.315 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-28A | UG-28A-S01 | P0166 | 2.0972 | 0.31499 | -0.5475 | -0.5475 | 0.2675 | 0.2675 | 11.99 | -0.5475 | -0.5475 | 0 | 0 | 0 | 1.1575 | Open cut | 0 | 0 | 0 | 2.315 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-28A | UG-28A-S01 | P0760 | 0.773 | 0.31499 | -0.5475 | -0.54691 | 0.2675 | 0.26809 | 11.21 | -0.5475 | -0.5472 | 0 | 0 | 0 | 1.1575 | Open cut | 0 | 0 | 0 | 2.315 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-28A | UG-28A-S01 | P0762 | 1.1 | 0.315 | -0.54691 | -0.54648 | 0.26809 | 0.26852 | 11.21 | -0.54691 | -0.54669 | 0 | 0 | 0 | 1.1575 | Open cut | 0 | 0 | 0 | 2.315 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-28A | UG-28A-S01 | P0170 | 0.16999 | 0.315 | -0.54648 | -0.54635 | 0.26852 | 0.26865 | 11.24 | -0.54648 | -0.54641 | 0 | 0 | 0 | 1.1575 | Open cut | 0 | 0 | 0 | 2.315 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-28A | UG-28A-S01 | P0332-01 | 5.8143 | 0.315 | -0.54635 | -0.54188 | 0.26865 | 0.27312 | 11.25 | -0.54635 | -0.54411 | 0 | 0 | 0 | 1.1575 | Open cut | 0 | 0 | 0 | 2.315 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-28A | UG-28A-S01 | P0332-02 | 4.1427 | 0.315 | -0.54188 | -0.53869 | 0.27312 | 0.27631 | 13.08 | -0.54188 | -0.54028 | 0 | 0 | 0 | 1.1575 | Open cut | 0 | 0 | 0 | 2.315 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-28A | UG-28A-S01 | P0759 | 0.77299 | 0.315 | -0.53869 | -0.5381 | 0.27631 | 0.2769 | 13.24 | -0.53869 | -0.53839 | 0 | 0 | 0 | 1.1575 | Open cut | 0 | 0 | 0 | 2.315 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-28A | UG-28A-S01 | P0758 | 0.77903 | 0.315 | -0.5381 | -0.5375 | 0.2769 | 0.2775 | 13.24 | -0.5381 | -0.5378 | 0 | 0 | 0 | 1.1575 | Open cut | 0 | 0 | 0 | 2.315 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-28A | UG-28A-S01 | P0165 | 2.0972 | 0.31499 | -0.5375 | -0.5375 | 0.2775 | 0.2775 | 14.02 | -0.5375 | -0.5375 | 0 | 0 | 0 | 1.1575 | Open cut | 0 | 0 | 0 | 2.315 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99
UG-28A | UG-28A-S01 | P0403 | 0.04551 | 0.31499 | -0.5375 | -0.5375 | 0.2775 | 0.2775 | 16.11 | -0.5375 | -0.5375 | 0 | 0 | 0 | 1.1575 | Open cut | 0 | 0 | 0 | 2.315 | 0 | 0 | 0 | 0 | 99 | 99 | 99 | 99

## Packages
Packages - method, quantities, dewatering, flotation and dates
One row per work package from the package workbook (201). Method and quantities recalculate from Inputs and Piece check. Start / Finish come from the Activities sheet. Pile and sheet quantities are planning placeholders until designs exist.
Line | Package | Front | Planning name | Pipe type | Printed size | Package type | Tie-in structure(s) | Structure ready (date) | Aeration zones with open piles within 15 m | Aeration gate (date) | Crossing ID hold | Fittings (no.) | Planning OD (m) | Plan length (m) | R start (m) | R end (m) | R deepest (m) | Max depth below GWL (m) | Max excavation depth from NG (m) | Shored length (m) | Open-cut length (m) | Excavation method | Excavation shored (m3) | Excavation open cut (m3) | Piled slab concrete (m3) | Pipe displacement (m3) | Backfill (m3) | Pipe-support piles (no.) | Sheet pile wall (m) | Sheet pile length (m) | Sheet pile area (m2) | Drawdown required below GWL (m) | Dewatering method | Min flotation FoS, backfill to NG | Min flotation FoS, final to FL | Flotation action | Start | Finish | Sequence rank | Holds before release (package workbook) | Sequence notes (package workbook) | Interactions used in the logic | Trench open after laying (days) | Dewatering running (days)
UG-01 | UG-01-S02 | F1 | GRP-UG01-S02-EL019-EL295-(-5.44/-6.52)-276m | GRP | 28 | Run |  | 0 |  | 0 | Yes | 13 | 2.5864 | 276.0606 | -5.4426 | -6.5165 | -7.4373 | 5.9373 | 6.7373 | 276.0606 | 0 | Sheet piles | 7037.0478 | 0 | 488.87 | 1413.4105 | 5134.7674 | 188 | 552.1211 | 14 | 7729.696 | 6.4373 | Deep wells or two-stage wellpoints | 1.0999 | 2.6538 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-01 | 2027-03-01 | 14 | Common holds only (see Read Me). | Identify P0279 (no level) before excavating. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | None | -15 | 65
UG-01 | UG-01-S03 | F1 | GRP-UG01-S03-EL295-PST-(-6.52/-6.52)-29m | GRP | 28 | Tie-in | PST | 0 |  | 0 | No | 0 | 0.61306 | 29.4102 | -6.5165 | -6.5165 | -6.5165 | 5.0165 | 5.8165 | 29.4102 | 0 | Sheet piles | 447.0044 | 0 | 23.7203 | 8.6816 | 414.6026 | 11 | 58.8203 | 12 | 705.8441 | 5.5165 | Deep wells or two-stage wellpoints | 9.8167 | 16.2949 | No extra measure | 2026-12-03 | 2027-03-05 | 15 | Common holds only (see Read Me). | PST wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | closure: lay after UG-01-S02 laid | -1 | 87
UG-01 | UG-01-S01 | F1 | GRP-UG01-S01-GRT-EL019-(-5.39/-5.44)-19m | GRP | 28 | Tie-in | GRT | 0 |  | 0 | No | 2 | 2.5864 | 18.8052 | -5.3932 | -5.4426 | -5.4426 | 3.9426 | 4.7426 | 18.8052 | 0 | Sheet piles | 405.5321 | 0 | 33.662 | 98.3207 | 273.5494 | 16 | 37.6103 | 10 | 376.1033 | 4.4426 | Single-stage wellpoints | 1.0542 | 2.5898 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-03 | 2027-03-06 | 16 | Common holds only (see Read Me). | grit removal / fine screens wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | closure: lay after UG-01-S02 laid | -2 | 89
UG-02 | UG-02-S03 | F1 | GRP-UG02-S03-CH091-CH156-(-5.81/-6.17)-65m | GRP | 28 | Run |  | 0 | 3, 5 (18 piles) | 2026-11-07 | No | 0 | 2.0696 | 65.1 | -5.8081 | -6.1678 | -6.1678 | 4.6678 | 5.4678 | 65.1 | 0 | Sheet piles | 1400.9398 | 0 | 99.9158 | 219.0018 | 1082.0222 | 46 | 130.2 | 11 | 1432.2 | 5.1678 | Deep wells or two-stage wellpoints | 1.796 | 3.715 | No extra measure | 2026-12-03 | 2027-05-14 | 17 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). | One shared excavation and dewatering front with UG-03: lay all pipes before backfill. Decide the sequence against the 18 pending piles within 15 m. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-03-S01: backfill after both laid; shared trench with UG-03-S02: backfill after both laid | 64 | 104
UG-02 | UG-02-S02 | F1 | GRP-UG02-S02-EL013-CH091-(-5.38/-5.81)-78m | GRP | 28 | Run |  | 0 | 5 (4 piles) | 2026-11-07 | No | 0 | 2.0696 | 78.0475 | -5.3769 | -5.8081 | -5.8081 | 4.3081 | 5.1081 | 78.0475 | 0 | Sheet piles | 1553.9705 | 0 | 119.7877 | 262.5583 | 1171.6246 | 56 | 156.095 | 11 | 1717.0451 | 4.8081 | Deep wells or two-stage wellpoints | 1.5745 | 3.4935 | No extra measure | 2027-01-17 | 2027-05-20 | 18 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). | Decide the sequence against the 4 pending piles within 15 m. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-03-S01: backfill after both laid | 57 | 103
UG-02 | UG-02-S05 | F1 | GRP-UG02-S05-EL261-IPS-(-6.72/-6.73)-6m | GRP | 28 | Tie-in | IPS | 0 | 8 (3 piles) | 2026-11-29 | No | 0 | 2.0696 | 5.9679 | -6.725 | -6.7348 | -6.7348 | 5.2348 | 6.0348 | 5.9679 | 0 | Sheet piles | 146.4466 | 0 | 9.1595 | 20.0762 | 117.211 | 6 | 11.9357 | 13 | 155.1644 | 5.7348 | Deep wells or two-stage wellpoints | 2.2669 | 4.1859 | No extra measure | 2027-02-12 | 2027-05-21 | 19 | Common holds only (see Read Me). | IPS wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-03: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-24 before that line. Decide the sequence against the 3 pending piles within 15 m. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-24-S01: complete first; shared trench with UG-03-S04: start excavation with it; shared trench with UG-03-S05: start excavation with it; closure: lay after UG-02-S04 laid | 17 | 95
UG-02 | UG-02-S04 | F1 | GRP-UG02-S04-CH156-EL261-(-6.17/-6.72)-105m | GRP | 28 | Run |  | 0 | 3, 8 (32 piles) | 2026-11-29 | Yes | 2 | 2.0696 | 105.1941 | -6.1678 | -6.725 | -6.725 | 5.225 | 6.025 | 105.1941 | 0 | Sheet piles | 2464.8407 | 0 | 161.4523 | 353.8815 | 1949.5068 | 74 | 210.3881 | 13 | 2735.0459 | 5.725 | Deep wells or two-stage wellpoints | 1.9807 | 3.8997 | No extra measure | 2027-01-29 | 2027-06-09 | 20 | Common holds only (see Read Me). | One shared excavation and dewatering front with UG-03: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-24 before that line. Identify P0114 (no level) before excavating. Decide the sequence against the 32 pending piles within 15 m. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-24-S01: complete first; shared trench with UG-03-S01: backfill after both laid; shared trench with UG-03-S02: backfill after both laid; shared trench with UG-03-S03: backfill after both laid; shared trench with UG-03-S04: backfill after both laid; shared trench with UG-03-S05: start excavation with it | 40 | 107
UG-03 | UG-03-S01 | F1 | GRP-UG03-S01-EXPST-CH066-(-5.10/-5.86)-66m | GRP | 28 | Run |  | 0 |  | 0 | No | 3 | 2.0412 | 66 | -5.0959 | -5.8573 | -5.8573 | 4.3573 | 5.1573 | 66 | 0 | Sheet piles | 1291.1983 | 0 | 99.4565 | 210.8787 | 980.8631 | 46 | 132 | 11 | 1452 | 4.8573 | Deep wells or two-stage wellpoints | 1.5923 | 3.538 | No extra measure | 2027-02-12 | 2027-06-13 | 21 | existing PST (not modelled): structure not in the master model, tie-in position not checked. | One shared excavation and dewatering front with UG-02: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-24-S01: complete first; shared trench with UG-02-S02: start excavation with it; shared trench with UG-02-S03: start excavation with it; shared trench with UG-02-S04: start excavation with it | 36 | 73
UG-03 | UG-03-S02 | F1 | GRP-UG03-S02-CH066-CH082-(-5.86/-5.99)-16m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.0412 | 16 | -5.8573 | -5.9899 | -5.9899 | 4.4899 | 5.2899 | 16 | 0 | Sheet piles | 337.7545 | 0 | 24.3296 | 52.3578 | 261.0671 | 14 | 32 | 11 | 352 | 4.9899 | Deep wells or two-stage wellpoints | 1.8614 | 3.8071 | No extra measure | 2027-03-02 | 2027-06-14 | 22 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). | One shared excavation and dewatering front with UG-02: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-24 before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-24-S01: complete first; shared trench with UG-02-S03: start excavation with it; shared trench with UG-02-S04: start excavation with it | 34 | 66
UG-03 | UG-03-S04 | F1 | GRP-UG03-S04-CH168-EL175-(-6.70/-6.73)-7m | GRP | 28 | Run |  | 0 |  | 0 | No | 2 | 2.0696 | 6.9804 | -6.7039 | -6.7284 | -6.7284 | 5.2284 | 6.0284 | 6.9804 | 0 | Sheet piles | 170.2884 | 0 | 10.6579 | 23.1234 | 136.5071 | 8 | 13.9608 | 13 | 181.49 | 5.7284 | Deep wells or two-stage wellpoints | 2.2677 | 4.1868 | No extra measure | 2027-03-14 | 2027-06-16 | 23 | Common holds only (see Read Me). | One shared excavation and dewatering front with UG-02, UG-04: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-24 before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-24-S01: complete first; shared trench with UG-02-S04: start excavation with it; shared trench with UG-02-S05: backfill after both laid; shared trench with UG-04-S01: backfill after both laid; shared trench with UG-04-S02: backfill after both laid | 31 | 65
UG-03 | UG-03-S05 | F1 | GRP-UG03-S05-EL175-IPS-(-6.73/-6.73)-11m | GRP | 28 | Tie-in | IPS | 0 |  | 0 | No | 0 | 2.0696 | 10.9788 | -6.7284 | -6.7348 | -6.7348 | 5.2348 | 6.0348 | 10.9788 | 0 | Sheet piles | 269.4872 | 0 | 16.8502 | 36.9331 | 215.7038 | 10 | 21.9576 | 13 | 285.4483 | 5.7348 | Deep wells or two-stage wellpoints | 2.2687 | 4.1877 | No extra measure | 2027-03-18 | 2027-05-26 | 24 | Common holds only (see Read Me). | IPS wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-02, UG-04: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-24 before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-24-S01: complete first; shared trench with UG-02-S04: backfill after both laid; shared trench with UG-02-S05: backfill after both laid; shared trench with UG-04-S01: backfill after both laid; shared trench with UG-04-S02: backfill after both laid; closure: lay after UG-03-S04 laid | 5 | 66
UG-04 | UG-04-S01 | F1 | GRP-UG04-S01-EXPST-EL010-(-5.09/-5.86)-10m | GRP | 28 | Run |  | 0 |  | 0 | No | 5 | 2.0696 | 10.3097 | -5.0858 | -5.8622 | -5.8622 | 4.3622 | 5.1622 | 10.3097 | 0 | Sheet piles | 191.5741 | 0 | 14.9574 | 29.7652 | 146.8515 | 10 | 20.6194 | 11 | 226.8132 | 4.8622 | Deep wells or two-stage wellpoints | 1.5923 | 3.538 | No extra measure | 2027-03-18 | 2027-06-18 | 25 | existing PST (not modelled): structure not in the master model, tie-in position not checked. | One shared excavation and dewatering front with UG-03: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-24 before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-24-S01: complete first; shared trench with UG-03-S04: start excavation with it; shared trench with UG-03-S05: start excavation with it | 28 | 65
UG-04 | UG-04-S02 | F1 | GRP-UG04-S02-EL010-IPS-(-5.86/-6.73)-12m | GRP | 28 | Tie-in | IPS | 0 |  | 0 | No | 0 | 2.0696 | 12.3452 | -5.8622 | -6.7348 | -6.7348 | 5.2348 | 6.0348 | 12.3452 | 0 | Sheet piles | 281.2679 | 0 | 18.9474 | 41.5298 | 220.7907 | 12 | 24.6904 | 13 | 320.9752 | 5.7348 | Deep wells or two-stage wellpoints | 1.8238 | 3.7428 | No extra measure | 2027-03-21 | 2027-05-28 | 26 | Common holds only (see Read Me). | IPS wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-03: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-24 before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-24-S01: complete first; deeper than UG-24-S02: complete first; shared trench with UG-03-S04: start excavation with it; shared trench with UG-03-S05: start excavation with it; closure: lay after UG-04-S01 laid | -1 | 64
UG-03 | UG-03-S03 | F1 | GRP-UG03-S03-CH082-CH168-(-5.99/-6.70)-86m | GRP | 28 | Run |  | 0 |  | 0 | Yes | 0 | 2.0412 | 86.1 | -5.9899 | -6.7039 | -6.7039 | 5.2039 | 6.0039 | 86.1 | 0 | Sheet piles | 1964.8304 | 0 | 130.9237 | 281.7502 | 1552.1566 | 60 | 172.2 | 13 | 2238.6 | 5.7039 | Deep wells or two-stage wellpoints | 1.9305 | 3.8762 | No extra measure | 2027-03-21 | 2027-06-24 | 27 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). | One shared excavation and dewatering front with UG-02: lay all pipes before backfill. Identify P0117 (no level) before excavating. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-24-S01: complete first; shared trench with UG-02-S04: start excavation with it | 17 | 71
UG-02 | UG-02-S01 | F1 | GRP-UG02-S01-PST08-EL013-(-5.10/-5.38)-13m | GRP | 28 | Tie-in | PST08 | 0 |  | 0 | No | 3 | 2.0696 | 13.0525 | -5.0959 | -5.3769 | -5.3769 | 3.8769 | 4.6769 | 13.0525 | 0 | Sheet piles | 232.2498 | 0 | 18.8526 | 37.1869 | 176.2103 | 12 | 26.105 | 10 | 261.0499 | 4.3769 | Single-stage wellpoints | 1.5632 | 3.4822 | No extra measure | 2027-01-29 | 2027-03-29 | 28 | Common holds only (see Read Me). | PST basin 08 wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | closure: lay after UG-02-S02 laid | -2 | 55
UG-06 | UG-06-S02 | F2 | GRP-UG06-S02-EL021-CH049-(-4.05/-4.05)-28m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.249 | 27.9154 | -4.0545 | -4.0545 | -4.0545 | 2.5545 | 3.3545 | 27.9154 | 0 | Sheet piles | 397.885 | 0 | 45.3485 | 110.8948 | 241.6418 | 22 | 55.8308 | 7 | 390.8155 | 3.0545 | Single-stage wellpoints | 0.62899 | 2.3949 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-01 | 2026-12-30 | 175 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R007: Embedded prior source review identifies plan/section level differences at shown locations. R011: Component material HDPE differs from scheduled whole-line material GRP. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | None | -3 | 25
UG-25 | UG-25-S01 | F2 | GRP-UG25-S01-BYPCH-OUTF-(-4.55/-4.70)-495m | GRP | 28 | Run |  | 0 |  | 0 | No | 11 | 2.4836 | 495.2172 | -4.5518 | -4.7018 | -4.7018 | 3.2018 | 4.0018 | 495.2172 | 0 | Sheet piles | 8609.0665 | 0 | 862.2591 | 2396.6977 | 5350.1097 | 334 | 990.4344 | 9 | 8913.9093 | 3.7018 | Single-stage wellpoints | 0.78172 | 2.3808 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-02 | 2027-05-15 | 176 | R046: Component material HDPE differs from scheduled whole-line material GRP. Flow direction: levels: higher end taken as upstream (gravity assumption). overflow bypass chamber (not modelled): structure not in the master model, tie-in position not checked. outfall chamber (not modelled): structure not in the master model, tie-in position not checked. | One shared excavation and dewatering front with UG-26: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-05-S05: backfill after both laid; shared trench with UG-06-S05: backfill after both laid; shared trench with UG-26-S01: backfill after both laid | 61 | 140
UG-26 | UG-26-S01 | F2 | GRP-UG26-S01-BYPCH-OUTF-(-4.19/-4.56)-496m | GRP | 28 | Run |  | 0 |  | 0 | No | 6 | 2.4836 | 495.7146 | -4.1918 | -4.5618 | -4.5618 | 3.0618 | 3.8618 | 495.7146 | 0 | Sheet piles | 8189.5843 | 0 | 863.4343 | 2401.5018 | 4924.6483 | 334 | 991.4292 | 8 | 7931.4332 | 3.5618 | Single-stage wellpoints | 0.44983 | 2.049 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-06 | 2027-05-25 | 177 | Flow direction: levels: higher end taken as upstream (gravity assumption). overflow bypass chamber (not modelled): structure not in the master model, tie-in position not checked. outfall chamber (not modelled): structure not in the master model, tie-in position not checked. | One shared excavation and dewatering front with UG-25: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-05-S05: backfill after both laid; shared trench with UG-06-S05: backfill after both laid; shared trench with UG-25-S01: start excavation with it | 32 | 110
UG-06 | UG-06-S05 | F2 | GRP-UG06-S05-CH278-CHUG25-(-4.13/-4.12)-22m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.249 | 22.1072 | -4.1259 | -4.1245 | -4.1259 | 2.6259 | 3.4259 | 22.1072 | 0 | Sheet piles | 321.7389 | 0 | 35.9132 | 87.8219 | 198.0039 | 18 | 44.2144 | 7 | 309.5008 | 3.1259 | Single-stage wellpoints | 0.7017 | 2.4676 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-15 | 2027-05-12 | 178 | R007: Embedded prior source review identifies plan/section level differences at shown locations. chamber connecting UG-25 (not modelled): structure not in the master model, tie-in position not checked. | One shared excavation and dewatering front with UG-05: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-12A-S03: complete first; shared trench with UG-05-S04: backfill after both laid; shared trench with UG-05-S05: backfill after both laid; shared trench with UG-25-S01: start excavation with it; shared trench with UG-26-S01: start excavation with it | 38 | 73
UG-06 | UG-06-S04 | F2 | GRP-UG06-S04-CH147-CH278-(-4.13/-4.13)-130m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.249 | 130.4 | -4.1338 | -4.1259 | -4.1338 | 2.6338 | 3.4338 | 130.4 | 0 | Sheet piles | 1900.3754 | 0 | 211.8348 | 518.02 | 1170.5205 | 90 | 260.8 | 7 | 1825.6 | 3.1338 | Single-stage wellpoints | 0.7031 | 2.469 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-02-24 | 2027-05-28 | 179 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R007: Embedded prior source review identifies plan/section level differences at shown locations. | One shared excavation and dewatering front with UG-05, UG-12A: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-12A-S03: complete first; deeper than UG-12A-S04: complete first; deeper than UG-12A-S07: complete first; deeper than UG-12A-S08: complete first; shared trench with UG-05-S03: backfill after both laid; shared trench with UG-05-S04: backfill after both laid; shared trench with UG-05-S05: backfill after both laid | 37 | 83
UG-05 | UG-05-S05 | F2 | GRP-UG05-S05-CH282-CHUG25-(-4.12/-4.12)-25m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.249 | 25.0174 | -4.123 | -4.1245 | -4.1245 | 2.6245 | 3.4245 | 25.0174 | 0 | Sheet piles | 363.9417 | 0 | 40.6408 | 99.3829 | 223.918 | 20 | 50.0349 | 7 | 350.2441 | 3.1245 | Single-stage wellpoints | 0.70014 | 2.4661 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-02-27 | 2027-05-26 | 180 | R007: Embedded prior source review identifies plan/section level differences at shown locations. chamber connecting UG-25 (not modelled): structure not in the master model, tie-in position not checked. | One shared excavation and dewatering front with UG-06: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-06-S04: start excavation with it; shared trench with UG-06-S05: start excavation with it; shared trench with UG-25-S01: start excavation with it; shared trench with UG-26-S01: start excavation with it | 34 | 74
UG-06 | UG-06-S03 | F2 | GRP-UG06-S03-CH049-CH147-(-4.05/-4.13)-98m | GRP | 28 | Run |  | 0 |  | 0 | No | 6 | 2.249 | 98.3 | -4.0545 | -4.1338 | -4.1345 | 2.6345 | 3.4345 | 98.3 | 0 | Sheet piles | 1408.204 | 0 | 159.6882 | 390.4998 | 858.016 | 68 | 196.6 | 7 | 1376.2 | 3.1345 | Single-stage wellpoints | 0.62898 | 2.3949 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-03-10 | 2027-06-01 | 181 | R007: Embedded prior source review identifies plan/section level differences at shown locations. R011: Component material HDPE differs from scheduled whole-line material GRP. | One shared excavation and dewatering front with UG-05: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-12A-S05: complete first; shared trench with UG-05-S02: backfill after both laid; shared trench with UG-05-S03: backfill after both laid; shared trench with UG-05-S04: backfill after both laid | 28 | 75
UG-05 | UG-05-S04 | F2 | GRP-UG05-S04-CH158-CH282-(-4.12/-4.12)-123m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.249 | 123.2 | -4.1156 | -4.123 | -4.123 | 2.623 | 3.423 | 123.2 | 0 | Sheet piles | 1789.9342 | 0 | 200.1384 | 489.4177 | 1100.3781 | 86 | 246.4 | 7 | 1724.8 | 3.123 | Single-stage wellpoints | 0.69249 | 2.4584 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-03-13 | 2027-06-05 | 182 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R007: Embedded prior source review identifies plan/section level differences at shown locations. | One shared excavation and dewatering front with UG-06, UG-12A: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-12A-S03: complete first; deeper than UG-12A-S04: complete first; deeper than UG-12A-S08: complete first; shared trench with UG-06-S03: start excavation with it; shared trench with UG-06-S04: start excavation with it; shared trench with UG-06-S05: start excavation with it | 20 | 69
UG-05 | UG-05-S03 | F2 | GRP-UG05-S03-CH054-CH158-(-3.82/-4.12)-104m | GRP | 28 | Run |  | 0 |  | 0 | No | 4 | 2.249 | 104.2 | -3.8221 | -4.1156 | -4.1156 | 2.6156 | 3.4156 | 58.3 | 45.9 | Mixed: 58 m sheet piles | 834.5923 | 1550.2749 | 169.273 | 413.9399 | 1801.6543 | 72 | 116.6 | 7 | 816.2 | 3.1156 | Single-stage wellpoints | 0.38759 | 2.1535 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-03-22 | 2027-06-07 | 183 | R007: Embedded prior source review identifies plan/section level differences at shown locations. | One shared excavation and dewatering front with UG-06: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-06-S03: start excavation with it; shared trench with UG-06-S04: start excavation with it | 13 | 61
UG-05 | UG-05-S02 | F2 | GRP-UG05-S02-CH006-CH054-(-3.66/-3.82)-48m | GRP | 28 | Run |  | 0 |  | 0 | No | 2 | 2.2764 | 48.1 | -3.6603 | -3.8221 | -3.8221 | 2.3221 | 3.1221 | 0 | 48.1 | Open cut | 0 | 1502.7067 | 78.6404 | 194.6477 | 1229.4186 | 36 | 0 | 0 | 0 | 2.8221 | Single-stage wellpoints | 0.18879 | 1.9335 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-04-02 | 2027-07-18 | 184 | R007: Embedded prior source review identifies plan/section level differences at shown locations. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-06-S03: start excavation with it; shared trench with UG-24-S01: backfill after both laid; shared trench with UG-24-S02: backfill after both laid | 49 | 95
UG-06 | UG-06-S01 | F2 | GRP-UG06-S01-IPS-EL021-(-4.07/-4.05)-21m | GRP | 28 | Tie-in | IPS | 0 |  | 0 | No | 4 | 2.2764 | 21.1846 | -4.0682 | -4.0545 | -4.0682 | 2.5682 | 3.3682 | 21.1846 | 0 | Sheet piles | 303.281 | 0 | 34.5356 | 85.0181 | 183.7273 | 18 | 42.3692 | 7 | 296.5845 | 3.0682 | Single-stage wellpoints | 0.60737 | 2.3521 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-02 | 2027-06-03 | 185 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R007: Embedded prior source review identifies plan/section level differences at shown locations. R012: Component material HDPE differs from scheduled whole-line material GRP. | IPS wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-05-S01: backfill after both laid; closure: lay after UG-06-S02 laid | 150 | 180
UG-05 | UG-05-S01 | F2 | GRP-UG05-S01-IPS-CH006-(-3.64/-3.66)-6m | GRP | 28 | Tie-in | IPS | 0 |  | 0 | No | 0 | 2.2764 | 6 | -3.6382 | -3.6603 | -3.6603 | 2.1603 | 2.9603 | 0 | 6 | Open cut | 0 | 178.132 | 9.8292 | 24.4194 | 143.8834 | 6 | 0 | 0 | 0 | 2.6603 | Single-stage wellpoints | 0.16606 | 1.9107 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-04-12 | 2027-07-17 | 186 | R007: Embedded prior source review identifies plan/section level differences at shown locations. | IPS wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-06-S01: start excavation with it; shared trench with UG-24-S01: backfill after both laid; shared trench with UG-24-S02: backfill after both laid; closure: lay after UG-05-S02 laid | 44 | 94
UG-24 | UG-24-S01 | F2 | GRP-UG24-S01-EXPST-EL124-(-2.60/-3.02)-124m | GRP | 28 | Run |  | 0 | 3, 8 (31 piles) | 2026-11-29 | No | 8 | 2.045 | 123.7455 | -2.6 | -3.0225 | -3.0225 | 1.5225 | 2.3225 | 70 | 53.7455 | Mixed: 70 m sheet piles | 656.4329 | 1015.9257 | 185.1792 | 388.8128 | 1098.3666 | 86 | 140 | 5 | 700 | 2.0225 | Single-stage wellpoints | 0 | 1.6879 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-04-12 | 2027-07-22 | 187 | R041: Component material HDPE differs from scheduled whole-line material GRP. R042: Component material HDPE differs from scheduled whole-line material GRP. R043: Component material HDPE differs from scheduled whole-line material GRP. R044: Component material HDPE differs from scheduled whole-line material GRP. R045: Component material HDPE differs from scheduled whole-line material GRP. existing PST (not modelled): structure not in the master model, tie-in position not checked. | UG-02, UG-03, UG-04 is deeper here: lay and backfill it first. Decide the sequence against the 31 pending piles within 15 m. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-02-S04 backfilled (deeper); excavate after UG-02-S05 backfilled (deeper); excavate after UG-03-S01 backfilled (deeper); excavate after UG-03-S02 backfilled (deeper); excavate after UG-03-S03 backfilled (deeper); excavate after UG-03-S04 backfilled (deeper); excavate after UG-03-S05 backfilled (deeper); excavate after UG-04-S01 backfilled (deeper); excavate after UG-04-S02 backfilled (deeper); shared trench with UG-05-S01: start excavation with it; shared trench with UG-05-S02: start excavation with it; built by F2 (shared corridor; line system front F1) | 8 | 90
UG-24 | UG-24-S02 | F2 | GRP-UG24-S02-EL124-IPS-(-3.03/-3.03)-3m | GRP | 28 | Tie-in | IPS | 0 |  | 0 | No | 0 | 2.0696 | 3.0856 | -3.0348 | -3.0348 | -3.0348 | 1.5348 | 2.3348 | 0 | 3.0856 | Open cut | 0 | 61.972 | 4.7358 | 10.3801 | 46.8561 | 6 | 0 | 0 | 0 | 2.0348 | Single-stage wellpoints | 0 | 1.654 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-04-17 | 2027-07-19 | 188 | Common holds only (see Read Me). | IPS wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. UG-02 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-04-S02 backfilled (deeper); shared trench with UG-05-S01: start excavation with it; shared trench with UG-05-S02: start excavation with it; closure: lay after UG-24-S01 laid; built by F2 (shared corridor; line system front F1) | -1 | 91
UG-10 | UG-10-S04 | F3 | GRP-UG10-S04-CH146-CH200-(-3.76/-5.01)-53m | GRP | 28 | Run |  | 0 |  | 0 | No | 2 | 2.69 | 53.199 | -3.761 | -5.005 | -5.005 | 3.505 | 4.305 | 53.199 | 0 | Sheet piles | 1038.8937 | 0 | 98.1522 | 302.3416 | 638.4 | 38 | 106.398 | 9 | 957.582 | 4.005 | Single-stage wellpoints | 0 | 1.3644 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-01 | 2027-02-14 | 118 | Common holds only (see Read Me). | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-15-S02 backfilled (deeper) | -5 | 69
UG-10 | UG-10-S05 | F3 | GRP-UG10-S05-CH200-SDCA-(-5.01/-5.01)-6m | GRP | 28 | Tie-in | SDCA | 0 |  | 0 | No | 0 | 2.69 | 5.9997 | -5.005 | -5.005 | -5.005 | 3.505 | 4.305 | 5.9997 | 0 | Sheet piles | 121.1373 | 0 | 11.0695 | 34.0978 | 75.97 | 6 | 11.9995 | 9 | 107.9952 | 4.005 | Single-stage wellpoints | 0.81926 | 2.2957 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-02 | 2027-02-19 | 119 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). | secondary distribution chamber A wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-16A-S01: complete first; deeper than UG-16B-S01: complete first; closure: lay after UG-10-S04 laid | -1 | 76
UG-10 | UG-10-S03 | F3 | GRP-UG10-S03-CH114-CH146-(-3.36/-3.76)-32m | GRP | 28 | Run |  | 0 |  | 0 | No | 2 | 2.69 | 32.1 | -3.3584 | -3.761 | -3.761 | 2.261 | 3.061 | 15.7 | 16.4 | Mixed: 16 m sheet piles | 197.0752 | 464.5825 | 58.7767 | 178.6704 | 424.2106 | 24 | 31.4 | 7 | 219.8 | 2.761 | Single-stage wellpoints | 0 | 1.0564 | Anchor pipe to piled slab (permanent straps) | 2026-12-02 | 2027-02-21 | 120 | Common holds only (see Read Me). | UG-15, UG-22 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-15-S02 backfilled (deeper); excavate after UG-15-S03 backfilled (deeper); excavate after UG-21-S01 backfilled (deeper); excavate after UG-22-S01 backfilled (deeper); deeper than UG-28-S01: complete first; excavate after UG-28-S02 backfilled (deeper); deeper than UG-28A-S01: complete first | -2 | 31
UG-10 | UG-10-S02 | F3 | GRP-UG10-S02-EL007-CH114-(-3.19/-3.36)-107m | GRP | 28 | Run |  | 0 | 4, 7 (80 piles) | 2026-11-23 | No | 2 | 2.657 | 106.8559 | -3.1885 | -3.3584 | -3.3584 | 1.8584 | 2.6584 | 106.8559 | 0 | Sheet piles | 1252.6038 | 0 | 195.3858 | 592.4751 | 464.7429 | 74 | 213.7118 | 6 | 1282.2711 | 2.3584 | Single-stage wellpoints | 0 | 0.90697 | Anchor pipe to piled slab (permanent straps) | 2026-12-12 | 2027-03-07 | 121 | Common holds only (see Read Me). | UG-21, UG-28 is deeper here: lay and backfill it first. Decide the sequence against the 79 pending piles within 15 m. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-21-S01 backfilled (deeper); excavate after UG-22-S01 backfilled (deeper); deeper than UG-28-S01: complete first; excavate after UG-28-S02 backfilled (deeper); deeper than UG-28A-S01: complete first | -6 | 44
UG-10 | UG-10-S01 | F3 | GRP-UG10-S01-AER-EL007-(-3.20/-3.19)-7m | GRP | 28 | Tie-in | AER | 0 | 7 (1 piles) | 2026-11-23 | No | 2 | 2.69 | 7.4441 | -3.205 | -3.1885 | -3.205 | 1.705 | 2.505 | 5.2 | 2.2441 | Mixed: 5 m sheet piles | 60.6771 | 53.8096 | 13.6914 | 41.9459 | 58.8494 | 8 | 10.4 | 6 | 62.4 | 2.205 | Single-stage wellpoints | 0 | 0.88151 | Anchor pipe to piled slab (permanent straps) | 2026-12-18 | 2027-03-13 | 124 | Common holds only (see Read Me). | aeration tank wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Decide the sequence against the 1 pending piles within 15 m. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | closure: lay after UG-10-S02 laid | -2 | 82
UG-08 | UG-08-S06 | F3 | GRP-UG08-S06-CH224-CH277-(-4.99/-4.99)-53m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.657 | 53.014 | -4.9885 | -4.9885 | -4.9885 | 3.4885 | 4.2885 | 53.014 | 0 | Sheet piles | 1058.7712 | 0 | 96.9361 | 293.9431 | 667.892 | 38 | 106.028 | 9 | 954.252 | 3.9885 | Single-stage wellpoints | 0.83604 | 2.3308 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-18 | 2027-05-27 | 125 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-09-S06: backfill after both laid | 71 | 117
UG-09 | UG-09-S07 | F3 | GRP-UG09-S07-CH231-CH282-(-4.98/-4.98)-51m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.657 | 51.1819 | -4.9785 | -4.9785 | -4.9785 | 3.4785 | 4.2785 | 51.1819 | 0 | Sheet piles | 1019.7951 | 0 | 93.5859 | 283.7834 | 642.4258 | 38 | 102.3637 | 9 | 921.2733 | 3.9785 | Single-stage wellpoints | 0.83204 | 2.3268 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-05 | 2027-05-30 | 126 | Common holds only (see Read Me). | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-08-S05: backfill after both laid | 64 | 114
UG-08 | UG-08-S05 | F3 | GRP-UG08-S05-CH108-CH224-(-3.18/-4.99)-116m | GRP | 28 | Run |  | 0 |  | 0 | No | 8 | 2.69 | 116.1 | -3.175 | -4.9885 | -4.9885 | 3.4885 | 4.2885 | 54.1 | 62 | Mixed: 54 m sheet piles | 886.8239 | 1474.3357 | 213.002 | 649.7275 | 1498.43 | 80 | 108.2 | 9 | 973.8 | 3.9885 | Single-stage wellpoints | 0 | 0.85546 | Anchor pipe to piled slab (permanent straps) | 2027-01-15 | 2027-06-25 | 127 | Common holds only (see Read Me). | One shared excavation and dewatering front with UG-09: lay all pipes before backfill. UG-12, UG-13B is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-12-S03 backfilled (deeper); excavate after UG-13-S03 backfilled (deeper); excavate after UG-13B-S11 backfilled (deeper); shared trench with UG-09-S04: backfill after both laid; shared trench with UG-09-S05: backfill after both laid; shared trench with UG-09-S06: backfill after both laid; shared trench with UG-09-S07: start excavation with it | 72 | 135
UG-09 | UG-09-S06 | F3 | GRP-UG09-S06-CH168-CH231-(-3.30/-4.98)-62m | GRP | 28 | Run |  | 0 |  | 0 | No | 2 | 2.657 | 62.1171 | -3.2982 | -4.9785 | -4.9785 | 3.4785 | 4.2785 | 60.6171 | 1.5 | Mixed: 61 m sheet piles | 976.3561 | 38.3814 | 113.5811 | 344.4163 | 556.7401 | 44 | 121.2343 | 9 | 1091.1087 | 3.9785 | Single-stage wellpoints | 0 | 1.0034 | Anchor pipe to piled slab (permanent straps) | 2027-01-25 | 2027-06-29 | 128 | Common holds only (see Read Me). | One shared excavation and dewatering front with UG-08: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-13B-S08 backfilled (deeper); shared trench with UG-08-S05: start excavation with it; shared trench with UG-08-S06: start excavation with it | 33 | 110
UG-09 | UG-09-S05 | F3 | GRP-UG09-S05-CH150-CH168-(-3.17/-3.30)-18m | GRP | 28 | Run |  | 0 |  | 0 | No | 6 | 2.69 | 18.1 | -3.175 | -3.2982 | -3.2982 | 1.7982 | 2.5982 | 0 | 18.1 | Open cut | 0 | 430.3442 | 33.1406 | 100.7392 | 296.4645 | 16 | 0 | 0 | 0 | 2.2982 | Single-stage wellpoints | 0 | 0.85546 | Anchor pipe to piled slab (permanent straps) | 2027-02-13 | 2027-06-30 | 129 | Common holds only (see Read Me). | One shared excavation and dewatering front with UG-08: lay all pipes before backfill. UG-13B is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-12-S03 backfilled (deeper); excavate after UG-13B-S07 backfilled (deeper); excavate after UG-13B-S08 backfilled (deeper); excavate after UG-13B-S09 backfilled (deeper); excavate after UG-13B-S11 backfilled (deeper); shared trench with UG-08-S05: start excavation with it | 30 | 60
UG-08 | UG-08-S04 | F3 | GRP-UG08-S04-CH060-CH108-(-3.17/-3.18)-48m | GRP | 28 | Run |  | 0 |  | 0 | No | 3 | 2.69 | 48 | -3.175 | -3.175 | -3.175 | 1.675 | 2.475 | 0 | 48 | Open cut | 0 | 1129.8708 | 88.5599 | 272.794 | 768.5168 | 34 | 0 | 0 | 0 | 2.175 | Single-stage wellpoints | 0 | 0.85546 | Anchor pipe to piled slab (permanent straps) | 2027-02-24 | 2027-07-11 | 130 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). | One shared excavation and dewatering front with UG-09: lay all pipes before backfill. UG-13, UG-23 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-11-S03 backfilled (deeper); excavate after UG-11-S04 backfilled (deeper); excavate after UG-13-S05 backfilled (deeper); excavate after UG-23-S02 backfilled (deeper); excavate after UG-23-S03 backfilled (deeper); excavate after UG-23-S04 backfilled (deeper); shared trench with UG-09-S03: backfill after both laid; shared trench with UG-09-S04: backfill after both laid | 30 | 70
UG-09 | UG-09-S04 | F3 | GRP-UG09-S04-CH067-CH150-(-3.16/-3.17)-83m | GRP | 28 | Run |  | 0 |  | 0 | No | 4 | 2.69 | 83.2 | -3.1585 | -3.175 | -3.175 | 1.675 | 2.475 | 0 | 83.2 | Open cut | 0 | 1958.308 | 153.497 | 472.7849 | 1332.0262 | 58 | 0 | 0 | 0 | 2.175 | Single-stage wellpoints | 0 | 0.85546 | Anchor pipe to piled slab (permanent straps) | 2027-03-01 | 2027-07-16 | 131 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). | One shared excavation and dewatering front with UG-08: lay all pipes before backfill. UG-12, UG-13B, UG-23 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-12-S03 backfilled (deeper); excavate after UG-13B-S07 backfilled (deeper); excavate after UG-13B-S08 backfilled (deeper); excavate after UG-13B-S11 backfilled (deeper); excavate after UG-23-S03 backfilled (deeper); excavate after UG-23-S04 backfilled (deeper); shared trench with UG-08-S03: backfill after both laid; shared trench with UG-08-S04: start excavation with it; shared trench with UG-08-S05: start excavation with it | 22 | 72
UG-08 | UG-08-S03 | F3 | GRP-UG08-S03-CH038-CH060-(-3.16/-3.17)-22m | GRP | 28 | Run |  | 0 |  | 0 | No | 2 | 2.69 | 22 | -3.1585 | -3.175 | -3.175 | 1.675 | 2.475 | 18.908 | 3.092 | Mixed: 19 m sheet piles | 216.4823 | 71.9462 | 40.2351 | 122.0499 | 126.1435 | 18 | 37.8161 | 5 | 189.0804 | 2.175 | Single-stage wellpoints | 0 | 0.85546 | Anchor pipe to piled slab (permanent straps) | 2027-03-10 | 2027-07-18 | 132 | Common holds only (see Read Me). | One shared excavation and dewatering front with UG-09: lay all pipes before backfill. UG-11, UG-23 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-11-S03 backfilled (deeper); excavate after UG-11-S04 backfilled (deeper); excavate after UG-23-S03 backfilled (deeper); excavate after UG-23-S04 backfilled (deeper); excavate after UG-23-S05 backfilled (deeper); shared trench with UG-09-S02: backfill after both laid; shared trench with UG-09-S03: backfill after both laid; shared trench with UG-09-S04: start excavation with it | 21 | 66
UG-08 | UG-08-S02 | F3 | GRP-UG08-S02-EL021-CH038-(-3.16/-3.16)-17m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.657 | 17.4789 | -3.1585 | -3.1585 | -3.1585 | 1.6585 | 2.4585 | 17.4789 | 0 | Sheet piles | 200.1199 | 0 | 31.9602 | 96.914 | 71.2457 | 14 | 34.9578 | 5 | 174.789 | 2.1585 | Single-stage wellpoints | 0 | 0.88059 | Anchor pipe to piled slab (permanent straps) | 2027-03-24 | 2027-07-22 | 133 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). | One shared excavation and dewatering front with UG-09: lay all pipes before backfill. UG-23 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-11-S04 backfilled (deeper); excavate after UG-23-S04 backfilled (deeper); excavate after UG-23-S05 backfilled (deeper); shared trench with UG-09-S01: backfill after both laid; shared trench with UG-09-S02: backfill after both laid; shared trench with UG-09-S03: backfill after both laid | 19 | 67
UG-09 | UG-09-S03 | F3 | GRP-UG09-S03-CH044-CH067-(-3.16/-3.16)-23m | GRP | 28 | Run |  | 0 |  | 0 | No | 1 | 2.657 | 23.1 | -3.1585 | -3.1585 | -3.1585 | 1.6585 | 2.4585 | 5.9 | 17.2 | Mixed: 6 m sheet piles | 67.5504 | 399.3435 | 42.2383 | 128.0807 | 296.5748 | 18 | 11.8 | 5 | 59 | 2.1585 | Single-stage wellpoints | 0 | 0.88059 | Anchor pipe to piled slab (permanent straps) | 2027-03-29 | 2027-07-24 | 134 | Common holds only (see Read Me). | One shared excavation and dewatering front with UG-08: lay all pipes before backfill. UG-11, UG-23 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-11-S04 backfilled (deeper); excavate after UG-11-S05 backfilled (deeper); excavate after UG-23-S03 backfilled (deeper); excavate after UG-23-S04 backfilled (deeper); excavate after UG-23-S05 backfilled (deeper); shared trench with UG-08-S02: start excavation with it; shared trench with UG-08-S03: start excavation with it; shared trench with UG-08-S04: start excavation with it | 15 | 67
UG-08 | UG-08-S01 | F3 | GRP-UG08-S01-AER-EL021-(-3.17/-3.16)-21m | GRP | 28 | Tie-in | AER | 0 |  | 0 | No | 2 | 2.69 | 20.5211 | -3.175 | -3.1585 | -3.175 | 1.675 | 2.475 | 0 | 20.5211 | Open cut | 0 | 482.2094 | 37.8185 | 116.2651 | 328.1259 | 16 | 0 | 0 | 0 | 2.175 | Single-stage wellpoints | 0 | 0.85546 | Anchor pipe to piled slab (permanent straps) | 2027-03-29 | 2027-07-22 | 135 | Common holds only (see Read Me). | aeration tank wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-09: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-23-S05 backfilled (deeper); shared trench with UG-09-S01: start excavation with it; shared trench with UG-09-S02: backfill after both laid; closure: lay after UG-08-S02 laid | 12 | 112
UG-09 | UG-09-S02 | F3 | GRP-UG09-S02-EL024-CH044-(-3.16/-3.16)-20m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.657 | 20.2371 | -3.1585 | -3.1585 | -3.1585 | 1.6585 | 2.4585 | 14.1 | 6.1371 | Mixed: 14 m sheet piles | 161.434 | 142.4895 | 37.0035 | 112.2072 | 154.7128 | 16 | 28.2 | 5 | 141 | 2.1585 | Single-stage wellpoints | 0 | 0.88059 | Anchor pipe to piled slab (permanent straps) | 2027-04-02 | 2027-07-26 | 136 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). | One shared excavation and dewatering front with UG-08: lay all pipes before backfill. UG-23 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-23-S04 backfilled (deeper); excavate after UG-23-S05 backfilled (deeper); shared trench with UG-08-S01: start excavation with it; shared trench with UG-08-S02: start excavation with it; shared trench with UG-08-S03: start excavation with it | 11 | 66
UG-09 | UG-09-S01 | F3 | GRP-UG09-S01-AER-EL024-(-3.18/-3.16)-24m | GRP | 28 | Tie-in | AER | 0 |  | 0 | No | 2 | 2.69 | 23.8629 | -3.175 | -3.1585 | -3.175 | 1.675 | 2.475 | 0 | 23.8629 | Open cut | 0 | 560.8742 | 43.9842 | 135.2583 | 381.6318 | 18 | 0 | 0 | 0 | 2.175 | Single-stage wellpoints | 0 | 0.85545 | Anchor pipe to piled slab (permanent straps) | 2027-04-07 | 2027-07-24 | 137 | Common holds only (see Read Me). | aeration tank wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-08: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-23-S05 backfilled (deeper); shared trench with UG-08-S01: backfill after both laid; shared trench with UG-08-S02: start excavation with it; closure: lay after UG-09-S02 laid | -2 | 105
UG-08 | UG-08-S07 | F3 | GRP-UG08-S07-CH277-SDCC-(-4.99/-4.99)-6m | GRP | 28 | Tie-in | SDCC | 0 |  | 0 | No | 0 | 2.657 | 5.9999 | -4.9885 | -4.9885 | -4.9885 | 3.4885 | 4.2885 | 5.9999 | 0 | Sheet piles | 119.828 | 0 | 10.9709 | 33.2674 | 75.5897 | 6 | 11.9999 | 9 | 107.9989 | 3.9885 | Single-stage wellpoints | 0.83604 | 2.3308 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-05 | 2027-03-22 | 138 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). | secondary distribution chamber C wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-27K-S01: complete first; deeper than UG-27L-S01: complete first; closure: lay after UG-08-S06 laid | -1 | 73
UG-13A | UG-13A-S13 | F3 | HDPE-UG13A-S13-FSTK-EL030-(-4.10/-4.10)-30m | HDPE | 28 | Tie-in | FSTK | 0 |  | 0 | No | 2 | 1 | 30.3665 | -4.1 | -4.1 | -4.1 | 2.6 | 3.4 | 30.3665 | 0 | Sheet piles | 309.7385 | 0 | 30.3665 | 23.8497 | 255.5223 | 12 | 60.7331 | 7 | 425.1316 | 3.1 | Single-stage wellpoints | 3.0383 | 7.0098 | No extra measure | 2027-04-06 | 2027-07-24 | 139 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST K wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-27K-S01: backfill after both laid; closure: lay after UG-13A-S14 laid; built by F3 (shared corridor; line system front F7) | -2 | 104
UG-27K | UG-27K-S01 | F3 | HDPE-UG27K-S01-SDCC-FSTK-(0.79/-4.00)-38m | HDPE | 28 | Short connection | SDCC, FSTK | 0 |  | 0 | No | 8 | 1.6 | 37.7244 | 0.79 | -4 | -4 | 2.5 | 3.3 | 27.7244 | 10 | Mixed: 28 m sheet piles | 329.2831 | 61.6462 | 45.0315 | 69.6472 | 276.2506 | 28 | 55.4487 | 7 | 388.1411 | 3 | Single-stage wellpoints | 0.38438 | 2.8666 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-01 | 2027-07-23 | 140 | R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R057: 11 native short-fitting objects have all 24 mesh vertices coincident. Their embedded source centreline still has 0.584683786 m of represented 3D length. | Both connected structures (secondary distribution chamber C, FST K) built with their wall penetrations; lay between them. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-08-S07 backfilled (deeper); shared trench with UG-13A-S13: start excavation with it | 73 | 228
UG-09 | UG-09-S08 | F3 | GRP-UG09-S08-CH282-SDCB-(-4.98/-4.98)-6m | GRP | 28 | Tie-in | SDCB | 0 |  | 0 | No | 0 | 2.657 | 6 | -4.9785 | -4.9785 | -4.9785 | 3.4785 | 4.2785 | 6 | 0 | Sheet piles | 119.5492 | 0 | 10.9709 | 33.2675 | 75.3107 | 6 | 12 | 9 | 107.9996 | 3.9785 | Single-stage wellpoints | 0.83204 | 2.3268 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-15 | 2027-04-01 | 141 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). | secondary distribution chamber B wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-14E-S01: complete first; deeper than UG-14F-S01: complete first; closure: lay after UG-09-S07 laid | -1 | 73
UG-13B | UG-13B-S01 | F3 | HDPE-UG13B-S01-FSTE-EL031-(-4.10/-4.10)-31m | HDPE | 28 | Tie-in | FSTE | 0 |  | 0 | No | 2 | 1 | 30.7432 | -4.1 | -4.1 | -4.1 | 2.6 | 3.4 | 30.7432 | 0 | Sheet piles | 313.5796 | 0 | 30.7431 | 24.1454 | 258.6911 | 24 | 61.4864 | 7 | 430.4045 | 3.1 | Single-stage wellpoints | 3.0382 | 7.0098 | No extra measure | 2027-02-28 | 2027-06-01 | 142 | R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST E wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-14E-S01: backfill after both laid; closure: lay after UG-13B-S02 laid; built by F3 (shared corridor; line system front F7) | -2 | 88
UG-14E | UG-14E-S01 | F3 | HDPE-UG14E-S01-SDCB-FSTE-(0.80/-4.00)-38m | HDPE | 28 | Short connection | SDCB, FSTE | 0 |  | 0 | No | 8 | 1.6 | 37.5876 | 0.8 | -4 | -4 | 2.5 | 3.3 | 0 | 37.5876 | Open cut | 0 | 1001.0676 | 44.7265 | 69.1754 | 887.1658 | 28 | 0 | 0 | 0 | 3 | Single-stage wellpoints | 0.52798 | 3.0102 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-01 | 2027-06-01 | 143 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R008: 22 segments use civil-guide nominal inlet CL -2.70 and upstream nominal CL +2.10; intermediate 4.80 m fall arrangement is not detailed. R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. | Both connected structures (secondary distribution chamber B, FST E) built with their wall penetrations; lay between them. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-09-S08 backfilled (deeper); shared trench with UG-13B-S01: start excavation with it | 41 | 178
UG-11B | UG-11B-S08 | F3 | HDPE-UG11B-S08-EL339-FSTB-(-4.10/-4.10)-29m | HDPE | 28 | Tie-in | FSTB | 0 |  | 0 | No | 0 | 1 | 29.457 | -4.1 | -4.1 | -4.1 | 2.6 | 3.4 | 29.457 | 0 | Sheet piles | 300.4623 | 0 | 29.4571 | 23.1356 | 247.8695 | 22 | 58.9141 | 7 | 412.3986 | 3.1 | Single-stage wellpoints | 3.0382 | 7.0098 | No extra measure | 2027-02-07 | 2027-05-12 | 151 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST B wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-16B-S01: backfill after both laid; closure: lay after UG-11B-S07 laid; built by F3 (shared corridor; line system front F6) | -1 | 89
UG-16B | UG-16B-S01 | F3 | HDPE-UG16B-S01-SDCA-FSTB-(0.79/-4.00)-38m | HDPE | 28 | Short connection | SDCA, FSTB | 0 |  | 0 | No | 8 | 1.6 | 38.1234 | 0.79 | -4 | -4 | 2.5 | 3.3 | 28.004 | 10.1194 | Mixed: 28 m sheet piles | 332.6876 | 67.2763 | 45.0351 | 69.6527 | 285.2761 | 28 | 56.008 | 7 | 392.056 | 3 | Single-stage wellpoints | 0.28862 | 2.7708 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-01 | 2027-05-11 | 152 | R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R057: 11 native short-fitting objects have all 24 mesh vertices coincident. Their embedded source centreline still has 0.584683786 m of represented 3D length. | Both connected structures (secondary distribution chamber A, FST B) built with their wall penetrations; lay between them. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-10-S05 backfilled (deeper); shared trench with UG-11B-S08: start excavation with it | 58 | 155
UG-14F | UG-14F-S01 | F3 | HDPE-UG14F-S01-SDCB-FSTF-(0.80/-4.00)-38m | HDPE | 28 | Short connection | SDCB, FSTF | 0 |  | 0 | No | 8 | 1.6 | 38.0885 | 0.8 | -4 | -4 | 2.5 | 3.3 | 28.0375 | 10.051 | Mixed: 28 m sheet piles | 333.0858 | 84.5006 | 45.1143 | 69.7752 | 302.6969 | 28 | 56.075 | 7 | 392.525 | 3 | Single-stage wellpoints | 0.52666 | 3.0089 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-01 | 2027-05-25 | 189 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R008: 22 segments use civil-guide nominal inlet CL -2.70 and upstream nominal CL +2.10; intermediate 4.80 m fall arrangement is not detailed. R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. | Both connected structures (secondary distribution chamber B, FST F) built with their wall penetrations; lay between them. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-09-S08 backfilled (deeper); excavate after UG-13B-S09 backfilled (deeper); excavate after UG-13B-S10 backfilled (deeper) | -5 | 169
UG-27J | UG-27J-S02 | F3 | HDPE-UG27J-S02-CH016-FSTJ-(-4.00/-4.00)-22m | HDPE | 28 | Short connection | FSTJ | 0 |  | 0 | No | 0 | 1.6 | 22.0646 | -4 | -4 | -4 | 2.5 | 3.3 | 0 | 22.0646 | Open cut | 0 | 735.6319 | 28.6839 | 44.3633 | 662.5847 | 18 | 0 | 0 | 0 | 3 | Single-stage wellpoints | 1.4339 | 3.9161 | No extra measure | 2026-12-01 | 2027-07-08 | 190 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. | Both connected structures (secondary distribution chamber C, FST J) built with their wall penetrations; lay between them. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-13A-S15 backfilled (deeper) | -2 | 216
UG-27J | UG-27J-S01 | F3 | HDPE-UG27J-S01-SDCC-CH016-(0.79/-4.00)-16m | HDPE | 28 | Short connection | SDCC | 0 |  | 0 | No | 7 | 1.6 | 16 | 0.79 | -4 | -4 | 2.5 | 3.3 | 0.12144 | 15.8786 | Mixed: 0 m sheet piles | 1.4277 | 259.6341 | 16.343 | 25.2765 | 219.4423 | 14 | 0.24288 | 7 | 1.7002 | 3 | Single-stage wellpoints | 0.29876 | 2.781 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-01 | 2027-07-17 | 191 | R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. | Both connected structures (secondary distribution chamber C, FST J) built with their wall penetrations; lay between them. UG-13A is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-13A-S06 backfilled (deeper); excavate after UG-13A-S07 backfilled (deeper) | -5 | 224
UG-27L | UG-27L-S01 | F3 | HDPE-UG27L-S01-SDCC-FSTL-(0.79/-4.00)-38m | HDPE | 28 | Short connection | SDCC, FSTL | 0 |  | 0 | No | 8 | 1.6 | 38.1115 | 0.79 | -4 | -4 | 2.5 | 3.3 | 0 | 38.1115 | Open cut | 0 | 998.2598 | 45.0005 | 69.5989 | 883.6604 | 28 | 0 | 0 | 0 | 3 | Single-stage wellpoints | 0.30008 | 2.7823 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-01 | 2027-07-11 | 192 | R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R057: 11 native short-fitting objects have all 24 mesh vertices coincident. Their embedded source centreline still has 0.584683786 m of represented 3D length. | Both connected structures (secondary distribution chamber C, FST L) built with their wall penetrations; lay between them. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-08-S07 backfilled (deeper); excavate after UG-13A-S01 backfilled (deeper); excavate after UG-13A-S02 backfilled (deeper) | -5 | 218
UG-15 | UG-15-S05 | F4 | GRP-UG15-S05-CH139-EL155-(-5.32/-5.33)-16m | GRP | 28 | Run |  | 0 |  | 0 | No | 2 | 2.0696 | 16.228 | -5.3213 | -5.3348 | -5.3348 | 3.8348 | 4.6348 | 16.228 | 0 | Sheet piles | 303.6226 | 0 | 24.7203 | 53.3882 | 225.5141 | 14 | 32.456 | 10 | 324.5599 | 4.3348 | Single-stage wellpoints | 1.5529 | 3.4719 | No extra measure | 2026-12-01 | 2027-01-09 | 76 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-15A-S02: backfill after both laid | 12 | 35
UG-15 | UG-15-S04 | F4 | GRP-UG15-S04-CH123-CH139-(-5.32/-5.32)-16m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.0412 | 16.1 | -5.3225 | -5.3213 | -5.3225 | 3.8225 | 4.6225 | 16.1 | 0 | Sheet piles | 300.7183 | 0 | 24.4817 | 52.6855 | 223.5511 | 14 | 32.2 | 10 | 322 | 4.3225 | Single-stage wellpoints | 1.5823 | 3.528 | No extra measure | 2026-12-02 | 2027-01-11 | 77 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | One shared excavation and dewatering front with UG-15A: lay all pipes before backfill. UG-15A is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-15A-S02: backfill after both laid | 8 | 33
UG-15A | UG-15A-S02 | F4 | HDPE-UG15A-S02-EL006-CCT-(-4.90/-4.91)-12m | HDPE | 28 | Run |  | 0 |  | 0 | No | 4 | 1.2258 | 12.0663 | -4.9013 | -4.9142 | -4.9142 | 3.4142 | 4.2142 | 12.0663 | 0 | Sheet piles | 162.8036 | 0 | 13.323 | 13.8383 | 135.6423 | 12 | 24.1326 | 9 | 217.1933 | 3.9142 | Single-stage wellpoints | 2.9887 | 6.2286 | No extra measure | 2026-12-06 | 2027-01-13 | 78 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R024: Component material GRP differs from scheduled whole-line material HDPE. chlorine contact tank: structure not in the master model, tie-in position not checked. | UG-15 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-15-S04: start excavation with it; shared trench with UG-15-S05: start excavation with it | 4 | 31
UG-15 | UG-15-S06 | F4 | GRP-UG15-S06-EL155-CCT-(-5.33/-5.33)-13m | GRP | 28 | Tie-in | CCT | 0 |  | 0 | No | 0 | 2.0696 | 12.9696 | -5.3348 | -5.3348 | -5.3348 | 3.8348 | 4.6348 | 12.9696 | 0 | Sheet piles | 244.6306 | 0 | 19.9058 | 43.6307 | 181.0941 | 12 | 25.9392 | 10 | 259.3924 | 4.3348 | Single-stage wellpoints | 1.5529 | 3.4719 | No extra measure | 2026-12-02 | 2027-01-04 | 79 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | chlorine contact tank wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | closure: lay after UG-15-S05 laid | -1 | 29
UG-15 | UG-15-S03 | F4 | GRP-UG15-S03-CH065-CH123-(-5.33/-5.32)-57m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.0412 | 57.3 | -5.3267 | -5.3225 | -5.3267 | 3.8267 | 4.6267 | 57.3 | 0 | Sheet piles | 1070.8789 | 0 | 87.1307 | 187.508 | 796.2403 | 42 | 114.6 | 10 | 1146 | 4.3267 | Single-stage wellpoints | 1.5829 | 3.5286 | No extra measure | 2026-12-10 | 2027-01-21 | 80 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-10-S03: complete first | -4 | 32
UG-15 | UG-15-S02 | F4 | GRP-UG15-S02-CH049-CH065-(-5.33/-5.33)-16m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.0412 | 16.1 | -5.3279 | -5.3267 | -5.3279 | 3.8279 | 4.6279 | 16.1 | 0 | Sheet piles | 301.0671 | 0 | 24.4817 | 52.6855 | 223.8999 | 14 | 32.2 | 10 | 322 | 4.3279 | Single-stage wellpoints | 1.5851 | 3.5307 | No extra measure | 2026-12-14 | 2027-01-27 | 81 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Deepest first: lay and backfill this line to the bed level of UG-10 before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-10-S03: complete first; deeper than UG-10-S04: complete first | -2 | 30
UG-07 | UG-07-S02 | F4 | GRP-UG07-S02-CH020-CH056-(-3.62/-4.58)-35m | GRP | 28 | Run |  | 0 |  | 0 | No | 1 | 2.0696 | 35.2658 | -3.6171 | -4.5801 | -4.5801 | 3.0801 | 3.8801 | 33.2386 | 2.0272 | Mixed: 33 m sheet piles | 483.8219 | 60.7813 | 54.1259 | 118.6358 | 371.8415 | 26 | 66.4773 | 8 | 531.8183 | 3.5801 | Single-stage wellpoints | 0.39223 | 2.3112 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-25 | 2027-04-17 | 103 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | UG-12, UG-07A is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-12-S05 backfilled (deeper); excavate after UG-12-S06 backfilled (deeper); shared trench with UG-07A-S09: backfill after both laid; shared trench with UG-07A-S12: backfill after both laid | 19 | 104
UG-07A | UG-07A-S12 | F4 | HDPE-UG07A-S12-CH050-CCT-(-4.74/-3.62)-32m | HDPE | 28 | Run |  | 0 |  | 0 | No | 3 | 1.2258 | 32.069 | -4.7376 | -3.6175 | -4.7376 | 3.2376 | 4.0376 | 29.9 | 2.169 | Mixed: 30 m sheet piles | 363.8166 | 59.1164 | 35.3575 | 36.5799 | 350.9956 | 24 | 59.8 | 9 | 538.2 | 3.7376 | Single-stage wellpoints | 1.8644 | 5.1043 | No extra measure | 2026-12-29 | 2027-04-20 | 104 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R014: Component material GRP differs from scheduled whole-line material HDPE. chlorine contact tank: structure not in the master model, tie-in position not checked. | One shared excavation and dewatering front with UG-12: lay all pipes before backfill. UG-07 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-12-S04 backfilled (deeper); excavate after UG-12-S05 backfilled (deeper); excavate after UG-12-S06 backfilled (deeper); shared trench with UG-07-S01: backfill after both laid; shared trench with UG-07-S02: start excavation with it | 15 | 44
UG-07 | UG-07-S01 | F4 | GRP-UG07-S01-FSTE-CH020-(-3.22/-3.62)-20m | GRP | 28 | Run |  | 0 |  | 0 | No | 4 | 2.0696 | 20.2342 | -3.2195 | -3.6171 | -3.6171 | 2.1171 | 2.9171 | 0 | 20.2342 | Open cut | 0 | 497.8143 | 31.0184 | 67.83 | 398.9659 | 16 | 0 | 0 | 0 | 2.6171 | Single-stage wellpoints | 0 | 1.9126 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-05 | 2027-04-23 | 105 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. FST E: structure not in the master model, tie-in position not checked. | One shared excavation and dewatering front with UG-07A: lay all pipes before backfill. UG-07A is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-12-S06 backfilled (deeper); shared trench with UG-07A-S05: backfill after both laid; shared trench with UG-07A-S09: backfill after both laid; shared trench with UG-07A-S12: start excavation with it | 12 | 44
UG-07A | UG-07A-S09 | F4 | HDPE-UG07A-S09-EL003-CCT-(-2.97/-2.98)-12m | HDPE | 28 | Run |  | 0 |  | 0 | No | 1 | 1.2259 | 12.1656 | -2.969 | -2.982 | -2.982 | 1.482 | 2.282 | 0 | 12.1656 | Open cut | 0 | 211.0052 | 13.459 | 14.0517 | 183.4946 | 12 | 0 | 0 | 0 | 1.982 | Single-stage wellpoints | 1.0598 | 4.2996 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-11 | 2027-04-25 | 106 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R015: Component material GRP differs from scheduled whole-line material HDPE. chlorine contact tank: structure not in the master model, tie-in position not checked. | One shared excavation and dewatering front with UG-07: lay all pipes before backfill. UG-07 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-07-S01: start excavation with it; shared trench with UG-07-S02: start excavation with it | 9 | 43
UG-07A | UG-07A-S05 | F4 | HDPE-UG07A-S05-CH222-CCT-(-2.73/-3.03)-23m | HDPE | 28 | Run |  | 0 |  | 0 | No | 2 | 1.6552 | 23.4913 | -2.7326 | -3.0265 | -3.0265 | 1.5265 | 2.3265 | 0 | 23.4913 | Open cut | 0 | 397.7874 | 30.5939 | 47.5143 | 319.6792 | 18 | 0 | 0 | 0 | 2.0265 | Single-stage wellpoints | 0 | 2.3838 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-16 | 2027-04-27 | 107 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R013: Component material GRP differs from scheduled whole-line material HDPE. R016: Component material GRP differs from scheduled whole-line material HDPE. chlorine contact tank: structure not in the master model, tie-in position not checked. | UG-07 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-07-S01: start excavation with it | 5 | 43
UG-15A | UG-15A-S01 | F4 | HDPE-UG15A-S01-FSTA-EL006-(-4.90/-4.88)-6m | HDPE | 28 | Tie-in | FSTA | 0 |  | 0 | No | 1 | 1.2 | 6.033 | -4.9013 | -4.8839 | -4.9013 | 3.4013 | 4.2013 | 6.033 | 0 | Sheet piles | 81.0196 | 0 | 6.6286 | 6.7944 | 67.5966 | 8 | 12.0661 | 9 | 108.5948 | 3.9013 | Single-stage wellpoints | 3.0645 | 6.3742 | No extra measure | 2026-12-10 | 2027-01-16 | 115 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST A wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | closure: lay after UG-15A-S02 laid | -1 | 34
UG-15A | UG-15A-S03 | F4 | HDPE-UG15A-S03-FSTC-EL017-(-2.72/-2.72)-17m | HDPE | 28 | Tie-in | FSTC | 0 |  | 0 | No | 2 | 1.2 | 17.4504 | -2.72 | -2.72 | -2.72 | 1.22 | 2.02 | 0 | 17.4504 | Open cut | 0 | 249.625 | 19.1955 | 19.736 | 210.6935 | 14 | 0 | 0 | 0 | 1.72 | Single-stage wellpoints | 0.62298 | 3.9326 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-04-01 | 2027-07-06 | 116 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST C wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-11B, UG-17: lay all pipes before backfill. UG-11B is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-11B-S05 backfilled (deeper); excavate after UG-11B-S06 backfilled (deeper); excavate after UG-17-S03 backfilled (deeper); excavate after UG-17-S04 backfilled (deeper); closure: lay after UG-15A-S04 laid | -2 | 93
UG-15A | UG-15A-S07 | F4 | HDPE-UG15A-S07-FSTD-EL011-(-4.70/-4.70)-11m | HDPE | 28 | Tie-in | FSTD | 0 |  | 0 | No | 1 | 1.2 | 10.7128 | -4.7 | -4.6975 | -4.7 | 3.2 | 4 | 10.7128 | 0 | Sheet piles | 137.1195 | 0 | 11.7837 | 12.1143 | 113.2215 | 10 | 21.4257 | 8 | 171.4056 | 3.7 | Single-stage wellpoints | 2.8862 | 6.1959 | No extra measure | 2027-01-10 | 2027-02-27 | 117 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST D wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | closure: lay after UG-15A-S08 laid | -1 | 45
UG-07A | UG-07A-S03 | F4 | HDPE-UG07A-S03-TEE151-CH157-(-2.70/-2.70)-6m | HDPE | 28 | Run |  | 0 |  | 0 | No | 0 | 1.6 | 6.1264 | -2.6991 | -2.6983 | -2.6991 | 1.1991 | 1.9991 | 0 | 6.1264 | Open cut | 0 | 91.0697 | 7.9643 | 12.3178 | 70.7877 | 8 | 0 | 0 | 0 | 1.6991 | Single-stage wellpoints | 0 | 2.3337 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-20 | 2027-04-29 | 144 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | None | 2 | 43
UG-07A | UG-07A-S02 | F4 | HDPE-UG07A-S02-EL019-TEE151-(-2.50/-2.70)-132m | HDPE | 28 | Run |  | 0 |  | 0 | No | 8 | 1.6 | 132.377 | -2.4997 | -2.6991 | -2.6991 | 1.1991 | 1.9991 | 67.7836 | 64.5934 | Mixed: 68 m sheet piles | 388.9263 | 793.9448 | 147.4968 | 157.9864 | 877.388 | 92 | 135.5672 | 4 | 542.2687 | 1.6991 | Single-stage wellpoints | 0 | 2.332 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-25 | 2027-05-17 | 145 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | None | -8 | 62
UG-07A | UG-07A-S01 | F4 | HDPE-UG07A-S01-FSTE-EL019-(-2.50/-2.50)-19m | HDPE | 28 | Tie-in | FSTE | 0 |  | 0 | No | 2 | 1.2 | 18.6967 | -2.5 | -2.4997 | -2.5 | 1 | 1.8 | 0 | 18.6967 | Open cut | 0 | 222.8593 | 20.5662 | 21.145 | 181.1481 | 16 | 0 | 0 | 0 | 1.5 | Single-stage wellpoints | 0.19405 | 3.5037 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-28 | 2027-05-23 | 146 | R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST E wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | closure: lay after UG-07A-S02 laid | -2 | 112
UG-07A | UG-07A-S07 | F4 | HDPE-UG07A-S07-EL005-TEE-(-2.50/-2.50)-23m | HDPE | 28 | Run |  | 0 |  | 0 | No | 1 | 1.2 | 22.5092 | -2.5 | -2.4991 | -2.5 | 1 | 1.8 | 0 | 22.5092 | Open cut | 0 | 268.2987 | 24.7601 | 25.4573 | 218.0813 | 18 | 0 | 0 | 0 | 1.5 | Single-stage wellpoints | 0.19301 | 3.5027 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-28 | 2027-05-23 | 147 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | None | -2 | 60
UG-07A | UG-07A-S08 | F4 | HDPE-UG07A-S08-FSTH-EL003-(-2.97/-2.97)-3m | HDPE | 28 | Tie-in | FSTH | 0 |  | 0 | No | 2 | 1.2 | 2.9324 | -2.969 | -2.969 | -2.969 | 1.469 | 2.269 | 0 | 2.9324 | Open cut | 0 | 50.5482 | 3.2256 | 3.3164 | 44.0061 | 4 | 0 | 0 | 0 | 1.969 | Single-stage wellpoints | 1.1078 | 4.4175 | No extra measure | 2027-01-16 | 2027-04-24 | 148 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R050: Positive-length overlap of near-collinear source centrelines at 1 mm geometric diagnostic tolerance. | FST H wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-07: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | closure: lay after UG-07A-S09 laid | -2 | 96
UG-07A | UG-07A-S10 | F4 | HDPE-UG07A-S10-FSTF-EL009-(-2.70/-2.89)-9m | HDPE | 28 | Tie-in | FSTF | 0 |  | 0 | No | 1 | 1.2 | 9.2999 | -2.7 | -2.892 | -2.892 | 1.392 | 2.192 | 0 | 9.2999 | Open cut | 0 | 131.4782 | 10.2299 | 10.5179 | 110.7305 | 10 | 0 | 0 | 0 | 1.892 | Single-stage wellpoints | 0.58406 | 3.8937 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-22 | 2027-04-14 | 149 | R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST F wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-13B: lay all pipes before backfill. UG-12 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-12-S04 backfilled (deeper); excavate after UG-13B-S06 backfilled (deeper); excavate after UG-13B-S07 backfilled (deeper); closure: lay after UG-07A-S11 laid | -1 | 80
UG-07A | UG-07A-S06 | F4 | HDPE-UG07A-S06-FSTG-EL005-(-2.50/-2.50)-5m | HDPE | 28 | Tie-in | FSTG | 0 |  | 0 | No | 2 | 1.2 | 5.3578 | -2.5 | -2.5 | -2.5 | 1 | 1.8 | 0 | 5.3578 | Open cut | 0 | 63.8645 | 5.8935 | 6.0595 | 51.9114 | 6 | 0 | 0 | 0 | 1.5 | Single-stage wellpoints | 0.19468 | 3.5043 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-02-20 | 2027-08-07 | 170 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST G wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-11A-S02 backfilled (deeper); closure: lay after UG-07A-S07 laid | -2 | 166
UG-07A | UG-07A-S04 | F4 | HDPE-UG07A-S04-CH157-CH222-(-2.70/-2.73)-65m | HDPE | 28 | Run |  | 0 |  | 0 | No | 2 | 1.6 | 65.1 | -2.6983 | -2.7326 | -2.7326 | 1.2326 | 2.0326 | 30 | 35.1 | Mixed: 30 m sheet piles | 215.5574 | 520.0386 | 84.63 | 130.8912 | 520.0748 | 46 | 60 | 5 | 300 | 1.7326 | Single-stage wellpoints | 0 | 2.3216 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-02-20 | 2027-08-22 | 174 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | UG-11A is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-11A-S03 backfilled (deeper); excavate after UG-11A-S04 backfilled (deeper); excavate after UG-11A-S05 backfilled (deeper); excavate after UG-11A-S07 backfilled (deeper) | -5 | 150
UG-12 | UG-12-S07 | F5 | GRP-UG12-S07-CH210-CH227-(-5.47/-5.22)-17m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.0696 | 17.108 | -5.4656 | -5.2207 | -5.4656 | 3.9656 | 4.7656 | 17.108 | 0 | Sheet piles | 323.2665 | 0 | 26.2573 | 57.552 | 239.4571 | 14 | 34.216 | 10 | 342.16 | 4.4656 | Single-stage wellpoints | 1.4943 | 3.4133 | No extra measure | 2026-12-01 | 2027-03-02 | 4 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | One shared excavation and dewatering front with UG-07, UG-11: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-23 before that line. UG-11 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-11-S06 backfilled (deeper); deeper than UG-23-S06: complete first; deeper than UG-23-S07: complete first; shared trench with UG-07-S03: backfill after both laid; shared trench with UG-07-S04: backfill after both laid; shared trench with UG-11-S01: backfill after both laid | 31 | 87
UG-12 | UG-12-S08 | F5 | GRP-UG12-S08-CH227-CCT-(-5.22/-5.13)-6m | GRP | 28 | Tie-in | CCT | 0 |  | 0 | No | 0 | 2.0696 | 6.0004 | -5.2207 | -5.1348 | -5.2207 | 3.7207 | 4.5207 | 6.0004 | 0 | Sheet piles | 109.3427 | 0 | 9.2094 | 20.1856 | 79.9478 | 8 | 12.0008 | 10 | 120.0078 | 4.2207 | Single-stage wellpoints | 1.4502 | 3.3692 | No extra measure | 2026-12-02 | 2027-03-02 | 5 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | chlorine contact tank wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-07, UG-11: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-23 before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-11-S06 backfilled (deeper); shared trench with UG-07-S03: backfill after both laid; shared trench with UG-07-S04: backfill after both laid; shared trench with UG-11-S01: backfill after both laid; closure: lay after UG-12-S07 laid | 26 | 87
UG-11B | UG-11B-S14 | F5 | HDPE-UG11B-S14-CH018-TEE-(-4.63/-4.63)-20m | HDPE | 28 | Run |  | 0 |  | 0 | No | 2 | 2.0696 | 20.1538 | -4.6348 | -4.6348 | -4.6348 | 3.1348 | 3.9348 | 20.1538 | 0 | Sheet piles | 322.7249 | 0 | 30.9321 | 67.7987 | 223.9941 | 16 | 40.3077 | 8 | 322.4615 | 3.6348 | Single-stage wellpoints | 1.1934 | 3.1124 | No extra measure | 2026-12-02 | 2027-03-04 | 6 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R026: Component material GRP differs from scheduled whole-line material HDPE. R029: Component material GRP differs from scheduled whole-line material HDPE. R036: Component material GRP differs from scheduled whole-line material HDPE. R037: Component material GRP differs from scheduled whole-line material HDPE. Flow direction: not established: model order kept. | One shared excavation and dewatering front with UG-11: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-11 before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-23-S08: complete first; shared trench with UG-11-S01: backfill after both laid; built by F5 (shared corridor; line system front F6) | 27 | 53
UG-12 | UG-12-S06 | F5 | GRP-UG12-S06-CH168-CH210-(-6.07/-5.47)-42m | GRP | 28 | Run |  | 0 |  | 0 | No | 2 | 2.0696 | 42.1 | -6.0682 | -5.4656 | -6.0682 | 4.5682 | 5.3682 | 42.1 | 0 | Sheet piles | 868.1048 | 0 | 64.615 | 141.6262 | 661.8637 | 32 | 84.2 | 11 | 926.2 | 5.0682 | Deep wells or two-stage wellpoints | 1.6201 | 3.5391 | No extra measure | 2026-12-06 | 2027-03-07 | 7 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Deepest first: lay and backfill this line to the bed level of UG-07 before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-07-S01: complete first; deeper than UG-07-S02: complete first; deeper than UG-07A-S12: complete first; shared trench with UG-07-S03: backfill after both laid | 20 | 54
UG-07 | UG-07-S03 | F5 | GRP-UG07-S03-CH056-CH081-(-4.58/-5.03)-25m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.0696 | 25.227 | -4.5801 | -5.0282 | -5.0282 | 3.5282 | 4.3282 | 25.227 | 0 | Sheet piles | 421.3512 | 0 | 38.7184 | 84.8648 | 297.768 | 20 | 50.454 | 9 | 454.086 | 4.0282 | Single-stage wellpoints | 1.1653 | 3.0843 | No extra measure | 2026-12-11 | 2027-03-10 | 8 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | One shared excavation and dewatering front with UG-11, UG-12: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-23 before that line. UG-11 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-11-S06 backfilled (deeper); deeper than UG-23-S06: complete first; deeper than UG-23-S07: complete first; shared trench with UG-11-S01: backfill after both laid; shared trench with UG-12-S06: start excavation with it; shared trench with UG-12-S07: start excavation with it; shared trench with UG-12-S08: start excavation with it; built by F5 (shared corridor; line system front F4) | 16 | 51
UG-07 | UG-07-S04 | F5 | GRP-UG07-S04-CH081-CCT-(-5.03/-5.13)-6m | GRP | 28 | Tie-in | CCT | 0 |  | 0 | No | 0 | 2.0696 | 6.0003 | -5.0282 | -5.1348 | -5.1348 | 3.6348 | 4.4348 | 6.0003 | 0 | Sheet piles | 106.9917 | 0 | 9.2093 | 20.1854 | 77.5971 | 8 | 12.0006 | 9 | 108.0058 | 4.1348 | Single-stage wellpoints | 1.3954 | 3.3144 | No extra measure | 2026-12-20 | 2027-03-02 | 9 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | chlorine contact tank wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-11, UG-12: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-23 before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-11-S06 backfilled (deeper); shared trench with UG-11-S01: backfill after both laid; shared trench with UG-12-S07: start excavation with it; shared trench with UG-12-S08: start excavation with it; closure: lay after UG-07-S03 laid; built by F5 (shared corridor; line system front F4) | 4 | 69
UG-11 | UG-11-S01 | F5 | GRP-UG11-S01-FSTA-CH037-(-4.62/-4.62)-37m | GRP | 28 | Run |  | 0 |  | 0 | No | 4 | 2.0696 | 37.4 | -4.6248 | -4.6248 | -4.6248 | 3.1248 | 3.9248 | 37.4 | 0 | Sheet piles | 597.1146 | 0 | 57.3803 | 125.6787 | 414.0556 | 28 | 74.8 | 8 | 598.4 | 3.6248 | Single-stage wellpoints | 1.1882 | 3.1072 | No extra measure | 2026-12-20 | 2027-03-12 | 10 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. Flow direction: not established: model order kept. FST A: structure not in the master model, tie-in position not checked. | One shared excavation and dewatering front with UG-11B: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-23 before that line. UG-11B is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-23-S07: complete first; deeper than UG-23-S08: complete first; shared trench with UG-07-S03: start excavation with it; shared trench with UG-07-S04: start excavation with it; shared trench with UG-11B-S14: start excavation with it; shared trench with UG-12-S07: start excavation with it; shared trench with UG-12-S08: start excavation with it; built by F5 (shared corridor; line system front F6) | 9 | 50
UG-12 | UG-12-S05 | F5 | GRP-UG12-S05-CH143-CH168-(-6.18/-6.07)-24m | GRP | 28 | Run |  | 0 |  | 0 | No | 2 | 2.0696 | 24.1 | -6.1789 | -6.0682 | -6.1789 | 4.6789 | 5.4789 | 24.1 | 0 | Sheet piles | 532.8129 | 0 | 36.9887 | 81.0738 | 414.7504 | 20 | 48.2 | 11 | 530.2 | 5.1789 | Deep wells or two-stage wellpoints | 1.9296 | 3.8486 | No extra measure | 2026-12-25 | 2027-03-15 | 29 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | One shared excavation and dewatering front with UG-07A: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-07-S02: complete first; deeper than UG-07A-S11: complete first; deeper than UG-07A-S12: complete first | 5 | 49
UG-12 | UG-12-S02 | F5 | GRP-UG12-S02-CH030-CH046-(-3.08/-3.08)-16m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.0696 | 16 | -3.0756 | -3.081 | -3.081 | 1.581 | 2.381 | 0 | 16 | Open cut | 0 | 330.741 | 24.5568 | 53.8249 | 252.3593 | 14 | 0 | 0 | 0 | 2.081 | Single-stage wellpoints | 0 | 1.7 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-01 | 2027-07-11 | 61 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | One shared excavation and dewatering front with UG-12A: lay all pipes before backfill. UG-13, UG-12A is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-13-S02 backfilled (deeper); excavate after UG-13-S03 backfilled (deeper); shared trench with UG-12A-S12: backfill after both laid | 12 | 163
UG-12 | UG-12-S01 | F5 | GRP-UG12-S01-FSTI-CH030-(-3.05/-3.08)-30m | GRP | 28 | Run |  | 0 |  | 0 | No | 1 | 2.0696 | 30.1 | -3.0514 | -3.0756 | -3.0756 | 1.5756 | 2.3756 | 0 | 30.1 | Open cut | 0 | 618.9069 | 46.189 | 101.2031 | 471.5148 | 24 | 0 | 0 | 0 | 2.0756 | Single-stage wellpoints | 0 | 1.6889 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-06 | 2027-07-28 | 62 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. FST I: structure not in the master model, tie-in position not checked. | One shared excavation and dewatering front with UG-12A: lay all pipes before backfill. UG-12A is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-13-S02 backfilled (deeper); excavate after UG-13-S03 backfilled (deeper); shared trench with UG-12A-S06: backfill after both laid; shared trench with UG-12A-S10: backfill after both laid; shared trench with UG-12A-S12: backfill after both laid | 21 | 50
UG-12A | UG-12A-S12 | F5 | HDPE-UG12A-S12-CH006-CCT-(-2.64/-2.66)-8m | HDPE | 28 | Run |  | 0 |  | 0 | No | 1 | 1.2258 | 8.1697 | -2.6434 | -2.6563 | -2.6563 | 1.1563 | 1.9563 | 0 | 8.1697 | Open cut | 0 | 110.7254 | 9.0421 | 9.4509 | 92.2325 | 8 | 0 | 0 | 0 | 1.6563 | Single-stage wellpoints | 0.43923 | 3.6792 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-10 | 2027-07-30 | 63 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R017: Component material GRP differs from scheduled whole-line material HDPE. chlorine contact tank: structure not in the master model, tie-in position not checked. | One shared excavation and dewatering front with UG-12: lay all pipes before backfill. UG-13, UG-12 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-13-S03 backfilled (deeper); shared trench with UG-12-S01: start excavation with it; shared trench with UG-12-S02: start excavation with it | 19 | 49
UG-12A | UG-12A-S10 | F5 | HDPE-UG12A-S10-CH006-CCT-(-2.63/-2.65)-29m | HDPE | 28 | Run |  | 0 |  | 0 | No | 1 | 1.2258 | 29.2588 | -2.6346 | -2.6475 | -2.6475 | 1.1475 | 1.9475 | 0 | 29.2588 | Open cut | 0 | 392.8298 | 32.3227 | 33.6166 | 326.8905 | 22 | 0 | 0 | 0 | 1.6475 | Single-stage wellpoints | 0.42251 | 3.6625 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-16 | 2027-08-01 | 64 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R018: Component material GRP differs from scheduled whole-line material HDPE. R020: Component material GRP differs from scheduled whole-line material HDPE. chlorine contact tank: structure not in the master model, tie-in position not checked. | UG-12 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-12-S01: start excavation with it | 14 | 49
UG-12A | UG-12A-S06 | F5 | HDPE-UG12A-S06-CH242-CCT-(-2.83/-2.85)-39m | HDPE | 28 | Run |  | 0 |  | 0 | No | 1 | 1.6334 | 39.0435 | -2.83 | -2.8475 | -2.8475 | 1.3475 | 2.1475 | 0 | 39.0435 | Open cut | 0 | 641.7501 | 50.7915 | 78.6791 | 512.2796 | 30 | 0 | 0 | 0 | 1.8475 | Single-stage wellpoints | 0.019126 | 2.4506 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-19 | 2027-08-04 | 65 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R019: Component material GRP differs from scheduled whole-line material HDPE. R021: Component material GRP differs from scheduled whole-line material HDPE. chlorine contact tank: structure not in the master model, tie-in position not checked. | UG-12 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-12-S01: start excavation with it | 7 | 50
UG-12A | UG-12A-S05 | F5 | HDPE-UG12A-S05-CH226-CH242-(-2.83/-2.83)-15m | HDPE | 28 | Run |  | 0 |  | 0 | No | 2 | 1.6 | 15.1 | -2.83 | -2.83 | -2.83 | 1.33 | 2.13 | 0 | 15.1 | Open cut | 0 | 247.9685 | 19.63 | 30.3601 | 197.9784 | 14 | 0 | 0 | 0 | 1.83 | Single-stage wellpoints | 0.043801 | 2.526 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-25 | 2027-08-06 | 193 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | One shared excavation and dewatering front with UG-06: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-06-S03 backfilled (deeper) | 4 | 49
UG-12A | UG-12A-S04 | F5 | HDPE-UG12A-S04-TEE150-CH226-(-2.89/-2.83)-77m | HDPE | 28 | Run |  | 0 |  | 0 | No | 2 | 1.6 | 76.674 | -2.8892 | -2.83 | -2.8892 | 1.3892 | 2.1892 | 36.1076 | 40.5664 | Mixed: 36 m sheet piles | 279.3366 | 678.1957 | 99.6761 | 154.1619 | 703.6943 | 54 | 72.2153 | 5 | 361.0763 | 1.8892 | Single-stage wellpoints | 0.043804 | 2.526 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-02-01 | 2027-08-16 | 194 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | One shared excavation and dewatering front with UG-05, UG-06: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-05-S04 backfilled (deeper); excavate after UG-06-S04 backfilled (deeper) | -6 | 58
UG-12A | UG-12A-S03 | F5 | HDPE-UG12A-S03-CH085-TEE150-(-2.63/-2.89)-65m | HDPE | 28 | Run |  | 0 |  | 0 | No | 4 | 1.6 | 64.526 | -2.63 | -2.8892 | -2.8892 | 1.3892 | 2.1892 | 40 | 24.526 | Mixed: 40 m sheet piles | 250.8067 | 356.5887 | 72.4836 | 79.5903 | 455.3215 | 46 | 80 | 5 | 400 | 1.8892 | Single-stage wellpoints | 0.11937 | 2.6016 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-02-05 | 2027-08-27 | 195 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | One shared excavation and dewatering front with UG-05, UG-06: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-05-S04 backfilled (deeper); excavate after UG-06-S04 backfilled (deeper); excavate after UG-06-S05 backfilled (deeper) | -5 | 65
UG-12A | UG-12A-S02 | F5 | HDPE-UG12A-S02-EL015-CH085-(-2.70/-2.63)-70m | HDPE | 28 | Run |  | 0 |  | 0 | No | 2 | 1.2 | 69.9458 | -2.6958 | -2.63 | -2.6958 | 1.1958 | 1.9958 | 0 | 69.9458 | Open cut | 0 | 952.9319 | 76.9404 | 79.1067 | 796.8848 | 50 | 0 | 0 | 0 | 1.6958 | Single-stage wellpoints | 0.44778 | 3.7574 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-02-18 | 2027-09-07 | 196 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | None | -5 | 73
UG-12A | UG-12A-S01 | F5 | HDPE-UG12A-S01-FSTK-EL015-(-2.70/-2.70)-15m | HDPE | 28 | Tie-in | FSTK | 0 |  | 0 | No | 2 | 1.2 | 15.2542 | -2.7 | -2.6958 | -2.7 | 1.2 | 2 | 0 | 15.2542 | Open cut | 0 | 214.6849 | 16.7796 | 17.252 | 180.6533 | 14 | 0 | 0 | 0 | 1.7 | Single-stage wellpoints | 0.57582 | 3.8855 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-03-02 | 2027-09-13 | 197 | R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST K wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | closure: lay after UG-12A-S02 laid | -2 | 192
UG-12A | UG-12A-S08 | F5 | HDPE-UG12A-S08-EL011-TEE-(-2.70/-2.69)-5m | HDPE | 28 | Run |  | 0 |  | 0 | No | 0 | 1.2 | 5.2744 | -2.7 | -2.6892 | -2.7 | 1.2 | 2 | 0 | 5.2744 | Open cut | 0 | 73.9439 | 5.8018 | 5.9651 | 62.177 | 6 | 0 | 0 | 0 | 1.7 | Single-stage wellpoints | 0.563 | 3.8727 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-03-02 | 2027-09-12 | 198 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-05-S04 backfilled (deeper); excavate after UG-06-S04 backfilled (deeper) | -1 | 73
UG-12A | UG-12A-S07 | F5 | HDPE-UG12A-S07-FSTI-EL011-(-2.70/-2.70)-11m | HDPE | 28 | Tie-in | FSTI | 0 |  | 0 | No | 2 | 1.2 | 11.1248 | -2.7 | -2.7 | -2.7 | 1.2 | 2 | 0 | 11.1248 | Open cut | 0 | 156.6366 | 12.2372 | 12.5818 | 131.8175 | 10 | 0 | 0 | 0 | 1.7 | Single-stage wellpoints | 0.58406 | 3.8937 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-03-14 | 2027-09-18 | 199 | R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R057: 11 native short-fitting objects have all 24 mesh vertices coincident. Their embedded source centreline still has 0.584683786 m of represented 3D length. | FST I wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-06-S04 backfilled (deeper); closure: lay after UG-12A-S08 laid | -2 | 186
UG-12A | UG-12A-S09 | F5 | HDPE-UG12A-S09-FSTJ-CH006-(-2.63/-2.63)-6m | HDPE | 28 | Tie-in | FSTJ | 0 |  | 0 | No | 0 | 1.2 | 6 | -2.6346 | -2.6346 | -2.6346 | 1.1346 | 1.9346 | 0 | 6 | Open cut | 0 | 80.1357 | 6.6 | 6.7858 | 66.7499 | 8 | 0 | 0 | 0 | 1.6346 | Single-stage wellpoints | 0.45671 | 3.7664 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-19 | 2027-07-25 | 200 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST J wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-13A-S15 backfilled (deeper); closure: lay after UG-12A-S10 laid | -1 | 185
UG-12A | UG-12A-S11 | F5 | HDPE-UG12A-S11-FSTL-CH006-(-2.64/-2.64)-6m | HDPE | 28 | Tie-in | FSTL | 0 |  | 0 | No | 0 | 1.2 | 6 | -2.6434 | -2.6434 | -2.6434 | 1.1434 | 1.9434 | 0 | 6 | Open cut | 0 | 80.7122 | 6.6 | 6.7858 | 67.3264 | 6 | 0 | 0 | 0 | 1.6434 | Single-stage wellpoints | 0.47379 | 3.7834 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-16 | 2027-07-18 | 201 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST L wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-12: lay all pipes before backfill. UG-13 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-13-S03 backfilled (deeper); closure: lay after UG-12A-S12 laid | -1 | 181
UG-11 | UG-11-S02 | F6 | GRP-UG11-S02-CH037-RASPS-(-4.62/-4.30)-26m | GRP | 28 | Run |  | 0 |  | 0 | No | 4 | 2.0696 | 26.246 | -4.6248 | -4.3 | -4.6248 | 3.1248 | 3.9248 | 26.246 | 0 | Sheet piles | 384.348 | 0 | 37.1888 | 71.3357 | 275.8234 | 20 | 52.4921 | 8 | 419.9366 | 3.6248 | Single-stage wellpoints | 1.1882 | 3.1072 | No extra measure | 2026-12-01 | 2027-01-09 | 1 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. Flow direction: not established: model order kept. RAS/WAS pumping station: structure not in the master model, tie-in position not checked. | Deepest first: lay and backfill this line to the bed level of UG-23 before that line. UG-11A is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-23-S08: complete first; shared trench with UG-11A-S05: backfill after both laid | 9 | 34
UG-11A | UG-11A-S05 | F6 | HDPE-UG11A-S05-CH124-RASPS-(-4.29/-4.30)-40m | HDPE | 28 | Run |  | 0 |  | 0 | No | 1 | 1.42 | 40.1906 | -4.29 | -4.3 | -4.3 | 2.8 | 3.6 | 40.1906 | 0 | Sheet piles | 490.5894 | 0 | 48.2309 | 61.8781 | 380.4804 | 30 | 80.3813 | 8 | 643.0501 | 3.3 | Single-stage wellpoints | 1.9749 | 4.7718 | No extra measure | 2026-12-02 | 2027-01-11 | 2 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. RAS/WAS pumping station: structure not in the master model, tie-in position not checked. | UG-11 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-07A-S04: complete first; shared trench with UG-11-S02: start excavation with it | 2 | 30
UG-11 | UG-11-S06 | F6 | GRP-UG11-S06-CH082-RASPS-(-7.59/-7.07)-43m | GRP | 28 | Run |  | 0 |  | 0 | No | 1 | 2.0696 | 43.2042 | -7.594 | -7.0671 | -7.6048 | 6.1048 | 6.9048 | 43.2042 | 0 | Sheet piles | 1210.8238 | 0 | 66.1752 | 144.6937 | 999.9549 | 32 | 86.4084 | 14 | 1209.7175 | 6.6048 | Deep wells or two-stage wellpoints | 2.7133 | 4.6323 | No extra measure | 2026-12-07 | 2027-01-19 | 3 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. Flow direction: not established: model order kept. RAS/WAS pumping station: structure not in the master model, tie-in position not checked. | Deepest first: lay and backfill this line to the bed level of UG-23, UG-07, UG-12 before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-07-S03: complete first; deeper than UG-07-S04: complete first; deeper than UG-12-S07: complete first; deeper than UG-12-S08: complete first; deeper than UG-23-S06: complete first; deeper than UG-23-S07: complete first | -4 | 31
UG-11 | UG-11-S05 | F6 | GRP-UG11-S05-CH041-CH082-(-7.58/-7.59)-41m | GRP | 28 | Run |  | 0 |  | 0 | No | 4 | 2.0696 | 41.3 | -7.5836 | -7.594 | -7.594 | 6.094 | 6.894 | 41.3 | 0 | Sheet piles | 1102.9987 | 0 | 60.1169 | 123.1967 | 919.6851 | 30 | 82.6 | 14 | 1156.4 | 6.594 | Deep wells or two-stage wellpoints | 2.7079 | 4.6269 | No extra measure | 2026-12-14 | 2027-01-28 | 11 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. Flow direction: not established: model order kept. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-09-S03: complete first; deeper than UG-23-S04: complete first; deeper than UG-23-S06: complete first | -4 | 31
UG-11 | UG-11-S04 | F6 | GRP-UG11-S04-CH023-CH041-(-7.58/-7.58)-18m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.0696 | 18.1 | -7.5791 | -7.5836 | -7.5836 | 6.0836 | 6.8836 | 18.1 | 0 | Sheet piles | 506.8789 | 0 | 27.7799 | 60.8893 | 418.2097 | 16 | 36.2 | 14 | 506.8 | 6.5836 | Deep wells or two-stage wellpoints | 2.7056 | 4.6246 | No extra measure | 2026-12-23 | 2027-02-03 | 12 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. Flow direction: not established: model order kept. | Deepest first: lay and backfill this line to the bed level of UG-08, UG-09, UG-23 before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-08-S02: complete first; deeper than UG-08-S03: complete first; deeper than UG-08-S04: complete first; deeper than UG-09-S03: complete first; deeper than UG-23-S04: complete first | -2 | 31
UG-11 | UG-11-S03 | F6 | GRP-UG11-S03-FSTA-CH023-(-7.57/-7.58)-23m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.0696 | 23.1 | -7.5748 | -7.5791 | -7.5791 | 6.0791 | 6.8791 | 23.1 | 0 | Sheet piles | 646.4328 | 0 | 35.4539 | 77.7096 | 533.2694 | 18 | 46.2 | 14 | 646.8 | 6.5791 | Deep wells or two-stage wellpoints | 2.7034 | 4.6224 | No extra measure | 2026-12-30 | 2027-02-09 | 13 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. Flow direction: not established: model order kept. FST A: structure not in the master model, tie-in position not checked. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-08-S03: complete first; deeper than UG-08-S04: complete first | -2 | 33
UG-23 | UG-23-S09 | F6 | HDPE-UG23-S09-CH197-CH287-(-1.96/-1.97)-90m | HDPE | 28 | Run |  | 0 |  | 0 | No | 2 | 0.63 | 90.079 | -1.965 | -1.965 | -1.965 | 0.465 | 1.265 | 0 | 90.079 | Open cut | 0 | 559.1569 | 73.4144 | 28.0799 | 457.6625 | 32 | 0 | 0 | 0 | 0.965 | Single-stage wellpoints | 99 | 99 | No extra measure | 2027-01-04 | 2027-02-22 | 108 | Common holds only (see Read Me). | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | None | -7 | 41
UG-23 | UG-23-S10 | F6 | HDPE-UG23-S10-CH287-WPD-(-1.97/-1.97)-6m | HDPE | 28 | Tie-in | WPD | 0 |  | 0 | No | 0 | 0.63 | 5.9999 | -1.965 | -1.965 | -1.965 | 0.465 | 1.265 | 0 | 5.9999 | Open cut | 0 | 37.2442 | 4.89 | 1.8704 | 30.4839 | 3 | 0 | 0 | 0 | 0.965 | Single-stage wellpoints | 99 | 99 | No extra measure | 2027-01-09 | 2027-02-27 | 109 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). | WAS pre-dewatering building wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | closure: lay after UG-23-S09 laid | -1 | 47
UG-23 | UG-23-S08 | F6 | HDPE-UG23-S08-CH151-CH197-(-1.96/-1.96)-46m | HDPE | 28 | Run |  | 0 |  | 0 | No | 0 | 0.62999 | 46 | -1.965 | -1.965 | -1.965 | 0.465 | 1.265 | 0 | 46 | Open cut | 0 | 285.5391 | 37.4899 | 14.3391 | 233.7101 | 17 | 0 | 0 | 0 | 0.965 | Single-stage wellpoints | 99 | 99 | No extra measure | 2027-01-09 | 2027-03-28 | 110 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). | UG-11 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-11-S01 backfilled (deeper); excavate after UG-11-S02 backfilled (deeper); excavate after UG-11B-S14 backfilled (deeper) | -5 | 67
UG-23 | UG-23-S07 | F6 | HDPE-UG23-S07-CH135-CH151-(-1.96/-1.96)-16m | HDPE | 28 | Run |  | 0 |  | 0 | No | 0 | 0.62999 | 16 | -1.965 | -1.965 | -1.965 | 0.465 | 1.265 | 0 | 16 | Open cut | 0 | 99.3179 | 13.04 | 4.9875 | 81.2905 | 7 | 0 | 0 | 0 | 0.965 | Single-stage wellpoints | 99 | 99 | No extra measure | 2027-01-18 | 2027-04-03 | 111 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). | UG-07, UG-11, UG-12 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-07-S03 backfilled (deeper); excavate after UG-11-S01 backfilled (deeper); excavate after UG-11-S06 backfilled (deeper); excavate after UG-12-S07 backfilled (deeper) | -2 | 32
UG-23 | UG-23-S06 | F6 | HDPE-UG23-S06-TEE090-CH135-(-2.96/-1.96)-45m | HDPE | 28 | Run |  | 0 |  | 0 | No | 8 | 0.63 | 45.3875 | -2.9607 | -1.965 | -2.9607 | 1.4607 | 2.2607 | 13.9891 | 31.3984 | Mixed: 14 m sheet piles | 46.5407 | 200.8607 | 36.9907 | 14.1482 | 196.2625 | 17 | 27.9781 | 5 | 139.8905 | 1.9607 | Single-stage wellpoints | 1.4671 | 7.7712 | No extra measure | 2027-01-23 | 2027-04-12 | 112 | Common holds only (see Read Me). | UG-11 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-07-S03 backfilled (deeper); excavate after UG-11-S05 backfilled (deeper); excavate after UG-11-S06 backfilled (deeper); excavate after UG-12-S07 backfilled (deeper) | -3 | 40
UG-23 | UG-23-S05 | F6 | HDPE-UG23-S05-CH058-TEE090-(-5.07/-2.96)-33m | HDPE | 28 | Run |  | 0 |  | 0 | No | 5 | 0.63 | 32.6262 | -5.075 | -2.9607 | -5.075 | 3.575 | 4.375 | 32.5555 | 0.07071 | Mixed: 33 m sheet piles | 365.6952 | 1.1206 | 26.5852 | 10.1604 | 330.0701 | 12 | 65.111 | 9 | 585.9988 | 4.075 | Single-stage wellpoints | 3.5246 | 9.8286 | No extra measure | 2027-01-26 | 2027-04-19 | 113 | R047: Same endpoints, component and nodes, but different CAD envelope diameters [0.6300043436700478, 0.6178954427808209]. | Deepest first: lay and backfill this line to the bed level of UG-08, UG-09 before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-08-S01: complete first; deeper than UG-08-S02: complete first; deeper than UG-08-S03: complete first; deeper than UG-09-S01: complete first; deeper than UG-09-S02: complete first; deeper than UG-09-S03: complete first | -2 | 44
UG-23 | UG-23-S04 | F6 | HDPE-UG23-S04-CH035-CH058-(-5.07/-5.07)-23m | HDPE | 28 | Run |  | 0 |  | 0 | No | 0 | 0.63 | 23 | -5.075 | -5.075 | -5.075 | 3.575 | 4.375 | 23 | 0 | Sheet piles | 264.6436 | 0 | 18.745 | 7.1696 | 238.7289 | 9 | 46 | 9 | 414 | 4.075 | Single-stage wellpoints | 7.092 | 13.3961 | No extra measure | 2027-01-31 | 2027-04-25 | 114 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). | Deepest first: lay and backfill this line to the bed level of UG-08, UG-09 before that line. UG-11 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-08-S02: complete first; deeper than UG-08-S03: complete first; deeper than UG-08-S04: complete first; deeper than UG-09-S02: complete first; deeper than UG-09-S03: complete first; deeper than UG-09-S04: complete first; excavate after UG-11-S04 backfilled (deeper); excavate after UG-11-S05 backfilled (deeper) | -2 | 47
UG-11B | UG-11B-S07 | F6 | HDPE-UG11B-S07-TEE259-EL339-(-4.30/-4.10)-80m | HDPE | 28 | Run |  | 0 |  | 0 | No | 9 | 1.4 | 79.9312 | -4.3 | -4.1 | -4.3 | 2.8 | 3.6 | 79.9312 | 0 | Sheet piles | 843.449 | 0 | 82.6909 | 73.1842 | 687.5739 | 56 | 159.8625 | 8 | 1278.8997 | 3.3 | Single-stage wellpoints | 2.0183 | 4.8552 | No extra measure | 2027-02-04 | 2027-05-07 | 150 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Deepest first: lay and backfill this line to the bed level of UG-16D before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-16D-S01: complete first | -5 | 57
UG-11B | UG-11B-S04 | F6 | HDPE-UG11B-S04-TEE126-CH166-(-4.63/-4.30)-40m | HDPE | 28 | Run |  | 0 |  | 0 | No | 4 | 2.0696 | 40.2557 | -4.6348 | -4.3 | -4.6348 | 3.1348 | 3.9348 | 40.2557 | 0 | Sheet piles | 531.1552 | 0 | 51.7196 | 80.5137 | 398.9219 | 30 | 80.5114 | 8 | 644.0913 | 3.6348 | Single-stage wellpoints | 1.1934 | 3.1124 | No extra measure | 2027-02-07 | 2027-05-16 | 153 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R030: Component material GRP differs from scheduled whole-line material HDPE. R032: Component material GRP differs from scheduled whole-line material HDPE. R034: Component material GRP differs from scheduled whole-line material HDPE. R035: Component material GRP differs from scheduled whole-line material HDPE. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | None | -4 | 61
UG-11B | UG-11B-S03 | F6 | HDPE-UG11B-S03-TEE056-TEE126-(-4.63/-4.63)-70m | HDPE | 28 | Run |  | 0 |  | 0 | No | 0 | 2.0696 | 70.2152 | -4.6348 | -4.6348 | -4.6348 | 3.1348 | 3.9348 | 70.2152 | 0 | Sheet piles | 1124.359 | 0 | 107.7662 | 236.2068 | 780.386 | 50 | 140.4304 | 8 | 1123.4434 | 3.6348 | Single-stage wellpoints | 1.1934 | 3.1124 | No extra measure | 2027-02-21 | 2027-05-27 | 154 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R027: Component material GRP differs from scheduled whole-line material HDPE. R031: Component material GRP differs from scheduled whole-line material HDPE. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | None | -5 | 68
UG-11B | UG-11B-S02 | F6 | HDPE-UG11B-S02-CH006-TEE056-(-4.10/-4.11)-50m | HDPE | 28 | Run |  | 0 |  | 0 | No | 1 | 1.0222 | 49.6291 | -4.1 | -4.1111 | -4.1111 | 2.6111 | 3.4111 | 49.6291 | 0 | Sheet piles | 506.9345 | 0 | 49.7022 | 39.2107 | 418.0216 | 36 | 99.2582 | 7 | 694.8071 | 3.1111 | Single-stage wellpoints | 2.9609 | 6.8464 | No extra measure | 2027-02-28 | 2027-06-06 | 155 | R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R028: Component material GRP differs from scheduled whole-line material HDPE. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-16A-S01: backfill after both laid | -6 | 72
UG-11B | UG-11B-S01 | F6 | HDPE-UG11B-S01-FSTA-CH006-(-4.10/-4.10)-6m | HDPE | 28 | Tie-in | FSTA | 0 |  | 0 | No | 0 | 0.99999 | 6 | -4.1 | -4.1 | -4.1 | 2.6 | 3.4 | 6 | 0 | Sheet piles | 61.1998 | 0 | 6 | 4.7123 | 50.4875 | 3 | 12 | 7 | 84 | 3.1 | Single-stage wellpoints | 3.0383 | 7.0099 | No extra measure | 2027-03-12 | 2027-06-11 | 156 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST A wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-16A-S01: backfill after both laid; closure: lay after UG-11B-S02 laid | -1 | 88
UG-16A | UG-16A-S01 | F6 | HDPE-UG16A-S01-SDCA-FSTA-(0.79/-4.00)-38m | HDPE | 28 | Short connection | SDCA, FSTA | 0 |  | 0 | No | 8 | 1.6 | 37.7775 | 0.79 | -4 | -4 | 2.5 | 3.3 | 27.7775 | 10 | Mixed: 28 m sheet piles | 329.9764 | 64.9254 | 45.0292 | 69.6437 | 280.2289 | 28 | 55.5551 | 7 | 388.8855 | 3 | Single-stage wellpoints | 0.35253 | 2.8348 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-01 | 2027-06-10 | 157 | R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. | Both connected structures (secondary distribution chamber A, FST A) built with their wall penetrations; lay between them. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-10-S05 backfilled (deeper); shared trench with UG-11B-S01: start excavation with it; shared trench with UG-11B-S02: start excavation with it; built by F6 (shared corridor; line system front F3) | 45 | 185
UG-11B | UG-11B-S10 | F6 | HDPE-UG11B-S10-CH006-TEE-(-4.10/-4.11)-49m | HDPE | 28 | Run |  | 0 |  | 0 | No | 1 | 1.0219 | 49.4448 | -4.1 | -4.111 | -4.111 | 2.611 | 3.411 | 49.4448 | 0 | Sheet piles | 505.0285 | 0 | 49.5152 | 39.0576 | 416.4557 | 36 | 98.8895 | 7 | 692.2266 | 3.111 | Single-stage wellpoints | 2.9617 | 6.848 | No extra measure | 2027-03-12 | 2027-06-16 | 158 | R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R033: Component material GRP differs from scheduled whole-line material HDPE. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-16C-S01: backfill after both laid | -6 | 78
UG-11B | UG-11B-S09 | F6 | HDPE-UG11B-S09-FSTC-CH006-(-4.10/-4.10)-6m | HDPE | 28 | Tie-in | FSTC | 0 |  | 0 | No | 0 | 1 | 6 | -4.1 | -4.1 | -4.1 | 2.6 | 3.4 | 6 | 0 | Sheet piles | 61.1999 | 0 | 6 | 4.7124 | 50.4876 | 3 | 12 | 7 | 84 | 3.1 | Single-stage wellpoints | 3.0383 | 7.0098 | No extra measure | 2027-03-22 | 2027-06-21 | 159 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST C wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-16C-S01: backfill after both laid; closure: lay after UG-11B-S10 laid | -1 | 88
UG-16C | UG-16C-S01 | F6 | HDPE-UG16C-S01-SDCA-FSTC-(0.80/-4.00)-38m | HDPE | 28 | Short connection | SDCA, FSTC | 0 |  | 0 | No | 5 | 1.6 | 38.3838 | 0.8 | -4 | -4 | 2.5 | 3.3 | 0 | 38.3838 | Open cut | 0 | 1012.689 | 46.0071 | 71.156 | 895.5259 | 28 | 0 | 0 | 0 | 3 | Single-stage wellpoints | 0.36897 | 2.8512 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-01 | 2027-06-21 | 160 | R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R057: 11 native short-fitting objects have all 24 mesh vertices coincident. Their embedded source centreline still has 0.584683786 m of represented 3D length. | Both connected structures (secondary distribution chamber A, FST C) built with their wall penetrations; lay between them. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-11B-S09: start excavation with it; shared trench with UG-11B-S10: start excavation with it; built by F6 (shared corridor; line system front F3) | 52 | 198
UG-11B | UG-11B-S12 | F6 | HDPE-UG11B-S12-CH006-TEE-(-4.10/-4.10)-33m | HDPE | 28 | Run |  | 0 |  | 0 | No | 0 | 1 | 32.7629 | -4.1 | -4.1 | -4.1 | 2.6 | 3.4 | 32.7629 | 0 | Sheet piles | 334.1819 | 0 | 32.7629 | 25.7319 | 275.687 | 24 | 65.5259 | 7 | 458.681 | 3.1 | Single-stage wellpoints | 3.0383 | 7.0098 | No extra measure | 2027-03-22 | 2027-06-23 | 161 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-16D-S01: backfill after both laid | -3 | 79
UG-11B | UG-11B-S11 | F6 | HDPE-UG11B-S11-FSTD-CH006-(-4.10/-4.10)-6m | HDPE | 28 | Tie-in | FSTD | 0 |  | 0 | No | 0 | 1 | 6 | -4.1 | -4.1 | -4.1 | 2.6 | 3.4 | 6 | 0 | Sheet piles | 61.2 | 0 | 6 | 4.7124 | 50.4876 | 6 | 12 | 7 | 84 | 3.1 | Single-stage wellpoints | 3.0383 | 7.0098 | No extra measure | 2027-04-01 | 2027-06-28 | 162 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST D wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-16D-S01: backfill after both laid; closure: lay after UG-11B-S12 laid | -1 | 85
UG-16D | UG-16D-S01 | F6 | HDPE-UG16D-S01-SDCA-FSTD-(0.79/-4.00)-36m | HDPE | 28 | Short connection | SDCA, FSTD | 0 |  | 0 | No | 7 | 1.6 | 36.3001 | 0.79 | -4 | -4 | 2.5 | 3.3 | 26.3001 | 10 | Mixed: 26 m sheet piles | 312.4349 | 64.4099 | 42.8052 | 66.2039 | 267.8356 | 28 | 52.6003 | 7 | 368.2018 | 3 | Single-stage wellpoints | 0.3057 | 2.7879 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-01 | 2027-06-27 | 163 | R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R057: 11 native short-fitting objects have all 24 mesh vertices coincident. Their embedded source centreline still has 0.584683786 m of represented 3D length. | Both connected structures (secondary distribution chamber A, FST D) built with their wall penetrations; lay between them. UG-11B is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-11B-S07 backfilled (deeper); shared trench with UG-11B-S11: start excavation with it; shared trench with UG-11B-S12: start excavation with it; built by F6 (shared corridor; line system front F3) | 34 | 202
UG-11B | UG-11B-S13 | F6 | HDPE-UG11B-S13-TEE-CH018-(-4.63/-4.63)-18m | HDPE | 28 | Run |  | 0 |  | 0 | No | 0 | 2.0696 | 18.1 | -4.6348 | -4.6348 | -4.6348 | 3.1348 | 3.9348 | 18.1 | 0 | Sheet piles | 289.8363 | 0 | 27.7799 | 60.8893 | 201.1672 | 16 | 36.2 | 8 | 289.6 | 3.6348 | Single-stage wellpoints | 1.1934 | 3.1124 | No extra measure | 2027-04-01 | 2027-06-29 | 164 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R026: Component material GRP differs from scheduled whole-line material HDPE. Flow direction: not established: model order kept. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | None | -2 | 80
UG-11A | UG-11A-S04 | F6 | HDPE-UG11A-S04-TEE084-CH124-(-4.29/-4.29)-40m | HDPE | 28 | Run |  | 0 |  | 0 | No | 1 | 1.4 | 39.672 | -4.29 | -4.29 | -4.29 | 2.79 | 3.59 | 39.672 | 0 | Sheet piles | 484.2376 | 0 | 47.6065 | 61.0707 | 375.5604 | 30 | 79.3441 | 8 | 634.7525 | 3.29 | Single-stage wellpoints | 2.0107 | 4.8476 | No extra measure | 2027-04-07 | 2027-07-08 | 165 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Deepest first: lay and backfill this line to the bed level of UG-07A before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-07A-S04: complete first | -5 | 82
UG-11A | UG-11A-S03 | F6 | HDPE-UG11A-S03-CH054-TEE084-(-4.29/-4.29)-30m | HDPE | 28 | Run |  | 0 |  | 0 | No | 3 | 1.4 | 29.728 | -4.29 | -4.29 | -4.29 | 2.79 | 3.59 | 29.728 | 0 | Sheet piles | 362.8145 | 0 | 35.6693 | 45.7439 | 281.4013 | 22 | 59.4559 | 8 | 475.6475 | 3.29 | Single-stage wellpoints | 2.0107 | 4.8474 | No extra measure | 2027-04-12 | 2027-07-15 | 166 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Deepest first: lay and backfill this line to the bed level of UG-07A before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-07A-S04: complete first | -2 | 83
UG-11A | UG-11A-S02 | F6 | HDPE-UG11A-S02-CH006-CH054-(-4.09/-4.29)-48m | HDPE | 28 | Run |  | 0 |  | 0 | No | 1 | 1.4 | 48.3 | -4.09 | -4.29 | -4.29 | 2.79 | 3.59 | 48.3 | 0 | Sheet piles | 528.4907 | 0 | 51.962 | 51.7406 | 424.7881 | 36 | 96.6 | 8 | 772.8 | 3.29 | Single-stage wellpoints | 2.0107 | 4.8474 | No extra measure | 2027-04-19 | 2027-07-25 | 167 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-07A-S06: complete first; shared trench with UG-14G-S01: backfill after both laid | -5 | 86
UG-11A | UG-11A-S01 | F6 | HDPE-UG11A-S01-FSTG-CH006-(-4.09/-4.09)-6m | HDPE | 28 | Tie-in | FSTG | 0 |  | 0 | No | 0 | 0.99999 | 6 | -4.09 | -4.09 | -4.09 | 2.59 | 3.39 | 6 | 0 | Sheet piles | 61.0196 | 0 | 6 | 4.7123 | 50.3074 | 3 | 12 | 7 | 84 | 3.09 | Single-stage wellpoints | 3.0277 | 6.9993 | No extra measure | 2027-04-25 | 2027-07-30 | 168 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST G wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-14G-S01: backfill after both laid; closure: lay after UG-11A-S02 laid | -1 | 93
UG-14G | UG-14G-S01 | F6 | HDPE-UG14G-S01-SDCB-FSTG-(0.81/-3.98)-38m | HDPE | 28 | Short connection | SDCB, FSTG | 0 |  | 0 | No | 8 | 1.6 | 38.2988 | 0.81 | -3.98 | -3.98 | 2.48 | 3.28 | 0 | 38.2988 | Open cut | 0 | 988.5207 | 45.0884 | 69.7351 | 873.6972 | 28 | 0 | 0 | 0 | 2.98 | Single-stage wellpoints | 0.28087 | 2.7631 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-01 | 2027-07-30 | 169 | R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R057: 11 native short-fitting objects have all 24 mesh vertices coincident. Their embedded source centreline still has 0.584683786 m of represented 3D length. | Both connected structures (secondary distribution chamber B, FST G) built with their wall penetrations; lay between them. UG-13B is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-13B-S02 backfilled (deeper); excavate after UG-13B-S03 backfilled (deeper); shared trench with UG-11A-S01: start excavation with it; shared trench with UG-11A-S02: start excavation with it; built by F6 (shared corridor; line system front F3) | 45 | 237
UG-11A | UG-11A-S07 | F6 | HDPE-UG11A-S07-CH006-TEE-(-4.09/-4.19)-36m | HDPE | 28 | Run |  | 0 |  | 0 | No | 3 | 1.2 | 36.1403 | -4.09 | -4.19 | -4.19 | 2.69 | 3.49 | 36.1403 | 0 | Sheet piles | 370.217 | 0 | 36.4078 | 29.3091 | 304.5 | 28 | 72.2806 | 7 | 505.9641 | 3.19 | Single-stage wellpoints | 2.4344 | 5.7441 | No extra measure | 2027-04-25 | 2027-08-03 | 171 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R053: Positive-length overlap of near-collinear source centrelines at 1 mm geometric diagnostic tolerance. | Deepest first: lay and backfill this line to the bed level of UG-07A before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-07A-S04: complete first; shared trench with UG-14H-S01: backfill after both laid | -4 | 85
UG-11A | UG-11A-S06 | F6 | HDPE-UG11A-S06-FSTH-CH006-(-4.09/-4.09)-6m | HDPE | 28 | Tie-in | FSTH | 0 |  | 0 | No | 0 | 0.99999 | 6 | -4.09 | -4.09 | -4.09 | 2.59 | 3.39 | 6 | 0 | Sheet piles | 61.0198 | 0 | 6 | 4.7123 | 50.3075 | 3 | 12 | 7 | 84 | 3.09 | Single-stage wellpoints | 3.0277 | 6.9993 | No extra measure | 2027-05-05 | 2027-08-08 | 172 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST H wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-14H-S01: backfill after both laid; closure: lay after UG-11A-S07 laid | -1 | 92
UG-14H | UG-14H-S01 | F6 | HDPE-UG14H-S01-SDCB-FSTH-(0.81/-3.98)-38m | HDPE | 28 | Short connection | SDCB, FSTH | 0 |  | 0 | No | 8 | 1.6 | 38.1766 | 0.81 | -3.98 | -3.98 | 2.48 | 3.28 | 0 | 38.1766 | Open cut | 0 | 988.3716 | 45.0547 | 69.6829 | 873.634 | 28 | 0 | 0 | 0 | 2.98 | Single-stage wellpoints | 0.27658 | 2.7588 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-01 | 2027-08-08 | 173 | R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. | Both connected structures (secondary distribution chamber B, FST H) built with their wall penetrations; lay between them. UG-13B is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-13B-S04 backfilled (deeper); shared trench with UG-11A-S06: start excavation with it; shared trench with UG-11A-S07: start excavation with it; built by F6 (shared corridor; line system front F3) | 58 | 246
UG-12 | UG-12-S04 | F7 | GRP-UG12-S04-CH101-CH143-(-6.34/-6.18)-42m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.0696 | 42.1 | -6.3381 | -6.1789 | -6.3381 | 4.8381 | 5.6381 | 42.1 | 0 | Sheet piles | 952.3387 | 0 | 64.6151 | 141.627 | 746.0965 | 32 | 84.2 | 12 | 1010.4 | 5.3381 | Deep wells or two-stage wellpoints | 1.9864 | 3.9054 | No extra measure | 2026-12-01 | 2027-01-16 | 30 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | One shared excavation and dewatering front with UG-13B: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-07A before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-07A-S10: complete first; deeper than UG-07A-S11: complete first; deeper than UG-07A-S12: complete first; shared trench with UG-13B-S05: backfill after both laid; shared trench with UG-13B-S06: backfill after both laid; shared trench with UG-13B-S07: backfill after both laid; built by F7 (shared corridor; line system front F5); COORDINATE ON SITE: do not backfill beside UG-13B-S07 until it is laid (link left out to keep the logic loop-free); COORDINATE ON SITE: do not backfill beside UG-13B-S06 until it is laid (link left out to keep the logic loop-free) | 11 | 40
UG-13B | UG-13B-S05 | F7 | HDPE-UG13B-S05-CH096-CH160-(-4.11/-5.40)-64m | HDPE | 28 | Run |  | 0 |  | 0 | No | 4 | 1 | 64.1 | -4.107 | -5.3984 | -5.3984 | 3.8984 | 4.6984 | 64.1 | 0 | Sheet piles | 790.4793 | 0 | 64.0957 | 50.3305 | 676.053 | 23 | 128.2 | 10 | 1282 | 4.3984 | Single-stage wellpoints | 3.0487 | 7.0203 | No extra measure | 2026-12-02 | 2027-01-20 | 31 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-07A-S11: backfill after both laid; shared trench with UG-12-S04: start excavation with it; COORDINATE ON SITE: do not backfill beside UG-07A-S11 until it is laid (link left out to keep the logic loop-free) | 4 | 35
UG-13 | UG-13-S03 | F7 | GRP-UG13-S03-CH052-RASPS-(-5.92/-5.61)-32m | GRP | 28 | Run |  | 0 |  | 0 | No | 2 | 2.0412 | 32.2696 | -5.9205 | -5.61 | -5.9206 | 4.4206 | 5.2206 | 32.2696 | 0 | Sheet piles | 673.1069 | 0 | 48.5137 | 102.5758 | 522.0174 | 24 | 64.5392 | 11 | 709.9314 | 4.9206 | Deep wells or two-stage wellpoints | 1.8943 | 3.84 | No extra measure | 2026-12-11 | 2027-01-23 | 32 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. RAS/WAS pumping station: structure not in the master model, tie-in position not checked. | Deepest first: lay and backfill this line to the bed level of UG-12, UG-12A before that line. UG-13B is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-08-S05: complete first; deeper than UG-12-S01: complete first; deeper than UG-12-S02: complete first; deeper than UG-12-S03: complete first; deeper than UG-12A-S11: complete first; deeper than UG-12A-S12: complete first; shared trench with UG-13B-S11: backfill after both laid; COORDINATE ON SITE: do not backfill beside UG-13B-S11 until it is laid (link left out to keep the logic loop-free) | 0 | 32
UG-13 | UG-13-S04 | F7 | GRP-UG13-S04-FSTI-CH037-(-5.92/-5.92)-37m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.0412 | 37.2 | -5.9206 | -5.9206 | -5.9206 | 4.4206 | 5.2206 | 37.2 | 0 | Sheet piles | 784.8278 | 0 | 56.5664 | 121.7323 | 606.5291 | 28 | 74.4 | 11 | 818.4 | 4.9206 | Deep wells or two-stage wellpoints | 1.8943 | 3.84 | No extra measure | 2026-12-17 | 2027-02-01 | 33 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. FST I: structure not in the master model, tie-in position not checked. | Deepest first: lay and backfill this line to the bed level of UG-12 before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-12-S03: complete first; shared trench with UG-13B-S11: backfill after both laid; COORDINATE ON SITE: do not backfill beside UG-13B-S11 until it is laid (link left out to keep the logic loop-free) | -5 | 35
UG-12 | UG-12-S03 | F7 | GRP-UG12-S03-CH046-CH101-(-3.08/-6.34)-55m | GRP | 28 | Run |  | 0 |  | 0 | No | 4 | 2.0697 | 55.2 | -3.081 | -6.3381 | -6.4648 | 4.9648 | 5.7648 | 41.3 | 13.9 | Mixed: 41 m sheet piles | 919.3976 | 302.4676 | 84.7213 | 185.6978 | 951.4461 | 40 | 82.6 | 12 | 991.2 | 5.4648 | Deep wells or two-stage wellpoints | 0 | 1.7061 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-23 | 2027-03-13 | 34 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | One shared excavation and dewatering front with UG-13B: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-08, UG-09 before that line. UG-13 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-08-S05: complete first; deeper than UG-09-S04: complete first; deeper than UG-09-S05: complete first; excavate after UG-13-S03 backfilled (deeper); excavate after UG-13-S04 backfilled (deeper); deeper than UG-13B-S08: complete first; shared trench with UG-13B-S06: backfill after both laid; shared trench with UG-13B-S07: backfill after both laid; shared trench with UG-13B-S11: backfill after both laid; built by F7 (shared corridor; line system front F5) | 22 | 68
UG-13B | UG-13B-S11 | F7 | HDPE-UG13B-S11-TEE-TEE-(-5.60/-5.60)-15m | HDPE | 28 | Run |  | 0 |  | 0 | No | 1 | 1.4 | 14.5305 | -5.6 | -5.6 | -5.6 | 4.1 | 4.9 | 14.5305 | 0 | Sheet piles | 242.0777 | 0 | 17.4366 | 22.3679 | 202.2732 | 12 | 29.061 | 10 | 290.6096 | 4.6 | Deep wells or two-stage wellpoints | 3.0054 | 5.8422 | No extra measure | 2026-12-30 | 2027-03-15 | 35 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. Flow direction: not established: model order kept. | One shared excavation and dewatering front with UG-12, UG-13: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-08, UG-09 before that line. UG-13 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-08-S05: complete first; deeper than UG-09-S04: complete first; deeper than UG-09-S05: complete first; shared trench with UG-12-S03: start excavation with it; shared trench with UG-13-S03: start excavation with it; shared trench with UG-13-S04: start excavation with it | 20 | 48
UG-13B | UG-13B-S07 | F7 | HDPE-UG13B-S07-CH197-TEE223-(-5.40/-5.40)-26m | HDPE | 28 | Run |  | 0 |  | 0 | No | 3 | 1.4 | 25.6651 | -5.4 | -5.4 | -5.6 | 4.1 | 4.9 | 25.6651 | 0 | Sheet piles | 367.6421 | 0 | 26.1154 | 21.8551 | 319.6716 | 20 | 51.3302 | 10 | 513.3018 | 4.6 | Deep wells or two-stage wellpoints | 3.0054 | 5.8422 | No extra measure | 2027-01-09 | 2027-03-18 | 36 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R052: Positive-length overlap of near-collinear source centrelines at 1 mm geometric diagnostic tolerance. R054: Positive-length overlap of near-collinear source centrelines at 1 mm geometric diagnostic tolerance. | One shared excavation and dewatering front with UG-12: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-07A-S10: complete first; deeper than UG-07A-S11: complete first; deeper than UG-09-S04: complete first; deeper than UG-09-S05: complete first; shared trench with UG-12-S03: start excavation with it; shared trench with UG-12-S04: start excavation with it | 15 | 49
UG-13B | UG-13B-S06 | F7 | HDPE-UG13B-S06-CH160-CH197-(-5.40/-5.40)-37m | HDPE | 28 | Run |  | 0 |  | 0 | No | 2 | 1 | 37 | -5.3984 | -5.4 | -5.4 | 3.9 | 4.7 | 37 | 0 | Sheet piles | 521.6958 | 0 | 37 | 29.0597 | 455.6361 | 14 | 74 | 10 | 740 | 4.4 | Single-stage wellpoints | 4.4184 | 8.39 | No extra measure | 2027-01-13 | 2027-04-02 | 37 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | One shared excavation and dewatering front with UG-07A, UG-12: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-07A before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-07A-S10: complete first; shared trench with UG-07A-S11: backfill after both laid; shared trench with UG-12-S03: start excavation with it; shared trench with UG-12-S04: start excavation with it | 21 | 61
UG-07A | UG-07A-S11 | F7 | HDPE-UG07A-S11-EL009-CH050-(-2.89/-4.74)-41m | HDPE | 28 | Run |  | 0 |  | 0 | No | 2 | 1.2 | 40.8001 | -2.892 | -4.7376 | -4.82 | 3.32 | 4.12 | 39.504 | 1.2961 | Mixed: 40 m sheet piles | 507.8686 | 25.2835 | 44.8801 | 46.144 | 442.1279 | 30 | 79.008 | 9 | 711.0717 | 3.82 | Single-stage wellpoints | 0.95796 | 4.2676 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-18 | 2027-04-05 | 38 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | One shared excavation and dewatering front with UG-13B: lay all pipes before backfill. UG-12, UG-13B is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-12-S04 backfilled (deeper); excavate after UG-12-S05 backfilled (deeper); excavate after UG-13B-S07 backfilled (deeper); shared trench with UG-13B-S05: start excavation with it; shared trench with UG-13B-S06: start excavation with it; built by F7 (shared corridor; line system front F4) | 3 | 61
UG-13B | UG-13B-S12 | F7 | HDPE-UG13B-S12-RASPS-RASPS-(-5.93/-5.93)-5m | HDPE | 28 | Short connection | RASPS, RASPS | 0 |  | 0 | No | 0 | 2.0696 | 4.9228 | -5.9348 | -5.9348 | -5.9348 | 4.4348 | 5.2348 | 4.9228 | 0 | Sheet piles | 104.873 | 0 | 7.5555 | 16.5606 | 80.7569 | 6 | 9.8456 | 11 | 108.3014 | 4.9348 | Deep wells or two-stage wellpoints | 1.8611 | 3.7801 | No extra measure | 2026-12-01 | 2027-04-27 | 42 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Both connected structures (RAS/WAS pumping station, RAS/WAS pumping station) built with their wall penetrations; lay between them. One shared excavation and dewatering front with UG-13, UG-23: lay all pipes before backfill. UG-13 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-13-S05: backfill after both laid; shared trench with UG-23-S01: backfill after both laid; shared trench with UG-23-S02: backfill after both laid; shared trench with UG-23-S03: backfill after both laid | 122 | 144
UG-13 | UG-13-S05 | F7 | GRP-UG13-S05-CH037-RASPS-(-5.92/-5.93)-44m | GRP | 28 | Run |  | 0 |  | 0 | No | 2 | 2.0696 | 44.3431 | -5.9206 | -5.9348 | -5.9348 | 4.4348 | 5.2348 | 44.3431 | 0 | Sheet piles | 935.9426 | 0 | 67.4567 | 145.291 | 723.1949 | 32 | 88.6862 | 11 | 975.5483 | 4.9348 | Deep wells or two-stage wellpoints | 1.8611 | 3.7801 | No extra measure | 2027-01-22 | 2027-04-29 | 43 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Deepest first: lay and backfill this line to the bed level of UG-08 before that line. UG-13B is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-08-S04: complete first; shared trench with UG-13B-S12: start excavation with it; shared trench with UG-23-S01: backfill after both laid; shared trench with UG-23-S02: backfill after both laid; shared trench with UG-23-S03: backfill after both laid | 17 | 52
UG-23 | UG-23-S03 | F7 | HDPE-UG23-S03-CH015-CH035-(-5.07/-5.07)-20m | HDPE | 28 | Run |  | 0 |  | 0 | No | 2 | 0.63 | 20 | -5.075 | -5.075 | -5.075 | 3.575 | 4.375 | 20 | 0 | Sheet piles | 230.1248 | 0 | 16.3 | 6.2344 | 207.5903 | 8 | 40 | 9 | 360 | 4.075 | Single-stage wellpoints | 7.092 | 13.3961 | No extra measure | 2027-01-29 | 2027-05-01 | 44 | Common holds only (see Read Me). | Deepest first: lay and backfill this line to the bed level of UG-08, UG-09 before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-08-S03: complete first; deeper than UG-08-S04: complete first; deeper than UG-09-S03: complete first; deeper than UG-09-S04: complete first; shared trench with UG-13-S05: start excavation with it; shared trench with UG-13B-S12: start excavation with it; built by F7 (shared corridor; line system front F6) | 15 | 48
UG-23 | UG-23-S02 | F7 | HDPE-UG23-S02-EL011-CH015-(-5.07/-5.07)-4m | HDPE | 28 | Run |  | 0 |  | 0 | No | 0 | 0.63 | 3.6133 | -5.075 | -5.075 | -5.075 | 3.575 | 4.375 | 3.6133 | 0 | Sheet piles | 41.5753 | 0 | 2.9448 | 1.1263 | 37.5042 | 3 | 7.2266 | 9 | 65.0392 | 4.075 | Single-stage wellpoints | 7.0921 | 13.3962 | No extra measure | 2027-02-07 | 2027-05-03 | 45 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). | One shared excavation and dewatering front with UG-13, UG-13B: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-08-S04: complete first; shared trench with UG-13-S05: start excavation with it; shared trench with UG-13B-S12: start excavation with it; built by F7 (shared corridor; line system front F6) | 12 | 48
UG-23 | UG-23-S01 | F7 | HDPE-UG23-S01-RASPS-EL011-(-5.07/-5.08)-11m | HDPE | 28 | Tie-in | RASPS | 0 |  | 0 | No | 2 | 0.63 | 11.3867 | -5.075 | -5.075 | -5.075 | 3.575 | 4.375 | 11.3867 | 0 | Sheet piles | 131.0181 | 0 | 9.2801 | 3.5495 | 118.1885 | 5 | 22.7734 | 9 | 204.9608 | 4.075 | Single-stage wellpoints | 7.092 | 13.396 | No extra measure | 2027-02-10 | 2027-04-29 | 46 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). | RAS/WAS pumping station wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-13, UG-13B: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-13-S05: start excavation with it; shared trench with UG-13B-S12: start excavation with it; closure: lay after UG-23-S02 laid; built by F7 (shared corridor; line system front F6) | -2 | 75
UG-13B | UG-13B-S09 | F7 | HDPE-UG13B-S09-CH238-CH268-(-5.40/-5.40)-30m | HDPE | 28 | Run |  | 0 |  | 0 | No | 0 | 1 | 30.038 | -5.4 | -5.4 | -5.4 | 3.9 | 4.7 | 30.038 | 0 | Sheet piles | 423.5358 | 0 | 30.038 | 23.5918 | 369.906 | 12 | 60.076 | 10 | 600.76 | 4.4 | Single-stage wellpoints | 4.4201 | 8.3917 | No extra measure | 2027-02-10 | 2027-05-06 | 47 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-09-S05: complete first; deeper than UG-14F-S01: complete first | 7 | 49
UG-13B | UG-13B-S10 | F7 | HDPE-UG13B-S10-CH268-FSTF-(-5.40/-5.40)-6m | HDPE | 28 | Tie-in | FSTF | 0 |  | 0 | No | 0 | 1 | 6.0001 | -5.4 | -5.4 | -5.4 | 3.9 | 4.7 | 6.0001 | 0 | Sheet piles | 84.6007 | 0 | 6.0001 | 4.7124 | 73.8883 | 4 | 12.0001 | 10 | 120.0011 | 4.4 | Single-stage wellpoints | 4.4201 | 8.3917 | No extra measure | 2027-02-12 | 2027-05-05 | 48 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST F wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-14F-S01: complete first; closure: lay after UG-13B-S09 laid | -1 | 79
UG-13B | UG-13B-S08 | F7 | HDPE-UG13B-S08-TEE223-CH238-(-5.40/-5.40)-16m | HDPE | 28 | Run |  | 0 |  | 0 | No | 3 | 1 | 16.1415 | -5.4 | -5.4 | -5.4 | 3.9 | 4.7 | 16.1415 | 0 | Sheet piles | 227.5191 | 0 | 16.1354 | 12.6584 | 198.7253 | 7 | 32.283 | 10 | 322.8298 | 4.4 | Single-stage wellpoints | 4.4201 | 8.3917 | No extra measure | 2027-02-12 | 2027-05-08 | 49 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R052: Positive-length overlap of near-collinear source centrelines at 1 mm geometric diagnostic tolerance. R054: Positive-length overlap of near-collinear source centrelines at 1 mm geometric diagnostic tolerance. | Deepest first: lay and backfill this line to the bed level of UG-09 before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-09-S04: complete first; deeper than UG-09-S05: complete first; deeper than UG-09-S06: complete first; excavate after UG-12-S03 backfilled (deeper) | 4 | 48
UG-13B | UG-13B-S04 | F7 | HDPE-UG13B-S04-CH072-CH096-(-4.10/-4.11)-24m | HDPE | 28 | Run |  | 0 |  | 0 | No | 5 | 1.0018 | 24 | -4.1009 | -4.107 | -4.107 | 2.607 | 3.407 | 24 | 0 | Sheet piles | 244.6939 | 0 | 23.9621 | 18.7308 | 202.001 | 20 | 48 | 7 | 336 | 3.107 | Single-stage wellpoints | 3.0319 | 6.9965 | No extra measure | 2027-02-16 | 2027-05-13 | 50 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R057: 11 native short-fitting objects have all 24 mesh vertices coincident. Their embedded source centreline still has 0.584683786 m of represented 3D length. | Deepest first: lay and backfill this line to the bed level of UG-14H before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-14H-S01: complete first | -1 | 51
UG-13B | UG-13B-S03 | F7 | HDPE-UG13B-S03-CH057-CH072-(-4.10/-4.10)-15m | HDPE | 28 | Run |  | 0 |  | 0 | No | 0 | 1.0018 | 15 | -4.1009 | -4.1009 | -4.1009 | 2.6009 | 3.4009 | 15 | 0 | Sheet piles | 153.1302 | 0 | 15.0133 | 11.8227 | 126.2942 | 12 | 30 | 7 | 210 | 3.1009 | Single-stage wellpoints | 3.0319 | 6.9965 | No extra measure | 2027-02-19 | 2027-05-19 | 51 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | One shared excavation and dewatering front with UG-14G: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-14G before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-14G-S01: complete first | -2 | 55
UG-13B | UG-13B-S02 | F7 | HDPE-UG13B-S02-EL031-CH057-(-4.10/-4.10)-26m | HDPE | 28 | Run |  | 0 |  | 0 | No | 4 | 1.0018 | 26.2568 | -4.1 | -4.1009 | -4.1009 | 2.6009 | 3.4009 | 26.2568 | 0 | Sheet piles | 267.8852 | 0 | 26.2635 | 20.6431 | 220.9786 | 20 | 52.5136 | 7 | 367.5955 | 3.1009 | Single-stage wellpoints | 3.0319 | 6.9965 | No extra measure | 2027-02-24 | 2027-05-26 | 52 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-14G-S01: complete first | -2 | 60
UG-13A | UG-13A-S07 | F7 | HDPE-UG13A-S07-CH070-TEE080-(-5.56/-5.60)-11m | HDPE | 28 | Run |  | 0 |  | 0 | No | 3 | 1.4 | 10.536 | -5.5611 | -5.6 | -5.6 | 4.1 | 4.9 | 10.536 | 0 | Sheet piles | 174.8346 | 0 | 12.6432 | 16.2187 | 145.9728 | 10 | 21.072 | 10 | 210.7202 | 4.6 | Deep wells or two-stage wellpoints | 2.9759 | 5.8128 | No extra measure | 2027-02-28 | 2027-05-31 | 53 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-27J-S01: complete first | -1 | 62
UG-13 | UG-13-S02 | F7 | GRP-UG13-S02-EL020-CH052-(-5.93/-5.92)-33m | GRP | 28 | Run |  | 0 |  | 0 | No | 2 | 2.0696 | 32.6819 | -5.9348 | -5.9205 | -5.9348 | 4.4348 | 5.2348 | 32.6819 | 0 | Sheet piles | 694.536 | 0 | 50.0428 | 109.1851 | 535.3081 | 24 | 65.3637 | 11 | 719.001 | 4.9348 | Deep wells or two-stage wellpoints | 1.8611 | 3.7801 | No extra measure | 2027-03-05 | 2027-06-18 | 54 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | One shared excavation and dewatering front with UG-13A: lay all pipes before backfill. UG-13A is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-12-S01: complete first; deeper than UG-12-S02: complete first; shared trench with UG-13A-S02: backfill after both laid; shared trench with UG-13A-S16: backfill after both laid | 12 | 78
UG-13A | UG-13A-S02 | F7 | HDPE-UG13A-S02-CH006-RASPS-(-5.40/-5.41)-32m | HDPE | 28 | Run |  | 0 |  | 0 | No | 3 | 1.022 | 32.2439 | -5.4 | -5.411 | -5.411 | 3.911 | 4.711 | 32.2439 | 0 | Sheet piles | 454.8232 | 0 | 32.2587 | 25.3718 | 397.1927 | 24 | 64.4878 | 10 | 644.8776 | 4.411 | Single-stage wellpoints | 4.3138 | 8.2 | No extra measure | 2027-03-08 | 2027-06-21 | 55 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R038: Component material GRP differs from scheduled whole-line material HDPE. R040: Component material GRP differs from scheduled whole-line material HDPE. RAS/WAS pumping station: structure not in the master model, tie-in position not checked. | UG-13 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-27L-S01: complete first; shared trench with UG-13-S02: start excavation with it | 8 | 77
UG-13 | UG-13-S01 | F7 | GRP-UG13-S01-FSTJ-EL020-(-5.61/-5.92)-20m | GRP | 28 | Tie-in | FSTJ | 0 |  | 0 | No | 3 | 2.045 | 19.7181 | -5.6148 | -5.9225 | -5.9225 | 4.4225 | 5.2225 | 19.7181 | 0 | Sheet piles | 404.2676 | 0 | 29.1368 | 59.9207 | 315.2101 | 16 | 39.4363 | 11 | 433.799 | 4.9225 | Deep wells or two-stage wellpoints | 1.8898 | 3.8319 | No extra measure | 2027-03-08 | 2027-06-27 | 56 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST J wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-13A: lay all pipes before backfill. UG-13A is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-13A-S08: backfill after both laid; shared trench with UG-13A-S11: backfill after both laid; shared trench with UG-13A-S12: backfill after both laid; shared trench with UG-13A-S16: backfill after both laid; closure: lay after UG-13-S02 laid | 15 | 107
UG-13A | UG-13A-S16 | F7 | HDPE-UG13A-S16-EL029-RASPS-(-5.40/-5.41)-9m | HDPE | 28 | Run |  | 0 |  | 0 | No | 1 | 1.0221 | 9.2744 | -5.4 | -5.411 | -5.411 | 3.911 | 4.711 | 9.2744 | 0 | Sheet piles | 131.0515 | 0 | 9.2971 | 7.3564 | 114.398 | 10 | 18.5488 | 10 | 185.4875 | 4.411 | Single-stage wellpoints | 4.3132 | 8.1991 | No extra measure | 2027-03-14 | 2027-06-23 | 57 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R039: Component material GRP differs from scheduled whole-line material HDPE. RAS/WAS pumping station: structure not in the master model, tie-in position not checked. | UG-13 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-13-S01: start excavation with it; shared trench with UG-13-S02: start excavation with it | 6 | 76
UG-13A | UG-13A-S08 | F7 | HDPE-UG13A-S08-TEE080-FSTJ-(-5.60/-5.60)-12m | HDPE | 28 | Tie-in | FSTJ | 0 |  | 0 | No | 0 | 1.4 | 11.5705 | -5.6 | -5.6 | -5.6 | 4.1 | 4.9 | 11.5705 | 0 | Sheet piles | 192.7645 | 0 | 13.8846 | 17.8114 | 161.0685 | 10 | 23.141 | 10 | 231.4099 | 4.6 | Deep wells or two-stage wellpoints | 3.0054 | 5.8422 | No extra measure | 2027-03-05 | 2027-06-12 | 58 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST J wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. UG-13 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-13-S01: start excavation with it; closure: lay after UG-13A-S07 laid | 9 | 96
UG-13A | UG-13A-S12 | F7 | HDPE-UG13A-S12-CH006-TEE-(-5.60/-5.60)-5m | HDPE | 28 | Run |  | 0 |  | 0 | No | 0 | 1.4 | 5.2637 | -5.6 | -5.6 | -5.6 | 4.1 | 4.9 | 5.2637 | 0 | Sheet piles | 87.6926 | 0 | 6.3164 | 8.1027 | 73.2735 | 6 | 10.5274 | 10 | 105.2736 | 4.6 | Deep wells or two-stage wellpoints | 3.0054 | 5.8423 | No extra measure | 2027-03-20 | 2027-06-25 | 59 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | One shared excavation and dewatering front with UG-13: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-13-S01: start excavation with it | 3 | 76
UG-13A | UG-13A-S11 | F7 | HDPE-UG13A-S11-FSTJ-CH006-(-5.60/-5.60)-6m | HDPE | 28 | Tie-in | FSTJ | 0 |  | 0 | No | 0 | 1.4 | 6 | -5.6 | -5.6 | -5.6 | 4.1 | 4.9 | 6 | 0 | Sheet piles | 99.9597 | 0 | 7.2 | 9.2362 | 83.5235 | 6 | 12 | 10 | 120 | 4.6 | Deep wells or two-stage wellpoints | 3.0054 | 5.8423 | No extra measure | 2027-03-23 | 2027-06-29 | 60 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST J wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-13: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-13-S01: start excavation with it; closure: lay after UG-13A-S12 laid | -1 | 95
UG-13A | UG-13A-S01 | F7 | HDPE-UG13A-S01-FSTL-CH006-(-5.40/-5.40)-6m | HDPE | 28 | Tie-in | FSTL | 0 |  | 0 | No | 0 | 1 | 6 | -5.4 | -5.4 | -5.4 | 3.9 | 4.7 | 6 | 0 | Sheet piles | 84.5999 | 0 | 6 | 4.7124 | 73.8875 | 4 | 12 | 10 | 120 | 4.4 | Single-stage wellpoints | 4.4201 | 8.3917 | No extra measure | 2027-03-14 | 2027-06-19 | 66 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST L wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-27L-S01: complete first; closure: lay after UG-13A-S02 laid | -1 | 94
UG-13A | UG-13A-S06 | F7 | HDPE-UG13A-S06-CH053-CH070-(-5.50/-5.56)-16m | HDPE | 28 | Run |  | 0 |  | 0 | No | 0 | 1.4 | 16.1 | -5.5016 | -5.5611 | -5.5611 | 4.0611 | 4.8611 | 16.1 | 0 | Sheet piles | 264.468 | 0 | 19.3199 | 24.7837 | 220.3644 | 14 | 32.2 | 10 | 322 | 4.5611 | Deep wells or two-stage wellpoints | 2.9307 | 5.7676 | No extra measure | 2027-03-23 | 2027-06-30 | 67 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Deepest first: lay and backfill this line to the bed level of UG-27J before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-27J-S01: complete first | -1 | 79
UG-13A | UG-13A-S05 | F7 | HDPE-UG13A-S05-TEE048-CH053-(-5.48/-5.50)-5m | HDPE | 28 | Run |  | 0 |  | 0 | No | 1 | 1.4 | 5.1884 | -5.4824 | -5.5016 | -5.5016 | 4.0016 | 4.8016 | 5.1884 | 0 | Sheet piles | 84.5336 | 0 | 6.2261 | 7.9869 | 70.3207 | 6 | 10.3768 | 10 | 103.7681 | 4.5016 | Deep wells or two-stage wellpoints | 2.9161 | 5.7529 | No extra measure | 2027-03-26 | 2027-07-05 | 68 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | None | -1 | 81
UG-13A | UG-13A-S10 | F7 | HDPE-UG13A-S10-EL001-TEE-(-5.40/-5.48)-16m | HDPE | 28 | Run |  | 0 |  | 0 | No | 2 | 1.4001 | 15.8257 | -5.4 | -5.4825 | -5.6001 | 4.1001 | 4.9001 | 15.8257 | 0 | Sheet piles | 236.8824 | 0 | 16.9187 | 16.5501 | 203.4136 | 14 | 31.6514 | 10 | 316.5137 | 4.6001 | Deep wells or two-stage wellpoints | 2.9158 | 5.7524 | No extra measure | 2027-03-30 | 2027-07-11 | 69 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-27I-S01: complete first | -2 | 85
UG-13A | UG-13A-S09 | F7 | HDPE-UG13A-S09-SDCC-EL001-(-5.39/-5.39)-1m | HDPE | 28 | Tie-in | SDCC | 0 |  | 0 | No | 1 | 0.98078 | 0.6364 | -5.3904 | -5.3904 | -5.3904 | 3.8904 | 4.6904 | 0.6364 | 0 | Sheet piles | 8.8975 | 0 | 0.63028 | 0.4808 | 7.7864 | 2 | 1.2728 | 10 | 12.7279 | 4.3904 | Single-stage wellpoints | 4.5171 | 8.5665 | No extra measure | 2027-04-02 | 2027-07-16 | 70 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | secondary distribution chamber C wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-27I-S01: complete first; closure: lay after UG-13A-S10 laid | -1 | 102
UG-13A | UG-13A-S14 | F7 | HDPE-UG13A-S14-EL030-SDCC-(-4.10/-4.09)-31m | HDPE | 28 | Run |  | 0 |  | 0 | No | 5 | 1 | 31.4977 | -4.1 | -4.0904 | -4.1 | 2.6 | 3.4 | 31.4977 | 0 | Sheet piles | 321.2159 | 0 | 31.4915 | 24.719 | 265.0054 | 12 | 62.9954 | 7 | 440.9676 | 3.1 | Single-stage wellpoints | 3.0383 | 7.0099 | No extra measure | 2027-04-02 | 2027-07-18 | 71 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-27I-S01: complete first | -2 | 90
UG-13A | UG-13A-S04 | F7 | HDPE-UG13A-S04-CH006-TEE048-(-4.15/-5.48)-42m | HDPE | 28 | Run |  | 0 |  | 0 | No | 8 | 1.4 | 42.2116 | -4.15 | -5.4824 | -5.4824 | 3.9824 | 4.7824 | 42.2116 | 0 | Sheet piles | 463.5811 | 0 | 42.782 | 35.3032 | 385.4959 | 32 | 84.4232 | 10 | 844.2319 | 4.4824 | Single-stage wellpoints | 2.7045 | 5.5413 | No extra measure | 2027-04-06 | 2027-08-06 | 72 | R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-27I-S01: backfill after both laid | 11 | 107
UG-13A | UG-13A-S03 | F7 | HDPE-UG13A-S03-FSTI-CH006-(-4.15/-4.15)-6m | HDPE | 28 | Tie-in | FSTI | 0 |  | 0 | No | 0 | 1 | 6 | -4.15 | -4.15 | -4.15 | 2.65 | 3.45 | 6 | 0 | Sheet piles | 62.0999 | 0 | 6 | 4.7124 | 51.3876 | 4 | 12 | 7 | 84 | 3.15 | Single-stage wellpoints | 3.0914 | 7.063 | No extra measure | 2027-04-10 | 2027-08-05 | 73 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST I wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-27I-S01: backfill after both laid; closure: lay after UG-13A-S04 laid | 6 | 114
UG-27I | UG-27I-S01 | F7 | HDPE-UG27I-S01-SDCC-FSTI-(0.79/-4.00)-38m | HDPE | 28 | Short connection | SDCC, FSTI | 0 |  | 0 | No | 8 | 1.6 | 37.5872 | 0.79 | -4 | -4 | 2.5 | 3.3 | 0.83997 | 36.7472 | Mixed: 1 m sheet piles | 9.2607 | 965.6476 | 44.6945 | 69.1255 | 861.0883 | 28 | 1.6799 | 7 | 11.7596 | 3 | Single-stage wellpoints | 0.3001 | 2.7823 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-01 | 2027-08-07 | 74 | R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R057: 11 native short-fitting objects have all 24 mesh vertices coincident. Their embedded source centreline still has 0.584683786 m of represented 3D length. | Both connected structures (secondary distribution chamber C, FST I) built with their wall penetrations; lay between them. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-13A-S09 backfilled (deeper); excavate after UG-13A-S10 backfilled (deeper); excavate after UG-13A-S14 backfilled (deeper); shared trench with UG-13A-S03: start excavation with it; shared trench with UG-13A-S04: start excavation with it; built by F7 (shared corridor; line system front F3) | -5 | 244
UG-13A | UG-13A-S15 | F7 | HDPE-UG13A-S15-FSTJ-EL029-(-5.40/-5.40)-29m | HDPE | 28 | Tie-in | FSTJ | 0 |  | 0 | No | 2 | 1 | 29.1958 | -5.4 | -5.4 | -5.4 | 3.9 | 4.7 | 29.1958 | 0 | Sheet piles | 411.6609 | 0 | 29.1958 | 22.9303 | 359.5348 | 11 | 58.3917 | 10 | 583.9166 | 4.4 | Single-stage wellpoints | 4.4201 | 8.3917 | No extra measure | 2027-03-20 | 2027-06-25 | 75 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST J wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-12A-S09: complete first; deeper than UG-27J-S02: complete first; closure: lay after UG-13A-S16 laid | -2 | 92
UG-21 | UG-21-S01 | F8 | GRP-UG21-S01-CCT-WFT-(-6.24/-6.24)-12m | GRP | 28 | Short connection | CCT, WFT | 0 |  | 0 | No | 0 | 2.2764 | 12.2026 | -6.2382 | -6.2382 | -6.2382 | 4.7382 | 5.5382 | 12.2026 | 0 | Sheet piles | 289.0006 | 0 | 19.9903 | 49.6636 | 219.3467 | 12 | 24.4052 | 12 | 292.8622 | 5.2382 | Deep wells or two-stage wellpoints | 1.7371 | 3.4818 | No extra measure | 2026-12-01 | 2026-12-28 | 39 | R006: Embedded prior source review records section CL -4.66 versus plan labels around -4.60. | Both connected structures (chlorine contact tank, fire & service water structure (AW-FIRE)) built with their wall penetrations; lay between them. One shared excavation and dewatering front with UG-22, UG-28: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-10, UG-28A before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-10-S02: complete first; deeper than UG-10-S03: complete first; deeper than UG-28-S01: complete first; deeper than UG-28A-S01: complete first; shared trench with UG-22-S01: backfill after both laid; shared trench with UG-28-S02: backfill after both laid | 2 | 24
UG-22 | UG-22-S01 | F8 | GRP-UG22-S01-CCT-WFT-(-6.24/-6.24)-12m | GRP | 28 | Short connection | CCT, WFT | 0 |  | 0 | No | 0 | 2.2764 | 12.2104 | -6.2382 | -6.2382 | -6.2382 | 4.7382 | 5.5382 | 12.2104 | 0 | Sheet piles | 289.1853 | 0 | 20.003 | 49.6953 | 219.4869 | 12 | 24.4208 | 12 | 293.0494 | 5.2382 | Deep wells or two-stage wellpoints | 1.7371 | 3.4818 | No extra measure | 2026-12-01 | 2026-12-28 | 40 | R006: Embedded prior source review records section CL -4.66 versus plan labels around -4.60. | Both connected structures (chlorine contact tank, fire & service water structure (AW-FIRE)) built with their wall penetrations; lay between them. One shared excavation and dewatering front with UG-21, UG-28: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-10, UG-28A before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-10-S02: complete first; deeper than UG-10-S03: complete first; deeper than UG-17-S01: complete first; deeper than UG-28-S01: complete first; deeper than UG-28A-S01: complete first; shared trench with UG-21-S01: start excavation with it; shared trench with UG-28-S02: backfill after both laid | 2 | 24
UG-28 | UG-28-S02 | F8 | HDPE-UG28-S02-CCT-WFT-(-5.60/-5.60)-12m | HDPE | 28 | Short connection | CCT, WFT | 0 |  | 0 | No | 5 | 0.5 | 12.4454 | -5.6 | -5.6 | -5.6 | 4.1 | 4.9 | 12.4454 | 0 | Sheet piles | 152.4565 | 0 | 9.3341 | 2.4437 | 140.6787 | 6 | 24.8909 | 10 | 248.9085 | 4.6 | Deep wells or two-stage wellpoints | 10.3284 | 18.2715 | No extra measure | 2026-12-01 | 2026-12-30 | 41 | Common holds only (see Read Me). | Both connected structures (chlorine contact tank, fire & service water structure (AW-FIRE)) built with their wall penetrations; lay between them. One shared excavation and dewatering front with UG-21: lay all pipes before backfill. Deepest first: lay and backfill this line to the bed level of UG-10, UG-28A before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-10-S02: complete first; deeper than UG-10-S03: complete first; deeper than UG-28A-S01: complete first; shared trench with UG-21-S01: start excavation with it; shared trench with UG-22-S01: start excavation with it | -2 | 26
UG-15 | UG-15-S01 | F8 | GRP-UG15-S01-FSTA-CH049-(-5.03/-5.33)-49m | GRP | 28 | Run |  | 0 |  | 0 | No | 3 | 2.0696 | 49.3 | -5.033 | -5.3279 | -5.3448 | 3.8448 | 4.6448 | 49.3 | 0 | Sheet piles | 920.8634 | 0 | 75.037 | 161.8636 | 683.9628 | 36 | 98.6 | 10 | 986 | 4.3448 | Single-stage wellpoints | 1.507 | 3.426 | No extra measure | 2026-12-01 | 2027-01-11 | 82 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. FST A: structure not in the master model, tie-in position not checked. | Deepest first: lay and backfill this line to the bed level of UG-17 before that line. UG-15A is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-17-S01: complete first; deeper than UG-17-S02: complete first; shared trench with UG-15A-S06: backfill after both laid; shared trench with UG-15A-S09: backfill after both laid; shared trench with UG-15A-S10: backfill after both laid; shared trench with UG-17-S03: backfill after both laid; built by F8 (shared corridor; line system front F4); COORDINATE ON SITE: do not backfill beside UG-17-S03 until it is laid (link left out to keep the logic loop-free) | 12 | 37
UG-15A | UG-15A-S10 | F8 | HDPE-UG15A-S10-EL001-CCT-(-4.82/-4.84)-6m | HDPE | 28 | Run |  | 0 |  | 0 | No | 1 | 1.2258 | 6.3125 | -4.825 | -4.8379 | -4.8379 | 3.3379 | 4.1379 | 6.3125 | 0 | Sheet piles | 83.7718 | 0 | 6.9827 | 7.2878 | 69.5013 | 8 | 12.6249 | 9 | 113.6243 | 3.8379 | Single-stage wellpoints | 2.9226 | 6.1624 | No extra measure | 2026-12-02 | 2027-01-21 | 83 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R023: Component material GRP differs from scheduled whole-line material HDPE. chlorine contact tank: structure not in the master model, tie-in position not checked. | One shared excavation and dewatering front with UG-15: lay all pipes before backfill. UG-15 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-15-S01: start excavation with it; shared trench with UG-17-S02: backfill after both laid; built by F8 (shared corridor; line system front F4) | 18 | 42
UG-15A | UG-15A-S09 | F8 | HDPE-UG15A-S09-FSTB-EL001-(-4.82/-4.82)-1m | HDPE | 28 | Tie-in | FSTB | 0 |  | 0 | No | 1 | 1.2 | 0.88082 | -4.825 | -4.8163 | -4.825 | 3.325 | 4.125 | 0.88082 | 0 | Sheet piles | 11.595 | 0 | 0.96612 | 0.98577 | 9.6431 | 4 | 1.7616 | 9 | 15.8548 | 3.825 | Single-stage wellpoints | 2.9969 | 6.3066 | No extra measure | 2026-12-07 | 2027-01-10 | 84 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R009: 36 recorded tank interfaces: 13 nominal agreements and 23 model/guide vertical differences. Most pipe values are interpolated at openings. R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | FST B wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-15: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-15-S01: start excavation with it; closure: lay after UG-15A-S10 laid; built by F8 (shared corridor; line system front F4) | -1 | 31
UG-15A | UG-15A-S06 | F8 | HDPE-UG15A-S06-TEE149-CCT-(-4.90/-5.03)-63m | HDPE | 28 | Run |  | 0 |  | 0 | No | 3 | 1.6552 | 62.5267 | -4.9 | -5.033 | -5.033 | 3.533 | 4.333 | 62.5267 | 0 | Sheet piles | 949.8489 | 0 | 81.4639 | 126.6336 | 741.7514 | 44 | 125.0534 | 9 | 1125.4805 | 4.033 | Single-stage wellpoints | 1.9771 | 4.3765 | No extra measure | 2026-12-07 | 2027-04-12 | 85 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. R022: Component material GRP differs from scheduled whole-line material HDPE. R025: Component material GRP differs from scheduled whole-line material HDPE. chlorine contact tank: structure not in the master model, tie-in position not checked. | One shared excavation and dewatering front with UG-17: lay all pipes before backfill. UG-15 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-15-S01: start excavation with it; shared trench with UG-17-S02: backfill after both laid; shared trench with UG-17-S03: backfill after both laid; built by F8 (shared corridor; line system front F4) | 90 | 120
UG-17 | UG-17-S02 | F8 | GRP-UG17-S02-EL015-CH060-(-3.93/-4.32)-45m | GRP | 28 | Run |  | 0 |  | 0 | No | 2 | 2.2764 | 45.2674 | -3.9282 | -4.3182 | -4.3182 | 2.8182 | 3.6182 | 40 | 5.2674 | Mixed: 40 m sheet piles | 598.7892 | 183.5759 | 74.1571 | 184.2349 | 523.9731 | 34 | 80 | 8 | 640 | 3.3182 | Single-stage wellpoints | 0.46367 | 2.2084 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-09 | 2027-05-13 | 86 | Flow direction: levels: higher end taken as upstream (gravity assumption). | One shared excavation and dewatering front with UG-18: lay all pipes before backfill. UG-15 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-15-S01 backfilled (deeper); shared trench with UG-15A-S06: start excavation with it; shared trench with UG-15A-S10: start excavation with it; shared trench with UG-18-S01: backfill after both laid; shared trench with UG-18-S02: backfill after both laid | 111 | 146
UG-19 | UG-19-S03 | F8 | GRP-UG19-S03-TEE033-TEPS-(-4.28/-4.68)-82m | GRP | 28 | Run |  | 0 |  | 0 | No | 7 | 1.8626 | 82.2204 | -4.2804 | -4.6813 | -4.6813 | 3.1813 | 3.9813 | 82.2204 | 0 | Sheet piles | 1202.9904 | 0 | 117.4934 | 222.9726 | 862.5244 | 58 | 164.4409 | 8 | 1315.5271 | 3.6813 | Single-stage wellpoints | 1.2481 | 3.3804 | No extra measure | 2026-12-15 | 2027-05-17 | 87 | R049: Same endpoints, component and nodes, but different CAD envelope diameters [1.826378651619077, 1.8410003320057806]. Flow direction: levels: higher end taken as upstream (gravity assumption). treated effluent pump station (not modelled): structure not in the master model, tie-in position not checked. | One shared excavation and dewatering front with UG-20: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-20-S02: backfill after both laid | 104 | 138
UG-20 | UG-20-S02 | F8 | GRP-UG20-S02-EL003-TEPS-(-4.31/-4.58)-107m | GRP | 28 | Run |  | 0 |  | 0 | No | 8 | 1.8626 | 107.0069 | -4.3113 | -4.5813 | -4.5813 | 3.0813 | 3.8813 | 107.0069 | 0 | Sheet piles | 1532.138 | 0 | 152.9431 | 290.3524 | 1088.8425 | 74 | 214.0138 | 8 | 1712.1101 | 3.5813 | Single-stage wellpoints | 1.2595 | 3.3918 | No extra measure | 2026-12-20 | 2027-05-21 | 88 | Flow direction: levels: higher end taken as upstream (gravity assumption). treated effluent pump station (not modelled): structure not in the master model, tie-in position not checked. | One shared excavation and dewatering front with UG-19: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-18-S02: backfill after both laid; shared trench with UG-19-S01: backfill after both laid; shared trench with UG-19-S02: backfill after both laid; shared trench with UG-19-S03: start excavation with it | 97 | 138
UG-20 | UG-20-S01 | F8 | GRP-UG20-S01-WFT-EL003-(-4.31/-4.31)-3m | GRP | 28 | Tie-in | WFT | 0 |  | 0 | No | 2 | 1.8626 | 2.7185 | -4.3113 | -4.3113 | -4.3113 | 2.8113 | 3.6113 | 2.7185 | 0 | Sheet piles | 37.9197 | 0 | 3.8909 | 7.4071 | 26.6217 | 4 | 5.4369 | 8 | 43.4953 | 3.3113 | Single-stage wellpoints | 1.2595 | 3.3918 | No extra measure | 2026-12-27 | 2027-02-21 | 89 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). Flow direction: levels: higher end taken as upstream (gravity assumption). | fire & service water structure (AW-FIRE) wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-19: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-19-S01: backfill after both laid; shared trench with UG-19-S02: backfill after both laid; closure: lay after UG-20-S02 laid | 6 | 53
UG-19 | UG-19-S02 | F8 | GRP-UG19-S02-EL003-TEE033-(-4.03/-4.27)-31m | GRP | 28 | Run |  | 0 |  | 0 | No | 5 | 1.8626 | 30.5156 | -4.0313 | -4.2731 | -4.2783 | 2.7783 | 3.5783 | 30.5156 | 0 | Sheet piles | 407.6953 | 0 | 43.6498 | 82.99 | 281.0555 | 24 | 61.0312 | 8 | 488.2497 | 3.2783 | Single-stage wellpoints | 1.0997 | 3.232 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-27 | 2027-05-21 | 90 | R048: Same endpoints, component and nodes, but different CAD envelope diameters [1.8409980399798413, 1.826374015686294]. Flow direction: levels: higher end taken as upstream (gravity assumption). | One shared excavation and dewatering front with UG-20: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-20-S01: start excavation with it; shared trench with UG-20-S02: start excavation with it | 94 | 131
UG-19 | UG-19-S01 | F8 | GRP-UG19-S01-WFT-EL003-(-4.03/-4.03)-3m | GRP | 28 | Tie-in | WFT | 0 |  | 0 | No | 2 | 1.8626 | 2.5061 | -4.0313 | -4.0313 | -4.0313 | 2.5313 | 3.3313 | 2.5061 | 0 | Sheet piles | 32.2471 | 0 | 3.587 | 6.8285 | 21.8316 | 4 | 5.0122 | 7 | 35.0853 | 3.0313 | Single-stage wellpoints | 1.0997 | 3.232 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-06 | 2027-02-23 | 91 | Flow direction: levels: higher end taken as upstream (gravity assumption). | fire & service water structure (AW-FIRE) wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-20: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-20-S01: start excavation with it; shared trench with UG-20-S02: start excavation with it; closure: lay after UG-19-S02 laid | -2 | 45
UG-15A | UG-15A-S08 | F8 | HDPE-UG15A-S08-EL011-TEE-(-4.70/-4.70)-11m | HDPE | 28 | Run |  | 0 |  | 0 | No | 0 | 1.2 | 10.9818 | -4.7 | -4.7 | -4.7 | 3.2 | 4 | 10.9818 | 0 | Sheet piles | 140.5672 | 0 | 12.08 | 12.4202 | 116.067 | 10 | 21.9636 | 9 | 197.6725 | 3.7 | Single-stage wellpoints | 2.8862 | 6.1958 | No extra measure | 2027-01-06 | 2027-05-22 | 92 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-17-S03: backfill after both laid; built by F8 (shared corridor; line system front F4) | 91 | 129
UG-15A | UG-15A-S05 | F8 | HDPE-UG15A-S05-CH027-TEE149-(-4.66/-4.90)-122m | HDPE | 28 | Run |  | 0 |  | 0 | No | 6 | 1.6 | 122.1198 | -4.6624 | -4.9 | -4.9 | 3.4 | 4.2 | 122.1198 | 0 | Sheet piles | 1568.8756 | 0 | 135.2076 | 141.9602 | 1291.7077 | 84 | 244.2397 | 9 | 2198.1569 | 3.9 | Single-stage wellpoints | 2.0318 | 4.514 | No extra measure | 2027-01-10 | 2027-05-28 | 93 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | One shared excavation and dewatering front with UG-17: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-11B-S06: backfill after both laid; shared trench with UG-17-S03: backfill after both laid; shared trench with UG-18-S02: backfill after both laid; built by F8 (shared corridor; line system front F4) | 82 | 130
UG-17 | UG-17-S04 | F8 | GRP-UG17-S04-CH267-CH343-(-4.30/-4.30)-76m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.249 | 76 | -4.3045 | -4.3045 | -4.3045 | 2.8045 | 3.6045 | 76 | 0 | Sheet piles | 1163.9819 | 0 | 123.4622 | 301.9149 | 738.6049 | 54 | 152 | 8 | 1216 | 3.3045 | Single-stage wellpoints | 0.85725 | 2.6232 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-12 | 2027-05-30 | 94 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). Flow direction: levels: higher end taken as upstream (gravity assumption). | One shared excavation and dewatering front with UG-11B, UG-18: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-15A-S03: complete first; deeper than UG-15A-S04: complete first; shared trench with UG-11B-S05: backfill after both laid; shared trench with UG-11B-S06: backfill after both laid; shared trench with UG-18-S02: backfill after both laid | 76 | 122
UG-17 | UG-17-S05 | F8 | GRP-UG17-S05-CH343-OUTF-(-4.30/-4.30)-25m | GRP | 28 | Run |  | 0 |  | 0 | No | 0 | 2.249 | 24.9735 | -4.3045 | -4.3045 | -4.3045 | 2.8045 | 3.6045 | 24.9735 | 0 | Sheet piles | 382.4824 | 0 | 40.5695 | 99.2087 | 242.7042 | 20 | 49.9469 | 8 | 399.5754 | 3.3045 | Single-stage wellpoints | 0.85725 | 2.6232 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-01-23 | 2027-05-30 | 95 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). Flow direction: levels: higher end taken as upstream (gravity assumption). outfall chamber (not modelled): structure not in the master model, tie-in position not checked. | One shared excavation and dewatering front with UG-18: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-11B-S05: backfill after both laid; shared trench with UG-18-S02: backfill after both laid | 73 | 117
UG-11B | UG-11B-S05 | F8 | HDPE-UG11B-S05-CH166-CH241-(-4.30/-4.30)-75m | HDPE | 28 | Run |  | 0 |  | 0 | No | 4 | 1.425 | 75.1 | -4.3 | -4.3 | -4.3125 | 2.8125 | 3.6125 | 75.1 | 0 | Sheet piles | 919.4929 | 0 | 90.1453 | 115.7197 | 713.6278 | 54 | 150.2 | 8 | 1201.6 | 3.3125 | Single-stage wellpoints | 1.9736 | 4.7607 | No extra measure | 2027-01-30 | 2027-06-04 | 96 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | One shared excavation and dewatering front with UG-17: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-15A-S03: complete first; deeper than UG-15A-S04: complete first; shared trench with UG-17-S03: backfill after both laid; shared trench with UG-17-S04: start excavation with it; shared trench with UG-17-S05: start excavation with it; built by F8 (shared corridor; line system front F6) | 66 | 117
UG-17 | UG-17-S03 | F8 | GRP-UG17-S03-CH060-CH267-(-4.32/-4.30)-207m | GRP | 28 | Run |  | 0 |  | 0 | No | 6 | 2.2764 | 207.1 | -4.3182 | -4.3045 | -4.3182 | 2.8182 | 3.6182 | 207.1 | 0 | Sheet piles | 3176.5415 | 0 | 336.8429 | 825.6212 | 2014.0774 | 142 | 414.2 | 8 | 3313.6 | 3.3182 | Single-stage wellpoints | 0.84054 | 2.5852 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-02-02 | 2027-06-22 | 97 | Flow direction: levels: higher end taken as upstream (gravity assumption). | One shared excavation and dewatering front with UG-15A, UG-18: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-15A-S03: complete first; shared trench with UG-11B-S05: start excavation with it; shared trench with UG-11B-S06: backfill after both laid; shared trench with UG-15-S01: start excavation with it; shared trench with UG-15A-S04: backfill after both laid; shared trench with UG-15A-S05: start excavation with it; shared trench with UG-15A-S06: start excavation with it; shared trench with UG-15A-S08: start excavation with it; shared trench with UG-18-S02: backfill after both laid | 63 | 123
UG-18 | UG-18-S02 | F8 | GRP-UG18-S02-EL011-OUTF-(-3.93/-4.30)-365m | GRP | 28 | Run |  | 0 |  | 0 | No | 8 | 2.2764 | 364.5418 | -3.9282 | -4.3045 | -4.3171 | 2.8171 | 3.6171 | 364.5418 | 0 | Sheet piles | 5579.2448 | 0 | 594.7593 | 1466.3648 | 3518.1207 | 246 | 729.0836 | 8 | 5832.6688 | 3.3171 | Single-stage wellpoints | 0.46367 | 2.2083 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-02-09 | 2027-07-04 | 98 | Flow direction: levels: higher end taken as upstream (gravity assumption). outfall chamber (not modelled): structure not in the master model, tie-in position not checked. | One shared excavation and dewatering front with UG-17: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-15A-S05: start excavation with it; shared trench with UG-17-S01: backfill after both laid; shared trench with UG-17-S02: start excavation with it; shared trench with UG-17-S03: start excavation with it; shared trench with UG-17-S04: start excavation with it; shared trench with UG-17-S05: start excavation with it; shared trench with UG-20-S02: start excavation with it | 44 | 112
UG-11B | UG-11B-S06 | F8 | HDPE-UG11B-S06-CH241-TEE259-(-4.30/-4.30)-18m | HDPE | 28 | Run |  | 0 |  | 0 | No | 2 | 1.425 | 17.6867 | -4.3 | -4.3 | -4.3125 | 2.8125 | 3.6125 | 17.6867 | 0 | Sheet piles | 216.7524 | 0 | 21.2492 | 27.338 | 168.1652 | 14 | 35.3735 | 8 | 282.9878 | 3.3125 | Single-stage wellpoints | 1.9736 | 4.7607 | No extra measure | 2027-02-27 | 2027-06-23 | 99 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | Deepest first: lay and backfill this line to the bed level of UG-15A before that line. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | deeper than UG-15A-S03: complete first; shared trench with UG-15A-S04: backfill after both laid; shared trench with UG-15A-S05: start excavation with it; shared trench with UG-17-S03: start excavation with it; shared trench with UG-17-S04: start excavation with it; built by F8 (shared corridor; line system front F6) | 46 | 83
UG-15A | UG-15A-S04 | F8 | HDPE-UG15A-S04-EL017-CH027-(-2.72/-4.66)-10m | HDPE | 28 | Run |  | 0 |  | 0 | No | 3 | 1.2 | 9.6496 | -2.72 | -4.6624 | -4.6624 | 3.1624 | 3.9624 | 7.1 | 2.5496 | Mixed: 7 m sheet piles | 84.8095 | 41.0975 | 10.6047 | 10.8771 | 104.4252 | 10 | 14.2 | 8 | 113.6 | 3.6624 | Single-stage wellpoints | 0.62298 | 3.9326 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-03-29 | 2027-06-25 | 100 | R010: Local FCT outlet branches have approximately 1.20 m CAD envelopes and sludge branches approximately 1.00 m, versus larger scheduled trunk sizes. UG-12A is printed DN1600, not OD1600. | One shared excavation and dewatering front with UG-11B, UG-17: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-11B-S05 backfilled (deeper); excavate after UG-17-S04 backfilled (deeper); shared trench with UG-11B-S06: start excavation with it; shared trench with UG-17-S03: start excavation with it; built by F8 (shared corridor; line system front F4) | 13 | 82
UG-17 | UG-17-S01 | F8 | GRP-UG17-S01-WFT-EL015-(-3.93/-3.91)-15m | GRP | 28 | Tie-in | WFT | 0 |  | 0 | No | 6 | 2.2764 | 14.7326 | -3.9282 | -3.9145 | -3.9282 | 2.4282 | 3.2282 | 0 | 14.7326 | Open cut | 0 | 502.9318 | 24.0159 | 59.1182 | 419.7976 | 12 | 0 | 0 | 0 | 2.9282 | Single-stage wellpoints | 0.46367 | 2.2083 | Keep dewatering on until fill reaches FL, or strap to slab | 2026-12-15 | 2027-05-12 | 101 | Flow direction: levels: higher end taken as upstream (gravity assumption). | fire & service water structure (AW-FIRE) wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-18: lay all pipes before backfill. UG-15 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-15-S01 backfilled (deeper); excavate after UG-22-S01 backfilled (deeper); shared trench with UG-18-S01: backfill after both laid; shared trench with UG-18-S02: start excavation with it; closure: lay after UG-17-S02 laid | 30 | 146
UG-18 | UG-18-S01 | F8 | GRP-UG18-S01-WFT-EL011-(-3.93/-3.91)-11m | GRP | 28 | Tie-in | WFT | 0 |  | 0 | No | 6 | 2.2764 | 10.5191 | -3.9282 | -3.9145 | -3.9282 | 2.4282 | 3.2282 | 0 | 10.5191 | Open cut | 0 | 358.2952 | 17.1135 | 41.9699 | 299.2118 | 10 | 0 | 0 | 0 | 2.9282 | Single-stage wellpoints | 0.46367 | 2.2083 | Keep dewatering on until fill reaches FL, or strap to slab | 2027-02-27 | 2027-05-14 | 102 | Flow direction: levels: higher end taken as upstream (gravity assumption). | fire & service water structure (AW-FIRE) wall and penetration built; its excavation backfilled to pipe zone. Lay as the closure to the structure. One shared excavation and dewatering front with UG-17: lay all pipes before backfill. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | shared trench with UG-17-S01: start excavation with it; shared trench with UG-17-S02: start excavation with it; closure: lay after UG-18-S02 laid | -4 | 74
UG-28 | UG-28-S01 | F8 | HDPE-UG28-S01-CCT-CCT-(-0.64/-0.64)-1m | HDPE | 28 | Short connection | CCT, CCT | 0 |  | 0 | No | 1 | 0.5 | 1.1 | -0.63898 | -0.63941 | -0.63941 | 0 | 0 | 0 | 1.1 | Open cut | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | Not required | 99 | 99 | No extra measure | 2026-12-01 | 2027-03-19 | 122 | No drawing level anchor inside the package: levels interpolated between anchors elsewhere (no longitudinal profile). R051: Positive-length overlap of near-collinear source centrelines at 1 mm geometric diagnostic tolerance. R055: Positive-length overlap of near-collinear source centrelines at 1 mm geometric diagnostic tolerance. | Both connected structures (chlorine contact tank, chlorine contact tank) built with their wall penetrations; lay between them. One shared excavation and dewatering front with UG-28A: lay all pipes before backfill. UG-10, UG-21, UG-22, UG-28A is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-10-S02 backfilled (deeper); excavate after UG-10-S03 backfilled (deeper); excavate after UG-21-S01 backfilled (deeper); excavate after UG-22-S01 backfilled (deeper); shared trench with UG-28A-S01: backfill after both laid | 4 | 0
UG-28A | UG-28A-S01 | F8 | HDPE-UG28A-S01-CCT-CCT-(-0.55/-0.54)-18m | HDPE | 28 | Short connection | CCT, CCT | 0 |  | 0 | No | 7 | 0.315 | 17.8374 | -0.5475 | -0.5375 | -0.5475 | 0 | 0 | 0 | 17.8374 | Open cut | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | Not required | 99 | 99 | No extra measure | 2026-12-01 | 2027-03-21 | 123 | R051: Positive-length overlap of near-collinear source centrelines at 1 mm geometric diagnostic tolerance. R055: Positive-length overlap of near-collinear source centrelines at 1 mm geometric diagnostic tolerance. R057: 11 native short-fitting objects have all 24 mesh vertices coincident. Their embedded source centreline still has 0.584683786 m of represented 3D length. | Both connected structures (chlorine contact tank, chlorine contact tank) built with their wall penetrations; lay between them. One shared excavation and dewatering front with UG-28: lay all pipes before backfill. UG-10, UG-21, UG-22, UG-28 is deeper here: lay and backfill it first. Where shoring is flagged, it is on the side facing the nearest structure or pile (Pieces, Nearest item). | excavate after UG-10-S02 backfilled (deeper); excavate after UG-10-S03 backfilled (deeper); excavate after UG-21-S01 backfilled (deeper); excavate after UG-22-S01 backfilled (deeper); excavate after UG-28-S02 backfilled (deeper); shared trench with UG-28-S01: start excavation with it | -4 | 0
| Total | [12 empty] | 8151.3679 | [5 empty] | 6561.5933 | 1589.7746 |  | 104633.083 | 29959.9607 | 11770.1362 | 25377.3629 | 97445.5446 | 5788 | 13123.1866 |  | 116308.6076
| Check: plan length vs package workbook | [12 empty] | 8151.3679
| Difference (should be 0) | [12 empty] | 0

## Activities
Activities and logic (calendar dates; finish = start of next day)
11 activities per package. Start = latest of: predecessor in the package + start-to-start lag (ladder), crew release from the previous package of the same front (chain), deeper / shared-trench / closure links, and gates. Finish = later of start + duration and predecessor finish + FF lag. Durations recalculate from Inputs and Fronts.
Activity ID | WBS | Front | Line | Package | Code | Activity | Quantity | Unit | Duration (work days) | Duration (cal. days) | Ladder predecessor | SS lag (cal. days) | FF lag (cal. days) | Other predecessors (type) | Start | Finish | Crew released | Chain predecessor
UG-01-S02-A010 | AW.PIPE.F1.UG-01.UG-01-S02 | F1 | UG-01 | UG-01-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-01-S02-A020 | AW.PIPE.F1.UG-01.UG-01-S02 | F1 | UG-01 | UG-01-S02 | A020 | Set-out, crossing survey and working platform | 276.0606 | m | 4 | 5 | UG-01-S02-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-06
UG-01-S02-A030 | AW.PIPE.F1.UG-01.UG-01-S02 | F1 | UG-01 | UG-01-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 188 | piles | 38 | 45 | UG-01-S02-A020 | 2 | 2 | gate: D_PILEDES | 2026-12-03 | 2027-01-17 | 2027-01-17
UG-01-S02-A040 | AW.PIPE.F1.UG-01.UG-01-S02 | F1 | UG-01 | UG-01-S02 | A040 | Install sheet piles (shored lengths) | 552.1211 | m wall | 23 | 27 | UG-01-S02-A030 | 14 | 2 |  | 2026-12-17 | 2027-01-19 | 2027-01-19
UG-01-S02-A050 | AW.PIPE.F1.UG-01.UG-01-S02 | F1 | UG-01 | UG-01-S02 | A050 | Install dewatering and draw down | 276.0606 | m | 14 | 17 | UG-01-S02-A040 | 9 | 2 |  | 2026-12-26 | 2027-01-21
UG-01-S02-A060 | AW.PIPE.F1.UG-01.UG-01-S02 | F1 | UG-01 | UG-01-S02 | A060 | Excavate and strut to formation | 7037.0478 | m3 | 29 | 34 | UG-01-S02-A050 | 12 | 2 | gate: D_XING | 2027-01-07 | 2027-02-10 | 2027-02-10
UG-01-S02-A070 | AW.PIPE.F1.UG-01.UG-01-S02 | F1 | UG-01 | UG-01-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 276.0606 | m | 27 | 32 | UG-01-S02-A060 | 11 | 2 |  | 2027-01-18 | 2027-02-19 | 2027-02-19
UG-01-S02-A080 | AW.PIPE.F1.UG-01.UG-01-S02 | F1 | UG-01 | UG-01-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 276.0606 | m | 21 | 25 | UG-01-S02-A070 | 10 | 2 |  | 2027-01-28 | 2027-02-22 | 2027-02-22
UG-01-S02-A090 | AW.PIPE.F1.UG-01.UG-01-S02 | F1 | UG-01 | UG-01-S02 | A090 | Surround, joint test and line test | 276.0606 | m | 4 | 5 | UG-01-S02-A080 | 8 | 2 |  | 2027-02-05 | 2027-02-24
UG-01-S02-A100 | AW.PIPE.F1.UG-01.UG-01-S02 | F1 | UG-01 | UG-01-S02 | A100 | Backfill to NG and remove struts | 5134.7674 | m3 | 15 | 18 | UG-01-S02-A090 | 2 | 2 |  | 2027-02-07 | 2027-02-26 | 2027-02-26
UG-01-S02-A110 | AW.PIPE.F1.UG-01.UG-01-S02 | F1 | UG-01 | UG-01-S02 | A110 | Dewatering off, extract sheets, reinstate | 552.1211 | m wall | 13 | 16 | UG-01-S02-A100 | 6 | 2 |  | 2027-02-13 | 2027-03-01
UG-01-S03-A010 | AW.PIPE.F1.UG-01.UG-01-S03 | F1 | UG-01 | UG-01-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-01-S03-A020 | AW.PIPE.F1.UG-01.UG-01-S03 | F1 | UG-01 | UG-01-S03 | A020 | Set-out, crossing survey and working platform | 29.4102 | m | 1 | 2 | UG-01-S03-A010 |  |  | FS from A010; UG-01-S02-A030 (SS, tie-in team follows the adjacent run) | 2026-12-03 | 2026-12-05
UG-01-S03-A030 | AW.PIPE.F1.UG-01.UG-01-S03 | F1 | UG-01 | UG-01-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 11 | piles | 3 | 4 | UG-01-S03-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-04 | 2026-12-08 | 2026-12-08
UG-01-S03-A040 | AW.PIPE.F1.UG-01.UG-01-S03 | F1 | UG-01 | UG-01-S03 | A040 | Install sheet piles (shored lengths) | 58.8203 | m wall | 3 | 4 | UG-01-S03-A030 | 2 | 2 |  | 2026-12-06 | 2026-12-10 | 2026-12-10
UG-01-S03-A050 | AW.PIPE.F1.UG-01.UG-01-S03 | F1 | UG-01 | UG-01-S03 | A050 | Install dewatering and draw down | 29.4102 | m | 8 | 10 | UG-01-S03-A040 | 2 | 2 |  | 2026-12-08 | 2026-12-18
UG-01-S03-A060 | AW.PIPE.F1.UG-01.UG-01-S03 | F1 | UG-01 | UG-01-S03 | A060 | Excavate and strut to formation | 447.0044 | m3 | 2 | 3 | UG-01-S03-A050 | 10 | 2 |  | 2026-12-18 | 2026-12-21 | 2026-12-21
UG-01-S03-A070 | AW.PIPE.F1.UG-01.UG-01-S03 | F1 | UG-01 | UG-01-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 29.4102 | m | 6 | 7 | UG-01-S03-A060 | 1 | 2 |  | 2026-12-19 | 2026-12-26 | 2026-12-26
UG-01-S03-A080 | AW.PIPE.F1.UG-01.UG-01-S03 | F1 | UG-01 | UG-01-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 29.4102 | m | 4 | 5 | UG-01-S03-A070 | 3 | 2 | UG-01-S02-A080 (FS, closure) | 2027-02-22 | 2027-02-27 | 2027-02-27
UG-01-S03-A090 | AW.PIPE.F1.UG-01.UG-01-S03 | F1 | UG-01 | UG-01-S03 | A090 | Surround, joint test and line test | 29.4102 | m | 3 | 4 | UG-01-S03-A080 | 2 | 2 |  | 2027-02-24 | 2027-03-01
UG-01-S03-A100 | AW.PIPE.F1.UG-01.UG-01-S03 | F1 | UG-01 | UG-01-S03 | A100 | Backfill to NG and remove struts | 414.6026 | m3 | 2 | 3 | UG-01-S03-A090 | 2 | 2 |  | 2027-02-26 | 2027-03-03 | 2027-03-03
UG-01-S03-A110 | AW.PIPE.F1.UG-01.UG-01-S03 | F1 | UG-01 | UG-01-S03 | A110 | Dewatering off, extract sheets, reinstate | 58.8203 | m wall | 3 | 4 | UG-01-S03-A100 | 1 | 2 |  | 2027-02-27 | 2027-03-05
UG-01-S01-A010 | AW.PIPE.F1.UG-01.UG-01-S01 | F1 | UG-01 | UG-01-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-01-S01-A020 | AW.PIPE.F1.UG-01.UG-01-S01 | F1 | UG-01 | UG-01-S01 | A020 | Set-out, crossing survey and working platform | 18.8052 | m | 1 | 2 | UG-01-S01-A010 |  |  | FS from A010; UG-01-S02-A030 (SS, tie-in team follows the adjacent run) | 2026-12-03 | 2026-12-05
UG-01-S01-A030 | AW.PIPE.F1.UG-01.UG-01-S01 | F1 | UG-01 | UG-01-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 16 | piles | 4 | 5 | UG-01-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-04 | 2026-12-09 | 2026-12-09
UG-01-S01-A040 | AW.PIPE.F1.UG-01.UG-01-S01 | F1 | UG-01 | UG-01-S01 | A040 | Install sheet piles (shored lengths) | 37.6103 | m wall | 2 | 3 | UG-01-S01-A030 | 2 | 2 |  | 2026-12-06 | 2026-12-11 | 2026-12-11
UG-01-S01-A050 | AW.PIPE.F1.UG-01.UG-01-S01 | F1 | UG-01 | UG-01-S01 | A050 | Install dewatering and draw down | 18.8052 | m | 8 | 10 | UG-01-S01-A040 | 1 | 2 |  | 2026-12-07 | 2026-12-17
UG-01-S01-A060 | AW.PIPE.F1.UG-01.UG-01-S01 | F1 | UG-01 | UG-01-S01 | A060 | Excavate and strut to formation | 405.5321 | m3 | 2 | 3 | UG-01-S01-A050 | 10 | 2 |  | 2026-12-17 | 2026-12-20 | 2026-12-20
UG-01-S01-A070 | AW.PIPE.F1.UG-01.UG-01-S01 | F1 | UG-01 | UG-01-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 18.8052 | m | 5 | 6 | UG-01-S01-A060 | 1 | 2 |  | 2026-12-18 | 2026-12-24 | 2026-12-24
UG-01-S01-A080 | AW.PIPE.F1.UG-01.UG-01-S01 | F1 | UG-01 | UG-01-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 18.8052 | m | 5 | 6 | UG-01-S01-A070 | 2 | 2 | UG-01-S02-A080 (FS, closure) | 2027-02-22 | 2027-02-28 | 2027-02-28
UG-01-S01-A090 | AW.PIPE.F1.UG-01.UG-01-S01 | F1 | UG-01 | UG-01-S01 | A090 | Surround, joint test and line test | 18.8052 | m | 3 | 4 | UG-01-S01-A080 | 2 | 2 |  | 2027-02-24 | 2027-03-02
UG-01-S01-A100 | AW.PIPE.F1.UG-01.UG-01-S01 | F1 | UG-01 | UG-01-S01 | A100 | Backfill to NG and remove struts | 273.5494 | m3 | 1 | 2 | UG-01-S01-A090 | 2 | 2 |  | 2027-02-26 | 2027-03-04 | 2027-03-04
UG-01-S01-A110 | AW.PIPE.F1.UG-01.UG-01-S01 | F1 | UG-01 | UG-01-S01 | A110 | Dewatering off, extract sheets, reinstate | 37.6103 | m wall | 2 | 3 | UG-01-S01-A100 | 1 | 2 |  | 2027-02-27 | 2027-03-06
UG-02-S03-A010 | AW.PIPE.F1.UG-02.UG-02-S03 | F1 | UG-02 | UG-02-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, aeration zone piling | 2026-12-01 | 2026-12-01
UG-02-S03-A020 | AW.PIPE.F1.UG-02.UG-02-S03 | F1 | UG-02 | UG-02-S03 | A020 | Set-out, crossing survey and working platform | 65.1 | m | 1 | 2 | UG-02-S03-A010 |  |  | FS from A010; UG-01-S02-A030 (SS, set-out one package ahead of piling) | 2026-12-03 | 2026-12-05
UG-02-S03-A030 | AW.PIPE.F1.UG-02.UG-02-S03 | F1 | UG-02 | UG-02-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 46 | piles | 10 | 12 | UG-02-S03-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-17 | 2027-01-29 | 2027-01-29 | UG-01-S02-A030
UG-02-S03-A040 | AW.PIPE.F1.UG-02.UG-02-S03 | F1 | UG-02 | UG-02-S03 | A040 | Install sheet piles (shored lengths) | 130.2 | m wall | 6 | 7 | UG-02-S03-A030 | 4 | 2 |  | 2027-01-21 | 2027-01-31 | 2027-01-31 | UG-01-S02-A040
UG-02-S03-A050 | AW.PIPE.F1.UG-02.UG-02-S03 | F1 | UG-02 | UG-02-S03 | A050 | Install dewatering and draw down | 65.1 | m | 9 | 11 | UG-02-S03-A040 | 3 | 2 | UG-01-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-30 | 2027-02-10
UG-02-S03-A060 | AW.PIPE.F1.UG-02.UG-02-S03 | F1 | UG-02 | UG-02-S03 | A060 | Excavate and strut to formation | 1400.9398 | m3 | 6 | 7 | UG-02-S03-A050 | 10 | 2 |  | 2027-02-10 | 2027-02-17 | 2027-02-17 | UG-01-S02-A060
UG-02-S03-A070 | AW.PIPE.F1.UG-02.UG-02-S03 | F1 | UG-02 | UG-02-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 65.1 | m | 9 | 11 | UG-02-S03-A060 | 3 | 2 |  | 2027-02-19 | 2027-03-02 | 2027-03-02 | UG-01-S02-A070
UG-02-S03-A080 | AW.PIPE.F1.UG-02.UG-02-S03 | F1 | UG-02 | UG-02-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 65.1 | m | 4 | 5 | UG-02-S03-A070 | 4 | 2 |  | 2027-02-23 | 2027-03-04 | 2027-03-04 | UG-01-S02-A080
UG-02-S03-A090 | AW.PIPE.F1.UG-02.UG-02-S03 | F1 | UG-02 | UG-02-S03 | A090 | Surround, joint test and line test | 65.1 | m | 3 | 4 | UG-02-S03-A080 | 2 | 2 |  | 2027-02-25 | 2027-03-06
UG-02-S03-A100 | AW.PIPE.F1.UG-02.UG-02-S03 | F1 | UG-02 | UG-02-S03 | A100 | Backfill to NG and remove struts | 1082.0222 | m3 | 4 | 5 | UG-02-S03-A090 | 2 | 2 | UG-03-S01-A080 (FS, shared trench laid); UG-03-S02-A080 (FS, shared trench laid) | 2027-05-07 | 2027-05-12 | 2027-05-12 | UG-01-S02-A100
UG-02-S03-A110 | AW.PIPE.F1.UG-02.UG-02-S03 | F1 | UG-02 | UG-02-S03 | A110 | Dewatering off, extract sheets, reinstate | 130.2 | m wall | 4 | 5 | UG-02-S03-A100 | 2 | 2 |  | 2027-05-09 | 2027-05-14
UG-02-S02-A010 | AW.PIPE.F1.UG-02.UG-02-S02 | F1 | UG-02 | UG-02-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, aeration zone piling | 2026-12-01 | 2026-12-01
UG-02-S02-A020 | AW.PIPE.F1.UG-02.UG-02-S02 | F1 | UG-02 | UG-02-S02 | A020 | Set-out, crossing survey and working platform | 78.0475 | m | 1 | 2 | UG-02-S02-A010 |  |  | FS from A010; UG-02-S03-A030 (SS, set-out one package ahead of piling) | 2027-01-17 | 2027-01-19
UG-02-S02-A030 | AW.PIPE.F1.UG-02.UG-02-S02 | F1 | UG-02 | UG-02-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 56 | piles | 12 | 14 | UG-02-S02-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-29 | 2027-02-12 | 2027-02-12 | UG-02-S03-A030
UG-02-S02-A040 | AW.PIPE.F1.UG-02.UG-02-S02 | F1 | UG-02 | UG-02-S02 | A040 | Install sheet piles (shored lengths) | 156.095 | m wall | 7 | 9 | UG-02-S02-A030 | 5 | 2 |  | 2027-02-03 | 2027-02-14 | 2027-02-14 | UG-02-S03-A040
UG-02-S02-A050 | AW.PIPE.F1.UG-02.UG-02-S02 | F1 | UG-02 | UG-02-S02 | A050 | Install dewatering and draw down | 78.0475 | m | 9 | 11 | UG-02-S02-A040 | 3 | 2 | UG-02-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-02-06 | 2027-02-17
UG-02-S02-A060 | AW.PIPE.F1.UG-02.UG-02-S02 | F1 | UG-02 | UG-02-S02 | A060 | Excavate and strut to formation | 1553.9705 | m3 | 7 | 9 | UG-02-S02-A050 | 10 | 2 |  | 2027-02-17 | 2027-02-26 | 2027-02-26 | UG-02-S03-A060
UG-02-S02-A070 | AW.PIPE.F1.UG-02.UG-02-S02 | F1 | UG-02 | UG-02-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 78.0475 | m | 10 | 12 | UG-02-S02-A060 | 3 | 2 |  | 2027-03-02 | 2027-03-14 | 2027-03-14 | UG-02-S03-A070
UG-02-S02-A080 | AW.PIPE.F1.UG-02.UG-02-S02 | F1 | UG-02 | UG-02-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 78.0475 | m | 4 | 5 | UG-02-S02-A070 | 4 | 2 |  | 2027-03-06 | 2027-03-16 | 2027-03-16 | UG-02-S03-A080
UG-02-S02-A090 | AW.PIPE.F1.UG-02.UG-02-S02 | F1 | UG-02 | UG-02-S02 | A090 | Surround, joint test and line test | 78.0475 | m | 3 | 4 | UG-02-S02-A080 | 2 | 2 |  | 2027-03-08 | 2027-03-18
UG-02-S02-A100 | AW.PIPE.F1.UG-02.UG-02-S02 | F1 | UG-02 | UG-02-S02 | A100 | Backfill to NG and remove struts | 1171.6246 | m3 | 4 | 5 | UG-02-S02-A090 | 2 | 2 | UG-03-S01-A080 (FS, shared trench laid) | 2027-05-12 | 2027-05-17 | 2027-05-17 | UG-02-S03-A100
UG-02-S02-A110 | AW.PIPE.F1.UG-02.UG-02-S02 | F1 | UG-02 | UG-02-S02 | A110 | Dewatering off, extract sheets, reinstate | 156.095 | m wall | 5 | 6 | UG-02-S02-A100 | 2 | 2 |  | 2027-05-14 | 2027-05-20
UG-02-S05-A010 | AW.PIPE.F1.UG-02.UG-02-S05 | F1 | UG-02 | UG-02-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready, aeration zone piling | 2026-12-01 | 2026-12-01
UG-02-S05-A020 | AW.PIPE.F1.UG-02.UG-02-S05 | F1 | UG-02 | UG-02-S05 | A020 | Set-out, crossing survey and working platform | 5.9679 | m | 1 | 2 | UG-02-S05-A010 |  |  | FS from A010; UG-02-S04-A030 (SS, tie-in team follows the adjacent run) | 2027-02-12 | 2027-02-14
UG-02-S05-A030 | AW.PIPE.F1.UG-02.UG-02-S05 | F1 | UG-02 | UG-02-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 6 | piles | 2 | 3 | UG-02-S05-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-13 | 2027-02-16 | 2027-02-16
UG-02-S05-A040 | AW.PIPE.F1.UG-02.UG-02-S05 | F1 | UG-02 | UG-02-S05 | A040 | Install sheet piles (shored lengths) | 11.9357 | m wall | 1 | 2 | UG-02-S05-A030 | 1 | 2 |  | 2027-02-14 | 2027-02-18 | 2027-02-18
UG-02-S05-A050 | AW.PIPE.F1.UG-02.UG-02-S05 | F1 | UG-02 | UG-02-S05 | A050 | Install dewatering and draw down | 5.9679 | m | 8 | 10 | UG-02-S05-A040 | 1 | 2 |  | 2027-02-15 | 2027-02-25
UG-02-S05-A060 | AW.PIPE.F1.UG-02.UG-02-S05 | F1 | UG-02 | UG-02-S05 | A060 | Excavate and strut to formation | 146.4466 | m3 | 1 | 2 | UG-02-S05-A050 | 10 | 2 | UG-03-S04-A060 (SS, shared trench); UG-03-S05-A060 (SS, shared trench) | 2027-04-22 | 2027-04-24 | 2027-04-24
UG-02-S05-A070 | AW.PIPE.F1.UG-02.UG-02-S05 | F1 | UG-02 | UG-02-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 5.9679 | m | 4 | 5 | UG-02-S05-A060 | 1 | 2 |  | 2027-04-23 | 2027-04-28 | 2027-04-28
UG-02-S05-A080 | AW.PIPE.F1.UG-02.UG-02-S05 | F1 | UG-02 | UG-02-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 5.9679 | m | 4 | 5 | UG-02-S05-A070 | 2 | 2 | UG-02-S04-A080 (FS, closure) | 2027-04-25 | 2027-04-30 | 2027-04-30
UG-02-S05-A090 | AW.PIPE.F1.UG-02.UG-02-S05 | F1 | UG-02 | UG-02-S05 | A090 | Surround, joint test and line test | 5.9679 | m | 3 | 4 | UG-02-S05-A080 | 2 | 2 |  | 2027-04-27 | 2027-05-02
UG-02-S05-A100 | AW.PIPE.F1.UG-02.UG-02-S05 | F1 | UG-02 | UG-02-S05 | A100 | Backfill to NG and remove struts | 117.211 | m3 | 1 | 2 | UG-02-S05-A090 | 2 | 2 | UG-03-S04-A080 (FS, shared trench laid); UG-03-S05-A080 (FS, shared trench laid) | 2027-05-17 | 2027-05-19 | 2027-05-19
UG-02-S05-A110 | AW.PIPE.F1.UG-02.UG-02-S05 | F1 | UG-02 | UG-02-S05 | A110 | Dewatering off, extract sheets, reinstate | 11.9357 | m wall | 2 | 3 | UG-02-S05-A100 | 1 | 2 |  | 2027-05-18 | 2027-05-21
UG-02-S04-A010 | AW.PIPE.F1.UG-02.UG-02-S04 | F1 | UG-02 | UG-02-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, aeration zone piling | 2026-12-01 | 2026-12-01
UG-02-S04-A020 | AW.PIPE.F1.UG-02.UG-02-S04 | F1 | UG-02 | UG-02-S04 | A020 | Set-out, crossing survey and working platform | 105.1941 | m | 2 | 3 | UG-02-S04-A010 |  |  | FS from A010; UG-02-S02-A030 (SS, set-out one package ahead of piling) | 2027-01-29 | 2027-02-01
UG-02-S04-A030 | AW.PIPE.F1.UG-02.UG-02-S04 | F1 | UG-02 | UG-02-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 74 | piles | 15 | 18 | UG-02-S04-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-12 | 2027-03-02 | 2027-03-02 | UG-02-S02-A030
UG-02-S04-A040 | AW.PIPE.F1.UG-02.UG-02-S04 | F1 | UG-02 | UG-02-S04 | A040 | Install sheet piles (shored lengths) | 210.3881 | m wall | 9 | 11 | UG-02-S04-A030 | 6 | 2 |  | 2027-02-18 | 2027-03-04 | 2027-03-04 | UG-02-S02-A040
UG-02-S04-A050 | AW.PIPE.F1.UG-02.UG-02-S04 | F1 | UG-02 | UG-02-S04 | A050 | Install dewatering and draw down | 105.1941 | m | 10 | 12 | UG-02-S04-A040 | 4 | 2 | UG-02-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-02-22 | 2027-03-06
UG-02-S04-A060 | AW.PIPE.F1.UG-02.UG-02-S04 | F1 | UG-02 | UG-02-S04 | A060 | Excavate and strut to formation | 2464.8407 | m3 | 10 | 12 | UG-02-S04-A050 | 10 | 2 | gate: D_XING; UG-03-S05-A060 (SS, shared trench) | 2027-03-31 | 2027-04-12 | 2027-04-12 | UG-02-S02-A060
UG-02-S04-A070 | AW.PIPE.F1.UG-02.UG-02-S04 | F1 | UG-02 | UG-02-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 105.1941 | m | 12 | 14 | UG-02-S04-A060 | 4 | 2 |  | 2027-04-04 | 2027-04-18 | 2027-04-18 | UG-02-S02-A070
UG-02-S04-A080 | AW.PIPE.F1.UG-02.UG-02-S04 | F1 | UG-02 | UG-02-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 105.1941 | m | 7 | 9 | UG-02-S04-A070 | 5 | 2 |  | 2027-04-09 | 2027-04-20 | 2027-04-20 | UG-02-S02-A080
UG-02-S04-A090 | AW.PIPE.F1.UG-02.UG-02-S04 | F1 | UG-02 | UG-02-S04 | A090 | Surround, joint test and line test | 105.1941 | m | 3 | 4 | UG-02-S04-A080 | 3 | 2 |  | 2027-04-12 | 2027-04-22
UG-02-S04-A100 | AW.PIPE.F1.UG-02.UG-02-S04 | F1 | UG-02 | UG-02-S04 | A100 | Backfill to NG and remove struts | 1949.5068 | m3 | 6 | 7 | UG-02-S04-A090 | 2 | 2 | UG-03-S01-A080 (FS, shared trench laid); UG-03-S02-A080 (FS, shared trench laid); UG-03-S03-A080 (FS, shared trench laid); UG-03-S04-A080 (FS, shared trench laid); UG-03-S05-A080 (FS, shared trench laid) | 2027-05-30 | 2027-06-06 | 2027-06-06 | UG-02-S02-A100
UG-02-S04-A110 | AW.PIPE.F1.UG-02.UG-02-S04 | F1 | UG-02 | UG-02-S04 | A110 | Dewatering off, extract sheets, reinstate | 210.3881 | m wall | 6 | 7 | UG-02-S04-A100 | 3 | 2 |  | 2027-06-02 | 2027-06-09
UG-03-S01-A010 | AW.PIPE.F1.UG-03.UG-03-S01 | F1 | UG-03 | UG-03-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-03-S01-A020 | AW.PIPE.F1.UG-03.UG-03-S01 | F1 | UG-03 | UG-03-S01 | A020 | Set-out, crossing survey and working platform | 66 | m | 1 | 2 | UG-03-S01-A010 |  |  | FS from A010; UG-02-S04-A030 (SS, set-out one package ahead of piling) | 2027-02-12 | 2027-02-14
UG-03-S01-A030 | AW.PIPE.F1.UG-03.UG-03-S01 | F1 | UG-03 | UG-03-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 46 | piles | 10 | 12 | UG-03-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-02 | 2027-03-14 | 2027-03-14 | UG-02-S04-A030
UG-03-S01-A040 | AW.PIPE.F1.UG-03.UG-03-S01 | F1 | UG-03 | UG-03-S01 | A040 | Install sheet piles (shored lengths) | 132 | m wall | 6 | 7 | UG-03-S01-A030 | 4 | 2 |  | 2027-03-06 | 2027-03-16 | 2027-03-16 | UG-02-S04-A040
UG-03-S01-A050 | AW.PIPE.F1.UG-03.UG-03-S01 | F1 | UG-03 | UG-03-S01 | A050 | Install dewatering and draw down | 66 | m | 9 | 11 | UG-03-S01-A040 | 3 | 2 | UG-02-S04-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-01 | 2027-04-12
UG-03-S01-A060 | AW.PIPE.F1.UG-03.UG-03-S01 | F1 | UG-03 | UG-03-S01 | A060 | Excavate and strut to formation | 1291.1983 | m3 | 6 | 7 | UG-03-S01-A050 | 10 | 2 | UG-02-S02-A060 (SS, shared trench); UG-02-S03-A060 (SS, shared trench); UG-02-S04-A060 (SS, shared trench) | 2027-04-12 | 2027-04-19 | 2027-04-19 | UG-02-S04-A060
UG-03-S01-A070 | AW.PIPE.F1.UG-03.UG-03-S01 | F1 | UG-03 | UG-03-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 66 | m | 9 | 11 | UG-03-S01-A060 | 3 | 2 |  | 2027-04-18 | 2027-04-29 | 2027-04-29 | UG-02-S04-A070
UG-03-S01-A080 | AW.PIPE.F1.UG-03.UG-03-S01 | F1 | UG-03 | UG-03-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 66 | m | 5 | 6 | UG-03-S01-A070 | 4 | 2 |  | 2027-04-22 | 2027-05-01 | 2027-05-01 | UG-02-S04-A080
UG-03-S01-A090 | AW.PIPE.F1.UG-03.UG-03-S01 | F1 | UG-03 | UG-03-S01 | A090 | Surround, joint test and line test | 66 | m | 3 | 4 | UG-03-S01-A080 | 2 | 2 |  | 2027-04-24 | 2027-05-03
UG-03-S01-A100 | AW.PIPE.F1.UG-03.UG-03-S01 | F1 | UG-03 | UG-03-S01 | A100 | Backfill to NG and remove struts | 980.8631 | m3 | 3 | 4 | UG-03-S01-A090 | 2 | 2 | UG-02-S02-A080 (FS, shared trench laid); UG-02-S03-A080 (FS, shared trench laid); UG-02-S04-A080 (FS, shared trench laid) | 2027-06-06 | 2027-06-10 | 2027-06-10 | UG-02-S04-A100
UG-03-S01-A110 | AW.PIPE.F1.UG-03.UG-03-S01 | F1 | UG-03 | UG-03-S01 | A110 | Dewatering off, extract sheets, reinstate | 132 | m wall | 4 | 5 | UG-03-S01-A100 | 2 | 2 |  | 2027-06-08 | 2027-06-13
UG-03-S02-A010 | AW.PIPE.F1.UG-03.UG-03-S02 | F1 | UG-03 | UG-03-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-03-S02-A020 | AW.PIPE.F1.UG-03.UG-03-S02 | F1 | UG-03 | UG-03-S02 | A020 | Set-out, crossing survey and working platform | 16 | m | 1 | 2 | UG-03-S02-A010 |  |  | FS from A010; UG-03-S01-A030 (SS, set-out one package ahead of piling) | 2027-03-02 | 2027-03-04
UG-03-S02-A030 | AW.PIPE.F1.UG-03.UG-03-S02 | F1 | UG-03 | UG-03-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 14 | piles | 3 | 4 | UG-03-S02-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-14 | 2027-03-18 | 2027-03-18 | UG-03-S01-A030
UG-03-S02-A040 | AW.PIPE.F1.UG-03.UG-03-S02 | F1 | UG-03 | UG-03-S02 | A040 | Install sheet piles (shored lengths) | 32 | m wall | 2 | 3 | UG-03-S02-A030 | 2 | 2 |  | 2027-03-16 | 2027-03-20 | 2027-03-20 | UG-03-S01-A040
UG-03-S02-A050 | AW.PIPE.F1.UG-03.UG-03-S02 | F1 | UG-03 | UG-03-S02 | A050 | Install dewatering and draw down | 16 | m | 8 | 10 | UG-03-S02-A040 | 1 | 2 | UG-03-S01-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-09 | 2027-04-19
UG-03-S02-A060 | AW.PIPE.F1.UG-03.UG-03-S02 | F1 | UG-03 | UG-03-S02 | A060 | Excavate and strut to formation | 337.7545 | m3 | 2 | 3 | UG-03-S02-A050 | 10 | 2 | UG-02-S03-A060 (SS, shared trench); UG-02-S04-A060 (SS, shared trench) | 2027-04-19 | 2027-04-22 | 2027-04-22 | UG-03-S01-A060
UG-03-S02-A070 | AW.PIPE.F1.UG-03.UG-03-S02 | F1 | UG-03 | UG-03-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 16 | m | 5 | 6 | UG-03-S02-A060 | 1 | 2 |  | 2027-04-29 | 2027-05-05 | 2027-05-05 | UG-03-S01-A070
UG-03-S02-A080 | AW.PIPE.F1.UG-03.UG-03-S02 | F1 | UG-03 | UG-03-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 16 | m | 1 | 2 | UG-03-S02-A070 | 2 | 2 |  | 2027-05-01 | 2027-05-07 | 2027-05-07 | UG-03-S01-A080
UG-03-S02-A090 | AW.PIPE.F1.UG-03.UG-03-S02 | F1 | UG-03 | UG-03-S02 | A090 | Surround, joint test and line test | 16 | m | 3 | 4 | UG-03-S02-A080 | 1 | 2 |  | 2027-05-02 | 2027-05-09
UG-03-S02-A100 | AW.PIPE.F1.UG-03.UG-03-S02 | F1 | UG-03 | UG-03-S02 | A100 | Backfill to NG and remove struts | 261.0671 | m3 | 1 | 2 | UG-03-S02-A090 | 2 | 2 | UG-02-S03-A080 (FS, shared trench laid); UG-02-S04-A080 (FS, shared trench laid) | 2027-06-10 | 2027-06-12 | 2027-06-12 | UG-03-S01-A100
UG-03-S02-A110 | AW.PIPE.F1.UG-03.UG-03-S02 | F1 | UG-03 | UG-03-S02 | A110 | Dewatering off, extract sheets, reinstate | 32 | m wall | 2 | 3 | UG-03-S02-A100 | 1 | 2 |  | 2027-06-11 | 2027-06-14
UG-03-S04-A010 | AW.PIPE.F1.UG-03.UG-03-S04 | F1 | UG-03 | UG-03-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-03-S04-A020 | AW.PIPE.F1.UG-03.UG-03-S04 | F1 | UG-03 | UG-03-S04 | A020 | Set-out, crossing survey and working platform | 6.9804 | m | 1 | 2 | UG-03-S04-A010 |  |  | FS from A010; UG-03-S02-A030 (SS, set-out one package ahead of piling) | 2027-03-14 | 2027-03-16
UG-03-S04-A030 | AW.PIPE.F1.UG-03.UG-03-S04 | F1 | UG-03 | UG-03-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 8 | piles | 2 | 3 | UG-03-S04-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-18 | 2027-03-21 | 2027-03-21 | UG-03-S02-A030
UG-03-S04-A040 | AW.PIPE.F1.UG-03.UG-03-S04 | F1 | UG-03 | UG-03-S04 | A040 | Install sheet piles (shored lengths) | 13.9608 | m wall | 1 | 2 | UG-03-S04-A030 | 1 | 2 |  | 2027-03-20 | 2027-03-23 | 2027-03-23 | UG-03-S02-A040
UG-03-S04-A050 | AW.PIPE.F1.UG-03.UG-03-S04 | F1 | UG-03 | UG-03-S04 | A050 | Install dewatering and draw down | 6.9804 | m | 8 | 10 | UG-03-S04-A040 | 1 | 2 | UG-03-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-12 | 2027-04-22
UG-03-S04-A060 | AW.PIPE.F1.UG-03.UG-03-S04 | F1 | UG-03 | UG-03-S04 | A060 | Excavate and strut to formation | 170.2884 | m3 | 1 | 2 | UG-03-S04-A050 | 10 | 2 | UG-02-S04-A060 (SS, shared trench) | 2027-04-22 | 2027-04-24 | 2027-04-24 | UG-03-S02-A060
UG-03-S04-A070 | AW.PIPE.F1.UG-03.UG-03-S04 | F1 | UG-03 | UG-03-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6.9804 | m | 4 | 5 | UG-03-S04-A060 | 1 | 2 |  | 2027-05-05 | 2027-05-10 | 2027-05-10 | UG-03-S02-A070
UG-03-S04-A080 | AW.PIPE.F1.UG-03.UG-03-S04 | F1 | UG-03 | UG-03-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6.9804 | m | 2 | 3 | UG-03-S04-A070 | 2 | 2 |  | 2027-05-07 | 2027-05-12 | 2027-05-12 | UG-03-S02-A080
UG-03-S04-A090 | AW.PIPE.F1.UG-03.UG-03-S04 | F1 | UG-03 | UG-03-S04 | A090 | Surround, joint test and line test | 6.9804 | m | 3 | 4 | UG-03-S04-A080 | 1 | 2 |  | 2027-05-08 | 2027-05-14
UG-03-S04-A100 | AW.PIPE.F1.UG-03.UG-03-S04 | F1 | UG-03 | UG-03-S04 | A100 | Backfill to NG and remove struts | 136.5071 | m3 | 1 | 2 | UG-03-S04-A090 | 2 | 2 | UG-02-S04-A080 (FS, shared trench laid); UG-02-S05-A080 (FS, shared trench laid); UG-04-S01-A080 (FS, shared trench laid); UG-04-S02-A080 (FS, shared trench laid) | 2027-06-12 | 2027-06-14 | 2027-06-14 | UG-03-S02-A100
UG-03-S04-A110 | AW.PIPE.F1.UG-03.UG-03-S04 | F1 | UG-03 | UG-03-S04 | A110 | Dewatering off, extract sheets, reinstate | 13.9608 | m wall | 2 | 3 | UG-03-S04-A100 | 1 | 2 |  | 2027-06-13 | 2027-06-16
UG-03-S05-A010 | AW.PIPE.F1.UG-03.UG-03-S05 | F1 | UG-03 | UG-03-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-03-S05-A020 | AW.PIPE.F1.UG-03.UG-03-S05 | F1 | UG-03 | UG-03-S05 | A020 | Set-out, crossing survey and working platform | 10.9788 | m | 1 | 2 | UG-03-S05-A010 |  |  | FS from A010; UG-03-S04-A030 (SS, tie-in team follows the adjacent run) | 2027-03-18 | 2027-03-20
UG-03-S05-A030 | AW.PIPE.F1.UG-03.UG-03-S05 | F1 | UG-03 | UG-03-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 10 | piles | 2 | 3 | UG-03-S05-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-19 | 2027-03-22 | 2027-03-22
UG-03-S05-A040 | AW.PIPE.F1.UG-03.UG-03-S05 | F1 | UG-03 | UG-03-S05 | A040 | Install sheet piles (shored lengths) | 21.9576 | m wall | 1 | 2 | UG-03-S05-A030 | 1 | 2 |  | 2027-03-20 | 2027-03-24 | 2027-03-24
UG-03-S05-A050 | AW.PIPE.F1.UG-03.UG-03-S05 | F1 | UG-03 | UG-03-S05 | A050 | Install dewatering and draw down | 10.9788 | m | 8 | 10 | UG-03-S05-A040 | 1 | 2 |  | 2027-03-21 | 2027-03-31
UG-03-S05-A060 | AW.PIPE.F1.UG-03.UG-03-S05 | F1 | UG-03 | UG-03-S05 | A060 | Excavate and strut to formation | 269.4872 | m3 | 2 | 3 | UG-03-S05-A050 | 10 | 2 |  | 2027-03-31 | 2027-04-03 | 2027-04-03
UG-03-S05-A070 | AW.PIPE.F1.UG-03.UG-03-S05 | F1 | UG-03 | UG-03-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 10.9788 | m | 4 | 5 | UG-03-S05-A060 | 1 | 2 |  | 2027-04-01 | 2027-04-06 | 2027-04-06
UG-03-S05-A080 | AW.PIPE.F1.UG-03.UG-03-S05 | F1 | UG-03 | UG-03-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 10.9788 | m | 4 | 5 | UG-03-S05-A070 | 2 | 2 | UG-03-S04-A080 (FS, closure) | 2027-05-12 | 2027-05-17 | 2027-05-17
UG-03-S05-A090 | AW.PIPE.F1.UG-03.UG-03-S05 | F1 | UG-03 | UG-03-S05 | A090 | Surround, joint test and line test | 10.9788 | m | 3 | 4 | UG-03-S05-A080 | 2 | 2 |  | 2027-05-14 | 2027-05-19
UG-03-S05-A100 | AW.PIPE.F1.UG-03.UG-03-S05 | F1 | UG-03 | UG-03-S05 | A100 | Backfill to NG and remove struts | 215.7038 | m3 | 1 | 2 | UG-03-S05-A090 | 2 | 2 | UG-02-S04-A080 (FS, shared trench laid); UG-02-S05-A080 (FS, shared trench laid); UG-04-S01-A080 (FS, shared trench laid); UG-04-S02-A080 (FS, shared trench laid) | 2027-05-22 | 2027-05-24 | 2027-05-24
UG-03-S05-A110 | AW.PIPE.F1.UG-03.UG-03-S05 | F1 | UG-03 | UG-03-S05 | A110 | Dewatering off, extract sheets, reinstate | 21.9576 | m wall | 2 | 3 | UG-03-S05-A100 | 1 | 2 |  | 2027-05-23 | 2027-05-26
UG-04-S01-A010 | AW.PIPE.F1.UG-04.UG-04-S01 | F1 | UG-04 | UG-04-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-04-S01-A020 | AW.PIPE.F1.UG-04.UG-04-S01 | F1 | UG-04 | UG-04-S01 | A020 | Set-out, crossing survey and working platform | 10.3097 | m | 1 | 2 | UG-04-S01-A010 |  |  | FS from A010; UG-03-S04-A030 (SS, set-out one package ahead of piling) | 2027-03-18 | 2027-03-20
UG-04-S01-A030 | AW.PIPE.F1.UG-04.UG-04-S01 | F1 | UG-04 | UG-04-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 10 | piles | 2 | 3 | UG-04-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-21 | 2027-03-24 | 2027-03-24 | UG-03-S04-A030
UG-04-S01-A040 | AW.PIPE.F1.UG-04.UG-04-S01 | F1 | UG-04 | UG-04-S01 | A040 | Install sheet piles (shored lengths) | 20.6194 | m wall | 1 | 2 | UG-04-S01-A030 | 1 | 2 |  | 2027-03-23 | 2027-03-26 | 2027-03-26 | UG-03-S04-A040
UG-04-S01-A050 | AW.PIPE.F1.UG-04.UG-04-S01 | F1 | UG-04 | UG-04-S01 | A050 | Install dewatering and draw down | 10.3097 | m | 8 | 10 | UG-04-S01-A040 | 1 | 2 | UG-03-S04-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-14 | 2027-04-24
UG-04-S01-A060 | AW.PIPE.F1.UG-04.UG-04-S01 | F1 | UG-04 | UG-04-S01 | A060 | Excavate and strut to formation | 191.5741 | m3 | 1 | 2 | UG-04-S01-A050 | 10 | 2 | UG-03-S04-A060 (SS, shared trench); UG-03-S05-A060 (SS, shared trench) | 2027-04-24 | 2027-04-26 | 2027-04-26 | UG-03-S04-A060
UG-04-S01-A070 | AW.PIPE.F1.UG-04.UG-04-S01 | F1 | UG-04 | UG-04-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 10.3097 | m | 4 | 5 | UG-04-S01-A060 | 1 | 2 |  | 2027-05-10 | 2027-05-15 | 2027-05-15 | UG-03-S04-A070
UG-04-S01-A080 | AW.PIPE.F1.UG-04.UG-04-S01 | F1 | UG-04 | UG-04-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 10.3097 | m | 4 | 5 | UG-04-S01-A070 | 2 | 2 |  | 2027-05-12 | 2027-05-17 | 2027-05-17 | UG-03-S04-A080
UG-04-S01-A090 | AW.PIPE.F1.UG-04.UG-04-S01 | F1 | UG-04 | UG-04-S01 | A090 | Surround, joint test and line test | 10.3097 | m | 3 | 4 | UG-04-S01-A080 | 2 | 2 |  | 2027-05-14 | 2027-05-19
UG-04-S01-A100 | AW.PIPE.F1.UG-04.UG-04-S01 | F1 | UG-04 | UG-04-S01 | A100 | Backfill to NG and remove struts | 146.8515 | m3 | 1 | 2 | UG-04-S01-A090 | 2 | 2 | UG-03-S04-A080 (FS, shared trench laid); UG-03-S05-A080 (FS, shared trench laid) | 2027-06-14 | 2027-06-16 | 2027-06-16 | UG-03-S04-A100
UG-04-S01-A110 | AW.PIPE.F1.UG-04.UG-04-S01 | F1 | UG-04 | UG-04-S01 | A110 | Dewatering off, extract sheets, reinstate | 20.6194 | m wall | 2 | 3 | UG-04-S01-A100 | 1 | 2 |  | 2027-06-15 | 2027-06-18
UG-04-S02-A010 | AW.PIPE.F1.UG-04.UG-04-S02 | F1 | UG-04 | UG-04-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-04-S02-A020 | AW.PIPE.F1.UG-04.UG-04-S02 | F1 | UG-04 | UG-04-S02 | A020 | Set-out, crossing survey and working platform | 12.3452 | m | 1 | 2 | UG-04-S02-A010 |  |  | FS from A010; UG-04-S01-A030 (SS, tie-in team follows the adjacent run) | 2027-03-21 | 2027-03-23
UG-04-S02-A030 | AW.PIPE.F1.UG-04.UG-04-S02 | F1 | UG-04 | UG-04-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 12 | piles | 3 | 4 | UG-04-S02-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-22 | 2027-03-26 | 2027-03-26
UG-04-S02-A040 | AW.PIPE.F1.UG-04.UG-04-S02 | F1 | UG-04 | UG-04-S02 | A040 | Install sheet piles (shored lengths) | 24.6904 | m wall | 1 | 2 | UG-04-S02-A030 | 2 | 2 |  | 2027-03-24 | 2027-03-28 | 2027-03-28
UG-04-S02-A050 | AW.PIPE.F1.UG-04.UG-04-S02 | F1 | UG-04 | UG-04-S02 | A050 | Install dewatering and draw down | 12.3452 | m | 8 | 10 | UG-04-S02-A040 | 1 | 2 |  | 2027-03-25 | 2027-04-04
UG-04-S02-A060 | AW.PIPE.F1.UG-04.UG-04-S02 | F1 | UG-04 | UG-04-S02 | A060 | Excavate and strut to formation | 281.2679 | m3 | 2 | 3 | UG-04-S02-A050 | 10 | 2 | UG-03-S04-A060 (SS, shared trench); UG-03-S05-A060 (SS, shared trench) | 2027-04-22 | 2027-04-25 | 2027-04-25
UG-04-S02-A070 | AW.PIPE.F1.UG-04.UG-04-S02 | F1 | UG-04 | UG-04-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 12.3452 | m | 5 | 6 | UG-04-S02-A060 | 1 | 2 |  | 2027-04-23 | 2027-04-29 | 2027-04-29
UG-04-S02-A080 | AW.PIPE.F1.UG-04.UG-04-S02 | F1 | UG-04 | UG-04-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 12.3452 | m | 4 | 5 | UG-04-S02-A070 | 2 | 2 | UG-04-S01-A080 (FS, closure) | 2027-05-17 | 2027-05-22 | 2027-05-22
UG-04-S02-A090 | AW.PIPE.F1.UG-04.UG-04-S02 | F1 | UG-04 | UG-04-S02 | A090 | Surround, joint test and line test | 12.3452 | m | 3 | 4 | UG-04-S02-A080 | 2 | 2 |  | 2027-05-19 | 2027-05-24
UG-04-S02-A100 | AW.PIPE.F1.UG-04.UG-04-S02 | F1 | UG-04 | UG-04-S02 | A100 | Backfill to NG and remove struts | 220.7907 | m3 | 1 | 2 | UG-04-S02-A090 | 2 | 2 | UG-03-S04-A080 (FS, shared trench laid); UG-03-S05-A080 (FS, shared trench laid) | 2027-05-21 | 2027-05-26 | 2027-05-26
UG-04-S02-A110 | AW.PIPE.F1.UG-04.UG-04-S02 | F1 | UG-04 | UG-04-S02 | A110 | Dewatering off, extract sheets, reinstate | 24.6904 | m wall | 2 | 3 | UG-04-S02-A100 | 1 | 2 |  | 2027-05-22 | 2027-05-28
UG-03-S03-A010 | AW.PIPE.F1.UG-03.UG-03-S03 | F1 | UG-03 | UG-03-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-03-S03-A020 | AW.PIPE.F1.UG-03.UG-03-S03 | F1 | UG-03 | UG-03-S03 | A020 | Set-out, crossing survey and working platform | 86.1 | m | 2 | 3 | UG-03-S03-A010 |  |  | FS from A010; UG-04-S01-A030 (SS, set-out one package ahead of piling) | 2027-03-21 | 2027-03-24
UG-03-S03-A030 | AW.PIPE.F1.UG-03.UG-03-S03 | F1 | UG-03 | UG-03-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 60 | piles | 12 | 14 | UG-03-S03-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-24 | 2027-04-07 | 2027-04-07 | UG-04-S01-A030
UG-03-S03-A040 | AW.PIPE.F1.UG-03.UG-03-S03 | F1 | UG-03 | UG-03-S03 | A040 | Install sheet piles (shored lengths) | 172.2 | m wall | 7 | 9 | UG-03-S03-A030 | 5 | 2 |  | 2027-03-29 | 2027-04-09 | 2027-04-09 | UG-04-S01-A040
UG-03-S03-A050 | AW.PIPE.F1.UG-03.UG-03-S03 | F1 | UG-03 | UG-03-S03 | A050 | Install dewatering and draw down | 86.1 | m | 10 | 12 | UG-03-S03-A040 | 3 | 2 | UG-04-S01-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-14 | 2027-04-26
UG-03-S03-A060 | AW.PIPE.F1.UG-03.UG-03-S03 | F1 | UG-03 | UG-03-S03 | A060 | Excavate and strut to formation | 1964.8304 | m3 | 8 | 10 | UG-03-S03-A050 | 10 | 2 | gate: D_XING; UG-02-S04-A060 (SS, shared trench) | 2027-04-26 | 2027-05-06 | 2027-05-06 | UG-04-S01-A060
UG-03-S03-A070 | AW.PIPE.F1.UG-03.UG-03-S03 | F1 | UG-03 | UG-03-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 86.1 | m | 11 | 13 | UG-03-S03-A060 | 3 | 2 |  | 2027-05-15 | 2027-05-28 | 2027-05-28 | UG-04-S01-A070
UG-03-S03-A080 | AW.PIPE.F1.UG-03.UG-03-S03 | F1 | UG-03 | UG-03-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 86.1 | m | 5 | 6 | UG-03-S03-A070 | 4 | 2 |  | 2027-05-19 | 2027-05-30 | 2027-05-30 | UG-04-S01-A080
UG-03-S03-A090 | AW.PIPE.F1.UG-03.UG-03-S03 | F1 | UG-03 | UG-03-S03 | A090 | Surround, joint test and line test | 86.1 | m | 3 | 4 | UG-03-S03-A080 | 2 | 2 |  | 2027-05-21 | 2027-06-01
UG-03-S03-A100 | AW.PIPE.F1.UG-03.UG-03-S03 | F1 | UG-03 | UG-03-S03 | A100 | Backfill to NG and remove struts | 1552.1566 | m3 | 5 | 6 | UG-03-S03-A090 | 2 | 2 | UG-02-S04-A080 (FS, shared trench laid) | 2027-06-16 | 2027-06-22 | 2027-06-22 | UG-04-S01-A100
UG-03-S03-A110 | AW.PIPE.F1.UG-03.UG-03-S03 | F1 | UG-03 | UG-03-S03 | A110 | Dewatering off, extract sheets, reinstate | 172.2 | m wall | 5 | 6 | UG-03-S03-A100 | 2 | 2 |  | 2027-06-18 | 2027-06-24
UG-02-S01-A010 | AW.PIPE.F1.UG-02.UG-02-S01 | F1 | UG-02 | UG-02-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-02-S01-A020 | AW.PIPE.F1.UG-02.UG-02-S01 | F1 | UG-02 | UG-02-S01 | A020 | Set-out, crossing survey and working platform | 13.0525 | m | 1 | 2 | UG-02-S01-A010 |  |  | FS from A010; UG-02-S02-A030 (SS, tie-in team follows the adjacent run) | 2027-01-29 | 2027-01-31
UG-02-S01-A030 | AW.PIPE.F1.UG-02.UG-02-S01 | F1 | UG-02 | UG-02-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 12 | piles | 3 | 4 | UG-02-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-30 | 2027-02-03 | 2027-02-03
UG-02-S01-A040 | AW.PIPE.F1.UG-02.UG-02-S01 | F1 | UG-02 | UG-02-S01 | A040 | Install sheet piles (shored lengths) | 26.105 | m wall | 2 | 3 | UG-02-S01-A030 | 2 | 2 |  | 2027-02-01 | 2027-02-05 | 2027-02-05
UG-02-S01-A050 | AW.PIPE.F1.UG-02.UG-02-S01 | F1 | UG-02 | UG-02-S01 | A050 | Install dewatering and draw down | 13.0525 | m | 8 | 10 | UG-02-S01-A040 | 1 | 2 |  | 2027-02-02 | 2027-02-12
UG-02-S01-A060 | AW.PIPE.F1.UG-02.UG-02-S01 | F1 | UG-02 | UG-02-S01 | A060 | Excavate and strut to formation | 232.2498 | m3 | 1 | 2 | UG-02-S01-A050 | 10 | 2 |  | 2027-02-12 | 2027-02-14 | 2027-02-14
UG-02-S01-A070 | AW.PIPE.F1.UG-02.UG-02-S01 | F1 | UG-02 | UG-02-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 13.0525 | m | 5 | 6 | UG-02-S01-A060 | 1 | 2 |  | 2027-02-13 | 2027-02-19 | 2027-02-19
UG-02-S01-A080 | AW.PIPE.F1.UG-02.UG-02-S01 | F1 | UG-02 | UG-02-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 13.0525 | m | 6 | 7 | UG-02-S01-A070 | 2 | 2 | UG-02-S02-A080 (FS, closure) | 2027-03-16 | 2027-03-23 | 2027-03-23
UG-02-S01-A090 | AW.PIPE.F1.UG-02.UG-02-S01 | F1 | UG-02 | UG-02-S01 | A090 | Surround, joint test and line test | 13.0525 | m | 3 | 4 | UG-02-S01-A080 | 3 | 2 |  | 2027-03-19 | 2027-03-25
UG-02-S01-A100 | AW.PIPE.F1.UG-02.UG-02-S01 | F1 | UG-02 | UG-02-S01 | A100 | Backfill to NG and remove struts | 176.2103 | m3 | 1 | 2 | UG-02-S01-A090 | 2 | 2 |  | 2027-03-21 | 2027-03-27 | 2027-03-27
UG-02-S01-A110 | AW.PIPE.F1.UG-02.UG-02-S01 | F1 | UG-02 | UG-02-S01 | A110 | Dewatering off, extract sheets, reinstate | 26.105 | m wall | 2 | 3 | UG-02-S01-A100 | 1 | 2 |  | 2027-03-22 | 2027-03-29
UG-06-S02-A010 | AW.PIPE.F2.UG-06.UG-06-S02 | F2 | UG-06 | UG-06-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-06-S02-A020 | AW.PIPE.F2.UG-06.UG-06-S02 | F2 | UG-06 | UG-06-S02 | A020 | Set-out, crossing survey and working platform | 27.9154 | m | 1 | 2 | UG-06-S02-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-06-S02-A030 | AW.PIPE.F2.UG-06.UG-06-S02 | F2 | UG-06 | UG-06-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 22 | piles | 3 | 4 | UG-06-S02-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-06 | 2026-12-06
UG-06-S02-A040 | AW.PIPE.F2.UG-06.UG-06-S02 | F2 | UG-06 | UG-06-S02 | A040 | Install sheet piles (shored lengths) | 55.8308 | m wall | 2 | 3 | UG-06-S02-A030 | 2 | 2 |  | 2026-12-04 | 2026-12-08 | 2026-12-08
UG-06-S02-A050 | AW.PIPE.F2.UG-06.UG-06-S02 | F2 | UG-06 | UG-06-S02 | A050 | Install dewatering and draw down | 27.9154 | m | 8 | 10 | UG-06-S02-A040 | 1 | 2 |  | 2026-12-05 | 2026-12-15
UG-06-S02-A060 | AW.PIPE.F2.UG-06.UG-06-S02 | F2 | UG-06 | UG-06-S02 | A060 | Excavate and strut to formation | 397.885 | m3 | 1 | 2 | UG-06-S02-A050 | 10 | 2 |  | 2026-12-15 | 2026-12-17 | 2026-12-17
UG-06-S02-A070 | AW.PIPE.F2.UG-06.UG-06-S02 | F2 | UG-06 | UG-06-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 27.9154 | m | 5 | 6 | UG-06-S02-A060 | 1 | 2 |  | 2026-12-16 | 2026-12-22 | 2026-12-22
UG-06-S02-A080 | AW.PIPE.F2.UG-06.UG-06-S02 | F2 | UG-06 | UG-06-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 27.9154 | m | 1 | 2 | UG-06-S02-A070 | 2 | 2 |  | 2026-12-18 | 2026-12-24 | 2026-12-24
UG-06-S02-A090 | AW.PIPE.F2.UG-06.UG-06-S02 | F2 | UG-06 | UG-06-S02 | A090 | Surround, joint test and line test | 27.9154 | m | 3 | 4 | UG-06-S02-A080 | 1 | 2 |  | 2026-12-19 | 2026-12-26
UG-06-S02-A100 | AW.PIPE.F2.UG-06.UG-06-S02 | F2 | UG-06 | UG-06-S02 | A100 | Backfill to NG and remove struts | 241.6418 | m3 | 1 | 2 | UG-06-S02-A090 | 2 | 2 |  | 2026-12-21 | 2026-12-28 | 2026-12-28
UG-06-S02-A110 | AW.PIPE.F2.UG-06.UG-06-S02 | F2 | UG-06 | UG-06-S02 | A110 | Dewatering off, extract sheets, reinstate | 55.8308 | m wall | 3 | 4 | UG-06-S02-A100 | 1 | 2 |  | 2026-12-22 | 2026-12-30
UG-25-S01-A010 | AW.PIPE.F2.UG-25.UG-25-S01 | F2 | UG-25 | UG-25-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-25-S01-A020 | AW.PIPE.F2.UG-25.UG-25-S01 | F2 | UG-25 | UG-25-S01 | A020 | Set-out, crossing survey and working platform | 495.2172 | m | 7 | 9 | UG-25-S01-A010 |  |  | FS from A010; UG-06-S02-A030 (SS, set-out one package ahead of piling) | 2026-12-02 | 2026-12-11
UG-25-S01-A030 | AW.PIPE.F2.UG-25.UG-25-S01 | F2 | UG-25 | UG-25-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 334 | piles | 34 | 40 | UG-25-S01-A020 | 3 | 2 | gate: D_PILEDES | 2026-12-06 | 2027-01-15 | 2027-01-15 | UG-06-S02-A030
UG-25-S01-A040 | AW.PIPE.F2.UG-25.UG-25-S01 | F2 | UG-25 | UG-25-S01 | A040 | Install sheet piles (shored lengths) | 990.4344 | m wall | 20 | 24 | UG-25-S01-A030 | 12 | 2 |  | 2026-12-18 | 2027-01-17 | 2027-01-17 | UG-06-S02-A040
UG-25-S01-A050 | AW.PIPE.F2.UG-25.UG-25-S01 | F2 | UG-25 | UG-25-S01 | A050 | Install dewatering and draw down | 495.2172 | m | 20 | 24 | UG-25-S01-A040 | 8 | 2 | UG-06-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2026-12-26 | 2027-01-19
UG-25-S01-A060 | AW.PIPE.F2.UG-25.UG-25-S01 | F2 | UG-25 | UG-25-S01 | A060 | Excavate and strut to formation | 8609.0665 | m3 | 18 | 21 | UG-25-S01-A050 | 14 | 2 |  | 2027-01-09 | 2027-01-30 | 2027-01-30 | UG-06-S02-A060
UG-25-S01-A070 | AW.PIPE.F2.UG-25.UG-25-S01 | F2 | UG-25 | UG-25-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 495.2172 | m | 24 | 28 | UG-25-S01-A060 | 7 | 2 |  | 2027-01-16 | 2027-02-13 | 2027-02-13 | UG-06-S02-A070
UG-25-S01-A080 | AW.PIPE.F2.UG-25.UG-25-S01 | F2 | UG-25 | UG-25-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 495.2172 | m | 18 | 21 | UG-25-S01-A070 | 9 | 2 |  | 2027-01-25 | 2027-02-15 | 2027-02-15 | UG-06-S02-A080
UG-25-S01-A090 | AW.PIPE.F2.UG-25.UG-25-S01 | F2 | UG-25 | UG-25-S01 | A090 | Surround, joint test and line test | 495.2172 | m | 6 | 7 | UG-25-S01-A080 | 7 | 2 |  | 2027-02-01 | 2027-02-17
UG-25-S01-A100 | AW.PIPE.F2.UG-25.UG-25-S01 | F2 | UG-25 | UG-25-S01 | A100 | Backfill to NG and remove struts | 5350.1097 | m3 | 8 | 10 | UG-25-S01-A090 | 3 | 2 | UG-05-S05-A080 (FS, shared trench laid); UG-06-S05-A080 (FS, shared trench laid); UG-26-S01-A080 (FS, shared trench laid) | 2027-04-17 | 2027-04-27 | 2027-04-27 | UG-06-S02-A100
UG-25-S01-A110 | AW.PIPE.F2.UG-25.UG-25-S01 | F2 | UG-25 | UG-25-S01 | A110 | Dewatering off, extract sheets, reinstate | 990.4344 | m wall | 21 | 25 | UG-25-S01-A100 | 3 | 2 |  | 2027-04-20 | 2027-05-15
UG-26-S01-A010 | AW.PIPE.F2.UG-26.UG-26-S01 | F2 | UG-26 | UG-26-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-26-S01-A020 | AW.PIPE.F2.UG-26.UG-26-S01 | F2 | UG-26 | UG-26-S01 | A020 | Set-out, crossing survey and working platform | 495.7146 | m | 7 | 9 | UG-26-S01-A010 |  |  | FS from A010; UG-25-S01-A030 (SS, set-out one package ahead of piling) | 2026-12-06 | 2026-12-15
UG-26-S01-A030 | AW.PIPE.F2.UG-26.UG-26-S01 | F2 | UG-26 | UG-26-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 334 | piles | 34 | 40 | UG-26-S01-A020 | 3 | 2 | gate: D_PILEDES | 2027-01-15 | 2027-02-24 | 2027-02-24 | UG-25-S01-A030
UG-26-S01-A040 | AW.PIPE.F2.UG-26.UG-26-S01 | F2 | UG-26 | UG-26-S01 | A040 | Install sheet piles (shored lengths) | 991.4292 | m wall | 20 | 24 | UG-26-S01-A030 | 12 | 2 |  | 2027-01-27 | 2027-02-26 | 2027-02-26 | UG-25-S01-A040
UG-26-S01-A050 | AW.PIPE.F2.UG-26.UG-26-S01 | F2 | UG-26 | UG-26-S01 | A050 | Install dewatering and draw down | 495.7146 | m | 20 | 24 | UG-26-S01-A040 | 8 | 2 | UG-25-S01-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-02-04 | 2027-02-28
UG-26-S01-A060 | AW.PIPE.F2.UG-26.UG-26-S01 | F2 | UG-26 | UG-26-S01 | A060 | Excavate and strut to formation | 8189.5843 | m3 | 17 | 20 | UG-26-S01-A050 | 14 | 2 | UG-25-S01-A060 (SS, shared trench) | 2027-02-18 | 2027-03-10 | 2027-03-10 | UG-25-S01-A060
UG-26-S01-A070 | AW.PIPE.F2.UG-26.UG-26-S01 | F2 | UG-26 | UG-26-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 495.7146 | m | 24 | 28 | UG-26-S01-A060 | 6 | 2 |  | 2027-02-24 | 2027-03-24 | 2027-03-24 | UG-25-S01-A070
UG-26-S01-A080 | AW.PIPE.F2.UG-26.UG-26-S01 | F2 | UG-26 | UG-26-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 495.7146 | m | 16 | 19 | UG-26-S01-A070 | 9 | 2 |  | 2027-03-05 | 2027-03-26 | 2027-03-26 | UG-25-S01-A080
UG-26-S01-A090 | AW.PIPE.F2.UG-26.UG-26-S01 | F2 | UG-26 | UG-26-S01 | A090 | Surround, joint test and line test | 495.7146 | m | 6 | 7 | UG-26-S01-A080 | 6 | 2 |  | 2027-03-11 | 2027-03-28
UG-26-S01-A100 | AW.PIPE.F2.UG-26.UG-26-S01 | F2 | UG-26 | UG-26-S01 | A100 | Backfill to NG and remove struts | 4924.6483 | m3 | 8 | 10 | UG-26-S01-A090 | 3 | 2 | UG-05-S05-A080 (FS, shared trench laid); UG-06-S05-A080 (FS, shared trench laid); UG-25-S01-A080 (FS, shared trench laid) | 2027-04-27 | 2027-05-07 | 2027-05-07 | UG-25-S01-A100
UG-26-S01-A110 | AW.PIPE.F2.UG-26.UG-26-S01 | F2 | UG-26 | UG-26-S01 | A110 | Dewatering off, extract sheets, reinstate | 991.4292 | m wall | 21 | 25 | UG-26-S01-A100 | 3 | 2 |  | 2027-04-30 | 2027-05-25
UG-06-S05-A010 | AW.PIPE.F2.UG-06.UG-06-S05 | F2 | UG-06 | UG-06-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-06-S05-A020 | AW.PIPE.F2.UG-06.UG-06-S05 | F2 | UG-06 | UG-06-S05 | A020 | Set-out, crossing survey and working platform | 22.1072 | m | 1 | 2 | UG-06-S05-A010 |  |  | FS from A010; UG-26-S01-A030 (SS, set-out one package ahead of piling) | 2027-01-15 | 2027-01-17
UG-06-S05-A030 | AW.PIPE.F2.UG-06.UG-06-S05 | F2 | UG-06 | UG-06-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 18 | piles | 2 | 3 | UG-06-S05-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-24 | 2027-02-27 | 2027-02-27 | UG-26-S01-A030
UG-06-S05-A040 | AW.PIPE.F2.UG-06.UG-06-S05 | F2 | UG-06 | UG-06-S05 | A040 | Install sheet piles (shored lengths) | 44.2144 | m wall | 1 | 2 | UG-06-S05-A030 | 1 | 2 |  | 2027-02-26 | 2027-03-01 | 2027-03-01 | UG-26-S01-A040
UG-06-S05-A050 | AW.PIPE.F2.UG-06.UG-06-S05 | F2 | UG-06 | UG-06-S05 | A050 | Install dewatering and draw down | 22.1072 | m | 8 | 10 | UG-06-S05-A040 | 1 | 2 | UG-26-S01-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-02-28 | 2027-03-10
UG-06-S05-A060 | AW.PIPE.F2.UG-06.UG-06-S05 | F2 | UG-06 | UG-06-S05 | A060 | Excavate and strut to formation | 321.7389 | m3 | 1 | 2 | UG-06-S05-A050 | 10 | 2 | UG-25-S01-A060 (SS, shared trench); UG-26-S01-A060 (SS, shared trench) | 2027-03-10 | 2027-03-12 | 2027-03-12 | UG-26-S01-A060
UG-06-S05-A070 | AW.PIPE.F2.UG-06.UG-06-S05 | F2 | UG-06 | UG-06-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 22.1072 | m | 4 | 5 | UG-06-S05-A060 | 1 | 2 |  | 2027-03-24 | 2027-03-29 | 2027-03-29 | UG-26-S01-A070
UG-06-S05-A080 | AW.PIPE.F2.UG-06.UG-06-S05 | F2 | UG-06 | UG-06-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 22.1072 | m | 1 | 2 | UG-06-S05-A070 | 2 | 2 |  | 2027-03-26 | 2027-03-31 | 2027-03-31 | UG-26-S01-A080
UG-06-S05-A090 | AW.PIPE.F2.UG-06.UG-06-S05 | F2 | UG-06 | UG-06-S05 | A090 | Surround, joint test and line test | 22.1072 | m | 3 | 4 | UG-06-S05-A080 | 1 | 2 |  | 2027-03-27 | 2027-04-02
UG-06-S05-A100 | AW.PIPE.F2.UG-06.UG-06-S05 | F2 | UG-06 | UG-06-S05 | A100 | Backfill to NG and remove struts | 198.0039 | m3 | 1 | 2 | UG-06-S05-A090 | 2 | 2 | UG-05-S04-A080 (FS, shared trench laid); UG-05-S05-A080 (FS, shared trench laid); UG-25-S01-A080 (FS, shared trench laid); UG-26-S01-A080 (FS, shared trench laid) | 2027-05-08 | 2027-05-10 | 2027-05-10 | UG-26-S01-A100
UG-06-S05-A110 | AW.PIPE.F2.UG-06.UG-06-S05 | F2 | UG-06 | UG-06-S05 | A110 | Dewatering off, extract sheets, reinstate | 44.2144 | m wall | 2 | 3 | UG-06-S05-A100 | 1 | 2 |  | 2027-05-09 | 2027-05-12
UG-06-S04-A010 | AW.PIPE.F2.UG-06.UG-06-S04 | F2 | UG-06 | UG-06-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-06-S04-A020 | AW.PIPE.F2.UG-06.UG-06-S04 | F2 | UG-06 | UG-06-S04 | A020 | Set-out, crossing survey and working platform | 130.4 | m | 2 | 3 | UG-06-S04-A010 |  |  | FS from A010; UG-06-S05-A030 (SS, set-out one package ahead of piling) | 2027-02-24 | 2027-02-27
UG-06-S04-A030 | AW.PIPE.F2.UG-06.UG-06-S04 | F2 | UG-06 | UG-06-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 90 | piles | 9 | 11 | UG-06-S04-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-27 | 2027-03-10 | 2027-03-10 | UG-06-S05-A030
UG-06-S04-A040 | AW.PIPE.F2.UG-06.UG-06-S04 | F2 | UG-06 | UG-06-S04 | A040 | Install sheet piles (shored lengths) | 260.8 | m wall | 6 | 7 | UG-06-S04-A030 | 4 | 2 |  | 2027-03-03 | 2027-03-12 | 2027-03-12 | UG-06-S05-A040
UG-06-S04-A050 | AW.PIPE.F2.UG-06.UG-06-S04 | F2 | UG-06 | UG-06-S04 | A050 | Install dewatering and draw down | 130.4 | m | 11 | 13 | UG-06-S04-A040 | 3 | 2 | UG-06-S05-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-06 | 2027-03-19
UG-06-S04-A060 | AW.PIPE.F2.UG-06.UG-06-S04 | F2 | UG-06 | UG-06-S04 | A060 | Excavate and strut to formation | 1900.3754 | m3 | 4 | 5 | UG-06-S04-A050 | 11 | 2 |  | 2027-03-17 | 2027-03-22 | 2027-03-22 | UG-06-S05-A060
UG-06-S04-A070 | AW.PIPE.F2.UG-06.UG-06-S04 | F2 | UG-06 | UG-06-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 130.4 | m | 9 | 11 | UG-06-S04-A060 | 2 | 2 |  | 2027-03-29 | 2027-04-09 | 2027-04-09 | UG-06-S05-A070
UG-06-S04-A080 | AW.PIPE.F2.UG-06.UG-06-S04 | F2 | UG-06 | UG-06-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 130.4 | m | 4 | 5 | UG-06-S04-A070 | 4 | 2 |  | 2027-04-02 | 2027-04-11 | 2027-04-11 | UG-06-S05-A080
UG-06-S04-A090 | AW.PIPE.F2.UG-06.UG-06-S04 | F2 | UG-06 | UG-06-S04 | A090 | Surround, joint test and line test | 130.4 | m | 3 | 4 | UG-06-S04-A080 | 2 | 2 |  | 2027-04-04 | 2027-04-13
UG-06-S04-A100 | AW.PIPE.F2.UG-06.UG-06-S04 | F2 | UG-06 | UG-06-S04 | A100 | Backfill to NG and remove struts | 1170.5205 | m3 | 2 | 3 | UG-06-S04-A090 | 2 | 2 | UG-05-S03-A080 (FS, shared trench laid); UG-05-S04-A080 (FS, shared trench laid); UG-05-S05-A080 (FS, shared trench laid) | 2027-05-18 | 2027-05-21 | 2027-05-21 | UG-06-S05-A100
UG-06-S04-A110 | AW.PIPE.F2.UG-06.UG-06-S04 | F2 | UG-06 | UG-06-S04 | A110 | Dewatering off, extract sheets, reinstate | 260.8 | m wall | 7 | 9 | UG-06-S04-A100 | 1 | 2 |  | 2027-05-19 | 2027-05-28
UG-05-S05-A010 | AW.PIPE.F2.UG-05.UG-05-S05 | F2 | UG-05 | UG-05-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-05-S05-A020 | AW.PIPE.F2.UG-05.UG-05-S05 | F2 | UG-05 | UG-05-S05 | A020 | Set-out, crossing survey and working platform | 25.0174 | m | 1 | 2 | UG-05-S05-A010 |  |  | FS from A010; UG-06-S04-A030 (SS, set-out one package ahead of piling) | 2027-02-27 | 2027-03-01
UG-05-S05-A030 | AW.PIPE.F2.UG-05.UG-05-S05 | F2 | UG-05 | UG-05-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 20 | piles | 2 | 3 | UG-05-S05-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-10 | 2027-03-13 | 2027-03-13 | UG-06-S04-A030
UG-05-S05-A040 | AW.PIPE.F2.UG-05.UG-05-S05 | F2 | UG-05 | UG-05-S05 | A040 | Install sheet piles (shored lengths) | 50.0349 | m wall | 2 | 3 | UG-05-S05-A030 | 1 | 2 |  | 2027-03-12 | 2027-03-15 | 2027-03-15 | UG-06-S04-A040
UG-05-S05-A050 | AW.PIPE.F2.UG-05.UG-05-S05 | F2 | UG-05 | UG-05-S05 | A050 | Install dewatering and draw down | 25.0174 | m | 8 | 10 | UG-05-S05-A040 | 1 | 2 | UG-06-S04-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-13 | 2027-03-23
UG-05-S05-A060 | AW.PIPE.F2.UG-05.UG-05-S05 | F2 | UG-05 | UG-05-S05 | A060 | Excavate and strut to formation | 363.9417 | m3 | 1 | 2 | UG-05-S05-A050 | 10 | 2 | UG-06-S04-A060 (SS, shared trench); UG-06-S05-A060 (SS, shared trench); UG-25-S01-A060 (SS, shared trench); UG-26-S01-A060 (SS, shared trench) | 2027-03-23 | 2027-03-25 | 2027-03-25 | UG-06-S04-A060
UG-05-S05-A070 | AW.PIPE.F2.UG-05.UG-05-S05 | F2 | UG-05 | UG-05-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 25.0174 | m | 5 | 6 | UG-05-S05-A060 | 1 | 2 |  | 2027-04-09 | 2027-04-15 | 2027-04-15 | UG-06-S04-A070
UG-05-S05-A080 | AW.PIPE.F2.UG-05.UG-05-S05 | F2 | UG-05 | UG-05-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 25.0174 | m | 1 | 2 | UG-05-S05-A070 | 2 | 2 |  | 2027-04-11 | 2027-04-17 | 2027-04-17 | UG-06-S04-A080
UG-05-S05-A090 | AW.PIPE.F2.UG-05.UG-05-S05 | F2 | UG-05 | UG-05-S05 | A090 | Surround, joint test and line test | 25.0174 | m | 3 | 4 | UG-05-S05-A080 | 1 | 2 |  | 2027-04-12 | 2027-04-19
UG-05-S05-A100 | AW.PIPE.F2.UG-05.UG-05-S05 | F2 | UG-05 | UG-05-S05 | A100 | Backfill to NG and remove struts | 223.918 | m3 | 1 | 2 | UG-05-S05-A090 | 2 | 2 | UG-06-S04-A080 (FS, shared trench laid); UG-06-S05-A080 (FS, shared trench laid); UG-25-S01-A080 (FS, shared trench laid); UG-26-S01-A080 (FS, shared trench laid) | 2027-05-21 | 2027-05-23 | 2027-05-23 | UG-06-S04-A100
UG-05-S05-A110 | AW.PIPE.F2.UG-05.UG-05-S05 | F2 | UG-05 | UG-05-S05 | A110 | Dewatering off, extract sheets, reinstate | 50.0349 | m wall | 3 | 4 | UG-05-S05-A100 | 1 | 2 |  | 2027-05-22 | 2027-05-26
UG-06-S03-A010 | AW.PIPE.F2.UG-06.UG-06-S03 | F2 | UG-06 | UG-06-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-06-S03-A020 | AW.PIPE.F2.UG-06.UG-06-S03 | F2 | UG-06 | UG-06-S03 | A020 | Set-out, crossing survey and working platform | 98.3 | m | 2 | 3 | UG-06-S03-A010 |  |  | FS from A010; UG-05-S05-A030 (SS, set-out one package ahead of piling) | 2027-03-10 | 2027-03-13
UG-06-S03-A030 | AW.PIPE.F2.UG-06.UG-06-S03 | F2 | UG-06 | UG-06-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 68 | piles | 7 | 9 | UG-06-S03-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-13 | 2027-03-22 | 2027-03-22 | UG-05-S05-A030
UG-06-S03-A040 | AW.PIPE.F2.UG-06.UG-06-S03 | F2 | UG-06 | UG-06-S03 | A040 | Install sheet piles (shored lengths) | 196.6 | m wall | 4 | 5 | UG-06-S03-A030 | 3 | 2 |  | 2027-03-16 | 2027-03-24 | 2027-03-24 | UG-05-S05-A040
UG-06-S03-A050 | AW.PIPE.F2.UG-06.UG-06-S03 | F2 | UG-06 | UG-06-S03 | A050 | Install dewatering and draw down | 98.3 | m | 10 | 12 | UG-06-S03-A040 | 2 | 2 | UG-05-S05-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-18 | 2027-03-30
UG-06-S03-A060 | AW.PIPE.F2.UG-06.UG-06-S03 | F2 | UG-06 | UG-06-S03 | A060 | Excavate and strut to formation | 1408.204 | m3 | 3 | 4 | UG-06-S03-A050 | 10 | 2 |  | 2027-03-28 | 2027-04-01 | 2027-04-01 | UG-05-S05-A060
UG-06-S03-A070 | AW.PIPE.F2.UG-06.UG-06-S03 | F2 | UG-06 | UG-06-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 98.3 | m | 8 | 10 | UG-06-S03-A060 | 2 | 2 |  | 2027-04-15 | 2027-04-25 | 2027-04-25 | UG-05-S05-A070
UG-06-S03-A080 | AW.PIPE.F2.UG-06.UG-06-S03 | F2 | UG-06 | UG-06-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 98.3 | m | 6 | 7 | UG-06-S03-A070 | 3 | 2 |  | 2027-04-18 | 2027-04-27 | 2027-04-27 | UG-05-S05-A080
UG-06-S03-A090 | AW.PIPE.F2.UG-06.UG-06-S03 | F2 | UG-06 | UG-06-S03 | A090 | Surround, joint test and line test | 98.3 | m | 3 | 4 | UG-06-S03-A080 | 3 | 2 |  | 2027-04-21 | 2027-04-29
UG-06-S03-A100 | AW.PIPE.F2.UG-06.UG-06-S03 | F2 | UG-06 | UG-06-S03 | A100 | Backfill to NG and remove struts | 858.016 | m3 | 2 | 3 | UG-06-S03-A090 | 2 | 2 | UG-05-S02-A080 (FS, shared trench laid); UG-05-S03-A080 (FS, shared trench laid); UG-05-S04-A080 (FS, shared trench laid) | 2027-05-25 | 2027-05-28 | 2027-05-28 | UG-05-S05-A100
UG-06-S03-A110 | AW.PIPE.F2.UG-06.UG-06-S03 | F2 | UG-06 | UG-06-S03 | A110 | Dewatering off, extract sheets, reinstate | 196.6 | m wall | 5 | 6 | UG-06-S03-A100 | 1 | 2 |  | 2027-05-26 | 2027-06-01
UG-05-S04-A010 | AW.PIPE.F2.UG-05.UG-05-S04 | F2 | UG-05 | UG-05-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-05-S04-A020 | AW.PIPE.F2.UG-05.UG-05-S04 | F2 | UG-05 | UG-05-S04 | A020 | Set-out, crossing survey and working platform | 123.2 | m | 2 | 3 | UG-05-S04-A010 |  |  | FS from A010; UG-06-S03-A030 (SS, set-out one package ahead of piling) | 2027-03-13 | 2027-03-16
UG-05-S04-A030 | AW.PIPE.F2.UG-05.UG-05-S04 | F2 | UG-05 | UG-05-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 86 | piles | 9 | 11 | UG-05-S04-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-22 | 2027-04-02 | 2027-04-02 | UG-06-S03-A030
UG-05-S04-A040 | AW.PIPE.F2.UG-05.UG-05-S04 | F2 | UG-05 | UG-05-S04 | A040 | Install sheet piles (shored lengths) | 246.4 | m wall | 5 | 6 | UG-05-S04-A030 | 4 | 2 |  | 2027-03-26 | 2027-04-04 | 2027-04-04 | UG-06-S03-A040
UG-05-S04-A050 | AW.PIPE.F2.UG-05.UG-05-S04 | F2 | UG-05 | UG-05-S04 | A050 | Install dewatering and draw down | 123.2 | m | 11 | 13 | UG-05-S04-A040 | 2 | 2 | UG-06-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-28 | 2027-04-10
UG-05-S04-A060 | AW.PIPE.F2.UG-05.UG-05-S04 | F2 | UG-05 | UG-05-S04 | A060 | Excavate and strut to formation | 1789.9342 | m3 | 4 | 5 | UG-05-S04-A050 | 11 | 2 | UG-06-S03-A060 (SS, shared trench); UG-06-S04-A060 (SS, shared trench); UG-06-S05-A060 (SS, shared trench) | 2027-04-08 | 2027-04-13 | 2027-04-13 | UG-06-S03-A060
UG-05-S04-A070 | AW.PIPE.F2.UG-05.UG-05-S04 | F2 | UG-05 | UG-05-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 123.2 | m | 9 | 11 | UG-05-S04-A060 | 2 | 2 |  | 2027-04-25 | 2027-05-06 | 2027-05-06 | UG-06-S03-A070
UG-05-S04-A080 | AW.PIPE.F2.UG-05.UG-05-S04 | F2 | UG-05 | UG-05-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 123.2 | m | 4 | 5 | UG-05-S04-A070 | 4 | 2 |  | 2027-04-29 | 2027-05-08 | 2027-05-08 | UG-06-S03-A080
UG-05-S04-A090 | AW.PIPE.F2.UG-05.UG-05-S04 | F2 | UG-05 | UG-05-S04 | A090 | Surround, joint test and line test | 123.2 | m | 3 | 4 | UG-05-S04-A080 | 2 | 2 |  | 2027-05-01 | 2027-05-10
UG-05-S04-A100 | AW.PIPE.F2.UG-05.UG-05-S04 | F2 | UG-05 | UG-05-S04 | A100 | Backfill to NG and remove struts | 1100.3781 | m3 | 2 | 3 | UG-05-S04-A090 | 2 | 2 | UG-06-S03-A080 (FS, shared trench laid); UG-06-S04-A080 (FS, shared trench laid); UG-06-S05-A080 (FS, shared trench laid) | 2027-05-28 | 2027-05-31 | 2027-05-31 | UG-06-S03-A100
UG-05-S04-A110 | AW.PIPE.F2.UG-05.UG-05-S04 | F2 | UG-05 | UG-05-S04 | A110 | Dewatering off, extract sheets, reinstate | 246.4 | m wall | 6 | 7 | UG-05-S04-A100 | 1 | 2 |  | 2027-05-29 | 2027-06-05
UG-05-S03-A010 | AW.PIPE.F2.UG-05.UG-05-S03 | F2 | UG-05 | UG-05-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-05-S03-A020 | AW.PIPE.F2.UG-05.UG-05-S03 | F2 | UG-05 | UG-05-S03 | A020 | Set-out, crossing survey and working platform | 104.2 | m | 2 | 3 | UG-05-S03-A010 |  |  | FS from A010; UG-05-S04-A030 (SS, set-out one package ahead of piling) | 2027-03-22 | 2027-03-25
UG-05-S03-A030 | AW.PIPE.F2.UG-05.UG-05-S03 | F2 | UG-05 | UG-05-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 72 | piles | 8 | 10 | UG-05-S03-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-02 | 2027-04-12 | 2027-04-12 | UG-05-S04-A030
UG-05-S03-A040 | AW.PIPE.F2.UG-05.UG-05-S03 | F2 | UG-05 | UG-05-S03 | A040 | Install sheet piles (shored lengths) | 116.6 | m wall | 3 | 4 | UG-05-S03-A030 | 3 | 2 |  | 2027-04-05 | 2027-04-14 | 2027-04-14 | UG-05-S04-A040
UG-05-S03-A050 | AW.PIPE.F2.UG-05.UG-05-S03 | F2 | UG-05 | UG-05-S03 | A050 | Install dewatering and draw down | 104.2 | m | 10 | 12 | UG-05-S03-A040 | 2 | 2 | UG-05-S04-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-07 | 2027-04-19
UG-05-S03-A060 | AW.PIPE.F2.UG-05.UG-05-S03 | F2 | UG-05 | UG-05-S03 | A060 | Excavate and strut to formation | 2384.8672 | m3 | 4 | 5 | UG-05-S03-A050 | 10 | 2 | UG-06-S03-A060 (SS, shared trench); UG-06-S04-A060 (SS, shared trench) | 2027-04-17 | 2027-04-22 | 2027-04-22 | UG-05-S04-A060
UG-05-S03-A070 | AW.PIPE.F2.UG-05.UG-05-S03 | F2 | UG-05 | UG-05-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 104.2 | m | 8 | 10 | UG-05-S03-A060 | 2 | 2 |  | 2027-05-06 | 2027-05-16 | 2027-05-16 | UG-05-S04-A070
UG-05-S03-A080 | AW.PIPE.F2.UG-05.UG-05-S03 | F2 | UG-05 | UG-05-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 104.2 | m | 5 | 6 | UG-05-S03-A070 | 3 | 2 |  | 2027-05-09 | 2027-05-18 | 2027-05-18 | UG-05-S04-A080
UG-05-S03-A090 | AW.PIPE.F2.UG-05.UG-05-S03 | F2 | UG-05 | UG-05-S03 | A090 | Surround, joint test and line test | 104.2 | m | 3 | 4 | UG-05-S03-A080 | 2 | 2 |  | 2027-05-11 | 2027-05-20
UG-05-S03-A100 | AW.PIPE.F2.UG-05.UG-05-S03 | F2 | UG-05 | UG-05-S03 | A100 | Backfill to NG and remove struts | 1801.6543 | m3 | 3 | 4 | UG-05-S03-A090 | 2 | 2 | UG-06-S03-A080 (FS, shared trench laid); UG-06-S04-A080 (FS, shared trench laid) | 2027-05-31 | 2027-06-04 | 2027-06-04 | UG-05-S04-A100
UG-05-S03-A110 | AW.PIPE.F2.UG-05.UG-05-S03 | F2 | UG-05 | UG-05-S03 | A110 | Dewatering off, extract sheets, reinstate | 116.6 | m wall | 4 | 5 | UG-05-S03-A100 | 2 | 2 |  | 2027-06-02 | 2027-06-07
UG-05-S02-A010 | AW.PIPE.F2.UG-05.UG-05-S02 | F2 | UG-05 | UG-05-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-05-S02-A020 | AW.PIPE.F2.UG-05.UG-05-S02 | F2 | UG-05 | UG-05-S02 | A020 | Set-out, crossing survey and working platform | 48.1 | m | 1 | 2 | UG-05-S02-A010 |  |  | FS from A010; UG-05-S03-A030 (SS, set-out one package ahead of piling) | 2027-04-02 | 2027-04-04
UG-05-S02-A030 | AW.PIPE.F2.UG-05.UG-05-S02 | F2 | UG-05 | UG-05-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 36 | piles | 4 | 5 | UG-05-S02-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-12 | 2027-04-17 | 2027-04-17 | UG-05-S03-A030
UG-05-S02-A040 | AW.PIPE.F2.UG-05.UG-05-S02 | F2 | UG-05 | UG-05-S02 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-05-S02-A030 | 2 | 0 |  | 2027-04-14 | 2027-04-17 | 2027-04-14 | UG-05-S03-A040
UG-05-S02-A050 | AW.PIPE.F2.UG-05.UG-05-S02 | F2 | UG-05 | UG-05-S02 | A050 | Install dewatering and draw down | 48.1 | m | 9 | 11 | UG-05-S02-A040 | 0 | 2 | UG-05-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-14 | 2027-04-25
UG-05-S02-A060 | AW.PIPE.F2.UG-05.UG-05-S02 | F2 | UG-05 | UG-05-S02 | A060 | Excavate and strut to formation | 1502.7067 | m3 | 2 | 3 | UG-05-S02-A050 | 10 | 2 | UG-06-S03-A060 (SS, shared trench) | 2027-04-24 | 2027-04-27 | 2027-04-27 | UG-05-S03-A060
UG-05-S02-A070 | AW.PIPE.F2.UG-05.UG-05-S02 | F2 | UG-05 | UG-05-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 48.1 | m | 6 | 7 | UG-05-S02-A060 | 1 | 2 |  | 2027-05-16 | 2027-05-23 | 2027-05-23 | UG-05-S03-A070
UG-05-S02-A080 | AW.PIPE.F2.UG-05.UG-05-S02 | F2 | UG-05 | UG-05-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 48.1 | m | 3 | 4 | UG-05-S02-A070 | 3 | 2 |  | 2027-05-19 | 2027-05-25 | 2027-05-25 | UG-05-S03-A080
UG-05-S02-A090 | AW.PIPE.F2.UG-05.UG-05-S02 | F2 | UG-05 | UG-05-S02 | A090 | Surround, joint test and line test | 48.1 | m | 3 | 4 | UG-05-S02-A080 | 2 | 2 |  | 2027-05-21 | 2027-05-27
UG-05-S02-A100 | AW.PIPE.F2.UG-05.UG-05-S02 | F2 | UG-05 | UG-05-S02 | A100 | Backfill to NG and remove struts | 1229.4186 | m3 | 2 | 3 | UG-05-S02-A090 | 2 | 2 | UG-06-S03-A080 (FS, shared trench laid); UG-24-S01-A080 (FS, shared trench laid); UG-24-S02-A080 (FS, shared trench laid) | 2027-07-13 | 2027-07-16 | 2027-07-16 | UG-05-S03-A100
UG-05-S02-A110 | AW.PIPE.F2.UG-05.UG-05-S02 | F2 | UG-05 | UG-05-S02 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-05-S02-A100 | 1 | 2 |  | 2027-07-14 | 2027-07-18
UG-06-S01-A010 | AW.PIPE.F2.UG-06.UG-06-S01 | F2 | UG-06 | UG-06-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-06-S01-A020 | AW.PIPE.F2.UG-06.UG-06-S01 | F2 | UG-06 | UG-06-S01 | A020 | Set-out, crossing survey and working platform | 21.1846 | m | 1 | 2 | UG-06-S01-A010 |  |  | FS from A010; UG-06-S02-A030 (SS, tie-in team follows the adjacent run) | 2026-12-02 | 2026-12-04
UG-06-S01-A030 | AW.PIPE.F2.UG-06.UG-06-S01 | F2 | UG-06 | UG-06-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 18 | piles | 2 | 3 | UG-06-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-03 | 2026-12-06 | 2026-12-06
UG-06-S01-A040 | AW.PIPE.F2.UG-06.UG-06-S01 | F2 | UG-06 | UG-06-S01 | A040 | Install sheet piles (shored lengths) | 42.3692 | m wall | 1 | 2 | UG-06-S01-A030 | 1 | 2 |  | 2026-12-04 | 2026-12-08 | 2026-12-08
UG-06-S01-A050 | AW.PIPE.F2.UG-06.UG-06-S01 | F2 | UG-06 | UG-06-S01 | A050 | Install dewatering and draw down | 21.1846 | m | 8 | 10 | UG-06-S01-A040 | 1 | 2 |  | 2026-12-05 | 2026-12-15
UG-06-S01-A060 | AW.PIPE.F2.UG-06.UG-06-S01 | F2 | UG-06 | UG-06-S01 | A060 | Excavate and strut to formation | 303.281 | m3 | 1 | 2 | UG-06-S01-A050 | 10 | 2 |  | 2026-12-15 | 2026-12-17 | 2026-12-17
UG-06-S01-A070 | AW.PIPE.F2.UG-06.UG-06-S01 | F2 | UG-06 | UG-06-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 21.1846 | m | 4 | 5 | UG-06-S01-A060 | 1 | 2 |  | 2026-12-16 | 2026-12-21 | 2026-12-21
UG-06-S01-A080 | AW.PIPE.F2.UG-06.UG-06-S01 | F2 | UG-06 | UG-06-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 21.1846 | m | 6 | 7 | UG-06-S01-A070 | 2 | 2 | UG-06-S02-A080 (FS, closure) | 2026-12-24 | 2026-12-31 | 2026-12-31
UG-06-S01-A090 | AW.PIPE.F2.UG-06.UG-06-S01 | F2 | UG-06 | UG-06-S01 | A090 | Surround, joint test and line test | 21.1846 | m | 3 | 4 | UG-06-S01-A080 | 3 | 2 |  | 2026-12-27 | 2027-01-02
UG-06-S01-A100 | AW.PIPE.F2.UG-06.UG-06-S01 | F2 | UG-06 | UG-06-S01 | A100 | Backfill to NG and remove struts | 183.7273 | m3 | 1 | 2 | UG-06-S01-A090 | 2 | 2 | UG-05-S01-A080 (FS, shared trench laid) | 2027-05-30 | 2027-06-01 | 2027-06-01
UG-06-S01-A110 | AW.PIPE.F2.UG-06.UG-06-S01 | F2 | UG-06 | UG-06-S01 | A110 | Dewatering off, extract sheets, reinstate | 42.3692 | m wall | 2 | 3 | UG-06-S01-A100 | 1 | 2 |  | 2027-05-31 | 2027-06-03
UG-05-S01-A010 | AW.PIPE.F2.UG-05.UG-05-S01 | F2 | UG-05 | UG-05-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-05-S01-A020 | AW.PIPE.F2.UG-05.UG-05-S01 | F2 | UG-05 | UG-05-S01 | A020 | Set-out, crossing survey and working platform | 6 | m | 1 | 2 | UG-05-S01-A010 |  |  | FS from A010; UG-05-S02-A030 (SS, tie-in team follows the adjacent run) | 2027-04-12 | 2027-04-14
UG-05-S01-A030 | AW.PIPE.F2.UG-05.UG-05-S01 | F2 | UG-05 | UG-05-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 6 | piles | 1 | 2 | UG-05-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-13 | 2027-04-16 | 2027-04-16
UG-05-S01-A040 | AW.PIPE.F2.UG-05.UG-05-S01 | F2 | UG-05 | UG-05-S01 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-05-S01-A030 | 1 | 0 |  | 2027-04-14 | 2027-04-16 | 0
UG-05-S01-A050 | AW.PIPE.F2.UG-05.UG-05-S01 | F2 | UG-05 | UG-05-S01 | A050 | Install dewatering and draw down | 6 | m | 8 | 10 | UG-05-S01-A040 | 0 | 2 |  | 2027-04-14 | 2027-04-24
UG-05-S01-A060 | AW.PIPE.F2.UG-05.UG-05-S01 | F2 | UG-05 | UG-05-S01 | A060 | Excavate and strut to formation | 178.132 | m3 | 1 | 2 | UG-05-S01-A050 | 10 | 2 | UG-06-S01-A060 (SS, shared trench) | 2027-04-24 | 2027-04-26 | 2027-04-26
UG-05-S01-A070 | AW.PIPE.F2.UG-05.UG-05-S01 | F2 | UG-05 | UG-05-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6 | m | 4 | 5 | UG-05-S01-A060 | 1 | 2 |  | 2027-04-25 | 2027-04-30 | 2027-04-30
UG-05-S01-A080 | AW.PIPE.F2.UG-05.UG-05-S01 | F2 | UG-05 | UG-05-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6 | m | 4 | 5 | UG-05-S01-A070 | 2 | 2 | UG-05-S02-A080 (FS, closure) | 2027-05-25 | 2027-05-30 | 2027-05-30
UG-05-S01-A090 | AW.PIPE.F2.UG-05.UG-05-S01 | F2 | UG-05 | UG-05-S01 | A090 | Surround, joint test and line test | 6 | m | 3 | 4 | UG-05-S01-A080 | 2 | 2 |  | 2027-05-27 | 2027-06-01
UG-05-S01-A100 | AW.PIPE.F2.UG-05.UG-05-S01 | F2 | UG-05 | UG-05-S01 | A100 | Backfill to NG and remove struts | 143.8834 | m3 | 1 | 2 | UG-05-S01-A090 | 2 | 2 | UG-06-S01-A080 (FS, shared trench laid); UG-24-S01-A080 (FS, shared trench laid); UG-24-S02-A080 (FS, shared trench laid) | 2027-07-13 | 2027-07-15 | 2027-07-15
UG-05-S01-A110 | AW.PIPE.F2.UG-05.UG-05-S01 | F2 | UG-05 | UG-05-S01 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-05-S01-A100 | 1 | 2 |  | 2027-07-14 | 2027-07-17
UG-24-S01-A010 | AW.PIPE.F2.UG-24.UG-24-S01 | F2 | UG-24 | UG-24-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, aeration zone piling | 2026-12-01 | 2026-12-01
UG-24-S01-A020 | AW.PIPE.F2.UG-24.UG-24-S01 | F2 | UG-24 | UG-24-S01 | A020 | Set-out, crossing survey and working platform | 123.7455 | m | 2 | 3 | UG-24-S01-A010 |  |  | FS from A010; UG-05-S02-A030 (SS, set-out one package ahead of piling) | 2027-04-12 | 2027-04-15
UG-24-S01-A030 | AW.PIPE.F2.UG-24.UG-24-S01 | F2 | UG-24 | UG-24-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 86 | piles | 9 | 11 | UG-24-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-17 | 2027-04-28 | 2027-04-28 | UG-05-S02-A030
UG-24-S01-A040 | AW.PIPE.F2.UG-24.UG-24-S01 | F2 | UG-24 | UG-24-S01 | A040 | Install sheet piles (shored lengths) | 140 | m wall | 3 | 4 | UG-24-S01-A030 | 4 | 2 |  | 2027-04-21 | 2027-04-30 | 2027-04-30 | UG-05-S02-A040
UG-24-S01-A050 | AW.PIPE.F2.UG-24.UG-24-S01 | F2 | UG-24 | UG-24-S01 | A050 | Install dewatering and draw down | 123.7455 | m | 11 | 13 | UG-24-S01-A040 | 2 | 2 | UG-05-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-23 | 2027-05-06
UG-24-S01-A060 | AW.PIPE.F2.UG-24.UG-24-S01 | F2 | UG-24 | UG-24-S01 | A060 | Excavate and strut to formation | 1672.3586 | m3 | 3 | 4 | UG-24-S01-A050 | 11 | 2 | UG-02-S04-A100 (FS, deeper first); UG-02-S05-A100 (FS, deeper first); UG-03-S01-A100 (FS, deeper first); UG-03-S02-A100 (FS, deeper first); UG-03-S03-A100 (FS, deeper first); UG-03-S04-A100 (FS, deeper first); UG-03-S05-A100 (FS, deeper first); UG-04-S01-A100 (FS, deeper first); UG-04-S02-A100 (FS, deeper first); UG-05-S01-A060 (SS, shared trench); UG-05-S02-A060 (SS, shared trench) | 2027-06-22 | 2027-06-26 | 2027-06-26 | UG-05-S02-A060
UG-24-S01-A070 | AW.PIPE.F2.UG-24.UG-24-S01 | F2 | UG-24 | UG-24-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 123.7455 | m | 9 | 11 | UG-24-S01-A060 | 2 | 2 |  | 2027-06-24 | 2027-07-05 | 2027-07-05 | UG-05-S02-A070
UG-24-S01-A080 | AW.PIPE.F2.UG-24.UG-24-S01 | F2 | UG-24 | UG-24-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 123.7455 | m | 8 | 10 | UG-24-S01-A070 | 4 | 2 |  | 2027-06-28 | 2027-07-08 | 2027-07-08 | UG-05-S02-A080
UG-24-S01-A090 | AW.PIPE.F2.UG-24.UG-24-S01 | F2 | UG-24 | UG-24-S01 | A090 | Surround, joint test and line test | 123.7455 | m | 3 | 4 | UG-24-S01-A080 | 3 | 2 |  | 2027-07-01 | 2027-07-10
UG-24-S01-A100 | AW.PIPE.F2.UG-24.UG-24-S01 | F2 | UG-24 | UG-24-S01 | A100 | Backfill to NG and remove struts | 1098.3666 | m3 | 2 | 3 | UG-24-S01-A090 | 2 | 2 | UG-05-S01-A080 (FS, shared trench laid); UG-05-S02-A080 (FS, shared trench laid) | 2027-07-16 | 2027-07-19 | 2027-07-19 | UG-05-S02-A100
UG-24-S01-A110 | AW.PIPE.F2.UG-24.UG-24-S01 | F2 | UG-24 | UG-24-S01 | A110 | Dewatering off, extract sheets, reinstate | 140 | m wall | 4 | 5 | UG-24-S01-A100 | 1 | 2 |  | 2027-07-17 | 2027-07-22
UG-24-S02-A010 | AW.PIPE.F2.UG-24.UG-24-S02 | F2 | UG-24 | UG-24-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-24-S02-A020 | AW.PIPE.F2.UG-24.UG-24-S02 | F2 | UG-24 | UG-24-S02 | A020 | Set-out, crossing survey and working platform | 3.0856 | m | 1 | 2 | UG-24-S02-A010 |  |  | FS from A010; UG-24-S01-A030 (SS, tie-in team follows the adjacent run) | 2027-04-17 | 2027-04-19
UG-24-S02-A030 | AW.PIPE.F2.UG-24.UG-24-S02 | F2 | UG-24 | UG-24-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 6 | piles | 1 | 2 | UG-24-S02-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-18 | 2027-04-21 | 2027-04-21
UG-24-S02-A040 | AW.PIPE.F2.UG-24.UG-24-S02 | F2 | UG-24 | UG-24-S02 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-24-S02-A030 | 1 | 0 |  | 2027-04-19 | 2027-04-21 | 0
UG-24-S02-A050 | AW.PIPE.F2.UG-24.UG-24-S02 | F2 | UG-24 | UG-24-S02 | A050 | Install dewatering and draw down | 3.0856 | m | 8 | 10 | UG-24-S02-A040 | 0 | 2 |  | 2027-04-19 | 2027-04-29
UG-24-S02-A060 | AW.PIPE.F2.UG-24.UG-24-S02 | F2 | UG-24 | UG-24-S02 | A060 | Excavate and strut to formation | 61.972 | m3 | 1 | 2 | UG-24-S02-A050 | 10 | 2 | UG-04-S02-A100 (FS, deeper first); UG-05-S01-A060 (SS, shared trench); UG-05-S02-A060 (SS, shared trench) | 2027-05-26 | 2027-05-28 | 2027-05-28
UG-24-S02-A070 | AW.PIPE.F2.UG-24.UG-24-S02 | F2 | UG-24 | UG-24-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 3.0856 | m | 4 | 5 | UG-24-S02-A060 | 1 | 2 |  | 2027-05-27 | 2027-06-01 | 2027-06-01
UG-24-S02-A080 | AW.PIPE.F2.UG-24.UG-24-S02 | F2 | UG-24 | UG-24-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 3.0856 | m | 4 | 5 | UG-24-S02-A070 | 2 | 2 | UG-24-S01-A080 (FS, closure) | 2027-07-08 | 2027-07-13 | 2027-07-13
UG-24-S02-A090 | AW.PIPE.F2.UG-24.UG-24-S02 | F2 | UG-24 | UG-24-S02 | A090 | Surround, joint test and line test | 3.0856 | m | 3 | 4 | UG-24-S02-A080 | 2 | 2 |  | 2027-07-10 | 2027-07-15
UG-24-S02-A100 | AW.PIPE.F2.UG-24.UG-24-S02 | F2 | UG-24 | UG-24-S02 | A100 | Backfill to NG and remove struts | 46.8561 | m3 | 1 | 2 | UG-24-S02-A090 | 2 | 2 | UG-05-S01-A080 (FS, shared trench laid); UG-05-S02-A080 (FS, shared trench laid) | 2027-07-12 | 2027-07-17 | 2027-07-17
UG-24-S02-A110 | AW.PIPE.F2.UG-24.UG-24-S02 | F2 | UG-24 | UG-24-S02 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-24-S02-A100 | 1 | 2 |  | 2027-07-13 | 2027-07-19
UG-10-S04-A010 | AW.PIPE.F3.UG-10.UG-10-S04 | F3 | UG-10 | UG-10-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-10-S04-A020 | AW.PIPE.F3.UG-10.UG-10-S04 | F3 | UG-10 | UG-10-S04 | A020 | Set-out, crossing survey and working platform | 53.199 | m | 1 | 2 | UG-10-S04-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-10-S04-A030 | AW.PIPE.F3.UG-10.UG-10-S04 | F3 | UG-10 | UG-10-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 38 | piles | 8 | 10 | UG-10-S04-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-12 | 2026-12-12
UG-10-S04-A040 | AW.PIPE.F3.UG-10.UG-10-S04 | F3 | UG-10 | UG-10-S04 | A040 | Install sheet piles (shored lengths) | 106.398 | m wall | 5 | 6 | UG-10-S04-A030 | 3 | 2 |  | 2026-12-05 | 2026-12-14 | 2026-12-14
UG-10-S04-A050 | AW.PIPE.F3.UG-10.UG-10-S04 | F3 | UG-10 | UG-10-S04 | A050 | Install dewatering and draw down | 53.199 | m | 9 | 11 | UG-10-S04-A040 | 2 | 2 |  | 2026-12-07 | 2026-12-18
UG-10-S04-A060 | AW.PIPE.F3.UG-10.UG-10-S04 | F3 | UG-10 | UG-10-S04 | A060 | Excavate and strut to formation | 1038.8937 | m3 | 5 | 6 | UG-10-S04-A050 | 10 | 2 | UG-15-S02-A100 (FS, deeper first) | 2027-01-25 | 2027-01-31 | 2027-01-31
UG-10-S04-A070 | AW.PIPE.F3.UG-10.UG-10-S04 | F3 | UG-10 | UG-10-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 53.199 | m | 8 | 10 | UG-10-S04-A060 | 2 | 2 |  | 2027-01-27 | 2027-02-06 | 2027-02-06
UG-10-S04-A080 | AW.PIPE.F3.UG-10.UG-10-S04 | F3 | UG-10 | UG-10-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 53.199 | m | 4 | 5 | UG-10-S04-A070 | 3 | 2 |  | 2027-01-30 | 2027-02-08 | 2027-02-08
UG-10-S04-A090 | AW.PIPE.F3.UG-10.UG-10-S04 | F3 | UG-10 | UG-10-S04 | A090 | Surround, joint test and line test | 53.199 | m | 3 | 4 | UG-10-S04-A080 | 2 | 2 |  | 2027-02-01 | 2027-02-10
UG-10-S04-A100 | AW.PIPE.F3.UG-10.UG-10-S04 | F3 | UG-10 | UG-10-S04 | A100 | Backfill to NG and remove struts | 638.4 | m3 | 2 | 3 | UG-10-S04-A090 | 2 | 2 |  | 2027-02-03 | 2027-02-12 | 2027-02-12
UG-10-S04-A110 | AW.PIPE.F3.UG-10.UG-10-S04 | F3 | UG-10 | UG-10-S04 | A110 | Dewatering off, extract sheets, reinstate | 106.398 | m wall | 4 | 5 | UG-10-S04-A100 | 1 | 2 |  | 2027-02-04 | 2027-02-14
UG-10-S05-A010 | AW.PIPE.F3.UG-10.UG-10-S05 | F3 | UG-10 | UG-10-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-10-S05-A020 | AW.PIPE.F3.UG-10.UG-10-S05 | F3 | UG-10 | UG-10-S05 | A020 | Set-out, crossing survey and working platform | 5.9997 | m | 1 | 2 | UG-10-S05-A010 |  |  | FS from A010; UG-10-S04-A030 (SS, tie-in team follows the adjacent run) | 2026-12-02 | 2026-12-04
UG-10-S05-A030 | AW.PIPE.F3.UG-10.UG-10-S05 | F3 | UG-10 | UG-10-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 6 | piles | 2 | 3 | UG-10-S05-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-03 | 2026-12-06 | 2026-12-06
UG-10-S05-A040 | AW.PIPE.F3.UG-10.UG-10-S05 | F3 | UG-10 | UG-10-S05 | A040 | Install sheet piles (shored lengths) | 11.9995 | m wall | 1 | 2 | UG-10-S05-A030 | 1 | 2 |  | 2026-12-04 | 2026-12-08 | 2026-12-08
UG-10-S05-A050 | AW.PIPE.F3.UG-10.UG-10-S05 | F3 | UG-10 | UG-10-S05 | A050 | Install dewatering and draw down | 5.9997 | m | 8 | 10 | UG-10-S05-A040 | 1 | 2 |  | 2026-12-05 | 2026-12-15
UG-10-S05-A060 | AW.PIPE.F3.UG-10.UG-10-S05 | F3 | UG-10 | UG-10-S05 | A060 | Excavate and strut to formation | 121.1373 | m3 | 1 | 2 | UG-10-S05-A050 | 10 | 2 |  | 2026-12-15 | 2026-12-17 | 2026-12-17
UG-10-S05-A070 | AW.PIPE.F3.UG-10.UG-10-S05 | F3 | UG-10 | UG-10-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 5.9997 | m | 4 | 5 | UG-10-S05-A060 | 1 | 2 |  | 2026-12-16 | 2026-12-21 | 2026-12-21
UG-10-S05-A080 | AW.PIPE.F3.UG-10.UG-10-S05 | F3 | UG-10 | UG-10-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 5.9997 | m | 4 | 5 | UG-10-S05-A070 | 2 | 2 | UG-10-S04-A080 (FS, closure) | 2027-02-08 | 2027-02-13 | 2027-02-13
UG-10-S05-A090 | AW.PIPE.F3.UG-10.UG-10-S05 | F3 | UG-10 | UG-10-S05 | A090 | Surround, joint test and line test | 5.9997 | m | 3 | 4 | UG-10-S05-A080 | 2 | 2 |  | 2027-02-10 | 2027-02-15
UG-10-S05-A100 | AW.PIPE.F3.UG-10.UG-10-S05 | F3 | UG-10 | UG-10-S05 | A100 | Backfill to NG and remove struts | 75.97 | m3 | 1 | 2 | UG-10-S05-A090 | 2 | 2 |  | 2027-02-12 | 2027-02-17 | 2027-02-17
UG-10-S05-A110 | AW.PIPE.F3.UG-10.UG-10-S05 | F3 | UG-10 | UG-10-S05 | A110 | Dewatering off, extract sheets, reinstate | 11.9995 | m wall | 2 | 3 | UG-10-S05-A100 | 1 | 2 |  | 2027-02-13 | 2027-02-19
UG-10-S03-A010 | AW.PIPE.F3.UG-10.UG-10-S03 | F3 | UG-10 | UG-10-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-10-S03-A020 | AW.PIPE.F3.UG-10.UG-10-S03 | F3 | UG-10 | UG-10-S03 | A020 | Set-out, crossing survey and working platform | 32.1 | m | 1 | 2 | UG-10-S03-A010 |  |  | FS from A010; UG-10-S04-A030 (SS, set-out one package ahead of piling) | 2026-12-02 | 2026-12-04
UG-10-S03-A030 | AW.PIPE.F3.UG-10.UG-10-S03 | F3 | UG-10 | UG-10-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 24 | piles | 5 | 6 | UG-10-S03-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-12 | 2026-12-18 | 2026-12-18 | UG-10-S04-A030
UG-10-S03-A040 | AW.PIPE.F3.UG-10.UG-10-S03 | F3 | UG-10 | UG-10-S03 | A040 | Install sheet piles (shored lengths) | 31.4 | m wall | 2 | 3 | UG-10-S03-A030 | 2 | 2 |  | 2026-12-14 | 2026-12-20 | 2026-12-20 | UG-10-S04-A040
UG-10-S03-A050 | AW.PIPE.F3.UG-10.UG-10-S03 | F3 | UG-10 | UG-10-S03 | A050 | Install dewatering and draw down | 32.1 | m | 8 | 10 | UG-10-S03-A040 | 1 | 2 | UG-10-S04-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-21 | 2027-01-31
UG-10-S03-A060 | AW.PIPE.F3.UG-10.UG-10-S03 | F3 | UG-10 | UG-10-S03 | A060 | Excavate and strut to formation | 661.6578 | m3 | 2 | 3 | UG-10-S03-A050 | 10 | 2 | UG-15-S02-A100 (FS, deeper first); UG-15-S03-A100 (FS, deeper first); UG-21-S01-A100 (FS, deeper first); UG-22-S01-A100 (FS, deeper first); UG-28-S02-A100 (FS, deeper first) | 2027-01-31 | 2027-02-03 | 2027-02-03 | UG-10-S04-A060
UG-10-S03-A070 | AW.PIPE.F3.UG-10.UG-10-S03 | F3 | UG-10 | UG-10-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 32.1 | m | 6 | 7 | UG-10-S03-A060 | 1 | 2 |  | 2027-02-06 | 2027-02-13 | 2027-02-13 | UG-10-S04-A070
UG-10-S03-A080 | AW.PIPE.F3.UG-10.UG-10-S03 | F3 | UG-10 | UG-10-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 32.1 | m | 3 | 4 | UG-10-S03-A070 | 3 | 2 |  | 2027-02-09 | 2027-02-15 | 2027-02-15 | UG-10-S04-A080
UG-10-S03-A090 | AW.PIPE.F3.UG-10.UG-10-S03 | F3 | UG-10 | UG-10-S03 | A090 | Surround, joint test and line test | 32.1 | m | 3 | 4 | UG-10-S03-A080 | 2 | 2 |  | 2027-02-11 | 2027-02-17
UG-10-S03-A100 | AW.PIPE.F3.UG-10.UG-10-S03 | F3 | UG-10 | UG-10-S03 | A100 | Backfill to NG and remove struts | 424.2106 | m3 | 2 | 3 | UG-10-S03-A090 | 2 | 2 |  | 2027-02-13 | 2027-02-19 | 2027-02-19 | UG-10-S04-A100
UG-10-S03-A110 | AW.PIPE.F3.UG-10.UG-10-S03 | F3 | UG-10 | UG-10-S03 | A110 | Dewatering off, extract sheets, reinstate | 31.4 | m wall | 2 | 3 | UG-10-S03-A100 | 1 | 2 |  | 2027-02-14 | 2027-02-21
UG-10-S02-A010 | AW.PIPE.F3.UG-10.UG-10-S02 | F3 | UG-10 | UG-10-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, aeration zone piling | 2026-12-01 | 2026-12-01
UG-10-S02-A020 | AW.PIPE.F3.UG-10.UG-10-S02 | F3 | UG-10 | UG-10-S02 | A020 | Set-out, crossing survey and working platform | 106.8559 | m | 2 | 3 | UG-10-S02-A010 |  |  | FS from A010; UG-10-S03-A030 (SS, set-out one package ahead of piling) | 2026-12-12 | 2026-12-15
UG-10-S02-A030 | AW.PIPE.F3.UG-10.UG-10-S02 | F3 | UG-10 | UG-10-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 74 | piles | 15 | 18 | UG-10-S02-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-18 | 2027-01-05 | 2027-01-05 | UG-10-S03-A030
UG-10-S02-A040 | AW.PIPE.F3.UG-10.UG-10-S02 | F3 | UG-10 | UG-10-S02 | A040 | Install sheet piles (shored lengths) | 213.7118 | m wall | 9 | 11 | UG-10-S02-A030 | 6 | 2 |  | 2026-12-24 | 2027-01-07 | 2027-01-07 | UG-10-S03-A040
UG-10-S02-A050 | AW.PIPE.F3.UG-10.UG-10-S02 | F3 | UG-10 | UG-10-S02 | A050 | Install dewatering and draw down | 106.8559 | m | 10 | 12 | UG-10-S02-A040 | 4 | 2 | UG-10-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-22 | 2027-02-03
UG-10-S02-A060 | AW.PIPE.F3.UG-10.UG-10-S02 | F3 | UG-10 | UG-10-S02 | A060 | Excavate and strut to formation | 1252.6038 | m3 | 6 | 7 | UG-10-S02-A050 | 10 | 2 | UG-21-S01-A100 (FS, deeper first); UG-22-S01-A100 (FS, deeper first); UG-28-S02-A100 (FS, deeper first) | 2027-02-03 | 2027-02-10 | 2027-02-10 | UG-10-S03-A060
UG-10-S02-A070 | AW.PIPE.F3.UG-10.UG-10-S02 | F3 | UG-10 | UG-10-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 106.8559 | m | 12 | 14 | UG-10-S02-A060 | 3 | 2 |  | 2027-02-13 | 2027-02-27 | 2027-02-27 | UG-10-S03-A070
UG-10-S02-A080 | AW.PIPE.F3.UG-10.UG-10-S02 | F3 | UG-10 | UG-10-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 106.8559 | m | 7 | 9 | UG-10-S02-A070 | 5 | 2 |  | 2027-02-18 | 2027-03-01 | 2027-03-01 | UG-10-S03-A080
UG-10-S02-A090 | AW.PIPE.F3.UG-10.UG-10-S02 | F3 | UG-10 | UG-10-S02 | A090 | Surround, joint test and line test | 106.8559 | m | 3 | 4 | UG-10-S02-A080 | 3 | 2 |  | 2027-02-21 | 2027-03-03
UG-10-S02-A100 | AW.PIPE.F3.UG-10.UG-10-S02 | F3 | UG-10 | UG-10-S02 | A100 | Backfill to NG and remove struts | 464.7429 | m3 | 2 | 3 | UG-10-S02-A090 | 2 | 2 |  | 2027-02-23 | 2027-03-05 | 2027-03-05 | UG-10-S03-A100
UG-10-S02-A110 | AW.PIPE.F3.UG-10.UG-10-S02 | F3 | UG-10 | UG-10-S02 | A110 | Dewatering off, extract sheets, reinstate | 213.7118 | m wall | 6 | 7 | UG-10-S02-A100 | 1 | 2 |  | 2027-02-24 | 2027-03-07
UG-10-S01-A010 | AW.PIPE.F3.UG-10.UG-10-S01 | F3 | UG-10 | UG-10-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready, aeration zone piling | 2026-12-01 | 2026-12-01
UG-10-S01-A020 | AW.PIPE.F3.UG-10.UG-10-S01 | F3 | UG-10 | UG-10-S01 | A020 | Set-out, crossing survey and working platform | 7.4441 | m | 1 | 2 | UG-10-S01-A010 |  |  | FS from A010; UG-10-S02-A030 (SS, tie-in team follows the adjacent run) | 2026-12-18 | 2026-12-20
UG-10-S01-A030 | AW.PIPE.F3.UG-10.UG-10-S01 | F3 | UG-10 | UG-10-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 8 | piles | 2 | 3 | UG-10-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-19 | 2026-12-22 | 2026-12-22
UG-10-S01-A040 | AW.PIPE.F3.UG-10.UG-10-S01 | F3 | UG-10 | UG-10-S01 | A040 | Install sheet piles (shored lengths) | 10.4 | m wall | 1 | 2 | UG-10-S01-A030 | 1 | 2 |  | 2026-12-20 | 2026-12-24 | 2026-12-24
UG-10-S01-A050 | AW.PIPE.F3.UG-10.UG-10-S01 | F3 | UG-10 | UG-10-S01 | A050 | Install dewatering and draw down | 7.4441 | m | 8 | 10 | UG-10-S01-A040 | 1 | 2 |  | 2026-12-21 | 2026-12-31
UG-10-S01-A060 | AW.PIPE.F3.UG-10.UG-10-S01 | F3 | UG-10 | UG-10-S01 | A060 | Excavate and strut to formation | 114.4867 | m3 | 1 | 2 | UG-10-S01-A050 | 10 | 2 |  | 2026-12-31 | 2027-01-02 | 2027-01-02
UG-10-S01-A070 | AW.PIPE.F3.UG-10.UG-10-S01 | F3 | UG-10 | UG-10-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 7.4441 | m | 4 | 5 | UG-10-S01-A060 | 1 | 2 |  | 2027-01-01 | 2027-01-06 | 2027-01-06
UG-10-S01-A080 | AW.PIPE.F3.UG-10.UG-10-S01 | F3 | UG-10 | UG-10-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 7.4441 | m | 5 | 6 | UG-10-S01-A070 | 2 | 2 | UG-10-S02-A080 (FS, closure) | 2027-03-01 | 2027-03-07 | 2027-03-07
UG-10-S01-A090 | AW.PIPE.F3.UG-10.UG-10-S01 | F3 | UG-10 | UG-10-S01 | A090 | Surround, joint test and line test | 7.4441 | m | 3 | 4 | UG-10-S01-A080 | 2 | 2 |  | 2027-03-03 | 2027-03-09
UG-10-S01-A100 | AW.PIPE.F3.UG-10.UG-10-S01 | F3 | UG-10 | UG-10-S01 | A100 | Backfill to NG and remove struts | 58.8494 | m3 | 1 | 2 | UG-10-S01-A090 | 2 | 2 |  | 2027-03-05 | 2027-03-11 | 2027-03-11
UG-10-S01-A110 | AW.PIPE.F3.UG-10.UG-10-S01 | F3 | UG-10 | UG-10-S01 | A110 | Dewatering off, extract sheets, reinstate | 10.4 | m wall | 2 | 3 | UG-10-S01-A100 | 1 | 2 |  | 2027-03-06 | 2027-03-13
UG-08-S06-A010 | AW.PIPE.F3.UG-08.UG-08-S06 | F3 | UG-08 | UG-08-S06 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-08-S06-A020 | AW.PIPE.F3.UG-08.UG-08-S06 | F3 | UG-08 | UG-08-S06 | A020 | Set-out, crossing survey and working platform | 53.014 | m | 1 | 2 | UG-08-S06-A010 |  |  | FS from A010; UG-10-S02-A030 (SS, set-out one package ahead of piling) | 2026-12-18 | 2026-12-20
UG-08-S06-A030 | AW.PIPE.F3.UG-08.UG-08-S06 | F3 | UG-08 | UG-08-S06 | A030 | Pipe-support piling from platform (incl. integrity tests) | 38 | piles | 8 | 10 | UG-08-S06-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-05 | 2027-01-15 | 2027-01-15 | UG-10-S02-A030
UG-08-S06-A040 | AW.PIPE.F3.UG-08.UG-08-S06 | F3 | UG-08 | UG-08-S06 | A040 | Install sheet piles (shored lengths) | 106.028 | m wall | 5 | 6 | UG-08-S06-A030 | 3 | 2 |  | 2027-01-08 | 2027-01-17 | 2027-01-17 | UG-10-S02-A040
UG-08-S06-A050 | AW.PIPE.F3.UG-08.UG-08-S06 | F3 | UG-08 | UG-08-S06 | A050 | Install dewatering and draw down | 53.014 | m | 9 | 11 | UG-08-S06-A040 | 2 | 2 | UG-10-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-30 | 2027-02-10
UG-08-S06-A060 | AW.PIPE.F3.UG-08.UG-08-S06 | F3 | UG-08 | UG-08-S06 | A060 | Excavate and strut to formation | 1058.7712 | m3 | 5 | 6 | UG-08-S06-A050 | 10 | 2 |  | 2027-02-10 | 2027-02-16 | 2027-02-16 | UG-10-S02-A060
UG-08-S06-A070 | AW.PIPE.F3.UG-08.UG-08-S06 | F3 | UG-08 | UG-08-S06 | A070 | Trim piles, blinding and piled slab (incl. cure) | 53.014 | m | 8 | 10 | UG-08-S06-A060 | 2 | 2 |  | 2027-02-27 | 2027-03-09 | 2027-03-09 | UG-10-S02-A070
UG-08-S06-A080 | AW.PIPE.F3.UG-08.UG-08-S06 | F3 | UG-08 | UG-08-S06 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 53.014 | m | 3 | 4 | UG-08-S06-A070 | 3 | 2 |  | 2027-03-02 | 2027-03-11 | 2027-03-11 | UG-10-S02-A080
UG-08-S06-A090 | AW.PIPE.F3.UG-08.UG-08-S06 | F3 | UG-08 | UG-08-S06 | A090 | Surround, joint test and line test | 53.014 | m | 3 | 4 | UG-08-S06-A080 | 2 | 2 |  | 2027-03-04 | 2027-03-13
UG-08-S06-A100 | AW.PIPE.F3.UG-08.UG-08-S06 | F3 | UG-08 | UG-08-S06 | A100 | Backfill to NG and remove struts | 667.892 | m3 | 2 | 3 | UG-08-S06-A090 | 2 | 2 | UG-09-S06-A080 (FS, shared trench laid) | 2027-05-21 | 2027-05-24 | 2027-05-24 | UG-10-S02-A100
UG-08-S06-A110 | AW.PIPE.F3.UG-08.UG-08-S06 | F3 | UG-08 | UG-08-S06 | A110 | Dewatering off, extract sheets, reinstate | 106.028 | m wall | 4 | 5 | UG-08-S06-A100 | 1 | 2 |  | 2027-05-22 | 2027-05-27
UG-09-S07-A010 | AW.PIPE.F3.UG-09.UG-09-S07 | F3 | UG-09 | UG-09-S07 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-09-S07-A020 | AW.PIPE.F3.UG-09.UG-09-S07 | F3 | UG-09 | UG-09-S07 | A020 | Set-out, crossing survey and working platform | 51.1819 | m | 1 | 2 | UG-09-S07-A010 |  |  | FS from A010; UG-08-S06-A030 (SS, set-out one package ahead of piling) | 2027-01-05 | 2027-01-07
UG-09-S07-A030 | AW.PIPE.F3.UG-09.UG-09-S07 | F3 | UG-09 | UG-09-S07 | A030 | Pipe-support piling from platform (incl. integrity tests) | 38 | piles | 8 | 10 | UG-09-S07-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-15 | 2027-01-25 | 2027-01-25 | UG-08-S06-A030
UG-09-S07-A040 | AW.PIPE.F3.UG-09.UG-09-S07 | F3 | UG-09 | UG-09-S07 | A040 | Install sheet piles (shored lengths) | 102.3637 | m wall | 5 | 6 | UG-09-S07-A030 | 3 | 2 |  | 2027-01-18 | 2027-01-27 | 2027-01-27 | UG-08-S06-A040
UG-09-S07-A050 | AW.PIPE.F3.UG-09.UG-09-S07 | F3 | UG-09 | UG-09-S07 | A050 | Install dewatering and draw down | 51.1819 | m | 9 | 11 | UG-09-S07-A040 | 2 | 2 | UG-08-S06-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-02-05 | 2027-02-16
UG-09-S07-A060 | AW.PIPE.F3.UG-09.UG-09-S07 | F3 | UG-09 | UG-09-S07 | A060 | Excavate and strut to formation | 1019.7951 | m3 | 5 | 6 | UG-09-S07-A050 | 10 | 2 |  | 2027-02-16 | 2027-02-22 | 2027-02-22 | UG-08-S06-A060
UG-09-S07-A070 | AW.PIPE.F3.UG-09.UG-09-S07 | F3 | UG-09 | UG-09-S07 | A070 | Trim piles, blinding and piled slab (incl. cure) | 51.1819 | m | 8 | 10 | UG-09-S07-A060 | 2 | 2 |  | 2027-03-09 | 2027-03-19 | 2027-03-19 | UG-08-S06-A070
UG-09-S07-A080 | AW.PIPE.F3.UG-09.UG-09-S07 | F3 | UG-09 | UG-09-S07 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 51.1819 | m | 3 | 4 | UG-09-S07-A070 | 3 | 2 |  | 2027-03-12 | 2027-03-21 | 2027-03-21 | UG-08-S06-A080
UG-09-S07-A090 | AW.PIPE.F3.UG-09.UG-09-S07 | F3 | UG-09 | UG-09-S07 | A090 | Surround, joint test and line test | 51.1819 | m | 3 | 4 | UG-09-S07-A080 | 2 | 2 |  | 2027-03-14 | 2027-03-23
UG-09-S07-A100 | AW.PIPE.F3.UG-09.UG-09-S07 | F3 | UG-09 | UG-09-S07 | A100 | Backfill to NG and remove struts | 642.4258 | m3 | 2 | 3 | UG-09-S07-A090 | 2 | 2 | UG-08-S05-A080 (FS, shared trench laid) | 2027-05-24 | 2027-05-27 | 2027-05-27 | UG-08-S06-A100
UG-09-S07-A110 | AW.PIPE.F3.UG-09.UG-09-S07 | F3 | UG-09 | UG-09-S07 | A110 | Dewatering off, extract sheets, reinstate | 102.3637 | m wall | 4 | 5 | UG-09-S07-A100 | 1 | 2 |  | 2027-05-25 | 2027-05-30
UG-08-S05-A010 | AW.PIPE.F3.UG-08.UG-08-S05 | F3 | UG-08 | UG-08-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-08-S05-A020 | AW.PIPE.F3.UG-08.UG-08-S05 | F3 | UG-08 | UG-08-S05 | A020 | Set-out, crossing survey and working platform | 116.1 | m | 2 | 3 | UG-08-S05-A010 |  |  | FS from A010; UG-09-S07-A030 (SS, set-out one package ahead of piling) | 2027-01-15 | 2027-01-18
UG-08-S05-A030 | AW.PIPE.F3.UG-08.UG-08-S05 | F3 | UG-08 | UG-08-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 80 | piles | 16 | 19 | UG-08-S05-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-25 | 2027-02-13 | 2027-02-13 | UG-09-S07-A030
UG-08-S05-A040 | AW.PIPE.F3.UG-08.UG-08-S05 | F3 | UG-08 | UG-08-S05 | A040 | Install sheet piles (shored lengths) | 108.2 | m wall | 5 | 6 | UG-08-S05-A030 | 6 | 2 |  | 2027-01-31 | 2027-02-15 | 2027-02-15 | UG-09-S07-A040
UG-08-S05-A050 | AW.PIPE.F3.UG-08.UG-08-S05 | F3 | UG-08 | UG-08-S05 | A050 | Install dewatering and draw down | 116.1 | m | 10 | 12 | UG-08-S05-A040 | 2 | 2 | UG-09-S07-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-02-10 | 2027-02-22
UG-08-S05-A060 | AW.PIPE.F3.UG-08.UG-08-S05 | F3 | UG-08 | UG-08-S05 | A060 | Excavate and strut to formation | 2361.1595 | m3 | 7 | 9 | UG-08-S05-A050 | 10 | 2 | UG-12-S03-A100 (FS, deeper first); UG-13-S03-A100 (FS, deeper first); UG-13B-S11-A100 (FS, deeper first); UG-09-S07-A060 (SS, shared trench) | 2027-03-13 | 2027-03-22 | 2027-03-22 | UG-09-S07-A060
UG-08-S05-A070 | AW.PIPE.F3.UG-08.UG-08-S05 | F3 | UG-08 | UG-08-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 116.1 | m | 13 | 16 | UG-08-S05-A060 | 3 | 2 |  | 2027-03-19 | 2027-04-04 | 2027-04-04 | UG-09-S07-A070
UG-08-S05-A080 | AW.PIPE.F3.UG-08.UG-08-S05 | F3 | UG-08 | UG-08-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 116.1 | m | 10 | 12 | UG-08-S05-A070 | 5 | 2 |  | 2027-03-24 | 2027-04-06 | 2027-04-06 | UG-09-S07-A080
UG-08-S05-A090 | AW.PIPE.F3.UG-08.UG-08-S05 | F3 | UG-08 | UG-08-S05 | A090 | Surround, joint test and line test | 116.1 | m | 3 | 4 | UG-08-S05-A080 | 4 | 2 |  | 2027-03-28 | 2027-04-08
UG-08-S05-A100 | AW.PIPE.F3.UG-08.UG-08-S05 | F3 | UG-08 | UG-08-S05 | A100 | Backfill to NG and remove struts | 1498.43 | m3 | 5 | 6 | UG-08-S05-A090 | 2 | 2 | UG-09-S04-A080 (FS, shared trench laid); UG-09-S05-A080 (FS, shared trench laid); UG-09-S06-A080 (FS, shared trench laid); UG-09-S07-A080 (FS, shared trench laid) | 2027-06-17 | 2027-06-23 | 2027-06-23 | UG-09-S07-A100
UG-08-S05-A110 | AW.PIPE.F3.UG-08.UG-08-S05 | F3 | UG-08 | UG-08-S05 | A110 | Dewatering off, extract sheets, reinstate | 108.2 | m wall | 4 | 5 | UG-08-S05-A100 | 2 | 2 |  | 2027-06-19 | 2027-06-25
UG-09-S06-A010 | AW.PIPE.F3.UG-09.UG-09-S06 | F3 | UG-09 | UG-09-S06 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-09-S06-A020 | AW.PIPE.F3.UG-09.UG-09-S06 | F3 | UG-09 | UG-09-S06 | A020 | Set-out, crossing survey and working platform | 62.1171 | m | 1 | 2 | UG-09-S06-A010 |  |  | FS from A010; UG-08-S05-A030 (SS, set-out one package ahead of piling) | 2027-01-25 | 2027-01-27
UG-09-S06-A030 | AW.PIPE.F3.UG-09.UG-09-S06 | F3 | UG-09 | UG-09-S06 | A030 | Pipe-support piling from platform (incl. integrity tests) | 44 | piles | 9 | 11 | UG-09-S06-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-13 | 2027-02-24 | 2027-02-24 | UG-08-S05-A030
UG-09-S06-A040 | AW.PIPE.F3.UG-09.UG-09-S06 | F3 | UG-09 | UG-09-S06 | A040 | Install sheet piles (shored lengths) | 121.2343 | m wall | 5 | 6 | UG-09-S06-A030 | 4 | 2 |  | 2027-02-17 | 2027-02-26 | 2027-02-26 | UG-08-S05-A040
UG-09-S06-A050 | AW.PIPE.F3.UG-09.UG-09-S06 | F3 | UG-09 | UG-09-S06 | A050 | Install dewatering and draw down | 62.1171 | m | 9 | 11 | UG-09-S06-A040 | 2 | 2 | UG-08-S05-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-11 | 2027-03-22
UG-09-S06-A060 | AW.PIPE.F3.UG-09.UG-09-S06 | F3 | UG-09 | UG-09-S06 | A060 | Excavate and strut to formation | 1014.7375 | m3 | 4 | 5 | UG-09-S06-A050 | 10 | 2 | UG-13B-S08-A100 (FS, deeper first); UG-08-S05-A060 (SS, shared trench); UG-08-S06-A060 (SS, shared trench) | 2027-05-06 | 2027-05-11 | 2027-05-11 | UG-08-S05-A060
UG-09-S06-A070 | AW.PIPE.F3.UG-09.UG-09-S06 | F3 | UG-09 | UG-09-S06 | A070 | Trim piles, blinding and piled slab (incl. cure) | 62.1171 | m | 9 | 11 | UG-09-S06-A060 | 2 | 2 |  | 2027-05-08 | 2027-05-19 | 2027-05-19 | UG-08-S05-A070
UG-09-S06-A080 | AW.PIPE.F3.UG-09.UG-09-S06 | F3 | UG-09 | UG-09-S06 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 62.1171 | m | 5 | 6 | UG-09-S06-A070 | 4 | 2 |  | 2027-05-12 | 2027-05-21 | 2027-05-21 | UG-08-S05-A080
UG-09-S06-A090 | AW.PIPE.F3.UG-09.UG-09-S06 | F3 | UG-09 | UG-09-S06 | A090 | Surround, joint test and line test | 62.1171 | m | 3 | 4 | UG-09-S06-A080 | 2 | 2 |  | 2027-05-14 | 2027-05-23
UG-09-S06-A100 | AW.PIPE.F3.UG-09.UG-09-S06 | F3 | UG-09 | UG-09-S06 | A100 | Backfill to NG and remove struts | 556.7401 | m3 | 2 | 3 | UG-09-S06-A090 | 2 | 2 | UG-08-S05-A080 (FS, shared trench laid); UG-08-S06-A080 (FS, shared trench laid) | 2027-06-23 | 2027-06-26 | 2027-06-26 | UG-08-S05-A100
UG-09-S06-A110 | AW.PIPE.F3.UG-09.UG-09-S06 | F3 | UG-09 | UG-09-S06 | A110 | Dewatering off, extract sheets, reinstate | 121.2343 | m wall | 4 | 5 | UG-09-S06-A100 | 1 | 2 |  | 2027-06-24 | 2027-06-29
UG-09-S05-A010 | AW.PIPE.F3.UG-09.UG-09-S05 | F3 | UG-09 | UG-09-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-09-S05-A020 | AW.PIPE.F3.UG-09.UG-09-S05 | F3 | UG-09 | UG-09-S05 | A020 | Set-out, crossing survey and working platform | 18.1 | m | 1 | 2 | UG-09-S05-A010 |  |  | FS from A010; UG-09-S06-A030 (SS, set-out one package ahead of piling) | 2027-02-13 | 2027-02-15
UG-09-S05-A030 | AW.PIPE.F3.UG-09.UG-09-S05 | F3 | UG-09 | UG-09-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 16 | piles | 4 | 5 | UG-09-S05-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-24 | 2027-03-01 | 2027-03-01 | UG-09-S06-A030
UG-09-S05-A040 | AW.PIPE.F3.UG-09.UG-09-S05 | F3 | UG-09 | UG-09-S05 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-09-S05-A030 | 2 | 0 |  | 2027-02-26 | 2027-03-01 | 2027-02-26 | UG-09-S06-A040
UG-09-S05-A050 | AW.PIPE.F3.UG-09.UG-09-S05 | F3 | UG-09 | UG-09-S05 | A050 | Install dewatering and draw down | 18.1 | m | 8 | 10 | UG-09-S05-A040 | 0 | 2 | UG-09-S06-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-05-01 | 2027-05-11
UG-09-S05-A060 | AW.PIPE.F3.UG-09.UG-09-S05 | F3 | UG-09 | UG-09-S05 | A060 | Excavate and strut to formation | 430.3442 | m3 | 1 | 2 | UG-09-S05-A050 | 10 | 2 | UG-12-S03-A100 (FS, deeper first); UG-13B-S07-A100 (FS, deeper first); UG-13B-S08-A100 (FS, deeper first); UG-13B-S09-A100 (FS, deeper first); UG-13B-S11-A100 (FS, deeper first); UG-08-S05-A060 (SS, shared trench) | 2027-05-11 | 2027-05-13 | 2027-05-13 | UG-09-S06-A060
UG-09-S05-A070 | AW.PIPE.F3.UG-09.UG-09-S05 | F3 | UG-09 | UG-09-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 18.1 | m | 5 | 6 | UG-09-S05-A060 | 1 | 2 |  | 2027-05-19 | 2027-05-25 | 2027-05-25 | UG-09-S06-A070
UG-09-S05-A080 | AW.PIPE.F3.UG-09.UG-09-S05 | F3 | UG-09 | UG-09-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 18.1 | m | 4 | 5 | UG-09-S05-A070 | 2 | 2 |  | 2027-05-21 | 2027-05-27 | 2027-05-27 | UG-09-S06-A080
UG-09-S05-A090 | AW.PIPE.F3.UG-09.UG-09-S05 | F3 | UG-09 | UG-09-S05 | A090 | Surround, joint test and line test | 18.1 | m | 3 | 4 | UG-09-S05-A080 | 2 | 2 |  | 2027-05-23 | 2027-05-29
UG-09-S05-A100 | AW.PIPE.F3.UG-09.UG-09-S05 | F3 | UG-09 | UG-09-S05 | A100 | Backfill to NG and remove struts | 296.4645 | m3 | 1 | 2 | UG-09-S05-A090 | 2 | 2 | UG-08-S05-A080 (FS, shared trench laid) | 2027-06-26 | 2027-06-28 | 2027-06-28 | UG-09-S06-A100
UG-09-S05-A110 | AW.PIPE.F3.UG-09.UG-09-S05 | F3 | UG-09 | UG-09-S05 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-09-S05-A100 | 1 | 2 |  | 2027-06-27 | 2027-06-30
UG-08-S04-A010 | AW.PIPE.F3.UG-08.UG-08-S04 | F3 | UG-08 | UG-08-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-08-S04-A020 | AW.PIPE.F3.UG-08.UG-08-S04 | F3 | UG-08 | UG-08-S04 | A020 | Set-out, crossing survey and working platform | 48 | m | 1 | 2 | UG-08-S04-A010 |  |  | FS from A010; UG-09-S05-A030 (SS, set-out one package ahead of piling) | 2027-02-24 | 2027-02-26
UG-08-S04-A030 | AW.PIPE.F3.UG-08.UG-08-S04 | F3 | UG-08 | UG-08-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 34 | piles | 7 | 9 | UG-08-S04-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-01 | 2027-03-10 | 2027-03-10 | UG-09-S05-A030
UG-08-S04-A040 | AW.PIPE.F3.UG-08.UG-08-S04 | F3 | UG-08 | UG-08-S04 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-08-S04-A030 | 3 | 0 |  | 2027-03-04 | 2027-03-10 | 2027-02-26 | UG-09-S05-A040
UG-08-S04-A050 | AW.PIPE.F3.UG-08.UG-08-S04 | F3 | UG-08 | UG-08-S04 | A050 | Install dewatering and draw down | 48 | m | 9 | 11 | UG-08-S04-A040 | 0 | 2 | UG-09-S05-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-05-02 | 2027-05-13
UG-08-S04-A060 | AW.PIPE.F3.UG-08.UG-08-S04 | F3 | UG-08 | UG-08-S04 | A060 | Excavate and strut to formation | 1129.8708 | m3 | 3 | 4 | UG-08-S04-A050 | 10 | 2 | UG-11-S03-A100 (FS, deeper first); UG-11-S04-A100 (FS, deeper first); UG-13-S05-A100 (FS, deeper first); UG-23-S02-A100 (FS, deeper first); UG-23-S03-A100 (FS, deeper first); UG-23-S04-A100 (FS, deeper first) | 2027-05-13 | 2027-05-17 | 2027-05-17 | UG-09-S05-A060
UG-08-S04-A070 | AW.PIPE.F3.UG-08.UG-08-S04 | F3 | UG-08 | UG-08-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 48 | m | 7 | 9 | UG-08-S04-A060 | 2 | 2 |  | 2027-05-25 | 2027-06-03 | 2027-06-03 | UG-09-S05-A070
UG-08-S04-A080 | AW.PIPE.F3.UG-08.UG-08-S04 | F3 | UG-08 | UG-08-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 48 | m | 4 | 5 | UG-08-S04-A070 | 3 | 2 |  | 2027-05-28 | 2027-06-05 | 2027-06-05 | UG-09-S05-A080
UG-08-S04-A090 | AW.PIPE.F3.UG-08.UG-08-S04 | F3 | UG-08 | UG-08-S04 | A090 | Surround, joint test and line test | 48 | m | 3 | 4 | UG-08-S04-A080 | 2 | 2 |  | 2027-05-30 | 2027-06-07
UG-08-S04-A100 | AW.PIPE.F3.UG-08.UG-08-S04 | F3 | UG-08 | UG-08-S04 | A100 | Backfill to NG and remove struts | 768.5168 | m3 | 3 | 4 | UG-08-S04-A090 | 2 | 2 | UG-09-S03-A080 (FS, shared trench laid); UG-09-S04-A080 (FS, shared trench laid) | 2027-07-05 | 2027-07-09 | 2027-07-09 | UG-09-S05-A100
UG-08-S04-A110 | AW.PIPE.F3.UG-08.UG-08-S04 | F3 | UG-08 | UG-08-S04 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-08-S04-A100 | 2 | 2 |  | 2027-07-07 | 2027-07-11
UG-09-S04-A010 | AW.PIPE.F3.UG-09.UG-09-S04 | F3 | UG-09 | UG-09-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-09-S04-A020 | AW.PIPE.F3.UG-09.UG-09-S04 | F3 | UG-09 | UG-09-S04 | A020 | Set-out, crossing survey and working platform | 83.2 | m | 2 | 3 | UG-09-S04-A010 |  |  | FS from A010; UG-08-S04-A030 (SS, set-out one package ahead of piling) | 2027-03-01 | 2027-03-04
UG-09-S04-A030 | AW.PIPE.F3.UG-09.UG-09-S04 | F3 | UG-09 | UG-09-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 58 | piles | 12 | 14 | UG-09-S04-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-10 | 2027-03-24 | 2027-03-24 | UG-08-S04-A030
UG-09-S04-A040 | AW.PIPE.F3.UG-09.UG-09-S04 | F3 | UG-09 | UG-09-S04 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-09-S04-A030 | 5 | 0 |  | 2027-03-15 | 2027-03-24 | 2027-02-26 | UG-08-S04-A040
UG-09-S04-A050 | AW.PIPE.F3.UG-09.UG-09-S04 | F3 | UG-09 | UG-09-S04 | A050 | Install dewatering and draw down | 83.2 | m | 10 | 12 | UG-09-S04-A040 | 0 | 2 | UG-08-S04-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-05-05 | 2027-05-17
UG-09-S04-A060 | AW.PIPE.F3.UG-09.UG-09-S04 | F3 | UG-09 | UG-09-S04 | A060 | Excavate and strut to formation | 1958.308 | m3 | 5 | 6 | UG-09-S04-A050 | 10 | 2 | UG-12-S03-A100 (FS, deeper first); UG-13B-S07-A100 (FS, deeper first); UG-13B-S08-A100 (FS, deeper first); UG-13B-S11-A100 (FS, deeper first); UG-23-S03-A100 (FS, deeper first); UG-23-S04-A100 (FS, deeper first); UG-08-S04-A060 (SS, shared trench); UG-08-S05-A060 (SS, shared trench) | 2027-05-17 | 2027-05-23 | 2027-05-23 | UG-08-S04-A060
UG-09-S04-A070 | AW.PIPE.F3.UG-09.UG-09-S04 | F3 | UG-09 | UG-09-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 83.2 | m | 10 | 12 | UG-09-S04-A060 | 2 | 2 |  | 2027-06-03 | 2027-06-15 | 2027-06-15 | UG-08-S04-A070
UG-09-S04-A080 | AW.PIPE.F3.UG-09.UG-09-S04 | F3 | UG-09 | UG-09-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 83.2 | m | 7 | 9 | UG-09-S04-A070 | 4 | 2 |  | 2027-06-07 | 2027-06-17 | 2027-06-17 | UG-08-S04-A080
UG-09-S04-A090 | AW.PIPE.F3.UG-09.UG-09-S04 | F3 | UG-09 | UG-09-S04 | A090 | Surround, joint test and line test | 83.2 | m | 3 | 4 | UG-09-S04-A080 | 3 | 2 |  | 2027-06-10 | 2027-06-19
UG-09-S04-A100 | AW.PIPE.F3.UG-09.UG-09-S04 | F3 | UG-09 | UG-09-S04 | A100 | Backfill to NG and remove struts | 1332.0262 | m3 | 4 | 5 | UG-09-S04-A090 | 2 | 2 | UG-08-S03-A080 (FS, shared trench laid); UG-08-S04-A080 (FS, shared trench laid); UG-08-S05-A080 (FS, shared trench laid) | 2027-07-09 | 2027-07-14 | 2027-07-14 | UG-08-S04-A100
UG-09-S04-A110 | AW.PIPE.F3.UG-09.UG-09-S04 | F3 | UG-09 | UG-09-S04 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-09-S04-A100 | 2 | 2 |  | 2027-07-11 | 2027-07-16
UG-08-S03-A010 | AW.PIPE.F3.UG-08.UG-08-S03 | F3 | UG-08 | UG-08-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-08-S03-A020 | AW.PIPE.F3.UG-08.UG-08-S03 | F3 | UG-08 | UG-08-S03 | A020 | Set-out, crossing survey and working platform | 22 | m | 1 | 2 | UG-08-S03-A010 |  |  | FS from A010; UG-09-S04-A030 (SS, set-out one package ahead of piling) | 2027-03-10 | 2027-03-12
UG-08-S03-A030 | AW.PIPE.F3.UG-08.UG-08-S03 | F3 | UG-08 | UG-08-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 18 | piles | 4 | 5 | UG-08-S03-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-24 | 2027-03-29 | 2027-03-29 | UG-09-S04-A030
UG-08-S03-A040 | AW.PIPE.F3.UG-08.UG-08-S03 | F3 | UG-08 | UG-08-S03 | A040 | Install sheet piles (shored lengths) | 37.8161 | m wall | 2 | 3 | UG-08-S03-A030 | 2 | 2 |  | 2027-03-26 | 2027-03-31 | 2027-03-31 | UG-09-S04-A040
UG-08-S03-A050 | AW.PIPE.F3.UG-08.UG-08-S03 | F3 | UG-08 | UG-08-S03 | A050 | Install dewatering and draw down | 22 | m | 8 | 10 | UG-08-S03-A040 | 1 | 2 | UG-09-S04-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-05-13 | 2027-05-23
UG-08-S03-A060 | AW.PIPE.F3.UG-08.UG-08-S03 | F3 | UG-08 | UG-08-S03 | A060 | Excavate and strut to formation | 288.4285 | m3 | 2 | 3 | UG-08-S03-A050 | 10 | 2 | UG-11-S03-A100 (FS, deeper first); UG-11-S04-A100 (FS, deeper first); UG-23-S03-A100 (FS, deeper first); UG-23-S04-A100 (FS, deeper first); UG-23-S05-A100 (FS, deeper first); UG-09-S04-A060 (SS, shared trench) | 2027-05-23 | 2027-05-26 | 2027-05-26 | UG-09-S04-A060
UG-08-S03-A070 | AW.PIPE.F3.UG-08.UG-08-S03 | F3 | UG-08 | UG-08-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 22 | m | 5 | 6 | UG-08-S03-A060 | 1 | 2 |  | 2027-06-15 | 2027-06-21 | 2027-06-21 | UG-09-S04-A070
UG-08-S03-A080 | AW.PIPE.F3.UG-08.UG-08-S03 | F3 | UG-08 | UG-08-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 22 | m | 3 | 4 | UG-08-S03-A070 | 2 | 2 |  | 2027-06-17 | 2027-06-23 | 2027-06-23 | UG-09-S04-A080
UG-08-S03-A090 | AW.PIPE.F3.UG-08.UG-08-S03 | F3 | UG-08 | UG-08-S03 | A090 | Surround, joint test and line test | 22 | m | 3 | 4 | UG-08-S03-A080 | 2 | 2 |  | 2027-06-19 | 2027-06-25
UG-08-S03-A100 | AW.PIPE.F3.UG-08.UG-08-S03 | F3 | UG-08 | UG-08-S03 | A100 | Backfill to NG and remove struts | 126.1435 | m3 | 1 | 2 | UG-08-S03-A090 | 2 | 2 | UG-09-S02-A080 (FS, shared trench laid); UG-09-S03-A080 (FS, shared trench laid); UG-09-S04-A080 (FS, shared trench laid) | 2027-07-14 | 2027-07-16 | 2027-07-16 | UG-09-S04-A100
UG-08-S03-A110 | AW.PIPE.F3.UG-08.UG-08-S03 | F3 | UG-08 | UG-08-S03 | A110 | Dewatering off, extract sheets, reinstate | 37.8161 | m wall | 2 | 3 | UG-08-S03-A100 | 1 | 2 |  | 2027-07-15 | 2027-07-18
UG-08-S02-A010 | AW.PIPE.F3.UG-08.UG-08-S02 | F3 | UG-08 | UG-08-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-08-S02-A020 | AW.PIPE.F3.UG-08.UG-08-S02 | F3 | UG-08 | UG-08-S02 | A020 | Set-out, crossing survey and working platform | 17.4789 | m | 1 | 2 | UG-08-S02-A010 |  |  | FS from A010; UG-08-S03-A030 (SS, set-out one package ahead of piling) | 2027-03-24 | 2027-03-26
UG-08-S02-A030 | AW.PIPE.F3.UG-08.UG-08-S02 | F3 | UG-08 | UG-08-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 14 | piles | 3 | 4 | UG-08-S02-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-29 | 2027-04-02 | 2027-04-02 | UG-08-S03-A030
UG-08-S02-A040 | AW.PIPE.F3.UG-08.UG-08-S02 | F3 | UG-08 | UG-08-S02 | A040 | Install sheet piles (shored lengths) | 34.9578 | m wall | 2 | 3 | UG-08-S02-A030 | 2 | 2 |  | 2027-03-31 | 2027-04-04 | 2027-04-04 | UG-08-S03-A040
UG-08-S02-A050 | AW.PIPE.F3.UG-08.UG-08-S02 | F3 | UG-08 | UG-08-S02 | A050 | Install dewatering and draw down | 17.4789 | m | 8 | 10 | UG-08-S02-A040 | 1 | 2 | UG-08-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-05-16 | 2027-05-26
UG-08-S02-A060 | AW.PIPE.F3.UG-08.UG-08-S02 | F3 | UG-08 | UG-08-S02 | A060 | Excavate and strut to formation | 200.1199 | m3 | 1 | 2 | UG-08-S02-A050 | 10 | 2 | UG-11-S04-A100 (FS, deeper first); UG-23-S04-A100 (FS, deeper first); UG-23-S05-A100 (FS, deeper first) | 2027-05-26 | 2027-05-28 | 2027-05-28 | UG-08-S03-A060
UG-08-S02-A070 | AW.PIPE.F3.UG-08.UG-08-S02 | F3 | UG-08 | UG-08-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 17.4789 | m | 5 | 6 | UG-08-S02-A060 | 1 | 2 |  | 2027-06-21 | 2027-06-27 | 2027-06-27 | UG-08-S03-A070
UG-08-S02-A080 | AW.PIPE.F3.UG-08.UG-08-S02 | F3 | UG-08 | UG-08-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 17.4789 | m | 1 | 2 | UG-08-S02-A070 | 2 | 2 |  | 2027-06-23 | 2027-06-29 | 2027-06-29 | UG-08-S03-A080
UG-08-S02-A090 | AW.PIPE.F3.UG-08.UG-08-S02 | F3 | UG-08 | UG-08-S02 | A090 | Surround, joint test and line test | 17.4789 | m | 3 | 4 | UG-08-S02-A080 | 1 | 2 |  | 2027-06-24 | 2027-07-01
UG-08-S02-A100 | AW.PIPE.F3.UG-08.UG-08-S02 | F3 | UG-08 | UG-08-S02 | A100 | Backfill to NG and remove struts | 71.2457 | m3 | 1 | 2 | UG-08-S02-A090 | 2 | 2 | UG-09-S01-A080 (FS, shared trench laid); UG-09-S02-A080 (FS, shared trench laid); UG-09-S03-A080 (FS, shared trench laid) | 2027-07-18 | 2027-07-20 | 2027-07-20 | UG-08-S03-A100
UG-08-S02-A110 | AW.PIPE.F3.UG-08.UG-08-S02 | F3 | UG-08 | UG-08-S02 | A110 | Dewatering off, extract sheets, reinstate | 34.9578 | m wall | 2 | 3 | UG-08-S02-A100 | 1 | 2 |  | 2027-07-19 | 2027-07-22
UG-09-S03-A010 | AW.PIPE.F3.UG-09.UG-09-S03 | F3 | UG-09 | UG-09-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-09-S03-A020 | AW.PIPE.F3.UG-09.UG-09-S03 | F3 | UG-09 | UG-09-S03 | A020 | Set-out, crossing survey and working platform | 23.1 | m | 1 | 2 | UG-09-S03-A010 |  |  | FS from A010; UG-08-S02-A030 (SS, set-out one package ahead of piling) | 2027-03-29 | 2027-03-31
UG-09-S03-A030 | AW.PIPE.F3.UG-09.UG-09-S03 | F3 | UG-09 | UG-09-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 18 | piles | 4 | 5 | UG-09-S03-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-02 | 2027-04-07 | 2027-04-07 | UG-08-S02-A030
UG-09-S03-A040 | AW.PIPE.F3.UG-09.UG-09-S03 | F3 | UG-09 | UG-09-S03 | A040 | Install sheet piles (shored lengths) | 11.8 | m wall | 1 | 2 | UG-09-S03-A030 | 2 | 2 |  | 2027-04-04 | 2027-04-09 | 2027-04-09 | UG-08-S02-A040
UG-09-S03-A050 | AW.PIPE.F3.UG-09.UG-09-S03 | F3 | UG-09 | UG-09-S03 | A050 | Install dewatering and draw down | 23.1 | m | 8 | 10 | UG-09-S03-A040 | 1 | 2 | UG-08-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-05-18 | 2027-05-28
UG-09-S03-A060 | AW.PIPE.F3.UG-09.UG-09-S03 | F3 | UG-09 | UG-09-S03 | A060 | Excavate and strut to formation | 466.8938 | m3 | 2 | 3 | UG-09-S03-A050 | 10 | 2 | UG-11-S04-A100 (FS, deeper first); UG-11-S05-A100 (FS, deeper first); UG-23-S03-A100 (FS, deeper first); UG-23-S04-A100 (FS, deeper first); UG-23-S05-A100 (FS, deeper first); UG-08-S02-A060 (SS, shared trench); UG-08-S03-A060 (SS, shared trench); UG-08-S04-A060 (SS, shared trench) | 2027-05-28 | 2027-05-31 | 2027-05-31 | UG-08-S02-A060
UG-09-S03-A070 | AW.PIPE.F3.UG-09.UG-09-S03 | F3 | UG-09 | UG-09-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 23.1 | m | 5 | 6 | UG-09-S03-A060 | 1 | 2 |  | 2027-06-27 | 2027-07-03 | 2027-07-03 | UG-08-S02-A070
UG-09-S03-A080 | AW.PIPE.F3.UG-09.UG-09-S03 | F3 | UG-09 | UG-09-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 23.1 | m | 2 | 3 | UG-09-S03-A070 | 2 | 2 |  | 2027-06-29 | 2027-07-05 | 2027-07-05 | UG-08-S02-A080
UG-09-S03-A090 | AW.PIPE.F3.UG-09.UG-09-S03 | F3 | UG-09 | UG-09-S03 | A090 | Surround, joint test and line test | 23.1 | m | 3 | 4 | UG-09-S03-A080 | 1 | 2 |  | 2027-06-30 | 2027-07-07
UG-09-S03-A100 | AW.PIPE.F3.UG-09.UG-09-S03 | F3 | UG-09 | UG-09-S03 | A100 | Backfill to NG and remove struts | 296.5748 | m3 | 1 | 2 | UG-09-S03-A090 | 2 | 2 | UG-08-S02-A080 (FS, shared trench laid); UG-08-S03-A080 (FS, shared trench laid); UG-08-S04-A080 (FS, shared trench laid) | 2027-07-20 | 2027-07-22 | 2027-07-22 | UG-08-S02-A100
UG-09-S03-A110 | AW.PIPE.F3.UG-09.UG-09-S03 | F3 | UG-09 | UG-09-S03 | A110 | Dewatering off, extract sheets, reinstate | 11.8 | m wall | 2 | 3 | UG-09-S03-A100 | 1 | 2 |  | 2027-07-21 | 2027-07-24
UG-08-S01-A010 | AW.PIPE.F3.UG-08.UG-08-S01 | F3 | UG-08 | UG-08-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-08-S01-A020 | AW.PIPE.F3.UG-08.UG-08-S01 | F3 | UG-08 | UG-08-S01 | A020 | Set-out, crossing survey and working platform | 20.5211 | m | 1 | 2 | UG-08-S01-A010 |  |  | FS from A010; UG-08-S02-A030 (SS, tie-in team follows the adjacent run) | 2027-03-29 | 2027-03-31
UG-08-S01-A030 | AW.PIPE.F3.UG-08.UG-08-S01 | F3 | UG-08 | UG-08-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 16 | piles | 4 | 5 | UG-08-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-30 | 2027-04-04 | 2027-04-04
UG-08-S01-A040 | AW.PIPE.F3.UG-08.UG-08-S01 | F3 | UG-08 | UG-08-S01 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-08-S01-A030 | 2 | 0 |  | 2027-04-01 | 2027-04-04 | 0
UG-08-S01-A050 | AW.PIPE.F3.UG-08.UG-08-S01 | F3 | UG-08 | UG-08-S01 | A050 | Install dewatering and draw down | 20.5211 | m | 8 | 10 | UG-08-S01-A040 | 0 | 2 |  | 2027-04-01 | 2027-04-11
UG-08-S01-A060 | AW.PIPE.F3.UG-08.UG-08-S01 | F3 | UG-08 | UG-08-S01 | A060 | Excavate and strut to formation | 482.2094 | m3 | 2 | 3 | UG-08-S01-A050 | 10 | 2 | UG-23-S05-A100 (FS, deeper first); UG-09-S01-A060 (SS, shared trench) | 2027-05-26 | 2027-05-29 | 2027-05-29
UG-08-S01-A070 | AW.PIPE.F3.UG-08.UG-08-S01 | F3 | UG-08 | UG-08-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 20.5211 | m | 5 | 6 | UG-08-S01-A060 | 1 | 2 |  | 2027-05-27 | 2027-06-02 | 2027-06-02
UG-08-S01-A080 | AW.PIPE.F3.UG-08.UG-08-S01 | F3 | UG-08 | UG-08-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 20.5211 | m | 6 | 7 | UG-08-S01-A070 | 2 | 2 | UG-08-S02-A080 (FS, closure) | 2027-06-29 | 2027-07-06 | 2027-07-06
UG-08-S01-A090 | AW.PIPE.F3.UG-08.UG-08-S01 | F3 | UG-08 | UG-08-S01 | A090 | Surround, joint test and line test | 20.5211 | m | 3 | 4 | UG-08-S01-A080 | 3 | 2 |  | 2027-07-02 | 2027-07-08
UG-08-S01-A100 | AW.PIPE.F3.UG-08.UG-08-S01 | F3 | UG-08 | UG-08-S01 | A100 | Backfill to NG and remove struts | 328.1259 | m3 | 1 | 2 | UG-08-S01-A090 | 2 | 2 | UG-09-S01-A080 (FS, shared trench laid); UG-09-S02-A080 (FS, shared trench laid) | 2027-07-18 | 2027-07-20 | 2027-07-20
UG-08-S01-A110 | AW.PIPE.F3.UG-08.UG-08-S01 | F3 | UG-08 | UG-08-S01 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-08-S01-A100 | 1 | 2 |  | 2027-07-19 | 2027-07-22
UG-09-S02-A010 | AW.PIPE.F3.UG-09.UG-09-S02 | F3 | UG-09 | UG-09-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-09-S02-A020 | AW.PIPE.F3.UG-09.UG-09-S02 | F3 | UG-09 | UG-09-S02 | A020 | Set-out, crossing survey and working platform | 20.2371 | m | 1 | 2 | UG-09-S02-A010 |  |  | FS from A010; UG-09-S03-A030 (SS, set-out one package ahead of piling) | 2027-04-02 | 2027-04-04
UG-09-S02-A030 | AW.PIPE.F3.UG-09.UG-09-S02 | F3 | UG-09 | UG-09-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 16 | piles | 4 | 5 | UG-09-S02-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-07 | 2027-04-12 | 2027-04-12 | UG-09-S03-A030
UG-09-S02-A040 | AW.PIPE.F3.UG-09.UG-09-S02 | F3 | UG-09 | UG-09-S02 | A040 | Install sheet piles (shored lengths) | 28.2 | m wall | 2 | 3 | UG-09-S02-A030 | 2 | 2 |  | 2027-04-09 | 2027-04-14 | 2027-04-14 | UG-09-S03-A040
UG-09-S02-A050 | AW.PIPE.F3.UG-09.UG-09-S02 | F3 | UG-09 | UG-09-S02 | A050 | Install dewatering and draw down | 20.2371 | m | 8 | 10 | UG-09-S02-A040 | 1 | 2 | UG-09-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-05-21 | 2027-05-31
UG-09-S02-A060 | AW.PIPE.F3.UG-09.UG-09-S02 | F3 | UG-09 | UG-09-S02 | A060 | Excavate and strut to formation | 303.9235 | m3 | 1 | 2 | UG-09-S02-A050 | 10 | 2 | UG-23-S04-A100 (FS, deeper first); UG-23-S05-A100 (FS, deeper first); UG-08-S01-A060 (SS, shared trench); UG-08-S02-A060 (SS, shared trench); UG-08-S03-A060 (SS, shared trench) | 2027-05-31 | 2027-06-02 | 2027-06-02 | UG-09-S03-A060
UG-09-S02-A070 | AW.PIPE.F3.UG-09.UG-09-S02 | F3 | UG-09 | UG-09-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 20.2371 | m | 5 | 6 | UG-09-S02-A060 | 1 | 2 |  | 2027-07-03 | 2027-07-09 | 2027-07-09 | UG-09-S03-A070
UG-09-S02-A080 | AW.PIPE.F3.UG-09.UG-09-S02 | F3 | UG-09 | UG-09-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 20.2371 | m | 2 | 3 | UG-09-S02-A070 | 2 | 2 |  | 2027-07-05 | 2027-07-11 | 2027-07-11 | UG-09-S03-A080
UG-09-S02-A090 | AW.PIPE.F3.UG-09.UG-09-S02 | F3 | UG-09 | UG-09-S02 | A090 | Surround, joint test and line test | 20.2371 | m | 3 | 4 | UG-09-S02-A080 | 1 | 2 |  | 2027-07-06 | 2027-07-13
UG-09-S02-A100 | AW.PIPE.F3.UG-09.UG-09-S02 | F3 | UG-09 | UG-09-S02 | A100 | Backfill to NG and remove struts | 154.7128 | m3 | 1 | 2 | UG-09-S02-A090 | 2 | 2 | UG-08-S01-A080 (FS, shared trench laid); UG-08-S02-A080 (FS, shared trench laid); UG-08-S03-A080 (FS, shared trench laid) | 2027-07-22 | 2027-07-24 | 2027-07-24 | UG-09-S03-A100
UG-09-S02-A110 | AW.PIPE.F3.UG-09.UG-09-S02 | F3 | UG-09 | UG-09-S02 | A110 | Dewatering off, extract sheets, reinstate | 28.2 | m wall | 2 | 3 | UG-09-S02-A100 | 1 | 2 |  | 2027-07-23 | 2027-07-26
UG-09-S01-A010 | AW.PIPE.F3.UG-09.UG-09-S01 | F3 | UG-09 | UG-09-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-09-S01-A020 | AW.PIPE.F3.UG-09.UG-09-S01 | F3 | UG-09 | UG-09-S01 | A020 | Set-out, crossing survey and working platform | 23.8629 | m | 1 | 2 | UG-09-S01-A010 |  |  | FS from A010; UG-09-S02-A030 (SS, tie-in team follows the adjacent run) | 2027-04-07 | 2027-04-09
UG-09-S01-A030 | AW.PIPE.F3.UG-09.UG-09-S01 | F3 | UG-09 | UG-09-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 18 | piles | 4 | 5 | UG-09-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-08 | 2027-04-13 | 2027-04-13
UG-09-S01-A040 | AW.PIPE.F3.UG-09.UG-09-S01 | F3 | UG-09 | UG-09-S01 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-09-S01-A030 | 2 | 0 |  | 2027-04-10 | 2027-04-13 | 0
UG-09-S01-A050 | AW.PIPE.F3.UG-09.UG-09-S01 | F3 | UG-09 | UG-09-S01 | A050 | Install dewatering and draw down | 23.8629 | m | 8 | 10 | UG-09-S01-A040 | 0 | 2 |  | 2027-04-10 | 2027-04-20
UG-09-S01-A060 | AW.PIPE.F3.UG-09.UG-09-S01 | F3 | UG-09 | UG-09-S01 | A060 | Excavate and strut to formation | 560.8742 | m3 | 2 | 3 | UG-09-S01-A050 | 10 | 2 | UG-23-S05-A100 (FS, deeper first); UG-08-S02-A060 (SS, shared trench) | 2027-05-26 | 2027-05-29 | 2027-05-29
UG-09-S01-A070 | AW.PIPE.F3.UG-09.UG-09-S01 | F3 | UG-09 | UG-09-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 23.8629 | m | 5 | 6 | UG-09-S01-A060 | 1 | 2 |  | 2027-05-27 | 2027-06-02 | 2027-06-02
UG-09-S01-A080 | AW.PIPE.F3.UG-09.UG-09-S01 | F3 | UG-09 | UG-09-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 23.8629 | m | 6 | 7 | UG-09-S01-A070 | 2 | 2 | UG-09-S02-A080 (FS, closure) | 2027-07-11 | 2027-07-18 | 2027-07-18
UG-09-S01-A090 | AW.PIPE.F3.UG-09.UG-09-S01 | F3 | UG-09 | UG-09-S01 | A090 | Surround, joint test and line test | 23.8629 | m | 3 | 4 | UG-09-S01-A080 | 3 | 2 |  | 2027-07-14 | 2027-07-20
UG-09-S01-A100 | AW.PIPE.F3.UG-09.UG-09-S01 | F3 | UG-09 | UG-09-S01 | A100 | Backfill to NG and remove struts | 381.6318 | m3 | 2 | 3 | UG-09-S01-A090 | 2 | 2 | UG-08-S01-A080 (FS, shared trench laid); UG-08-S02-A080 (FS, shared trench laid) | 2027-07-16 | 2027-07-22 | 2027-07-22
UG-09-S01-A110 | AW.PIPE.F3.UG-09.UG-09-S01 | F3 | UG-09 | UG-09-S01 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-09-S01-A100 | 1 | 2 |  | 2027-07-17 | 2027-07-24
UG-08-S07-A010 | AW.PIPE.F3.UG-08.UG-08-S07 | F3 | UG-08 | UG-08-S07 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-08-S07-A020 | AW.PIPE.F3.UG-08.UG-08-S07 | F3 | UG-08 | UG-08-S07 | A020 | Set-out, crossing survey and working platform | 5.9999 | m | 1 | 2 | UG-08-S07-A010 |  |  | FS from A010; UG-08-S06-A030 (SS, tie-in team follows the adjacent run) | 2027-01-05 | 2027-01-07
UG-08-S07-A030 | AW.PIPE.F3.UG-08.UG-08-S07 | F3 | UG-08 | UG-08-S07 | A030 | Pipe-support piling from platform (incl. integrity tests) | 6 | piles | 2 | 3 | UG-08-S07-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-06 | 2027-01-09 | 2027-01-09
UG-08-S07-A040 | AW.PIPE.F3.UG-08.UG-08-S07 | F3 | UG-08 | UG-08-S07 | A040 | Install sheet piles (shored lengths) | 11.9999 | m wall | 1 | 2 | UG-08-S07-A030 | 1 | 2 |  | 2027-01-07 | 2027-01-11 | 2027-01-11
UG-08-S07-A050 | AW.PIPE.F3.UG-08.UG-08-S07 | F3 | UG-08 | UG-08-S07 | A050 | Install dewatering and draw down | 5.9999 | m | 8 | 10 | UG-08-S07-A040 | 1 | 2 |  | 2027-01-08 | 2027-01-18
UG-08-S07-A060 | AW.PIPE.F3.UG-08.UG-08-S07 | F3 | UG-08 | UG-08-S07 | A060 | Excavate and strut to formation | 119.828 | m3 | 1 | 2 | UG-08-S07-A050 | 10 | 2 |  | 2027-01-18 | 2027-01-20 | 2027-01-20
UG-08-S07-A070 | AW.PIPE.F3.UG-08.UG-08-S07 | F3 | UG-08 | UG-08-S07 | A070 | Trim piles, blinding and piled slab (incl. cure) | 5.9999 | m | 4 | 5 | UG-08-S07-A060 | 1 | 2 |  | 2027-01-19 | 2027-01-24 | 2027-01-24
UG-08-S07-A080 | AW.PIPE.F3.UG-08.UG-08-S07 | F3 | UG-08 | UG-08-S07 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 5.9999 | m | 4 | 5 | UG-08-S07-A070 | 2 | 2 | UG-08-S06-A080 (FS, closure) | 2027-03-11 | 2027-03-16 | 2027-03-16
UG-08-S07-A090 | AW.PIPE.F3.UG-08.UG-08-S07 | F3 | UG-08 | UG-08-S07 | A090 | Surround, joint test and line test | 5.9999 | m | 3 | 4 | UG-08-S07-A080 | 2 | 2 |  | 2027-03-13 | 2027-03-18
UG-08-S07-A100 | AW.PIPE.F3.UG-08.UG-08-S07 | F3 | UG-08 | UG-08-S07 | A100 | Backfill to NG and remove struts | 75.5897 | m3 | 1 | 2 | UG-08-S07-A090 | 2 | 2 |  | 2027-03-15 | 2027-03-20 | 2027-03-20
UG-08-S07-A110 | AW.PIPE.F3.UG-08.UG-08-S07 | F3 | UG-08 | UG-08-S07 | A110 | Dewatering off, extract sheets, reinstate | 11.9999 | m wall | 2 | 3 | UG-08-S07-A100 | 1 | 2 |  | 2027-03-16 | 2027-03-22
UG-13A-S13-A010 | AW.PIPE.F3.UG-13A.UG-13A-S13 | F3 | UG-13A | UG-13A-S13 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-13A-S13-A020 | AW.PIPE.F3.UG-13A.UG-13A-S13 | F3 | UG-13A | UG-13A-S13 | A020 | Set-out, crossing survey and working platform | 30.3665 | m | 1 | 2 | UG-13A-S13-A010 |  |  | FS from A010; UG-13A-S14-A030 (SS, tie-in team follows the adjacent run) | 2027-04-06 | 2027-04-08
UG-13A-S13-A030 | AW.PIPE.F3.UG-13A.UG-13A-S13 | F3 | UG-13A | UG-13A-S13 | A030 | Pipe-support piling from platform (incl. integrity tests) | 12 | piles | 3 | 4 | UG-13A-S13-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-07 | 2027-04-11 | 2027-04-11
UG-13A-S13-A040 | AW.PIPE.F3.UG-13A.UG-13A-S13 | F3 | UG-13A | UG-13A-S13 | A040 | Install sheet piles (shored lengths) | 60.7331 | m wall | 3 | 4 | UG-13A-S13-A030 | 2 | 2 |  | 2027-04-09 | 2027-04-13 | 2027-04-13
UG-13A-S13-A050 | AW.PIPE.F3.UG-13A.UG-13A-S13 | F3 | UG-13A | UG-13A-S13 | A050 | Install dewatering and draw down | 30.3665 | m | 8 | 10 | UG-13A-S13-A040 | 2 | 2 |  | 2027-04-11 | 2027-04-21
UG-13A-S13-A060 | AW.PIPE.F3.UG-13A.UG-13A-S13 | F3 | UG-13A | UG-13A-S13 | A060 | Excavate and strut to formation | 309.7385 | m3 | 2 | 3 | UG-13A-S13-A050 | 10 | 2 |  | 2027-04-21 | 2027-04-24 | 2027-04-24
UG-13A-S13-A070 | AW.PIPE.F3.UG-13A.UG-13A-S13 | F3 | UG-13A | UG-13A-S13 | A070 | Trim piles, blinding and piled slab (incl. cure) | 30.3665 | m | 6 | 7 | UG-13A-S13-A060 | 1 | 2 |  | 2027-04-22 | 2027-04-29 | 2027-04-29
UG-13A-S13-A080 | AW.PIPE.F3.UG-13A.UG-13A-S13 | F3 | UG-13A | UG-13A-S13 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 30.3665 | m | 5 | 6 | UG-13A-S13-A070 | 3 | 2 | UG-13A-S14-A080 (FS, closure) | 2027-07-12 | 2027-07-18 | 2027-07-18
UG-13A-S13-A090 | AW.PIPE.F3.UG-13A.UG-13A-S13 | F3 | UG-13A | UG-13A-S13 | A090 | Surround, joint test and line test | 30.3665 | m | 3 | 4 | UG-13A-S13-A080 | 2 | 2 |  | 2027-07-14 | 2027-07-20
UG-13A-S13-A100 | AW.PIPE.F3.UG-13A.UG-13A-S13 | F3 | UG-13A | UG-13A-S13 | A100 | Backfill to NG and remove struts | 255.5223 | m3 | 1 | 2 | UG-13A-S13-A090 | 2 | 2 | UG-27K-S01-A080 (FS, shared trench laid) | 2027-07-16 | 2027-07-22 | 2027-07-22
UG-13A-S13-A110 | AW.PIPE.F3.UG-13A.UG-13A-S13 | F3 | UG-13A | UG-13A-S13 | A110 | Dewatering off, extract sheets, reinstate | 60.7331 | m wall | 3 | 4 | UG-13A-S13-A100 | 1 | 2 |  | 2027-07-17 | 2027-07-24
UG-27K-S01-A010 | AW.PIPE.F3.UG-27K.UG-27K-S01 | F3 | UG-27K | UG-27K-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-27K-S01-A020 | AW.PIPE.F3.UG-27K.UG-27K-S01 | F3 | UG-27K | UG-27K-S01 | A020 | Set-out, crossing survey and working platform | 37.7244 | m | 1 | 2 | UG-27K-S01-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-27K-S01-A030 | AW.PIPE.F3.UG-27K.UG-27K-S01 | F3 | UG-27K | UG-27K-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 28 | piles | 6 | 7 | UG-27K-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-09 | 2026-12-09
UG-27K-S01-A040 | AW.PIPE.F3.UG-27K.UG-27K-S01 | F3 | UG-27K | UG-27K-S01 | A040 | Install sheet piles (shored lengths) | 55.4487 | m wall | 3 | 4 | UG-27K-S01-A030 | 3 | 2 |  | 2026-12-05 | 2026-12-11 | 2026-12-11
UG-27K-S01-A050 | AW.PIPE.F3.UG-27K.UG-27K-S01 | F3 | UG-27K | UG-27K-S01 | A050 | Install dewatering and draw down | 37.7244 | m | 8 | 10 | UG-27K-S01-A040 | 2 | 2 |  | 2026-12-07 | 2026-12-17
UG-27K-S01-A060 | AW.PIPE.F3.UG-27K.UG-27K-S01 | F3 | UG-27K | UG-27K-S01 | A060 | Excavate and strut to formation | 390.9293 | m3 | 2 | 3 | UG-27K-S01-A050 | 10 | 2 | UG-08-S07-A100 (FS, deeper first); UG-13A-S13-A060 (SS, shared trench) | 2027-04-21 | 2027-04-24 | 2027-04-24
UG-27K-S01-A070 | AW.PIPE.F3.UG-27K.UG-27K-S01 | F3 | UG-27K | UG-27K-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 37.7244 | m | 7 | 9 | UG-27K-S01-A060 | 1 | 2 |  | 2027-04-22 | 2027-05-01 | 2027-05-01
UG-27K-S01-A080 | AW.PIPE.F3.UG-27K.UG-27K-S01 | F3 | UG-27K | UG-27K-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 37.7244 | m | 9 | 11 | UG-27K-S01-A070 | 3 | 2 |  | 2027-04-25 | 2027-05-06 | 2027-05-06
UG-27K-S01-A090 | AW.PIPE.F3.UG-27K.UG-27K-S01 | F3 | UG-27K | UG-27K-S01 | A090 | Surround, joint test and line test | 37.7244 | m | 3 | 4 | UG-27K-S01-A080 | 4 | 2 |  | 2027-04-29 | 2027-05-08
UG-27K-S01-A100 | AW.PIPE.F3.UG-27K.UG-27K-S01 | F3 | UG-27K | UG-27K-S01 | A100 | Backfill to NG and remove struts | 276.2506 | m3 | 1 | 2 | UG-27K-S01-A090 | 2 | 2 | UG-13A-S13-A080 (FS, shared trench laid) | 2027-07-18 | 2027-07-20 | 2027-07-20
UG-27K-S01-A110 | AW.PIPE.F3.UG-27K.UG-27K-S01 | F3 | UG-27K | UG-27K-S01 | A110 | Dewatering off, extract sheets, reinstate | 55.4487 | m wall | 3 | 4 | UG-27K-S01-A100 | 1 | 2 |  | 2027-07-19 | 2027-07-23
UG-09-S08-A010 | AW.PIPE.F3.UG-09.UG-09-S08 | F3 | UG-09 | UG-09-S08 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-09-S08-A020 | AW.PIPE.F3.UG-09.UG-09-S08 | F3 | UG-09 | UG-09-S08 | A020 | Set-out, crossing survey and working platform | 6 | m | 1 | 2 | UG-09-S08-A010 |  |  | FS from A010; UG-09-S07-A030 (SS, tie-in team follows the adjacent run) | 2027-01-15 | 2027-01-17
UG-09-S08-A030 | AW.PIPE.F3.UG-09.UG-09-S08 | F3 | UG-09 | UG-09-S08 | A030 | Pipe-support piling from platform (incl. integrity tests) | 6 | piles | 2 | 3 | UG-09-S08-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-16 | 2027-01-19 | 2027-01-19
UG-09-S08-A040 | AW.PIPE.F3.UG-09.UG-09-S08 | F3 | UG-09 | UG-09-S08 | A040 | Install sheet piles (shored lengths) | 12 | m wall | 1 | 2 | UG-09-S08-A030 | 1 | 2 |  | 2027-01-17 | 2027-01-21 | 2027-01-21
UG-09-S08-A050 | AW.PIPE.F3.UG-09.UG-09-S08 | F3 | UG-09 | UG-09-S08 | A050 | Install dewatering and draw down | 6 | m | 8 | 10 | UG-09-S08-A040 | 1 | 2 |  | 2027-01-18 | 2027-01-28
UG-09-S08-A060 | AW.PIPE.F3.UG-09.UG-09-S08 | F3 | UG-09 | UG-09-S08 | A060 | Excavate and strut to formation | 119.5492 | m3 | 1 | 2 | UG-09-S08-A050 | 10 | 2 |  | 2027-01-28 | 2027-01-30 | 2027-01-30
UG-09-S08-A070 | AW.PIPE.F3.UG-09.UG-09-S08 | F3 | UG-09 | UG-09-S08 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6 | m | 4 | 5 | UG-09-S08-A060 | 1 | 2 |  | 2027-01-29 | 2027-02-03 | 2027-02-03
UG-09-S08-A080 | AW.PIPE.F3.UG-09.UG-09-S08 | F3 | UG-09 | UG-09-S08 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6 | m | 4 | 5 | UG-09-S08-A070 | 2 | 2 | UG-09-S07-A080 (FS, closure) | 2027-03-21 | 2027-03-26 | 2027-03-26
UG-09-S08-A090 | AW.PIPE.F3.UG-09.UG-09-S08 | F3 | UG-09 | UG-09-S08 | A090 | Surround, joint test and line test | 6 | m | 3 | 4 | UG-09-S08-A080 | 2 | 2 |  | 2027-03-23 | 2027-03-28
UG-09-S08-A100 | AW.PIPE.F3.UG-09.UG-09-S08 | F3 | UG-09 | UG-09-S08 | A100 | Backfill to NG and remove struts | 75.3107 | m3 | 1 | 2 | UG-09-S08-A090 | 2 | 2 |  | 2027-03-25 | 2027-03-30 | 2027-03-30
UG-09-S08-A110 | AW.PIPE.F3.UG-09.UG-09-S08 | F3 | UG-09 | UG-09-S08 | A110 | Dewatering off, extract sheets, reinstate | 12 | m wall | 2 | 3 | UG-09-S08-A100 | 1 | 2 |  | 2027-03-26 | 2027-04-01
UG-13B-S01-A010 | AW.PIPE.F3.UG-13B.UG-13B-S01 | F3 | UG-13B | UG-13B-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-13B-S01-A020 | AW.PIPE.F3.UG-13B.UG-13B-S01 | F3 | UG-13B | UG-13B-S01 | A020 | Set-out, crossing survey and working platform | 30.7432 | m | 1 | 2 | UG-13B-S01-A010 |  |  | FS from A010; UG-13B-S02-A030 (SS, tie-in team follows the adjacent run) | 2027-02-28 | 2027-03-02
UG-13B-S01-A030 | AW.PIPE.F3.UG-13B.UG-13B-S01 | F3 | UG-13B | UG-13B-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 24 | piles | 5 | 6 | UG-13B-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-01 | 2027-03-07 | 2027-03-07
UG-13B-S01-A040 | AW.PIPE.F3.UG-13B.UG-13B-S01 | F3 | UG-13B | UG-13B-S01 | A040 | Install sheet piles (shored lengths) | 61.4864 | m wall | 3 | 4 | UG-13B-S01-A030 | 2 | 2 |  | 2027-03-03 | 2027-03-09 | 2027-03-09
UG-13B-S01-A050 | AW.PIPE.F3.UG-13B.UG-13B-S01 | F3 | UG-13B | UG-13B-S01 | A050 | Install dewatering and draw down | 30.7432 | m | 8 | 10 | UG-13B-S01-A040 | 2 | 2 |  | 2027-03-05 | 2027-03-15
UG-13B-S01-A060 | AW.PIPE.F3.UG-13B.UG-13B-S01 | F3 | UG-13B | UG-13B-S01 | A060 | Excavate and strut to formation | 313.5796 | m3 | 2 | 3 | UG-13B-S01-A050 | 10 | 2 |  | 2027-03-15 | 2027-03-18 | 2027-03-18
UG-13B-S01-A070 | AW.PIPE.F3.UG-13B.UG-13B-S01 | F3 | UG-13B | UG-13B-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 30.7432 | m | 6 | 7 | UG-13B-S01-A060 | 1 | 2 |  | 2027-03-16 | 2027-03-23 | 2027-03-23
UG-13B-S01-A080 | AW.PIPE.F3.UG-13B.UG-13B-S01 | F3 | UG-13B | UG-13B-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 30.7432 | m | 5 | 6 | UG-13B-S01-A070 | 3 | 2 | UG-13B-S02-A080 (FS, closure) | 2027-05-20 | 2027-05-26 | 2027-05-26
UG-13B-S01-A090 | AW.PIPE.F3.UG-13B.UG-13B-S01 | F3 | UG-13B | UG-13B-S01 | A090 | Surround, joint test and line test | 30.7432 | m | 3 | 4 | UG-13B-S01-A080 | 2 | 2 |  | 2027-05-22 | 2027-05-28
UG-13B-S01-A100 | AW.PIPE.F3.UG-13B.UG-13B-S01 | F3 | UG-13B | UG-13B-S01 | A100 | Backfill to NG and remove struts | 258.6911 | m3 | 1 | 2 | UG-13B-S01-A090 | 2 | 2 | UG-14E-S01-A080 (FS, shared trench laid) | 2027-05-24 | 2027-05-30 | 2027-05-30
UG-13B-S01-A110 | AW.PIPE.F3.UG-13B.UG-13B-S01 | F3 | UG-13B | UG-13B-S01 | A110 | Dewatering off, extract sheets, reinstate | 61.4864 | m wall | 3 | 4 | UG-13B-S01-A100 | 1 | 2 |  | 2027-05-25 | 2027-06-01
UG-14E-S01-A010 | AW.PIPE.F3.UG-14E.UG-14E-S01 | F3 | UG-14E | UG-14E-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-14E-S01-A020 | AW.PIPE.F3.UG-14E.UG-14E-S01 | F3 | UG-14E | UG-14E-S01 | A020 | Set-out, crossing survey and working platform | 37.5876 | m | 1 | 2 | UG-14E-S01-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-14E-S01-A030 | AW.PIPE.F3.UG-14E.UG-14E-S01 | F3 | UG-14E | UG-14E-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 28 | piles | 6 | 7 | UG-14E-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-09 | 2026-12-09
UG-14E-S01-A040 | AW.PIPE.F3.UG-14E.UG-14E-S01 | F3 | UG-14E | UG-14E-S01 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-14E-S01-A030 | 3 | 0 |  | 2026-12-05 | 2026-12-09 | 0
UG-14E-S01-A050 | AW.PIPE.F3.UG-14E.UG-14E-S01 | F3 | UG-14E | UG-14E-S01 | A050 | Install dewatering and draw down | 37.5876 | m | 8 | 10 | UG-14E-S01-A040 | 0 | 2 |  | 2026-12-05 | 2026-12-15
UG-14E-S01-A060 | AW.PIPE.F3.UG-14E.UG-14E-S01 | F3 | UG-14E | UG-14E-S01 | A060 | Excavate and strut to formation | 1001.0676 | m3 | 3 | 4 | UG-14E-S01-A050 | 10 | 2 | UG-09-S08-A100 (FS, deeper first); UG-13B-S01-A060 (SS, shared trench) | 2027-03-30 | 2027-04-03 | 2027-04-03
UG-14E-S01-A070 | AW.PIPE.F3.UG-14E.UG-14E-S01 | F3 | UG-14E | UG-14E-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 37.5876 | m | 7 | 9 | UG-14E-S01-A060 | 2 | 2 |  | 2027-04-01 | 2027-04-10 | 2027-04-10
UG-14E-S01-A080 | AW.PIPE.F3.UG-14E.UG-14E-S01 | F3 | UG-14E | UG-14E-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 37.5876 | m | 9 | 11 | UG-14E-S01-A070 | 3 | 2 |  | 2027-04-04 | 2027-04-15 | 2027-04-15
UG-14E-S01-A090 | AW.PIPE.F3.UG-14E.UG-14E-S01 | F3 | UG-14E | UG-14E-S01 | A090 | Surround, joint test and line test | 37.5876 | m | 3 | 4 | UG-14E-S01-A080 | 4 | 2 |  | 2027-04-08 | 2027-04-17
UG-14E-S01-A100 | AW.PIPE.F3.UG-14E.UG-14E-S01 | F3 | UG-14E | UG-14E-S01 | A100 | Backfill to NG and remove struts | 887.1658 | m3 | 3 | 4 | UG-14E-S01-A090 | 2 | 2 | UG-13B-S01-A080 (FS, shared trench laid) | 2027-05-26 | 2027-05-30 | 2027-05-30
UG-14E-S01-A110 | AW.PIPE.F3.UG-14E.UG-14E-S01 | F3 | UG-14E | UG-14E-S01 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-14E-S01-A100 | 2 | 2 |  | 2027-05-28 | 2027-06-01
UG-11B-S08-A010 | AW.PIPE.F3.UG-11B.UG-11B-S08 | F3 | UG-11B | UG-11B-S08 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-11B-S08-A020 | AW.PIPE.F3.UG-11B.UG-11B-S08 | F3 | UG-11B | UG-11B-S08 | A020 | Set-out, crossing survey and working platform | 29.457 | m | 1 | 2 | UG-11B-S08-A010 |  |  | FS from A010; UG-11B-S07-A030 (SS, tie-in team follows the adjacent run) | 2027-02-07 | 2027-02-09
UG-11B-S08-A030 | AW.PIPE.F3.UG-11B.UG-11B-S08 | F3 | UG-11B | UG-11B-S08 | A030 | Pipe-support piling from platform (incl. integrity tests) | 22 | piles | 5 | 6 | UG-11B-S08-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-08 | 2027-02-14 | 2027-02-14
UG-11B-S08-A040 | AW.PIPE.F3.UG-11B.UG-11B-S08 | F3 | UG-11B | UG-11B-S08 | A040 | Install sheet piles (shored lengths) | 58.9141 | m wall | 3 | 4 | UG-11B-S08-A030 | 2 | 2 |  | 2027-02-10 | 2027-02-16 | 2027-02-16
UG-11B-S08-A050 | AW.PIPE.F3.UG-11B.UG-11B-S08 | F3 | UG-11B | UG-11B-S08 | A050 | Install dewatering and draw down | 29.457 | m | 8 | 10 | UG-11B-S08-A040 | 2 | 2 |  | 2027-02-12 | 2027-02-22
UG-11B-S08-A060 | AW.PIPE.F3.UG-11B.UG-11B-S08 | F3 | UG-11B | UG-11B-S08 | A060 | Excavate and strut to formation | 300.4623 | m3 | 2 | 3 | UG-11B-S08-A050 | 10 | 2 |  | 2027-02-22 | 2027-02-25 | 2027-02-25
UG-11B-S08-A070 | AW.PIPE.F3.UG-11B.UG-11B-S08 | F3 | UG-11B | UG-11B-S08 | A070 | Trim piles, blinding and piled slab (incl. cure) | 29.457 | m | 6 | 7 | UG-11B-S08-A060 | 1 | 2 |  | 2027-02-23 | 2027-03-02 | 2027-03-02
UG-11B-S08-A080 | AW.PIPE.F3.UG-11B.UG-11B-S08 | F3 | UG-11B | UG-11B-S08 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 29.457 | m | 4 | 5 | UG-11B-S08-A070 | 3 | 2 | UG-11B-S07-A080 (FS, closure) | 2027-05-01 | 2027-05-06 | 2027-05-06
UG-11B-S08-A090 | AW.PIPE.F3.UG-11B.UG-11B-S08 | F3 | UG-11B | UG-11B-S08 | A090 | Surround, joint test and line test | 29.457 | m | 3 | 4 | UG-11B-S08-A080 | 2 | 2 |  | 2027-05-03 | 2027-05-08
UG-11B-S08-A100 | AW.PIPE.F3.UG-11B.UG-11B-S08 | F3 | UG-11B | UG-11B-S08 | A100 | Backfill to NG and remove struts | 247.8695 | m3 | 1 | 2 | UG-11B-S08-A090 | 2 | 2 | UG-16B-S01-A080 (FS, shared trench laid) | 2027-05-05 | 2027-05-10 | 2027-05-10
UG-11B-S08-A110 | AW.PIPE.F3.UG-11B.UG-11B-S08 | F3 | UG-11B | UG-11B-S08 | A110 | Dewatering off, extract sheets, reinstate | 58.9141 | m wall | 3 | 4 | UG-11B-S08-A100 | 1 | 2 |  | 2027-05-06 | 2027-05-12
UG-16B-S01-A010 | AW.PIPE.F3.UG-16B.UG-16B-S01 | F3 | UG-16B | UG-16B-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-16B-S01-A020 | AW.PIPE.F3.UG-16B.UG-16B-S01 | F3 | UG-16B | UG-16B-S01 | A020 | Set-out, crossing survey and working platform | 38.1234 | m | 1 | 2 | UG-16B-S01-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-16B-S01-A030 | AW.PIPE.F3.UG-16B.UG-16B-S01 | F3 | UG-16B | UG-16B-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 28 | piles | 6 | 7 | UG-16B-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-09 | 2026-12-09
UG-16B-S01-A040 | AW.PIPE.F3.UG-16B.UG-16B-S01 | F3 | UG-16B | UG-16B-S01 | A040 | Install sheet piles (shored lengths) | 56.008 | m wall | 3 | 4 | UG-16B-S01-A030 | 3 | 2 |  | 2026-12-05 | 2026-12-11 | 2026-12-11
UG-16B-S01-A050 | AW.PIPE.F3.UG-16B.UG-16B-S01 | F3 | UG-16B | UG-16B-S01 | A050 | Install dewatering and draw down | 38.1234 | m | 8 | 10 | UG-16B-S01-A040 | 2 | 2 |  | 2026-12-07 | 2026-12-17
UG-16B-S01-A060 | AW.PIPE.F3.UG-16B.UG-16B-S01 | F3 | UG-16B | UG-16B-S01 | A060 | Excavate and strut to formation | 399.9639 | m3 | 2 | 3 | UG-16B-S01-A050 | 10 | 2 | UG-10-S05-A100 (FS, deeper first); UG-11B-S08-A060 (SS, shared trench) | 2027-02-22 | 2027-02-25 | 2027-02-25
UG-16B-S01-A070 | AW.PIPE.F3.UG-16B.UG-16B-S01 | F3 | UG-16B | UG-16B-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 38.1234 | m | 7 | 9 | UG-16B-S01-A060 | 1 | 2 |  | 2027-02-23 | 2027-03-04 | 2027-03-04
UG-16B-S01-A080 | AW.PIPE.F3.UG-16B.UG-16B-S01 | F3 | UG-16B | UG-16B-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 38.1234 | m | 9 | 11 | UG-16B-S01-A070 | 3 | 2 |  | 2027-02-26 | 2027-03-09 | 2027-03-09
UG-16B-S01-A090 | AW.PIPE.F3.UG-16B.UG-16B-S01 | F3 | UG-16B | UG-16B-S01 | A090 | Surround, joint test and line test | 38.1234 | m | 3 | 4 | UG-16B-S01-A080 | 4 | 2 |  | 2027-03-02 | 2027-03-11
UG-16B-S01-A100 | AW.PIPE.F3.UG-16B.UG-16B-S01 | F3 | UG-16B | UG-16B-S01 | A100 | Backfill to NG and remove struts | 285.2761 | m3 | 1 | 2 | UG-16B-S01-A090 | 2 | 2 | UG-11B-S08-A080 (FS, shared trench laid) | 2027-05-06 | 2027-05-08 | 2027-05-08
UG-16B-S01-A110 | AW.PIPE.F3.UG-16B.UG-16B-S01 | F3 | UG-16B | UG-16B-S01 | A110 | Dewatering off, extract sheets, reinstate | 56.008 | m wall | 3 | 4 | UG-16B-S01-A100 | 1 | 2 |  | 2027-05-07 | 2027-05-11
UG-14F-S01-A010 | AW.PIPE.F3.UG-14F.UG-14F-S01 | F3 | UG-14F | UG-14F-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-14F-S01-A020 | AW.PIPE.F3.UG-14F.UG-14F-S01 | F3 | UG-14F | UG-14F-S01 | A020 | Set-out, crossing survey and working platform | 38.0885 | m | 1 | 2 | UG-14F-S01-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-14F-S01-A030 | AW.PIPE.F3.UG-14F.UG-14F-S01 | F3 | UG-14F | UG-14F-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 28 | piles | 6 | 7 | UG-14F-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-09 | 2026-12-09
UG-14F-S01-A040 | AW.PIPE.F3.UG-14F.UG-14F-S01 | F3 | UG-14F | UG-14F-S01 | A040 | Install sheet piles (shored lengths) | 56.075 | m wall | 3 | 4 | UG-14F-S01-A030 | 3 | 2 |  | 2026-12-05 | 2026-12-11 | 2026-12-11
UG-14F-S01-A050 | AW.PIPE.F3.UG-14F.UG-14F-S01 | F3 | UG-14F | UG-14F-S01 | A050 | Install dewatering and draw down | 38.0885 | m | 8 | 10 | UG-14F-S01-A040 | 2 | 2 |  | 2026-12-07 | 2026-12-17
UG-14F-S01-A060 | AW.PIPE.F3.UG-14F.UG-14F-S01 | F3 | UG-14F | UG-14F-S01 | A060 | Excavate and strut to formation | 417.5864 | m3 | 2 | 3 | UG-14F-S01-A050 | 10 | 2 | UG-09-S08-A100 (FS, deeper first); UG-13B-S09-A100 (FS, deeper first); UG-13B-S10-A100 (FS, deeper first) | 2027-05-04 | 2027-05-07 | 2027-05-07
UG-14F-S01-A070 | AW.PIPE.F3.UG-14F.UG-14F-S01 | F3 | UG-14F | UG-14F-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 38.0885 | m | 7 | 9 | UG-14F-S01-A060 | 1 | 2 |  | 2027-05-05 | 2027-05-14 | 2027-05-14
UG-14F-S01-A080 | AW.PIPE.F3.UG-14F.UG-14F-S01 | F3 | UG-14F | UG-14F-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 38.0885 | m | 9 | 11 | UG-14F-S01-A070 | 3 | 2 |  | 2027-05-08 | 2027-05-19 | 2027-05-19
UG-14F-S01-A090 | AW.PIPE.F3.UG-14F.UG-14F-S01 | F3 | UG-14F | UG-14F-S01 | A090 | Surround, joint test and line test | 38.0885 | m | 3 | 4 | UG-14F-S01-A080 | 4 | 2 |  | 2027-05-12 | 2027-05-21
UG-14F-S01-A100 | AW.PIPE.F3.UG-14F.UG-14F-S01 | F3 | UG-14F | UG-14F-S01 | A100 | Backfill to NG and remove struts | 302.6969 | m3 | 1 | 2 | UG-14F-S01-A090 | 2 | 2 |  | 2027-05-14 | 2027-05-23 | 2027-05-23
UG-14F-S01-A110 | AW.PIPE.F3.UG-14F.UG-14F-S01 | F3 | UG-14F | UG-14F-S01 | A110 | Dewatering off, extract sheets, reinstate | 56.075 | m wall | 3 | 4 | UG-14F-S01-A100 | 1 | 2 |  | 2027-05-15 | 2027-05-25
UG-27J-S02-A010 | AW.PIPE.F3.UG-27J.UG-27J-S02 | F3 | UG-27J | UG-27J-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-27J-S02-A020 | AW.PIPE.F3.UG-27J.UG-27J-S02 | F3 | UG-27J | UG-27J-S02 | A020 | Set-out, crossing survey and working platform | 22.0646 | m | 1 | 2 | UG-27J-S02-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-27J-S02-A030 | AW.PIPE.F3.UG-27J.UG-27J-S02 | F3 | UG-27J | UG-27J-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 18 | piles | 4 | 5 | UG-27J-S02-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-07 | 2026-12-07
UG-27J-S02-A040 | AW.PIPE.F3.UG-27J.UG-27J-S02 | F3 | UG-27J | UG-27J-S02 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-27J-S02-A030 | 2 | 0 |  | 2026-12-04 | 2026-12-07 | 0
UG-27J-S02-A050 | AW.PIPE.F3.UG-27J.UG-27J-S02 | F3 | UG-27J | UG-27J-S02 | A050 | Install dewatering and draw down | 22.0646 | m | 8 | 10 | UG-27J-S02-A040 | 0 | 2 |  | 2026-12-04 | 2026-12-14
UG-27J-S02-A060 | AW.PIPE.F3.UG-27J.UG-27J-S02 | F3 | UG-27J | UG-27J-S02 | A060 | Excavate and strut to formation | 735.6319 | m3 | 2 | 3 | UG-27J-S02-A050 | 10 | 2 | UG-13A-S15-A100 (FS, deeper first) | 2027-06-23 | 2027-06-26 | 2027-06-26
UG-27J-S02-A070 | AW.PIPE.F3.UG-27J.UG-27J-S02 | F3 | UG-27J | UG-27J-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 22.0646 | m | 5 | 6 | UG-27J-S02-A060 | 1 | 2 |  | 2027-06-24 | 2027-06-30 | 2027-06-30
UG-27J-S02-A080 | AW.PIPE.F3.UG-27J.UG-27J-S02 | F3 | UG-27J | UG-27J-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 22.0646 | m | 4 | 5 | UG-27J-S02-A070 | 2 | 2 |  | 2027-06-26 | 2027-07-02 | 2027-07-02
UG-27J-S02-A090 | AW.PIPE.F3.UG-27J.UG-27J-S02 | F3 | UG-27J | UG-27J-S02 | A090 | Surround, joint test and line test | 22.0646 | m | 3 | 4 | UG-27J-S02-A080 | 2 | 2 |  | 2027-06-28 | 2027-07-04
UG-27J-S02-A100 | AW.PIPE.F3.UG-27J.UG-27J-S02 | F3 | UG-27J | UG-27J-S02 | A100 | Backfill to NG and remove struts | 662.5847 | m3 | 2 | 3 | UG-27J-S02-A090 | 2 | 2 |  | 2027-06-30 | 2027-07-06 | 2027-07-06
UG-27J-S02-A110 | AW.PIPE.F3.UG-27J.UG-27J-S02 | F3 | UG-27J | UG-27J-S02 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-27J-S02-A100 | 1 | 2 |  | 2027-07-01 | 2027-07-08
UG-27J-S01-A010 | AW.PIPE.F3.UG-27J.UG-27J-S01 | F3 | UG-27J | UG-27J-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-27J-S01-A020 | AW.PIPE.F3.UG-27J.UG-27J-S01 | F3 | UG-27J | UG-27J-S01 | A020 | Set-out, crossing survey and working platform | 16 | m | 1 | 2 | UG-27J-S01-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-27J-S01-A030 | AW.PIPE.F3.UG-27J.UG-27J-S01 | F3 | UG-27J | UG-27J-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 14 | piles | 3 | 4 | UG-27J-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-06 | 2026-12-06
UG-27J-S01-A040 | AW.PIPE.F3.UG-27J.UG-27J-S01 | F3 | UG-27J | UG-27J-S01 | A040 | Install sheet piles (shored lengths) | 0.24288 | m wall | 1 | 2 | UG-27J-S01-A030 | 2 | 2 |  | 2026-12-04 | 2026-12-08 | 2026-12-08
UG-27J-S01-A050 | AW.PIPE.F3.UG-27J.UG-27J-S01 | F3 | UG-27J | UG-27J-S01 | A050 | Install dewatering and draw down | 16 | m | 8 | 10 | UG-27J-S01-A040 | 1 | 2 |  | 2026-12-05 | 2026-12-15
UG-27J-S01-A060 | AW.PIPE.F3.UG-27J.UG-27J-S01 | F3 | UG-27J | UG-27J-S01 | A060 | Excavate and strut to formation | 261.0618 | m3 | 1 | 2 | UG-27J-S01-A050 | 10 | 2 | UG-13A-S06-A100 (FS, deeper first); UG-13A-S07-A100 (FS, deeper first) | 2027-06-28 | 2027-06-30 | 2027-06-30
UG-27J-S01-A070 | AW.PIPE.F3.UG-27J.UG-27J-S01 | F3 | UG-27J | UG-27J-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 16 | m | 5 | 6 | UG-27J-S01-A060 | 1 | 2 |  | 2027-06-29 | 2027-07-05 | 2027-07-05
UG-27J-S01-A080 | AW.PIPE.F3.UG-27J.UG-27J-S01 | F3 | UG-27J | UG-27J-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 16 | m | 8 | 10 | UG-27J-S01-A070 | 2 | 2 |  | 2027-07-01 | 2027-07-11 | 2027-07-11
UG-27J-S01-A090 | AW.PIPE.F3.UG-27J.UG-27J-S01 | F3 | UG-27J | UG-27J-S01 | A090 | Surround, joint test and line test | 16 | m | 3 | 4 | UG-27J-S01-A080 | 3 | 2 |  | 2027-07-04 | 2027-07-13
UG-27J-S01-A100 | AW.PIPE.F3.UG-27J.UG-27J-S01 | F3 | UG-27J | UG-27J-S01 | A100 | Backfill to NG and remove struts | 219.4423 | m3 | 1 | 2 | UG-27J-S01-A090 | 2 | 2 |  | 2027-07-06 | 2027-07-15 | 2027-07-15
UG-27J-S01-A110 | AW.PIPE.F3.UG-27J.UG-27J-S01 | F3 | UG-27J | UG-27J-S01 | A110 | Dewatering off, extract sheets, reinstate | 0.24288 | m wall | 2 | 3 | UG-27J-S01-A100 | 1 | 2 |  | 2027-07-07 | 2027-07-17
UG-27L-S01-A010 | AW.PIPE.F3.UG-27L.UG-27L-S01 | F3 | UG-27L | UG-27L-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-27L-S01-A020 | AW.PIPE.F3.UG-27L.UG-27L-S01 | F3 | UG-27L | UG-27L-S01 | A020 | Set-out, crossing survey and working platform | 38.1115 | m | 1 | 2 | UG-27L-S01-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-27L-S01-A030 | AW.PIPE.F3.UG-27L.UG-27L-S01 | F3 | UG-27L | UG-27L-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 28 | piles | 6 | 7 | UG-27L-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-09 | 2026-12-09
UG-27L-S01-A040 | AW.PIPE.F3.UG-27L.UG-27L-S01 | F3 | UG-27L | UG-27L-S01 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-27L-S01-A030 | 3 | 0 |  | 2026-12-05 | 2026-12-09 | 0
UG-27L-S01-A050 | AW.PIPE.F3.UG-27L.UG-27L-S01 | F3 | UG-27L | UG-27L-S01 | A050 | Install dewatering and draw down | 38.1115 | m | 8 | 10 | UG-27L-S01-A040 | 0 | 2 |  | 2026-12-05 | 2026-12-15
UG-27L-S01-A060 | AW.PIPE.F3.UG-27L.UG-27L-S01 | F3 | UG-27L | UG-27L-S01 | A060 | Excavate and strut to formation | 998.2598 | m3 | 3 | 4 | UG-27L-S01-A050 | 10 | 2 | UG-08-S07-A100 (FS, deeper first); UG-13A-S01-A100 (FS, deeper first); UG-13A-S02-A100 (FS, deeper first) | 2027-06-19 | 2027-06-23 | 2027-06-23
UG-27L-S01-A070 | AW.PIPE.F3.UG-27L.UG-27L-S01 | F3 | UG-27L | UG-27L-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 38.1115 | m | 7 | 9 | UG-27L-S01-A060 | 2 | 2 |  | 2027-06-21 | 2027-06-30 | 2027-06-30
UG-27L-S01-A080 | AW.PIPE.F3.UG-27L.UG-27L-S01 | F3 | UG-27L | UG-27L-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 38.1115 | m | 9 | 11 | UG-27L-S01-A070 | 3 | 2 |  | 2027-06-24 | 2027-07-05 | 2027-07-05
UG-27L-S01-A090 | AW.PIPE.F3.UG-27L.UG-27L-S01 | F3 | UG-27L | UG-27L-S01 | A090 | Surround, joint test and line test | 38.1115 | m | 3 | 4 | UG-27L-S01-A080 | 4 | 2 |  | 2027-06-28 | 2027-07-07
UG-27L-S01-A100 | AW.PIPE.F3.UG-27L.UG-27L-S01 | F3 | UG-27L | UG-27L-S01 | A100 | Backfill to NG and remove struts | 883.6604 | m3 | 3 | 4 | UG-27L-S01-A090 | 2 | 2 |  | 2027-06-30 | 2027-07-09 | 2027-07-09
UG-27L-S01-A110 | AW.PIPE.F3.UG-27L.UG-27L-S01 | F3 | UG-27L | UG-27L-S01 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-27L-S01-A100 | 2 | 2 |  | 2027-07-02 | 2027-07-11
UG-15-S05-A010 | AW.PIPE.F4.UG-15.UG-15-S05 | F4 | UG-15 | UG-15-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-15-S05-A020 | AW.PIPE.F4.UG-15.UG-15-S05 | F4 | UG-15 | UG-15-S05 | A020 | Set-out, crossing survey and working platform | 16.228 | m | 1 | 2 | UG-15-S05-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-15-S05-A030 | AW.PIPE.F4.UG-15.UG-15-S05 | F4 | UG-15 | UG-15-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 14 | piles | 3 | 4 | UG-15-S05-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-06 | 2026-12-06
UG-15-S05-A040 | AW.PIPE.F4.UG-15.UG-15-S05 | F4 | UG-15 | UG-15-S05 | A040 | Install sheet piles (shored lengths) | 32.456 | m wall | 2 | 3 | UG-15-S05-A030 | 2 | 2 |  | 2026-12-04 | 2026-12-08 | 2026-12-08
UG-15-S05-A050 | AW.PIPE.F4.UG-15.UG-15-S05 | F4 | UG-15 | UG-15-S05 | A050 | Install dewatering and draw down | 16.228 | m | 8 | 10 | UG-15-S05-A040 | 1 | 2 |  | 2026-12-05 | 2026-12-15
UG-15-S05-A060 | AW.PIPE.F4.UG-15.UG-15-S05 | F4 | UG-15 | UG-15-S05 | A060 | Excavate and strut to formation | 303.6226 | m3 | 2 | 3 | UG-15-S05-A050 | 10 | 2 |  | 2026-12-15 | 2026-12-18 | 2026-12-18
UG-15-S05-A070 | AW.PIPE.F4.UG-15.UG-15-S05 | F4 | UG-15 | UG-15-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 16.228 | m | 5 | 6 | UG-15-S05-A060 | 1 | 2 |  | 2026-12-16 | 2026-12-22 | 2026-12-22
UG-15-S05-A080 | AW.PIPE.F4.UG-15.UG-15-S05 | F4 | UG-15 | UG-15-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 16.228 | m | 2 | 3 | UG-15-S05-A070 | 2 | 2 |  | 2026-12-18 | 2026-12-24 | 2026-12-24
UG-15-S05-A090 | AW.PIPE.F4.UG-15.UG-15-S05 | F4 | UG-15 | UG-15-S05 | A090 | Surround, joint test and line test | 16.228 | m | 3 | 4 | UG-15-S05-A080 | 1 | 2 |  | 2026-12-19 | 2026-12-26
UG-15-S05-A100 | AW.PIPE.F4.UG-15.UG-15-S05 | F4 | UG-15 | UG-15-S05 | A100 | Backfill to NG and remove struts | 225.5141 | m3 | 1 | 2 | UG-15-S05-A090 | 2 | 2 | UG-15A-S02-A080 (FS, shared trench laid) | 2027-01-05 | 2027-01-07 | 2027-01-07
UG-15-S05-A110 | AW.PIPE.F4.UG-15.UG-15-S05 | F4 | UG-15 | UG-15-S05 | A110 | Dewatering off, extract sheets, reinstate | 32.456 | m wall | 2 | 3 | UG-15-S05-A100 | 1 | 2 |  | 2027-01-06 | 2027-01-09
UG-15-S04-A010 | AW.PIPE.F4.UG-15.UG-15-S04 | F4 | UG-15 | UG-15-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-15-S04-A020 | AW.PIPE.F4.UG-15.UG-15-S04 | F4 | UG-15 | UG-15-S04 | A020 | Set-out, crossing survey and working platform | 16.1 | m | 1 | 2 | UG-15-S04-A010 |  |  | FS from A010; UG-15-S05-A030 (SS, set-out one package ahead of piling) | 2026-12-02 | 2026-12-04
UG-15-S04-A030 | AW.PIPE.F4.UG-15.UG-15-S04 | F4 | UG-15 | UG-15-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 14 | piles | 3 | 4 | UG-15-S04-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-06 | 2026-12-10 | 2026-12-10 | UG-15-S05-A030
UG-15-S04-A040 | AW.PIPE.F4.UG-15.UG-15-S04 | F4 | UG-15 | UG-15-S04 | A040 | Install sheet piles (shored lengths) | 32.2 | m wall | 2 | 3 | UG-15-S04-A030 | 2 | 2 |  | 2026-12-08 | 2026-12-12 | 2026-12-12 | UG-15-S05-A040
UG-15-S04-A050 | AW.PIPE.F4.UG-15.UG-15-S04 | F4 | UG-15 | UG-15-S04 | A050 | Install dewatering and draw down | 16.1 | m | 8 | 10 | UG-15-S04-A040 | 1 | 2 | UG-15-S05-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2026-12-09 | 2026-12-19
UG-15-S04-A060 | AW.PIPE.F4.UG-15.UG-15-S04 | F4 | UG-15 | UG-15-S04 | A060 | Excavate and strut to formation | 300.7183 | m3 | 2 | 3 | UG-15-S04-A050 | 10 | 2 |  | 2026-12-19 | 2026-12-22 | 2026-12-22 | UG-15-S05-A060
UG-15-S04-A070 | AW.PIPE.F4.UG-15.UG-15-S04 | F4 | UG-15 | UG-15-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 16.1 | m | 5 | 6 | UG-15-S04-A060 | 1 | 2 |  | 2026-12-22 | 2026-12-28 | 2026-12-28 | UG-15-S05-A070
UG-15-S04-A080 | AW.PIPE.F4.UG-15.UG-15-S04 | F4 | UG-15 | UG-15-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 16.1 | m | 1 | 2 | UG-15-S04-A070 | 2 | 2 |  | 2026-12-24 | 2026-12-30 | 2026-12-30 | UG-15-S05-A080
UG-15-S04-A090 | AW.PIPE.F4.UG-15.UG-15-S04 | F4 | UG-15 | UG-15-S04 | A090 | Surround, joint test and line test | 16.1 | m | 3 | 4 | UG-15-S04-A080 | 1 | 2 |  | 2026-12-25 | 2027-01-01
UG-15-S04-A100 | AW.PIPE.F4.UG-15.UG-15-S04 | F4 | UG-15 | UG-15-S04 | A100 | Backfill to NG and remove struts | 223.5511 | m3 | 1 | 2 | UG-15-S04-A090 | 2 | 2 | UG-15A-S02-A080 (FS, shared trench laid) | 2027-01-07 | 2027-01-09 | 2027-01-09 | UG-15-S05-A100
UG-15-S04-A110 | AW.PIPE.F4.UG-15.UG-15-S04 | F4 | UG-15 | UG-15-S04 | A110 | Dewatering off, extract sheets, reinstate | 32.2 | m wall | 2 | 3 | UG-15-S04-A100 | 1 | 2 |  | 2027-01-08 | 2027-01-11
UG-15A-S02-A010 | AW.PIPE.F4.UG-15A.UG-15A-S02 | F4 | UG-15A | UG-15A-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-15A-S02-A020 | AW.PIPE.F4.UG-15A.UG-15A-S02 | F4 | UG-15A | UG-15A-S02 | A020 | Set-out, crossing survey and working platform | 12.0663 | m | 1 | 2 | UG-15A-S02-A010 |  |  | FS from A010; UG-15-S04-A030 (SS, set-out one package ahead of piling) | 2026-12-06 | 2026-12-08
UG-15A-S02-A030 | AW.PIPE.F4.UG-15A.UG-15A-S02 | F4 | UG-15A | UG-15A-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 12 | piles | 3 | 4 | UG-15A-S02-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-10 | 2026-12-14 | 2026-12-14 | UG-15-S04-A030
UG-15A-S02-A040 | AW.PIPE.F4.UG-15A.UG-15A-S02 | F4 | UG-15A | UG-15A-S02 | A040 | Install sheet piles (shored lengths) | 24.1326 | m wall | 1 | 2 | UG-15A-S02-A030 | 2 | 2 |  | 2026-12-12 | 2026-12-16 | 2026-12-16 | UG-15-S04-A040
UG-15A-S02-A050 | AW.PIPE.F4.UG-15A.UG-15A-S02 | F4 | UG-15A | UG-15A-S02 | A050 | Install dewatering and draw down | 12.0663 | m | 8 | 10 | UG-15A-S02-A040 | 1 | 2 | UG-15-S04-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2026-12-13 | 2026-12-23
UG-15A-S02-A060 | AW.PIPE.F4.UG-15A.UG-15A-S02 | F4 | UG-15A | UG-15A-S02 | A060 | Excavate and strut to formation | 162.8036 | m3 | 1 | 2 | UG-15A-S02-A050 | 10 | 2 | UG-15-S04-A060 (SS, shared trench); UG-15-S05-A060 (SS, shared trench) | 2026-12-23 | 2026-12-25 | 2026-12-25 | UG-15-S04-A060
UG-15A-S02-A070 | AW.PIPE.F4.UG-15A.UG-15A-S02 | F4 | UG-15A | UG-15A-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 12.0663 | m | 5 | 6 | UG-15A-S02-A060 | 1 | 2 |  | 2026-12-28 | 2027-01-03 | 2027-01-03 | UG-15-S04-A070
UG-15A-S02-A080 | AW.PIPE.F4.UG-15A.UG-15A-S02 | F4 | UG-15A | UG-15A-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 12.0663 | m | 3 | 4 | UG-15A-S02-A070 | 2 | 2 |  | 2026-12-30 | 2027-01-05 | 2027-01-05 | UG-15-S04-A080
UG-15A-S02-A090 | AW.PIPE.F4.UG-15A.UG-15A-S02 | F4 | UG-15A | UG-15A-S02 | A090 | Surround, joint test and line test | 12.0663 | m | 3 | 4 | UG-15A-S02-A080 | 2 | 2 |  | 2027-01-01 | 2027-01-07
UG-15A-S02-A100 | AW.PIPE.F4.UG-15A.UG-15A-S02 | F4 | UG-15A | UG-15A-S02 | A100 | Backfill to NG and remove struts | 135.6423 | m3 | 1 | 2 | UG-15A-S02-A090 | 2 | 2 | UG-15-S04-A080 (FS, shared trench laid); UG-15-S05-A080 (FS, shared trench laid) | 2027-01-09 | 2027-01-11 | 2027-01-11 | UG-15-S04-A100
UG-15A-S02-A110 | AW.PIPE.F4.UG-15A.UG-15A-S02 | F4 | UG-15A | UG-15A-S02 | A110 | Dewatering off, extract sheets, reinstate | 24.1326 | m wall | 2 | 3 | UG-15A-S02-A100 | 1 | 2 |  | 2027-01-10 | 2027-01-13
UG-15-S06-A010 | AW.PIPE.F4.UG-15.UG-15-S06 | F4 | UG-15 | UG-15-S06 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-15-S06-A020 | AW.PIPE.F4.UG-15.UG-15-S06 | F4 | UG-15 | UG-15-S06 | A020 | Set-out, crossing survey and working platform | 12.9696 | m | 1 | 2 | UG-15-S06-A010 |  |  | FS from A010; UG-15-S05-A030 (SS, tie-in team follows the adjacent run) | 2026-12-02 | 2026-12-04
UG-15-S06-A030 | AW.PIPE.F4.UG-15.UG-15-S06 | F4 | UG-15 | UG-15-S06 | A030 | Pipe-support piling from platform (incl. integrity tests) | 12 | piles | 3 | 4 | UG-15-S06-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-03 | 2026-12-07 | 2026-12-07
UG-15-S06-A040 | AW.PIPE.F4.UG-15.UG-15-S06 | F4 | UG-15 | UG-15-S06 | A040 | Install sheet piles (shored lengths) | 25.9392 | m wall | 2 | 3 | UG-15-S06-A030 | 2 | 2 |  | 2026-12-05 | 2026-12-09 | 2026-12-09
UG-15-S06-A050 | AW.PIPE.F4.UG-15.UG-15-S06 | F4 | UG-15 | UG-15-S06 | A050 | Install dewatering and draw down | 12.9696 | m | 8 | 10 | UG-15-S06-A040 | 1 | 2 |  | 2026-12-06 | 2026-12-16
UG-15-S06-A060 | AW.PIPE.F4.UG-15.UG-15-S06 | F4 | UG-15 | UG-15-S06 | A060 | Excavate and strut to formation | 244.6306 | m3 | 1 | 2 | UG-15-S06-A050 | 10 | 2 |  | 2026-12-16 | 2026-12-18 | 2026-12-18
UG-15-S06-A070 | AW.PIPE.F4.UG-15.UG-15-S06 | F4 | UG-15 | UG-15-S06 | A070 | Trim piles, blinding and piled slab (incl. cure) | 12.9696 | m | 5 | 6 | UG-15-S06-A060 | 1 | 2 |  | 2026-12-17 | 2026-12-23 | 2026-12-23
UG-15-S06-A080 | AW.PIPE.F4.UG-15.UG-15-S06 | F4 | UG-15 | UG-15-S06 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 12.9696 | m | 4 | 5 | UG-15-S06-A070 | 2 | 2 | UG-15-S05-A080 (FS, closure) | 2026-12-24 | 2026-12-29 | 2026-12-29
UG-15-S06-A090 | AW.PIPE.F4.UG-15.UG-15-S06 | F4 | UG-15 | UG-15-S06 | A090 | Surround, joint test and line test | 12.9696 | m | 3 | 4 | UG-15-S06-A080 | 2 | 2 |  | 2026-12-26 | 2026-12-31
UG-15-S06-A100 | AW.PIPE.F4.UG-15.UG-15-S06 | F4 | UG-15 | UG-15-S06 | A100 | Backfill to NG and remove struts | 181.0941 | m3 | 1 | 2 | UG-15-S06-A090 | 2 | 2 |  | 2026-12-28 | 2027-01-02 | 2027-01-02
UG-15-S06-A110 | AW.PIPE.F4.UG-15.UG-15-S06 | F4 | UG-15 | UG-15-S06 | A110 | Dewatering off, extract sheets, reinstate | 25.9392 | m wall | 2 | 3 | UG-15-S06-A100 | 1 | 2 |  | 2026-12-29 | 2027-01-04
UG-15-S03-A010 | AW.PIPE.F4.UG-15.UG-15-S03 | F4 | UG-15 | UG-15-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-15-S03-A020 | AW.PIPE.F4.UG-15.UG-15-S03 | F4 | UG-15 | UG-15-S03 | A020 | Set-out, crossing survey and working platform | 57.3 | m | 1 | 2 | UG-15-S03-A010 |  |  | FS from A010; UG-15A-S02-A030 (SS, set-out one package ahead of piling) | 2026-12-10 | 2026-12-12
UG-15-S03-A030 | AW.PIPE.F4.UG-15.UG-15-S03 | F4 | UG-15 | UG-15-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 42 | piles | 9 | 11 | UG-15-S03-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-14 | 2026-12-25 | 2026-12-25 | UG-15A-S02-A030
UG-15-S03-A040 | AW.PIPE.F4.UG-15.UG-15-S03 | F4 | UG-15 | UG-15-S03 | A040 | Install sheet piles (shored lengths) | 114.6 | m wall | 5 | 6 | UG-15-S03-A030 | 4 | 2 |  | 2026-12-18 | 2026-12-27 | 2026-12-27 | UG-15A-S02-A040
UG-15-S03-A050 | AW.PIPE.F4.UG-15.UG-15-S03 | F4 | UG-15 | UG-15-S03 | A050 | Install dewatering and draw down | 57.3 | m | 9 | 11 | UG-15-S03-A040 | 2 | 2 | UG-15A-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2026-12-20 | 2026-12-31
UG-15-S03-A060 | AW.PIPE.F4.UG-15.UG-15-S03 | F4 | UG-15 | UG-15-S03 | A060 | Excavate and strut to formation | 1070.8789 | m3 | 5 | 6 | UG-15-S03-A050 | 10 | 2 |  | 2026-12-30 | 2027-01-05 | 2027-01-05 | UG-15A-S02-A060
UG-15-S03-A070 | AW.PIPE.F4.UG-15.UG-15-S03 | F4 | UG-15 | UG-15-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 57.3 | m | 8 | 10 | UG-15-S03-A060 | 2 | 2 |  | 2027-01-03 | 2027-01-13 | 2027-01-13 | UG-15A-S02-A070
UG-15-S03-A080 | AW.PIPE.F4.UG-15.UG-15-S03 | F4 | UG-15 | UG-15-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 57.3 | m | 3 | 4 | UG-15-S03-A070 | 3 | 2 |  | 2027-01-06 | 2027-01-15 | 2027-01-15 | UG-15A-S02-A080
UG-15-S03-A090 | AW.PIPE.F4.UG-15.UG-15-S03 | F4 | UG-15 | UG-15-S03 | A090 | Surround, joint test and line test | 57.3 | m | 3 | 4 | UG-15-S03-A080 | 2 | 2 |  | 2027-01-08 | 2027-01-17
UG-15-S03-A100 | AW.PIPE.F4.UG-15.UG-15-S03 | F4 | UG-15 | UG-15-S03 | A100 | Backfill to NG and remove struts | 796.2403 | m3 | 3 | 4 | UG-15-S03-A090 | 2 | 2 |  | 2027-01-11 | 2027-01-19 | 2027-01-19 | UG-15A-S02-A100
UG-15-S03-A110 | AW.PIPE.F4.UG-15.UG-15-S03 | F4 | UG-15 | UG-15-S03 | A110 | Dewatering off, extract sheets, reinstate | 114.6 | m wall | 4 | 5 | UG-15-S03-A100 | 2 | 2 |  | 2027-01-13 | 2027-01-21
UG-15-S02-A010 | AW.PIPE.F4.UG-15.UG-15-S02 | F4 | UG-15 | UG-15-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-15-S02-A020 | AW.PIPE.F4.UG-15.UG-15-S02 | F4 | UG-15 | UG-15-S02 | A020 | Set-out, crossing survey and working platform | 16.1 | m | 1 | 2 | UG-15-S02-A010 |  |  | FS from A010; UG-15-S03-A030 (SS, set-out one package ahead of piling) | 2026-12-14 | 2026-12-16
UG-15-S02-A030 | AW.PIPE.F4.UG-15.UG-15-S02 | F4 | UG-15 | UG-15-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 14 | piles | 3 | 4 | UG-15-S02-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-25 | 2026-12-29 | 2026-12-29 | UG-15-S03-A030
UG-15-S02-A040 | AW.PIPE.F4.UG-15.UG-15-S02 | F4 | UG-15 | UG-15-S02 | A040 | Install sheet piles (shored lengths) | 32.2 | m wall | 2 | 3 | UG-15-S02-A030 | 2 | 2 |  | 2026-12-27 | 2026-12-31 | 2026-12-31 | UG-15-S03-A040
UG-15-S02-A050 | AW.PIPE.F4.UG-15.UG-15-S02 | F4 | UG-15 | UG-15-S02 | A050 | Install dewatering and draw down | 16.1 | m | 8 | 10 | UG-15-S02-A040 | 1 | 2 | UG-15-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2026-12-28 | 2027-01-07
UG-15-S02-A060 | AW.PIPE.F4.UG-15.UG-15-S02 | F4 | UG-15 | UG-15-S02 | A060 | Excavate and strut to formation | 301.0671 | m3 | 2 | 3 | UG-15-S02-A050 | 10 | 2 |  | 2027-01-07 | 2027-01-10 | 2027-01-10 | UG-15-S03-A060
UG-15-S02-A070 | AW.PIPE.F4.UG-15.UG-15-S02 | F4 | UG-15 | UG-15-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 16.1 | m | 5 | 6 | UG-15-S02-A060 | 1 | 2 |  | 2027-01-13 | 2027-01-19 | 2027-01-19 | UG-15-S03-A070
UG-15-S02-A080 | AW.PIPE.F4.UG-15.UG-15-S02 | F4 | UG-15 | UG-15-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 16.1 | m | 1 | 2 | UG-15-S02-A070 | 2 | 2 |  | 2027-01-15 | 2027-01-21 | 2027-01-21 | UG-15-S03-A080
UG-15-S02-A090 | AW.PIPE.F4.UG-15.UG-15-S02 | F4 | UG-15 | UG-15-S02 | A090 | Surround, joint test and line test | 16.1 | m | 3 | 4 | UG-15-S02-A080 | 1 | 2 |  | 2027-01-16 | 2027-01-23
UG-15-S02-A100 | AW.PIPE.F4.UG-15.UG-15-S02 | F4 | UG-15 | UG-15-S02 | A100 | Backfill to NG and remove struts | 223.8999 | m3 | 1 | 2 | UG-15-S02-A090 | 2 | 2 |  | 2027-01-19 | 2027-01-25 | 2027-01-25 | UG-15-S03-A100
UG-15-S02-A110 | AW.PIPE.F4.UG-15.UG-15-S02 | F4 | UG-15 | UG-15-S02 | A110 | Dewatering off, extract sheets, reinstate | 32.2 | m wall | 2 | 3 | UG-15-S02-A100 | 1 | 2 |  | 2027-01-20 | 2027-01-27
UG-07-S02-A010 | AW.PIPE.F4.UG-07.UG-07-S02 | F4 | UG-07 | UG-07-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-07-S02-A020 | AW.PIPE.F4.UG-07.UG-07-S02 | F4 | UG-07 | UG-07-S02 | A020 | Set-out, crossing survey and working platform | 35.2658 | m | 1 | 2 | UG-07-S02-A010 |  |  | FS from A010; UG-15-S02-A030 (SS, set-out one package ahead of piling) | 2026-12-25 | 2026-12-27
UG-07-S02-A030 | AW.PIPE.F4.UG-07.UG-07-S02 | F4 | UG-07 | UG-07-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 26 | piles | 6 | 7 | UG-07-S02-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-29 | 2027-01-05 | 2027-01-05 | UG-15-S02-A030
UG-07-S02-A040 | AW.PIPE.F4.UG-07.UG-07-S02 | F4 | UG-07 | UG-07-S02 | A040 | Install sheet piles (shored lengths) | 66.4773 | m wall | 3 | 4 | UG-07-S02-A030 | 3 | 2 |  | 2027-01-01 | 2027-01-07 | 2027-01-07 | UG-15-S02-A040
UG-07-S02-A050 | AW.PIPE.F4.UG-07.UG-07-S02 | F4 | UG-07 | UG-07-S02 | A050 | Install dewatering and draw down | 35.2658 | m | 8 | 10 | UG-07-S02-A040 | 2 | 2 | UG-15-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-03 | 2027-01-13
UG-07-S02-A060 | AW.PIPE.F4.UG-07.UG-07-S02 | F4 | UG-07 | UG-07-S02 | A060 | Excavate and strut to formation | 544.6032 | m3 | 3 | 4 | UG-07-S02-A050 | 10 | 2 | UG-12-S05-A100 (FS, deeper first); UG-12-S06-A100 (FS, deeper first) | 2027-03-13 | 2027-03-17 | 2027-03-17 | UG-15-S02-A060
UG-07-S02-A070 | AW.PIPE.F4.UG-07.UG-07-S02 | F4 | UG-07 | UG-07-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 35.2658 | m | 6 | 7 | UG-07-S02-A060 | 2 | 2 |  | 2027-03-15 | 2027-03-22 | 2027-03-22 | UG-15-S02-A070
UG-07-S02-A080 | AW.PIPE.F4.UG-07.UG-07-S02 | F4 | UG-07 | UG-07-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 35.2658 | m | 3 | 4 | UG-07-S02-A070 | 3 | 2 |  | 2027-03-18 | 2027-03-24 | 2027-03-24 | UG-15-S02-A080
UG-07-S02-A090 | AW.PIPE.F4.UG-07.UG-07-S02 | F4 | UG-07 | UG-07-S02 | A090 | Surround, joint test and line test | 35.2658 | m | 3 | 4 | UG-07-S02-A080 | 2 | 2 |  | 2027-03-20 | 2027-03-26
UG-07-S02-A100 | AW.PIPE.F4.UG-07.UG-07-S02 | F4 | UG-07 | UG-07-S02 | A100 | Backfill to NG and remove struts | 371.8415 | m3 | 2 | 3 | UG-07-S02-A090 | 2 | 2 | UG-07A-S09-A080 (FS, shared trench laid); UG-07A-S12-A080 (FS, shared trench laid) | 2027-04-12 | 2027-04-15 | 2027-04-15 | UG-15-S02-A100
UG-07-S02-A110 | AW.PIPE.F4.UG-07.UG-07-S02 | F4 | UG-07 | UG-07-S02 | A110 | Dewatering off, extract sheets, reinstate | 66.4773 | m wall | 3 | 4 | UG-07-S02-A100 | 1 | 2 |  | 2027-04-13 | 2027-04-17
UG-07A-S12-A010 | AW.PIPE.F4.UG-07A.UG-07A-S12 | F4 | UG-07A | UG-07A-S12 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-07A-S12-A020 | AW.PIPE.F4.UG-07A.UG-07A-S12 | F4 | UG-07A | UG-07A-S12 | A020 | Set-out, crossing survey and working platform | 32.069 | m | 1 | 2 | UG-07A-S12-A010 |  |  | FS from A010; UG-07-S02-A030 (SS, set-out one package ahead of piling) | 2026-12-29 | 2026-12-31
UG-07A-S12-A030 | AW.PIPE.F4.UG-07A.UG-07A-S12 | F4 | UG-07A | UG-07A-S12 | A030 | Pipe-support piling from platform (incl. integrity tests) | 24 | piles | 5 | 6 | UG-07A-S12-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-05 | 2027-01-11 | 2027-01-11 | UG-07-S02-A030
UG-07A-S12-A040 | AW.PIPE.F4.UG-07A.UG-07A-S12 | F4 | UG-07A | UG-07A-S12 | A040 | Install sheet piles (shored lengths) | 59.8 | m wall | 3 | 4 | UG-07A-S12-A030 | 2 | 2 |  | 2027-01-07 | 2027-01-13 | 2027-01-13 | UG-07-S02-A040
UG-07A-S12-A050 | AW.PIPE.F4.UG-07A.UG-07A-S12 | F4 | UG-07A | UG-07A-S12 | A050 | Install dewatering and draw down | 32.069 | m | 8 | 10 | UG-07A-S12-A040 | 2 | 2 | UG-07-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-07 | 2027-03-17
UG-07A-S12-A060 | AW.PIPE.F4.UG-07A.UG-07A-S12 | F4 | UG-07A | UG-07A-S12 | A060 | Excavate and strut to formation | 422.933 | m3 | 2 | 3 | UG-07A-S12-A050 | 10 | 2 | UG-12-S04-A100 (FS, deeper first); UG-12-S05-A100 (FS, deeper first); UG-12-S06-A100 (FS, deeper first); UG-07-S02-A060 (SS, shared trench) | 2027-03-17 | 2027-03-20 | 2027-03-20 | UG-07-S02-A060
UG-07A-S12-A070 | AW.PIPE.F4.UG-07A.UG-07A-S12 | F4 | UG-07A | UG-07A-S12 | A070 | Trim piles, blinding and piled slab (incl. cure) | 32.069 | m | 6 | 7 | UG-07A-S12-A060 | 1 | 2 |  | 2027-03-22 | 2027-03-29 | 2027-03-29 | UG-07-S02-A070
UG-07A-S12-A080 | AW.PIPE.F4.UG-07A.UG-07A-S12 | F4 | UG-07A | UG-07A-S12 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 32.069 | m | 3 | 4 | UG-07A-S12-A070 | 3 | 2 |  | 2027-03-25 | 2027-03-31 | 2027-03-31 | UG-07-S02-A080
UG-07A-S12-A090 | AW.PIPE.F4.UG-07A.UG-07A-S12 | F4 | UG-07A | UG-07A-S12 | A090 | Surround, joint test and line test | 32.069 | m | 3 | 4 | UG-07A-S12-A080 | 2 | 2 |  | 2027-03-27 | 2027-04-02
UG-07A-S12-A100 | AW.PIPE.F4.UG-07A.UG-07A-S12 | F4 | UG-07A | UG-07A-S12 | A100 | Backfill to NG and remove struts | 350.9956 | m3 | 2 | 3 | UG-07A-S12-A090 | 2 | 2 | UG-07-S01-A080 (FS, shared trench laid); UG-07-S02-A080 (FS, shared trench laid) | 2027-04-15 | 2027-04-18 | 2027-04-18 | UG-07-S02-A100
UG-07A-S12-A110 | AW.PIPE.F4.UG-07A.UG-07A-S12 | F4 | UG-07A | UG-07A-S12 | A110 | Dewatering off, extract sheets, reinstate | 59.8 | m wall | 3 | 4 | UG-07A-S12-A100 | 1 | 2 |  | 2027-04-16 | 2027-04-20
UG-07-S01-A010 | AW.PIPE.F4.UG-07.UG-07-S01 | F4 | UG-07 | UG-07-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-07-S01-A020 | AW.PIPE.F4.UG-07.UG-07-S01 | F4 | UG-07 | UG-07-S01 | A020 | Set-out, crossing survey and working platform | 20.2342 | m | 1 | 2 | UG-07-S01-A010 |  |  | FS from A010; UG-07A-S12-A030 (SS, set-out one package ahead of piling) | 2027-01-05 | 2027-01-07
UG-07-S01-A030 | AW.PIPE.F4.UG-07.UG-07-S01 | F4 | UG-07 | UG-07-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 16 | piles | 4 | 5 | UG-07-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-11 | 2027-01-16 | 2027-01-16 | UG-07A-S12-A030
UG-07-S01-A040 | AW.PIPE.F4.UG-07.UG-07-S01 | F4 | UG-07 | UG-07-S01 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-07-S01-A030 | 2 | 0 |  | 2027-01-13 | 2027-01-16 | 2027-01-13 | UG-07A-S12-A040
UG-07-S01-A050 | AW.PIPE.F4.UG-07.UG-07-S01 | F4 | UG-07 | UG-07-S01 | A050 | Install dewatering and draw down | 20.2342 | m | 8 | 10 | UG-07-S01-A040 | 0 | 2 | UG-07A-S12-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-10 | 2027-03-20
UG-07-S01-A060 | AW.PIPE.F4.UG-07.UG-07-S01 | F4 | UG-07 | UG-07-S01 | A060 | Excavate and strut to formation | 497.8143 | m3 | 2 | 3 | UG-07-S01-A050 | 10 | 2 | UG-12-S06-A100 (FS, deeper first); UG-07A-S12-A060 (SS, shared trench) | 2027-03-20 | 2027-03-23 | 2027-03-23 | UG-07A-S12-A060
UG-07-S01-A070 | AW.PIPE.F4.UG-07.UG-07-S01 | F4 | UG-07 | UG-07-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 20.2342 | m | 5 | 6 | UG-07-S01-A060 | 1 | 2 |  | 2027-03-29 | 2027-04-04 | 2027-04-04 | UG-07A-S12-A070
UG-07-S01-A080 | AW.PIPE.F4.UG-07.UG-07-S01 | F4 | UG-07 | UG-07-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 20.2342 | m | 4 | 5 | UG-07-S01-A070 | 2 | 2 |  | 2027-03-31 | 2027-04-06 | 2027-04-06 | UG-07A-S12-A080
UG-07-S01-A090 | AW.PIPE.F4.UG-07.UG-07-S01 | F4 | UG-07 | UG-07-S01 | A090 | Surround, joint test and line test | 20.2342 | m | 3 | 4 | UG-07-S01-A080 | 2 | 2 |  | 2027-04-02 | 2027-04-08
UG-07-S01-A100 | AW.PIPE.F4.UG-07.UG-07-S01 | F4 | UG-07 | UG-07-S01 | A100 | Backfill to NG and remove struts | 398.9659 | m3 | 2 | 3 | UG-07-S01-A090 | 2 | 2 | UG-07A-S05-A080 (FS, shared trench laid); UG-07A-S09-A080 (FS, shared trench laid); UG-07A-S12-A080 (FS, shared trench laid) | 2027-04-18 | 2027-04-21 | 2027-04-21 | UG-07A-S12-A100
UG-07-S01-A110 | AW.PIPE.F4.UG-07.UG-07-S01 | F4 | UG-07 | UG-07-S01 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-07-S01-A100 | 1 | 2 |  | 2027-04-19 | 2027-04-23
UG-07A-S09-A010 | AW.PIPE.F4.UG-07A.UG-07A-S09 | F4 | UG-07A | UG-07A-S09 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-07A-S09-A020 | AW.PIPE.F4.UG-07A.UG-07A-S09 | F4 | UG-07A | UG-07A-S09 | A020 | Set-out, crossing survey and working platform | 12.1656 | m | 1 | 2 | UG-07A-S09-A010 |  |  | FS from A010; UG-07-S01-A030 (SS, set-out one package ahead of piling) | 2027-01-11 | 2027-01-13
UG-07A-S09-A030 | AW.PIPE.F4.UG-07A.UG-07A-S09 | F4 | UG-07A | UG-07A-S09 | A030 | Pipe-support piling from platform (incl. integrity tests) | 12 | piles | 3 | 4 | UG-07A-S09-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-16 | 2027-01-20 | 2027-01-20 | UG-07-S01-A030
UG-07A-S09-A040 | AW.PIPE.F4.UG-07A.UG-07A-S09 | F4 | UG-07A | UG-07A-S09 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-07A-S09-A030 | 2 | 0 |  | 2027-01-18 | 2027-01-20 | 2027-01-13 | UG-07-S01-A040
UG-07A-S09-A050 | AW.PIPE.F4.UG-07A.UG-07A-S09 | F4 | UG-07A | UG-07A-S09 | A050 | Install dewatering and draw down | 12.1656 | m | 8 | 10 | UG-07A-S09-A040 | 0 | 2 | UG-07-S01-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-13 | 2027-03-23
UG-07A-S09-A060 | AW.PIPE.F4.UG-07A.UG-07A-S09 | F4 | UG-07A | UG-07A-S09 | A060 | Excavate and strut to formation | 211.0052 | m3 | 1 | 2 | UG-07A-S09-A050 | 10 | 2 | UG-07-S01-A060 (SS, shared trench); UG-07-S02-A060 (SS, shared trench) | 2027-03-23 | 2027-03-25 | 2027-03-25 | UG-07-S01-A060
UG-07A-S09-A070 | AW.PIPE.F4.UG-07A.UG-07A-S09 | F4 | UG-07A | UG-07A-S09 | A070 | Trim piles, blinding and piled slab (incl. cure) | 12.1656 | m | 5 | 6 | UG-07A-S09-A060 | 1 | 2 |  | 2027-04-04 | 2027-04-10 | 2027-04-10 | UG-07-S01-A070
UG-07A-S09-A080 | AW.PIPE.F4.UG-07A.UG-07A-S09 | F4 | UG-07A | UG-07A-S09 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 12.1656 | m | 1 | 2 | UG-07A-S09-A070 | 2 | 2 |  | 2027-04-06 | 2027-04-12 | 2027-04-12 | UG-07-S01-A080
UG-07A-S09-A090 | AW.PIPE.F4.UG-07A.UG-07A-S09 | F4 | UG-07A | UG-07A-S09 | A090 | Surround, joint test and line test | 12.1656 | m | 3 | 4 | UG-07A-S09-A080 | 1 | 2 |  | 2027-04-07 | 2027-04-14
UG-07A-S09-A100 | AW.PIPE.F4.UG-07A.UG-07A-S09 | F4 | UG-07A | UG-07A-S09 | A100 | Backfill to NG and remove struts | 183.4946 | m3 | 1 | 2 | UG-07A-S09-A090 | 2 | 2 | UG-07-S01-A080 (FS, shared trench laid); UG-07-S02-A080 (FS, shared trench laid) | 2027-04-21 | 2027-04-23 | 2027-04-23 | UG-07-S01-A100
UG-07A-S09-A110 | AW.PIPE.F4.UG-07A.UG-07A-S09 | F4 | UG-07A | UG-07A-S09 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-07A-S09-A100 | 1 | 2 |  | 2027-04-22 | 2027-04-25
UG-07A-S05-A010 | AW.PIPE.F4.UG-07A.UG-07A-S05 | F4 | UG-07A | UG-07A-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-07A-S05-A020 | AW.PIPE.F4.UG-07A.UG-07A-S05 | F4 | UG-07A | UG-07A-S05 | A020 | Set-out, crossing survey and working platform | 23.4913 | m | 1 | 2 | UG-07A-S05-A010 |  |  | FS from A010; UG-07A-S09-A030 (SS, set-out one package ahead of piling) | 2027-01-16 | 2027-01-18
UG-07A-S05-A030 | AW.PIPE.F4.UG-07A.UG-07A-S05 | F4 | UG-07A | UG-07A-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 18 | piles | 4 | 5 | UG-07A-S05-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-20 | 2027-01-25 | 2027-01-25 | UG-07A-S09-A030
UG-07A-S05-A040 | AW.PIPE.F4.UG-07A.UG-07A-S05 | F4 | UG-07A | UG-07A-S05 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-07A-S05-A030 | 2 | 0 |  | 2027-01-22 | 2027-01-25 | 2027-01-13 | UG-07A-S09-A040
UG-07A-S05-A050 | AW.PIPE.F4.UG-07A.UG-07A-S05 | F4 | UG-07A | UG-07A-S05 | A050 | Install dewatering and draw down | 23.4913 | m | 8 | 10 | UG-07A-S05-A040 | 0 | 2 | UG-07A-S09-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-15 | 2027-03-25
UG-07A-S05-A060 | AW.PIPE.F4.UG-07A.UG-07A-S05 | F4 | UG-07A | UG-07A-S05 | A060 | Excavate and strut to formation | 397.7874 | m3 | 1 | 2 | UG-07A-S05-A050 | 10 | 2 | UG-07-S01-A060 (SS, shared trench) | 2027-03-25 | 2027-03-27 | 2027-03-27 | UG-07A-S09-A060
UG-07A-S05-A070 | AW.PIPE.F4.UG-07A.UG-07A-S05 | F4 | UG-07A | UG-07A-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 23.4913 | m | 5 | 6 | UG-07A-S05-A060 | 1 | 2 |  | 2027-04-10 | 2027-04-16 | 2027-04-16 | UG-07A-S09-A070
UG-07A-S05-A080 | AW.PIPE.F4.UG-07A.UG-07A-S05 | F4 | UG-07A | UG-07A-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 23.4913 | m | 2 | 3 | UG-07A-S05-A070 | 2 | 2 |  | 2027-04-12 | 2027-04-18 | 2027-04-18 | UG-07A-S09-A080
UG-07A-S05-A090 | AW.PIPE.F4.UG-07A.UG-07A-S05 | F4 | UG-07A | UG-07A-S05 | A090 | Surround, joint test and line test | 23.4913 | m | 3 | 4 | UG-07A-S05-A080 | 1 | 2 |  | 2027-04-13 | 2027-04-20
UG-07A-S05-A100 | AW.PIPE.F4.UG-07A.UG-07A-S05 | F4 | UG-07A | UG-07A-S05 | A100 | Backfill to NG and remove struts | 319.6792 | m3 | 1 | 2 | UG-07A-S05-A090 | 2 | 2 | UG-07-S01-A080 (FS, shared trench laid) | 2027-04-23 | 2027-04-25 | 2027-04-25 | UG-07A-S09-A100
UG-07A-S05-A110 | AW.PIPE.F4.UG-07A.UG-07A-S05 | F4 | UG-07A | UG-07A-S05 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-07A-S05-A100 | 1 | 2 |  | 2027-04-24 | 2027-04-27
UG-15A-S01-A010 | AW.PIPE.F4.UG-15A.UG-15A-S01 | F4 | UG-15A | UG-15A-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-15A-S01-A020 | AW.PIPE.F4.UG-15A.UG-15A-S01 | F4 | UG-15A | UG-15A-S01 | A020 | Set-out, crossing survey and working platform | 6.033 | m | 1 | 2 | UG-15A-S01-A010 |  |  | FS from A010; UG-15A-S02-A030 (SS, tie-in team follows the adjacent run) | 2026-12-10 | 2026-12-12
UG-15A-S01-A030 | AW.PIPE.F4.UG-15A.UG-15A-S01 | F4 | UG-15A | UG-15A-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 8 | piles | 2 | 3 | UG-15A-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-11 | 2026-12-14 | 2026-12-14
UG-15A-S01-A040 | AW.PIPE.F4.UG-15A.UG-15A-S01 | F4 | UG-15A | UG-15A-S01 | A040 | Install sheet piles (shored lengths) | 12.0661 | m wall | 1 | 2 | UG-15A-S01-A030 | 1 | 2 |  | 2026-12-12 | 2026-12-16 | 2026-12-16
UG-15A-S01-A050 | AW.PIPE.F4.UG-15A.UG-15A-S01 | F4 | UG-15A | UG-15A-S01 | A050 | Install dewatering and draw down | 6.033 | m | 8 | 10 | UG-15A-S01-A040 | 1 | 2 |  | 2026-12-13 | 2026-12-23
UG-15A-S01-A060 | AW.PIPE.F4.UG-15A.UG-15A-S01 | F4 | UG-15A | UG-15A-S01 | A060 | Excavate and strut to formation | 81.0196 | m3 | 1 | 2 | UG-15A-S01-A050 | 10 | 2 |  | 2026-12-23 | 2026-12-25 | 2026-12-25
UG-15A-S01-A070 | AW.PIPE.F4.UG-15A.UG-15A-S01 | F4 | UG-15A | UG-15A-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6.033 | m | 4 | 5 | UG-15A-S01-A060 | 1 | 2 |  | 2026-12-24 | 2026-12-29 | 2026-12-29
UG-15A-S01-A080 | AW.PIPE.F4.UG-15A.UG-15A-S01 | F4 | UG-15A | UG-15A-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6.033 | m | 4 | 5 | UG-15A-S01-A070 | 2 | 2 | UG-15A-S02-A080 (FS, closure) | 2027-01-05 | 2027-01-10 | 2027-01-10
UG-15A-S01-A090 | AW.PIPE.F4.UG-15A.UG-15A-S01 | F4 | UG-15A | UG-15A-S01 | A090 | Surround, joint test and line test | 6.033 | m | 3 | 4 | UG-15A-S01-A080 | 2 | 2 |  | 2027-01-07 | 2027-01-12
UG-15A-S01-A100 | AW.PIPE.F4.UG-15A.UG-15A-S01 | F4 | UG-15A | UG-15A-S01 | A100 | Backfill to NG and remove struts | 67.5966 | m3 | 1 | 2 | UG-15A-S01-A090 | 2 | 2 |  | 2027-01-09 | 2027-01-14 | 2027-01-14
UG-15A-S01-A110 | AW.PIPE.F4.UG-15A.UG-15A-S01 | F4 | UG-15A | UG-15A-S01 | A110 | Dewatering off, extract sheets, reinstate | 12.0661 | m wall | 2 | 3 | UG-15A-S01-A100 | 1 | 2 |  | 2027-01-10 | 2027-01-16
UG-15A-S03-A010 | AW.PIPE.F4.UG-15A.UG-15A-S03 | F4 | UG-15A | UG-15A-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-15A-S03-A020 | AW.PIPE.F4.UG-15A.UG-15A-S03 | F4 | UG-15A | UG-15A-S03 | A020 | Set-out, crossing survey and working platform | 17.4504 | m | 1 | 2 | UG-15A-S03-A010 |  |  | FS from A010; UG-15A-S04-A030 (SS, tie-in team follows the adjacent run) | 2027-04-01 | 2027-04-03
UG-15A-S03-A030 | AW.PIPE.F4.UG-15A.UG-15A-S03 | F4 | UG-15A | UG-15A-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 14 | piles | 3 | 4 | UG-15A-S03-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-02 | 2027-04-06 | 2027-04-06
UG-15A-S03-A040 | AW.PIPE.F4.UG-15A.UG-15A-S03 | F4 | UG-15A | UG-15A-S03 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-15A-S03-A030 | 2 | 0 |  | 2027-04-04 | 2027-04-06 | 0
UG-15A-S03-A050 | AW.PIPE.F4.UG-15A.UG-15A-S03 | F4 | UG-15A | UG-15A-S03 | A050 | Install dewatering and draw down | 17.4504 | m | 8 | 10 | UG-15A-S03-A040 | 0 | 2 |  | 2027-04-04 | 2027-04-14
UG-15A-S03-A060 | AW.PIPE.F4.UG-15A.UG-15A-S03 | F4 | UG-15A | UG-15A-S03 | A060 | Excavate and strut to formation | 249.625 | m3 | 1 | 2 | UG-15A-S03-A050 | 10 | 2 | UG-11B-S05-A100 (FS, deeper first); UG-11B-S06-A100 (FS, deeper first); UG-17-S03-A100 (FS, deeper first); UG-17-S04-A100 (FS, deeper first) | 2027-06-21 | 2027-06-23 | 2027-06-23
UG-15A-S03-A070 | AW.PIPE.F4.UG-15A.UG-15A-S03 | F4 | UG-15A | UG-15A-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 17.4504 | m | 5 | 6 | UG-15A-S03-A060 | 1 | 2 |  | 2027-06-22 | 2027-06-28 | 2027-06-28
UG-15A-S03-A080 | AW.PIPE.F4.UG-15A.UG-15A-S03 | F4 | UG-15A | UG-15A-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 17.4504 | m | 5 | 6 | UG-15A-S03-A070 | 2 | 2 | UG-15A-S04-A080 (FS, closure) | 2027-06-24 | 2027-06-30 | 2027-06-30
UG-15A-S03-A090 | AW.PIPE.F4.UG-15A.UG-15A-S03 | F4 | UG-15A | UG-15A-S03 | A090 | Surround, joint test and line test | 17.4504 | m | 3 | 4 | UG-15A-S03-A080 | 2 | 2 |  | 2027-06-26 | 2027-07-02
UG-15A-S03-A100 | AW.PIPE.F4.UG-15A.UG-15A-S03 | F4 | UG-15A | UG-15A-S03 | A100 | Backfill to NG and remove struts | 210.6935 | m3 | 1 | 2 | UG-15A-S03-A090 | 2 | 2 |  | 2027-06-28 | 2027-07-04 | 2027-07-04
UG-15A-S03-A110 | AW.PIPE.F4.UG-15A.UG-15A-S03 | F4 | UG-15A | UG-15A-S03 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-15A-S03-A100 | 1 | 2 |  | 2027-06-29 | 2027-07-06
UG-15A-S07-A010 | AW.PIPE.F4.UG-15A.UG-15A-S07 | F4 | UG-15A | UG-15A-S07 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-15A-S07-A020 | AW.PIPE.F4.UG-15A.UG-15A-S07 | F4 | UG-15A | UG-15A-S07 | A020 | Set-out, crossing survey and working platform | 10.7128 | m | 1 | 2 | UG-15A-S07-A010 |  |  | FS from A010; UG-15A-S08-A030 (SS, tie-in team follows the adjacent run) | 2027-01-10 | 2027-01-12
UG-15A-S07-A030 | AW.PIPE.F4.UG-15A.UG-15A-S07 | F4 | UG-15A | UG-15A-S07 | A030 | Pipe-support piling from platform (incl. integrity tests) | 10 | piles | 2 | 3 | UG-15A-S07-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-11 | 2027-01-14 | 2027-01-14
UG-15A-S07-A040 | AW.PIPE.F4.UG-15A.UG-15A-S07 | F4 | UG-15A | UG-15A-S07 | A040 | Install sheet piles (shored lengths) | 21.4257 | m wall | 1 | 2 | UG-15A-S07-A030 | 1 | 2 |  | 2027-01-12 | 2027-01-16 | 2027-01-16
UG-15A-S07-A050 | AW.PIPE.F4.UG-15A.UG-15A-S07 | F4 | UG-15A | UG-15A-S07 | A050 | Install dewatering and draw down | 10.7128 | m | 8 | 10 | UG-15A-S07-A040 | 1 | 2 |  | 2027-01-13 | 2027-01-23
UG-15A-S07-A060 | AW.PIPE.F4.UG-15A.UG-15A-S07 | F4 | UG-15A | UG-15A-S07 | A060 | Excavate and strut to formation | 137.1195 | m3 | 1 | 2 | UG-15A-S07-A050 | 10 | 2 |  | 2027-01-23 | 2027-01-25 | 2027-01-25
UG-15A-S07-A070 | AW.PIPE.F4.UG-15A.UG-15A-S07 | F4 | UG-15A | UG-15A-S07 | A070 | Trim piles, blinding and piled slab (incl. cure) | 10.7128 | m | 4 | 5 | UG-15A-S07-A060 | 1 | 2 |  | 2027-01-24 | 2027-01-29 | 2027-01-29
UG-15A-S07-A080 | AW.PIPE.F4.UG-15A.UG-15A-S07 | F4 | UG-15A | UG-15A-S07 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 10.7128 | m | 4 | 5 | UG-15A-S07-A070 | 2 | 2 | UG-15A-S08-A080 (FS, closure) | 2027-02-16 | 2027-02-21 | 2027-02-21
UG-15A-S07-A090 | AW.PIPE.F4.UG-15A.UG-15A-S07 | F4 | UG-15A | UG-15A-S07 | A090 | Surround, joint test and line test | 10.7128 | m | 3 | 4 | UG-15A-S07-A080 | 2 | 2 |  | 2027-02-18 | 2027-02-23
UG-15A-S07-A100 | AW.PIPE.F4.UG-15A.UG-15A-S07 | F4 | UG-15A | UG-15A-S07 | A100 | Backfill to NG and remove struts | 113.2215 | m3 | 1 | 2 | UG-15A-S07-A090 | 2 | 2 |  | 2027-02-20 | 2027-02-25 | 2027-02-25
UG-15A-S07-A110 | AW.PIPE.F4.UG-15A.UG-15A-S07 | F4 | UG-15A | UG-15A-S07 | A110 | Dewatering off, extract sheets, reinstate | 21.4257 | m wall | 2 | 3 | UG-15A-S07-A100 | 1 | 2 |  | 2027-02-21 | 2027-02-27
UG-07A-S03-A010 | AW.PIPE.F4.UG-07A.UG-07A-S03 | F4 | UG-07A | UG-07A-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-07A-S03-A020 | AW.PIPE.F4.UG-07A.UG-07A-S03 | F4 | UG-07A | UG-07A-S03 | A020 | Set-out, crossing survey and working platform | 6.1264 | m | 1 | 2 | UG-07A-S03-A010 |  |  | FS from A010; UG-07A-S05-A030 (SS, set-out one package ahead of piling) | 2027-01-20 | 2027-01-22
UG-07A-S03-A030 | AW.PIPE.F4.UG-07A.UG-07A-S03 | F4 | UG-07A | UG-07A-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 8 | piles | 2 | 3 | UG-07A-S03-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-25 | 2027-01-28 | 2027-01-28 | UG-07A-S05-A030
UG-07A-S03-A040 | AW.PIPE.F4.UG-07A.UG-07A-S03 | F4 | UG-07A | UG-07A-S03 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-07A-S03-A030 | 1 | 0 |  | 2027-01-26 | 2027-01-28 | 2027-01-13 | UG-07A-S05-A040
UG-07A-S03-A050 | AW.PIPE.F4.UG-07A.UG-07A-S03 | F4 | UG-07A | UG-07A-S03 | A050 | Install dewatering and draw down | 6.1264 | m | 8 | 10 | UG-07A-S03-A040 | 0 | 2 | UG-07A-S05-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-17 | 2027-03-27
UG-07A-S03-A060 | AW.PIPE.F4.UG-07A.UG-07A-S03 | F4 | UG-07A | UG-07A-S03 | A060 | Excavate and strut to formation | 91.0697 | m3 | 1 | 2 | UG-07A-S03-A050 | 10 | 2 |  | 2027-03-27 | 2027-03-29 | 2027-03-29 | UG-07A-S05-A060
UG-07A-S03-A070 | AW.PIPE.F4.UG-07A.UG-07A-S03 | F4 | UG-07A | UG-07A-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6.1264 | m | 4 | 5 | UG-07A-S03-A060 | 1 | 2 |  | 2027-04-16 | 2027-04-21 | 2027-04-21 | UG-07A-S05-A070
UG-07A-S03-A080 | AW.PIPE.F4.UG-07A.UG-07A-S03 | F4 | UG-07A | UG-07A-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6.1264 | m | 1 | 2 | UG-07A-S03-A070 | 2 | 2 |  | 2027-04-18 | 2027-04-23 | 2027-04-23 | UG-07A-S05-A080
UG-07A-S03-A090 | AW.PIPE.F4.UG-07A.UG-07A-S03 | F4 | UG-07A | UG-07A-S03 | A090 | Surround, joint test and line test | 6.1264 | m | 3 | 4 | UG-07A-S03-A080 | 1 | 2 |  | 2027-04-19 | 2027-04-25
UG-07A-S03-A100 | AW.PIPE.F4.UG-07A.UG-07A-S03 | F4 | UG-07A | UG-07A-S03 | A100 | Backfill to NG and remove struts | 70.7877 | m3 | 1 | 2 | UG-07A-S03-A090 | 2 | 2 |  | 2027-04-25 | 2027-04-27 | 2027-04-27 | UG-07A-S05-A100
UG-07A-S03-A110 | AW.PIPE.F4.UG-07A.UG-07A-S03 | F4 | UG-07A | UG-07A-S03 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-07A-S03-A100 | 1 | 2 |  | 2027-04-26 | 2027-04-29
UG-07A-S02-A010 | AW.PIPE.F4.UG-07A.UG-07A-S02 | F4 | UG-07A | UG-07A-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-07A-S02-A020 | AW.PIPE.F4.UG-07A.UG-07A-S02 | F4 | UG-07A | UG-07A-S02 | A020 | Set-out, crossing survey and working platform | 132.377 | m | 2 | 3 | UG-07A-S02-A010 |  |  | FS from A010; UG-07A-S03-A030 (SS, set-out one package ahead of piling) | 2027-01-25 | 2027-01-28
UG-07A-S02-A030 | AW.PIPE.F4.UG-07A.UG-07A-S02 | F4 | UG-07A | UG-07A-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 92 | piles | 19 | 23 | UG-07A-S02-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-28 | 2027-02-20 | 2027-02-20 | UG-07A-S03-A030
UG-07A-S02-A040 | AW.PIPE.F4.UG-07A.UG-07A-S02 | F4 | UG-07A | UG-07A-S02 | A040 | Install sheet piles (shored lengths) | 135.5672 | m wall | 6 | 7 | UG-07A-S02-A030 | 7 | 2 |  | 2027-02-04 | 2027-02-22 | 2027-02-22 | UG-07A-S03-A040
UG-07A-S02-A050 | AW.PIPE.F4.UG-07A.UG-07A-S02 | F4 | UG-07A | UG-07A-S02 | A050 | Install dewatering and draw down | 132.377 | m | 11 | 13 | UG-07A-S02-A040 | 3 | 2 | UG-07A-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-16 | 2027-03-29
UG-07A-S02-A060 | AW.PIPE.F4.UG-07A.UG-07A-S02 | F4 | UG-07A | UG-07A-S02 | A060 | Excavate and strut to formation | 1182.8711 | m3 | 4 | 5 | UG-07A-S02-A050 | 11 | 2 |  | 2027-03-29 | 2027-04-03 | 2027-04-03 | UG-07A-S03-A060
UG-07A-S02-A070 | AW.PIPE.F4.UG-07A.UG-07A-S02 | F4 | UG-07A | UG-07A-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 132.377 | m | 15 | 18 | UG-07A-S02-A060 | 2 | 2 |  | 2027-04-21 | 2027-05-09 | 2027-05-09 | UG-07A-S03-A070
UG-07A-S02-A080 | AW.PIPE.F4.UG-07A.UG-07A-S02 | F4 | UG-07A | UG-07A-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 132.377 | m | 9 | 11 | UG-07A-S02-A070 | 6 | 2 |  | 2027-04-27 | 2027-05-11 | 2027-05-11 | UG-07A-S03-A080
UG-07A-S02-A090 | AW.PIPE.F4.UG-07A.UG-07A-S02 | F4 | UG-07A | UG-07A-S02 | A090 | Surround, joint test and line test | 132.377 | m | 3 | 4 | UG-07A-S02-A080 | 4 | 2 |  | 2027-05-01 | 2027-05-13
UG-07A-S02-A100 | AW.PIPE.F4.UG-07A.UG-07A-S02 | F4 | UG-07A | UG-07A-S02 | A100 | Backfill to NG and remove struts | 877.388 | m3 | 3 | 4 | UG-07A-S02-A090 | 2 | 2 |  | 2027-05-03 | 2027-05-15 | 2027-05-15 | UG-07A-S03-A100
UG-07A-S02-A110 | AW.PIPE.F4.UG-07A.UG-07A-S02 | F4 | UG-07A | UG-07A-S02 | A110 | Dewatering off, extract sheets, reinstate | 135.5672 | m wall | 4 | 5 | UG-07A-S02-A100 | 2 | 2 |  | 2027-05-05 | 2027-05-17
UG-07A-S01-A010 | AW.PIPE.F4.UG-07A.UG-07A-S01 | F4 | UG-07A | UG-07A-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-07A-S01-A020 | AW.PIPE.F4.UG-07A.UG-07A-S01 | F4 | UG-07A | UG-07A-S01 | A020 | Set-out, crossing survey and working platform | 18.6967 | m | 1 | 2 | UG-07A-S01-A010 |  |  | FS from A010; UG-07A-S02-A030 (SS, tie-in team follows the adjacent run) | 2027-01-28 | 2027-01-30
UG-07A-S01-A030 | AW.PIPE.F4.UG-07A.UG-07A-S01 | F4 | UG-07A | UG-07A-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 16 | piles | 4 | 5 | UG-07A-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-29 | 2027-02-03 | 2027-02-03
UG-07A-S01-A040 | AW.PIPE.F4.UG-07A.UG-07A-S01 | F4 | UG-07A | UG-07A-S01 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-07A-S01-A030 | 2 | 0 |  | 2027-01-31 | 2027-02-03 | 0
UG-07A-S01-A050 | AW.PIPE.F4.UG-07A.UG-07A-S01 | F4 | UG-07A | UG-07A-S01 | A050 | Install dewatering and draw down | 18.6967 | m | 8 | 10 | UG-07A-S01-A040 | 0 | 2 |  | 2027-01-31 | 2027-02-10
UG-07A-S01-A060 | AW.PIPE.F4.UG-07A.UG-07A-S01 | F4 | UG-07A | UG-07A-S01 | A060 | Excavate and strut to formation | 222.8593 | m3 | 1 | 2 | UG-07A-S01-A050 | 10 | 2 |  | 2027-02-10 | 2027-02-12 | 2027-02-12
UG-07A-S01-A070 | AW.PIPE.F4.UG-07A.UG-07A-S01 | F4 | UG-07A | UG-07A-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 18.6967 | m | 5 | 6 | UG-07A-S01-A060 | 1 | 2 |  | 2027-02-11 | 2027-02-17 | 2027-02-17
UG-07A-S01-A080 | AW.PIPE.F4.UG-07A.UG-07A-S01 | F4 | UG-07A | UG-07A-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 18.6967 | m | 5 | 6 | UG-07A-S01-A070 | 2 | 2 | UG-07A-S02-A080 (FS, closure) | 2027-05-11 | 2027-05-17 | 2027-05-17
UG-07A-S01-A090 | AW.PIPE.F4.UG-07A.UG-07A-S01 | F4 | UG-07A | UG-07A-S01 | A090 | Surround, joint test and line test | 18.6967 | m | 3 | 4 | UG-07A-S01-A080 | 2 | 2 |  | 2027-05-13 | 2027-05-19
UG-07A-S01-A100 | AW.PIPE.F4.UG-07A.UG-07A-S01 | F4 | UG-07A | UG-07A-S01 | A100 | Backfill to NG and remove struts | 181.1481 | m3 | 1 | 2 | UG-07A-S01-A090 | 2 | 2 |  | 2027-05-15 | 2027-05-21 | 2027-05-21
UG-07A-S01-A110 | AW.PIPE.F4.UG-07A.UG-07A-S01 | F4 | UG-07A | UG-07A-S01 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-07A-S01-A100 | 1 | 2 |  | 2027-05-16 | 2027-05-23
UG-07A-S07-A010 | AW.PIPE.F4.UG-07A.UG-07A-S07 | F4 | UG-07A | UG-07A-S07 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-07A-S07-A020 | AW.PIPE.F4.UG-07A.UG-07A-S07 | F4 | UG-07A | UG-07A-S07 | A020 | Set-out, crossing survey and working platform | 22.5092 | m | 1 | 2 | UG-07A-S07-A010 |  |  | FS from A010; UG-07A-S02-A030 (SS, set-out one package ahead of piling) | 2027-01-28 | 2027-01-30
UG-07A-S07-A030 | AW.PIPE.F4.UG-07A.UG-07A-S07 | F4 | UG-07A | UG-07A-S07 | A030 | Pipe-support piling from platform (incl. integrity tests) | 18 | piles | 4 | 5 | UG-07A-S07-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-20 | 2027-02-25 | 2027-02-25 | UG-07A-S02-A030
UG-07A-S07-A040 | AW.PIPE.F4.UG-07A.UG-07A-S07 | F4 | UG-07A | UG-07A-S07 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-07A-S07-A030 | 2 | 0 |  | 2027-02-22 | 2027-02-25 | 2027-02-22 | UG-07A-S02-A040
UG-07A-S07-A050 | AW.PIPE.F4.UG-07A.UG-07A-S07 | F4 | UG-07A | UG-07A-S07 | A050 | Install dewatering and draw down | 22.5092 | m | 8 | 10 | UG-07A-S07-A040 | 0 | 2 | UG-07A-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-24 | 2027-04-03
UG-07A-S07-A060 | AW.PIPE.F4.UG-07A.UG-07A-S07 | F4 | UG-07A | UG-07A-S07 | A060 | Excavate and strut to formation | 268.2987 | m3 | 1 | 2 | UG-07A-S07-A050 | 10 | 2 |  | 2027-04-03 | 2027-04-05 | 2027-04-05 | UG-07A-S02-A060
UG-07A-S07-A070 | AW.PIPE.F4.UG-07A.UG-07A-S07 | F4 | UG-07A | UG-07A-S07 | A070 | Trim piles, blinding and piled slab (incl. cure) | 22.5092 | m | 5 | 6 | UG-07A-S07-A060 | 1 | 2 |  | 2027-05-09 | 2027-05-15 | 2027-05-15 | UG-07A-S02-A070
UG-07A-S07-A080 | AW.PIPE.F4.UG-07A.UG-07A-S07 | F4 | UG-07A | UG-07A-S07 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 22.5092 | m | 2 | 3 | UG-07A-S07-A070 | 2 | 2 |  | 2027-05-11 | 2027-05-17 | 2027-05-17 | UG-07A-S02-A080
UG-07A-S07-A090 | AW.PIPE.F4.UG-07A.UG-07A-S07 | F4 | UG-07A | UG-07A-S07 | A090 | Surround, joint test and line test | 22.5092 | m | 3 | 4 | UG-07A-S07-A080 | 1 | 2 |  | 2027-05-12 | 2027-05-19
UG-07A-S07-A100 | AW.PIPE.F4.UG-07A.UG-07A-S07 | F4 | UG-07A | UG-07A-S07 | A100 | Backfill to NG and remove struts | 218.0813 | m3 | 1 | 2 | UG-07A-S07-A090 | 2 | 2 |  | 2027-05-15 | 2027-05-21 | 2027-05-21 | UG-07A-S02-A100
UG-07A-S07-A110 | AW.PIPE.F4.UG-07A.UG-07A-S07 | F4 | UG-07A | UG-07A-S07 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-07A-S07-A100 | 1 | 2 |  | 2027-05-16 | 2027-05-23
UG-07A-S08-A010 | AW.PIPE.F4.UG-07A.UG-07A-S08 | F4 | UG-07A | UG-07A-S08 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-07A-S08-A020 | AW.PIPE.F4.UG-07A.UG-07A-S08 | F4 | UG-07A | UG-07A-S08 | A020 | Set-out, crossing survey and working platform | 2.9324 | m | 1 | 2 | UG-07A-S08-A010 |  |  | FS from A010; UG-07A-S09-A030 (SS, tie-in team follows the adjacent run) | 2027-01-16 | 2027-01-18
UG-07A-S08-A030 | AW.PIPE.F4.UG-07A.UG-07A-S08 | F4 | UG-07A | UG-07A-S08 | A030 | Pipe-support piling from platform (incl. integrity tests) | 4 | piles | 1 | 2 | UG-07A-S08-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-17 | 2027-01-20 | 2027-01-20
UG-07A-S08-A040 | AW.PIPE.F4.UG-07A.UG-07A-S08 | F4 | UG-07A | UG-07A-S08 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-07A-S08-A030 | 1 | 0 |  | 2027-01-18 | 2027-01-20 | 0
UG-07A-S08-A050 | AW.PIPE.F4.UG-07A.UG-07A-S08 | F4 | UG-07A | UG-07A-S08 | A050 | Install dewatering and draw down | 2.9324 | m | 8 | 10 | UG-07A-S08-A040 | 0 | 2 |  | 2027-01-18 | 2027-01-28
UG-07A-S08-A060 | AW.PIPE.F4.UG-07A.UG-07A-S08 | F4 | UG-07A | UG-07A-S08 | A060 | Excavate and strut to formation | 50.5482 | m3 | 1 | 2 | UG-07A-S08-A050 | 10 | 2 |  | 2027-01-28 | 2027-01-30 | 2027-01-30
UG-07A-S08-A070 | AW.PIPE.F4.UG-07A.UG-07A-S08 | F4 | UG-07A | UG-07A-S08 | A070 | Trim piles, blinding and piled slab (incl. cure) | 2.9324 | m | 4 | 5 | UG-07A-S08-A060 | 1 | 2 |  | 2027-01-29 | 2027-02-03 | 2027-02-03
UG-07A-S08-A080 | AW.PIPE.F4.UG-07A.UG-07A-S08 | F4 | UG-07A | UG-07A-S08 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 2.9324 | m | 5 | 6 | UG-07A-S08-A070 | 2 | 2 | UG-07A-S09-A080 (FS, closure) | 2027-04-12 | 2027-04-18 | 2027-04-18
UG-07A-S08-A090 | AW.PIPE.F4.UG-07A.UG-07A-S08 | F4 | UG-07A | UG-07A-S08 | A090 | Surround, joint test and line test | 2.9324 | m | 3 | 4 | UG-07A-S08-A080 | 2 | 2 |  | 2027-04-14 | 2027-04-20
UG-07A-S08-A100 | AW.PIPE.F4.UG-07A.UG-07A-S08 | F4 | UG-07A | UG-07A-S08 | A100 | Backfill to NG and remove struts | 44.0061 | m3 | 1 | 2 | UG-07A-S08-A090 | 2 | 2 |  | 2027-04-16 | 2027-04-22 | 2027-04-22
UG-07A-S08-A110 | AW.PIPE.F4.UG-07A.UG-07A-S08 | F4 | UG-07A | UG-07A-S08 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-07A-S08-A100 | 1 | 2 |  | 2027-04-17 | 2027-04-24
UG-07A-S10-A010 | AW.PIPE.F4.UG-07A.UG-07A-S10 | F4 | UG-07A | UG-07A-S10 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-07A-S10-A020 | AW.PIPE.F4.UG-07A.UG-07A-S10 | F4 | UG-07A | UG-07A-S10 | A020 | Set-out, crossing survey and working platform | 9.2999 | m | 1 | 2 | UG-07A-S10-A010 |  |  | FS from A010; UG-07A-S11-A030 (SS, tie-in team follows the adjacent run) | 2027-01-22 | 2027-01-24
UG-07A-S10-A030 | AW.PIPE.F4.UG-07A.UG-07A-S10 | F4 | UG-07A | UG-07A-S10 | A030 | Pipe-support piling from platform (incl. integrity tests) | 10 | piles | 2 | 3 | UG-07A-S10-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-23 | 2027-01-26 | 2027-01-26
UG-07A-S10-A040 | AW.PIPE.F4.UG-07A.UG-07A-S10 | F4 | UG-07A | UG-07A-S10 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-07A-S10-A030 | 1 | 0 |  | 2027-01-24 | 2027-01-26 | 0
UG-07A-S10-A050 | AW.PIPE.F4.UG-07A.UG-07A-S10 | F4 | UG-07A | UG-07A-S10 | A050 | Install dewatering and draw down | 9.2999 | m | 8 | 10 | UG-07A-S10-A040 | 0 | 2 |  | 2027-01-24 | 2027-02-03
UG-07A-S10-A060 | AW.PIPE.F4.UG-07A.UG-07A-S10 | F4 | UG-07A | UG-07A-S10 | A060 | Excavate and strut to formation | 131.4782 | m3 | 1 | 2 | UG-07A-S10-A050 | 10 | 2 | UG-12-S04-A100 (FS, deeper first); UG-13B-S06-A100 (FS, deeper first); UG-13B-S07-A100 (FS, deeper first) | 2027-03-31 | 2027-04-02 | 2027-04-02
UG-07A-S10-A070 | AW.PIPE.F4.UG-07A.UG-07A-S10 | F4 | UG-07A | UG-07A-S10 | A070 | Trim piles, blinding and piled slab (incl. cure) | 9.2999 | m | 4 | 5 | UG-07A-S10-A060 | 1 | 2 |  | 2027-04-01 | 2027-04-06 | 2027-04-06
UG-07A-S10-A080 | AW.PIPE.F4.UG-07A.UG-07A-S10 | F4 | UG-07A | UG-07A-S10 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 9.2999 | m | 4 | 5 | UG-07A-S10-A070 | 2 | 2 | UG-07A-S11-A080 (FS, closure) | 2027-04-03 | 2027-04-08 | 2027-04-08
UG-07A-S10-A090 | AW.PIPE.F4.UG-07A.UG-07A-S10 | F4 | UG-07A | UG-07A-S10 | A090 | Surround, joint test and line test | 9.2999 | m | 3 | 4 | UG-07A-S10-A080 | 2 | 2 |  | 2027-04-05 | 2027-04-10
UG-07A-S10-A100 | AW.PIPE.F4.UG-07A.UG-07A-S10 | F4 | UG-07A | UG-07A-S10 | A100 | Backfill to NG and remove struts | 110.7305 | m3 | 1 | 2 | UG-07A-S10-A090 | 2 | 2 |  | 2027-04-07 | 2027-04-12 | 2027-04-12
UG-07A-S10-A110 | AW.PIPE.F4.UG-07A.UG-07A-S10 | F4 | UG-07A | UG-07A-S10 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-07A-S10-A100 | 1 | 2 |  | 2027-04-08 | 2027-04-14
UG-07A-S06-A010 | AW.PIPE.F4.UG-07A.UG-07A-S06 | F4 | UG-07A | UG-07A-S06 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-07A-S06-A020 | AW.PIPE.F4.UG-07A.UG-07A-S06 | F4 | UG-07A | UG-07A-S06 | A020 | Set-out, crossing survey and working platform | 5.3578 | m | 1 | 2 | UG-07A-S06-A010 |  |  | FS from A010; UG-07A-S07-A030 (SS, tie-in team follows the adjacent run) | 2027-02-20 | 2027-02-22
UG-07A-S06-A030 | AW.PIPE.F4.UG-07A.UG-07A-S06 | F4 | UG-07A | UG-07A-S06 | A030 | Pipe-support piling from platform (incl. integrity tests) | 6 | piles | 2 | 3 | UG-07A-S06-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-21 | 2027-02-24 | 2027-02-24
UG-07A-S06-A040 | AW.PIPE.F4.UG-07A.UG-07A-S06 | F4 | UG-07A | UG-07A-S06 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-07A-S06-A030 | 1 | 0 |  | 2027-02-22 | 2027-02-24 | 0
UG-07A-S06-A050 | AW.PIPE.F4.UG-07A.UG-07A-S06 | F4 | UG-07A | UG-07A-S06 | A050 | Install dewatering and draw down | 5.3578 | m | 8 | 10 | UG-07A-S06-A040 | 0 | 2 |  | 2027-02-22 | 2027-03-04
UG-07A-S06-A060 | AW.PIPE.F4.UG-07A.UG-07A-S06 | F4 | UG-07A | UG-07A-S06 | A060 | Excavate and strut to formation | 63.8645 | m3 | 1 | 2 | UG-07A-S06-A050 | 10 | 2 | UG-11A-S02-A100 (FS, deeper first) | 2027-07-23 | 2027-07-25 | 2027-07-25
UG-07A-S06-A070 | AW.PIPE.F4.UG-07A.UG-07A-S06 | F4 | UG-07A | UG-07A-S06 | A070 | Trim piles, blinding and piled slab (incl. cure) | 5.3578 | m | 4 | 5 | UG-07A-S06-A060 | 1 | 2 |  | 2027-07-24 | 2027-07-29 | 2027-07-29
UG-07A-S06-A080 | AW.PIPE.F4.UG-07A.UG-07A-S06 | F4 | UG-07A | UG-07A-S06 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 5.3578 | m | 5 | 6 | UG-07A-S06-A070 | 2 | 2 | UG-07A-S07-A080 (FS, closure) | 2027-07-26 | 2027-08-01 | 2027-08-01
UG-07A-S06-A090 | AW.PIPE.F4.UG-07A.UG-07A-S06 | F4 | UG-07A | UG-07A-S06 | A090 | Surround, joint test and line test | 5.3578 | m | 3 | 4 | UG-07A-S06-A080 | 2 | 2 |  | 2027-07-28 | 2027-08-03
UG-07A-S06-A100 | AW.PIPE.F4.UG-07A.UG-07A-S06 | F4 | UG-07A | UG-07A-S06 | A100 | Backfill to NG and remove struts | 51.9114 | m3 | 1 | 2 | UG-07A-S06-A090 | 2 | 2 |  | 2027-07-30 | 2027-08-05 | 2027-08-05
UG-07A-S06-A110 | AW.PIPE.F4.UG-07A.UG-07A-S06 | F4 | UG-07A | UG-07A-S06 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-07A-S06-A100 | 1 | 2 |  | 2027-07-31 | 2027-08-07
UG-07A-S04-A010 | AW.PIPE.F4.UG-07A.UG-07A-S04 | F4 | UG-07A | UG-07A-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-07A-S04-A020 | AW.PIPE.F4.UG-07A.UG-07A-S04 | F4 | UG-07A | UG-07A-S04 | A020 | Set-out, crossing survey and working platform | 65.1 | m | 1 | 2 | UG-07A-S04-A010 |  |  | FS from A010; UG-07A-S07-A030 (SS, set-out one package ahead of piling) | 2027-02-20 | 2027-02-22
UG-07A-S04-A030 | AW.PIPE.F4.UG-07A.UG-07A-S04 | F4 | UG-07A | UG-07A-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 46 | piles | 10 | 12 | UG-07A-S04-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-25 | 2027-03-09 | 2027-03-09 | UG-07A-S07-A030
UG-07A-S04-A040 | AW.PIPE.F4.UG-07A.UG-07A-S04 | F4 | UG-07A | UG-07A-S04 | A040 | Install sheet piles (shored lengths) | 60 | m wall | 3 | 4 | UG-07A-S04-A030 | 4 | 2 |  | 2027-03-01 | 2027-03-11 | 2027-03-11 | UG-07A-S07-A040
UG-07A-S04-A050 | AW.PIPE.F4.UG-07A.UG-07A-S04 | F4 | UG-07A | UG-07A-S04 | A050 | Install dewatering and draw down | 65.1 | m | 9 | 11 | UG-07A-S04-A040 | 2 | 2 | UG-07A-S07-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-25 | 2027-04-05
UG-07A-S04-A060 | AW.PIPE.F4.UG-07A.UG-07A-S04 | F4 | UG-07A | UG-07A-S04 | A060 | Excavate and strut to formation | 735.596 | m3 | 3 | 4 | UG-07A-S04-A050 | 10 | 2 | UG-11A-S03-A100 (FS, deeper first); UG-11A-S04-A100 (FS, deeper first); UG-11A-S05-A100 (FS, deeper first); UG-11A-S07-A100 (FS, deeper first) | 2027-08-01 | 2027-08-05 | 2027-08-05 | UG-07A-S07-A060
UG-07A-S04-A070 | AW.PIPE.F4.UG-07A.UG-07A-S04 | F4 | UG-07A | UG-07A-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 65.1 | m | 9 | 11 | UG-07A-S04-A060 | 2 | 2 |  | 2027-08-03 | 2027-08-14 | 2027-08-14 | UG-07A-S07-A070
UG-07A-S04-A080 | AW.PIPE.F4.UG-07A.UG-07A-S04 | F4 | UG-07A | UG-07A-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 65.1 | m | 4 | 5 | UG-07A-S04-A070 | 4 | 2 |  | 2027-08-07 | 2027-08-16 | 2027-08-16 | UG-07A-S07-A080
UG-07A-S04-A090 | AW.PIPE.F4.UG-07A.UG-07A-S04 | F4 | UG-07A | UG-07A-S04 | A090 | Surround, joint test and line test | 65.1 | m | 3 | 4 | UG-07A-S04-A080 | 2 | 2 |  | 2027-08-09 | 2027-08-18
UG-07A-S04-A100 | AW.PIPE.F4.UG-07A.UG-07A-S04 | F4 | UG-07A | UG-07A-S04 | A100 | Backfill to NG and remove struts | 520.0748 | m3 | 2 | 3 | UG-07A-S04-A090 | 2 | 2 |  | 2027-08-11 | 2027-08-20 | 2027-08-20 | UG-07A-S07-A100
UG-07A-S04-A110 | AW.PIPE.F4.UG-07A.UG-07A-S04 | F4 | UG-07A | UG-07A-S04 | A110 | Dewatering off, extract sheets, reinstate | 60 | m wall | 3 | 4 | UG-07A-S04-A100 | 1 | 2 |  | 2027-08-12 | 2027-08-22
UG-12-S07-A010 | AW.PIPE.F5.UG-12.UG-12-S07 | F5 | UG-12 | UG-12-S07 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-12-S07-A020 | AW.PIPE.F5.UG-12.UG-12-S07 | F5 | UG-12 | UG-12-S07 | A020 | Set-out, crossing survey and working platform | 17.108 | m | 1 | 2 | UG-12-S07-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-12-S07-A030 | AW.PIPE.F5.UG-12.UG-12-S07 | F5 | UG-12 | UG-12-S07 | A030 | Pipe-support piling from platform (incl. integrity tests) | 14 | piles | 3 | 4 | UG-12-S07-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-06 | 2026-12-06
UG-12-S07-A040 | AW.PIPE.F5.UG-12.UG-12-S07 | F5 | UG-12 | UG-12-S07 | A040 | Install sheet piles (shored lengths) | 34.216 | m wall | 2 | 3 | UG-12-S07-A030 | 2 | 2 |  | 2026-12-04 | 2026-12-08 | 2026-12-08
UG-12-S07-A050 | AW.PIPE.F5.UG-12.UG-12-S07 | F5 | UG-12 | UG-12-S07 | A050 | Install dewatering and draw down | 17.108 | m | 8 | 10 | UG-12-S07-A040 | 1 | 2 |  | 2026-12-05 | 2026-12-15
UG-12-S07-A060 | AW.PIPE.F5.UG-12.UG-12-S07 | F5 | UG-12 | UG-12-S07 | A060 | Excavate and strut to formation | 323.2665 | m3 | 2 | 3 | UG-12-S07-A050 | 10 | 2 | UG-11-S06-A100 (FS, deeper first) | 2027-01-17 | 2027-01-20 | 2027-01-20
UG-12-S07-A070 | AW.PIPE.F5.UG-12.UG-12-S07 | F5 | UG-12 | UG-12-S07 | A070 | Trim piles, blinding and piled slab (incl. cure) | 17.108 | m | 5 | 6 | UG-12-S07-A060 | 1 | 2 |  | 2027-01-18 | 2027-01-24 | 2027-01-24
UG-12-S07-A080 | AW.PIPE.F5.UG-12.UG-12-S07 | F5 | UG-12 | UG-12-S07 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 17.108 | m | 1 | 2 | UG-12-S07-A070 | 2 | 2 |  | 2027-01-20 | 2027-01-26 | 2027-01-26
UG-12-S07-A090 | AW.PIPE.F5.UG-12.UG-12-S07 | F5 | UG-12 | UG-12-S07 | A090 | Surround, joint test and line test | 17.108 | m | 3 | 4 | UG-12-S07-A080 | 1 | 2 |  | 2027-01-21 | 2027-01-28
UG-12-S07-A100 | AW.PIPE.F5.UG-12.UG-12-S07 | F5 | UG-12 | UG-12-S07 | A100 | Backfill to NG and remove struts | 239.4571 | m3 | 1 | 2 | UG-12-S07-A090 | 2 | 2 | UG-07-S03-A080 (FS, shared trench laid); UG-07-S04-A080 (FS, shared trench laid); UG-11-S01-A080 (FS, shared trench laid) | 2027-02-26 | 2027-02-28 | 2027-02-28
UG-12-S07-A110 | AW.PIPE.F5.UG-12.UG-12-S07 | F5 | UG-12 | UG-12-S07 | A110 | Dewatering off, extract sheets, reinstate | 34.216 | m wall | 2 | 3 | UG-12-S07-A100 | 1 | 2 |  | 2027-02-27 | 2027-03-02
UG-12-S08-A010 | AW.PIPE.F5.UG-12.UG-12-S08 | F5 | UG-12 | UG-12-S08 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-12-S08-A020 | AW.PIPE.F5.UG-12.UG-12-S08 | F5 | UG-12 | UG-12-S08 | A020 | Set-out, crossing survey and working platform | 6.0004 | m | 1 | 2 | UG-12-S08-A010 |  |  | FS from A010; UG-12-S07-A030 (SS, tie-in team follows the adjacent run) | 2026-12-02 | 2026-12-04
UG-12-S08-A030 | AW.PIPE.F5.UG-12.UG-12-S08 | F5 | UG-12 | UG-12-S08 | A030 | Pipe-support piling from platform (incl. integrity tests) | 8 | piles | 2 | 3 | UG-12-S08-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-03 | 2026-12-06 | 2026-12-06
UG-12-S08-A040 | AW.PIPE.F5.UG-12.UG-12-S08 | F5 | UG-12 | UG-12-S08 | A040 | Install sheet piles (shored lengths) | 12.0008 | m wall | 1 | 2 | UG-12-S08-A030 | 1 | 2 |  | 2026-12-04 | 2026-12-08 | 2026-12-08
UG-12-S08-A050 | AW.PIPE.F5.UG-12.UG-12-S08 | F5 | UG-12 | UG-12-S08 | A050 | Install dewatering and draw down | 6.0004 | m | 8 | 10 | UG-12-S08-A040 | 1 | 2 |  | 2026-12-05 | 2026-12-15
UG-12-S08-A060 | AW.PIPE.F5.UG-12.UG-12-S08 | F5 | UG-12 | UG-12-S08 | A060 | Excavate and strut to formation | 109.3427 | m3 | 1 | 2 | UG-12-S08-A050 | 10 | 2 | UG-11-S06-A100 (FS, deeper first) | 2027-01-17 | 2027-01-19 | 2027-01-19
UG-12-S08-A070 | AW.PIPE.F5.UG-12.UG-12-S08 | F5 | UG-12 | UG-12-S08 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6.0004 | m | 4 | 5 | UG-12-S08-A060 | 1 | 2 |  | 2027-01-18 | 2027-01-23 | 2027-01-23
UG-12-S08-A080 | AW.PIPE.F5.UG-12.UG-12-S08 | F5 | UG-12 | UG-12-S08 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6.0004 | m | 4 | 5 | UG-12-S08-A070 | 2 | 2 | UG-12-S07-A080 (FS, closure) | 2027-01-26 | 2027-01-31 | 2027-01-31
UG-12-S08-A090 | AW.PIPE.F5.UG-12.UG-12-S08 | F5 | UG-12 | UG-12-S08 | A090 | Surround, joint test and line test | 6.0004 | m | 3 | 4 | UG-12-S08-A080 | 2 | 2 |  | 2027-01-28 | 2027-02-02
UG-12-S08-A100 | AW.PIPE.F5.UG-12.UG-12-S08 | F5 | UG-12 | UG-12-S08 | A100 | Backfill to NG and remove struts | 79.9478 | m3 | 1 | 2 | UG-12-S08-A090 | 2 | 2 | UG-07-S03-A080 (FS, shared trench laid); UG-07-S04-A080 (FS, shared trench laid); UG-11-S01-A080 (FS, shared trench laid) | 2027-02-26 | 2027-02-28 | 2027-02-28
UG-12-S08-A110 | AW.PIPE.F5.UG-12.UG-12-S08 | F5 | UG-12 | UG-12-S08 | A110 | Dewatering off, extract sheets, reinstate | 12.0008 | m wall | 2 | 3 | UG-12-S08-A100 | 1 | 2 |  | 2027-02-27 | 2027-03-02
UG-11B-S14-A010 | AW.PIPE.F5.UG-11B.UG-11B-S14 | F5 | UG-11B | UG-11B-S14 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11B-S14-A020 | AW.PIPE.F5.UG-11B.UG-11B-S14 | F5 | UG-11B | UG-11B-S14 | A020 | Set-out, crossing survey and working platform | 20.1538 | m | 1 | 2 | UG-11B-S14-A010 |  |  | FS from A010; UG-12-S07-A030 (SS, set-out one package ahead of piling) | 2026-12-02 | 2026-12-04
UG-11B-S14-A030 | AW.PIPE.F5.UG-11B.UG-11B-S14 | F5 | UG-11B | UG-11B-S14 | A030 | Pipe-support piling from platform (incl. integrity tests) | 16 | piles | 4 | 5 | UG-11B-S14-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-06 | 2026-12-11 | 2026-12-11 | UG-12-S07-A030
UG-11B-S14-A040 | AW.PIPE.F5.UG-11B.UG-11B-S14 | F5 | UG-11B | UG-11B-S14 | A040 | Install sheet piles (shored lengths) | 40.3077 | m wall | 2 | 3 | UG-11B-S14-A030 | 2 | 2 |  | 2026-12-08 | 2026-12-13 | 2026-12-13 | UG-12-S07-A040
UG-11B-S14-A050 | AW.PIPE.F5.UG-11B.UG-11B-S14 | F5 | UG-11B | UG-11B-S14 | A050 | Install dewatering and draw down | 20.1538 | m | 8 | 10 | UG-11B-S14-A040 | 1 | 2 | UG-12-S07-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-10 | 2027-01-20
UG-11B-S14-A060 | AW.PIPE.F5.UG-11B.UG-11B-S14 | F5 | UG-11B | UG-11B-S14 | A060 | Excavate and strut to formation | 322.7249 | m3 | 2 | 3 | UG-11B-S14-A050 | 10 | 2 |  | 2027-01-20 | 2027-01-23 | 2027-01-23 | UG-12-S07-A060
UG-11B-S14-A070 | AW.PIPE.F5.UG-11B.UG-11B-S14 | F5 | UG-11B | UG-11B-S14 | A070 | Trim piles, blinding and piled slab (incl. cure) | 20.1538 | m | 5 | 6 | UG-11B-S14-A060 | 1 | 2 |  | 2027-01-24 | 2027-01-30 | 2027-01-30 | UG-12-S07-A070
UG-11B-S14-A080 | AW.PIPE.F5.UG-11B.UG-11B-S14 | F5 | UG-11B | UG-11B-S14 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 20.1538 | m | 3 | 4 | UG-11B-S14-A070 | 2 | 2 |  | 2027-01-26 | 2027-02-01 | 2027-02-01 | UG-12-S07-A080
UG-11B-S14-A090 | AW.PIPE.F5.UG-11B.UG-11B-S14 | F5 | UG-11B | UG-11B-S14 | A090 | Surround, joint test and line test | 20.1538 | m | 3 | 4 | UG-11B-S14-A080 | 2 | 2 |  | 2027-01-28 | 2027-02-03
UG-11B-S14-A100 | AW.PIPE.F5.UG-11B.UG-11B-S14 | F5 | UG-11B | UG-11B-S14 | A100 | Backfill to NG and remove struts | 223.9941 | m3 | 1 | 2 | UG-11B-S14-A090 | 2 | 2 | UG-11-S01-A080 (FS, shared trench laid) | 2027-02-28 | 2027-03-02 | 2027-03-02 | UG-12-S07-A100
UG-11B-S14-A110 | AW.PIPE.F5.UG-11B.UG-11B-S14 | F5 | UG-11B | UG-11B-S14 | A110 | Dewatering off, extract sheets, reinstate | 40.3077 | m wall | 2 | 3 | UG-11B-S14-A100 | 1 | 2 |  | 2027-03-01 | 2027-03-04
UG-12-S06-A010 | AW.PIPE.F5.UG-12.UG-12-S06 | F5 | UG-12 | UG-12-S06 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-12-S06-A020 | AW.PIPE.F5.UG-12.UG-12-S06 | F5 | UG-12 | UG-12-S06 | A020 | Set-out, crossing survey and working platform | 42.1 | m | 1 | 2 | UG-12-S06-A010 |  |  | FS from A010; UG-11B-S14-A030 (SS, set-out one package ahead of piling) | 2026-12-06 | 2026-12-08
UG-12-S06-A030 | AW.PIPE.F5.UG-12.UG-12-S06 | F5 | UG-12 | UG-12-S06 | A030 | Pipe-support piling from platform (incl. integrity tests) | 32 | piles | 7 | 9 | UG-12-S06-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-11 | 2026-12-20 | 2026-12-20 | UG-11B-S14-A030
UG-12-S06-A040 | AW.PIPE.F5.UG-12.UG-12-S06 | F5 | UG-12 | UG-12-S06 | A040 | Install sheet piles (shored lengths) | 84.2 | m wall | 4 | 5 | UG-12-S06-A030 | 3 | 2 |  | 2026-12-14 | 2026-12-22 | 2026-12-22 | UG-11B-S14-A040
UG-12-S06-A050 | AW.PIPE.F5.UG-12.UG-12-S06 | F5 | UG-12 | UG-12-S06 | A050 | Install dewatering and draw down | 42.1 | m | 9 | 11 | UG-12-S06-A040 | 2 | 2 | UG-11B-S14-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-12 | 2027-01-23
UG-12-S06-A060 | AW.PIPE.F5.UG-12.UG-12-S06 | F5 | UG-12 | UG-12-S06 | A060 | Excavate and strut to formation | 868.1048 | m3 | 4 | 5 | UG-12-S06-A050 | 10 | 2 |  | 2027-01-23 | 2027-01-28 | 2027-01-28 | UG-11B-S14-A060
UG-12-S06-A070 | AW.PIPE.F5.UG-12.UG-12-S06 | F5 | UG-12 | UG-12-S06 | A070 | Trim piles, blinding and piled slab (incl. cure) | 42.1 | m | 7 | 9 | UG-12-S06-A060 | 2 | 2 |  | 2027-01-30 | 2027-02-08 | 2027-02-08 | UG-11B-S14-A070
UG-12-S06-A080 | AW.PIPE.F5.UG-12.UG-12-S06 | F5 | UG-12 | UG-12-S06 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 42.1 | m | 4 | 5 | UG-12-S06-A070 | 3 | 2 |  | 2027-02-02 | 2027-02-10 | 2027-02-10 | UG-11B-S14-A080
UG-12-S06-A090 | AW.PIPE.F5.UG-12.UG-12-S06 | F5 | UG-12 | UG-12-S06 | A090 | Surround, joint test and line test | 42.1 | m | 3 | 4 | UG-12-S06-A080 | 2 | 2 |  | 2027-02-04 | 2027-02-12
UG-12-S06-A100 | AW.PIPE.F5.UG-12.UG-12-S06 | F5 | UG-12 | UG-12-S06 | A100 | Backfill to NG and remove struts | 661.8637 | m3 | 2 | 3 | UG-12-S06-A090 | 2 | 2 | UG-07-S03-A080 (FS, shared trench laid) | 2027-03-02 | 2027-03-05 | 2027-03-05 | UG-11B-S14-A100
UG-12-S06-A110 | AW.PIPE.F5.UG-12.UG-12-S06 | F5 | UG-12 | UG-12-S06 | A110 | Dewatering off, extract sheets, reinstate | 84.2 | m wall | 3 | 4 | UG-12-S06-A100 | 1 | 2 |  | 2027-03-03 | 2027-03-07
UG-07-S03-A010 | AW.PIPE.F5.UG-07.UG-07-S03 | F5 | UG-07 | UG-07-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-07-S03-A020 | AW.PIPE.F5.UG-07.UG-07-S03 | F5 | UG-07 | UG-07-S03 | A020 | Set-out, crossing survey and working platform | 25.227 | m | 1 | 2 | UG-07-S03-A010 |  |  | FS from A010; UG-12-S06-A030 (SS, set-out one package ahead of piling) | 2026-12-11 | 2026-12-13
UG-07-S03-A030 | AW.PIPE.F5.UG-07.UG-07-S03 | F5 | UG-07 | UG-07-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 20 | piles | 4 | 5 | UG-07-S03-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-20 | 2026-12-25 | 2026-12-25 | UG-12-S06-A030
UG-07-S03-A040 | AW.PIPE.F5.UG-07.UG-07-S03 | F5 | UG-07 | UG-07-S03 | A040 | Install sheet piles (shored lengths) | 50.454 | m wall | 3 | 4 | UG-07-S03-A030 | 2 | 2 |  | 2026-12-22 | 2026-12-27 | 2026-12-27 | UG-12-S06-A040
UG-07-S03-A050 | AW.PIPE.F5.UG-07.UG-07-S03 | F5 | UG-07 | UG-07-S03 | A050 | Install dewatering and draw down | 25.227 | m | 8 | 10 | UG-07-S03-A040 | 2 | 2 | UG-12-S06-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-18 | 2027-01-28
UG-07-S03-A060 | AW.PIPE.F5.UG-07.UG-07-S03 | F5 | UG-07 | UG-07-S03 | A060 | Excavate and strut to formation | 421.3512 | m3 | 2 | 3 | UG-07-S03-A050 | 10 | 2 | UG-11-S06-A100 (FS, deeper first); UG-12-S06-A060 (SS, shared trench); UG-12-S07-A060 (SS, shared trench); UG-12-S08-A060 (SS, shared trench) | 2027-01-28 | 2027-01-31 | 2027-01-31 | UG-12-S06-A060
UG-07-S03-A070 | AW.PIPE.F5.UG-07.UG-07-S03 | F5 | UG-07 | UG-07-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 25.227 | m | 6 | 7 | UG-07-S03-A060 | 1 | 2 |  | 2027-02-08 | 2027-02-15 | 2027-02-15 | UG-12-S06-A070
UG-07-S03-A080 | AW.PIPE.F5.UG-07.UG-07-S03 | F5 | UG-07 | UG-07-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 25.227 | m | 2 | 3 | UG-07-S03-A070 | 3 | 2 |  | 2027-02-11 | 2027-02-17 | 2027-02-17 | UG-12-S06-A080
UG-07-S03-A090 | AW.PIPE.F5.UG-07.UG-07-S03 | F5 | UG-07 | UG-07-S03 | A090 | Surround, joint test and line test | 25.227 | m | 3 | 4 | UG-07-S03-A080 | 1 | 2 |  | 2027-02-12 | 2027-02-19
UG-07-S03-A100 | AW.PIPE.F5.UG-07.UG-07-S03 | F5 | UG-07 | UG-07-S03 | A100 | Backfill to NG and remove struts | 297.768 | m3 | 1 | 2 | UG-07-S03-A090 | 2 | 2 | UG-11-S01-A080 (FS, shared trench laid); UG-12-S06-A080 (FS, shared trench laid); UG-12-S07-A080 (FS, shared trench laid); UG-12-S08-A080 (FS, shared trench laid) | 2027-03-05 | 2027-03-07 | 2027-03-07 | UG-12-S06-A100
UG-07-S03-A110 | AW.PIPE.F5.UG-07.UG-07-S03 | F5 | UG-07 | UG-07-S03 | A110 | Dewatering off, extract sheets, reinstate | 50.454 | m wall | 3 | 4 | UG-07-S03-A100 | 1 | 2 |  | 2027-03-06 | 2027-03-10
UG-07-S04-A010 | AW.PIPE.F5.UG-07.UG-07-S04 | F5 | UG-07 | UG-07-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-07-S04-A020 | AW.PIPE.F5.UG-07.UG-07-S04 | F5 | UG-07 | UG-07-S04 | A020 | Set-out, crossing survey and working platform | 6.0003 | m | 1 | 2 | UG-07-S04-A010 |  |  | FS from A010; UG-07-S03-A030 (SS, tie-in team follows the adjacent run) | 2026-12-20 | 2026-12-22
UG-07-S04-A030 | AW.PIPE.F5.UG-07.UG-07-S04 | F5 | UG-07 | UG-07-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 8 | piles | 2 | 3 | UG-07-S04-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-21 | 2026-12-24 | 2026-12-24
UG-07-S04-A040 | AW.PIPE.F5.UG-07.UG-07-S04 | F5 | UG-07 | UG-07-S04 | A040 | Install sheet piles (shored lengths) | 12.0006 | m wall | 1 | 2 | UG-07-S04-A030 | 1 | 2 |  | 2026-12-22 | 2026-12-26 | 2026-12-26
UG-07-S04-A050 | AW.PIPE.F5.UG-07.UG-07-S04 | F5 | UG-07 | UG-07-S04 | A050 | Install dewatering and draw down | 6.0003 | m | 8 | 10 | UG-07-S04-A040 | 1 | 2 |  | 2026-12-23 | 2027-01-02
UG-07-S04-A060 | AW.PIPE.F5.UG-07.UG-07-S04 | F5 | UG-07 | UG-07-S04 | A060 | Excavate and strut to formation | 106.9917 | m3 | 1 | 2 | UG-07-S04-A050 | 10 | 2 | UG-11-S06-A100 (FS, deeper first); UG-12-S07-A060 (SS, shared trench); UG-12-S08-A060 (SS, shared trench) | 2027-01-17 | 2027-01-19 | 2027-01-19
UG-07-S04-A070 | AW.PIPE.F5.UG-07.UG-07-S04 | F5 | UG-07 | UG-07-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6.0003 | m | 4 | 5 | UG-07-S04-A060 | 1 | 2 |  | 2027-01-18 | 2027-01-23 | 2027-01-23
UG-07-S04-A080 | AW.PIPE.F5.UG-07.UG-07-S04 | F5 | UG-07 | UG-07-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6.0003 | m | 4 | 5 | UG-07-S04-A070 | 2 | 2 | UG-07-S03-A080 (FS, closure) | 2027-02-17 | 2027-02-22 | 2027-02-22
UG-07-S04-A090 | AW.PIPE.F5.UG-07.UG-07-S04 | F5 | UG-07 | UG-07-S04 | A090 | Surround, joint test and line test | 6.0003 | m | 3 | 4 | UG-07-S04-A080 | 2 | 2 |  | 2027-02-19 | 2027-02-24
UG-07-S04-A100 | AW.PIPE.F5.UG-07.UG-07-S04 | F5 | UG-07 | UG-07-S04 | A100 | Backfill to NG and remove struts | 77.5971 | m3 | 1 | 2 | UG-07-S04-A090 | 2 | 2 | UG-11-S01-A080 (FS, shared trench laid); UG-12-S07-A080 (FS, shared trench laid); UG-12-S08-A080 (FS, shared trench laid) | 2027-02-26 | 2027-02-28 | 2027-02-28
UG-07-S04-A110 | AW.PIPE.F5.UG-07.UG-07-S04 | F5 | UG-07 | UG-07-S04 | A110 | Dewatering off, extract sheets, reinstate | 12.0006 | m wall | 2 | 3 | UG-07-S04-A100 | 1 | 2 |  | 2027-02-27 | 2027-03-02
UG-11-S01-A010 | AW.PIPE.F5.UG-11.UG-11-S01 | F5 | UG-11 | UG-11-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11-S01-A020 | AW.PIPE.F5.UG-11.UG-11-S01 | F5 | UG-11 | UG-11-S01 | A020 | Set-out, crossing survey and working platform | 37.4 | m | 1 | 2 | UG-11-S01-A010 |  |  | FS from A010; UG-07-S03-A030 (SS, set-out one package ahead of piling) | 2026-12-20 | 2026-12-22
UG-11-S01-A030 | AW.PIPE.F5.UG-11.UG-11-S01 | F5 | UG-11 | UG-11-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 28 | piles | 6 | 7 | UG-11-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-25 | 2027-01-01 | 2027-01-01 | UG-07-S03-A030
UG-11-S01-A040 | AW.PIPE.F5.UG-11.UG-11-S01 | F5 | UG-11 | UG-11-S01 | A040 | Install sheet piles (shored lengths) | 74.8 | m wall | 3 | 4 | UG-11-S01-A030 | 3 | 2 |  | 2026-12-28 | 2027-01-03 | 2027-01-03 | UG-07-S03-A040
UG-11-S01-A050 | AW.PIPE.F5.UG-11.UG-11-S01 | F5 | UG-11 | UG-11-S01 | A050 | Install dewatering and draw down | 37.4 | m | 8 | 10 | UG-11-S01-A040 | 2 | 2 | UG-07-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-21 | 2027-01-31
UG-11-S01-A060 | AW.PIPE.F5.UG-11.UG-11-S01 | F5 | UG-11 | UG-11-S01 | A060 | Excavate and strut to formation | 597.1146 | m3 | 3 | 4 | UG-11-S01-A050 | 10 | 2 | UG-07-S03-A060 (SS, shared trench); UG-07-S04-A060 (SS, shared trench); UG-11B-S14-A060 (SS, shared trench); UG-12-S07-A060 (SS, shared trench); UG-12-S08-A060 (SS, shared trench) | 2027-01-31 | 2027-02-04 | 2027-02-04 | UG-07-S03-A060
UG-11-S01-A070 | AW.PIPE.F5.UG-11.UG-11-S01 | F5 | UG-11 | UG-11-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 37.4 | m | 7 | 9 | UG-11-S01-A060 | 2 | 2 |  | 2027-02-15 | 2027-02-24 | 2027-02-24 | UG-07-S03-A070
UG-11-S01-A080 | AW.PIPE.F5.UG-11.UG-11-S01 | F5 | UG-11 | UG-11-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 37.4 | m | 4 | 5 | UG-11-S01-A070 | 3 | 2 |  | 2027-02-18 | 2027-02-26 | 2027-02-26 | UG-07-S03-A080
UG-11-S01-A090 | AW.PIPE.F5.UG-11.UG-11-S01 | F5 | UG-11 | UG-11-S01 | A090 | Surround, joint test and line test | 37.4 | m | 3 | 4 | UG-11-S01-A080 | 2 | 2 |  | 2027-02-20 | 2027-02-28
UG-11-S01-A100 | AW.PIPE.F5.UG-11.UG-11-S01 | F5 | UG-11 | UG-11-S01 | A100 | Backfill to NG and remove struts | 414.0556 | m3 | 2 | 3 | UG-11-S01-A090 | 2 | 2 | UG-07-S03-A080 (FS, shared trench laid); UG-07-S04-A080 (FS, shared trench laid); UG-11B-S14-A080 (FS, shared trench laid); UG-12-S07-A080 (FS, shared trench laid); UG-12-S08-A080 (FS, shared trench laid) | 2027-03-07 | 2027-03-10 | 2027-03-10 | UG-07-S03-A100
UG-11-S01-A110 | AW.PIPE.F5.UG-11.UG-11-S01 | F5 | UG-11 | UG-11-S01 | A110 | Dewatering off, extract sheets, reinstate | 74.8 | m wall | 3 | 4 | UG-11-S01-A100 | 1 | 2 |  | 2027-03-08 | 2027-03-12
UG-12-S05-A010 | AW.PIPE.F5.UG-12.UG-12-S05 | F5 | UG-12 | UG-12-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-12-S05-A020 | AW.PIPE.F5.UG-12.UG-12-S05 | F5 | UG-12 | UG-12-S05 | A020 | Set-out, crossing survey and working platform | 24.1 | m | 1 | 2 | UG-12-S05-A010 |  |  | FS from A010; UG-11-S01-A030 (SS, set-out one package ahead of piling) | 2026-12-25 | 2026-12-27
UG-12-S05-A030 | AW.PIPE.F5.UG-12.UG-12-S05 | F5 | UG-12 | UG-12-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 20 | piles | 4 | 5 | UG-12-S05-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-01 | 2027-01-06 | 2027-01-06 | UG-11-S01-A030
UG-12-S05-A040 | AW.PIPE.F5.UG-12.UG-12-S05 | F5 | UG-12 | UG-12-S05 | A040 | Install sheet piles (shored lengths) | 48.2 | m wall | 2 | 3 | UG-12-S05-A030 | 2 | 2 |  | 2027-01-03 | 2027-01-08 | 2027-01-08 | UG-11-S01-A040
UG-12-S05-A050 | AW.PIPE.F5.UG-12.UG-12-S05 | F5 | UG-12 | UG-12-S05 | A050 | Install dewatering and draw down | 24.1 | m | 8 | 10 | UG-12-S05-A040 | 1 | 2 | UG-11-S01-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-25 | 2027-02-04
UG-12-S05-A060 | AW.PIPE.F5.UG-12.UG-12-S05 | F5 | UG-12 | UG-12-S05 | A060 | Excavate and strut to formation | 532.8129 | m3 | 3 | 4 | UG-12-S05-A050 | 10 | 2 |  | 2027-02-04 | 2027-02-08 | 2027-02-08 | UG-11-S01-A060
UG-12-S05-A070 | AW.PIPE.F5.UG-12.UG-12-S05 | F5 | UG-12 | UG-12-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 24.1 | m | 6 | 7 | UG-12-S05-A060 | 2 | 2 |  | 2027-02-24 | 2027-03-03 | 2027-03-03 | UG-11-S01-A070
UG-12-S05-A080 | AW.PIPE.F5.UG-12.UG-12-S05 | F5 | UG-12 | UG-12-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 24.1 | m | 3 | 4 | UG-12-S05-A070 | 3 | 2 |  | 2027-02-27 | 2027-03-05 | 2027-03-05 | UG-11-S01-A080
UG-12-S05-A090 | AW.PIPE.F5.UG-12.UG-12-S05 | F5 | UG-12 | UG-12-S05 | A090 | Surround, joint test and line test | 24.1 | m | 3 | 4 | UG-12-S05-A080 | 2 | 2 |  | 2027-03-01 | 2027-03-07
UG-12-S05-A100 | AW.PIPE.F5.UG-12.UG-12-S05 | F5 | UG-12 | UG-12-S05 | A100 | Backfill to NG and remove struts | 414.7504 | m3 | 2 | 3 | UG-12-S05-A090 | 2 | 2 |  | 2027-03-10 | 2027-03-13 | 2027-03-13 | UG-11-S01-A100
UG-12-S05-A110 | AW.PIPE.F5.UG-12.UG-12-S05 | F5 | UG-12 | UG-12-S05 | A110 | Dewatering off, extract sheets, reinstate | 48.2 | m wall | 2 | 3 | UG-12-S05-A100 | 1 | 2 |  | 2027-03-11 | 2027-03-15
UG-12-S02-A010 | AW.PIPE.F5.UG-12.UG-12-S02 | F5 | UG-12 | UG-12-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-12-S02-A020 | AW.PIPE.F5.UG-12.UG-12-S02 | F5 | UG-12 | UG-12-S02 | A020 | Set-out, crossing survey and working platform | 16 | m | 1 | 2 | UG-12-S02-A010 |  |  | FS from A010; UG-12-S05-A030 (SS, set-out one package ahead of piling) | 2027-01-01 | 2027-01-03
UG-12-S02-A030 | AW.PIPE.F5.UG-12.UG-12-S02 | F5 | UG-12 | UG-12-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 14 | piles | 3 | 4 | UG-12-S02-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-06 | 2027-01-10 | 2027-01-10 | UG-12-S05-A030
UG-12-S02-A040 | AW.PIPE.F5.UG-12.UG-12-S02 | F5 | UG-12 | UG-12-S02 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-12-S02-A030 | 2 | 0 |  | 2027-01-08 | 2027-01-10 | 2027-01-08 | UG-12-S05-A040
UG-12-S02-A050 | AW.PIPE.F5.UG-12.UG-12-S02 | F5 | UG-12 | UG-12-S02 | A050 | Install dewatering and draw down | 16 | m | 8 | 10 | UG-12-S02-A040 | 0 | 2 | UG-12-S05-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-29 | 2027-02-08
UG-12-S02-A060 | AW.PIPE.F5.UG-12.UG-12-S02 | F5 | UG-12 | UG-12-S02 | A060 | Excavate and strut to formation | 330.741 | m3 | 1 | 2 | UG-12-S02-A050 | 10 | 2 | UG-13-S02-A100 (FS, deeper first); UG-13-S03-A100 (FS, deeper first) | 2027-06-16 | 2027-06-18 | 2027-06-18 | UG-12-S05-A060
UG-12-S02-A070 | AW.PIPE.F5.UG-12.UG-12-S02 | F5 | UG-12 | UG-12-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 16 | m | 5 | 6 | UG-12-S02-A060 | 1 | 2 |  | 2027-06-17 | 2027-06-23 | 2027-06-23 | UG-12-S05-A070
UG-12-S02-A080 | AW.PIPE.F5.UG-12.UG-12-S02 | F5 | UG-12 | UG-12-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 16 | m | 1 | 2 | UG-12-S02-A070 | 2 | 2 |  | 2027-06-19 | 2027-06-25 | 2027-06-25 | UG-12-S05-A080
UG-12-S02-A090 | AW.PIPE.F5.UG-12.UG-12-S02 | F5 | UG-12 | UG-12-S02 | A090 | Surround, joint test and line test | 16 | m | 3 | 4 | UG-12-S02-A080 | 1 | 2 |  | 2027-06-20 | 2027-06-27
UG-12-S02-A100 | AW.PIPE.F5.UG-12.UG-12-S02 | F5 | UG-12 | UG-12-S02 | A100 | Backfill to NG and remove struts | 252.3593 | m3 | 1 | 2 | UG-12-S02-A090 | 2 | 2 | UG-12A-S12-A080 (FS, shared trench laid) | 2027-07-07 | 2027-07-09 | 2027-07-09 | UG-12-S05-A100
UG-12-S02-A110 | AW.PIPE.F5.UG-12.UG-12-S02 | F5 | UG-12 | UG-12-S02 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-12-S02-A100 | 1 | 2 |  | 2027-07-08 | 2027-07-11
UG-12-S01-A010 | AW.PIPE.F5.UG-12.UG-12-S01 | F5 | UG-12 | UG-12-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-12-S01-A020 | AW.PIPE.F5.UG-12.UG-12-S01 | F5 | UG-12 | UG-12-S01 | A020 | Set-out, crossing survey and working platform | 30.1 | m | 1 | 2 | UG-12-S01-A010 |  |  | FS from A010; UG-12-S02-A030 (SS, set-out one package ahead of piling) | 2027-01-06 | 2027-01-08
UG-12-S01-A030 | AW.PIPE.F5.UG-12.UG-12-S01 | F5 | UG-12 | UG-12-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 24 | piles | 5 | 6 | UG-12-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-10 | 2027-01-16 | 2027-01-16 | UG-12-S02-A030
UG-12-S01-A040 | AW.PIPE.F5.UG-12.UG-12-S01 | F5 | UG-12 | UG-12-S01 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-12-S01-A030 | 2 | 0 |  | 2027-01-12 | 2027-01-16 | 2027-01-08 | UG-12-S02-A040
UG-12-S01-A050 | AW.PIPE.F5.UG-12.UG-12-S01 | F5 | UG-12 | UG-12-S01 | A050 | Install dewatering and draw down | 30.1 | m | 8 | 10 | UG-12-S01-A040 | 0 | 2 | UG-12-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-06-08 | 2027-06-18
UG-12-S01-A060 | AW.PIPE.F5.UG-12.UG-12-S01 | F5 | UG-12 | UG-12-S01 | A060 | Excavate and strut to formation | 618.9069 | m3 | 2 | 3 | UG-12-S01-A050 | 10 | 2 | UG-13-S02-A100 (FS, deeper first); UG-13-S03-A100 (FS, deeper first) | 2027-06-18 | 2027-06-21 | 2027-06-21 | UG-12-S02-A060
UG-12-S01-A070 | AW.PIPE.F5.UG-12.UG-12-S01 | F5 | UG-12 | UG-12-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 30.1 | m | 6 | 7 | UG-12-S01-A060 | 1 | 2 |  | 2027-06-23 | 2027-06-30 | 2027-06-30 | UG-12-S02-A070
UG-12-S01-A080 | AW.PIPE.F5.UG-12.UG-12-S01 | F5 | UG-12 | UG-12-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 30.1 | m | 3 | 4 | UG-12-S01-A070 | 3 | 2 |  | 2027-06-26 | 2027-07-02 | 2027-07-02 | UG-12-S02-A080
UG-12-S01-A090 | AW.PIPE.F5.UG-12.UG-12-S01 | F5 | UG-12 | UG-12-S01 | A090 | Surround, joint test and line test | 30.1 | m | 3 | 4 | UG-12-S01-A080 | 2 | 2 |  | 2027-06-28 | 2027-07-04
UG-12-S01-A100 | AW.PIPE.F5.UG-12.UG-12-S01 | F5 | UG-12 | UG-12-S01 | A100 | Backfill to NG and remove struts | 471.5148 | m3 | 2 | 3 | UG-12-S01-A090 | 2 | 2 | UG-12A-S06-A080 (FS, shared trench laid); UG-12A-S10-A080 (FS, shared trench laid); UG-12A-S12-A080 (FS, shared trench laid) | 2027-07-23 | 2027-07-26 | 2027-07-26 | UG-12-S02-A100
UG-12-S01-A110 | AW.PIPE.F5.UG-12.UG-12-S01 | F5 | UG-12 | UG-12-S01 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-12-S01-A100 | 1 | 2 |  | 2027-07-24 | 2027-07-28
UG-12A-S12-A010 | AW.PIPE.F5.UG-12A.UG-12A-S12 | F5 | UG-12A | UG-12A-S12 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-12A-S12-A020 | AW.PIPE.F5.UG-12A.UG-12A-S12 | F5 | UG-12A | UG-12A-S12 | A020 | Set-out, crossing survey and working platform | 8.1697 | m | 1 | 2 | UG-12A-S12-A010 |  |  | FS from A010; UG-12-S01-A030 (SS, set-out one package ahead of piling) | 2027-01-10 | 2027-01-12
UG-12A-S12-A030 | AW.PIPE.F5.UG-12A.UG-12A-S12 | F5 | UG-12A | UG-12A-S12 | A030 | Pipe-support piling from platform (incl. integrity tests) | 8 | piles | 2 | 3 | UG-12A-S12-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-16 | 2027-01-19 | 2027-01-19 | UG-12-S01-A030
UG-12A-S12-A040 | AW.PIPE.F5.UG-12A.UG-12A-S12 | F5 | UG-12A | UG-12A-S12 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-12A-S12-A030 | 1 | 0 |  | 2027-01-17 | 2027-01-19 | 2027-01-08 | UG-12-S01-A040
UG-12A-S12-A050 | AW.PIPE.F5.UG-12A.UG-12A-S12 | F5 | UG-12A | UG-12A-S12 | A050 | Install dewatering and draw down | 8.1697 | m | 8 | 10 | UG-12A-S12-A040 | 0 | 2 | UG-12-S01-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-06-11 | 2027-06-21
UG-12A-S12-A060 | AW.PIPE.F5.UG-12A.UG-12A-S12 | F5 | UG-12A | UG-12A-S12 | A060 | Excavate and strut to formation | 110.7254 | m3 | 1 | 2 | UG-12A-S12-A050 | 10 | 2 | UG-13-S03-A100 (FS, deeper first); UG-12-S01-A060 (SS, shared trench); UG-12-S02-A060 (SS, shared trench) | 2027-06-21 | 2027-06-23 | 2027-06-23 | UG-12-S01-A060
UG-12A-S12-A070 | AW.PIPE.F5.UG-12A.UG-12A-S12 | F5 | UG-12A | UG-12A-S12 | A070 | Trim piles, blinding and piled slab (incl. cure) | 8.1697 | m | 4 | 5 | UG-12A-S12-A060 | 1 | 2 |  | 2027-06-30 | 2027-07-05 | 2027-07-05 | UG-12-S01-A070
UG-12A-S12-A080 | AW.PIPE.F5.UG-12A.UG-12A-S12 | F5 | UG-12A | UG-12A-S12 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 8.1697 | m | 1 | 2 | UG-12A-S12-A070 | 2 | 2 |  | 2027-07-02 | 2027-07-07 | 2027-07-07 | UG-12-S01-A080
UG-12A-S12-A090 | AW.PIPE.F5.UG-12A.UG-12A-S12 | F5 | UG-12A | UG-12A-S12 | A090 | Surround, joint test and line test | 8.1697 | m | 3 | 4 | UG-12A-S12-A080 | 1 | 2 |  | 2027-07-03 | 2027-07-09
UG-12A-S12-A100 | AW.PIPE.F5.UG-12A.UG-12A-S12 | F5 | UG-12A | UG-12A-S12 | A100 | Backfill to NG and remove struts | 92.2325 | m3 | 1 | 2 | UG-12A-S12-A090 | 2 | 2 | UG-12-S01-A080 (FS, shared trench laid); UG-12-S02-A080 (FS, shared trench laid) | 2027-07-26 | 2027-07-28 | 2027-07-28 | UG-12-S01-A100
UG-12A-S12-A110 | AW.PIPE.F5.UG-12A.UG-12A-S12 | F5 | UG-12A | UG-12A-S12 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-12A-S12-A100 | 1 | 2 |  | 2027-07-27 | 2027-07-30
UG-12A-S10-A010 | AW.PIPE.F5.UG-12A.UG-12A-S10 | F5 | UG-12A | UG-12A-S10 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-12A-S10-A020 | AW.PIPE.F5.UG-12A.UG-12A-S10 | F5 | UG-12A | UG-12A-S10 | A020 | Set-out, crossing survey and working platform | 29.2588 | m | 1 | 2 | UG-12A-S10-A010 |  |  | FS from A010; UG-12A-S12-A030 (SS, set-out one package ahead of piling) | 2027-01-16 | 2027-01-18
UG-12A-S10-A030 | AW.PIPE.F5.UG-12A.UG-12A-S10 | F5 | UG-12A | UG-12A-S10 | A030 | Pipe-support piling from platform (incl. integrity tests) | 22 | piles | 5 | 6 | UG-12A-S10-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-19 | 2027-01-25 | 2027-01-25 | UG-12A-S12-A030
UG-12A-S10-A040 | AW.PIPE.F5.UG-12A.UG-12A-S10 | F5 | UG-12A | UG-12A-S10 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-12A-S10-A030 | 2 | 0 |  | 2027-01-21 | 2027-01-25 | 2027-01-08 | UG-12A-S12-A040
UG-12A-S10-A050 | AW.PIPE.F5.UG-12A.UG-12A-S10 | F5 | UG-12A | UG-12A-S10 | A050 | Install dewatering and draw down | 29.2588 | m | 8 | 10 | UG-12A-S10-A040 | 0 | 2 | UG-12A-S12-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-06-13 | 2027-06-23
UG-12A-S10-A060 | AW.PIPE.F5.UG-12A.UG-12A-S10 | F5 | UG-12A | UG-12A-S10 | A060 | Excavate and strut to formation | 392.8298 | m3 | 1 | 2 | UG-12A-S10-A050 | 10 | 2 | UG-12-S01-A060 (SS, shared trench) | 2027-06-23 | 2027-06-25 | 2027-06-25 | UG-12A-S12-A060
UG-12A-S10-A070 | AW.PIPE.F5.UG-12A.UG-12A-S10 | F5 | UG-12A | UG-12A-S10 | A070 | Trim piles, blinding and piled slab (incl. cure) | 29.2588 | m | 6 | 7 | UG-12A-S10-A060 | 1 | 2 |  | 2027-07-05 | 2027-07-12 | 2027-07-12 | UG-12A-S12-A070
UG-12A-S10-A080 | AW.PIPE.F5.UG-12A.UG-12A-S10 | F5 | UG-12A | UG-12A-S10 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 29.2588 | m | 2 | 3 | UG-12A-S10-A070 | 3 | 2 |  | 2027-07-08 | 2027-07-14 | 2027-07-14 | UG-12A-S12-A080
UG-12A-S10-A090 | AW.PIPE.F5.UG-12A.UG-12A-S10 | F5 | UG-12A | UG-12A-S10 | A090 | Surround, joint test and line test | 29.2588 | m | 3 | 4 | UG-12A-S10-A080 | 1 | 2 |  | 2027-07-09 | 2027-07-16
UG-12A-S10-A100 | AW.PIPE.F5.UG-12A.UG-12A-S10 | F5 | UG-12A | UG-12A-S10 | A100 | Backfill to NG and remove struts | 326.8905 | m3 | 1 | 2 | UG-12A-S10-A090 | 2 | 2 | UG-12-S01-A080 (FS, shared trench laid) | 2027-07-28 | 2027-07-30 | 2027-07-30 | UG-12A-S12-A100
UG-12A-S10-A110 | AW.PIPE.F5.UG-12A.UG-12A-S10 | F5 | UG-12A | UG-12A-S10 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-12A-S10-A100 | 1 | 2 |  | 2027-07-29 | 2027-08-01
UG-12A-S06-A010 | AW.PIPE.F5.UG-12A.UG-12A-S06 | F5 | UG-12A | UG-12A-S06 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-12A-S06-A020 | AW.PIPE.F5.UG-12A.UG-12A-S06 | F5 | UG-12A | UG-12A-S06 | A020 | Set-out, crossing survey and working platform | 39.0435 | m | 1 | 2 | UG-12A-S06-A010 |  |  | FS from A010; UG-12A-S10-A030 (SS, set-out one package ahead of piling) | 2027-01-19 | 2027-01-21
UG-12A-S06-A030 | AW.PIPE.F5.UG-12A.UG-12A-S06 | F5 | UG-12A | UG-12A-S06 | A030 | Pipe-support piling from platform (incl. integrity tests) | 30 | piles | 6 | 7 | UG-12A-S06-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-25 | 2027-02-01 | 2027-02-01 | UG-12A-S10-A030
UG-12A-S06-A040 | AW.PIPE.F5.UG-12A.UG-12A-S06 | F5 | UG-12A | UG-12A-S06 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-12A-S06-A030 | 3 | 0 |  | 2027-01-28 | 2027-02-01 | 2027-01-08 | UG-12A-S10-A040
UG-12A-S06-A050 | AW.PIPE.F5.UG-12A.UG-12A-S06 | F5 | UG-12A | UG-12A-S06 | A050 | Install dewatering and draw down | 39.0435 | m | 8 | 10 | UG-12A-S06-A040 | 0 | 2 | UG-12A-S10-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-06-15 | 2027-06-25
UG-12A-S06-A060 | AW.PIPE.F5.UG-12A.UG-12A-S06 | F5 | UG-12A | UG-12A-S06 | A060 | Excavate and strut to formation | 641.7501 | m3 | 2 | 3 | UG-12A-S06-A050 | 10 | 2 | UG-12-S01-A060 (SS, shared trench) | 2027-06-25 | 2027-06-28 | 2027-06-28 | UG-12A-S10-A060
UG-12A-S06-A070 | AW.PIPE.F5.UG-12A.UG-12A-S06 | F5 | UG-12A | UG-12A-S06 | A070 | Trim piles, blinding and piled slab (incl. cure) | 39.0435 | m | 7 | 9 | UG-12A-S06-A060 | 1 | 2 |  | 2027-07-12 | 2027-07-21 | 2027-07-21 | UG-12A-S10-A070
UG-12A-S06-A080 | AW.PIPE.F5.UG-12A.UG-12A-S06 | F5 | UG-12A | UG-12A-S06 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 39.0435 | m | 2 | 3 | UG-12A-S06-A070 | 3 | 2 |  | 2027-07-15 | 2027-07-23 | 2027-07-23 | UG-12A-S10-A080
UG-12A-S06-A090 | AW.PIPE.F5.UG-12A.UG-12A-S06 | F5 | UG-12A | UG-12A-S06 | A090 | Surround, joint test and line test | 39.0435 | m | 3 | 4 | UG-12A-S06-A080 | 1 | 2 |  | 2027-07-16 | 2027-07-25
UG-12A-S06-A100 | AW.PIPE.F5.UG-12A.UG-12A-S06 | F5 | UG-12A | UG-12A-S06 | A100 | Backfill to NG and remove struts | 512.2796 | m3 | 2 | 3 | UG-12A-S06-A090 | 2 | 2 | UG-12-S01-A080 (FS, shared trench laid) | 2027-07-30 | 2027-08-02 | 2027-08-02 | UG-12A-S10-A100
UG-12A-S06-A110 | AW.PIPE.F5.UG-12A.UG-12A-S06 | F5 | UG-12A | UG-12A-S06 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-12A-S06-A100 | 1 | 2 |  | 2027-07-31 | 2027-08-04
UG-12A-S05-A010 | AW.PIPE.F5.UG-12A.UG-12A-S05 | F5 | UG-12A | UG-12A-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-12A-S05-A020 | AW.PIPE.F5.UG-12A.UG-12A-S05 | F5 | UG-12A | UG-12A-S05 | A020 | Set-out, crossing survey and working platform | 15.1 | m | 1 | 2 | UG-12A-S05-A010 |  |  | FS from A010; UG-12A-S06-A030 (SS, set-out one package ahead of piling) | 2027-01-25 | 2027-01-27
UG-12A-S05-A030 | AW.PIPE.F5.UG-12A.UG-12A-S05 | F5 | UG-12A | UG-12A-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 14 | piles | 3 | 4 | UG-12A-S05-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-01 | 2027-02-05 | 2027-02-05 | UG-12A-S06-A030
UG-12A-S05-A040 | AW.PIPE.F5.UG-12A.UG-12A-S05 | F5 | UG-12A | UG-12A-S05 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-12A-S05-A030 | 2 | 0 |  | 2027-02-03 | 2027-02-05 | 2027-01-08 | UG-12A-S06-A040
UG-12A-S05-A050 | AW.PIPE.F5.UG-12A.UG-12A-S05 | F5 | UG-12A | UG-12A-S05 | A050 | Install dewatering and draw down | 15.1 | m | 8 | 10 | UG-12A-S05-A040 | 0 | 2 | UG-12A-S06-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-06-18 | 2027-06-28
UG-12A-S05-A060 | AW.PIPE.F5.UG-12A.UG-12A-S05 | F5 | UG-12A | UG-12A-S05 | A060 | Excavate and strut to formation | 247.9685 | m3 | 1 | 2 | UG-12A-S05-A050 | 10 | 2 | UG-06-S03-A100 (FS, deeper first) | 2027-06-28 | 2027-06-30 | 2027-06-30 | UG-12A-S06-A060
UG-12A-S05-A070 | AW.PIPE.F5.UG-12A.UG-12A-S05 | F5 | UG-12A | UG-12A-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 15.1 | m | 5 | 6 | UG-12A-S05-A060 | 1 | 2 |  | 2027-07-21 | 2027-07-27 | 2027-07-27 | UG-12A-S06-A070
UG-12A-S05-A080 | AW.PIPE.F5.UG-12A.UG-12A-S05 | F5 | UG-12A | UG-12A-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 15.1 | m | 2 | 3 | UG-12A-S05-A070 | 2 | 2 |  | 2027-07-23 | 2027-07-29 | 2027-07-29 | UG-12A-S06-A080
UG-12A-S05-A090 | AW.PIPE.F5.UG-12A.UG-12A-S05 | F5 | UG-12A | UG-12A-S05 | A090 | Surround, joint test and line test | 15.1 | m | 3 | 4 | UG-12A-S05-A080 | 1 | 2 |  | 2027-07-24 | 2027-07-31
UG-12A-S05-A100 | AW.PIPE.F5.UG-12A.UG-12A-S05 | F5 | UG-12A | UG-12A-S05 | A100 | Backfill to NG and remove struts | 197.9784 | m3 | 1 | 2 | UG-12A-S05-A090 | 2 | 2 |  | 2027-08-02 | 2027-08-04 | 2027-08-04 | UG-12A-S06-A100
UG-12A-S05-A110 | AW.PIPE.F5.UG-12A.UG-12A-S05 | F5 | UG-12A | UG-12A-S05 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-12A-S05-A100 | 1 | 2 |  | 2027-08-03 | 2027-08-06
UG-12A-S04-A010 | AW.PIPE.F5.UG-12A.UG-12A-S04 | F5 | UG-12A | UG-12A-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-12A-S04-A020 | AW.PIPE.F5.UG-12A.UG-12A-S04 | F5 | UG-12A | UG-12A-S04 | A020 | Set-out, crossing survey and working platform | 76.674 | m | 1 | 2 | UG-12A-S04-A010 |  |  | FS from A010; UG-12A-S05-A030 (SS, set-out one package ahead of piling) | 2027-02-01 | 2027-02-03
UG-12A-S04-A030 | AW.PIPE.F5.UG-12A.UG-12A-S04 | F5 | UG-12A | UG-12A-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 54 | piles | 11 | 13 | UG-12A-S04-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-05 | 2027-02-18 | 2027-02-18 | UG-12A-S05-A030
UG-12A-S04-A040 | AW.PIPE.F5.UG-12A.UG-12A-S04 | F5 | UG-12A | UG-12A-S04 | A040 | Install sheet piles (shored lengths) | 72.2153 | m wall | 3 | 4 | UG-12A-S04-A030 | 4 | 2 |  | 2027-02-09 | 2027-02-20 | 2027-02-20 | UG-12A-S05-A040
UG-12A-S04-A050 | AW.PIPE.F5.UG-12A.UG-12A-S04 | F5 | UG-12A | UG-12A-S04 | A050 | Install dewatering and draw down | 76.674 | m | 9 | 11 | UG-12A-S04-A040 | 2 | 2 | UG-12A-S05-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-06-19 | 2027-06-30
UG-12A-S04-A060 | AW.PIPE.F5.UG-12A.UG-12A-S04 | F5 | UG-12A | UG-12A-S04 | A060 | Excavate and strut to formation | 957.5324 | m3 | 3 | 4 | UG-12A-S04-A050 | 10 | 2 | UG-05-S04-A100 (FS, deeper first); UG-06-S04-A100 (FS, deeper first) | 2027-06-30 | 2027-07-04 | 2027-07-04 | UG-12A-S05-A060
UG-12A-S04-A070 | AW.PIPE.F5.UG-12A.UG-12A-S04 | F5 | UG-12A | UG-12A-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 76.674 | m | 10 | 12 | UG-12A-S04-A060 | 2 | 2 |  | 2027-07-27 | 2027-08-08 | 2027-08-08 | UG-12A-S05-A070
UG-12A-S04-A080 | AW.PIPE.F5.UG-12A.UG-12A-S04 | F5 | UG-12A | UG-12A-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 76.674 | m | 4 | 5 | UG-12A-S04-A070 | 4 | 2 |  | 2027-07-31 | 2027-08-10 | 2027-08-10 | UG-12A-S05-A080
UG-12A-S04-A090 | AW.PIPE.F5.UG-12A.UG-12A-S04 | F5 | UG-12A | UG-12A-S04 | A090 | Surround, joint test and line test | 76.674 | m | 3 | 4 | UG-12A-S04-A080 | 2 | 2 |  | 2027-08-02 | 2027-08-12
UG-12A-S04-A100 | AW.PIPE.F5.UG-12A.UG-12A-S04 | F5 | UG-12A | UG-12A-S04 | A100 | Backfill to NG and remove struts | 703.6943 | m3 | 3 | 4 | UG-12A-S04-A090 | 2 | 2 |  | 2027-08-04 | 2027-08-14 | 2027-08-14 | UG-12A-S05-A100
UG-12A-S04-A110 | AW.PIPE.F5.UG-12A.UG-12A-S04 | F5 | UG-12A | UG-12A-S04 | A110 | Dewatering off, extract sheets, reinstate | 72.2153 | m wall | 3 | 4 | UG-12A-S04-A100 | 2 | 2 |  | 2027-08-06 | 2027-08-16
UG-12A-S03-A010 | AW.PIPE.F5.UG-12A.UG-12A-S03 | F5 | UG-12A | UG-12A-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-12A-S03-A020 | AW.PIPE.F5.UG-12A.UG-12A-S03 | F5 | UG-12A | UG-12A-S03 | A020 | Set-out, crossing survey and working platform | 64.526 | m | 1 | 2 | UG-12A-S03-A010 |  |  | FS from A010; UG-12A-S04-A030 (SS, set-out one package ahead of piling) | 2027-02-05 | 2027-02-07
UG-12A-S03-A030 | AW.PIPE.F5.UG-12A.UG-12A-S03 | F5 | UG-12A | UG-12A-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 46 | piles | 10 | 12 | UG-12A-S03-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-18 | 2027-03-02 | 2027-03-02 | UG-12A-S04-A030
UG-12A-S03-A040 | AW.PIPE.F5.UG-12A.UG-12A-S03 | F5 | UG-12A | UG-12A-S03 | A040 | Install sheet piles (shored lengths) | 80 | m wall | 4 | 5 | UG-12A-S03-A030 | 4 | 2 |  | 2027-02-22 | 2027-03-04 | 2027-03-04 | UG-12A-S04-A040
UG-12A-S03-A050 | AW.PIPE.F5.UG-12A.UG-12A-S03 | F5 | UG-12A | UG-12A-S03 | A050 | Install dewatering and draw down | 64.526 | m | 9 | 11 | UG-12A-S03-A040 | 2 | 2 | UG-12A-S04-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-06-23 | 2027-07-04
UG-12A-S03-A060 | AW.PIPE.F5.UG-12A.UG-12A-S03 | F5 | UG-12A | UG-12A-S03 | A060 | Excavate and strut to formation | 607.3954 | m3 | 2 | 3 | UG-12A-S03-A050 | 10 | 2 | UG-05-S04-A100 (FS, deeper first); UG-06-S04-A100 (FS, deeper first); UG-06-S05-A100 (FS, deeper first) | 2027-07-04 | 2027-07-07 | 2027-07-07 | UG-12A-S04-A060
UG-12A-S03-A070 | AW.PIPE.F5.UG-12A.UG-12A-S03 | F5 | UG-12A | UG-12A-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 64.526 | m | 9 | 11 | UG-12A-S03-A060 | 1 | 2 |  | 2027-08-08 | 2027-08-19 | 2027-08-19 | UG-12A-S04-A070
UG-12A-S03-A080 | AW.PIPE.F5.UG-12A.UG-12A-S03 | F5 | UG-12A | UG-12A-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 64.526 | m | 5 | 6 | UG-12A-S03-A070 | 4 | 2 |  | 2027-08-12 | 2027-08-21 | 2027-08-21 | UG-12A-S04-A080
UG-12A-S03-A090 | AW.PIPE.F5.UG-12A.UG-12A-S03 | F5 | UG-12A | UG-12A-S03 | A090 | Surround, joint test and line test | 64.526 | m | 3 | 4 | UG-12A-S03-A080 | 2 | 2 |  | 2027-08-14 | 2027-08-23
UG-12A-S03-A100 | AW.PIPE.F5.UG-12A.UG-12A-S03 | F5 | UG-12A | UG-12A-S03 | A100 | Backfill to NG and remove struts | 455.3215 | m3 | 2 | 3 | UG-12A-S03-A090 | 2 | 2 |  | 2027-08-16 | 2027-08-25 | 2027-08-25 | UG-12A-S04-A100
UG-12A-S03-A110 | AW.PIPE.F5.UG-12A.UG-12A-S03 | F5 | UG-12A | UG-12A-S03 | A110 | Dewatering off, extract sheets, reinstate | 80 | m wall | 3 | 4 | UG-12A-S03-A100 | 1 | 2 |  | 2027-08-17 | 2027-08-27
UG-12A-S02-A010 | AW.PIPE.F5.UG-12A.UG-12A-S02 | F5 | UG-12A | UG-12A-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-12A-S02-A020 | AW.PIPE.F5.UG-12A.UG-12A-S02 | F5 | UG-12A | UG-12A-S02 | A020 | Set-out, crossing survey and working platform | 69.9458 | m | 1 | 2 | UG-12A-S02-A010 |  |  | FS from A010; UG-12A-S03-A030 (SS, set-out one package ahead of piling) | 2027-02-18 | 2027-02-20
UG-12A-S02-A030 | AW.PIPE.F5.UG-12A.UG-12A-S02 | F5 | UG-12A | UG-12A-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 50 | piles | 10 | 12 | UG-12A-S02-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-02 | 2027-03-14 | 2027-03-14 | UG-12A-S03-A030
UG-12A-S02-A040 | AW.PIPE.F5.UG-12A.UG-12A-S02 | F5 | UG-12A | UG-12A-S02 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-12A-S02-A030 | 4 | 0 |  | 2027-03-06 | 2027-03-14 | 2027-03-04 | UG-12A-S03-A040
UG-12A-S02-A050 | AW.PIPE.F5.UG-12A.UG-12A-S02 | F5 | UG-12A | UG-12A-S02 | A050 | Install dewatering and draw down | 69.9458 | m | 9 | 11 | UG-12A-S02-A040 | 0 | 2 | UG-12A-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-06-26 | 2027-07-07
UG-12A-S02-A060 | AW.PIPE.F5.UG-12A.UG-12A-S02 | F5 | UG-12A | UG-12A-S02 | A060 | Excavate and strut to formation | 952.9319 | m3 | 3 | 4 | UG-12A-S02-A050 | 10 | 2 |  | 2027-07-07 | 2027-07-11 | 2027-07-11 | UG-12A-S03-A060
UG-12A-S02-A070 | AW.PIPE.F5.UG-12A.UG-12A-S02 | F5 | UG-12A | UG-12A-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 69.9458 | m | 9 | 11 | UG-12A-S02-A060 | 2 | 2 |  | 2027-08-19 | 2027-08-30 | 2027-08-30 | UG-12A-S03-A070
UG-12A-S02-A080 | AW.PIPE.F5.UG-12A.UG-12A-S02 | F5 | UG-12A | UG-12A-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 69.9458 | m | 3 | 4 | UG-12A-S02-A070 | 4 | 2 |  | 2027-08-23 | 2027-09-01 | 2027-09-01 | UG-12A-S03-A080
UG-12A-S02-A090 | AW.PIPE.F5.UG-12A.UG-12A-S02 | F5 | UG-12A | UG-12A-S02 | A090 | Surround, joint test and line test | 69.9458 | m | 3 | 4 | UG-12A-S02-A080 | 2 | 2 |  | 2027-08-25 | 2027-09-03
UG-12A-S02-A100 | AW.PIPE.F5.UG-12A.UG-12A-S02 | F5 | UG-12A | UG-12A-S02 | A100 | Backfill to NG and remove struts | 796.8848 | m3 | 3 | 4 | UG-12A-S02-A090 | 2 | 2 |  | 2027-08-27 | 2027-09-05 | 2027-09-05 | UG-12A-S03-A100
UG-12A-S02-A110 | AW.PIPE.F5.UG-12A.UG-12A-S02 | F5 | UG-12A | UG-12A-S02 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-12A-S02-A100 | 2 | 2 |  | 2027-08-29 | 2027-09-07
UG-12A-S01-A010 | AW.PIPE.F5.UG-12A.UG-12A-S01 | F5 | UG-12A | UG-12A-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-12A-S01-A020 | AW.PIPE.F5.UG-12A.UG-12A-S01 | F5 | UG-12A | UG-12A-S01 | A020 | Set-out, crossing survey and working platform | 15.2542 | m | 1 | 2 | UG-12A-S01-A010 |  |  | FS from A010; UG-12A-S02-A030 (SS, tie-in team follows the adjacent run) | 2027-03-02 | 2027-03-04
UG-12A-S01-A030 | AW.PIPE.F5.UG-12A.UG-12A-S01 | F5 | UG-12A | UG-12A-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 14 | piles | 3 | 4 | UG-12A-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-03 | 2027-03-07 | 2027-03-07
UG-12A-S01-A040 | AW.PIPE.F5.UG-12A.UG-12A-S01 | F5 | UG-12A | UG-12A-S01 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-12A-S01-A030 | 2 | 0 |  | 2027-03-05 | 2027-03-07 | 0
UG-12A-S01-A050 | AW.PIPE.F5.UG-12A.UG-12A-S01 | F5 | UG-12A | UG-12A-S01 | A050 | Install dewatering and draw down | 15.2542 | m | 8 | 10 | UG-12A-S01-A040 | 0 | 2 |  | 2027-03-05 | 2027-03-15
UG-12A-S01-A060 | AW.PIPE.F5.UG-12A.UG-12A-S01 | F5 | UG-12A | UG-12A-S01 | A060 | Excavate and strut to formation | 214.6849 | m3 | 1 | 2 | UG-12A-S01-A050 | 10 | 2 |  | 2027-03-15 | 2027-03-17 | 2027-03-17
UG-12A-S01-A070 | AW.PIPE.F5.UG-12A.UG-12A-S01 | F5 | UG-12A | UG-12A-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 15.2542 | m | 5 | 6 | UG-12A-S01-A060 | 1 | 2 |  | 2027-03-16 | 2027-03-22 | 2027-03-22
UG-12A-S01-A080 | AW.PIPE.F5.UG-12A.UG-12A-S01 | F5 | UG-12A | UG-12A-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 15.2542 | m | 5 | 6 | UG-12A-S01-A070 | 2 | 2 | UG-12A-S02-A080 (FS, closure) | 2027-09-01 | 2027-09-07 | 2027-09-07
UG-12A-S01-A090 | AW.PIPE.F5.UG-12A.UG-12A-S01 | F5 | UG-12A | UG-12A-S01 | A090 | Surround, joint test and line test | 15.2542 | m | 3 | 4 | UG-12A-S01-A080 | 2 | 2 |  | 2027-09-03 | 2027-09-09
UG-12A-S01-A100 | AW.PIPE.F5.UG-12A.UG-12A-S01 | F5 | UG-12A | UG-12A-S01 | A100 | Backfill to NG and remove struts | 180.6533 | m3 | 1 | 2 | UG-12A-S01-A090 | 2 | 2 |  | 2027-09-05 | 2027-09-11 | 2027-09-11
UG-12A-S01-A110 | AW.PIPE.F5.UG-12A.UG-12A-S01 | F5 | UG-12A | UG-12A-S01 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-12A-S01-A100 | 1 | 2 |  | 2027-09-06 | 2027-09-13
UG-12A-S08-A010 | AW.PIPE.F5.UG-12A.UG-12A-S08 | F5 | UG-12A | UG-12A-S08 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-12A-S08-A020 | AW.PIPE.F5.UG-12A.UG-12A-S08 | F5 | UG-12A | UG-12A-S08 | A020 | Set-out, crossing survey and working platform | 5.2744 | m | 1 | 2 | UG-12A-S08-A010 |  |  | FS from A010; UG-12A-S02-A030 (SS, set-out one package ahead of piling) | 2027-03-02 | 2027-03-04
UG-12A-S08-A030 | AW.PIPE.F5.UG-12A.UG-12A-S08 | F5 | UG-12A | UG-12A-S08 | A030 | Pipe-support piling from platform (incl. integrity tests) | 6 | piles | 2 | 3 | UG-12A-S08-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-14 | 2027-03-17 | 2027-03-17 | UG-12A-S02-A030
UG-12A-S08-A040 | AW.PIPE.F5.UG-12A.UG-12A-S08 | F5 | UG-12A | UG-12A-S08 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-12A-S08-A030 | 1 | 0 |  | 2027-03-15 | 2027-03-17 | 2027-03-04 | UG-12A-S02-A040
UG-12A-S08-A050 | AW.PIPE.F5.UG-12A.UG-12A-S08 | F5 | UG-12A | UG-12A-S08 | A050 | Install dewatering and draw down | 5.2744 | m | 8 | 10 | UG-12A-S08-A040 | 0 | 2 | UG-12A-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-07-01 | 2027-07-11
UG-12A-S08-A060 | AW.PIPE.F5.UG-12A.UG-12A-S08 | F5 | UG-12A | UG-12A-S08 | A060 | Excavate and strut to formation | 73.9439 | m3 | 1 | 2 | UG-12A-S08-A050 | 10 | 2 | UG-05-S04-A100 (FS, deeper first); UG-06-S04-A100 (FS, deeper first) | 2027-07-11 | 2027-07-13 | 2027-07-13 | UG-12A-S02-A060
UG-12A-S08-A070 | AW.PIPE.F5.UG-12A.UG-12A-S08 | F5 | UG-12A | UG-12A-S08 | A070 | Trim piles, blinding and piled slab (incl. cure) | 5.2744 | m | 4 | 5 | UG-12A-S08-A060 | 1 | 2 |  | 2027-08-30 | 2027-09-04 | 2027-09-04 | UG-12A-S02-A070
UG-12A-S08-A080 | AW.PIPE.F5.UG-12A.UG-12A-S08 | F5 | UG-12A | UG-12A-S08 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 5.2744 | m | 1 | 2 | UG-12A-S08-A070 | 2 | 2 |  | 2027-09-01 | 2027-09-06 | 2027-09-06 | UG-12A-S02-A080
UG-12A-S08-A090 | AW.PIPE.F5.UG-12A.UG-12A-S08 | F5 | UG-12A | UG-12A-S08 | A090 | Surround, joint test and line test | 5.2744 | m | 3 | 4 | UG-12A-S08-A080 | 1 | 2 |  | 2027-09-02 | 2027-09-08
UG-12A-S08-A100 | AW.PIPE.F5.UG-12A.UG-12A-S08 | F5 | UG-12A | UG-12A-S08 | A100 | Backfill to NG and remove struts | 62.177 | m3 | 1 | 2 | UG-12A-S08-A090 | 2 | 2 |  | 2027-09-05 | 2027-09-10 | 2027-09-10 | UG-12A-S02-A100
UG-12A-S08-A110 | AW.PIPE.F5.UG-12A.UG-12A-S08 | F5 | UG-12A | UG-12A-S08 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-12A-S08-A100 | 1 | 2 |  | 2027-09-06 | 2027-09-12
UG-12A-S07-A010 | AW.PIPE.F5.UG-12A.UG-12A-S07 | F5 | UG-12A | UG-12A-S07 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-12A-S07-A020 | AW.PIPE.F5.UG-12A.UG-12A-S07 | F5 | UG-12A | UG-12A-S07 | A020 | Set-out, crossing survey and working platform | 11.1248 | m | 1 | 2 | UG-12A-S07-A010 |  |  | FS from A010; UG-12A-S08-A030 (SS, tie-in team follows the adjacent run) | 2027-03-14 | 2027-03-16
UG-12A-S07-A030 | AW.PIPE.F5.UG-12A.UG-12A-S07 | F5 | UG-12A | UG-12A-S07 | A030 | Pipe-support piling from platform (incl. integrity tests) | 10 | piles | 2 | 3 | UG-12A-S07-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-15 | 2027-03-18 | 2027-03-18
UG-12A-S07-A040 | AW.PIPE.F5.UG-12A.UG-12A-S07 | F5 | UG-12A | UG-12A-S07 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-12A-S07-A030 | 1 | 0 |  | 2027-03-16 | 2027-03-18 | 0
UG-12A-S07-A050 | AW.PIPE.F5.UG-12A.UG-12A-S07 | F5 | UG-12A | UG-12A-S07 | A050 | Install dewatering and draw down | 11.1248 | m | 8 | 10 | UG-12A-S07-A040 | 0 | 2 |  | 2027-03-16 | 2027-03-26
UG-12A-S07-A060 | AW.PIPE.F5.UG-12A.UG-12A-S07 | F5 | UG-12A | UG-12A-S07 | A060 | Excavate and strut to formation | 156.6366 | m3 | 1 | 2 | UG-12A-S07-A050 | 10 | 2 | UG-06-S04-A100 (FS, deeper first) | 2027-05-21 | 2027-05-23 | 2027-05-23
UG-12A-S07-A070 | AW.PIPE.F5.UG-12A.UG-12A-S07 | F5 | UG-12A | UG-12A-S07 | A070 | Trim piles, blinding and piled slab (incl. cure) | 11.1248 | m | 4 | 5 | UG-12A-S07-A060 | 1 | 2 |  | 2027-05-22 | 2027-05-27 | 2027-05-27
UG-12A-S07-A080 | AW.PIPE.F5.UG-12A.UG-12A-S07 | F5 | UG-12A | UG-12A-S07 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 11.1248 | m | 5 | 6 | UG-12A-S07-A070 | 2 | 2 | UG-12A-S08-A080 (FS, closure) | 2027-09-06 | 2027-09-12 | 2027-09-12
UG-12A-S07-A090 | AW.PIPE.F5.UG-12A.UG-12A-S07 | F5 | UG-12A | UG-12A-S07 | A090 | Surround, joint test and line test | 11.1248 | m | 3 | 4 | UG-12A-S07-A080 | 2 | 2 |  | 2027-09-08 | 2027-09-14
UG-12A-S07-A100 | AW.PIPE.F5.UG-12A.UG-12A-S07 | F5 | UG-12A | UG-12A-S07 | A100 | Backfill to NG and remove struts | 131.8175 | m3 | 1 | 2 | UG-12A-S07-A090 | 2 | 2 |  | 2027-09-10 | 2027-09-16 | 2027-09-16
UG-12A-S07-A110 | AW.PIPE.F5.UG-12A.UG-12A-S07 | F5 | UG-12A | UG-12A-S07 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-12A-S07-A100 | 1 | 2 |  | 2027-09-11 | 2027-09-18
UG-12A-S09-A010 | AW.PIPE.F5.UG-12A.UG-12A-S09 | F5 | UG-12A | UG-12A-S09 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-12A-S09-A020 | AW.PIPE.F5.UG-12A.UG-12A-S09 | F5 | UG-12A | UG-12A-S09 | A020 | Set-out, crossing survey and working platform | 6 | m | 1 | 2 | UG-12A-S09-A010 |  |  | FS from A010; UG-12A-S10-A030 (SS, tie-in team follows the adjacent run) | 2027-01-19 | 2027-01-21
UG-12A-S09-A030 | AW.PIPE.F5.UG-12A.UG-12A-S09 | F5 | UG-12A | UG-12A-S09 | A030 | Pipe-support piling from platform (incl. integrity tests) | 8 | piles | 2 | 3 | UG-12A-S09-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-20 | 2027-01-23 | 2027-01-23
UG-12A-S09-A040 | AW.PIPE.F5.UG-12A.UG-12A-S09 | F5 | UG-12A | UG-12A-S09 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-12A-S09-A030 | 1 | 0 |  | 2027-01-21 | 2027-01-23 | 0
UG-12A-S09-A050 | AW.PIPE.F5.UG-12A.UG-12A-S09 | F5 | UG-12A | UG-12A-S09 | A050 | Install dewatering and draw down | 6 | m | 8 | 10 | UG-12A-S09-A040 | 0 | 2 |  | 2027-01-21 | 2027-01-31
UG-12A-S09-A060 | AW.PIPE.F5.UG-12A.UG-12A-S09 | F5 | UG-12A | UG-12A-S09 | A060 | Excavate and strut to formation | 80.1357 | m3 | 1 | 2 | UG-12A-S09-A050 | 10 | 2 | UG-13A-S15-A100 (FS, deeper first) | 2027-06-23 | 2027-06-25 | 2027-06-25
UG-12A-S09-A070 | AW.PIPE.F5.UG-12A.UG-12A-S09 | F5 | UG-12A | UG-12A-S09 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6 | m | 4 | 5 | UG-12A-S09-A060 | 1 | 2 |  | 2027-06-24 | 2027-06-29 | 2027-06-29
UG-12A-S09-A080 | AW.PIPE.F5.UG-12A.UG-12A-S09 | F5 | UG-12A | UG-12A-S09 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6 | m | 4 | 5 | UG-12A-S09-A070 | 2 | 2 | UG-12A-S10-A080 (FS, closure) | 2027-07-14 | 2027-07-19 | 2027-07-19
UG-12A-S09-A090 | AW.PIPE.F5.UG-12A.UG-12A-S09 | F5 | UG-12A | UG-12A-S09 | A090 | Surround, joint test and line test | 6 | m | 3 | 4 | UG-12A-S09-A080 | 2 | 2 |  | 2027-07-16 | 2027-07-21
UG-12A-S09-A100 | AW.PIPE.F5.UG-12A.UG-12A-S09 | F5 | UG-12A | UG-12A-S09 | A100 | Backfill to NG and remove struts | 66.7499 | m3 | 1 | 2 | UG-12A-S09-A090 | 2 | 2 |  | 2027-07-18 | 2027-07-23 | 2027-07-23
UG-12A-S09-A110 | AW.PIPE.F5.UG-12A.UG-12A-S09 | F5 | UG-12A | UG-12A-S09 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-12A-S09-A100 | 1 | 2 |  | 2027-07-19 | 2027-07-25
UG-12A-S11-A010 | AW.PIPE.F5.UG-12A.UG-12A-S11 | F5 | UG-12A | UG-12A-S11 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-12A-S11-A020 | AW.PIPE.F5.UG-12A.UG-12A-S11 | F5 | UG-12A | UG-12A-S11 | A020 | Set-out, crossing survey and working platform | 6 | m | 1 | 2 | UG-12A-S11-A010 |  |  | FS from A010; UG-12A-S12-A030 (SS, tie-in team follows the adjacent run) | 2027-01-16 | 2027-01-18
UG-12A-S11-A030 | AW.PIPE.F5.UG-12A.UG-12A-S11 | F5 | UG-12A | UG-12A-S11 | A030 | Pipe-support piling from platform (incl. integrity tests) | 6 | piles | 2 | 3 | UG-12A-S11-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-17 | 2027-01-20 | 2027-01-20
UG-12A-S11-A040 | AW.PIPE.F5.UG-12A.UG-12A-S11 | F5 | UG-12A | UG-12A-S11 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-12A-S11-A030 | 1 | 0 |  | 2027-01-18 | 2027-01-20 | 0
UG-12A-S11-A050 | AW.PIPE.F5.UG-12A.UG-12A-S11 | F5 | UG-12A | UG-12A-S11 | A050 | Install dewatering and draw down | 6 | m | 8 | 10 | UG-12A-S11-A040 | 0 | 2 |  | 2027-01-18 | 2027-01-28
UG-12A-S11-A060 | AW.PIPE.F5.UG-12A.UG-12A-S11 | F5 | UG-12A | UG-12A-S11 | A060 | Excavate and strut to formation | 80.7122 | m3 | 1 | 2 | UG-12A-S11-A050 | 10 | 2 | UG-13-S03-A100 (FS, deeper first) | 2027-01-28 | 2027-01-30 | 2027-01-30
UG-12A-S11-A070 | AW.PIPE.F5.UG-12A.UG-12A-S11 | F5 | UG-12A | UG-12A-S11 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6 | m | 4 | 5 | UG-12A-S11-A060 | 1 | 2 |  | 2027-01-29 | 2027-02-03 | 2027-02-03
UG-12A-S11-A080 | AW.PIPE.F5.UG-12A.UG-12A-S11 | F5 | UG-12A | UG-12A-S11 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6 | m | 4 | 5 | UG-12A-S11-A070 | 2 | 2 | UG-12A-S12-A080 (FS, closure) | 2027-07-07 | 2027-07-12 | 2027-07-12
UG-12A-S11-A090 | AW.PIPE.F5.UG-12A.UG-12A-S11 | F5 | UG-12A | UG-12A-S11 | A090 | Surround, joint test and line test | 6 | m | 3 | 4 | UG-12A-S11-A080 | 2 | 2 |  | 2027-07-09 | 2027-07-14
UG-12A-S11-A100 | AW.PIPE.F5.UG-12A.UG-12A-S11 | F5 | UG-12A | UG-12A-S11 | A100 | Backfill to NG and remove struts | 67.3264 | m3 | 1 | 2 | UG-12A-S11-A090 | 2 | 2 |  | 2027-07-11 | 2027-07-16 | 2027-07-16
UG-12A-S11-A110 | AW.PIPE.F5.UG-12A.UG-12A-S11 | F5 | UG-12A | UG-12A-S11 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-12A-S11-A100 | 1 | 2 |  | 2027-07-12 | 2027-07-18
UG-11-S02-A010 | AW.PIPE.F6.UG-11.UG-11-S02 | F6 | UG-11 | UG-11-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11-S02-A020 | AW.PIPE.F6.UG-11.UG-11-S02 | F6 | UG-11 | UG-11-S02 | A020 | Set-out, crossing survey and working platform | 26.246 | m | 1 | 2 | UG-11-S02-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-11-S02-A030 | AW.PIPE.F6.UG-11.UG-11-S02 | F6 | UG-11 | UG-11-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 20 | piles | 4 | 5 | UG-11-S02-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-07 | 2026-12-07
UG-11-S02-A040 | AW.PIPE.F6.UG-11.UG-11-S02 | F6 | UG-11 | UG-11-S02 | A040 | Install sheet piles (shored lengths) | 52.4921 | m wall | 3 | 4 | UG-11-S02-A030 | 2 | 2 |  | 2026-12-04 | 2026-12-09 | 2026-12-09
UG-11-S02-A050 | AW.PIPE.F6.UG-11.UG-11-S02 | F6 | UG-11 | UG-11-S02 | A050 | Install dewatering and draw down | 26.246 | m | 8 | 10 | UG-11-S02-A040 | 2 | 2 |  | 2026-12-06 | 2026-12-16
UG-11-S02-A060 | AW.PIPE.F6.UG-11.UG-11-S02 | F6 | UG-11 | UG-11-S02 | A060 | Excavate and strut to formation | 384.348 | m3 | 2 | 3 | UG-11-S02-A050 | 10 | 2 |  | 2026-12-16 | 2026-12-19 | 2026-12-19
UG-11-S02-A070 | AW.PIPE.F6.UG-11.UG-11-S02 | F6 | UG-11 | UG-11-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 26.246 | m | 6 | 7 | UG-11-S02-A060 | 1 | 2 |  | 2026-12-17 | 2026-12-24 | 2026-12-24
UG-11-S02-A080 | AW.PIPE.F6.UG-11.UG-11-S02 | F6 | UG-11 | UG-11-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 26.246 | m | 4 | 5 | UG-11-S02-A070 | 3 | 2 |  | 2026-12-20 | 2026-12-26 | 2026-12-26
UG-11-S02-A090 | AW.PIPE.F6.UG-11.UG-11-S02 | F6 | UG-11 | UG-11-S02 | A090 | Surround, joint test and line test | 26.246 | m | 3 | 4 | UG-11-S02-A080 | 2 | 2 |  | 2026-12-22 | 2026-12-28
UG-11-S02-A100 | AW.PIPE.F6.UG-11.UG-11-S02 | F6 | UG-11 | UG-11-S02 | A100 | Backfill to NG and remove struts | 275.8234 | m3 | 1 | 2 | UG-11-S02-A090 | 2 | 2 | UG-11A-S05-A080 (FS, shared trench laid) | 2027-01-04 | 2027-01-06 | 2027-01-06
UG-11-S02-A110 | AW.PIPE.F6.UG-11.UG-11-S02 | F6 | UG-11 | UG-11-S02 | A110 | Dewatering off, extract sheets, reinstate | 52.4921 | m wall | 3 | 4 | UG-11-S02-A100 | 1 | 2 |  | 2027-01-05 | 2027-01-09
UG-11A-S05-A010 | AW.PIPE.F6.UG-11A.UG-11A-S05 | F6 | UG-11A | UG-11A-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11A-S05-A020 | AW.PIPE.F6.UG-11A.UG-11A-S05 | F6 | UG-11A | UG-11A-S05 | A020 | Set-out, crossing survey and working platform | 40.1906 | m | 1 | 2 | UG-11A-S05-A010 |  |  | FS from A010; UG-11-S02-A030 (SS, set-out one package ahead of piling) | 2026-12-02 | 2026-12-04
UG-11A-S05-A030 | AW.PIPE.F6.UG-11A.UG-11A-S05 | F6 | UG-11A | UG-11A-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 30 | piles | 6 | 7 | UG-11A-S05-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-07 | 2026-12-14 | 2026-12-14 | UG-11-S02-A030
UG-11A-S05-A040 | AW.PIPE.F6.UG-11A.UG-11A-S05 | F6 | UG-11A | UG-11A-S05 | A040 | Install sheet piles (shored lengths) | 80.3813 | m wall | 4 | 5 | UG-11A-S05-A030 | 3 | 2 |  | 2026-12-10 | 2026-12-16 | 2026-12-16 | UG-11-S02-A040
UG-11A-S05-A050 | AW.PIPE.F6.UG-11A.UG-11A-S05 | F6 | UG-11A | UG-11A-S05 | A050 | Install dewatering and draw down | 40.1906 | m | 9 | 11 | UG-11A-S05-A040 | 2 | 2 | UG-11-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2026-12-12 | 2026-12-23
UG-11A-S05-A060 | AW.PIPE.F6.UG-11A.UG-11A-S05 | F6 | UG-11A | UG-11A-S05 | A060 | Excavate and strut to formation | 490.5894 | m3 | 2 | 3 | UG-11A-S05-A050 | 10 | 2 | UG-11-S02-A060 (SS, shared trench) | 2026-12-22 | 2026-12-25 | 2026-12-25 | UG-11-S02-A060
UG-11A-S05-A070 | AW.PIPE.F6.UG-11A.UG-11A-S05 | F6 | UG-11A | UG-11A-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 40.1906 | m | 7 | 9 | UG-11A-S05-A060 | 1 | 2 |  | 2026-12-24 | 2027-01-02 | 2027-01-02 | UG-11-S02-A070
UG-11A-S05-A080 | AW.PIPE.F6.UG-11A.UG-11A-S05 | F6 | UG-11A | UG-11A-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 40.1906 | m | 2 | 3 | UG-11A-S05-A070 | 3 | 2 |  | 2026-12-27 | 2027-01-04 | 2027-01-04 | UG-11-S02-A080
UG-11A-S05-A090 | AW.PIPE.F6.UG-11A.UG-11A-S05 | F6 | UG-11A | UG-11A-S05 | A090 | Surround, joint test and line test | 40.1906 | m | 3 | 4 | UG-11A-S05-A080 | 1 | 2 |  | 2026-12-28 | 2027-01-06
UG-11A-S05-A100 | AW.PIPE.F6.UG-11A.UG-11A-S05 | F6 | UG-11A | UG-11A-S05 | A100 | Backfill to NG and remove struts | 380.4804 | m3 | 2 | 3 | UG-11A-S05-A090 | 2 | 2 | UG-11-S02-A080 (FS, shared trench laid) | 2027-01-06 | 2027-01-09 | 2027-01-09 | UG-11-S02-A100
UG-11A-S05-A110 | AW.PIPE.F6.UG-11A.UG-11A-S05 | F6 | UG-11A | UG-11A-S05 | A110 | Dewatering off, extract sheets, reinstate | 80.3813 | m wall | 3 | 4 | UG-11A-S05-A100 | 1 | 2 |  | 2027-01-07 | 2027-01-11
UG-11-S06-A010 | AW.PIPE.F6.UG-11.UG-11-S06 | F6 | UG-11 | UG-11-S06 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11-S06-A020 | AW.PIPE.F6.UG-11.UG-11-S06 | F6 | UG-11 | UG-11-S06 | A020 | Set-out, crossing survey and working platform | 43.2042 | m | 1 | 2 | UG-11-S06-A010 |  |  | FS from A010; UG-11A-S05-A030 (SS, set-out one package ahead of piling) | 2026-12-07 | 2026-12-09
UG-11-S06-A030 | AW.PIPE.F6.UG-11.UG-11-S06 | F6 | UG-11 | UG-11-S06 | A030 | Pipe-support piling from platform (incl. integrity tests) | 32 | piles | 7 | 9 | UG-11-S06-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-14 | 2026-12-23 | 2026-12-23 | UG-11A-S05-A030
UG-11-S06-A040 | AW.PIPE.F6.UG-11.UG-11-S06 | F6 | UG-11 | UG-11-S06 | A040 | Install sheet piles (shored lengths) | 86.4084 | m wall | 4 | 5 | UG-11-S06-A030 | 3 | 2 |  | 2026-12-17 | 2026-12-25 | 2026-12-25 | UG-11A-S05-A040
UG-11-S06-A050 | AW.PIPE.F6.UG-11.UG-11-S06 | F6 | UG-11 | UG-11-S06 | A050 | Install dewatering and draw down | 43.2042 | m | 9 | 11 | UG-11-S06-A040 | 2 | 2 | UG-11A-S05-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2026-12-19 | 2026-12-30
UG-11-S06-A060 | AW.PIPE.F6.UG-11.UG-11-S06 | F6 | UG-11 | UG-11-S06 | A060 | Excavate and strut to formation | 1210.8238 | m3 | 5 | 6 | UG-11-S06-A050 | 10 | 2 |  | 2026-12-29 | 2027-01-04 | 2027-01-04 | UG-11A-S05-A060
UG-11-S06-A070 | AW.PIPE.F6.UG-11.UG-11-S06 | F6 | UG-11 | UG-11-S06 | A070 | Trim piles, blinding and piled slab (incl. cure) | 43.2042 | m | 7 | 9 | UG-11-S06-A060 | 2 | 2 |  | 2027-01-02 | 2027-01-11 | 2027-01-11 | UG-11A-S05-A070
UG-11-S06-A080 | AW.PIPE.F6.UG-11.UG-11-S06 | F6 | UG-11 | UG-11-S06 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 43.2042 | m | 3 | 4 | UG-11-S06-A070 | 3 | 2 |  | 2027-01-05 | 2027-01-13 | 2027-01-13 | UG-11A-S05-A080
UG-11-S06-A090 | AW.PIPE.F6.UG-11.UG-11-S06 | F6 | UG-11 | UG-11-S06 | A090 | Surround, joint test and line test | 43.2042 | m | 3 | 4 | UG-11-S06-A080 | 2 | 2 |  | 2027-01-07 | 2027-01-15
UG-11-S06-A100 | AW.PIPE.F6.UG-11.UG-11-S06 | F6 | UG-11 | UG-11-S06 | A100 | Backfill to NG and remove struts | 999.9549 | m3 | 3 | 4 | UG-11-S06-A090 | 2 | 2 |  | 2027-01-09 | 2027-01-17 | 2027-01-17 | UG-11A-S05-A100
UG-11-S06-A110 | AW.PIPE.F6.UG-11.UG-11-S06 | F6 | UG-11 | UG-11-S06 | A110 | Dewatering off, extract sheets, reinstate | 86.4084 | m wall | 3 | 4 | UG-11-S06-A100 | 2 | 2 |  | 2027-01-11 | 2027-01-19
UG-11-S05-A010 | AW.PIPE.F6.UG-11.UG-11-S05 | F6 | UG-11 | UG-11-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11-S05-A020 | AW.PIPE.F6.UG-11.UG-11-S05 | F6 | UG-11 | UG-11-S05 | A020 | Set-out, crossing survey and working platform | 41.3 | m | 1 | 2 | UG-11-S05-A010 |  |  | FS from A010; UG-11-S06-A030 (SS, set-out one package ahead of piling) | 2026-12-14 | 2026-12-16
UG-11-S05-A030 | AW.PIPE.F6.UG-11.UG-11-S05 | F6 | UG-11 | UG-11-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 30 | piles | 6 | 7 | UG-11-S05-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-23 | 2026-12-30 | 2026-12-30 | UG-11-S06-A030
UG-11-S05-A040 | AW.PIPE.F6.UG-11.UG-11-S05 | F6 | UG-11 | UG-11-S05 | A040 | Install sheet piles (shored lengths) | 82.6 | m wall | 4 | 5 | UG-11-S05-A030 | 3 | 2 |  | 2026-12-26 | 2027-01-01 | 2027-01-01 | UG-11-S06-A040
UG-11-S05-A050 | AW.PIPE.F6.UG-11.UG-11-S05 | F6 | UG-11 | UG-11-S05 | A050 | Install dewatering and draw down | 41.3 | m | 9 | 11 | UG-11-S05-A040 | 2 | 2 | UG-11-S06-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2026-12-28 | 2027-01-08
UG-11-S05-A060 | AW.PIPE.F6.UG-11.UG-11-S05 | F6 | UG-11 | UG-11-S05 | A060 | Excavate and strut to formation | 1102.9987 | m3 | 5 | 6 | UG-11-S05-A050 | 10 | 2 |  | 2027-01-07 | 2027-01-13 | 2027-01-13 | UG-11-S06-A060
UG-11-S05-A070 | AW.PIPE.F6.UG-11.UG-11-S05 | F6 | UG-11 | UG-11-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 41.3 | m | 7 | 9 | UG-11-S05-A060 | 2 | 2 |  | 2027-01-11 | 2027-01-20 | 2027-01-20 | UG-11-S06-A070
UG-11-S05-A080 | AW.PIPE.F6.UG-11.UG-11-S05 | F6 | UG-11 | UG-11-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 41.3 | m | 5 | 6 | UG-11-S05-A070 | 3 | 2 |  | 2027-01-14 | 2027-01-22 | 2027-01-22 | UG-11-S06-A080
UG-11-S05-A090 | AW.PIPE.F6.UG-11.UG-11-S05 | F6 | UG-11 | UG-11-S05 | A090 | Surround, joint test and line test | 41.3 | m | 3 | 4 | UG-11-S05-A080 | 2 | 2 |  | 2027-01-16 | 2027-01-24
UG-11-S05-A100 | AW.PIPE.F6.UG-11.UG-11-S05 | F6 | UG-11 | UG-11-S05 | A100 | Backfill to NG and remove struts | 919.6851 | m3 | 3 | 4 | UG-11-S05-A090 | 2 | 2 |  | 2027-01-18 | 2027-01-26 | 2027-01-26 | UG-11-S06-A100
UG-11-S05-A110 | AW.PIPE.F6.UG-11.UG-11-S05 | F6 | UG-11 | UG-11-S05 | A110 | Dewatering off, extract sheets, reinstate | 82.6 | m wall | 3 | 4 | UG-11-S05-A100 | 2 | 2 |  | 2027-01-20 | 2027-01-28
UG-11-S04-A010 | AW.PIPE.F6.UG-11.UG-11-S04 | F6 | UG-11 | UG-11-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11-S04-A020 | AW.PIPE.F6.UG-11.UG-11-S04 | F6 | UG-11 | UG-11-S04 | A020 | Set-out, crossing survey and working platform | 18.1 | m | 1 | 2 | UG-11-S04-A010 |  |  | FS from A010; UG-11-S05-A030 (SS, set-out one package ahead of piling) | 2026-12-23 | 2026-12-25
UG-11-S04-A030 | AW.PIPE.F6.UG-11.UG-11-S04 | F6 | UG-11 | UG-11-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 16 | piles | 4 | 5 | UG-11-S04-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-30 | 2027-01-04 | 2027-01-04 | UG-11-S05-A030
UG-11-S04-A040 | AW.PIPE.F6.UG-11.UG-11-S04 | F6 | UG-11 | UG-11-S04 | A040 | Install sheet piles (shored lengths) | 36.2 | m wall | 2 | 3 | UG-11-S04-A030 | 2 | 2 |  | 2027-01-01 | 2027-01-06 | 2027-01-06 | UG-11-S05-A040
UG-11-S04-A050 | AW.PIPE.F6.UG-11.UG-11-S04 | F6 | UG-11 | UG-11-S04 | A050 | Install dewatering and draw down | 18.1 | m | 8 | 10 | UG-11-S04-A040 | 1 | 2 | UG-11-S05-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-03 | 2027-01-13
UG-11-S04-A060 | AW.PIPE.F6.UG-11.UG-11-S04 | F6 | UG-11 | UG-11-S04 | A060 | Excavate and strut to formation | 506.8789 | m3 | 3 | 4 | UG-11-S04-A050 | 10 | 2 |  | 2027-01-13 | 2027-01-17 | 2027-01-17 | UG-11-S05-A060
UG-11-S04-A070 | AW.PIPE.F6.UG-11.UG-11-S04 | F6 | UG-11 | UG-11-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 18.1 | m | 5 | 6 | UG-11-S04-A060 | 2 | 2 |  | 2027-01-20 | 2027-01-26 | 2027-01-26 | UG-11-S05-A070
UG-11-S04-A080 | AW.PIPE.F6.UG-11.UG-11-S04 | F6 | UG-11 | UG-11-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 18.1 | m | 1 | 2 | UG-11-S04-A070 | 2 | 2 |  | 2027-01-22 | 2027-01-28 | 2027-01-28 | UG-11-S05-A080
UG-11-S04-A090 | AW.PIPE.F6.UG-11.UG-11-S04 | F6 | UG-11 | UG-11-S04 | A090 | Surround, joint test and line test | 18.1 | m | 3 | 4 | UG-11-S04-A080 | 1 | 2 |  | 2027-01-23 | 2027-01-30
UG-11-S04-A100 | AW.PIPE.F6.UG-11.UG-11-S04 | F6 | UG-11 | UG-11-S04 | A100 | Backfill to NG and remove struts | 418.2097 | m3 | 2 | 3 | UG-11-S04-A090 | 2 | 2 |  | 2027-01-26 | 2027-02-01 | 2027-02-01 | UG-11-S05-A100
UG-11-S04-A110 | AW.PIPE.F6.UG-11.UG-11-S04 | F6 | UG-11 | UG-11-S04 | A110 | Dewatering off, extract sheets, reinstate | 36.2 | m wall | 2 | 3 | UG-11-S04-A100 | 1 | 2 |  | 2027-01-27 | 2027-02-03
UG-11-S03-A010 | AW.PIPE.F6.UG-11.UG-11-S03 | F6 | UG-11 | UG-11-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11-S03-A020 | AW.PIPE.F6.UG-11.UG-11-S03 | F6 | UG-11 | UG-11-S03 | A020 | Set-out, crossing survey and working platform | 23.1 | m | 1 | 2 | UG-11-S03-A010 |  |  | FS from A010; UG-11-S04-A030 (SS, set-out one package ahead of piling) | 2026-12-30 | 2027-01-01
UG-11-S03-A030 | AW.PIPE.F6.UG-11.UG-11-S03 | F6 | UG-11 | UG-11-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 18 | piles | 4 | 5 | UG-11-S03-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-04 | 2027-01-09 | 2027-01-09 | UG-11-S04-A030
UG-11-S03-A040 | AW.PIPE.F6.UG-11.UG-11-S03 | F6 | UG-11 | UG-11-S03 | A040 | Install sheet piles (shored lengths) | 46.2 | m wall | 2 | 3 | UG-11-S03-A030 | 2 | 2 |  | 2027-01-06 | 2027-01-11 | 2027-01-11 | UG-11-S04-A040
UG-11-S03-A050 | AW.PIPE.F6.UG-11.UG-11-S03 | F6 | UG-11 | UG-11-S03 | A050 | Install dewatering and draw down | 23.1 | m | 8 | 10 | UG-11-S03-A040 | 1 | 2 | UG-11-S04-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-07 | 2027-01-17
UG-11-S03-A060 | AW.PIPE.F6.UG-11.UG-11-S03 | F6 | UG-11 | UG-11-S03 | A060 | Excavate and strut to formation | 646.4328 | m3 | 3 | 4 | UG-11-S03-A050 | 10 | 2 |  | 2027-01-17 | 2027-01-21 | 2027-01-21 | UG-11-S04-A060
UG-11-S03-A070 | AW.PIPE.F6.UG-11.UG-11-S03 | F6 | UG-11 | UG-11-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 23.1 | m | 5 | 6 | UG-11-S03-A060 | 2 | 2 |  | 2027-01-26 | 2027-02-01 | 2027-02-01 | UG-11-S04-A070
UG-11-S03-A080 | AW.PIPE.F6.UG-11.UG-11-S03 | F6 | UG-11 | UG-11-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 23.1 | m | 2 | 3 | UG-11-S03-A070 | 2 | 2 |  | 2027-01-28 | 2027-02-03 | 2027-02-03 | UG-11-S04-A080
UG-11-S03-A090 | AW.PIPE.F6.UG-11.UG-11-S03 | F6 | UG-11 | UG-11-S03 | A090 | Surround, joint test and line test | 23.1 | m | 3 | 4 | UG-11-S03-A080 | 1 | 2 |  | 2027-01-29 | 2027-02-05
UG-11-S03-A100 | AW.PIPE.F6.UG-11.UG-11-S03 | F6 | UG-11 | UG-11-S03 | A100 | Backfill to NG and remove struts | 533.2694 | m3 | 2 | 3 | UG-11-S03-A090 | 2 | 2 |  | 2027-02-01 | 2027-02-07 | 2027-02-07 | UG-11-S04-A100
UG-11-S03-A110 | AW.PIPE.F6.UG-11.UG-11-S03 | F6 | UG-11 | UG-11-S03 | A110 | Dewatering off, extract sheets, reinstate | 46.2 | m wall | 2 | 3 | UG-11-S03-A100 | 1 | 2 |  | 2027-02-02 | 2027-02-09
UG-23-S09-A010 | AW.PIPE.F6.UG-23.UG-23-S09 | F6 | UG-23 | UG-23-S09 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-23-S09-A020 | AW.PIPE.F6.UG-23.UG-23-S09 | F6 | UG-23 | UG-23-S09 | A020 | Set-out, crossing survey and working platform | 90.079 | m | 2 | 3 | UG-23-S09-A010 |  |  | FS from A010; UG-11-S03-A030 (SS, set-out one package ahead of piling) | 2027-01-04 | 2027-01-07
UG-23-S09-A030 | AW.PIPE.F6.UG-23.UG-23-S09 | F6 | UG-23 | UG-23-S09 | A030 | Pipe-support piling from platform (incl. integrity tests) | 32 | piles | 7 | 9 | UG-23-S09-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-09 | 2027-01-18 | 2027-01-18 | UG-11-S03-A030
UG-23-S09-A040 | AW.PIPE.F6.UG-23.UG-23-S09 | F6 | UG-23 | UG-23-S09 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-23-S09-A030 | 3 | 0 |  | 2027-01-12 | 2027-01-18 | 2027-01-11 | UG-11-S03-A040
UG-23-S09-A050 | AW.PIPE.F6.UG-23.UG-23-S09 | F6 | UG-23 | UG-23-S09 | A050 | Install dewatering and draw down | 90.079 | m | 10 | 12 | UG-23-S09-A040 | 0 | 2 | UG-11-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-12 | 2027-01-24
UG-23-S09-A060 | AW.PIPE.F6.UG-23.UG-23-S09 | F6 | UG-23 | UG-23-S09 | A060 | Excavate and strut to formation | 559.1569 | m3 | 2 | 3 | UG-23-S09-A050 | 10 | 2 |  | 2027-01-22 | 2027-01-26 | 2027-01-26 | UG-11-S03-A060
UG-23-S09-A070 | AW.PIPE.F6.UG-23.UG-23-S09 | F6 | UG-23 | UG-23-S09 | A070 | Trim piles, blinding and piled slab (incl. cure) | 90.079 | m | 11 | 13 | UG-23-S09-A060 | 1 | 2 |  | 2027-02-01 | 2027-02-14 | 2027-02-14 | UG-11-S03-A070
UG-23-S09-A080 | AW.PIPE.F6.UG-23.UG-23-S09 | F6 | UG-23 | UG-23-S09 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 90.079 | m | 4 | 5 | UG-23-S09-A070 | 4 | 2 |  | 2027-02-05 | 2027-02-16 | 2027-02-16 | UG-11-S03-A080
UG-23-S09-A090 | AW.PIPE.F6.UG-23.UG-23-S09 | F6 | UG-23 | UG-23-S09 | A090 | Surround, joint test and line test | 90.079 | m | 3 | 4 | UG-23-S09-A080 | 2 | 2 |  | 2027-02-07 | 2027-02-18
UG-23-S09-A100 | AW.PIPE.F6.UG-23.UG-23-S09 | F6 | UG-23 | UG-23-S09 | A100 | Backfill to NG and remove struts | 457.6625 | m3 | 2 | 3 | UG-23-S09-A090 | 2 | 2 |  | 2027-02-09 | 2027-02-20 | 2027-02-20 | UG-11-S03-A100
UG-23-S09-A110 | AW.PIPE.F6.UG-23.UG-23-S09 | F6 | UG-23 | UG-23-S09 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-23-S09-A100 | 1 | 2 |  | 2027-02-10 | 2027-02-22
UG-23-S10-A010 | AW.PIPE.F6.UG-23.UG-23-S10 | F6 | UG-23 | UG-23-S10 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-23-S10-A020 | AW.PIPE.F6.UG-23.UG-23-S10 | F6 | UG-23 | UG-23-S10 | A020 | Set-out, crossing survey and working platform | 5.9999 | m | 1 | 2 | UG-23-S10-A010 |  |  | FS from A010; UG-23-S09-A030 (SS, tie-in team follows the adjacent run) | 2027-01-09 | 2027-01-11
UG-23-S10-A030 | AW.PIPE.F6.UG-23.UG-23-S10 | F6 | UG-23 | UG-23-S10 | A030 | Pipe-support piling from platform (incl. integrity tests) | 3 | piles | 1 | 2 | UG-23-S10-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-10 | 2027-01-13 | 2027-01-13
UG-23-S10-A040 | AW.PIPE.F6.UG-23.UG-23-S10 | F6 | UG-23 | UG-23-S10 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-23-S10-A030 | 1 | 0 |  | 2027-01-11 | 2027-01-13 | 0
UG-23-S10-A050 | AW.PIPE.F6.UG-23.UG-23-S10 | F6 | UG-23 | UG-23-S10 | A050 | Install dewatering and draw down | 5.9999 | m | 8 | 10 | UG-23-S10-A040 | 0 | 2 |  | 2027-01-11 | 2027-01-21
UG-23-S10-A060 | AW.PIPE.F6.UG-23.UG-23-S10 | F6 | UG-23 | UG-23-S10 | A060 | Excavate and strut to formation | 37.2442 | m3 | 1 | 2 | UG-23-S10-A050 | 10 | 2 |  | 2027-01-21 | 2027-01-23 | 2027-01-23
UG-23-S10-A070 | AW.PIPE.F6.UG-23.UG-23-S10 | F6 | UG-23 | UG-23-S10 | A070 | Trim piles, blinding and piled slab (incl. cure) | 5.9999 | m | 4 | 5 | UG-23-S10-A060 | 1 | 2 |  | 2027-01-22 | 2027-01-27 | 2027-01-27
UG-23-S10-A080 | AW.PIPE.F6.UG-23.UG-23-S10 | F6 | UG-23 | UG-23-S10 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 5.9999 | m | 4 | 5 | UG-23-S10-A070 | 2 | 2 | UG-23-S09-A080 (FS, closure) | 2027-02-16 | 2027-02-21 | 2027-02-21
UG-23-S10-A090 | AW.PIPE.F6.UG-23.UG-23-S10 | F6 | UG-23 | UG-23-S10 | A090 | Surround, joint test and line test | 5.9999 | m | 3 | 4 | UG-23-S10-A080 | 2 | 2 |  | 2027-02-18 | 2027-02-23
UG-23-S10-A100 | AW.PIPE.F6.UG-23.UG-23-S10 | F6 | UG-23 | UG-23-S10 | A100 | Backfill to NG and remove struts | 30.4839 | m3 | 1 | 2 | UG-23-S10-A090 | 2 | 2 |  | 2027-02-20 | 2027-02-25 | 2027-02-25
UG-23-S10-A110 | AW.PIPE.F6.UG-23.UG-23-S10 | F6 | UG-23 | UG-23-S10 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-23-S10-A100 | 1 | 2 |  | 2027-02-21 | 2027-02-27
UG-23-S08-A010 | AW.PIPE.F6.UG-23.UG-23-S08 | F6 | UG-23 | UG-23-S08 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-23-S08-A020 | AW.PIPE.F6.UG-23.UG-23-S08 | F6 | UG-23 | UG-23-S08 | A020 | Set-out, crossing survey and working platform | 46 | m | 1 | 2 | UG-23-S08-A010 |  |  | FS from A010; UG-23-S09-A030 (SS, set-out one package ahead of piling) | 2027-01-09 | 2027-01-11
UG-23-S08-A030 | AW.PIPE.F6.UG-23.UG-23-S08 | F6 | UG-23 | UG-23-S08 | A030 | Pipe-support piling from platform (incl. integrity tests) | 17 | piles | 4 | 5 | UG-23-S08-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-18 | 2027-01-23 | 2027-01-23 | UG-23-S09-A030
UG-23-S08-A040 | AW.PIPE.F6.UG-23.UG-23-S08 | F6 | UG-23 | UG-23-S08 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-23-S08-A030 | 2 | 0 |  | 2027-01-20 | 2027-01-23 | 2027-01-11 | UG-23-S09-A040
UG-23-S08-A050 | AW.PIPE.F6.UG-23.UG-23-S08 | F6 | UG-23 | UG-23-S08 | A050 | Install dewatering and draw down | 46 | m | 9 | 11 | UG-23-S08-A040 | 0 | 2 | UG-23-S09-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-20 | 2027-01-31
UG-23-S08-A060 | AW.PIPE.F6.UG-23.UG-23-S08 | F6 | UG-23 | UG-23-S08 | A060 | Excavate and strut to formation | 285.5391 | m3 | 1 | 2 | UG-23-S08-A050 | 10 | 2 | UG-11-S01-A100 (FS, deeper first); UG-11-S02-A100 (FS, deeper first); UG-11B-S14-A100 (FS, deeper first) | 2027-03-10 | 2027-03-12 | 2027-03-12 | UG-23-S09-A060
UG-23-S08-A070 | AW.PIPE.F6.UG-23.UG-23-S08 | F6 | UG-23 | UG-23-S08 | A070 | Trim piles, blinding and piled slab (incl. cure) | 46 | m | 7 | 9 | UG-23-S08-A060 | 1 | 2 |  | 2027-03-11 | 2027-03-20 | 2027-03-20 | UG-23-S09-A070
UG-23-S08-A080 | AW.PIPE.F6.UG-23.UG-23-S08 | F6 | UG-23 | UG-23-S08 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 46 | m | 2 | 3 | UG-23-S08-A070 | 3 | 2 |  | 2027-03-14 | 2027-03-22 | 2027-03-22 | UG-23-S09-A080
UG-23-S08-A090 | AW.PIPE.F6.UG-23.UG-23-S08 | F6 | UG-23 | UG-23-S08 | A090 | Surround, joint test and line test | 46 | m | 3 | 4 | UG-23-S08-A080 | 1 | 2 |  | 2027-03-15 | 2027-03-24
UG-23-S08-A100 | AW.PIPE.F6.UG-23.UG-23-S08 | F6 | UG-23 | UG-23-S08 | A100 | Backfill to NG and remove struts | 233.7101 | m3 | 1 | 2 | UG-23-S08-A090 | 2 | 2 |  | 2027-03-17 | 2027-03-26 | 2027-03-26 | UG-23-S09-A100
UG-23-S08-A110 | AW.PIPE.F6.UG-23.UG-23-S08 | F6 | UG-23 | UG-23-S08 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-23-S08-A100 | 1 | 2 |  | 2027-03-18 | 2027-03-28
UG-23-S07-A010 | AW.PIPE.F6.UG-23.UG-23-S07 | F6 | UG-23 | UG-23-S07 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-23-S07-A020 | AW.PIPE.F6.UG-23.UG-23-S07 | F6 | UG-23 | UG-23-S07 | A020 | Set-out, crossing survey and working platform | 16 | m | 1 | 2 | UG-23-S07-A010 |  |  | FS from A010; UG-23-S08-A030 (SS, set-out one package ahead of piling) | 2027-01-18 | 2027-01-20
UG-23-S07-A030 | AW.PIPE.F6.UG-23.UG-23-S07 | F6 | UG-23 | UG-23-S07 | A030 | Pipe-support piling from platform (incl. integrity tests) | 7 | piles | 2 | 3 | UG-23-S07-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-23 | 2027-01-26 | 2027-01-26 | UG-23-S08-A030
UG-23-S07-A040 | AW.PIPE.F6.UG-23.UG-23-S07 | F6 | UG-23 | UG-23-S07 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-23-S07-A030 | 1 | 0 |  | 2027-01-24 | 2027-01-26 | 2027-01-11 | UG-23-S08-A040
UG-23-S07-A050 | AW.PIPE.F6.UG-23.UG-23-S07 | F6 | UG-23 | UG-23-S07 | A050 | Install dewatering and draw down | 16 | m | 8 | 10 | UG-23-S07-A040 | 0 | 2 | UG-23-S08-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-02 | 2027-03-12
UG-23-S07-A060 | AW.PIPE.F6.UG-23.UG-23-S07 | F6 | UG-23 | UG-23-S07 | A060 | Excavate and strut to formation | 99.3179 | m3 | 1 | 2 | UG-23-S07-A050 | 10 | 2 | UG-07-S03-A100 (FS, deeper first); UG-11-S01-A100 (FS, deeper first); UG-11-S06-A100 (FS, deeper first); UG-12-S07-A100 (FS, deeper first) | 2027-03-12 | 2027-03-14 | 2027-03-14 | UG-23-S08-A060
UG-23-S07-A070 | AW.PIPE.F6.UG-23.UG-23-S07 | F6 | UG-23 | UG-23-S07 | A070 | Trim piles, blinding and piled slab (incl. cure) | 16 | m | 5 | 6 | UG-23-S07-A060 | 1 | 2 |  | 2027-03-20 | 2027-03-26 | 2027-03-26 | UG-23-S08-A070
UG-23-S07-A080 | AW.PIPE.F6.UG-23.UG-23-S07 | F6 | UG-23 | UG-23-S07 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 16 | m | 1 | 2 | UG-23-S07-A070 | 2 | 2 |  | 2027-03-22 | 2027-03-28 | 2027-03-28 | UG-23-S08-A080
UG-23-S07-A090 | AW.PIPE.F6.UG-23.UG-23-S07 | F6 | UG-23 | UG-23-S07 | A090 | Surround, joint test and line test | 16 | m | 3 | 4 | UG-23-S07-A080 | 1 | 2 |  | 2027-03-23 | 2027-03-30
UG-23-S07-A100 | AW.PIPE.F6.UG-23.UG-23-S07 | F6 | UG-23 | UG-23-S07 | A100 | Backfill to NG and remove struts | 81.2905 | m3 | 1 | 2 | UG-23-S07-A090 | 2 | 2 |  | 2027-03-26 | 2027-04-01 | 2027-04-01 | UG-23-S08-A100
UG-23-S07-A110 | AW.PIPE.F6.UG-23.UG-23-S07 | F6 | UG-23 | UG-23-S07 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-23-S07-A100 | 1 | 2 |  | 2027-03-27 | 2027-04-03
UG-23-S06-A010 | AW.PIPE.F6.UG-23.UG-23-S06 | F6 | UG-23 | UG-23-S06 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-23-S06-A020 | AW.PIPE.F6.UG-23.UG-23-S06 | F6 | UG-23 | UG-23-S06 | A020 | Set-out, crossing survey and working platform | 45.3875 | m | 1 | 2 | UG-23-S06-A010 |  |  | FS from A010; UG-23-S07-A030 (SS, set-out one package ahead of piling) | 2027-01-23 | 2027-01-25
UG-23-S06-A030 | AW.PIPE.F6.UG-23.UG-23-S06 | F6 | UG-23 | UG-23-S06 | A030 | Pipe-support piling from platform (incl. integrity tests) | 17 | piles | 4 | 5 | UG-23-S06-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-26 | 2027-01-31 | 2027-01-31 | UG-23-S07-A030
UG-23-S06-A040 | AW.PIPE.F6.UG-23.UG-23-S06 | F6 | UG-23 | UG-23-S06 | A040 | Install sheet piles (shored lengths) | 27.9781 | m wall | 2 | 3 | UG-23-S06-A030 | 2 | 2 |  | 2027-01-28 | 2027-02-02 | 2027-02-02 | UG-23-S07-A040
UG-23-S06-A050 | AW.PIPE.F6.UG-23.UG-23-S06 | F6 | UG-23 | UG-23-S06 | A050 | Install dewatering and draw down | 45.3875 | m | 9 | 11 | UG-23-S06-A040 | 1 | 2 | UG-23-S07-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-03 | 2027-03-14
UG-23-S06-A060 | AW.PIPE.F6.UG-23.UG-23-S06 | F6 | UG-23 | UG-23-S06 | A060 | Excavate and strut to formation | 247.4014 | m3 | 1 | 2 | UG-23-S06-A050 | 10 | 2 | UG-07-S03-A100 (FS, deeper first); UG-11-S05-A100 (FS, deeper first); UG-11-S06-A100 (FS, deeper first); UG-12-S07-A100 (FS, deeper first) | 2027-03-14 | 2027-03-16 | 2027-03-16 | UG-23-S07-A060
UG-23-S06-A070 | AW.PIPE.F6.UG-23.UG-23-S06 | F6 | UG-23 | UG-23-S06 | A070 | Trim piles, blinding and piled slab (incl. cure) | 45.3875 | m | 7 | 9 | UG-23-S06-A060 | 1 | 2 |  | 2027-03-26 | 2027-04-04 | 2027-04-04 | UG-23-S07-A070
UG-23-S06-A080 | AW.PIPE.F6.UG-23.UG-23-S06 | F6 | UG-23 | UG-23-S06 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 45.3875 | m | 6 | 7 | UG-23-S06-A070 | 3 | 2 |  | 2027-03-29 | 2027-04-06 | 2027-04-06 | UG-23-S07-A080
UG-23-S06-A090 | AW.PIPE.F6.UG-23.UG-23-S06 | F6 | UG-23 | UG-23-S06 | A090 | Surround, joint test and line test | 45.3875 | m | 3 | 4 | UG-23-S06-A080 | 3 | 2 |  | 2027-04-01 | 2027-04-08
UG-23-S06-A100 | AW.PIPE.F6.UG-23.UG-23-S06 | F6 | UG-23 | UG-23-S06 | A100 | Backfill to NG and remove struts | 196.2625 | m3 | 1 | 2 | UG-23-S06-A090 | 2 | 2 |  | 2027-04-03 | 2027-04-10 | 2027-04-10 | UG-23-S07-A100
UG-23-S06-A110 | AW.PIPE.F6.UG-23.UG-23-S06 | F6 | UG-23 | UG-23-S06 | A110 | Dewatering off, extract sheets, reinstate | 27.9781 | m wall | 2 | 3 | UG-23-S06-A100 | 1 | 2 |  | 2027-04-04 | 2027-04-12
UG-23-S05-A010 | AW.PIPE.F6.UG-23.UG-23-S05 | F6 | UG-23 | UG-23-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-23-S05-A020 | AW.PIPE.F6.UG-23.UG-23-S05 | F6 | UG-23 | UG-23-S05 | A020 | Set-out, crossing survey and working platform | 32.6262 | m | 1 | 2 | UG-23-S05-A010 |  |  | FS from A010; UG-23-S06-A030 (SS, set-out one package ahead of piling) | 2027-01-26 | 2027-01-28
UG-23-S05-A030 | AW.PIPE.F6.UG-23.UG-23-S05 | F6 | UG-23 | UG-23-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 12 | piles | 3 | 4 | UG-23-S05-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-31 | 2027-02-04 | 2027-02-04 | UG-23-S06-A030
UG-23-S05-A040 | AW.PIPE.F6.UG-23.UG-23-S05 | F6 | UG-23 | UG-23-S05 | A040 | Install sheet piles (shored lengths) | 65.111 | m wall | 3 | 4 | UG-23-S05-A030 | 2 | 2 |  | 2027-02-02 | 2027-02-06 | 2027-02-06 | UG-23-S06-A040
UG-23-S05-A050 | AW.PIPE.F6.UG-23.UG-23-S05 | F6 | UG-23 | UG-23-S05 | A050 | Install dewatering and draw down | 32.6262 | m | 8 | 10 | UG-23-S05-A040 | 2 | 2 | UG-23-S06-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-06 | 2027-03-16
UG-23-S05-A060 | AW.PIPE.F6.UG-23.UG-23-S05 | F6 | UG-23 | UG-23-S05 | A060 | Excavate and strut to formation | 366.8157 | m3 | 2 | 3 | UG-23-S05-A050 | 10 | 2 |  | 2027-03-16 | 2027-03-19 | 2027-03-19 | UG-23-S06-A060
UG-23-S05-A070 | AW.PIPE.F6.UG-23.UG-23-S05 | F6 | UG-23 | UG-23-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 32.6262 | m | 6 | 7 | UG-23-S05-A060 | 1 | 2 |  | 2027-04-04 | 2027-04-11 | 2027-04-11 | UG-23-S06-A070
UG-23-S05-A080 | AW.PIPE.F6.UG-23.UG-23-S05 | F6 | UG-23 | UG-23-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 32.6262 | m | 4 | 5 | UG-23-S05-A070 | 3 | 2 |  | 2027-04-07 | 2027-04-13 | 2027-04-13 | UG-23-S06-A080
UG-23-S05-A090 | AW.PIPE.F6.UG-23.UG-23-S05 | F6 | UG-23 | UG-23-S05 | A090 | Surround, joint test and line test | 32.6262 | m | 3 | 4 | UG-23-S05-A080 | 2 | 2 |  | 2027-04-09 | 2027-04-15
UG-23-S05-A100 | AW.PIPE.F6.UG-23.UG-23-S05 | F6 | UG-23 | UG-23-S05 | A100 | Backfill to NG and remove struts | 330.0701 | m3 | 1 | 2 | UG-23-S05-A090 | 2 | 2 |  | 2027-04-11 | 2027-04-17 | 2027-04-17 | UG-23-S06-A100
UG-23-S05-A110 | AW.PIPE.F6.UG-23.UG-23-S05 | F6 | UG-23 | UG-23-S05 | A110 | Dewatering off, extract sheets, reinstate | 65.111 | m wall | 3 | 4 | UG-23-S05-A100 | 1 | 2 |  | 2027-04-12 | 2027-04-19
UG-23-S04-A010 | AW.PIPE.F6.UG-23.UG-23-S04 | F6 | UG-23 | UG-23-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-23-S04-A020 | AW.PIPE.F6.UG-23.UG-23-S04 | F6 | UG-23 | UG-23-S04 | A020 | Set-out, crossing survey and working platform | 23 | m | 1 | 2 | UG-23-S04-A010 |  |  | FS from A010; UG-23-S05-A030 (SS, set-out one package ahead of piling) | 2027-01-31 | 2027-02-02
UG-23-S04-A030 | AW.PIPE.F6.UG-23.UG-23-S04 | F6 | UG-23 | UG-23-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 9 | piles | 2 | 3 | UG-23-S04-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-04 | 2027-02-07 | 2027-02-07 | UG-23-S05-A030
UG-23-S04-A040 | AW.PIPE.F6.UG-23.UG-23-S04 | F6 | UG-23 | UG-23-S04 | A040 | Install sheet piles (shored lengths) | 46 | m wall | 2 | 3 | UG-23-S04-A030 | 1 | 2 |  | 2027-02-06 | 2027-02-09 | 2027-02-09 | UG-23-S05-A040
UG-23-S04-A050 | AW.PIPE.F6.UG-23.UG-23-S04 | F6 | UG-23 | UG-23-S04 | A050 | Install dewatering and draw down | 23 | m | 8 | 10 | UG-23-S04-A040 | 1 | 2 | UG-23-S05-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-09 | 2027-03-19
UG-23-S04-A060 | AW.PIPE.F6.UG-23.UG-23-S04 | F6 | UG-23 | UG-23-S04 | A060 | Excavate and strut to formation | 264.6436 | m3 | 2 | 3 | UG-23-S04-A050 | 10 | 2 | UG-11-S04-A100 (FS, deeper first); UG-11-S05-A100 (FS, deeper first) | 2027-03-19 | 2027-03-22 | 2027-03-22 | UG-23-S05-A060
UG-23-S04-A070 | AW.PIPE.F6.UG-23.UG-23-S04 | F6 | UG-23 | UG-23-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 23 | m | 5 | 6 | UG-23-S04-A060 | 1 | 2 |  | 2027-04-11 | 2027-04-17 | 2027-04-17 | UG-23-S05-A070
UG-23-S04-A080 | AW.PIPE.F6.UG-23.UG-23-S04 | F6 | UG-23 | UG-23-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 23 | m | 1 | 2 | UG-23-S04-A070 | 2 | 2 |  | 2027-04-13 | 2027-04-19 | 2027-04-19 | UG-23-S05-A080
UG-23-S04-A090 | AW.PIPE.F6.UG-23.UG-23-S04 | F6 | UG-23 | UG-23-S04 | A090 | Surround, joint test and line test | 23 | m | 3 | 4 | UG-23-S04-A080 | 1 | 2 |  | 2027-04-14 | 2027-04-21
UG-23-S04-A100 | AW.PIPE.F6.UG-23.UG-23-S04 | F6 | UG-23 | UG-23-S04 | A100 | Backfill to NG and remove struts | 238.7289 | m3 | 1 | 2 | UG-23-S04-A090 | 2 | 2 |  | 2027-04-17 | 2027-04-23 | 2027-04-23 | UG-23-S05-A100
UG-23-S04-A110 | AW.PIPE.F6.UG-23.UG-23-S04 | F6 | UG-23 | UG-23-S04 | A110 | Dewatering off, extract sheets, reinstate | 46 | m wall | 2 | 3 | UG-23-S04-A100 | 1 | 2 |  | 2027-04-18 | 2027-04-25
UG-11B-S07-A010 | AW.PIPE.F6.UG-11B.UG-11B-S07 | F6 | UG-11B | UG-11B-S07 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11B-S07-A020 | AW.PIPE.F6.UG-11B.UG-11B-S07 | F6 | UG-11B | UG-11B-S07 | A020 | Set-out, crossing survey and working platform | 79.9312 | m | 1 | 2 | UG-11B-S07-A010 |  |  | FS from A010; UG-23-S04-A030 (SS, set-out one package ahead of piling) | 2027-02-04 | 2027-02-06
UG-11B-S07-A030 | AW.PIPE.F6.UG-11B.UG-11B-S07 | F6 | UG-11B | UG-11B-S07 | A030 | Pipe-support piling from platform (incl. integrity tests) | 56 | piles | 12 | 14 | UG-11B-S07-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-07 | 2027-02-21 | 2027-02-21 | UG-23-S04-A030
UG-11B-S07-A040 | AW.PIPE.F6.UG-11B.UG-11B-S07 | F6 | UG-11B | UG-11B-S07 | A040 | Install sheet piles (shored lengths) | 159.8625 | m wall | 7 | 9 | UG-11B-S07-A030 | 5 | 2 |  | 2027-02-12 | 2027-02-23 | 2027-02-23 | UG-23-S04-A040
UG-11B-S07-A050 | AW.PIPE.F6.UG-11B.UG-11B-S07 | F6 | UG-11B | UG-11B-S07 | A050 | Install dewatering and draw down | 79.9312 | m | 9 | 11 | UG-11B-S07-A040 | 3 | 2 | UG-23-S04-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-11 | 2027-03-22
UG-11B-S07-A060 | AW.PIPE.F6.UG-11B.UG-11B-S07 | F6 | UG-11B | UG-11B-S07 | A060 | Excavate and strut to formation | 843.449 | m3 | 4 | 5 | UG-11B-S07-A050 | 10 | 2 |  | 2027-03-22 | 2027-03-27 | 2027-03-27 | UG-23-S04-A060
UG-11B-S07-A070 | AW.PIPE.F6.UG-11B.UG-11B-S07 | F6 | UG-11B | UG-11B-S07 | A070 | Trim piles, blinding and piled slab (incl. cure) | 79.9312 | m | 10 | 12 | UG-11B-S07-A060 | 2 | 2 |  | 2027-04-17 | 2027-04-29 | 2027-04-29 | UG-23-S04-A070
UG-11B-S07-A080 | AW.PIPE.F6.UG-11B.UG-11B-S07 | F6 | UG-11B | UG-11B-S07 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 79.9312 | m | 8 | 10 | UG-11B-S07-A070 | 4 | 2 |  | 2027-04-21 | 2027-05-01 | 2027-05-01 | UG-23-S04-A080
UG-11B-S07-A090 | AW.PIPE.F6.UG-11B.UG-11B-S07 | F6 | UG-11B | UG-11B-S07 | A090 | Surround, joint test and line test | 79.9312 | m | 3 | 4 | UG-11B-S07-A080 | 3 | 2 |  | 2027-04-24 | 2027-05-03
UG-11B-S07-A100 | AW.PIPE.F6.UG-11B.UG-11B-S07 | F6 | UG-11B | UG-11B-S07 | A100 | Backfill to NG and remove struts | 687.5739 | m3 | 2 | 3 | UG-11B-S07-A090 | 2 | 2 |  | 2027-04-26 | 2027-05-05 | 2027-05-05 | UG-23-S04-A100
UG-11B-S07-A110 | AW.PIPE.F6.UG-11B.UG-11B-S07 | F6 | UG-11B | UG-11B-S07 | A110 | Dewatering off, extract sheets, reinstate | 159.8625 | m wall | 5 | 6 | UG-11B-S07-A100 | 1 | 2 |  | 2027-04-27 | 2027-05-07
UG-11B-S04-A010 | AW.PIPE.F6.UG-11B.UG-11B-S04 | F6 | UG-11B | UG-11B-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11B-S04-A020 | AW.PIPE.F6.UG-11B.UG-11B-S04 | F6 | UG-11B | UG-11B-S04 | A020 | Set-out, crossing survey and working platform | 40.2557 | m | 1 | 2 | UG-11B-S04-A010 |  |  | FS from A010; UG-11B-S07-A030 (SS, set-out one package ahead of piling) | 2027-02-07 | 2027-02-09
UG-11B-S04-A030 | AW.PIPE.F6.UG-11B.UG-11B-S04 | F6 | UG-11B | UG-11B-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 30 | piles | 6 | 7 | UG-11B-S04-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-21 | 2027-02-28 | 2027-02-28 | UG-11B-S07-A030
UG-11B-S04-A040 | AW.PIPE.F6.UG-11B.UG-11B-S04 | F6 | UG-11B | UG-11B-S04 | A040 | Install sheet piles (shored lengths) | 80.5114 | m wall | 4 | 5 | UG-11B-S04-A030 | 3 | 2 |  | 2027-02-24 | 2027-03-02 | 2027-03-02 | UG-11B-S07-A040
UG-11B-S04-A050 | AW.PIPE.F6.UG-11B.UG-11B-S04 | F6 | UG-11B | UG-11B-S04 | A050 | Install dewatering and draw down | 40.2557 | m | 9 | 11 | UG-11B-S04-A040 | 2 | 2 | UG-11B-S07-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-16 | 2027-03-27
UG-11B-S04-A060 | AW.PIPE.F6.UG-11B.UG-11B-S04 | F6 | UG-11B | UG-11B-S04 | A060 | Excavate and strut to formation | 531.1552 | m3 | 3 | 4 | UG-11B-S04-A050 | 10 | 2 |  | 2027-03-27 | 2027-03-31 | 2027-03-31 | UG-11B-S07-A060
UG-11B-S04-A070 | AW.PIPE.F6.UG-11B.UG-11B-S04 | F6 | UG-11B | UG-11B-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 40.2557 | m | 7 | 9 | UG-11B-S04-A060 | 2 | 2 |  | 2027-04-29 | 2027-05-08 | 2027-05-08 | UG-11B-S07-A070
UG-11B-S04-A080 | AW.PIPE.F6.UG-11B.UG-11B-S04 | F6 | UG-11B | UG-11B-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 40.2557 | m | 5 | 6 | UG-11B-S04-A070 | 3 | 2 |  | 2027-05-02 | 2027-05-10 | 2027-05-10 | UG-11B-S07-A080
UG-11B-S04-A090 | AW.PIPE.F6.UG-11B.UG-11B-S04 | F6 | UG-11B | UG-11B-S04 | A090 | Surround, joint test and line test | 40.2557 | m | 3 | 4 | UG-11B-S04-A080 | 2 | 2 |  | 2027-05-04 | 2027-05-12
UG-11B-S04-A100 | AW.PIPE.F6.UG-11B.UG-11B-S04 | F6 | UG-11B | UG-11B-S04 | A100 | Backfill to NG and remove struts | 398.9219 | m3 | 2 | 3 | UG-11B-S04-A090 | 2 | 2 |  | 2027-05-06 | 2027-05-14 | 2027-05-14 | UG-11B-S07-A100
UG-11B-S04-A110 | AW.PIPE.F6.UG-11B.UG-11B-S04 | F6 | UG-11B | UG-11B-S04 | A110 | Dewatering off, extract sheets, reinstate | 80.5114 | m wall | 3 | 4 | UG-11B-S04-A100 | 1 | 2 |  | 2027-05-07 | 2027-05-16
UG-11B-S03-A010 | AW.PIPE.F6.UG-11B.UG-11B-S03 | F6 | UG-11B | UG-11B-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11B-S03-A020 | AW.PIPE.F6.UG-11B.UG-11B-S03 | F6 | UG-11B | UG-11B-S03 | A020 | Set-out, crossing survey and working platform | 70.2152 | m | 1 | 2 | UG-11B-S03-A010 |  |  | FS from A010; UG-11B-S04-A030 (SS, set-out one package ahead of piling) | 2027-02-21 | 2027-02-23
UG-11B-S03-A030 | AW.PIPE.F6.UG-11B.UG-11B-S03 | F6 | UG-11B | UG-11B-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 50 | piles | 10 | 12 | UG-11B-S03-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-28 | 2027-03-12 | 2027-03-12 | UG-11B-S04-A030
UG-11B-S03-A040 | AW.PIPE.F6.UG-11B.UG-11B-S03 | F6 | UG-11B | UG-11B-S03 | A040 | Install sheet piles (shored lengths) | 140.4304 | m wall | 6 | 7 | UG-11B-S03-A030 | 4 | 2 |  | 2027-03-04 | 2027-03-14 | 2027-03-14 | UG-11B-S04-A040
UG-11B-S03-A050 | AW.PIPE.F6.UG-11B.UG-11B-S03 | F6 | UG-11B | UG-11B-S03 | A050 | Install dewatering and draw down | 70.2152 | m | 9 | 11 | UG-11B-S03-A040 | 3 | 2 | UG-11B-S04-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-20 | 2027-03-31
UG-11B-S03-A060 | AW.PIPE.F6.UG-11B.UG-11B-S03 | F6 | UG-11B | UG-11B-S03 | A060 | Excavate and strut to formation | 1124.359 | m3 | 5 | 6 | UG-11B-S03-A050 | 10 | 2 |  | 2027-03-31 | 2027-04-06 | 2027-04-06 | UG-11B-S04-A060
UG-11B-S03-A070 | AW.PIPE.F6.UG-11B.UG-11B-S03 | F6 | UG-11B | UG-11B-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 70.2152 | m | 9 | 11 | UG-11B-S03-A060 | 2 | 2 |  | 2027-05-08 | 2027-05-19 | 2027-05-19 | UG-11B-S04-A070
UG-11B-S03-A080 | AW.PIPE.F6.UG-11B.UG-11B-S03 | F6 | UG-11B | UG-11B-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 70.2152 | m | 4 | 5 | UG-11B-S03-A070 | 4 | 2 |  | 2027-05-12 | 2027-05-21 | 2027-05-21 | UG-11B-S04-A080
UG-11B-S03-A090 | AW.PIPE.F6.UG-11B.UG-11B-S03 | F6 | UG-11B | UG-11B-S03 | A090 | Surround, joint test and line test | 70.2152 | m | 3 | 4 | UG-11B-S03-A080 | 2 | 2 |  | 2027-05-14 | 2027-05-23
UG-11B-S03-A100 | AW.PIPE.F6.UG-11B.UG-11B-S03 | F6 | UG-11B | UG-11B-S03 | A100 | Backfill to NG and remove struts | 780.386 | m3 | 3 | 4 | UG-11B-S03-A090 | 2 | 2 |  | 2027-05-16 | 2027-05-25 | 2027-05-25 | UG-11B-S04-A100
UG-11B-S03-A110 | AW.PIPE.F6.UG-11B.UG-11B-S03 | F6 | UG-11B | UG-11B-S03 | A110 | Dewatering off, extract sheets, reinstate | 140.4304 | m wall | 4 | 5 | UG-11B-S03-A100 | 2 | 2 |  | 2027-05-18 | 2027-05-27
UG-11B-S02-A010 | AW.PIPE.F6.UG-11B.UG-11B-S02 | F6 | UG-11B | UG-11B-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11B-S02-A020 | AW.PIPE.F6.UG-11B.UG-11B-S02 | F6 | UG-11B | UG-11B-S02 | A020 | Set-out, crossing survey and working platform | 49.6291 | m | 1 | 2 | UG-11B-S02-A010 |  |  | FS from A010; UG-11B-S03-A030 (SS, set-out one package ahead of piling) | 2027-02-28 | 2027-03-02
UG-11B-S02-A030 | AW.PIPE.F6.UG-11B.UG-11B-S02 | F6 | UG-11B | UG-11B-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 36 | piles | 8 | 10 | UG-11B-S02-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-12 | 2027-03-22 | 2027-03-22 | UG-11B-S03-A030
UG-11B-S02-A040 | AW.PIPE.F6.UG-11B.UG-11B-S02 | F6 | UG-11B | UG-11B-S02 | A040 | Install sheet piles (shored lengths) | 99.2582 | m wall | 4 | 5 | UG-11B-S02-A030 | 3 | 2 |  | 2027-03-15 | 2027-03-24 | 2027-03-24 | UG-11B-S03-A040
UG-11B-S02-A050 | AW.PIPE.F6.UG-11B.UG-11B-S02 | F6 | UG-11B | UG-11B-S02 | A050 | Install dewatering and draw down | 49.6291 | m | 9 | 11 | UG-11B-S02-A040 | 2 | 2 | UG-11B-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-26 | 2027-04-06
UG-11B-S02-A060 | AW.PIPE.F6.UG-11B.UG-11B-S02 | F6 | UG-11B | UG-11B-S02 | A060 | Excavate and strut to formation | 506.9345 | m3 | 3 | 4 | UG-11B-S02-A050 | 10 | 2 |  | 2027-04-06 | 2027-04-10 | 2027-04-10 | UG-11B-S03-A060
UG-11B-S02-A070 | AW.PIPE.F6.UG-11B.UG-11B-S02 | F6 | UG-11B | UG-11B-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 49.6291 | m | 8 | 10 | UG-11B-S02-A060 | 2 | 2 |  | 2027-05-19 | 2027-05-29 | 2027-05-29 | UG-11B-S03-A070
UG-11B-S02-A080 | AW.PIPE.F6.UG-11B.UG-11B-S02 | F6 | UG-11B | UG-11B-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 49.6291 | m | 2 | 3 | UG-11B-S02-A070 | 3 | 2 |  | 2027-05-22 | 2027-05-31 | 2027-05-31 | UG-11B-S03-A080
UG-11B-S02-A090 | AW.PIPE.F6.UG-11B.UG-11B-S02 | F6 | UG-11B | UG-11B-S02 | A090 | Surround, joint test and line test | 49.6291 | m | 3 | 4 | UG-11B-S02-A080 | 1 | 2 |  | 2027-05-23 | 2027-06-02
UG-11B-S02-A100 | AW.PIPE.F6.UG-11B.UG-11B-S02 | F6 | UG-11B | UG-11B-S02 | A100 | Backfill to NG and remove struts | 418.0216 | m3 | 2 | 3 | UG-11B-S02-A090 | 2 | 2 | UG-16A-S01-A080 (FS, shared trench laid) | 2027-05-25 | 2027-06-04 | 2027-06-04 | UG-11B-S03-A100
UG-11B-S02-A110 | AW.PIPE.F6.UG-11B.UG-11B-S02 | F6 | UG-11B | UG-11B-S02 | A110 | Dewatering off, extract sheets, reinstate | 99.2582 | m wall | 3 | 4 | UG-11B-S02-A100 | 1 | 2 |  | 2027-05-26 | 2027-06-06
UG-11B-S01-A010 | AW.PIPE.F6.UG-11B.UG-11B-S01 | F6 | UG-11B | UG-11B-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-11B-S01-A020 | AW.PIPE.F6.UG-11B.UG-11B-S01 | F6 | UG-11B | UG-11B-S01 | A020 | Set-out, crossing survey and working platform | 6 | m | 1 | 2 | UG-11B-S01-A010 |  |  | FS from A010; UG-11B-S02-A030 (SS, tie-in team follows the adjacent run) | 2027-03-12 | 2027-03-14
UG-11B-S01-A030 | AW.PIPE.F6.UG-11B.UG-11B-S01 | F6 | UG-11B | UG-11B-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 3 | piles | 1 | 2 | UG-11B-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-13 | 2027-03-16 | 2027-03-16
UG-11B-S01-A040 | AW.PIPE.F6.UG-11B.UG-11B-S01 | F6 | UG-11B | UG-11B-S01 | A040 | Install sheet piles (shored lengths) | 12 | m wall | 1 | 2 | UG-11B-S01-A030 | 1 | 2 |  | 2027-03-14 | 2027-03-18 | 2027-03-18
UG-11B-S01-A050 | AW.PIPE.F6.UG-11B.UG-11B-S01 | F6 | UG-11B | UG-11B-S01 | A050 | Install dewatering and draw down | 6 | m | 8 | 10 | UG-11B-S01-A040 | 1 | 2 |  | 2027-03-15 | 2027-03-25
UG-11B-S01-A060 | AW.PIPE.F6.UG-11B.UG-11B-S01 | F6 | UG-11B | UG-11B-S01 | A060 | Excavate and strut to formation | 61.1998 | m3 | 1 | 2 | UG-11B-S01-A050 | 10 | 2 |  | 2027-03-25 | 2027-03-27 | 2027-03-27
UG-11B-S01-A070 | AW.PIPE.F6.UG-11B.UG-11B-S01 | F6 | UG-11B | UG-11B-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6 | m | 4 | 5 | UG-11B-S01-A060 | 1 | 2 |  | 2027-03-26 | 2027-03-31 | 2027-03-31
UG-11B-S01-A080 | AW.PIPE.F6.UG-11B.UG-11B-S01 | F6 | UG-11B | UG-11B-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6 | m | 4 | 5 | UG-11B-S01-A070 | 2 | 2 | UG-11B-S02-A080 (FS, closure) | 2027-05-31 | 2027-06-05 | 2027-06-05
UG-11B-S01-A090 | AW.PIPE.F6.UG-11B.UG-11B-S01 | F6 | UG-11B | UG-11B-S01 | A090 | Surround, joint test and line test | 6 | m | 3 | 4 | UG-11B-S01-A080 | 2 | 2 |  | 2027-06-02 | 2027-06-07
UG-11B-S01-A100 | AW.PIPE.F6.UG-11B.UG-11B-S01 | F6 | UG-11B | UG-11B-S01 | A100 | Backfill to NG and remove struts | 50.4875 | m3 | 1 | 2 | UG-11B-S01-A090 | 2 | 2 | UG-16A-S01-A080 (FS, shared trench laid) | 2027-06-04 | 2027-06-09 | 2027-06-09
UG-11B-S01-A110 | AW.PIPE.F6.UG-11B.UG-11B-S01 | F6 | UG-11B | UG-11B-S01 | A110 | Dewatering off, extract sheets, reinstate | 12 | m wall | 2 | 3 | UG-11B-S01-A100 | 1 | 2 |  | 2027-06-05 | 2027-06-11
UG-16A-S01-A010 | AW.PIPE.F6.UG-16A.UG-16A-S01 | F6 | UG-16A | UG-16A-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-16A-S01-A020 | AW.PIPE.F6.UG-16A.UG-16A-S01 | F6 | UG-16A | UG-16A-S01 | A020 | Set-out, crossing survey and working platform | 37.7775 | m | 1 | 2 | UG-16A-S01-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-16A-S01-A030 | AW.PIPE.F6.UG-16A.UG-16A-S01 | F6 | UG-16A | UG-16A-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 28 | piles | 6 | 7 | UG-16A-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-09 | 2026-12-09
UG-16A-S01-A040 | AW.PIPE.F6.UG-16A.UG-16A-S01 | F6 | UG-16A | UG-16A-S01 | A040 | Install sheet piles (shored lengths) | 55.5551 | m wall | 3 | 4 | UG-16A-S01-A030 | 3 | 2 |  | 2026-12-05 | 2026-12-11 | 2026-12-11
UG-16A-S01-A050 | AW.PIPE.F6.UG-16A.UG-16A-S01 | F6 | UG-16A | UG-16A-S01 | A050 | Install dewatering and draw down | 37.7775 | m | 8 | 10 | UG-16A-S01-A040 | 2 | 2 |  | 2026-12-07 | 2026-12-17
UG-16A-S01-A060 | AW.PIPE.F6.UG-16A.UG-16A-S01 | F6 | UG-16A | UG-16A-S01 | A060 | Excavate and strut to formation | 394.9017 | m3 | 2 | 3 | UG-16A-S01-A050 | 10 | 2 | UG-10-S05-A100 (FS, deeper first); UG-11B-S01-A060 (SS, shared trench); UG-11B-S02-A060 (SS, shared trench) | 2027-04-06 | 2027-04-09 | 2027-04-09
UG-16A-S01-A070 | AW.PIPE.F6.UG-16A.UG-16A-S01 | F6 | UG-16A | UG-16A-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 37.7775 | m | 7 | 9 | UG-16A-S01-A060 | 1 | 2 |  | 2027-04-07 | 2027-04-16 | 2027-04-16
UG-16A-S01-A080 | AW.PIPE.F6.UG-16A.UG-16A-S01 | F6 | UG-16A | UG-16A-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 37.7775 | m | 9 | 11 | UG-16A-S01-A070 | 3 | 2 |  | 2027-04-10 | 2027-04-21 | 2027-04-21
UG-16A-S01-A090 | AW.PIPE.F6.UG-16A.UG-16A-S01 | F6 | UG-16A | UG-16A-S01 | A090 | Surround, joint test and line test | 37.7775 | m | 3 | 4 | UG-16A-S01-A080 | 4 | 2 |  | 2027-04-14 | 2027-04-23
UG-16A-S01-A100 | AW.PIPE.F6.UG-16A.UG-16A-S01 | F6 | UG-16A | UG-16A-S01 | A100 | Backfill to NG and remove struts | 280.2289 | m3 | 1 | 2 | UG-16A-S01-A090 | 2 | 2 | UG-11B-S01-A080 (FS, shared trench laid); UG-11B-S02-A080 (FS, shared trench laid) | 2027-06-05 | 2027-06-07 | 2027-06-07
UG-16A-S01-A110 | AW.PIPE.F6.UG-16A.UG-16A-S01 | F6 | UG-16A | UG-16A-S01 | A110 | Dewatering off, extract sheets, reinstate | 55.5551 | m wall | 3 | 4 | UG-16A-S01-A100 | 1 | 2 |  | 2027-06-06 | 2027-06-10
UG-11B-S10-A010 | AW.PIPE.F6.UG-11B.UG-11B-S10 | F6 | UG-11B | UG-11B-S10 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11B-S10-A020 | AW.PIPE.F6.UG-11B.UG-11B-S10 | F6 | UG-11B | UG-11B-S10 | A020 | Set-out, crossing survey and working platform | 49.4448 | m | 1 | 2 | UG-11B-S10-A010 |  |  | FS from A010; UG-11B-S02-A030 (SS, set-out one package ahead of piling) | 2027-03-12 | 2027-03-14
UG-11B-S10-A030 | AW.PIPE.F6.UG-11B.UG-11B-S10 | F6 | UG-11B | UG-11B-S10 | A030 | Pipe-support piling from platform (incl. integrity tests) | 36 | piles | 8 | 10 | UG-11B-S10-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-22 | 2027-04-01 | 2027-04-01 | UG-11B-S02-A030
UG-11B-S10-A040 | AW.PIPE.F6.UG-11B.UG-11B-S10 | F6 | UG-11B | UG-11B-S10 | A040 | Install sheet piles (shored lengths) | 98.8895 | m wall | 4 | 5 | UG-11B-S10-A030 | 3 | 2 |  | 2027-03-25 | 2027-04-03 | 2027-04-03 | UG-11B-S02-A040
UG-11B-S10-A050 | AW.PIPE.F6.UG-11B.UG-11B-S10 | F6 | UG-11B | UG-11B-S10 | A050 | Install dewatering and draw down | 49.4448 | m | 9 | 11 | UG-11B-S10-A040 | 2 | 2 | UG-11B-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-30 | 2027-04-10
UG-11B-S10-A060 | AW.PIPE.F6.UG-11B.UG-11B-S10 | F6 | UG-11B | UG-11B-S10 | A060 | Excavate and strut to formation | 505.0285 | m3 | 3 | 4 | UG-11B-S10-A050 | 10 | 2 |  | 2027-04-10 | 2027-04-14 | 2027-04-14 | UG-11B-S02-A060
UG-11B-S10-A070 | AW.PIPE.F6.UG-11B.UG-11B-S10 | F6 | UG-11B | UG-11B-S10 | A070 | Trim piles, blinding and piled slab (incl. cure) | 49.4448 | m | 8 | 10 | UG-11B-S10-A060 | 2 | 2 |  | 2027-05-29 | 2027-06-08 | 2027-06-08 | UG-11B-S02-A070
UG-11B-S10-A080 | AW.PIPE.F6.UG-11B.UG-11B-S10 | F6 | UG-11B | UG-11B-S10 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 49.4448 | m | 2 | 3 | UG-11B-S10-A070 | 3 | 2 |  | 2027-06-01 | 2027-06-10 | 2027-06-10 | UG-11B-S02-A080
UG-11B-S10-A090 | AW.PIPE.F6.UG-11B.UG-11B-S10 | F6 | UG-11B | UG-11B-S10 | A090 | Surround, joint test and line test | 49.4448 | m | 3 | 4 | UG-11B-S10-A080 | 1 | 2 |  | 2027-06-02 | 2027-06-12
UG-11B-S10-A100 | AW.PIPE.F6.UG-11B.UG-11B-S10 | F6 | UG-11B | UG-11B-S10 | A100 | Backfill to NG and remove struts | 416.4557 | m3 | 2 | 3 | UG-11B-S10-A090 | 2 | 2 | UG-16C-S01-A080 (FS, shared trench laid) | 2027-06-04 | 2027-06-14 | 2027-06-14 | UG-11B-S02-A100
UG-11B-S10-A110 | AW.PIPE.F6.UG-11B.UG-11B-S10 | F6 | UG-11B | UG-11B-S10 | A110 | Dewatering off, extract sheets, reinstate | 98.8895 | m wall | 3 | 4 | UG-11B-S10-A100 | 1 | 2 |  | 2027-06-05 | 2027-06-16
UG-11B-S09-A010 | AW.PIPE.F6.UG-11B.UG-11B-S09 | F6 | UG-11B | UG-11B-S09 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-11B-S09-A020 | AW.PIPE.F6.UG-11B.UG-11B-S09 | F6 | UG-11B | UG-11B-S09 | A020 | Set-out, crossing survey and working platform | 6 | m | 1 | 2 | UG-11B-S09-A010 |  |  | FS from A010; UG-11B-S10-A030 (SS, tie-in team follows the adjacent run) | 2027-03-22 | 2027-03-24
UG-11B-S09-A030 | AW.PIPE.F6.UG-11B.UG-11B-S09 | F6 | UG-11B | UG-11B-S09 | A030 | Pipe-support piling from platform (incl. integrity tests) | 3 | piles | 1 | 2 | UG-11B-S09-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-23 | 2027-03-26 | 2027-03-26
UG-11B-S09-A040 | AW.PIPE.F6.UG-11B.UG-11B-S09 | F6 | UG-11B | UG-11B-S09 | A040 | Install sheet piles (shored lengths) | 12 | m wall | 1 | 2 | UG-11B-S09-A030 | 1 | 2 |  | 2027-03-24 | 2027-03-28 | 2027-03-28
UG-11B-S09-A050 | AW.PIPE.F6.UG-11B.UG-11B-S09 | F6 | UG-11B | UG-11B-S09 | A050 | Install dewatering and draw down | 6 | m | 8 | 10 | UG-11B-S09-A040 | 1 | 2 |  | 2027-03-25 | 2027-04-04
UG-11B-S09-A060 | AW.PIPE.F6.UG-11B.UG-11B-S09 | F6 | UG-11B | UG-11B-S09 | A060 | Excavate and strut to formation | 61.1999 | m3 | 1 | 2 | UG-11B-S09-A050 | 10 | 2 |  | 2027-04-04 | 2027-04-06 | 2027-04-06
UG-11B-S09-A070 | AW.PIPE.F6.UG-11B.UG-11B-S09 | F6 | UG-11B | UG-11B-S09 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6 | m | 4 | 5 | UG-11B-S09-A060 | 1 | 2 |  | 2027-04-05 | 2027-04-10 | 2027-04-10
UG-11B-S09-A080 | AW.PIPE.F6.UG-11B.UG-11B-S09 | F6 | UG-11B | UG-11B-S09 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6 | m | 4 | 5 | UG-11B-S09-A070 | 2 | 2 | UG-11B-S10-A080 (FS, closure) | 2027-06-10 | 2027-06-15 | 2027-06-15
UG-11B-S09-A090 | AW.PIPE.F6.UG-11B.UG-11B-S09 | F6 | UG-11B | UG-11B-S09 | A090 | Surround, joint test and line test | 6 | m | 3 | 4 | UG-11B-S09-A080 | 2 | 2 |  | 2027-06-12 | 2027-06-17
UG-11B-S09-A100 | AW.PIPE.F6.UG-11B.UG-11B-S09 | F6 | UG-11B | UG-11B-S09 | A100 | Backfill to NG and remove struts | 50.4876 | m3 | 1 | 2 | UG-11B-S09-A090 | 2 | 2 | UG-16C-S01-A080 (FS, shared trench laid) | 2027-06-14 | 2027-06-19 | 2027-06-19
UG-11B-S09-A110 | AW.PIPE.F6.UG-11B.UG-11B-S09 | F6 | UG-11B | UG-11B-S09 | A110 | Dewatering off, extract sheets, reinstate | 12 | m wall | 2 | 3 | UG-11B-S09-A100 | 1 | 2 |  | 2027-06-15 | 2027-06-21
UG-16C-S01-A010 | AW.PIPE.F6.UG-16C.UG-16C-S01 | F6 | UG-16C | UG-16C-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-16C-S01-A020 | AW.PIPE.F6.UG-16C.UG-16C-S01 | F6 | UG-16C | UG-16C-S01 | A020 | Set-out, crossing survey and working platform | 38.3838 | m | 1 | 2 | UG-16C-S01-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-16C-S01-A030 | AW.PIPE.F6.UG-16C.UG-16C-S01 | F6 | UG-16C | UG-16C-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 28 | piles | 6 | 7 | UG-16C-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-09 | 2026-12-09
UG-16C-S01-A040 | AW.PIPE.F6.UG-16C.UG-16C-S01 | F6 | UG-16C | UG-16C-S01 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-16C-S01-A030 | 3 | 0 |  | 2026-12-05 | 2026-12-09 | 0
UG-16C-S01-A050 | AW.PIPE.F6.UG-16C.UG-16C-S01 | F6 | UG-16C | UG-16C-S01 | A050 | Install dewatering and draw down | 38.3838 | m | 8 | 10 | UG-16C-S01-A040 | 0 | 2 |  | 2026-12-05 | 2026-12-15
UG-16C-S01-A060 | AW.PIPE.F6.UG-16C.UG-16C-S01 | F6 | UG-16C | UG-16C-S01 | A060 | Excavate and strut to formation | 1012.689 | m3 | 3 | 4 | UG-16C-S01-A050 | 10 | 2 | UG-11B-S09-A060 (SS, shared trench); UG-11B-S10-A060 (SS, shared trench) | 2027-04-10 | 2027-04-14 | 2027-04-14
UG-16C-S01-A070 | AW.PIPE.F6.UG-16C.UG-16C-S01 | F6 | UG-16C | UG-16C-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 38.3838 | m | 7 | 9 | UG-16C-S01-A060 | 2 | 2 |  | 2027-04-12 | 2027-04-21 | 2027-04-21
UG-16C-S01-A080 | AW.PIPE.F6.UG-16C.UG-16C-S01 | F6 | UG-16C | UG-16C-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 38.3838 | m | 7 | 9 | UG-16C-S01-A070 | 3 | 2 |  | 2027-04-15 | 2027-04-24 | 2027-04-24
UG-16C-S01-A090 | AW.PIPE.F6.UG-16C.UG-16C-S01 | F6 | UG-16C | UG-16C-S01 | A090 | Surround, joint test and line test | 38.3838 | m | 3 | 4 | UG-16C-S01-A080 | 3 | 2 |  | 2027-04-18 | 2027-04-26
UG-16C-S01-A100 | AW.PIPE.F6.UG-16C.UG-16C-S01 | F6 | UG-16C | UG-16C-S01 | A100 | Backfill to NG and remove struts | 895.5259 | m3 | 3 | 4 | UG-16C-S01-A090 | 2 | 2 | UG-11B-S09-A080 (FS, shared trench laid); UG-11B-S10-A080 (FS, shared trench laid) | 2027-06-15 | 2027-06-19 | 2027-06-19
UG-16C-S01-A110 | AW.PIPE.F6.UG-16C.UG-16C-S01 | F6 | UG-16C | UG-16C-S01 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-16C-S01-A100 | 2 | 2 |  | 2027-06-17 | 2027-06-21
UG-11B-S12-A010 | AW.PIPE.F6.UG-11B.UG-11B-S12 | F6 | UG-11B | UG-11B-S12 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11B-S12-A020 | AW.PIPE.F6.UG-11B.UG-11B-S12 | F6 | UG-11B | UG-11B-S12 | A020 | Set-out, crossing survey and working platform | 32.7629 | m | 1 | 2 | UG-11B-S12-A010 |  |  | FS from A010; UG-11B-S10-A030 (SS, set-out one package ahead of piling) | 2027-03-22 | 2027-03-24
UG-11B-S12-A030 | AW.PIPE.F6.UG-11B.UG-11B-S12 | F6 | UG-11B | UG-11B-S12 | A030 | Pipe-support piling from platform (incl. integrity tests) | 24 | piles | 5 | 6 | UG-11B-S12-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-01 | 2027-04-07 | 2027-04-07 | UG-11B-S10-A030
UG-11B-S12-A040 | AW.PIPE.F6.UG-11B.UG-11B-S12 | F6 | UG-11B | UG-11B-S12 | A040 | Install sheet piles (shored lengths) | 65.5259 | m wall | 3 | 4 | UG-11B-S12-A030 | 2 | 2 |  | 2027-04-03 | 2027-04-09 | 2027-04-09 | UG-11B-S10-A040
UG-11B-S12-A050 | AW.PIPE.F6.UG-11B.UG-11B-S12 | F6 | UG-11B | UG-11B-S12 | A050 | Install dewatering and draw down | 32.7629 | m | 8 | 10 | UG-11B-S12-A040 | 2 | 2 | UG-11B-S10-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-05 | 2027-04-15
UG-11B-S12-A060 | AW.PIPE.F6.UG-11B.UG-11B-S12 | F6 | UG-11B | UG-11B-S12 | A060 | Excavate and strut to formation | 334.1819 | m3 | 2 | 3 | UG-11B-S12-A050 | 10 | 2 |  | 2027-04-15 | 2027-04-18 | 2027-04-18 | UG-11B-S10-A060
UG-11B-S12-A070 | AW.PIPE.F6.UG-11B.UG-11B-S12 | F6 | UG-11B | UG-11B-S12 | A070 | Trim piles, blinding and piled slab (incl. cure) | 32.7629 | m | 6 | 7 | UG-11B-S12-A060 | 1 | 2 |  | 2027-06-08 | 2027-06-15 | 2027-06-15 | UG-11B-S10-A070
UG-11B-S12-A080 | AW.PIPE.F6.UG-11B.UG-11B-S12 | F6 | UG-11B | UG-11B-S12 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 32.7629 | m | 1 | 2 | UG-11B-S12-A070 | 3 | 2 |  | 2027-06-11 | 2027-06-17 | 2027-06-17 | UG-11B-S10-A080
UG-11B-S12-A090 | AW.PIPE.F6.UG-11B.UG-11B-S12 | F6 | UG-11B | UG-11B-S12 | A090 | Surround, joint test and line test | 32.7629 | m | 3 | 4 | UG-11B-S12-A080 | 1 | 2 |  | 2027-06-12 | 2027-06-19
UG-11B-S12-A100 | AW.PIPE.F6.UG-11B.UG-11B-S12 | F6 | UG-11B | UG-11B-S12 | A100 | Backfill to NG and remove struts | 275.687 | m3 | 1 | 2 | UG-11B-S12-A090 | 2 | 2 | UG-16D-S01-A080 (FS, shared trench laid) | 2027-06-14 | 2027-06-21 | 2027-06-21 | UG-11B-S10-A100
UG-11B-S12-A110 | AW.PIPE.F6.UG-11B.UG-11B-S12 | F6 | UG-11B | UG-11B-S12 | A110 | Dewatering off, extract sheets, reinstate | 65.5259 | m wall | 3 | 4 | UG-11B-S12-A100 | 1 | 2 |  | 2027-06-15 | 2027-06-23
UG-11B-S11-A010 | AW.PIPE.F6.UG-11B.UG-11B-S11 | F6 | UG-11B | UG-11B-S11 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-11B-S11-A020 | AW.PIPE.F6.UG-11B.UG-11B-S11 | F6 | UG-11B | UG-11B-S11 | A020 | Set-out, crossing survey and working platform | 6 | m | 1 | 2 | UG-11B-S11-A010 |  |  | FS from A010; UG-11B-S12-A030 (SS, tie-in team follows the adjacent run) | 2027-04-01 | 2027-04-03
UG-11B-S11-A030 | AW.PIPE.F6.UG-11B.UG-11B-S11 | F6 | UG-11B | UG-11B-S11 | A030 | Pipe-support piling from platform (incl. integrity tests) | 6 | piles | 2 | 3 | UG-11B-S11-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-02 | 2027-04-05 | 2027-04-05
UG-11B-S11-A040 | AW.PIPE.F6.UG-11B.UG-11B-S11 | F6 | UG-11B | UG-11B-S11 | A040 | Install sheet piles (shored lengths) | 12 | m wall | 1 | 2 | UG-11B-S11-A030 | 1 | 2 |  | 2027-04-03 | 2027-04-07 | 2027-04-07
UG-11B-S11-A050 | AW.PIPE.F6.UG-11B.UG-11B-S11 | F6 | UG-11B | UG-11B-S11 | A050 | Install dewatering and draw down | 6 | m | 8 | 10 | UG-11B-S11-A040 | 1 | 2 |  | 2027-04-04 | 2027-04-14
UG-11B-S11-A060 | AW.PIPE.F6.UG-11B.UG-11B-S11 | F6 | UG-11B | UG-11B-S11 | A060 | Excavate and strut to formation | 61.2 | m3 | 1 | 2 | UG-11B-S11-A050 | 10 | 2 |  | 2027-04-14 | 2027-04-16 | 2027-04-16
UG-11B-S11-A070 | AW.PIPE.F6.UG-11B.UG-11B-S11 | F6 | UG-11B | UG-11B-S11 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6 | m | 4 | 5 | UG-11B-S11-A060 | 1 | 2 |  | 2027-04-15 | 2027-04-20 | 2027-04-20
UG-11B-S11-A080 | AW.PIPE.F6.UG-11B.UG-11B-S11 | F6 | UG-11B | UG-11B-S11 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6 | m | 4 | 5 | UG-11B-S11-A070 | 2 | 2 | UG-11B-S12-A080 (FS, closure) | 2027-06-17 | 2027-06-22 | 2027-06-22
UG-11B-S11-A090 | AW.PIPE.F6.UG-11B.UG-11B-S11 | F6 | UG-11B | UG-11B-S11 | A090 | Surround, joint test and line test | 6 | m | 3 | 4 | UG-11B-S11-A080 | 2 | 2 |  | 2027-06-19 | 2027-06-24
UG-11B-S11-A100 | AW.PIPE.F6.UG-11B.UG-11B-S11 | F6 | UG-11B | UG-11B-S11 | A100 | Backfill to NG and remove struts | 50.4876 | m3 | 1 | 2 | UG-11B-S11-A090 | 2 | 2 | UG-16D-S01-A080 (FS, shared trench laid) | 2027-06-21 | 2027-06-26 | 2027-06-26
UG-11B-S11-A110 | AW.PIPE.F6.UG-11B.UG-11B-S11 | F6 | UG-11B | UG-11B-S11 | A110 | Dewatering off, extract sheets, reinstate | 12 | m wall | 2 | 3 | UG-11B-S11-A100 | 1 | 2 |  | 2027-06-22 | 2027-06-28
UG-16D-S01-A010 | AW.PIPE.F6.UG-16D.UG-16D-S01 | F6 | UG-16D | UG-16D-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-16D-S01-A020 | AW.PIPE.F6.UG-16D.UG-16D-S01 | F6 | UG-16D | UG-16D-S01 | A020 | Set-out, crossing survey and working platform | 36.3001 | m | 1 | 2 | UG-16D-S01-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-16D-S01-A030 | AW.PIPE.F6.UG-16D.UG-16D-S01 | F6 | UG-16D | UG-16D-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 28 | piles | 6 | 7 | UG-16D-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-09 | 2026-12-09
UG-16D-S01-A040 | AW.PIPE.F6.UG-16D.UG-16D-S01 | F6 | UG-16D | UG-16D-S01 | A040 | Install sheet piles (shored lengths) | 52.6003 | m wall | 3 | 4 | UG-16D-S01-A030 | 3 | 2 |  | 2026-12-05 | 2026-12-11 | 2026-12-11
UG-16D-S01-A050 | AW.PIPE.F6.UG-16D.UG-16D-S01 | F6 | UG-16D | UG-16D-S01 | A050 | Install dewatering and draw down | 36.3001 | m | 8 | 10 | UG-16D-S01-A040 | 2 | 2 |  | 2026-12-07 | 2026-12-17
UG-16D-S01-A060 | AW.PIPE.F6.UG-16D.UG-16D-S01 | F6 | UG-16D | UG-16D-S01 | A060 | Excavate and strut to formation | 376.8448 | m3 | 2 | 3 | UG-16D-S01-A050 | 10 | 2 | UG-11B-S07-A100 (FS, deeper first); UG-11B-S11-A060 (SS, shared trench); UG-11B-S12-A060 (SS, shared trench) | 2027-05-05 | 2027-05-08 | 2027-05-08
UG-16D-S01-A070 | AW.PIPE.F6.UG-16D.UG-16D-S01 | F6 | UG-16D | UG-16D-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 36.3001 | m | 7 | 9 | UG-16D-S01-A060 | 1 | 2 |  | 2027-05-06 | 2027-05-15 | 2027-05-15
UG-16D-S01-A080 | AW.PIPE.F6.UG-16D.UG-16D-S01 | F6 | UG-16D | UG-16D-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 36.3001 | m | 8 | 10 | UG-16D-S01-A070 | 3 | 2 |  | 2027-05-09 | 2027-05-19 | 2027-05-19
UG-16D-S01-A090 | AW.PIPE.F6.UG-16D.UG-16D-S01 | F6 | UG-16D | UG-16D-S01 | A090 | Surround, joint test and line test | 36.3001 | m | 3 | 4 | UG-16D-S01-A080 | 3 | 2 |  | 2027-05-12 | 2027-05-21
UG-16D-S01-A100 | AW.PIPE.F6.UG-16D.UG-16D-S01 | F6 | UG-16D | UG-16D-S01 | A100 | Backfill to NG and remove struts | 267.8356 | m3 | 1 | 2 | UG-16D-S01-A090 | 2 | 2 | UG-11B-S11-A080 (FS, shared trench laid); UG-11B-S12-A080 (FS, shared trench laid) | 2027-06-22 | 2027-06-24 | 2027-06-24
UG-16D-S01-A110 | AW.PIPE.F6.UG-16D.UG-16D-S01 | F6 | UG-16D | UG-16D-S01 | A110 | Dewatering off, extract sheets, reinstate | 52.6003 | m wall | 3 | 4 | UG-16D-S01-A100 | 1 | 2 |  | 2027-06-23 | 2027-06-27
UG-11B-S13-A010 | AW.PIPE.F6.UG-11B.UG-11B-S13 | F6 | UG-11B | UG-11B-S13 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11B-S13-A020 | AW.PIPE.F6.UG-11B.UG-11B-S13 | F6 | UG-11B | UG-11B-S13 | A020 | Set-out, crossing survey and working platform | 18.1 | m | 1 | 2 | UG-11B-S13-A010 |  |  | FS from A010; UG-11B-S12-A030 (SS, set-out one package ahead of piling) | 2027-04-01 | 2027-04-03
UG-11B-S13-A030 | AW.PIPE.F6.UG-11B.UG-11B-S13 | F6 | UG-11B | UG-11B-S13 | A030 | Pipe-support piling from platform (incl. integrity tests) | 16 | piles | 4 | 5 | UG-11B-S13-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-07 | 2027-04-12 | 2027-04-12 | UG-11B-S12-A030
UG-11B-S13-A040 | AW.PIPE.F6.UG-11B.UG-11B-S13 | F6 | UG-11B | UG-11B-S13 | A040 | Install sheet piles (shored lengths) | 36.2 | m wall | 2 | 3 | UG-11B-S13-A030 | 2 | 2 |  | 2027-04-09 | 2027-04-14 | 2027-04-14 | UG-11B-S12-A040
UG-11B-S13-A050 | AW.PIPE.F6.UG-11B.UG-11B-S13 | F6 | UG-11B | UG-11B-S13 | A050 | Install dewatering and draw down | 18.1 | m | 8 | 10 | UG-11B-S13-A040 | 1 | 2 | UG-11B-S12-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-10 | 2027-04-20
UG-11B-S13-A060 | AW.PIPE.F6.UG-11B.UG-11B-S13 | F6 | UG-11B | UG-11B-S13 | A060 | Excavate and strut to formation | 289.8363 | m3 | 2 | 3 | UG-11B-S13-A050 | 10 | 2 |  | 2027-04-20 | 2027-04-23 | 2027-04-23 | UG-11B-S12-A060
UG-11B-S13-A070 | AW.PIPE.F6.UG-11B.UG-11B-S13 | F6 | UG-11B | UG-11B-S13 | A070 | Trim piles, blinding and piled slab (incl. cure) | 18.1 | m | 5 | 6 | UG-11B-S13-A060 | 1 | 2 |  | 2027-06-15 | 2027-06-21 | 2027-06-21 | UG-11B-S12-A070
UG-11B-S13-A080 | AW.PIPE.F6.UG-11B.UG-11B-S13 | F6 | UG-11B | UG-11B-S13 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 18.1 | m | 1 | 2 | UG-11B-S13-A070 | 2 | 2 |  | 2027-06-17 | 2027-06-23 | 2027-06-23 | UG-11B-S12-A080
UG-11B-S13-A090 | AW.PIPE.F6.UG-11B.UG-11B-S13 | F6 | UG-11B | UG-11B-S13 | A090 | Surround, joint test and line test | 18.1 | m | 3 | 4 | UG-11B-S13-A080 | 1 | 2 |  | 2027-06-18 | 2027-06-25
UG-11B-S13-A100 | AW.PIPE.F6.UG-11B.UG-11B-S13 | F6 | UG-11B | UG-11B-S13 | A100 | Backfill to NG and remove struts | 201.1672 | m3 | 1 | 2 | UG-11B-S13-A090 | 2 | 2 |  | 2027-06-21 | 2027-06-27 | 2027-06-27 | UG-11B-S12-A100
UG-11B-S13-A110 | AW.PIPE.F6.UG-11B.UG-11B-S13 | F6 | UG-11B | UG-11B-S13 | A110 | Dewatering off, extract sheets, reinstate | 36.2 | m wall | 2 | 3 | UG-11B-S13-A100 | 1 | 2 |  | 2027-06-22 | 2027-06-29
UG-11A-S04-A010 | AW.PIPE.F6.UG-11A.UG-11A-S04 | F6 | UG-11A | UG-11A-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11A-S04-A020 | AW.PIPE.F6.UG-11A.UG-11A-S04 | F6 | UG-11A | UG-11A-S04 | A020 | Set-out, crossing survey and working platform | 39.672 | m | 1 | 2 | UG-11A-S04-A010 |  |  | FS from A010; UG-11B-S13-A030 (SS, set-out one package ahead of piling) | 2027-04-07 | 2027-04-09
UG-11A-S04-A030 | AW.PIPE.F6.UG-11A.UG-11A-S04 | F6 | UG-11A | UG-11A-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 30 | piles | 6 | 7 | UG-11A-S04-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-12 | 2027-04-19 | 2027-04-19 | UG-11B-S13-A030
UG-11A-S04-A040 | AW.PIPE.F6.UG-11A.UG-11A-S04 | F6 | UG-11A | UG-11A-S04 | A040 | Install sheet piles (shored lengths) | 79.3441 | m wall | 4 | 5 | UG-11A-S04-A030 | 3 | 2 |  | 2027-04-15 | 2027-04-21 | 2027-04-21 | UG-11B-S13-A040
UG-11A-S04-A050 | AW.PIPE.F6.UG-11A.UG-11A-S04 | F6 | UG-11A | UG-11A-S04 | A050 | Install dewatering and draw down | 39.672 | m | 8 | 10 | UG-11A-S04-A040 | 2 | 2 | UG-11B-S13-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-17 | 2027-04-27
UG-11A-S04-A060 | AW.PIPE.F6.UG-11A.UG-11A-S04 | F6 | UG-11A | UG-11A-S04 | A060 | Excavate and strut to formation | 484.2376 | m3 | 2 | 3 | UG-11A-S04-A050 | 10 | 2 |  | 2027-04-27 | 2027-04-30 | 2027-04-30 | UG-11B-S13-A060
UG-11A-S04-A070 | AW.PIPE.F6.UG-11A.UG-11A-S04 | F6 | UG-11A | UG-11A-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 39.672 | m | 7 | 9 | UG-11A-S04-A060 | 1 | 2 |  | 2027-06-21 | 2027-06-30 | 2027-06-30 | UG-11B-S13-A070
UG-11A-S04-A080 | AW.PIPE.F6.UG-11A.UG-11A-S04 | F6 | UG-11A | UG-11A-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 39.672 | m | 2 | 3 | UG-11A-S04-A070 | 3 | 2 |  | 2027-06-24 | 2027-07-02 | 2027-07-02 | UG-11B-S13-A080
UG-11A-S04-A090 | AW.PIPE.F6.UG-11A.UG-11A-S04 | F6 | UG-11A | UG-11A-S04 | A090 | Surround, joint test and line test | 39.672 | m | 3 | 4 | UG-11A-S04-A080 | 1 | 2 |  | 2027-06-25 | 2027-07-04
UG-11A-S04-A100 | AW.PIPE.F6.UG-11A.UG-11A-S04 | F6 | UG-11A | UG-11A-S04 | A100 | Backfill to NG and remove struts | 375.5604 | m3 | 2 | 3 | UG-11A-S04-A090 | 2 | 2 |  | 2027-06-27 | 2027-07-06 | 2027-07-06 | UG-11B-S13-A100
UG-11A-S04-A110 | AW.PIPE.F6.UG-11A.UG-11A-S04 | F6 | UG-11A | UG-11A-S04 | A110 | Dewatering off, extract sheets, reinstate | 79.3441 | m wall | 3 | 4 | UG-11A-S04-A100 | 1 | 2 |  | 2027-06-28 | 2027-07-08
UG-11A-S03-A010 | AW.PIPE.F6.UG-11A.UG-11A-S03 | F6 | UG-11A | UG-11A-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11A-S03-A020 | AW.PIPE.F6.UG-11A.UG-11A-S03 | F6 | UG-11A | UG-11A-S03 | A020 | Set-out, crossing survey and working platform | 29.728 | m | 1 | 2 | UG-11A-S03-A010 |  |  | FS from A010; UG-11A-S04-A030 (SS, set-out one package ahead of piling) | 2027-04-12 | 2027-04-14
UG-11A-S03-A030 | AW.PIPE.F6.UG-11A.UG-11A-S03 | F6 | UG-11A | UG-11A-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 22 | piles | 5 | 6 | UG-11A-S03-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-19 | 2027-04-25 | 2027-04-25 | UG-11A-S04-A030
UG-11A-S03-A040 | AW.PIPE.F6.UG-11A.UG-11A-S03 | F6 | UG-11A | UG-11A-S03 | A040 | Install sheet piles (shored lengths) | 59.4559 | m wall | 3 | 4 | UG-11A-S03-A030 | 2 | 2 |  | 2027-04-21 | 2027-04-27 | 2027-04-27 | UG-11A-S04-A040
UG-11A-S03-A050 | AW.PIPE.F6.UG-11A.UG-11A-S03 | F6 | UG-11A | UG-11A-S03 | A050 | Install dewatering and draw down | 29.728 | m | 8 | 10 | UG-11A-S03-A040 | 2 | 2 | UG-11A-S04-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-23 | 2027-05-03
UG-11A-S03-A060 | AW.PIPE.F6.UG-11A.UG-11A-S03 | F6 | UG-11A | UG-11A-S03 | A060 | Excavate and strut to formation | 362.8145 | m3 | 2 | 3 | UG-11A-S03-A050 | 10 | 2 |  | 2027-05-03 | 2027-05-06 | 2027-05-06 | UG-11A-S04-A060
UG-11A-S03-A070 | AW.PIPE.F6.UG-11A.UG-11A-S03 | F6 | UG-11A | UG-11A-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 29.728 | m | 6 | 7 | UG-11A-S03-A060 | 1 | 2 |  | 2027-06-30 | 2027-07-07 | 2027-07-07 | UG-11A-S04-A070
UG-11A-S03-A080 | AW.PIPE.F6.UG-11A.UG-11A-S03 | F6 | UG-11A | UG-11A-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 29.728 | m | 3 | 4 | UG-11A-S03-A070 | 3 | 2 |  | 2027-07-03 | 2027-07-09 | 2027-07-09 | UG-11A-S04-A080
UG-11A-S03-A090 | AW.PIPE.F6.UG-11A.UG-11A-S03 | F6 | UG-11A | UG-11A-S03 | A090 | Surround, joint test and line test | 29.728 | m | 3 | 4 | UG-11A-S03-A080 | 2 | 2 |  | 2027-07-05 | 2027-07-11
UG-11A-S03-A100 | AW.PIPE.F6.UG-11A.UG-11A-S03 | F6 | UG-11A | UG-11A-S03 | A100 | Backfill to NG and remove struts | 281.4013 | m3 | 1 | 2 | UG-11A-S03-A090 | 2 | 2 |  | 2027-07-07 | 2027-07-13 | 2027-07-13 | UG-11A-S04-A100
UG-11A-S03-A110 | AW.PIPE.F6.UG-11A.UG-11A-S03 | F6 | UG-11A | UG-11A-S03 | A110 | Dewatering off, extract sheets, reinstate | 59.4559 | m wall | 3 | 4 | UG-11A-S03-A100 | 1 | 2 |  | 2027-07-08 | 2027-07-15
UG-11A-S02-A010 | AW.PIPE.F6.UG-11A.UG-11A-S02 | F6 | UG-11A | UG-11A-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11A-S02-A020 | AW.PIPE.F6.UG-11A.UG-11A-S02 | F6 | UG-11A | UG-11A-S02 | A020 | Set-out, crossing survey and working platform | 48.3 | m | 1 | 2 | UG-11A-S02-A010 |  |  | FS from A010; UG-11A-S03-A030 (SS, set-out one package ahead of piling) | 2027-04-19 | 2027-04-21
UG-11A-S02-A030 | AW.PIPE.F6.UG-11A.UG-11A-S02 | F6 | UG-11A | UG-11A-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 36 | piles | 8 | 10 | UG-11A-S02-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-25 | 2027-05-05 | 2027-05-05 | UG-11A-S03-A030
UG-11A-S02-A040 | AW.PIPE.F6.UG-11A.UG-11A-S02 | F6 | UG-11A | UG-11A-S02 | A040 | Install sheet piles (shored lengths) | 96.6 | m wall | 4 | 5 | UG-11A-S02-A030 | 3 | 2 |  | 2027-04-28 | 2027-05-07 | 2027-05-07 | UG-11A-S03-A040
UG-11A-S02-A050 | AW.PIPE.F6.UG-11A.UG-11A-S02 | F6 | UG-11A | UG-11A-S02 | A050 | Install dewatering and draw down | 48.3 | m | 9 | 11 | UG-11A-S02-A040 | 2 | 2 | UG-11A-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-30 | 2027-05-11
UG-11A-S02-A060 | AW.PIPE.F6.UG-11A.UG-11A-S02 | F6 | UG-11A | UG-11A-S02 | A060 | Excavate and strut to formation | 528.4907 | m3 | 3 | 4 | UG-11A-S02-A050 | 10 | 2 |  | 2027-05-10 | 2027-05-14 | 2027-05-14 | UG-11A-S03-A060
UG-11A-S02-A070 | AW.PIPE.F6.UG-11A.UG-11A-S02 | F6 | UG-11A | UG-11A-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 48.3 | m | 8 | 10 | UG-11A-S02-A060 | 2 | 2 |  | 2027-07-07 | 2027-07-17 | 2027-07-17 | UG-11A-S03-A070
UG-11A-S02-A080 | AW.PIPE.F6.UG-11A.UG-11A-S02 | F6 | UG-11A | UG-11A-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 48.3 | m | 3 | 4 | UG-11A-S02-A070 | 3 | 2 |  | 2027-07-10 | 2027-07-19 | 2027-07-19 | UG-11A-S03-A080
UG-11A-S02-A090 | AW.PIPE.F6.UG-11A.UG-11A-S02 | F6 | UG-11A | UG-11A-S02 | A090 | Surround, joint test and line test | 48.3 | m | 3 | 4 | UG-11A-S02-A080 | 2 | 2 |  | 2027-07-12 | 2027-07-21
UG-11A-S02-A100 | AW.PIPE.F6.UG-11A.UG-11A-S02 | F6 | UG-11A | UG-11A-S02 | A100 | Backfill to NG and remove struts | 424.7881 | m3 | 2 | 3 | UG-11A-S02-A090 | 2 | 2 | UG-14G-S01-A080 (FS, shared trench laid) | 2027-07-14 | 2027-07-23 | 2027-07-23 | UG-11A-S03-A100
UG-11A-S02-A110 | AW.PIPE.F6.UG-11A.UG-11A-S02 | F6 | UG-11A | UG-11A-S02 | A110 | Dewatering off, extract sheets, reinstate | 96.6 | m wall | 3 | 4 | UG-11A-S02-A100 | 1 | 2 |  | 2027-07-15 | 2027-07-25
UG-11A-S01-A010 | AW.PIPE.F6.UG-11A.UG-11A-S01 | F6 | UG-11A | UG-11A-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-11A-S01-A020 | AW.PIPE.F6.UG-11A.UG-11A-S01 | F6 | UG-11A | UG-11A-S01 | A020 | Set-out, crossing survey and working platform | 6 | m | 1 | 2 | UG-11A-S01-A010 |  |  | FS from A010; UG-11A-S02-A030 (SS, tie-in team follows the adjacent run) | 2027-04-25 | 2027-04-27
UG-11A-S01-A030 | AW.PIPE.F6.UG-11A.UG-11A-S01 | F6 | UG-11A | UG-11A-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 3 | piles | 1 | 2 | UG-11A-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-26 | 2027-04-29 | 2027-04-29
UG-11A-S01-A040 | AW.PIPE.F6.UG-11A.UG-11A-S01 | F6 | UG-11A | UG-11A-S01 | A040 | Install sheet piles (shored lengths) | 12 | m wall | 1 | 2 | UG-11A-S01-A030 | 1 | 2 |  | 2027-04-27 | 2027-05-01 | 2027-05-01
UG-11A-S01-A050 | AW.PIPE.F6.UG-11A.UG-11A-S01 | F6 | UG-11A | UG-11A-S01 | A050 | Install dewatering and draw down | 6 | m | 8 | 10 | UG-11A-S01-A040 | 1 | 2 |  | 2027-04-28 | 2027-05-08
UG-11A-S01-A060 | AW.PIPE.F6.UG-11A.UG-11A-S01 | F6 | UG-11A | UG-11A-S01 | A060 | Excavate and strut to formation | 61.0196 | m3 | 1 | 2 | UG-11A-S01-A050 | 10 | 2 |  | 2027-05-08 | 2027-05-10 | 2027-05-10
UG-11A-S01-A070 | AW.PIPE.F6.UG-11A.UG-11A-S01 | F6 | UG-11A | UG-11A-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6 | m | 4 | 5 | UG-11A-S01-A060 | 1 | 2 |  | 2027-05-09 | 2027-05-14 | 2027-05-14
UG-11A-S01-A080 | AW.PIPE.F6.UG-11A.UG-11A-S01 | F6 | UG-11A | UG-11A-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6 | m | 4 | 5 | UG-11A-S01-A070 | 2 | 2 | UG-11A-S02-A080 (FS, closure) | 2027-07-19 | 2027-07-24 | 2027-07-24
UG-11A-S01-A090 | AW.PIPE.F6.UG-11A.UG-11A-S01 | F6 | UG-11A | UG-11A-S01 | A090 | Surround, joint test and line test | 6 | m | 3 | 4 | UG-11A-S01-A080 | 2 | 2 |  | 2027-07-21 | 2027-07-26
UG-11A-S01-A100 | AW.PIPE.F6.UG-11A.UG-11A-S01 | F6 | UG-11A | UG-11A-S01 | A100 | Backfill to NG and remove struts | 50.3074 | m3 | 1 | 2 | UG-11A-S01-A090 | 2 | 2 | UG-14G-S01-A080 (FS, shared trench laid) | 2027-07-23 | 2027-07-28 | 2027-07-28
UG-11A-S01-A110 | AW.PIPE.F6.UG-11A.UG-11A-S01 | F6 | UG-11A | UG-11A-S01 | A110 | Dewatering off, extract sheets, reinstate | 12 | m wall | 2 | 3 | UG-11A-S01-A100 | 1 | 2 |  | 2027-07-24 | 2027-07-30
UG-14G-S01-A010 | AW.PIPE.F6.UG-14G.UG-14G-S01 | F6 | UG-14G | UG-14G-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-14G-S01-A020 | AW.PIPE.F6.UG-14G.UG-14G-S01 | F6 | UG-14G | UG-14G-S01 | A020 | Set-out, crossing survey and working platform | 38.2988 | m | 1 | 2 | UG-14G-S01-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-14G-S01-A030 | AW.PIPE.F6.UG-14G.UG-14G-S01 | F6 | UG-14G | UG-14G-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 28 | piles | 6 | 7 | UG-14G-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-09 | 2026-12-09
UG-14G-S01-A040 | AW.PIPE.F6.UG-14G.UG-14G-S01 | F6 | UG-14G | UG-14G-S01 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-14G-S01-A030 | 3 | 0 |  | 2026-12-05 | 2026-12-09 | 0
UG-14G-S01-A050 | AW.PIPE.F6.UG-14G.UG-14G-S01 | F6 | UG-14G | UG-14G-S01 | A050 | Install dewatering and draw down | 38.2988 | m | 8 | 10 | UG-14G-S01-A040 | 0 | 2 |  | 2026-12-05 | 2026-12-15
UG-14G-S01-A060 | AW.PIPE.F6.UG-14G.UG-14G-S01 | F6 | UG-14G | UG-14G-S01 | A060 | Excavate and strut to formation | 988.5207 | m3 | 3 | 4 | UG-14G-S01-A050 | 10 | 2 | UG-13B-S02-A100 (FS, deeper first); UG-13B-S03-A100 (FS, deeper first); UG-11A-S01-A060 (SS, shared trench); UG-11A-S02-A060 (SS, shared trench) | 2027-05-24 | 2027-05-28 | 2027-05-28
UG-14G-S01-A070 | AW.PIPE.F6.UG-14G.UG-14G-S01 | F6 | UG-14G | UG-14G-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 38.2988 | m | 7 | 9 | UG-14G-S01-A060 | 2 | 2 |  | 2027-05-26 | 2027-06-04 | 2027-06-04
UG-14G-S01-A080 | AW.PIPE.F6.UG-14G.UG-14G-S01 | F6 | UG-14G | UG-14G-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 38.2988 | m | 9 | 11 | UG-14G-S01-A070 | 3 | 2 |  | 2027-05-29 | 2027-06-09 | 2027-06-09
UG-14G-S01-A090 | AW.PIPE.F6.UG-14G.UG-14G-S01 | F6 | UG-14G | UG-14G-S01 | A090 | Surround, joint test and line test | 38.2988 | m | 3 | 4 | UG-14G-S01-A080 | 4 | 2 |  | 2027-06-02 | 2027-06-11
UG-14G-S01-A100 | AW.PIPE.F6.UG-14G.UG-14G-S01 | F6 | UG-14G | UG-14G-S01 | A100 | Backfill to NG and remove struts | 873.6972 | m3 | 3 | 4 | UG-14G-S01-A090 | 2 | 2 | UG-11A-S01-A080 (FS, shared trench laid); UG-11A-S02-A080 (FS, shared trench laid) | 2027-07-24 | 2027-07-28 | 2027-07-28
UG-14G-S01-A110 | AW.PIPE.F6.UG-14G.UG-14G-S01 | F6 | UG-14G | UG-14G-S01 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-14G-S01-A100 | 2 | 2 |  | 2027-07-26 | 2027-07-30
UG-11A-S07-A010 | AW.PIPE.F6.UG-11A.UG-11A-S07 | F6 | UG-11A | UG-11A-S07 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11A-S07-A020 | AW.PIPE.F6.UG-11A.UG-11A-S07 | F6 | UG-11A | UG-11A-S07 | A020 | Set-out, crossing survey and working platform | 36.1403 | m | 1 | 2 | UG-11A-S07-A010 |  |  | FS from A010; UG-11A-S02-A030 (SS, set-out one package ahead of piling) | 2027-04-25 | 2027-04-27
UG-11A-S07-A030 | AW.PIPE.F6.UG-11A.UG-11A-S07 | F6 | UG-11A | UG-11A-S07 | A030 | Pipe-support piling from platform (incl. integrity tests) | 28 | piles | 6 | 7 | UG-11A-S07-A020 | 1 | 2 | gate: D_PILEDES | 2027-05-05 | 2027-05-12 | 2027-05-12 | UG-11A-S02-A030
UG-11A-S07-A040 | AW.PIPE.F6.UG-11A.UG-11A-S07 | F6 | UG-11A | UG-11A-S07 | A040 | Install sheet piles (shored lengths) | 72.2806 | m wall | 3 | 4 | UG-11A-S07-A030 | 3 | 2 |  | 2027-05-08 | 2027-05-14 | 2027-05-14 | UG-11A-S02-A040
UG-11A-S07-A050 | AW.PIPE.F6.UG-11A.UG-11A-S07 | F6 | UG-11A | UG-11A-S07 | A050 | Install dewatering and draw down | 36.1403 | m | 8 | 10 | UG-11A-S07-A040 | 2 | 2 | UG-11A-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-05-10 | 2027-05-20
UG-11A-S07-A060 | AW.PIPE.F6.UG-11A.UG-11A-S07 | F6 | UG-11A | UG-11A-S07 | A060 | Excavate and strut to formation | 370.217 | m3 | 2 | 3 | UG-11A-S07-A050 | 10 | 2 |  | 2027-05-20 | 2027-05-23 | 2027-05-23 | UG-11A-S02-A060
UG-11A-S07-A070 | AW.PIPE.F6.UG-11A.UG-11A-S07 | F6 | UG-11A | UG-11A-S07 | A070 | Trim piles, blinding and piled slab (incl. cure) | 36.1403 | m | 7 | 9 | UG-11A-S07-A060 | 1 | 2 |  | 2027-07-17 | 2027-07-26 | 2027-07-26 | UG-11A-S02-A070
UG-11A-S07-A080 | AW.PIPE.F6.UG-11A.UG-11A-S07 | F6 | UG-11A | UG-11A-S07 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 36.1403 | m | 3 | 4 | UG-11A-S07-A070 | 3 | 2 |  | 2027-07-20 | 2027-07-28 | 2027-07-28 | UG-11A-S02-A080
UG-11A-S07-A090 | AW.PIPE.F6.UG-11A.UG-11A-S07 | F6 | UG-11A | UG-11A-S07 | A090 | Surround, joint test and line test | 36.1403 | m | 3 | 4 | UG-11A-S07-A080 | 2 | 2 |  | 2027-07-22 | 2027-07-30
UG-11A-S07-A100 | AW.PIPE.F6.UG-11A.UG-11A-S07 | F6 | UG-11A | UG-11A-S07 | A100 | Backfill to NG and remove struts | 304.5 | m3 | 1 | 2 | UG-11A-S07-A090 | 2 | 2 | UG-14H-S01-A080 (FS, shared trench laid) | 2027-07-24 | 2027-08-01 | 2027-08-01 | UG-11A-S02-A100
UG-11A-S07-A110 | AW.PIPE.F6.UG-11A.UG-11A-S07 | F6 | UG-11A | UG-11A-S07 | A110 | Dewatering off, extract sheets, reinstate | 72.2806 | m wall | 3 | 4 | UG-11A-S07-A100 | 1 | 2 |  | 2027-07-25 | 2027-08-03
UG-11A-S06-A010 | AW.PIPE.F6.UG-11A.UG-11A-S06 | F6 | UG-11A | UG-11A-S06 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-11A-S06-A020 | AW.PIPE.F6.UG-11A.UG-11A-S06 | F6 | UG-11A | UG-11A-S06 | A020 | Set-out, crossing survey and working platform | 6 | m | 1 | 2 | UG-11A-S06-A010 |  |  | FS from A010; UG-11A-S07-A030 (SS, tie-in team follows the adjacent run) | 2027-05-05 | 2027-05-07
UG-11A-S06-A030 | AW.PIPE.F6.UG-11A.UG-11A-S06 | F6 | UG-11A | UG-11A-S06 | A030 | Pipe-support piling from platform (incl. integrity tests) | 3 | piles | 1 | 2 | UG-11A-S06-A020 | 1 | 2 | gate: D_PILEDES | 2027-05-06 | 2027-05-09 | 2027-05-09
UG-11A-S06-A040 | AW.PIPE.F6.UG-11A.UG-11A-S06 | F6 | UG-11A | UG-11A-S06 | A040 | Install sheet piles (shored lengths) | 12 | m wall | 1 | 2 | UG-11A-S06-A030 | 1 | 2 |  | 2027-05-07 | 2027-05-11 | 2027-05-11
UG-11A-S06-A050 | AW.PIPE.F6.UG-11A.UG-11A-S06 | F6 | UG-11A | UG-11A-S06 | A050 | Install dewatering and draw down | 6 | m | 8 | 10 | UG-11A-S06-A040 | 1 | 2 |  | 2027-05-08 | 2027-05-18
UG-11A-S06-A060 | AW.PIPE.F6.UG-11A.UG-11A-S06 | F6 | UG-11A | UG-11A-S06 | A060 | Excavate and strut to formation | 61.0198 | m3 | 1 | 2 | UG-11A-S06-A050 | 10 | 2 |  | 2027-05-18 | 2027-05-20 | 2027-05-20
UG-11A-S06-A070 | AW.PIPE.F6.UG-11A.UG-11A-S06 | F6 | UG-11A | UG-11A-S06 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6 | m | 4 | 5 | UG-11A-S06-A060 | 1 | 2 |  | 2027-05-19 | 2027-05-24 | 2027-05-24
UG-11A-S06-A080 | AW.PIPE.F6.UG-11A.UG-11A-S06 | F6 | UG-11A | UG-11A-S06 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6 | m | 4 | 5 | UG-11A-S06-A070 | 2 | 2 | UG-11A-S07-A080 (FS, closure) | 2027-07-28 | 2027-08-02 | 2027-08-02
UG-11A-S06-A090 | AW.PIPE.F6.UG-11A.UG-11A-S06 | F6 | UG-11A | UG-11A-S06 | A090 | Surround, joint test and line test | 6 | m | 3 | 4 | UG-11A-S06-A080 | 2 | 2 |  | 2027-07-30 | 2027-08-04
UG-11A-S06-A100 | AW.PIPE.F6.UG-11A.UG-11A-S06 | F6 | UG-11A | UG-11A-S06 | A100 | Backfill to NG and remove struts | 50.3075 | m3 | 1 | 2 | UG-11A-S06-A090 | 2 | 2 | UG-14H-S01-A080 (FS, shared trench laid) | 2027-08-01 | 2027-08-06 | 2027-08-06
UG-11A-S06-A110 | AW.PIPE.F6.UG-11A.UG-11A-S06 | F6 | UG-11A | UG-11A-S06 | A110 | Dewatering off, extract sheets, reinstate | 12 | m wall | 2 | 3 | UG-11A-S06-A100 | 1 | 2 |  | 2027-08-02 | 2027-08-08
UG-14H-S01-A010 | AW.PIPE.F6.UG-14H.UG-14H-S01 | F6 | UG-14H | UG-14H-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-14H-S01-A020 | AW.PIPE.F6.UG-14H.UG-14H-S01 | F6 | UG-14H | UG-14H-S01 | A020 | Set-out, crossing survey and working platform | 38.1766 | m | 1 | 2 | UG-14H-S01-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-14H-S01-A030 | AW.PIPE.F6.UG-14H.UG-14H-S01 | F6 | UG-14H | UG-14H-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 28 | piles | 6 | 7 | UG-14H-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-09 | 2026-12-09
UG-14H-S01-A040 | AW.PIPE.F6.UG-14H.UG-14H-S01 | F6 | UG-14H | UG-14H-S01 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-14H-S01-A030 | 3 | 0 |  | 2026-12-05 | 2026-12-09 | 0
UG-14H-S01-A050 | AW.PIPE.F6.UG-14H.UG-14H-S01 | F6 | UG-14H | UG-14H-S01 | A050 | Install dewatering and draw down | 38.1766 | m | 8 | 10 | UG-14H-S01-A040 | 0 | 2 |  | 2026-12-05 | 2026-12-15
UG-14H-S01-A060 | AW.PIPE.F6.UG-14H.UG-14H-S01 | F6 | UG-14H | UG-14H-S01 | A060 | Excavate and strut to formation | 988.3716 | m3 | 3 | 4 | UG-14H-S01-A050 | 10 | 2 | UG-13B-S04-A100 (FS, deeper first); UG-11A-S06-A060 (SS, shared trench); UG-11A-S07-A060 (SS, shared trench) | 2027-05-20 | 2027-05-24 | 2027-05-24
UG-14H-S01-A070 | AW.PIPE.F6.UG-14H.UG-14H-S01 | F6 | UG-14H | UG-14H-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 38.1766 | m | 7 | 9 | UG-14H-S01-A060 | 2 | 2 |  | 2027-05-22 | 2027-05-31 | 2027-05-31
UG-14H-S01-A080 | AW.PIPE.F6.UG-14H.UG-14H-S01 | F6 | UG-14H | UG-14H-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 38.1766 | m | 9 | 11 | UG-14H-S01-A070 | 3 | 2 |  | 2027-05-25 | 2027-06-05 | 2027-06-05
UG-14H-S01-A090 | AW.PIPE.F6.UG-14H.UG-14H-S01 | F6 | UG-14H | UG-14H-S01 | A090 | Surround, joint test and line test | 38.1766 | m | 3 | 4 | UG-14H-S01-A080 | 4 | 2 |  | 2027-05-29 | 2027-06-07
UG-14H-S01-A100 | AW.PIPE.F6.UG-14H.UG-14H-S01 | F6 | UG-14H | UG-14H-S01 | A100 | Backfill to NG and remove struts | 873.634 | m3 | 3 | 4 | UG-14H-S01-A090 | 2 | 2 | UG-11A-S06-A080 (FS, shared trench laid); UG-11A-S07-A080 (FS, shared trench laid) | 2027-08-02 | 2027-08-06 | 2027-08-06
UG-14H-S01-A110 | AW.PIPE.F6.UG-14H.UG-14H-S01 | F6 | UG-14H | UG-14H-S01 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-14H-S01-A100 | 2 | 2 |  | 2027-08-04 | 2027-08-08
UG-12-S04-A010 | AW.PIPE.F7.UG-12.UG-12-S04 | F7 | UG-12 | UG-12-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-12-S04-A020 | AW.PIPE.F7.UG-12.UG-12-S04 | F7 | UG-12 | UG-12-S04 | A020 | Set-out, crossing survey and working platform | 42.1 | m | 1 | 2 | UG-12-S04-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-12-S04-A030 | AW.PIPE.F7.UG-12.UG-12-S04 | F7 | UG-12 | UG-12-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 32 | piles | 7 | 9 | UG-12-S04-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-11 | 2026-12-11
UG-12-S04-A040 | AW.PIPE.F7.UG-12.UG-12-S04 | F7 | UG-12 | UG-12-S04 | A040 | Install sheet piles (shored lengths) | 84.2 | m wall | 4 | 5 | UG-12-S04-A030 | 3 | 2 |  | 2026-12-05 | 2026-12-13 | 2026-12-13
UG-12-S04-A050 | AW.PIPE.F7.UG-12.UG-12-S04 | F7 | UG-12 | UG-12-S04 | A050 | Install dewatering and draw down | 42.1 | m | 9 | 11 | UG-12-S04-A040 | 2 | 2 |  | 2026-12-07 | 2026-12-18
UG-12-S04-A060 | AW.PIPE.F7.UG-12.UG-12-S04 | F7 | UG-12 | UG-12-S04 | A060 | Excavate and strut to formation | 952.3387 | m3 | 4 | 5 | UG-12-S04-A050 | 10 | 2 |  | 2026-12-17 | 2026-12-22 | 2026-12-22
UG-12-S04-A070 | AW.PIPE.F7.UG-12.UG-12-S04 | F7 | UG-12 | UG-12-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 42.1 | m | 7 | 9 | UG-12-S04-A060 | 2 | 2 |  | 2026-12-19 | 2026-12-28 | 2026-12-28
UG-12-S04-A080 | AW.PIPE.F7.UG-12.UG-12-S04 | F7 | UG-12 | UG-12-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 42.1 | m | 3 | 4 | UG-12-S04-A070 | 3 | 2 |  | 2026-12-22 | 2026-12-30 | 2026-12-30
UG-12-S04-A090 | AW.PIPE.F7.UG-12.UG-12-S04 | F7 | UG-12 | UG-12-S04 | A090 | Surround, joint test and line test | 42.1 | m | 3 | 4 | UG-12-S04-A080 | 2 | 2 |  | 2026-12-24 | 2027-01-01
UG-12-S04-A100 | AW.PIPE.F7.UG-12.UG-12-S04 | F7 | UG-12 | UG-12-S04 | A100 | Backfill to NG and remove struts | 746.0965 | m3 | 3 | 4 | UG-12-S04-A090 | 2 | 2 | UG-13B-S05-A080 (FS, shared trench laid) | 2027-01-10 | 2027-01-14 | 2027-01-14
UG-12-S04-A110 | AW.PIPE.F7.UG-12.UG-12-S04 | F7 | UG-12 | UG-12-S04 | A110 | Dewatering off, extract sheets, reinstate | 84.2 | m wall | 3 | 4 | UG-12-S04-A100 | 2 | 2 |  | 2027-01-12 | 2027-01-16
UG-13B-S05-A010 | AW.PIPE.F7.UG-13B.UG-13B-S05 | F7 | UG-13B | UG-13B-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13B-S05-A020 | AW.PIPE.F7.UG-13B.UG-13B-S05 | F7 | UG-13B | UG-13B-S05 | A020 | Set-out, crossing survey and working platform | 64.1 | m | 1 | 2 | UG-13B-S05-A010 |  |  | FS from A010; UG-12-S04-A030 (SS, set-out one package ahead of piling) | 2026-12-02 | 2026-12-04
UG-13B-S05-A030 | AW.PIPE.F7.UG-13B.UG-13B-S05 | F7 | UG-13B | UG-13B-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 23 | piles | 5 | 6 | UG-13B-S05-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-11 | 2026-12-17 | 2026-12-17 | UG-12-S04-A030
UG-13B-S05-A040 | AW.PIPE.F7.UG-13B.UG-13B-S05 | F7 | UG-13B | UG-13B-S05 | A040 | Install sheet piles (shored lengths) | 128.2 | m wall | 6 | 7 | UG-13B-S05-A030 | 2 | 2 |  | 2026-12-13 | 2026-12-20 | 2026-12-20 | UG-12-S04-A040
UG-13B-S05-A050 | AW.PIPE.F7.UG-13B.UG-13B-S05 | F7 | UG-13B | UG-13B-S05 | A050 | Install dewatering and draw down | 64.1 | m | 9 | 11 | UG-13B-S05-A040 | 3 | 2 | UG-12-S04-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2026-12-16 | 2026-12-27
UG-13B-S05-A060 | AW.PIPE.F7.UG-13B.UG-13B-S05 | F7 | UG-13B | UG-13B-S05 | A060 | Excavate and strut to formation | 790.4793 | m3 | 4 | 5 | UG-13B-S05-A050 | 10 | 2 | UG-12-S04-A060 (SS, shared trench) | 2026-12-26 | 2026-12-31 | 2026-12-31 | UG-12-S04-A060
UG-13B-S05-A070 | AW.PIPE.F7.UG-13B.UG-13B-S05 | F7 | UG-13B | UG-13B-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 64.1 | m | 9 | 11 | UG-13B-S05-A060 | 2 | 2 |  | 2026-12-28 | 2027-01-08 | 2027-01-08 | UG-12-S04-A070
UG-13B-S05-A080 | AW.PIPE.F7.UG-13B.UG-13B-S05 | F7 | UG-13B | UG-13B-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 64.1 | m | 4 | 5 | UG-13B-S05-A070 | 4 | 2 |  | 2027-01-01 | 2027-01-10 | 2027-01-10 | UG-12-S04-A080
UG-13B-S05-A090 | AW.PIPE.F7.UG-13B.UG-13B-S05 | F7 | UG-13B | UG-13B-S05 | A090 | Surround, joint test and line test | 64.1 | m | 3 | 4 | UG-13B-S05-A080 | 2 | 2 |  | 2027-01-03 | 2027-01-12
UG-13B-S05-A100 | AW.PIPE.F7.UG-13B.UG-13B-S05 | F7 | UG-13B | UG-13B-S05 | A100 | Backfill to NG and remove struts | 676.053 | m3 | 2 | 3 | UG-13B-S05-A090 | 2 | 2 | UG-12-S04-A080 (FS, shared trench laid) | 2027-01-14 | 2027-01-17 | 2027-01-17 | UG-12-S04-A100
UG-13B-S05-A110 | AW.PIPE.F7.UG-13B.UG-13B-S05 | F7 | UG-13B | UG-13B-S05 | A110 | Dewatering off, extract sheets, reinstate | 128.2 | m wall | 4 | 5 | UG-13B-S05-A100 | 1 | 2 |  | 2027-01-15 | 2027-01-20
UG-13-S03-A010 | AW.PIPE.F7.UG-13.UG-13-S03 | F7 | UG-13 | UG-13-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13-S03-A020 | AW.PIPE.F7.UG-13.UG-13-S03 | F7 | UG-13 | UG-13-S03 | A020 | Set-out, crossing survey and working platform | 32.2696 | m | 1 | 2 | UG-13-S03-A010 |  |  | FS from A010; UG-13B-S05-A030 (SS, set-out one package ahead of piling) | 2026-12-11 | 2026-12-13
UG-13-S03-A030 | AW.PIPE.F7.UG-13.UG-13-S03 | F7 | UG-13 | UG-13-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 24 | piles | 5 | 6 | UG-13-S03-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-17 | 2026-12-23 | 2026-12-23 | UG-13B-S05-A030
UG-13-S03-A040 | AW.PIPE.F7.UG-13.UG-13-S03 | F7 | UG-13 | UG-13-S03 | A040 | Install sheet piles (shored lengths) | 64.5392 | m wall | 3 | 4 | UG-13-S03-A030 | 2 | 2 |  | 2026-12-20 | 2026-12-25 | 2026-12-25 | UG-13B-S05-A040
UG-13-S03-A050 | AW.PIPE.F7.UG-13.UG-13-S03 | F7 | UG-13 | UG-13-S03 | A050 | Install dewatering and draw down | 32.2696 | m | 8 | 10 | UG-13-S03-A040 | 2 | 2 | UG-13B-S05-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2026-12-22 | 2027-01-01
UG-13-S03-A060 | AW.PIPE.F7.UG-13.UG-13-S03 | F7 | UG-13 | UG-13-S03 | A060 | Excavate and strut to formation | 673.1069 | m3 | 3 | 4 | UG-13-S03-A050 | 10 | 2 |  | 2027-01-01 | 2027-01-05 | 2027-01-05 | UG-13B-S05-A060
UG-13-S03-A070 | AW.PIPE.F7.UG-13.UG-13-S03 | F7 | UG-13 | UG-13-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 32.2696 | m | 6 | 7 | UG-13-S03-A060 | 2 | 2 |  | 2027-01-08 | 2027-01-15 | 2027-01-15 | UG-13B-S05-A070
UG-13-S03-A080 | AW.PIPE.F7.UG-13.UG-13-S03 | F7 | UG-13 | UG-13-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 32.2696 | m | 3 | 4 | UG-13-S03-A070 | 3 | 2 |  | 2027-01-11 | 2027-01-17 | 2027-01-17 | UG-13B-S05-A080
UG-13-S03-A090 | AW.PIPE.F7.UG-13.UG-13-S03 | F7 | UG-13 | UG-13-S03 | A090 | Surround, joint test and line test | 32.2696 | m | 3 | 4 | UG-13-S03-A080 | 2 | 2 |  | 2027-01-13 | 2027-01-19
UG-13-S03-A100 | AW.PIPE.F7.UG-13.UG-13-S03 | F7 | UG-13 | UG-13-S03 | A100 | Backfill to NG and remove struts | 522.0174 | m3 | 2 | 3 | UG-13-S03-A090 | 2 | 2 |  | 2027-01-17 | 2027-01-21 | 2027-01-21 | UG-13B-S05-A100
UG-13-S03-A110 | AW.PIPE.F7.UG-13.UG-13-S03 | F7 | UG-13 | UG-13-S03 | A110 | Dewatering off, extract sheets, reinstate | 64.5392 | m wall | 3 | 4 | UG-13-S03-A100 | 1 | 2 |  | 2027-01-18 | 2027-01-23
UG-13-S04-A010 | AW.PIPE.F7.UG-13.UG-13-S04 | F7 | UG-13 | UG-13-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13-S04-A020 | AW.PIPE.F7.UG-13.UG-13-S04 | F7 | UG-13 | UG-13-S04 | A020 | Set-out, crossing survey and working platform | 37.2 | m | 1 | 2 | UG-13-S04-A010 |  |  | FS from A010; UG-13-S03-A030 (SS, set-out one package ahead of piling) | 2026-12-17 | 2026-12-19
UG-13-S04-A030 | AW.PIPE.F7.UG-13.UG-13-S04 | F7 | UG-13 | UG-13-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 28 | piles | 6 | 7 | UG-13-S04-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-23 | 2026-12-30 | 2026-12-30 | UG-13-S03-A030
UG-13-S04-A040 | AW.PIPE.F7.UG-13.UG-13-S04 | F7 | UG-13 | UG-13-S04 | A040 | Install sheet piles (shored lengths) | 74.4 | m wall | 3 | 4 | UG-13-S04-A030 | 3 | 2 |  | 2026-12-26 | 2027-01-01 | 2027-01-01 | UG-13-S03-A040
UG-13-S04-A050 | AW.PIPE.F7.UG-13.UG-13-S04 | F7 | UG-13 | UG-13-S04 | A050 | Install dewatering and draw down | 37.2 | m | 8 | 10 | UG-13-S04-A040 | 2 | 2 | UG-13-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2026-12-28 | 2027-01-07
UG-13-S04-A060 | AW.PIPE.F7.UG-13.UG-13-S04 | F7 | UG-13 | UG-13-S04 | A060 | Excavate and strut to formation | 784.8278 | m3 | 4 | 5 | UG-13-S04-A050 | 10 | 2 |  | 2027-01-07 | 2027-01-12 | 2027-01-12 | UG-13-S03-A060
UG-13-S04-A070 | AW.PIPE.F7.UG-13.UG-13-S04 | F7 | UG-13 | UG-13-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 37.2 | m | 7 | 9 | UG-13-S04-A060 | 2 | 2 |  | 2027-01-15 | 2027-01-24 | 2027-01-24 | UG-13-S03-A070
UG-13-S04-A080 | AW.PIPE.F7.UG-13.UG-13-S04 | F7 | UG-13 | UG-13-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 37.2 | m | 2 | 3 | UG-13-S04-A070 | 3 | 2 |  | 2027-01-18 | 2027-01-26 | 2027-01-26 | UG-13-S03-A080
UG-13-S04-A090 | AW.PIPE.F7.UG-13.UG-13-S04 | F7 | UG-13 | UG-13-S04 | A090 | Surround, joint test and line test | 37.2 | m | 3 | 4 | UG-13-S04-A080 | 1 | 2 |  | 2027-01-19 | 2027-01-28
UG-13-S04-A100 | AW.PIPE.F7.UG-13.UG-13-S04 | F7 | UG-13 | UG-13-S04 | A100 | Backfill to NG and remove struts | 606.5291 | m3 | 2 | 3 | UG-13-S04-A090 | 2 | 2 |  | 2027-01-21 | 2027-01-30 | 2027-01-30 | UG-13-S03-A100
UG-13-S04-A110 | AW.PIPE.F7.UG-13.UG-13-S04 | F7 | UG-13 | UG-13-S04 | A110 | Dewatering off, extract sheets, reinstate | 74.4 | m wall | 3 | 4 | UG-13-S04-A100 | 1 | 2 |  | 2027-01-22 | 2027-02-01
UG-12-S03-A010 | AW.PIPE.F7.UG-12.UG-12-S03 | F7 | UG-12 | UG-12-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-12-S03-A020 | AW.PIPE.F7.UG-12.UG-12-S03 | F7 | UG-12 | UG-12-S03 | A020 | Set-out, crossing survey and working platform | 55.2 | m | 1 | 2 | UG-12-S03-A010 |  |  | FS from A010; UG-13-S04-A030 (SS, set-out one package ahead of piling) | 2026-12-23 | 2026-12-25
UG-12-S03-A030 | AW.PIPE.F7.UG-12.UG-12-S03 | F7 | UG-12 | UG-12-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 40 | piles | 8 | 10 | UG-12-S03-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-30 | 2027-01-09 | 2027-01-09 | UG-13-S04-A030
UG-12-S03-A040 | AW.PIPE.F7.UG-12.UG-12-S03 | F7 | UG-12 | UG-12-S03 | A040 | Install sheet piles (shored lengths) | 82.6 | m wall | 4 | 5 | UG-12-S03-A030 | 3 | 2 |  | 2027-01-02 | 2027-01-11 | 2027-01-11 | UG-13-S04-A040
UG-12-S03-A050 | AW.PIPE.F7.UG-12.UG-12-S03 | F7 | UG-12 | UG-12-S03 | A050 | Install dewatering and draw down | 55.2 | m | 9 | 11 | UG-12-S03-A040 | 2 | 2 | UG-13-S04-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-04 | 2027-01-15
UG-12-S03-A060 | AW.PIPE.F7.UG-12.UG-12-S03 | F7 | UG-12 | UG-12-S03 | A060 | Excavate and strut to formation | 1221.8652 | m3 | 5 | 6 | UG-12-S03-A050 | 10 | 2 | UG-13-S03-A100 (FS, deeper first); UG-13-S04-A100 (FS, deeper first) | 2027-01-30 | 2027-02-05 | 2027-02-05 | UG-13-S04-A060
UG-12-S03-A070 | AW.PIPE.F7.UG-12.UG-12-S03 | F7 | UG-12 | UG-12-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 55.2 | m | 8 | 10 | UG-12-S03-A060 | 2 | 2 |  | 2027-02-01 | 2027-02-11 | 2027-02-11 | UG-13-S04-A070
UG-12-S03-A080 | AW.PIPE.F7.UG-12.UG-12-S03 | F7 | UG-12 | UG-12-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 55.2 | m | 5 | 6 | UG-12-S03-A070 | 3 | 2 |  | 2027-02-04 | 2027-02-13 | 2027-02-13 | UG-13-S04-A080
UG-12-S03-A090 | AW.PIPE.F7.UG-12.UG-12-S03 | F7 | UG-12 | UG-12-S03 | A090 | Surround, joint test and line test | 55.2 | m | 3 | 4 | UG-12-S03-A080 | 2 | 2 |  | 2027-02-06 | 2027-02-15
UG-12-S03-A100 | AW.PIPE.F7.UG-12.UG-12-S03 | F7 | UG-12 | UG-12-S03 | A100 | Backfill to NG and remove struts | 951.4461 | m3 | 3 | 4 | UG-12-S03-A090 | 2 | 2 | UG-13B-S06-A080 (FS, shared trench laid); UG-13B-S07-A080 (FS, shared trench laid); UG-13B-S11-A080 (FS, shared trench laid) | 2027-03-07 | 2027-03-11 | 2027-03-11 | UG-13-S04-A100
UG-12-S03-A110 | AW.PIPE.F7.UG-12.UG-12-S03 | F7 | UG-12 | UG-12-S03 | A110 | Dewatering off, extract sheets, reinstate | 82.6 | m wall | 3 | 4 | UG-12-S03-A100 | 2 | 2 |  | 2027-03-09 | 2027-03-13
UG-13B-S11-A010 | AW.PIPE.F7.UG-13B.UG-13B-S11 | F7 | UG-13B | UG-13B-S11 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13B-S11-A020 | AW.PIPE.F7.UG-13B.UG-13B-S11 | F7 | UG-13B | UG-13B-S11 | A020 | Set-out, crossing survey and working platform | 14.5305 | m | 1 | 2 | UG-13B-S11-A010 |  |  | FS from A010; UG-12-S03-A030 (SS, set-out one package ahead of piling) | 2026-12-30 | 2027-01-01
UG-13B-S11-A030 | AW.PIPE.F7.UG-13B.UG-13B-S11 | F7 | UG-13B | UG-13B-S11 | A030 | Pipe-support piling from platform (incl. integrity tests) | 12 | piles | 3 | 4 | UG-13B-S11-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-09 | 2027-01-13 | 2027-01-13 | UG-12-S03-A030
UG-13B-S11-A040 | AW.PIPE.F7.UG-13B.UG-13B-S11 | F7 | UG-13B | UG-13B-S11 | A040 | Install sheet piles (shored lengths) | 29.061 | m wall | 2 | 3 | UG-13B-S11-A030 | 2 | 2 |  | 2027-01-11 | 2027-01-15 | 2027-01-15 | UG-12-S03-A040
UG-13B-S11-A050 | AW.PIPE.F7.UG-13B.UG-13B-S11 | F7 | UG-13B | UG-13B-S11 | A050 | Install dewatering and draw down | 14.5305 | m | 8 | 10 | UG-13B-S11-A040 | 1 | 2 | UG-12-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-26 | 2027-02-05
UG-13B-S11-A060 | AW.PIPE.F7.UG-13B.UG-13B-S11 | F7 | UG-13B | UG-13B-S11 | A060 | Excavate and strut to formation | 242.0777 | m3 | 1 | 2 | UG-13B-S11-A050 | 10 | 2 | UG-12-S03-A060 (SS, shared trench); UG-13-S03-A060 (SS, shared trench); UG-13-S04-A060 (SS, shared trench) | 2027-02-05 | 2027-02-07 | 2027-02-07 | UG-12-S03-A060
UG-13B-S11-A070 | AW.PIPE.F7.UG-13B.UG-13B-S11 | F7 | UG-13B | UG-13B-S11 | A070 | Trim piles, blinding and piled slab (incl. cure) | 14.5305 | m | 5 | 6 | UG-13B-S11-A060 | 1 | 2 |  | 2027-02-11 | 2027-02-17 | 2027-02-17 | UG-12-S03-A070
UG-13B-S11-A080 | AW.PIPE.F7.UG-13B.UG-13B-S11 | F7 | UG-13B | UG-13B-S11 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 14.5305 | m | 1 | 2 | UG-13B-S11-A070 | 2 | 2 |  | 2027-02-13 | 2027-02-19 | 2027-02-19 | UG-12-S03-A080
UG-13B-S11-A090 | AW.PIPE.F7.UG-13B.UG-13B-S11 | F7 | UG-13B | UG-13B-S11 | A090 | Surround, joint test and line test | 14.5305 | m | 3 | 4 | UG-13B-S11-A080 | 1 | 2 |  | 2027-02-14 | 2027-02-21
UG-13B-S11-A100 | AW.PIPE.F7.UG-13B.UG-13B-S11 | F7 | UG-13B | UG-13B-S11 | A100 | Backfill to NG and remove struts | 202.2732 | m3 | 1 | 2 | UG-13B-S11-A090 | 2 | 2 | UG-12-S03-A080 (FS, shared trench laid); UG-13-S03-A080 (FS, shared trench laid); UG-13-S04-A080 (FS, shared trench laid) | 2027-03-11 | 2027-03-13 | 2027-03-13 | UG-12-S03-A100
UG-13B-S11-A110 | AW.PIPE.F7.UG-13B.UG-13B-S11 | F7 | UG-13B | UG-13B-S11 | A110 | Dewatering off, extract sheets, reinstate | 29.061 | m wall | 2 | 3 | UG-13B-S11-A100 | 1 | 2 |  | 2027-03-12 | 2027-03-15
UG-13B-S07-A010 | AW.PIPE.F7.UG-13B.UG-13B-S07 | F7 | UG-13B | UG-13B-S07 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13B-S07-A020 | AW.PIPE.F7.UG-13B.UG-13B-S07 | F7 | UG-13B | UG-13B-S07 | A020 | Set-out, crossing survey and working platform | 25.6651 | m | 1 | 2 | UG-13B-S07-A010 |  |  | FS from A010; UG-13B-S11-A030 (SS, set-out one package ahead of piling) | 2027-01-09 | 2027-01-11
UG-13B-S07-A030 | AW.PIPE.F7.UG-13B.UG-13B-S07 | F7 | UG-13B | UG-13B-S07 | A030 | Pipe-support piling from platform (incl. integrity tests) | 20 | piles | 4 | 5 | UG-13B-S07-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-13 | 2027-01-18 | 2027-01-18 | UG-13B-S11-A030
UG-13B-S07-A040 | AW.PIPE.F7.UG-13B.UG-13B-S07 | F7 | UG-13B | UG-13B-S07 | A040 | Install sheet piles (shored lengths) | 51.3302 | m wall | 3 | 4 | UG-13B-S07-A030 | 2 | 2 |  | 2027-01-15 | 2027-01-20 | 2027-01-20 | UG-13B-S11-A040
UG-13B-S07-A050 | AW.PIPE.F7.UG-13B.UG-13B-S07 | F7 | UG-13B | UG-13B-S07 | A050 | Install dewatering and draw down | 25.6651 | m | 8 | 10 | UG-13B-S07-A040 | 2 | 2 | UG-13B-S11-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-28 | 2027-02-07
UG-13B-S07-A060 | AW.PIPE.F7.UG-13B.UG-13B-S07 | F7 | UG-13B | UG-13B-S07 | A060 | Excavate and strut to formation | 367.6421 | m3 | 2 | 3 | UG-13B-S07-A050 | 10 | 2 | UG-12-S03-A060 (SS, shared trench); UG-12-S04-A060 (SS, shared trench) | 2027-02-07 | 2027-02-10 | 2027-02-10 | UG-13B-S11-A060
UG-13B-S07-A070 | AW.PIPE.F7.UG-13B.UG-13B-S07 | F7 | UG-13B | UG-13B-S07 | A070 | Trim piles, blinding and piled slab (incl. cure) | 25.6651 | m | 6 | 7 | UG-13B-S07-A060 | 1 | 2 |  | 2027-02-17 | 2027-02-24 | 2027-02-24 | UG-13B-S11-A070
UG-13B-S07-A080 | AW.PIPE.F7.UG-13B.UG-13B-S07 | F7 | UG-13B | UG-13B-S07 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 25.6651 | m | 3 | 4 | UG-13B-S07-A070 | 3 | 2 |  | 2027-02-20 | 2027-02-26 | 2027-02-26 | UG-13B-S11-A080
UG-13B-S07-A090 | AW.PIPE.F7.UG-13B.UG-13B-S07 | F7 | UG-13B | UG-13B-S07 | A090 | Surround, joint test and line test | 25.6651 | m | 3 | 4 | UG-13B-S07-A080 | 2 | 2 |  | 2027-02-22 | 2027-02-28
UG-13B-S07-A100 | AW.PIPE.F7.UG-13B.UG-13B-S07 | F7 | UG-13B | UG-13B-S07 | A100 | Backfill to NG and remove struts | 319.6716 | m3 | 1 | 2 | UG-13B-S07-A090 | 2 | 2 | UG-12-S03-A080 (FS, shared trench laid); UG-12-S04-A080 (FS, shared trench laid) | 2027-03-13 | 2027-03-15 | 2027-03-15 | UG-13B-S11-A100
UG-13B-S07-A110 | AW.PIPE.F7.UG-13B.UG-13B-S07 | F7 | UG-13B | UG-13B-S07 | A110 | Dewatering off, extract sheets, reinstate | 51.3302 | m wall | 3 | 4 | UG-13B-S07-A100 | 1 | 2 |  | 2027-03-14 | 2027-03-18
UG-13B-S06-A010 | AW.PIPE.F7.UG-13B.UG-13B-S06 | F7 | UG-13B | UG-13B-S06 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13B-S06-A020 | AW.PIPE.F7.UG-13B.UG-13B-S06 | F7 | UG-13B | UG-13B-S06 | A020 | Set-out, crossing survey and working platform | 37 | m | 1 | 2 | UG-13B-S06-A010 |  |  | FS from A010; UG-13B-S07-A030 (SS, set-out one package ahead of piling) | 2027-01-13 | 2027-01-15
UG-13B-S06-A030 | AW.PIPE.F7.UG-13B.UG-13B-S06 | F7 | UG-13B | UG-13B-S06 | A030 | Pipe-support piling from platform (incl. integrity tests) | 14 | piles | 3 | 4 | UG-13B-S06-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-18 | 2027-01-22 | 2027-01-22 | UG-13B-S07-A030
UG-13B-S06-A040 | AW.PIPE.F7.UG-13B.UG-13B-S06 | F7 | UG-13B | UG-13B-S06 | A040 | Install sheet piles (shored lengths) | 74 | m wall | 3 | 4 | UG-13B-S06-A030 | 2 | 2 |  | 2027-01-20 | 2027-01-24 | 2027-01-24 | UG-13B-S07-A040
UG-13B-S06-A050 | AW.PIPE.F7.UG-13B.UG-13B-S06 | F7 | UG-13B | UG-13B-S06 | A050 | Install dewatering and draw down | 37 | m | 8 | 10 | UG-13B-S06-A040 | 2 | 2 | UG-13B-S07-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-31 | 2027-02-10
UG-13B-S06-A060 | AW.PIPE.F7.UG-13B.UG-13B-S06 | F7 | UG-13B | UG-13B-S06 | A060 | Excavate and strut to formation | 521.6958 | m3 | 3 | 4 | UG-13B-S06-A050 | 10 | 2 | UG-12-S03-A060 (SS, shared trench); UG-12-S04-A060 (SS, shared trench) | 2027-02-10 | 2027-02-14 | 2027-02-14 | UG-13B-S07-A060
UG-13B-S06-A070 | AW.PIPE.F7.UG-13B.UG-13B-S06 | F7 | UG-13B | UG-13B-S06 | A070 | Trim piles, blinding and piled slab (incl. cure) | 37 | m | 7 | 9 | UG-13B-S06-A060 | 2 | 2 |  | 2027-02-24 | 2027-03-05 | 2027-03-05 | UG-13B-S07-A070
UG-13B-S06-A080 | AW.PIPE.F7.UG-13B.UG-13B-S06 | F7 | UG-13B | UG-13B-S06 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 37 | m | 2 | 3 | UG-13B-S06-A070 | 3 | 2 |  | 2027-02-27 | 2027-03-07 | 2027-03-07 | UG-13B-S07-A080
UG-13B-S06-A090 | AW.PIPE.F7.UG-13B.UG-13B-S06 | F7 | UG-13B | UG-13B-S06 | A090 | Surround, joint test and line test | 37 | m | 3 | 4 | UG-13B-S06-A080 | 1 | 2 |  | 2027-02-28 | 2027-03-09
UG-13B-S06-A100 | AW.PIPE.F7.UG-13B.UG-13B-S06 | F7 | UG-13B | UG-13B-S06 | A100 | Backfill to NG and remove struts | 455.6361 | m3 | 2 | 3 | UG-13B-S06-A090 | 2 | 2 | UG-07A-S11-A080 (FS, shared trench laid); UG-12-S03-A080 (FS, shared trench laid); UG-12-S04-A080 (FS, shared trench laid) | 2027-03-28 | 2027-03-31 | 2027-03-31 | UG-13B-S07-A100
UG-13B-S06-A110 | AW.PIPE.F7.UG-13B.UG-13B-S06 | F7 | UG-13B | UG-13B-S06 | A110 | Dewatering off, extract sheets, reinstate | 74 | m wall | 3 | 4 | UG-13B-S06-A100 | 1 | 2 |  | 2027-03-29 | 2027-04-02
UG-07A-S11-A010 | AW.PIPE.F7.UG-07A.UG-07A-S11 | F7 | UG-07A | UG-07A-S11 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-07A-S11-A020 | AW.PIPE.F7.UG-07A.UG-07A-S11 | F7 | UG-07A | UG-07A-S11 | A020 | Set-out, crossing survey and working platform | 40.8001 | m | 1 | 2 | UG-07A-S11-A010 |  |  | FS from A010; UG-13B-S06-A030 (SS, set-out one package ahead of piling) | 2027-01-18 | 2027-01-20
UG-07A-S11-A030 | AW.PIPE.F7.UG-07A.UG-07A-S11 | F7 | UG-07A | UG-07A-S11 | A030 | Pipe-support piling from platform (incl. integrity tests) | 30 | piles | 6 | 7 | UG-07A-S11-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-22 | 2027-01-29 | 2027-01-29 | UG-13B-S06-A030
UG-07A-S11-A040 | AW.PIPE.F7.UG-07A.UG-07A-S11 | F7 | UG-07A | UG-07A-S11 | A040 | Install sheet piles (shored lengths) | 79.008 | m wall | 4 | 5 | UG-07A-S11-A030 | 3 | 2 |  | 2027-01-25 | 2027-01-31 | 2027-01-31 | UG-13B-S06-A040
UG-07A-S11-A050 | AW.PIPE.F7.UG-07A.UG-07A-S11 | F7 | UG-07A | UG-07A-S11 | A050 | Install dewatering and draw down | 40.8001 | m | 9 | 11 | UG-07A-S11-A040 | 2 | 2 | UG-13B-S06-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-02-03 | 2027-02-14
UG-07A-S11-A060 | AW.PIPE.F7.UG-07A.UG-07A-S11 | F7 | UG-07A | UG-07A-S11 | A060 | Excavate and strut to formation | 533.1521 | m3 | 3 | 4 | UG-07A-S11-A050 | 10 | 2 | UG-12-S04-A100 (FS, deeper first); UG-12-S05-A100 (FS, deeper first); UG-13B-S07-A100 (FS, deeper first); UG-13B-S05-A060 (SS, shared trench); UG-13B-S06-A060 (SS, shared trench) | 2027-03-15 | 2027-03-19 | 2027-03-19 | UG-13B-S06-A060
UG-07A-S11-A070 | AW.PIPE.F7.UG-07A.UG-07A-S11 | F7 | UG-07A | UG-07A-S11 | A070 | Trim piles, blinding and piled slab (incl. cure) | 40.8001 | m | 7 | 9 | UG-07A-S11-A060 | 2 | 2 |  | 2027-03-17 | 2027-03-26 | 2027-03-26 | UG-13B-S06-A070
UG-07A-S11-A080 | AW.PIPE.F7.UG-07A.UG-07A-S11 | F7 | UG-07A | UG-07A-S11 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 40.8001 | m | 3 | 4 | UG-07A-S11-A070 | 3 | 2 |  | 2027-03-20 | 2027-03-28 | 2027-03-28 | UG-13B-S06-A080
UG-07A-S11-A090 | AW.PIPE.F7.UG-07A.UG-07A-S11 | F7 | UG-07A | UG-07A-S11 | A090 | Surround, joint test and line test | 40.8001 | m | 3 | 4 | UG-07A-S11-A080 | 2 | 2 |  | 2027-03-22 | 2027-03-30
UG-07A-S11-A100 | AW.PIPE.F7.UG-07A.UG-07A-S11 | F7 | UG-07A | UG-07A-S11 | A100 | Backfill to NG and remove struts | 442.1279 | m3 | 2 | 3 | UG-07A-S11-A090 | 2 | 2 | UG-13B-S05-A080 (FS, shared trench laid); UG-13B-S06-A080 (FS, shared trench laid) | 2027-03-31 | 2027-04-03 | 2027-04-03 | UG-13B-S06-A100
UG-07A-S11-A110 | AW.PIPE.F7.UG-07A.UG-07A-S11 | F7 | UG-07A | UG-07A-S11 | A110 | Dewatering off, extract sheets, reinstate | 79.008 | m wall | 3 | 4 | UG-07A-S11-A100 | 1 | 2 |  | 2027-04-01 | 2027-04-05
UG-13B-S12-A010 | AW.PIPE.F7.UG-13B.UG-13B-S12 | F7 | UG-13B | UG-13B-S12 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-13B-S12-A020 | AW.PIPE.F7.UG-13B.UG-13B-S12 | F7 | UG-13B | UG-13B-S12 | A020 | Set-out, crossing survey and working platform | 4.9228 | m | 1 | 2 | UG-13B-S12-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-13B-S12-A030 | AW.PIPE.F7.UG-13B.UG-13B-S12 | F7 | UG-13B | UG-13B-S12 | A030 | Pipe-support piling from platform (incl. integrity tests) | 6 | piles | 2 | 3 | UG-13B-S12-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-05 | 2026-12-05
UG-13B-S12-A040 | AW.PIPE.F7.UG-13B.UG-13B-S12 | F7 | UG-13B | UG-13B-S12 | A040 | Install sheet piles (shored lengths) | 9.8456 | m wall | 1 | 2 | UG-13B-S12-A030 | 1 | 2 |  | 2026-12-03 | 2026-12-07 | 2026-12-07
UG-13B-S12-A050 | AW.PIPE.F7.UG-13B.UG-13B-S12 | F7 | UG-13B | UG-13B-S12 | A050 | Install dewatering and draw down | 4.9228 | m | 8 | 10 | UG-13B-S12-A040 | 1 | 2 |  | 2026-12-04 | 2026-12-14
UG-13B-S12-A060 | AW.PIPE.F7.UG-13B.UG-13B-S12 | F7 | UG-13B | UG-13B-S12 | A060 | Excavate and strut to formation | 104.873 | m3 | 1 | 2 | UG-13B-S12-A050 | 10 | 2 |  | 2026-12-14 | 2026-12-16 | 2026-12-16
UG-13B-S12-A070 | AW.PIPE.F7.UG-13B.UG-13B-S12 | F7 | UG-13B | UG-13B-S12 | A070 | Trim piles, blinding and piled slab (incl. cure) | 4.9228 | m | 4 | 5 | UG-13B-S12-A060 | 1 | 2 |  | 2026-12-15 | 2026-12-20 | 2026-12-20
UG-13B-S12-A080 | AW.PIPE.F7.UG-13B.UG-13B-S12 | F7 | UG-13B | UG-13B-S12 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 4.9228 | m | 4 | 5 | UG-13B-S12-A070 | 2 | 2 |  | 2026-12-17 | 2026-12-22 | 2026-12-22
UG-13B-S12-A090 | AW.PIPE.F7.UG-13B.UG-13B-S12 | F7 | UG-13B | UG-13B-S12 | A090 | Surround, joint test and line test | 4.9228 | m | 3 | 4 | UG-13B-S12-A080 | 2 | 2 |  | 2026-12-19 | 2026-12-24
UG-13B-S12-A100 | AW.PIPE.F7.UG-13B.UG-13B-S12 | F7 | UG-13B | UG-13B-S12 | A100 | Backfill to NG and remove struts | 80.7569 | m3 | 1 | 2 | UG-13B-S12-A090 | 2 | 2 | UG-13-S05-A080 (FS, shared trench laid); UG-23-S01-A080 (FS, shared trench laid); UG-23-S02-A080 (FS, shared trench laid); UG-23-S03-A080 (FS, shared trench laid) | 2027-04-23 | 2027-04-25 | 2027-04-25
UG-13B-S12-A110 | AW.PIPE.F7.UG-13B.UG-13B-S12 | F7 | UG-13B | UG-13B-S12 | A110 | Dewatering off, extract sheets, reinstate | 9.8456 | m wall | 2 | 3 | UG-13B-S12-A100 | 1 | 2 |  | 2027-04-24 | 2027-04-27
UG-13-S05-A010 | AW.PIPE.F7.UG-13.UG-13-S05 | F7 | UG-13 | UG-13-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13-S05-A020 | AW.PIPE.F7.UG-13.UG-13-S05 | F7 | UG-13 | UG-13-S05 | A020 | Set-out, crossing survey and working platform | 44.3431 | m | 1 | 2 | UG-13-S05-A010 |  |  | FS from A010; UG-07A-S11-A030 (SS, set-out one package ahead of piling) | 2027-01-22 | 2027-01-24
UG-13-S05-A030 | AW.PIPE.F7.UG-13.UG-13-S05 | F7 | UG-13 | UG-13-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 32 | piles | 7 | 9 | UG-13-S05-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-29 | 2027-02-07 | 2027-02-07 | UG-07A-S11-A030
UG-13-S05-A040 | AW.PIPE.F7.UG-13.UG-13-S05 | F7 | UG-13 | UG-13-S05 | A040 | Install sheet piles (shored lengths) | 88.6862 | m wall | 4 | 5 | UG-13-S05-A030 | 3 | 2 |  | 2027-02-01 | 2027-02-09 | 2027-02-09 | UG-07A-S11-A040
UG-13-S05-A050 | AW.PIPE.F7.UG-13.UG-13-S05 | F7 | UG-13 | UG-13-S05 | A050 | Install dewatering and draw down | 44.3431 | m | 9 | 11 | UG-13-S05-A040 | 2 | 2 | UG-07A-S11-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-08 | 2027-03-19
UG-13-S05-A060 | AW.PIPE.F7.UG-13.UG-13-S05 | F7 | UG-13 | UG-13-S05 | A060 | Excavate and strut to formation | 935.9426 | m3 | 4 | 5 | UG-13-S05-A050 | 10 | 2 | UG-13B-S12-A060 (SS, shared trench) | 2027-03-19 | 2027-03-24 | 2027-03-24 | UG-07A-S11-A060
UG-13-S05-A070 | AW.PIPE.F7.UG-13.UG-13-S05 | F7 | UG-13 | UG-13-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 44.3431 | m | 7 | 9 | UG-13-S05-A060 | 2 | 2 |  | 2027-03-26 | 2027-04-04 | 2027-04-04 | UG-07A-S11-A070
UG-13-S05-A080 | AW.PIPE.F7.UG-13.UG-13-S05 | F7 | UG-13 | UG-13-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 44.3431 | m | 4 | 5 | UG-13-S05-A070 | 3 | 2 |  | 2027-03-29 | 2027-04-06 | 2027-04-06 | UG-07A-S11-A080
UG-13-S05-A090 | AW.PIPE.F7.UG-13.UG-13-S05 | F7 | UG-13 | UG-13-S05 | A090 | Surround, joint test and line test | 44.3431 | m | 3 | 4 | UG-13-S05-A080 | 2 | 2 |  | 2027-03-31 | 2027-04-08
UG-13-S05-A100 | AW.PIPE.F7.UG-13.UG-13-S05 | F7 | UG-13 | UG-13-S05 | A100 | Backfill to NG and remove struts | 723.1949 | m3 | 3 | 4 | UG-13-S05-A090 | 2 | 2 | UG-13B-S12-A080 (FS, shared trench laid); UG-23-S01-A080 (FS, shared trench laid); UG-23-S02-A080 (FS, shared trench laid); UG-23-S03-A080 (FS, shared trench laid) | 2027-04-23 | 2027-04-27 | 2027-04-27 | UG-07A-S11-A100
UG-13-S05-A110 | AW.PIPE.F7.UG-13.UG-13-S05 | F7 | UG-13 | UG-13-S05 | A110 | Dewatering off, extract sheets, reinstate | 88.6862 | m wall | 3 | 4 | UG-13-S05-A100 | 2 | 2 |  | 2027-04-25 | 2027-04-29
UG-23-S03-A010 | AW.PIPE.F7.UG-23.UG-23-S03 | F7 | UG-23 | UG-23-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-23-S03-A020 | AW.PIPE.F7.UG-23.UG-23-S03 | F7 | UG-23 | UG-23-S03 | A020 | Set-out, crossing survey and working platform | 20 | m | 1 | 2 | UG-23-S03-A010 |  |  | FS from A010; UG-13-S05-A030 (SS, set-out one package ahead of piling) | 2027-01-29 | 2027-01-31
UG-23-S03-A030 | AW.PIPE.F7.UG-23.UG-23-S03 | F7 | UG-23 | UG-23-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 8 | piles | 2 | 3 | UG-23-S03-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-07 | 2027-02-10 | 2027-02-10 | UG-13-S05-A030
UG-23-S03-A040 | AW.PIPE.F7.UG-23.UG-23-S03 | F7 | UG-23 | UG-23-S03 | A040 | Install sheet piles (shored lengths) | 40 | m wall | 2 | 3 | UG-23-S03-A030 | 1 | 2 |  | 2027-02-09 | 2027-02-12 | 2027-02-12 | UG-13-S05-A040
UG-23-S03-A050 | AW.PIPE.F7.UG-23.UG-23-S03 | F7 | UG-23 | UG-23-S03 | A050 | Install dewatering and draw down | 20 | m | 8 | 10 | UG-23-S03-A040 | 1 | 2 | UG-13-S05-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-14 | 2027-03-24
UG-23-S03-A060 | AW.PIPE.F7.UG-23.UG-23-S03 | F7 | UG-23 | UG-23-S03 | A060 | Excavate and strut to formation | 230.1248 | m3 | 1 | 2 | UG-23-S03-A050 | 10 | 2 | UG-13-S05-A060 (SS, shared trench); UG-13B-S12-A060 (SS, shared trench) | 2027-03-24 | 2027-03-26 | 2027-03-26 | UG-13-S05-A060
UG-23-S03-A070 | AW.PIPE.F7.UG-23.UG-23-S03 | F7 | UG-23 | UG-23-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 20 | m | 5 | 6 | UG-23-S03-A060 | 1 | 2 |  | 2027-04-04 | 2027-04-10 | 2027-04-10 | UG-13-S05-A070
UG-23-S03-A080 | AW.PIPE.F7.UG-23.UG-23-S03 | F7 | UG-23 | UG-23-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 20 | m | 2 | 3 | UG-23-S03-A070 | 2 | 2 |  | 2027-04-06 | 2027-04-12 | 2027-04-12 | UG-13-S05-A080
UG-23-S03-A090 | AW.PIPE.F7.UG-23.UG-23-S03 | F7 | UG-23 | UG-23-S03 | A090 | Surround, joint test and line test | 20 | m | 3 | 4 | UG-23-S03-A080 | 1 | 2 |  | 2027-04-07 | 2027-04-14
UG-23-S03-A100 | AW.PIPE.F7.UG-23.UG-23-S03 | F7 | UG-23 | UG-23-S03 | A100 | Backfill to NG and remove struts | 207.5903 | m3 | 1 | 2 | UG-23-S03-A090 | 2 | 2 | UG-13-S05-A080 (FS, shared trench laid); UG-13B-S12-A080 (FS, shared trench laid) | 2027-04-27 | 2027-04-29 | 2027-04-29 | UG-13-S05-A100
UG-23-S03-A110 | AW.PIPE.F7.UG-23.UG-23-S03 | F7 | UG-23 | UG-23-S03 | A110 | Dewatering off, extract sheets, reinstate | 40 | m wall | 2 | 3 | UG-23-S03-A100 | 1 | 2 |  | 2027-04-28 | 2027-05-01
UG-23-S02-A010 | AW.PIPE.F7.UG-23.UG-23-S02 | F7 | UG-23 | UG-23-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-23-S02-A020 | AW.PIPE.F7.UG-23.UG-23-S02 | F7 | UG-23 | UG-23-S02 | A020 | Set-out, crossing survey and working platform | 3.6133 | m | 1 | 2 | UG-23-S02-A010 |  |  | FS from A010; UG-23-S03-A030 (SS, set-out one package ahead of piling) | 2027-02-07 | 2027-02-09
UG-23-S02-A030 | AW.PIPE.F7.UG-23.UG-23-S02 | F7 | UG-23 | UG-23-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 3 | piles | 1 | 2 | UG-23-S02-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-10 | 2027-02-12 | 2027-02-12 | UG-23-S03-A030
UG-23-S02-A040 | AW.PIPE.F7.UG-23.UG-23-S02 | F7 | UG-23 | UG-23-S02 | A040 | Install sheet piles (shored lengths) | 7.2266 | m wall | 1 | 2 | UG-23-S02-A030 | 1 | 2 |  | 2027-02-12 | 2027-02-14 | 2027-02-14 | UG-23-S03-A040
UG-23-S02-A050 | AW.PIPE.F7.UG-23.UG-23-S02 | F7 | UG-23 | UG-23-S02 | A050 | Install dewatering and draw down | 3.6133 | m | 8 | 10 | UG-23-S02-A040 | 1 | 2 | UG-23-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-16 | 2027-03-26
UG-23-S02-A060 | AW.PIPE.F7.UG-23.UG-23-S02 | F7 | UG-23 | UG-23-S02 | A060 | Excavate and strut to formation | 41.5753 | m3 | 1 | 2 | UG-23-S02-A050 | 10 | 2 | UG-13-S05-A060 (SS, shared trench); UG-13B-S12-A060 (SS, shared trench) | 2027-03-26 | 2027-03-28 | 2027-03-28 | UG-23-S03-A060
UG-23-S02-A070 | AW.PIPE.F7.UG-23.UG-23-S02 | F7 | UG-23 | UG-23-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 3.6133 | m | 4 | 5 | UG-23-S02-A060 | 1 | 2 |  | 2027-04-10 | 2027-04-15 | 2027-04-15 | UG-23-S03-A070
UG-23-S02-A080 | AW.PIPE.F7.UG-23.UG-23-S02 | F7 | UG-23 | UG-23-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 3.6133 | m | 1 | 2 | UG-23-S02-A070 | 2 | 2 |  | 2027-04-12 | 2027-04-17 | 2027-04-17 | UG-23-S03-A080
UG-23-S02-A090 | AW.PIPE.F7.UG-23.UG-23-S02 | F7 | UG-23 | UG-23-S02 | A090 | Surround, joint test and line test | 3.6133 | m | 3 | 4 | UG-23-S02-A080 | 1 | 2 |  | 2027-04-13 | 2027-04-19
UG-23-S02-A100 | AW.PIPE.F7.UG-23.UG-23-S02 | F7 | UG-23 | UG-23-S02 | A100 | Backfill to NG and remove struts | 37.5042 | m3 | 1 | 2 | UG-23-S02-A090 | 2 | 2 | UG-13-S05-A080 (FS, shared trench laid); UG-13B-S12-A080 (FS, shared trench laid) | 2027-04-29 | 2027-05-01 | 2027-05-01 | UG-23-S03-A100
UG-23-S02-A110 | AW.PIPE.F7.UG-23.UG-23-S02 | F7 | UG-23 | UG-23-S02 | A110 | Dewatering off, extract sheets, reinstate | 7.2266 | m wall | 2 | 3 | UG-23-S02-A100 | 1 | 2 |  | 2027-04-30 | 2027-05-03
UG-23-S01-A010 | AW.PIPE.F7.UG-23.UG-23-S01 | F7 | UG-23 | UG-23-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-23-S01-A020 | AW.PIPE.F7.UG-23.UG-23-S01 | F7 | UG-23 | UG-23-S01 | A020 | Set-out, crossing survey and working platform | 11.3867 | m | 1 | 2 | UG-23-S01-A010 |  |  | FS from A010; UG-23-S02-A030 (SS, tie-in team follows the adjacent run) | 2027-02-10 | 2027-02-12
UG-23-S01-A030 | AW.PIPE.F7.UG-23.UG-23-S01 | F7 | UG-23 | UG-23-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 5 | piles | 1 | 2 | UG-23-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-11 | 2027-02-14 | 2027-02-14
UG-23-S01-A040 | AW.PIPE.F7.UG-23.UG-23-S01 | F7 | UG-23 | UG-23-S01 | A040 | Install sheet piles (shored lengths) | 22.7734 | m wall | 1 | 2 | UG-23-S01-A030 | 1 | 2 |  | 2027-02-12 | 2027-02-16 | 2027-02-16
UG-23-S01-A050 | AW.PIPE.F7.UG-23.UG-23-S01 | F7 | UG-23 | UG-23-S01 | A050 | Install dewatering and draw down | 11.3867 | m | 8 | 10 | UG-23-S01-A040 | 1 | 2 |  | 2027-02-13 | 2027-02-23
UG-23-S01-A060 | AW.PIPE.F7.UG-23.UG-23-S01 | F7 | UG-23 | UG-23-S01 | A060 | Excavate and strut to formation | 131.0181 | m3 | 1 | 2 | UG-23-S01-A050 | 10 | 2 | UG-13-S05-A060 (SS, shared trench); UG-13B-S12-A060 (SS, shared trench) | 2027-03-19 | 2027-03-21 | 2027-03-21
UG-23-S01-A070 | AW.PIPE.F7.UG-23.UG-23-S01 | F7 | UG-23 | UG-23-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 11.3867 | m | 4 | 5 | UG-23-S01-A060 | 1 | 2 |  | 2027-03-20 | 2027-03-25 | 2027-03-25
UG-23-S01-A080 | AW.PIPE.F7.UG-23.UG-23-S01 | F7 | UG-23 | UG-23-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 11.3867 | m | 5 | 6 | UG-23-S01-A070 | 2 | 2 | UG-23-S02-A080 (FS, closure) | 2027-04-17 | 2027-04-23 | 2027-04-23
UG-23-S01-A090 | AW.PIPE.F7.UG-23.UG-23-S01 | F7 | UG-23 | UG-23-S01 | A090 | Surround, joint test and line test | 11.3867 | m | 3 | 4 | UG-23-S01-A080 | 2 | 2 |  | 2027-04-19 | 2027-04-25
UG-23-S01-A100 | AW.PIPE.F7.UG-23.UG-23-S01 | F7 | UG-23 | UG-23-S01 | A100 | Backfill to NG and remove struts | 118.1885 | m3 | 1 | 2 | UG-23-S01-A090 | 2 | 2 | UG-13-S05-A080 (FS, shared trench laid); UG-13B-S12-A080 (FS, shared trench laid) | 2027-04-21 | 2027-04-27 | 2027-04-27
UG-23-S01-A110 | AW.PIPE.F7.UG-23.UG-23-S01 | F7 | UG-23 | UG-23-S01 | A110 | Dewatering off, extract sheets, reinstate | 22.7734 | m wall | 2 | 3 | UG-23-S01-A100 | 1 | 2 |  | 2027-04-22 | 2027-04-29
UG-13B-S09-A010 | AW.PIPE.F7.UG-13B.UG-13B-S09 | F7 | UG-13B | UG-13B-S09 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13B-S09-A020 | AW.PIPE.F7.UG-13B.UG-13B-S09 | F7 | UG-13B | UG-13B-S09 | A020 | Set-out, crossing survey and working platform | 30.038 | m | 1 | 2 | UG-13B-S09-A010 |  |  | FS from A010; UG-23-S02-A030 (SS, set-out one package ahead of piling) | 2027-02-10 | 2027-02-12
UG-13B-S09-A030 | AW.PIPE.F7.UG-13B.UG-13B-S09 | F7 | UG-13B | UG-13B-S09 | A030 | Pipe-support piling from platform (incl. integrity tests) | 12 | piles | 3 | 4 | UG-13B-S09-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-12 | 2027-02-16 | 2027-02-16 | UG-23-S02-A030
UG-13B-S09-A040 | AW.PIPE.F7.UG-13B.UG-13B-S09 | F7 | UG-13B | UG-13B-S09 | A040 | Install sheet piles (shored lengths) | 60.076 | m wall | 3 | 4 | UG-13B-S09-A030 | 2 | 2 |  | 2027-02-14 | 2027-02-18 | 2027-02-18 | UG-23-S02-A040
UG-13B-S09-A050 | AW.PIPE.F7.UG-13B.UG-13B-S09 | F7 | UG-13B | UG-13B-S09 | A050 | Install dewatering and draw down | 30.038 | m | 8 | 10 | UG-13B-S09-A040 | 2 | 2 | UG-23-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-18 | 2027-03-28
UG-13B-S09-A060 | AW.PIPE.F7.UG-13B.UG-13B-S09 | F7 | UG-13B | UG-13B-S09 | A060 | Excavate and strut to formation | 423.5358 | m3 | 2 | 3 | UG-13B-S09-A050 | 10 | 2 |  | 2027-03-28 | 2027-03-31 | 2027-03-31 | UG-23-S02-A060
UG-13B-S09-A070 | AW.PIPE.F7.UG-13B.UG-13B-S09 | F7 | UG-13B | UG-13B-S09 | A070 | Trim piles, blinding and piled slab (incl. cure) | 30.038 | m | 6 | 7 | UG-13B-S09-A060 | 1 | 2 |  | 2027-04-15 | 2027-04-22 | 2027-04-22 | UG-23-S02-A070
UG-13B-S09-A080 | AW.PIPE.F7.UG-13B.UG-13B-S09 | F7 | UG-13B | UG-13B-S09 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 30.038 | m | 1 | 2 | UG-13B-S09-A070 | 3 | 2 |  | 2027-04-18 | 2027-04-24 | 2027-04-24 | UG-23-S02-A080
UG-13B-S09-A090 | AW.PIPE.F7.UG-13B.UG-13B-S09 | F7 | UG-13B | UG-13B-S09 | A090 | Surround, joint test and line test | 30.038 | m | 3 | 4 | UG-13B-S09-A080 | 1 | 2 |  | 2027-04-19 | 2027-04-26
UG-13B-S09-A100 | AW.PIPE.F7.UG-13B.UG-13B-S09 | F7 | UG-13B | UG-13B-S09 | A100 | Backfill to NG and remove struts | 369.906 | m3 | 2 | 3 | UG-13B-S09-A090 | 2 | 2 |  | 2027-05-01 | 2027-05-04 | 2027-05-04 | UG-23-S02-A100
UG-13B-S09-A110 | AW.PIPE.F7.UG-13B.UG-13B-S09 | F7 | UG-13B | UG-13B-S09 | A110 | Dewatering off, extract sheets, reinstate | 60.076 | m wall | 3 | 4 | UG-13B-S09-A100 | 1 | 2 |  | 2027-05-02 | 2027-05-06
UG-13B-S10-A010 | AW.PIPE.F7.UG-13B.UG-13B-S10 | F7 | UG-13B | UG-13B-S10 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-13B-S10-A020 | AW.PIPE.F7.UG-13B.UG-13B-S10 | F7 | UG-13B | UG-13B-S10 | A020 | Set-out, crossing survey and working platform | 6.0001 | m | 1 | 2 | UG-13B-S10-A010 |  |  | FS from A010; UG-13B-S09-A030 (SS, tie-in team follows the adjacent run) | 2027-02-12 | 2027-02-14
UG-13B-S10-A030 | AW.PIPE.F7.UG-13B.UG-13B-S10 | F7 | UG-13B | UG-13B-S10 | A030 | Pipe-support piling from platform (incl. integrity tests) | 4 | piles | 1 | 2 | UG-13B-S10-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-13 | 2027-02-16 | 2027-02-16
UG-13B-S10-A040 | AW.PIPE.F7.UG-13B.UG-13B-S10 | F7 | UG-13B | UG-13B-S10 | A040 | Install sheet piles (shored lengths) | 12.0001 | m wall | 1 | 2 | UG-13B-S10-A030 | 1 | 2 |  | 2027-02-14 | 2027-02-18 | 2027-02-18
UG-13B-S10-A050 | AW.PIPE.F7.UG-13B.UG-13B-S10 | F7 | UG-13B | UG-13B-S10 | A050 | Install dewatering and draw down | 6.0001 | m | 8 | 10 | UG-13B-S10-A040 | 1 | 2 |  | 2027-02-15 | 2027-02-25
UG-13B-S10-A060 | AW.PIPE.F7.UG-13B.UG-13B-S10 | F7 | UG-13B | UG-13B-S10 | A060 | Excavate and strut to formation | 84.6007 | m3 | 1 | 2 | UG-13B-S10-A050 | 10 | 2 |  | 2027-02-25 | 2027-02-27 | 2027-02-27
UG-13B-S10-A070 | AW.PIPE.F7.UG-13B.UG-13B-S10 | F7 | UG-13B | UG-13B-S10 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6.0001 | m | 4 | 5 | UG-13B-S10-A060 | 1 | 2 |  | 2027-02-26 | 2027-03-03 | 2027-03-03
UG-13B-S10-A080 | AW.PIPE.F7.UG-13B.UG-13B-S10 | F7 | UG-13B | UG-13B-S10 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6.0001 | m | 4 | 5 | UG-13B-S10-A070 | 2 | 2 | UG-13B-S09-A080 (FS, closure) | 2027-04-24 | 2027-04-29 | 2027-04-29
UG-13B-S10-A090 | AW.PIPE.F7.UG-13B.UG-13B-S10 | F7 | UG-13B | UG-13B-S10 | A090 | Surround, joint test and line test | 6.0001 | m | 3 | 4 | UG-13B-S10-A080 | 2 | 2 |  | 2027-04-26 | 2027-05-01
UG-13B-S10-A100 | AW.PIPE.F7.UG-13B.UG-13B-S10 | F7 | UG-13B | UG-13B-S10 | A100 | Backfill to NG and remove struts | 73.8883 | m3 | 1 | 2 | UG-13B-S10-A090 | 2 | 2 |  | 2027-04-28 | 2027-05-03 | 2027-05-03
UG-13B-S10-A110 | AW.PIPE.F7.UG-13B.UG-13B-S10 | F7 | UG-13B | UG-13B-S10 | A110 | Dewatering off, extract sheets, reinstate | 12.0001 | m wall | 2 | 3 | UG-13B-S10-A100 | 1 | 2 |  | 2027-04-29 | 2027-05-05
UG-13B-S08-A010 | AW.PIPE.F7.UG-13B.UG-13B-S08 | F7 | UG-13B | UG-13B-S08 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13B-S08-A020 | AW.PIPE.F7.UG-13B.UG-13B-S08 | F7 | UG-13B | UG-13B-S08 | A020 | Set-out, crossing survey and working platform | 16.1415 | m | 1 | 2 | UG-13B-S08-A010 |  |  | FS from A010; UG-13B-S09-A030 (SS, set-out one package ahead of piling) | 2027-02-12 | 2027-02-14
UG-13B-S08-A030 | AW.PIPE.F7.UG-13B.UG-13B-S08 | F7 | UG-13B | UG-13B-S08 | A030 | Pipe-support piling from platform (incl. integrity tests) | 7 | piles | 2 | 3 | UG-13B-S08-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-16 | 2027-02-19 | 2027-02-19 | UG-13B-S09-A030
UG-13B-S08-A040 | AW.PIPE.F7.UG-13B.UG-13B-S08 | F7 | UG-13B | UG-13B-S08 | A040 | Install sheet piles (shored lengths) | 32.283 | m wall | 2 | 3 | UG-13B-S08-A030 | 1 | 2 |  | 2027-02-18 | 2027-02-21 | 2027-02-21 | UG-13B-S09-A040
UG-13B-S08-A050 | AW.PIPE.F7.UG-13B.UG-13B-S08 | F7 | UG-13B | UG-13B-S08 | A050 | Install dewatering and draw down | 16.1415 | m | 8 | 10 | UG-13B-S08-A040 | 1 | 2 | UG-13B-S09-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-21 | 2027-03-31
UG-13B-S08-A060 | AW.PIPE.F7.UG-13B.UG-13B-S08 | F7 | UG-13B | UG-13B-S08 | A060 | Excavate and strut to formation | 227.5191 | m3 | 1 | 2 | UG-13B-S08-A050 | 10 | 2 | UG-12-S03-A100 (FS, deeper first) | 2027-03-31 | 2027-04-02 | 2027-04-02 | UG-13B-S09-A060
UG-13B-S08-A070 | AW.PIPE.F7.UG-13B.UG-13B-S08 | F7 | UG-13B | UG-13B-S08 | A070 | Trim piles, blinding and piled slab (incl. cure) | 16.1415 | m | 5 | 6 | UG-13B-S08-A060 | 1 | 2 |  | 2027-04-22 | 2027-04-28 | 2027-04-28 | UG-13B-S09-A070
UG-13B-S08-A080 | AW.PIPE.F7.UG-13B.UG-13B-S08 | F7 | UG-13B | UG-13B-S08 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 16.1415 | m | 2 | 3 | UG-13B-S08-A070 | 2 | 2 |  | 2027-04-24 | 2027-04-30 | 2027-04-30 | UG-13B-S09-A080
UG-13B-S08-A090 | AW.PIPE.F7.UG-13B.UG-13B-S08 | F7 | UG-13B | UG-13B-S08 | A090 | Surround, joint test and line test | 16.1415 | m | 3 | 4 | UG-13B-S08-A080 | 1 | 2 |  | 2027-04-25 | 2027-05-02
UG-13B-S08-A100 | AW.PIPE.F7.UG-13B.UG-13B-S08 | F7 | UG-13B | UG-13B-S08 | A100 | Backfill to NG and remove struts | 198.7253 | m3 | 1 | 2 | UG-13B-S08-A090 | 2 | 2 |  | 2027-05-04 | 2027-05-06 | 2027-05-06 | UG-13B-S09-A100
UG-13B-S08-A110 | AW.PIPE.F7.UG-13B.UG-13B-S08 | F7 | UG-13B | UG-13B-S08 | A110 | Dewatering off, extract sheets, reinstate | 32.283 | m wall | 2 | 3 | UG-13B-S08-A100 | 1 | 2 |  | 2027-05-05 | 2027-05-08
UG-13B-S04-A010 | AW.PIPE.F7.UG-13B.UG-13B-S04 | F7 | UG-13B | UG-13B-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13B-S04-A020 | AW.PIPE.F7.UG-13B.UG-13B-S04 | F7 | UG-13B | UG-13B-S04 | A020 | Set-out, crossing survey and working platform | 24 | m | 1 | 2 | UG-13B-S04-A010 |  |  | FS from A010; UG-13B-S08-A030 (SS, set-out one package ahead of piling) | 2027-02-16 | 2027-02-18
UG-13B-S04-A030 | AW.PIPE.F7.UG-13B.UG-13B-S04 | F7 | UG-13B | UG-13B-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 20 | piles | 4 | 5 | UG-13B-S04-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-19 | 2027-02-24 | 2027-02-24 | UG-13B-S08-A030
UG-13B-S04-A040 | AW.PIPE.F7.UG-13B.UG-13B-S04 | F7 | UG-13B | UG-13B-S04 | A040 | Install sheet piles (shored lengths) | 48 | m wall | 2 | 3 | UG-13B-S04-A030 | 2 | 2 |  | 2027-02-21 | 2027-02-26 | 2027-02-26 | UG-13B-S08-A040
UG-13B-S04-A050 | AW.PIPE.F7.UG-13B.UG-13B-S04 | F7 | UG-13B | UG-13B-S04 | A050 | Install dewatering and draw down | 24 | m | 8 | 10 | UG-13B-S04-A040 | 1 | 2 | UG-13B-S08-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-23 | 2027-04-02
UG-13B-S04-A060 | AW.PIPE.F7.UG-13B.UG-13B-S04 | F7 | UG-13B | UG-13B-S04 | A060 | Excavate and strut to formation | 244.6939 | m3 | 1 | 2 | UG-13B-S04-A050 | 10 | 2 |  | 2027-04-02 | 2027-04-04 | 2027-04-04 | UG-13B-S08-A060
UG-13B-S04-A070 | AW.PIPE.F7.UG-13B.UG-13B-S04 | F7 | UG-13B | UG-13B-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 24 | m | 6 | 7 | UG-13B-S04-A060 | 1 | 2 |  | 2027-04-28 | 2027-05-05 | 2027-05-05 | UG-13B-S08-A070
UG-13B-S04-A080 | AW.PIPE.F7.UG-13B.UG-13B-S04 | F7 | UG-13B | UG-13B-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 24 | m | 4 | 5 | UG-13B-S04-A070 | 3 | 2 |  | 2027-05-01 | 2027-05-07 | 2027-05-07 | UG-13B-S08-A080
UG-13B-S04-A090 | AW.PIPE.F7.UG-13B.UG-13B-S04 | F7 | UG-13B | UG-13B-S04 | A090 | Surround, joint test and line test | 24 | m | 3 | 4 | UG-13B-S04-A080 | 2 | 2 |  | 2027-05-03 | 2027-05-09
UG-13B-S04-A100 | AW.PIPE.F7.UG-13B.UG-13B-S04 | F7 | UG-13B | UG-13B-S04 | A100 | Backfill to NG and remove struts | 202.001 | m3 | 1 | 2 | UG-13B-S04-A090 | 2 | 2 |  | 2027-05-06 | 2027-05-11 | 2027-05-11 | UG-13B-S08-A100
UG-13B-S04-A110 | AW.PIPE.F7.UG-13B.UG-13B-S04 | F7 | UG-13B | UG-13B-S04 | A110 | Dewatering off, extract sheets, reinstate | 48 | m wall | 2 | 3 | UG-13B-S04-A100 | 1 | 2 |  | 2027-05-07 | 2027-05-13
UG-13B-S03-A010 | AW.PIPE.F7.UG-13B.UG-13B-S03 | F7 | UG-13B | UG-13B-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13B-S03-A020 | AW.PIPE.F7.UG-13B.UG-13B-S03 | F7 | UG-13B | UG-13B-S03 | A020 | Set-out, crossing survey and working platform | 15 | m | 1 | 2 | UG-13B-S03-A010 |  |  | FS from A010; UG-13B-S04-A030 (SS, set-out one package ahead of piling) | 2027-02-19 | 2027-02-21
UG-13B-S03-A030 | AW.PIPE.F7.UG-13B.UG-13B-S03 | F7 | UG-13B | UG-13B-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 12 | piles | 3 | 4 | UG-13B-S03-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-24 | 2027-02-28 | 2027-02-28 | UG-13B-S04-A030
UG-13B-S03-A040 | AW.PIPE.F7.UG-13B.UG-13B-S03 | F7 | UG-13B | UG-13B-S03 | A040 | Install sheet piles (shored lengths) | 30 | m wall | 2 | 3 | UG-13B-S03-A030 | 2 | 2 |  | 2027-02-26 | 2027-03-02 | 2027-03-02 | UG-13B-S04-A040
UG-13B-S03-A050 | AW.PIPE.F7.UG-13B.UG-13B-S03 | F7 | UG-13B | UG-13B-S03 | A050 | Install dewatering and draw down | 15 | m | 8 | 10 | UG-13B-S03-A040 | 1 | 2 | UG-13B-S04-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-25 | 2027-04-04
UG-13B-S03-A060 | AW.PIPE.F7.UG-13B.UG-13B-S03 | F7 | UG-13B | UG-13B-S03 | A060 | Excavate and strut to formation | 153.1302 | m3 | 1 | 2 | UG-13B-S03-A050 | 10 | 2 |  | 2027-04-04 | 2027-04-06 | 2027-04-06 | UG-13B-S04-A060
UG-13B-S03-A070 | AW.PIPE.F7.UG-13B.UG-13B-S03 | F7 | UG-13B | UG-13B-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 15 | m | 5 | 6 | UG-13B-S03-A060 | 1 | 2 |  | 2027-05-05 | 2027-05-11 | 2027-05-11 | UG-13B-S04-A070
UG-13B-S03-A080 | AW.PIPE.F7.UG-13B.UG-13B-S03 | F7 | UG-13B | UG-13B-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 15 | m | 1 | 2 | UG-13B-S03-A070 | 2 | 2 |  | 2027-05-07 | 2027-05-13 | 2027-05-13 | UG-13B-S04-A080
UG-13B-S03-A090 | AW.PIPE.F7.UG-13B.UG-13B-S03 | F7 | UG-13B | UG-13B-S03 | A090 | Surround, joint test and line test | 15 | m | 3 | 4 | UG-13B-S03-A080 | 1 | 2 |  | 2027-05-08 | 2027-05-15
UG-13B-S03-A100 | AW.PIPE.F7.UG-13B.UG-13B-S03 | F7 | UG-13B | UG-13B-S03 | A100 | Backfill to NG and remove struts | 126.2942 | m3 | 1 | 2 | UG-13B-S03-A090 | 2 | 2 |  | 2027-05-11 | 2027-05-17 | 2027-05-17 | UG-13B-S04-A100
UG-13B-S03-A110 | AW.PIPE.F7.UG-13B.UG-13B-S03 | F7 | UG-13B | UG-13B-S03 | A110 | Dewatering off, extract sheets, reinstate | 30 | m wall | 2 | 3 | UG-13B-S03-A100 | 1 | 2 |  | 2027-05-12 | 2027-05-19
UG-13B-S02-A010 | AW.PIPE.F7.UG-13B.UG-13B-S02 | F7 | UG-13B | UG-13B-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13B-S02-A020 | AW.PIPE.F7.UG-13B.UG-13B-S02 | F7 | UG-13B | UG-13B-S02 | A020 | Set-out, crossing survey and working platform | 26.2568 | m | 1 | 2 | UG-13B-S02-A010 |  |  | FS from A010; UG-13B-S03-A030 (SS, set-out one package ahead of piling) | 2027-02-24 | 2027-02-26
UG-13B-S02-A030 | AW.PIPE.F7.UG-13B.UG-13B-S02 | F7 | UG-13B | UG-13B-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 20 | piles | 4 | 5 | UG-13B-S02-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-28 | 2027-03-05 | 2027-03-05 | UG-13B-S03-A030
UG-13B-S02-A040 | AW.PIPE.F7.UG-13B.UG-13B-S02 | F7 | UG-13B | UG-13B-S02 | A040 | Install sheet piles (shored lengths) | 52.5136 | m wall | 3 | 4 | UG-13B-S02-A030 | 2 | 2 |  | 2027-03-02 | 2027-03-07 | 2027-03-07 | UG-13B-S03-A040
UG-13B-S02-A050 | AW.PIPE.F7.UG-13B.UG-13B-S02 | F7 | UG-13B | UG-13B-S02 | A050 | Install dewatering and draw down | 26.2568 | m | 8 | 10 | UG-13B-S02-A040 | 2 | 2 | UG-13B-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-27 | 2027-04-06
UG-13B-S02-A060 | AW.PIPE.F7.UG-13B.UG-13B-S02 | F7 | UG-13B | UG-13B-S02 | A060 | Excavate and strut to formation | 267.8852 | m3 | 2 | 3 | UG-13B-S02-A050 | 10 | 2 |  | 2027-04-06 | 2027-04-09 | 2027-04-09 | UG-13B-S03-A060
UG-13B-S02-A070 | AW.PIPE.F7.UG-13B.UG-13B-S02 | F7 | UG-13B | UG-13B-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 26.2568 | m | 6 | 7 | UG-13B-S02-A060 | 1 | 2 |  | 2027-05-11 | 2027-05-18 | 2027-05-18 | UG-13B-S03-A070
UG-13B-S02-A080 | AW.PIPE.F7.UG-13B.UG-13B-S02 | F7 | UG-13B | UG-13B-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 26.2568 | m | 3 | 4 | UG-13B-S02-A070 | 3 | 2 |  | 2027-05-14 | 2027-05-20 | 2027-05-20 | UG-13B-S03-A080
UG-13B-S02-A090 | AW.PIPE.F7.UG-13B.UG-13B-S02 | F7 | UG-13B | UG-13B-S02 | A090 | Surround, joint test and line test | 26.2568 | m | 3 | 4 | UG-13B-S02-A080 | 2 | 2 |  | 2027-05-16 | 2027-05-22
UG-13B-S02-A100 | AW.PIPE.F7.UG-13B.UG-13B-S02 | F7 | UG-13B | UG-13B-S02 | A100 | Backfill to NG and remove struts | 220.9786 | m3 | 1 | 2 | UG-13B-S02-A090 | 2 | 2 |  | 2027-05-18 | 2027-05-24 | 2027-05-24 | UG-13B-S03-A100
UG-13B-S02-A110 | AW.PIPE.F7.UG-13B.UG-13B-S02 | F7 | UG-13B | UG-13B-S02 | A110 | Dewatering off, extract sheets, reinstate | 52.5136 | m wall | 3 | 4 | UG-13B-S02-A100 | 1 | 2 |  | 2027-05-19 | 2027-05-26
UG-13A-S07-A010 | AW.PIPE.F7.UG-13A.UG-13A-S07 | F7 | UG-13A | UG-13A-S07 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13A-S07-A020 | AW.PIPE.F7.UG-13A.UG-13A-S07 | F7 | UG-13A | UG-13A-S07 | A020 | Set-out, crossing survey and working platform | 10.536 | m | 1 | 2 | UG-13A-S07-A010 |  |  | FS from A010; UG-13B-S02-A030 (SS, set-out one package ahead of piling) | 2027-02-28 | 2027-03-02
UG-13A-S07-A030 | AW.PIPE.F7.UG-13A.UG-13A-S07 | F7 | UG-13A | UG-13A-S07 | A030 | Pipe-support piling from platform (incl. integrity tests) | 10 | piles | 2 | 3 | UG-13A-S07-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-05 | 2027-03-08 | 2027-03-08 | UG-13B-S02-A030
UG-13A-S07-A040 | AW.PIPE.F7.UG-13A.UG-13A-S07 | F7 | UG-13A | UG-13A-S07 | A040 | Install sheet piles (shored lengths) | 21.072 | m wall | 1 | 2 | UG-13A-S07-A030 | 1 | 2 |  | 2027-03-07 | 2027-03-10 | 2027-03-10 | UG-13B-S02-A040
UG-13A-S07-A050 | AW.PIPE.F7.UG-13A.UG-13A-S07 | F7 | UG-13A | UG-13A-S07 | A050 | Install dewatering and draw down | 10.536 | m | 8 | 10 | UG-13A-S07-A040 | 1 | 2 | UG-13B-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-30 | 2027-04-09
UG-13A-S07-A060 | AW.PIPE.F7.UG-13A.UG-13A-S07 | F7 | UG-13A | UG-13A-S07 | A060 | Excavate and strut to formation | 174.8346 | m3 | 1 | 2 | UG-13A-S07-A050 | 10 | 2 |  | 2027-04-09 | 2027-04-11 | 2027-04-11 | UG-13B-S02-A060
UG-13A-S07-A070 | AW.PIPE.F7.UG-13A.UG-13A-S07 | F7 | UG-13A | UG-13A-S07 | A070 | Trim piles, blinding and piled slab (incl. cure) | 10.536 | m | 4 | 5 | UG-13A-S07-A060 | 1 | 2 |  | 2027-05-18 | 2027-05-23 | 2027-05-23 | UG-13B-S02-A070
UG-13A-S07-A080 | AW.PIPE.F7.UG-13A.UG-13A-S07 | F7 | UG-13A | UG-13A-S07 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 10.536 | m | 2 | 3 | UG-13A-S07-A070 | 2 | 2 |  | 2027-05-20 | 2027-05-25 | 2027-05-25 | UG-13B-S02-A080
UG-13A-S07-A090 | AW.PIPE.F7.UG-13A.UG-13A-S07 | F7 | UG-13A | UG-13A-S07 | A090 | Surround, joint test and line test | 10.536 | m | 3 | 4 | UG-13A-S07-A080 | 1 | 2 |  | 2027-05-21 | 2027-05-27
UG-13A-S07-A100 | AW.PIPE.F7.UG-13A.UG-13A-S07 | F7 | UG-13A | UG-13A-S07 | A100 | Backfill to NG and remove struts | 145.9728 | m3 | 1 | 2 | UG-13A-S07-A090 | 2 | 2 |  | 2027-05-24 | 2027-05-29 | 2027-05-29 | UG-13B-S02-A100
UG-13A-S07-A110 | AW.PIPE.F7.UG-13A.UG-13A-S07 | F7 | UG-13A | UG-13A-S07 | A110 | Dewatering off, extract sheets, reinstate | 21.072 | m wall | 2 | 3 | UG-13A-S07-A100 | 1 | 2 |  | 2027-05-25 | 2027-05-31
UG-13-S02-A010 | AW.PIPE.F7.UG-13.UG-13-S02 | F7 | UG-13 | UG-13-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13-S02-A020 | AW.PIPE.F7.UG-13.UG-13-S02 | F7 | UG-13 | UG-13-S02 | A020 | Set-out, crossing survey and working platform | 32.6819 | m | 1 | 2 | UG-13-S02-A010 |  |  | FS from A010; UG-13A-S07-A030 (SS, set-out one package ahead of piling) | 2027-03-05 | 2027-03-07
UG-13-S02-A030 | AW.PIPE.F7.UG-13.UG-13-S02 | F7 | UG-13 | UG-13-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 24 | piles | 5 | 6 | UG-13-S02-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-08 | 2027-03-14 | 2027-03-14 | UG-13A-S07-A030
UG-13-S02-A040 | AW.PIPE.F7.UG-13.UG-13-S02 | F7 | UG-13 | UG-13-S02 | A040 | Install sheet piles (shored lengths) | 65.3637 | m wall | 3 | 4 | UG-13-S02-A030 | 2 | 2 |  | 2027-03-10 | 2027-03-16 | 2027-03-16 | UG-13A-S07-A040
UG-13-S02-A050 | AW.PIPE.F7.UG-13.UG-13-S02 | F7 | UG-13 | UG-13-S02 | A050 | Install dewatering and draw down | 32.6819 | m | 8 | 10 | UG-13-S02-A040 | 2 | 2 | UG-13A-S07-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-01 | 2027-04-11
UG-13-S02-A060 | AW.PIPE.F7.UG-13.UG-13-S02 | F7 | UG-13 | UG-13-S02 | A060 | Excavate and strut to formation | 694.536 | m3 | 3 | 4 | UG-13-S02-A050 | 10 | 2 |  | 2027-04-11 | 2027-04-15 | 2027-04-15 | UG-13A-S07-A060
UG-13-S02-A070 | AW.PIPE.F7.UG-13.UG-13-S02 | F7 | UG-13 | UG-13-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 32.6819 | m | 6 | 7 | UG-13-S02-A060 | 2 | 2 |  | 2027-05-23 | 2027-05-30 | 2027-05-30 | UG-13A-S07-A070
UG-13-S02-A080 | AW.PIPE.F7.UG-13.UG-13-S02 | F7 | UG-13 | UG-13-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 32.6819 | m | 3 | 4 | UG-13-S02-A070 | 3 | 2 |  | 2027-05-26 | 2027-06-01 | 2027-06-01 | UG-13A-S07-A080
UG-13-S02-A090 | AW.PIPE.F7.UG-13.UG-13-S02 | F7 | UG-13 | UG-13-S02 | A090 | Surround, joint test and line test | 32.6819 | m | 3 | 4 | UG-13-S02-A080 | 2 | 2 |  | 2027-05-28 | 2027-06-03
UG-13-S02-A100 | AW.PIPE.F7.UG-13.UG-13-S02 | F7 | UG-13 | UG-13-S02 | A100 | Backfill to NG and remove struts | 535.3081 | m3 | 2 | 3 | UG-13-S02-A090 | 2 | 2 | UG-13A-S02-A080 (FS, shared trench laid); UG-13A-S16-A080 (FS, shared trench laid) | 2027-06-13 | 2027-06-16 | 2027-06-16 | UG-13A-S07-A100
UG-13-S02-A110 | AW.PIPE.F7.UG-13.UG-13-S02 | F7 | UG-13 | UG-13-S02 | A110 | Dewatering off, extract sheets, reinstate | 65.3637 | m wall | 3 | 4 | UG-13-S02-A100 | 1 | 2 |  | 2027-06-14 | 2027-06-18
UG-13A-S02-A010 | AW.PIPE.F7.UG-13A.UG-13A-S02 | F7 | UG-13A | UG-13A-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13A-S02-A020 | AW.PIPE.F7.UG-13A.UG-13A-S02 | F7 | UG-13A | UG-13A-S02 | A020 | Set-out, crossing survey and working platform | 32.2439 | m | 1 | 2 | UG-13A-S02-A010 |  |  | FS from A010; UG-13-S02-A030 (SS, set-out one package ahead of piling) | 2027-03-08 | 2027-03-10
UG-13A-S02-A030 | AW.PIPE.F7.UG-13A.UG-13A-S02 | F7 | UG-13A | UG-13A-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 24 | piles | 5 | 6 | UG-13A-S02-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-14 | 2027-03-20 | 2027-03-20 | UG-13-S02-A030
UG-13A-S02-A040 | AW.PIPE.F7.UG-13A.UG-13A-S02 | F7 | UG-13A | UG-13A-S02 | A040 | Install sheet piles (shored lengths) | 64.4878 | m wall | 3 | 4 | UG-13A-S02-A030 | 2 | 2 |  | 2027-03-16 | 2027-03-22 | 2027-03-22 | UG-13-S02-A040
UG-13A-S02-A050 | AW.PIPE.F7.UG-13A.UG-13A-S02 | F7 | UG-13A | UG-13A-S02 | A050 | Install dewatering and draw down | 32.2439 | m | 8 | 10 | UG-13A-S02-A040 | 2 | 2 | UG-13-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-05 | 2027-04-15
UG-13A-S02-A060 | AW.PIPE.F7.UG-13A.UG-13A-S02 | F7 | UG-13A | UG-13A-S02 | A060 | Excavate and strut to formation | 454.8232 | m3 | 2 | 3 | UG-13A-S02-A050 | 10 | 2 | UG-13-S02-A060 (SS, shared trench) | 2027-04-15 | 2027-04-18 | 2027-04-18 | UG-13-S02-A060
UG-13A-S02-A070 | AW.PIPE.F7.UG-13A.UG-13A-S02 | F7 | UG-13A | UG-13A-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 32.2439 | m | 6 | 7 | UG-13A-S02-A060 | 1 | 2 |  | 2027-05-30 | 2027-06-06 | 2027-06-06 | UG-13-S02-A070
UG-13A-S02-A080 | AW.PIPE.F7.UG-13A.UG-13A-S02 | F7 | UG-13A | UG-13A-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 32.2439 | m | 3 | 4 | UG-13A-S02-A070 | 3 | 2 |  | 2027-06-02 | 2027-06-08 | 2027-06-08 | UG-13-S02-A080
UG-13A-S02-A090 | AW.PIPE.F7.UG-13A.UG-13A-S02 | F7 | UG-13A | UG-13A-S02 | A090 | Surround, joint test and line test | 32.2439 | m | 3 | 4 | UG-13A-S02-A080 | 2 | 2 |  | 2027-06-04 | 2027-06-10
UG-13A-S02-A100 | AW.PIPE.F7.UG-13A.UG-13A-S02 | F7 | UG-13A | UG-13A-S02 | A100 | Backfill to NG and remove struts | 397.1927 | m3 | 2 | 3 | UG-13A-S02-A090 | 2 | 2 | UG-13-S02-A080 (FS, shared trench laid) | 2027-06-16 | 2027-06-19 | 2027-06-19 | UG-13-S02-A100
UG-13A-S02-A110 | AW.PIPE.F7.UG-13A.UG-13A-S02 | F7 | UG-13A | UG-13A-S02 | A110 | Dewatering off, extract sheets, reinstate | 64.4878 | m wall | 3 | 4 | UG-13A-S02-A100 | 1 | 2 |  | 2027-06-17 | 2027-06-21
UG-13-S01-A010 | AW.PIPE.F7.UG-13.UG-13-S01 | F7 | UG-13 | UG-13-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-13-S01-A020 | AW.PIPE.F7.UG-13.UG-13-S01 | F7 | UG-13 | UG-13-S01 | A020 | Set-out, crossing survey and working platform | 19.7181 | m | 1 | 2 | UG-13-S01-A010 |  |  | FS from A010; UG-13-S02-A030 (SS, tie-in team follows the adjacent run) | 2027-03-08 | 2027-03-10
UG-13-S01-A030 | AW.PIPE.F7.UG-13.UG-13-S01 | F7 | UG-13 | UG-13-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 16 | piles | 4 | 5 | UG-13-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-09 | 2027-03-14 | 2027-03-14
UG-13-S01-A040 | AW.PIPE.F7.UG-13.UG-13-S01 | F7 | UG-13 | UG-13-S01 | A040 | Install sheet piles (shored lengths) | 39.4363 | m wall | 2 | 3 | UG-13-S01-A030 | 2 | 2 |  | 2027-03-11 | 2027-03-16 | 2027-03-16
UG-13-S01-A050 | AW.PIPE.F7.UG-13.UG-13-S01 | F7 | UG-13 | UG-13-S01 | A050 | Install dewatering and draw down | 19.7181 | m | 8 | 10 | UG-13-S01-A040 | 1 | 2 |  | 2027-03-12 | 2027-03-22
UG-13-S01-A060 | AW.PIPE.F7.UG-13.UG-13-S01 | F7 | UG-13 | UG-13-S01 | A060 | Excavate and strut to formation | 404.2676 | m3 | 2 | 3 | UG-13-S01-A050 | 10 | 2 |  | 2027-03-22 | 2027-03-25 | 2027-03-25
UG-13-S01-A070 | AW.PIPE.F7.UG-13.UG-13-S01 | F7 | UG-13 | UG-13-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 19.7181 | m | 5 | 6 | UG-13-S01-A060 | 1 | 2 |  | 2027-03-23 | 2027-03-29 | 2027-03-29
UG-13-S01-A080 | AW.PIPE.F7.UG-13.UG-13-S01 | F7 | UG-13 | UG-13-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 19.7181 | m | 6 | 7 | UG-13-S01-A070 | 2 | 2 | UG-13-S02-A080 (FS, closure) | 2027-06-01 | 2027-06-08 | 2027-06-08
UG-13-S01-A090 | AW.PIPE.F7.UG-13.UG-13-S01 | F7 | UG-13 | UG-13-S01 | A090 | Surround, joint test and line test | 19.7181 | m | 3 | 4 | UG-13-S01-A080 | 3 | 2 |  | 2027-06-04 | 2027-06-10
UG-13-S01-A100 | AW.PIPE.F7.UG-13.UG-13-S01 | F7 | UG-13 | UG-13-S01 | A100 | Backfill to NG and remove struts | 315.2101 | m3 | 1 | 2 | UG-13-S01-A090 | 2 | 2 | UG-13A-S08-A080 (FS, shared trench laid); UG-13A-S11-A080 (FS, shared trench laid); UG-13A-S12-A080 (FS, shared trench laid); UG-13A-S16-A080 (FS, shared trench laid) | 2027-06-23 | 2027-06-25 | 2027-06-25
UG-13-S01-A110 | AW.PIPE.F7.UG-13.UG-13-S01 | F7 | UG-13 | UG-13-S01 | A110 | Dewatering off, extract sheets, reinstate | 39.4363 | m wall | 2 | 3 | UG-13-S01-A100 | 1 | 2 |  | 2027-06-24 | 2027-06-27
UG-13A-S16-A010 | AW.PIPE.F7.UG-13A.UG-13A-S16 | F7 | UG-13A | UG-13A-S16 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13A-S16-A020 | AW.PIPE.F7.UG-13A.UG-13A-S16 | F7 | UG-13A | UG-13A-S16 | A020 | Set-out, crossing survey and working platform | 9.2744 | m | 1 | 2 | UG-13A-S16-A010 |  |  | FS from A010; UG-13A-S02-A030 (SS, set-out one package ahead of piling) | 2027-03-14 | 2027-03-16
UG-13A-S16-A030 | AW.PIPE.F7.UG-13A.UG-13A-S16 | F7 | UG-13A | UG-13A-S16 | A030 | Pipe-support piling from platform (incl. integrity tests) | 10 | piles | 2 | 3 | UG-13A-S16-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-20 | 2027-03-23 | 2027-03-23 | UG-13A-S02-A030
UG-13A-S16-A040 | AW.PIPE.F7.UG-13A.UG-13A-S16 | F7 | UG-13A | UG-13A-S16 | A040 | Install sheet piles (shored lengths) | 18.5488 | m wall | 1 | 2 | UG-13A-S16-A030 | 1 | 2 |  | 2027-03-22 | 2027-03-25 | 2027-03-25 | UG-13A-S02-A040
UG-13A-S16-A050 | AW.PIPE.F7.UG-13A.UG-13A-S16 | F7 | UG-13A | UG-13A-S16 | A050 | Install dewatering and draw down | 9.2744 | m | 8 | 10 | UG-13A-S16-A040 | 1 | 2 | UG-13A-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-08 | 2027-04-18
UG-13A-S16-A060 | AW.PIPE.F7.UG-13A.UG-13A-S16 | F7 | UG-13A | UG-13A-S16 | A060 | Excavate and strut to formation | 131.0515 | m3 | 1 | 2 | UG-13A-S16-A050 | 10 | 2 | UG-13-S01-A060 (SS, shared trench); UG-13-S02-A060 (SS, shared trench) | 2027-04-18 | 2027-04-20 | 2027-04-20 | UG-13A-S02-A060
UG-13A-S16-A070 | AW.PIPE.F7.UG-13A.UG-13A-S16 | F7 | UG-13A | UG-13A-S16 | A070 | Trim piles, blinding and piled slab (incl. cure) | 9.2744 | m | 4 | 5 | UG-13A-S16-A060 | 1 | 2 |  | 2027-06-06 | 2027-06-11 | 2027-06-11 | UG-13A-S02-A070
UG-13A-S16-A080 | AW.PIPE.F7.UG-13A.UG-13A-S16 | F7 | UG-13A | UG-13A-S16 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 9.2744 | m | 1 | 2 | UG-13A-S16-A070 | 2 | 2 |  | 2027-06-08 | 2027-06-13 | 2027-06-13 | UG-13A-S02-A080
UG-13A-S16-A090 | AW.PIPE.F7.UG-13A.UG-13A-S16 | F7 | UG-13A | UG-13A-S16 | A090 | Surround, joint test and line test | 9.2744 | m | 3 | 4 | UG-13A-S16-A080 | 1 | 2 |  | 2027-06-09 | 2027-06-15
UG-13A-S16-A100 | AW.PIPE.F7.UG-13A.UG-13A-S16 | F7 | UG-13A | UG-13A-S16 | A100 | Backfill to NG and remove struts | 114.398 | m3 | 1 | 2 | UG-13A-S16-A090 | 2 | 2 | UG-13-S01-A080 (FS, shared trench laid); UG-13-S02-A080 (FS, shared trench laid) | 2027-06-19 | 2027-06-21 | 2027-06-21 | UG-13A-S02-A100
UG-13A-S16-A110 | AW.PIPE.F7.UG-13A.UG-13A-S16 | F7 | UG-13A | UG-13A-S16 | A110 | Dewatering off, extract sheets, reinstate | 18.5488 | m wall | 2 | 3 | UG-13A-S16-A100 | 1 | 2 |  | 2027-06-20 | 2027-06-23
UG-13A-S08-A010 | AW.PIPE.F7.UG-13A.UG-13A-S08 | F7 | UG-13A | UG-13A-S08 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-13A-S08-A020 | AW.PIPE.F7.UG-13A.UG-13A-S08 | F7 | UG-13A | UG-13A-S08 | A020 | Set-out, crossing survey and working platform | 11.5705 | m | 1 | 2 | UG-13A-S08-A010 |  |  | FS from A010; UG-13A-S07-A030 (SS, tie-in team follows the adjacent run) | 2027-03-05 | 2027-03-07
UG-13A-S08-A030 | AW.PIPE.F7.UG-13A.UG-13A-S08 | F7 | UG-13A | UG-13A-S08 | A030 | Pipe-support piling from platform (incl. integrity tests) | 10 | piles | 2 | 3 | UG-13A-S08-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-06 | 2027-03-09 | 2027-03-09
UG-13A-S08-A040 | AW.PIPE.F7.UG-13A.UG-13A-S08 | F7 | UG-13A | UG-13A-S08 | A040 | Install sheet piles (shored lengths) | 23.141 | m wall | 1 | 2 | UG-13A-S08-A030 | 1 | 2 |  | 2027-03-07 | 2027-03-11 | 2027-03-11
UG-13A-S08-A050 | AW.PIPE.F7.UG-13A.UG-13A-S08 | F7 | UG-13A | UG-13A-S08 | A050 | Install dewatering and draw down | 11.5705 | m | 8 | 10 | UG-13A-S08-A040 | 1 | 2 |  | 2027-03-08 | 2027-03-18
UG-13A-S08-A060 | AW.PIPE.F7.UG-13A.UG-13A-S08 | F7 | UG-13A | UG-13A-S08 | A060 | Excavate and strut to formation | 192.7645 | m3 | 1 | 2 | UG-13A-S08-A050 | 10 | 2 | UG-13-S01-A060 (SS, shared trench) | 2027-03-22 | 2027-03-24 | 2027-03-24
UG-13A-S08-A070 | AW.PIPE.F7.UG-13A.UG-13A-S08 | F7 | UG-13A | UG-13A-S08 | A070 | Trim piles, blinding and piled slab (incl. cure) | 11.5705 | m | 4 | 5 | UG-13A-S08-A060 | 1 | 2 |  | 2027-03-23 | 2027-03-28 | 2027-03-28
UG-13A-S08-A080 | AW.PIPE.F7.UG-13A.UG-13A-S08 | F7 | UG-13A | UG-13A-S08 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 11.5705 | m | 4 | 5 | UG-13A-S08-A070 | 2 | 2 | UG-13A-S07-A080 (FS, closure) | 2027-05-25 | 2027-05-30 | 2027-05-30
UG-13A-S08-A090 | AW.PIPE.F7.UG-13A.UG-13A-S08 | F7 | UG-13A | UG-13A-S08 | A090 | Surround, joint test and line test | 11.5705 | m | 3 | 4 | UG-13A-S08-A080 | 2 | 2 |  | 2027-05-27 | 2027-06-01
UG-13A-S08-A100 | AW.PIPE.F7.UG-13A.UG-13A-S08 | F7 | UG-13A | UG-13A-S08 | A100 | Backfill to NG and remove struts | 161.0685 | m3 | 1 | 2 | UG-13A-S08-A090 | 2 | 2 | UG-13-S01-A080 (FS, shared trench laid) | 2027-06-08 | 2027-06-10 | 2027-06-10
UG-13A-S08-A110 | AW.PIPE.F7.UG-13A.UG-13A-S08 | F7 | UG-13A | UG-13A-S08 | A110 | Dewatering off, extract sheets, reinstate | 23.141 | m wall | 2 | 3 | UG-13A-S08-A100 | 1 | 2 |  | 2027-06-09 | 2027-06-12
UG-13A-S12-A010 | AW.PIPE.F7.UG-13A.UG-13A-S12 | F7 | UG-13A | UG-13A-S12 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13A-S12-A020 | AW.PIPE.F7.UG-13A.UG-13A-S12 | F7 | UG-13A | UG-13A-S12 | A020 | Set-out, crossing survey and working platform | 5.2637 | m | 1 | 2 | UG-13A-S12-A010 |  |  | FS from A010; UG-13A-S16-A030 (SS, set-out one package ahead of piling) | 2027-03-20 | 2027-03-22
UG-13A-S12-A030 | AW.PIPE.F7.UG-13A.UG-13A-S12 | F7 | UG-13A | UG-13A-S12 | A030 | Pipe-support piling from platform (incl. integrity tests) | 6 | piles | 2 | 3 | UG-13A-S12-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-23 | 2027-03-26 | 2027-03-26 | UG-13A-S16-A030
UG-13A-S12-A040 | AW.PIPE.F7.UG-13A.UG-13A-S12 | F7 | UG-13A | UG-13A-S12 | A040 | Install sheet piles (shored lengths) | 10.5274 | m wall | 1 | 2 | UG-13A-S12-A030 | 1 | 2 |  | 2027-03-25 | 2027-03-28 | 2027-03-28 | UG-13A-S16-A040
UG-13A-S12-A050 | AW.PIPE.F7.UG-13A.UG-13A-S12 | F7 | UG-13A | UG-13A-S12 | A050 | Install dewatering and draw down | 5.2637 | m | 8 | 10 | UG-13A-S12-A040 | 1 | 2 | UG-13A-S16-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-10 | 2027-04-20
UG-13A-S12-A060 | AW.PIPE.F7.UG-13A.UG-13A-S12 | F7 | UG-13A | UG-13A-S12 | A060 | Excavate and strut to formation | 87.6926 | m3 | 1 | 2 | UG-13A-S12-A050 | 10 | 2 | UG-13-S01-A060 (SS, shared trench) | 2027-04-20 | 2027-04-22 | 2027-04-22 | UG-13A-S16-A060
UG-13A-S12-A070 | AW.PIPE.F7.UG-13A.UG-13A-S12 | F7 | UG-13A | UG-13A-S12 | A070 | Trim piles, blinding and piled slab (incl. cure) | 5.2637 | m | 4 | 5 | UG-13A-S12-A060 | 1 | 2 |  | 2027-06-11 | 2027-06-16 | 2027-06-16 | UG-13A-S16-A070
UG-13A-S12-A080 | AW.PIPE.F7.UG-13A.UG-13A-S12 | F7 | UG-13A | UG-13A-S12 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 5.2637 | m | 1 | 2 | UG-13A-S12-A070 | 2 | 2 |  | 2027-06-13 | 2027-06-18 | 2027-06-18 | UG-13A-S16-A080
UG-13A-S12-A090 | AW.PIPE.F7.UG-13A.UG-13A-S12 | F7 | UG-13A | UG-13A-S12 | A090 | Surround, joint test and line test | 5.2637 | m | 3 | 4 | UG-13A-S12-A080 | 1 | 2 |  | 2027-06-14 | 2027-06-20
UG-13A-S12-A100 | AW.PIPE.F7.UG-13A.UG-13A-S12 | F7 | UG-13A | UG-13A-S12 | A100 | Backfill to NG and remove struts | 73.2735 | m3 | 1 | 2 | UG-13A-S12-A090 | 2 | 2 | UG-13-S01-A080 (FS, shared trench laid) | 2027-06-21 | 2027-06-23 | 2027-06-23 | UG-13A-S16-A100
UG-13A-S12-A110 | AW.PIPE.F7.UG-13A.UG-13A-S12 | F7 | UG-13A | UG-13A-S12 | A110 | Dewatering off, extract sheets, reinstate | 10.5274 | m wall | 2 | 3 | UG-13A-S12-A100 | 1 | 2 |  | 2027-06-22 | 2027-06-25
UG-13A-S11-A010 | AW.PIPE.F7.UG-13A.UG-13A-S11 | F7 | UG-13A | UG-13A-S11 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-13A-S11-A020 | AW.PIPE.F7.UG-13A.UG-13A-S11 | F7 | UG-13A | UG-13A-S11 | A020 | Set-out, crossing survey and working platform | 6 | m | 1 | 2 | UG-13A-S11-A010 |  |  | FS from A010; UG-13A-S12-A030 (SS, tie-in team follows the adjacent run) | 2027-03-23 | 2027-03-25
UG-13A-S11-A030 | AW.PIPE.F7.UG-13A.UG-13A-S11 | F7 | UG-13A | UG-13A-S11 | A030 | Pipe-support piling from platform (incl. integrity tests) | 6 | piles | 2 | 3 | UG-13A-S11-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-24 | 2027-03-27 | 2027-03-27
UG-13A-S11-A040 | AW.PIPE.F7.UG-13A.UG-13A-S11 | F7 | UG-13A | UG-13A-S11 | A040 | Install sheet piles (shored lengths) | 12 | m wall | 1 | 2 | UG-13A-S11-A030 | 1 | 2 |  | 2027-03-25 | 2027-03-29 | 2027-03-29
UG-13A-S11-A050 | AW.PIPE.F7.UG-13A.UG-13A-S11 | F7 | UG-13A | UG-13A-S11 | A050 | Install dewatering and draw down | 6 | m | 8 | 10 | UG-13A-S11-A040 | 1 | 2 |  | 2027-03-26 | 2027-04-05
UG-13A-S11-A060 | AW.PIPE.F7.UG-13A.UG-13A-S11 | F7 | UG-13A | UG-13A-S11 | A060 | Excavate and strut to formation | 99.9597 | m3 | 1 | 2 | UG-13A-S11-A050 | 10 | 2 | UG-13-S01-A060 (SS, shared trench) | 2027-04-05 | 2027-04-07 | 2027-04-07
UG-13A-S11-A070 | AW.PIPE.F7.UG-13A.UG-13A-S11 | F7 | UG-13A | UG-13A-S11 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6 | m | 4 | 5 | UG-13A-S11-A060 | 1 | 2 |  | 2027-04-06 | 2027-04-11 | 2027-04-11
UG-13A-S11-A080 | AW.PIPE.F7.UG-13A.UG-13A-S11 | F7 | UG-13A | UG-13A-S11 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6 | m | 4 | 5 | UG-13A-S11-A070 | 2 | 2 | UG-13A-S12-A080 (FS, closure) | 2027-06-18 | 2027-06-23 | 2027-06-23
UG-13A-S11-A090 | AW.PIPE.F7.UG-13A.UG-13A-S11 | F7 | UG-13A | UG-13A-S11 | A090 | Surround, joint test and line test | 6 | m | 3 | 4 | UG-13A-S11-A080 | 2 | 2 |  | 2027-06-20 | 2027-06-25
UG-13A-S11-A100 | AW.PIPE.F7.UG-13A.UG-13A-S11 | F7 | UG-13A | UG-13A-S11 | A100 | Backfill to NG and remove struts | 83.5235 | m3 | 1 | 2 | UG-13A-S11-A090 | 2 | 2 | UG-13-S01-A080 (FS, shared trench laid) | 2027-06-22 | 2027-06-27 | 2027-06-27
UG-13A-S11-A110 | AW.PIPE.F7.UG-13A.UG-13A-S11 | F7 | UG-13A | UG-13A-S11 | A110 | Dewatering off, extract sheets, reinstate | 12 | m wall | 2 | 3 | UG-13A-S11-A100 | 1 | 2 |  | 2027-06-23 | 2027-06-29
UG-13A-S01-A010 | AW.PIPE.F7.UG-13A.UG-13A-S01 | F7 | UG-13A | UG-13A-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-13A-S01-A020 | AW.PIPE.F7.UG-13A.UG-13A-S01 | F7 | UG-13A | UG-13A-S01 | A020 | Set-out, crossing survey and working platform | 6 | m | 1 | 2 | UG-13A-S01-A010 |  |  | FS from A010; UG-13A-S02-A030 (SS, tie-in team follows the adjacent run) | 2027-03-14 | 2027-03-16
UG-13A-S01-A030 | AW.PIPE.F7.UG-13A.UG-13A-S01 | F7 | UG-13A | UG-13A-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 4 | piles | 1 | 2 | UG-13A-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-15 | 2027-03-18 | 2027-03-18
UG-13A-S01-A040 | AW.PIPE.F7.UG-13A.UG-13A-S01 | F7 | UG-13A | UG-13A-S01 | A040 | Install sheet piles (shored lengths) | 12 | m wall | 1 | 2 | UG-13A-S01-A030 | 1 | 2 |  | 2027-03-16 | 2027-03-20 | 2027-03-20
UG-13A-S01-A050 | AW.PIPE.F7.UG-13A.UG-13A-S01 | F7 | UG-13A | UG-13A-S01 | A050 | Install dewatering and draw down | 6 | m | 8 | 10 | UG-13A-S01-A040 | 1 | 2 |  | 2027-03-17 | 2027-03-27
UG-13A-S01-A060 | AW.PIPE.F7.UG-13A.UG-13A-S01 | F7 | UG-13A | UG-13A-S01 | A060 | Excavate and strut to formation | 84.5999 | m3 | 1 | 2 | UG-13A-S01-A050 | 10 | 2 |  | 2027-03-27 | 2027-03-29 | 2027-03-29
UG-13A-S01-A070 | AW.PIPE.F7.UG-13A.UG-13A-S01 | F7 | UG-13A | UG-13A-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6 | m | 4 | 5 | UG-13A-S01-A060 | 1 | 2 |  | 2027-03-28 | 2027-04-02 | 2027-04-02
UG-13A-S01-A080 | AW.PIPE.F7.UG-13A.UG-13A-S01 | F7 | UG-13A | UG-13A-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6 | m | 4 | 5 | UG-13A-S01-A070 | 2 | 2 | UG-13A-S02-A080 (FS, closure) | 2027-06-08 | 2027-06-13 | 2027-06-13
UG-13A-S01-A090 | AW.PIPE.F7.UG-13A.UG-13A-S01 | F7 | UG-13A | UG-13A-S01 | A090 | Surround, joint test and line test | 6 | m | 3 | 4 | UG-13A-S01-A080 | 2 | 2 |  | 2027-06-10 | 2027-06-15
UG-13A-S01-A100 | AW.PIPE.F7.UG-13A.UG-13A-S01 | F7 | UG-13A | UG-13A-S01 | A100 | Backfill to NG and remove struts | 73.8875 | m3 | 1 | 2 | UG-13A-S01-A090 | 2 | 2 |  | 2027-06-12 | 2027-06-17 | 2027-06-17
UG-13A-S01-A110 | AW.PIPE.F7.UG-13A.UG-13A-S01 | F7 | UG-13A | UG-13A-S01 | A110 | Dewatering off, extract sheets, reinstate | 12 | m wall | 2 | 3 | UG-13A-S01-A100 | 1 | 2 |  | 2027-06-13 | 2027-06-19
UG-13A-S06-A010 | AW.PIPE.F7.UG-13A.UG-13A-S06 | F7 | UG-13A | UG-13A-S06 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13A-S06-A020 | AW.PIPE.F7.UG-13A.UG-13A-S06 | F7 | UG-13A | UG-13A-S06 | A020 | Set-out, crossing survey and working platform | 16.1 | m | 1 | 2 | UG-13A-S06-A010 |  |  | FS from A010; UG-13A-S12-A030 (SS, set-out one package ahead of piling) | 2027-03-23 | 2027-03-25
UG-13A-S06-A030 | AW.PIPE.F7.UG-13A.UG-13A-S06 | F7 | UG-13A | UG-13A-S06 | A030 | Pipe-support piling from platform (incl. integrity tests) | 14 | piles | 3 | 4 | UG-13A-S06-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-26 | 2027-03-30 | 2027-03-30 | UG-13A-S12-A030
UG-13A-S06-A040 | AW.PIPE.F7.UG-13A.UG-13A-S06 | F7 | UG-13A | UG-13A-S06 | A040 | Install sheet piles (shored lengths) | 32.2 | m wall | 2 | 3 | UG-13A-S06-A030 | 2 | 2 |  | 2027-03-28 | 2027-04-01 | 2027-04-01 | UG-13A-S12-A040
UG-13A-S06-A050 | AW.PIPE.F7.UG-13A.UG-13A-S06 | F7 | UG-13A | UG-13A-S06 | A050 | Install dewatering and draw down | 16.1 | m | 8 | 10 | UG-13A-S06-A040 | 1 | 2 | UG-13A-S12-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-12 | 2027-04-22
UG-13A-S06-A060 | AW.PIPE.F7.UG-13A.UG-13A-S06 | F7 | UG-13A | UG-13A-S06 | A060 | Excavate and strut to formation | 264.468 | m3 | 2 | 3 | UG-13A-S06-A050 | 10 | 2 |  | 2027-04-22 | 2027-04-25 | 2027-04-25 | UG-13A-S12-A060
UG-13A-S06-A070 | AW.PIPE.F7.UG-13A.UG-13A-S06 | F7 | UG-13A | UG-13A-S06 | A070 | Trim piles, blinding and piled slab (incl. cure) | 16.1 | m | 5 | 6 | UG-13A-S06-A060 | 1 | 2 |  | 2027-06-16 | 2027-06-22 | 2027-06-22 | UG-13A-S12-A070
UG-13A-S06-A080 | AW.PIPE.F7.UG-13A.UG-13A-S06 | F7 | UG-13A | UG-13A-S06 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 16.1 | m | 1 | 2 | UG-13A-S06-A070 | 2 | 2 |  | 2027-06-18 | 2027-06-24 | 2027-06-24 | UG-13A-S12-A080
UG-13A-S06-A090 | AW.PIPE.F7.UG-13A.UG-13A-S06 | F7 | UG-13A | UG-13A-S06 | A090 | Surround, joint test and line test | 16.1 | m | 3 | 4 | UG-13A-S06-A080 | 1 | 2 |  | 2027-06-19 | 2027-06-26
UG-13A-S06-A100 | AW.PIPE.F7.UG-13A.UG-13A-S06 | F7 | UG-13A | UG-13A-S06 | A100 | Backfill to NG and remove struts | 220.3644 | m3 | 1 | 2 | UG-13A-S06-A090 | 2 | 2 |  | 2027-06-23 | 2027-06-28 | 2027-06-28 | UG-13A-S12-A100
UG-13A-S06-A110 | AW.PIPE.F7.UG-13A.UG-13A-S06 | F7 | UG-13A | UG-13A-S06 | A110 | Dewatering off, extract sheets, reinstate | 32.2 | m wall | 2 | 3 | UG-13A-S06-A100 | 1 | 2 |  | 2027-06-24 | 2027-06-30
UG-13A-S05-A010 | AW.PIPE.F7.UG-13A.UG-13A-S05 | F7 | UG-13A | UG-13A-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13A-S05-A020 | AW.PIPE.F7.UG-13A.UG-13A-S05 | F7 | UG-13A | UG-13A-S05 | A020 | Set-out, crossing survey and working platform | 5.1884 | m | 1 | 2 | UG-13A-S05-A010 |  |  | FS from A010; UG-13A-S06-A030 (SS, set-out one package ahead of piling) | 2027-03-26 | 2027-03-28
UG-13A-S05-A030 | AW.PIPE.F7.UG-13A.UG-13A-S05 | F7 | UG-13A | UG-13A-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 6 | piles | 2 | 3 | UG-13A-S05-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-30 | 2027-04-02 | 2027-04-02 | UG-13A-S06-A030
UG-13A-S05-A040 | AW.PIPE.F7.UG-13A.UG-13A-S05 | F7 | UG-13A | UG-13A-S05 | A040 | Install sheet piles (shored lengths) | 10.3768 | m wall | 1 | 2 | UG-13A-S05-A030 | 1 | 2 |  | 2027-04-01 | 2027-04-04 | 2027-04-04 | UG-13A-S06-A040
UG-13A-S05-A050 | AW.PIPE.F7.UG-13A.UG-13A-S05 | F7 | UG-13A | UG-13A-S05 | A050 | Install dewatering and draw down | 5.1884 | m | 8 | 10 | UG-13A-S05-A040 | 1 | 2 | UG-13A-S06-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-15 | 2027-04-25
UG-13A-S05-A060 | AW.PIPE.F7.UG-13A.UG-13A-S05 | F7 | UG-13A | UG-13A-S05 | A060 | Excavate and strut to formation | 84.5336 | m3 | 1 | 2 | UG-13A-S05-A050 | 10 | 2 |  | 2027-04-25 | 2027-04-27 | 2027-04-27 | UG-13A-S06-A060
UG-13A-S05-A070 | AW.PIPE.F7.UG-13A.UG-13A-S05 | F7 | UG-13A | UG-13A-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 5.1884 | m | 4 | 5 | UG-13A-S05-A060 | 1 | 2 |  | 2027-06-22 | 2027-06-27 | 2027-06-27 | UG-13A-S06-A070
UG-13A-S05-A080 | AW.PIPE.F7.UG-13A.UG-13A-S05 | F7 | UG-13A | UG-13A-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 5.1884 | m | 1 | 2 | UG-13A-S05-A070 | 2 | 2 |  | 2027-06-24 | 2027-06-29 | 2027-06-29 | UG-13A-S06-A080
UG-13A-S05-A090 | AW.PIPE.F7.UG-13A.UG-13A-S05 | F7 | UG-13A | UG-13A-S05 | A090 | Surround, joint test and line test | 5.1884 | m | 3 | 4 | UG-13A-S05-A080 | 1 | 2 |  | 2027-06-25 | 2027-07-01
UG-13A-S05-A100 | AW.PIPE.F7.UG-13A.UG-13A-S05 | F7 | UG-13A | UG-13A-S05 | A100 | Backfill to NG and remove struts | 70.3207 | m3 | 1 | 2 | UG-13A-S05-A090 | 2 | 2 |  | 2027-06-28 | 2027-07-03 | 2027-07-03 | UG-13A-S06-A100
UG-13A-S05-A110 | AW.PIPE.F7.UG-13A.UG-13A-S05 | F7 | UG-13A | UG-13A-S05 | A110 | Dewatering off, extract sheets, reinstate | 10.3768 | m wall | 2 | 3 | UG-13A-S05-A100 | 1 | 2 |  | 2027-06-29 | 2027-07-05
UG-13A-S10-A010 | AW.PIPE.F7.UG-13A.UG-13A-S10 | F7 | UG-13A | UG-13A-S10 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13A-S10-A020 | AW.PIPE.F7.UG-13A.UG-13A-S10 | F7 | UG-13A | UG-13A-S10 | A020 | Set-out, crossing survey and working platform | 15.8257 | m | 1 | 2 | UG-13A-S10-A010 |  |  | FS from A010; UG-13A-S05-A030 (SS, set-out one package ahead of piling) | 2027-03-30 | 2027-04-01
UG-13A-S10-A030 | AW.PIPE.F7.UG-13A.UG-13A-S10 | F7 | UG-13A | UG-13A-S10 | A030 | Pipe-support piling from platform (incl. integrity tests) | 14 | piles | 3 | 4 | UG-13A-S10-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-02 | 2027-04-06 | 2027-04-06 | UG-13A-S05-A030
UG-13A-S10-A040 | AW.PIPE.F7.UG-13A.UG-13A-S10 | F7 | UG-13A | UG-13A-S10 | A040 | Install sheet piles (shored lengths) | 31.6514 | m wall | 2 | 3 | UG-13A-S10-A030 | 2 | 2 |  | 2027-04-04 | 2027-04-08 | 2027-04-08 | UG-13A-S05-A040
UG-13A-S10-A050 | AW.PIPE.F7.UG-13A.UG-13A-S10 | F7 | UG-13A | UG-13A-S10 | A050 | Install dewatering and draw down | 15.8257 | m | 8 | 10 | UG-13A-S10-A040 | 1 | 2 | UG-13A-S05-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-17 | 2027-04-27
UG-13A-S10-A060 | AW.PIPE.F7.UG-13A.UG-13A-S10 | F7 | UG-13A | UG-13A-S10 | A060 | Excavate and strut to formation | 236.8824 | m3 | 1 | 2 | UG-13A-S10-A050 | 10 | 2 |  | 2027-04-27 | 2027-04-29 | 2027-04-29 | UG-13A-S05-A060
UG-13A-S10-A070 | AW.PIPE.F7.UG-13A.UG-13A-S10 | F7 | UG-13A | UG-13A-S10 | A070 | Trim piles, blinding and piled slab (incl. cure) | 15.8257 | m | 5 | 6 | UG-13A-S10-A060 | 1 | 2 |  | 2027-06-27 | 2027-07-03 | 2027-07-03 | UG-13A-S05-A070
UG-13A-S10-A080 | AW.PIPE.F7.UG-13A.UG-13A-S10 | F7 | UG-13A | UG-13A-S10 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 15.8257 | m | 2 | 3 | UG-13A-S10-A070 | 2 | 2 |  | 2027-06-29 | 2027-07-05 | 2027-07-05 | UG-13A-S05-A080
UG-13A-S10-A090 | AW.PIPE.F7.UG-13A.UG-13A-S10 | F7 | UG-13A | UG-13A-S10 | A090 | Surround, joint test and line test | 15.8257 | m | 3 | 4 | UG-13A-S10-A080 | 1 | 2 |  | 2027-06-30 | 2027-07-07
UG-13A-S10-A100 | AW.PIPE.F7.UG-13A.UG-13A-S10 | F7 | UG-13A | UG-13A-S10 | A100 | Backfill to NG and remove struts | 203.4136 | m3 | 1 | 2 | UG-13A-S10-A090 | 2 | 2 |  | 2027-07-03 | 2027-07-09 | 2027-07-09 | UG-13A-S05-A100
UG-13A-S10-A110 | AW.PIPE.F7.UG-13A.UG-13A-S10 | F7 | UG-13A | UG-13A-S10 | A110 | Dewatering off, extract sheets, reinstate | 31.6514 | m wall | 2 | 3 | UG-13A-S10-A100 | 1 | 2 |  | 2027-07-04 | 2027-07-11
UG-13A-S09-A010 | AW.PIPE.F7.UG-13A.UG-13A-S09 | F7 | UG-13A | UG-13A-S09 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-13A-S09-A020 | AW.PIPE.F7.UG-13A.UG-13A-S09 | F7 | UG-13A | UG-13A-S09 | A020 | Set-out, crossing survey and working platform | 0.6364 | m | 1 | 2 | UG-13A-S09-A010 |  |  | FS from A010; UG-13A-S10-A030 (SS, tie-in team follows the adjacent run) | 2027-04-02 | 2027-04-04
UG-13A-S09-A030 | AW.PIPE.F7.UG-13A.UG-13A-S09 | F7 | UG-13A | UG-13A-S09 | A030 | Pipe-support piling from platform (incl. integrity tests) | 2 | piles | 1 | 2 | UG-13A-S09-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-03 | 2027-04-06 | 2027-04-06
UG-13A-S09-A040 | AW.PIPE.F7.UG-13A.UG-13A-S09 | F7 | UG-13A | UG-13A-S09 | A040 | Install sheet piles (shored lengths) | 1.2728 | m wall | 1 | 2 | UG-13A-S09-A030 | 1 | 2 |  | 2027-04-04 | 2027-04-08 | 2027-04-08
UG-13A-S09-A050 | AW.PIPE.F7.UG-13A.UG-13A-S09 | F7 | UG-13A | UG-13A-S09 | A050 | Install dewatering and draw down | 0.6364 | m | 8 | 10 | UG-13A-S09-A040 | 1 | 2 |  | 2027-04-05 | 2027-04-15
UG-13A-S09-A060 | AW.PIPE.F7.UG-13A.UG-13A-S09 | F7 | UG-13A | UG-13A-S09 | A060 | Excavate and strut to formation | 8.8975 | m3 | 1 | 2 | UG-13A-S09-A050 | 10 | 2 |  | 2027-04-15 | 2027-04-17 | 2027-04-17
UG-13A-S09-A070 | AW.PIPE.F7.UG-13A.UG-13A-S09 | F7 | UG-13A | UG-13A-S09 | A070 | Trim piles, blinding and piled slab (incl. cure) | 0.6364 | m | 4 | 5 | UG-13A-S09-A060 | 1 | 2 |  | 2027-04-16 | 2027-04-21 | 2027-04-21
UG-13A-S09-A080 | AW.PIPE.F7.UG-13A.UG-13A-S09 | F7 | UG-13A | UG-13A-S09 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 0.6364 | m | 4 | 5 | UG-13A-S09-A070 | 2 | 2 | UG-13A-S10-A080 (FS, closure) | 2027-07-05 | 2027-07-10 | 2027-07-10
UG-13A-S09-A090 | AW.PIPE.F7.UG-13A.UG-13A-S09 | F7 | UG-13A | UG-13A-S09 | A090 | Surround, joint test and line test | 0.6364 | m | 3 | 4 | UG-13A-S09-A080 | 2 | 2 |  | 2027-07-07 | 2027-07-12
UG-13A-S09-A100 | AW.PIPE.F7.UG-13A.UG-13A-S09 | F7 | UG-13A | UG-13A-S09 | A100 | Backfill to NG and remove struts | 7.7864 | m3 | 1 | 2 | UG-13A-S09-A090 | 2 | 2 |  | 2027-07-09 | 2027-07-14 | 2027-07-14
UG-13A-S09-A110 | AW.PIPE.F7.UG-13A.UG-13A-S09 | F7 | UG-13A | UG-13A-S09 | A110 | Dewatering off, extract sheets, reinstate | 1.2728 | m wall | 2 | 3 | UG-13A-S09-A100 | 1 | 2 |  | 2027-07-10 | 2027-07-16
UG-13A-S14-A010 | AW.PIPE.F7.UG-13A.UG-13A-S14 | F7 | UG-13A | UG-13A-S14 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13A-S14-A020 | AW.PIPE.F7.UG-13A.UG-13A-S14 | F7 | UG-13A | UG-13A-S14 | A020 | Set-out, crossing survey and working platform | 31.4977 | m | 1 | 2 | UG-13A-S14-A010 |  |  | FS from A010; UG-13A-S10-A030 (SS, set-out one package ahead of piling) | 2027-04-02 | 2027-04-04
UG-13A-S14-A030 | AW.PIPE.F7.UG-13A.UG-13A-S14 | F7 | UG-13A | UG-13A-S14 | A030 | Pipe-support piling from platform (incl. integrity tests) | 12 | piles | 3 | 4 | UG-13A-S14-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-06 | 2027-04-10 | 2027-04-10 | UG-13A-S10-A030
UG-13A-S14-A040 | AW.PIPE.F7.UG-13A.UG-13A-S14 | F7 | UG-13A | UG-13A-S14 | A040 | Install sheet piles (shored lengths) | 62.9954 | m wall | 3 | 4 | UG-13A-S14-A030 | 2 | 2 |  | 2027-04-08 | 2027-04-12 | 2027-04-12 | UG-13A-S10-A040
UG-13A-S14-A050 | AW.PIPE.F7.UG-13A.UG-13A-S14 | F7 | UG-13A | UG-13A-S14 | A050 | Install dewatering and draw down | 31.4977 | m | 8 | 10 | UG-13A-S14-A040 | 2 | 2 | UG-13A-S10-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-19 | 2027-04-29
UG-13A-S14-A060 | AW.PIPE.F7.UG-13A.UG-13A-S14 | F7 | UG-13A | UG-13A-S14 | A060 | Excavate and strut to formation | 321.2159 | m3 | 2 | 3 | UG-13A-S14-A050 | 10 | 2 |  | 2027-04-29 | 2027-05-02 | 2027-05-02 | UG-13A-S10-A060
UG-13A-S14-A070 | AW.PIPE.F7.UG-13A.UG-13A-S14 | F7 | UG-13A | UG-13A-S14 | A070 | Trim piles, blinding and piled slab (incl. cure) | 31.4977 | m | 6 | 7 | UG-13A-S14-A060 | 1 | 2 |  | 2027-07-03 | 2027-07-10 | 2027-07-10 | UG-13A-S10-A070
UG-13A-S14-A080 | AW.PIPE.F7.UG-13A.UG-13A-S14 | F7 | UG-13A | UG-13A-S14 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 31.4977 | m | 4 | 5 | UG-13A-S14-A070 | 3 | 2 |  | 2027-07-06 | 2027-07-12 | 2027-07-12 | UG-13A-S10-A080
UG-13A-S14-A090 | AW.PIPE.F7.UG-13A.UG-13A-S14 | F7 | UG-13A | UG-13A-S14 | A090 | Surround, joint test and line test | 31.4977 | m | 3 | 4 | UG-13A-S14-A080 | 2 | 2 |  | 2027-07-08 | 2027-07-14
UG-13A-S14-A100 | AW.PIPE.F7.UG-13A.UG-13A-S14 | F7 | UG-13A | UG-13A-S14 | A100 | Backfill to NG and remove struts | 265.0054 | m3 | 1 | 2 | UG-13A-S14-A090 | 2 | 2 |  | 2027-07-10 | 2027-07-16 | 2027-07-16 | UG-13A-S10-A100
UG-13A-S14-A110 | AW.PIPE.F7.UG-13A.UG-13A-S14 | F7 | UG-13A | UG-13A-S14 | A110 | Dewatering off, extract sheets, reinstate | 62.9954 | m wall | 3 | 4 | UG-13A-S14-A100 | 1 | 2 |  | 2027-07-11 | 2027-07-18
UG-13A-S04-A010 | AW.PIPE.F7.UG-13A.UG-13A-S04 | F7 | UG-13A | UG-13A-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-13A-S04-A020 | AW.PIPE.F7.UG-13A.UG-13A-S04 | F7 | UG-13A | UG-13A-S04 | A020 | Set-out, crossing survey and working platform | 42.2116 | m | 1 | 2 | UG-13A-S04-A010 |  |  | FS from A010; UG-13A-S14-A030 (SS, set-out one package ahead of piling) | 2027-04-06 | 2027-04-08
UG-13A-S04-A030 | AW.PIPE.F7.UG-13A.UG-13A-S04 | F7 | UG-13A | UG-13A-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 32 | piles | 7 | 9 | UG-13A-S04-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-10 | 2027-04-19 | 2027-04-19 | UG-13A-S14-A030
UG-13A-S04-A040 | AW.PIPE.F7.UG-13A.UG-13A-S04 | F7 | UG-13A | UG-13A-S04 | A040 | Install sheet piles (shored lengths) | 84.4232 | m wall | 4 | 5 | UG-13A-S04-A030 | 3 | 2 |  | 2027-04-13 | 2027-04-21 | 2027-04-21 | UG-13A-S14-A040
UG-13A-S04-A050 | AW.PIPE.F7.UG-13A.UG-13A-S04 | F7 | UG-13A | UG-13A-S04 | A050 | Install dewatering and draw down | 42.2116 | m | 9 | 11 | UG-13A-S04-A040 | 2 | 2 | UG-13A-S14-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-21 | 2027-05-02
UG-13A-S04-A060 | AW.PIPE.F7.UG-13A.UG-13A-S04 | F7 | UG-13A | UG-13A-S04 | A060 | Excavate and strut to formation | 463.5811 | m3 | 2 | 3 | UG-13A-S04-A050 | 10 | 2 |  | 2027-05-02 | 2027-05-05 | 2027-05-05 | UG-13A-S14-A060
UG-13A-S04-A070 | AW.PIPE.F7.UG-13A.UG-13A-S04 | F7 | UG-13A | UG-13A-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 42.2116 | m | 7 | 9 | UG-13A-S04-A060 | 1 | 2 |  | 2027-07-10 | 2027-07-19 | 2027-07-19 | UG-13A-S14-A070
UG-13A-S04-A080 | AW.PIPE.F7.UG-13A.UG-13A-S04 | F7 | UG-13A | UG-13A-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 42.2116 | m | 6 | 7 | UG-13A-S04-A070 | 3 | 2 |  | 2027-07-13 | 2027-07-21 | 2027-07-21 | UG-13A-S14-A080
UG-13A-S04-A090 | AW.PIPE.F7.UG-13A.UG-13A-S04 | F7 | UG-13A | UG-13A-S04 | A090 | Surround, joint test and line test | 42.2116 | m | 3 | 4 | UG-13A-S04-A080 | 3 | 2 |  | 2027-07-16 | 2027-07-23
UG-13A-S04-A100 | AW.PIPE.F7.UG-13A.UG-13A-S04 | F7 | UG-13A | UG-13A-S04 | A100 | Backfill to NG and remove struts | 385.4959 | m3 | 2 | 3 | UG-13A-S04-A090 | 2 | 2 | UG-27I-S01-A080 (FS, shared trench laid) | 2027-08-01 | 2027-08-04 | 2027-08-04 | UG-13A-S14-A100
UG-13A-S04-A110 | AW.PIPE.F7.UG-13A.UG-13A-S04 | F7 | UG-13A | UG-13A-S04 | A110 | Dewatering off, extract sheets, reinstate | 84.4232 | m wall | 3 | 4 | UG-13A-S04-A100 | 1 | 2 |  | 2027-08-02 | 2027-08-06
UG-13A-S03-A010 | AW.PIPE.F7.UG-13A.UG-13A-S03 | F7 | UG-13A | UG-13A-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-13A-S03-A020 | AW.PIPE.F7.UG-13A.UG-13A-S03 | F7 | UG-13A | UG-13A-S03 | A020 | Set-out, crossing survey and working platform | 6 | m | 1 | 2 | UG-13A-S03-A010 |  |  | FS from A010; UG-13A-S04-A030 (SS, tie-in team follows the adjacent run) | 2027-04-10 | 2027-04-12
UG-13A-S03-A030 | AW.PIPE.F7.UG-13A.UG-13A-S03 | F7 | UG-13A | UG-13A-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 4 | piles | 1 | 2 | UG-13A-S03-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-11 | 2027-04-14 | 2027-04-14
UG-13A-S03-A040 | AW.PIPE.F7.UG-13A.UG-13A-S03 | F7 | UG-13A | UG-13A-S03 | A040 | Install sheet piles (shored lengths) | 12 | m wall | 1 | 2 | UG-13A-S03-A030 | 1 | 2 |  | 2027-04-12 | 2027-04-16 | 2027-04-16
UG-13A-S03-A050 | AW.PIPE.F7.UG-13A.UG-13A-S03 | F7 | UG-13A | UG-13A-S03 | A050 | Install dewatering and draw down | 6 | m | 8 | 10 | UG-13A-S03-A040 | 1 | 2 |  | 2027-04-13 | 2027-04-23
UG-13A-S03-A060 | AW.PIPE.F7.UG-13A.UG-13A-S03 | F7 | UG-13A | UG-13A-S03 | A060 | Excavate and strut to formation | 62.0999 | m3 | 1 | 2 | UG-13A-S03-A050 | 10 | 2 |  | 2027-04-23 | 2027-04-25 | 2027-04-25
UG-13A-S03-A070 | AW.PIPE.F7.UG-13A.UG-13A-S03 | F7 | UG-13A | UG-13A-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6 | m | 4 | 5 | UG-13A-S03-A060 | 1 | 2 |  | 2027-04-24 | 2027-04-29 | 2027-04-29
UG-13A-S03-A080 | AW.PIPE.F7.UG-13A.UG-13A-S03 | F7 | UG-13A | UG-13A-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6 | m | 4 | 5 | UG-13A-S03-A070 | 2 | 2 | UG-13A-S04-A080 (FS, closure) | 2027-07-21 | 2027-07-26 | 2027-07-26
UG-13A-S03-A090 | AW.PIPE.F7.UG-13A.UG-13A-S03 | F7 | UG-13A | UG-13A-S03 | A090 | Surround, joint test and line test | 6 | m | 3 | 4 | UG-13A-S03-A080 | 2 | 2 |  | 2027-07-23 | 2027-07-28
UG-13A-S03-A100 | AW.PIPE.F7.UG-13A.UG-13A-S03 | F7 | UG-13A | UG-13A-S03 | A100 | Backfill to NG and remove struts | 51.3876 | m3 | 1 | 2 | UG-13A-S03-A090 | 2 | 2 | UG-27I-S01-A080 (FS, shared trench laid) | 2027-08-01 | 2027-08-03 | 2027-08-03
UG-13A-S03-A110 | AW.PIPE.F7.UG-13A.UG-13A-S03 | F7 | UG-13A | UG-13A-S03 | A110 | Dewatering off, extract sheets, reinstate | 12 | m wall | 2 | 3 | UG-13A-S03-A100 | 1 | 2 |  | 2027-08-02 | 2027-08-05
UG-27I-S01-A010 | AW.PIPE.F7.UG-27I.UG-27I-S01 | F7 | UG-27I | UG-27I-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-27I-S01-A020 | AW.PIPE.F7.UG-27I.UG-27I-S01 | F7 | UG-27I | UG-27I-S01 | A020 | Set-out, crossing survey and working platform | 37.5872 | m | 1 | 2 | UG-27I-S01-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-27I-S01-A030 | AW.PIPE.F7.UG-27I.UG-27I-S01 | F7 | UG-27I | UG-27I-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 28 | piles | 6 | 7 | UG-27I-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-09 | 2026-12-09
UG-27I-S01-A040 | AW.PIPE.F7.UG-27I.UG-27I-S01 | F7 | UG-27I | UG-27I-S01 | A040 | Install sheet piles (shored lengths) | 1.6799 | m wall | 1 | 2 | UG-27I-S01-A030 | 3 | 2 |  | 2026-12-05 | 2026-12-11 | 2026-12-11
UG-27I-S01-A050 | AW.PIPE.F7.UG-27I.UG-27I-S01 | F7 | UG-27I | UG-27I-S01 | A050 | Install dewatering and draw down | 37.5872 | m | 8 | 10 | UG-27I-S01-A040 | 1 | 2 |  | 2026-12-06 | 2026-12-16
UG-27I-S01-A060 | AW.PIPE.F7.UG-27I.UG-27I-S01 | F7 | UG-27I | UG-27I-S01 | A060 | Excavate and strut to formation | 974.9083 | m3 | 3 | 4 | UG-27I-S01-A050 | 10 | 2 | UG-13A-S09-A100 (FS, deeper first); UG-13A-S10-A100 (FS, deeper first); UG-13A-S14-A100 (FS, deeper first); UG-13A-S03-A060 (SS, shared trench); UG-13A-S04-A060 (SS, shared trench) | 2027-07-16 | 2027-07-20 | 2027-07-20
UG-27I-S01-A070 | AW.PIPE.F7.UG-27I.UG-27I-S01 | F7 | UG-27I | UG-27I-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 37.5872 | m | 7 | 9 | UG-27I-S01-A060 | 2 | 2 |  | 2027-07-18 | 2027-07-27 | 2027-07-27
UG-27I-S01-A080 | AW.PIPE.F7.UG-27I.UG-27I-S01 | F7 | UG-27I | UG-27I-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 37.5872 | m | 9 | 11 | UG-27I-S01-A070 | 3 | 2 |  | 2027-07-21 | 2027-08-01 | 2027-08-01
UG-27I-S01-A090 | AW.PIPE.F7.UG-27I.UG-27I-S01 | F7 | UG-27I | UG-27I-S01 | A090 | Surround, joint test and line test | 37.5872 | m | 3 | 4 | UG-27I-S01-A080 | 4 | 2 |  | 2027-07-25 | 2027-08-03
UG-27I-S01-A100 | AW.PIPE.F7.UG-27I.UG-27I-S01 | F7 | UG-27I | UG-27I-S01 | A100 | Backfill to NG and remove struts | 861.0883 | m3 | 3 | 4 | UG-27I-S01-A090 | 2 | 2 | UG-13A-S03-A080 (FS, shared trench laid); UG-13A-S04-A080 (FS, shared trench laid) | 2027-07-27 | 2027-08-05 | 2027-08-05
UG-27I-S01-A110 | AW.PIPE.F7.UG-27I.UG-27I-S01 | F7 | UG-27I | UG-27I-S01 | A110 | Dewatering off, extract sheets, reinstate | 1.6799 | m wall | 2 | 3 | UG-27I-S01-A100 | 2 | 2 |  | 2027-07-29 | 2027-08-07
UG-13A-S15-A010 | AW.PIPE.F7.UG-13A.UG-13A-S15 | F7 | UG-13A | UG-13A-S15 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-13A-S15-A020 | AW.PIPE.F7.UG-13A.UG-13A-S15 | F7 | UG-13A | UG-13A-S15 | A020 | Set-out, crossing survey and working platform | 29.1958 | m | 1 | 2 | UG-13A-S15-A010 |  |  | FS from A010; UG-13A-S16-A030 (SS, tie-in team follows the adjacent run) | 2027-03-20 | 2027-03-22
UG-13A-S15-A030 | AW.PIPE.F7.UG-13A.UG-13A-S15 | F7 | UG-13A | UG-13A-S15 | A030 | Pipe-support piling from platform (incl. integrity tests) | 11 | piles | 3 | 4 | UG-13A-S15-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-21 | 2027-03-25 | 2027-03-25
UG-13A-S15-A040 | AW.PIPE.F7.UG-13A.UG-13A-S15 | F7 | UG-13A | UG-13A-S15 | A040 | Install sheet piles (shored lengths) | 58.3917 | m wall | 3 | 4 | UG-13A-S15-A030 | 2 | 2 |  | 2027-03-23 | 2027-03-27 | 2027-03-27
UG-13A-S15-A050 | AW.PIPE.F7.UG-13A.UG-13A-S15 | F7 | UG-13A | UG-13A-S15 | A050 | Install dewatering and draw down | 29.1958 | m | 8 | 10 | UG-13A-S15-A040 | 2 | 2 |  | 2027-03-25 | 2027-04-04
UG-13A-S15-A060 | AW.PIPE.F7.UG-13A.UG-13A-S15 | F7 | UG-13A | UG-13A-S15 | A060 | Excavate and strut to formation | 411.6609 | m3 | 2 | 3 | UG-13A-S15-A050 | 10 | 2 |  | 2027-04-04 | 2027-04-07 | 2027-04-07
UG-13A-S15-A070 | AW.PIPE.F7.UG-13A.UG-13A-S15 | F7 | UG-13A | UG-13A-S15 | A070 | Trim piles, blinding and piled slab (incl. cure) | 29.1958 | m | 6 | 7 | UG-13A-S15-A060 | 1 | 2 |  | 2027-04-05 | 2027-04-12 | 2027-04-12
UG-13A-S15-A080 | AW.PIPE.F7.UG-13A.UG-13A-S15 | F7 | UG-13A | UG-13A-S15 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 29.1958 | m | 5 | 6 | UG-13A-S15-A070 | 3 | 2 | UG-13A-S16-A080 (FS, closure) | 2027-06-13 | 2027-06-19 | 2027-06-19
UG-13A-S15-A090 | AW.PIPE.F7.UG-13A.UG-13A-S15 | F7 | UG-13A | UG-13A-S15 | A090 | Surround, joint test and line test | 29.1958 | m | 3 | 4 | UG-13A-S15-A080 | 2 | 2 |  | 2027-06-15 | 2027-06-21
UG-13A-S15-A100 | AW.PIPE.F7.UG-13A.UG-13A-S15 | F7 | UG-13A | UG-13A-S15 | A100 | Backfill to NG and remove struts | 359.5348 | m3 | 2 | 3 | UG-13A-S15-A090 | 2 | 2 |  | 2027-06-17 | 2027-06-23 | 2027-06-23
UG-13A-S15-A110 | AW.PIPE.F7.UG-13A.UG-13A-S15 | F7 | UG-13A | UG-13A-S15 | A110 | Dewatering off, extract sheets, reinstate | 58.3917 | m wall | 3 | 4 | UG-13A-S15-A100 | 1 | 2 |  | 2027-06-18 | 2027-06-25
UG-21-S01-A010 | AW.PIPE.F8.UG-21.UG-21-S01 | F8 | UG-21 | UG-21-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-21-S01-A020 | AW.PIPE.F8.UG-21.UG-21-S01 | F8 | UG-21 | UG-21-S01 | A020 | Set-out, crossing survey and working platform | 12.2026 | m | 1 | 2 | UG-21-S01-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-21-S01-A030 | AW.PIPE.F8.UG-21.UG-21-S01 | F8 | UG-21 | UG-21-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 12 | piles | 2 | 3 | UG-21-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-05 | 2026-12-05
UG-21-S01-A040 | AW.PIPE.F8.UG-21.UG-21-S01 | F8 | UG-21 | UG-21-S01 | A040 | Install sheet piles (shored lengths) | 24.4052 | m wall | 1 | 2 | UG-21-S01-A030 | 1 | 2 |  | 2026-12-03 | 2026-12-07 | 2026-12-07
UG-21-S01-A050 | AW.PIPE.F8.UG-21.UG-21-S01 | F8 | UG-21 | UG-21-S01 | A050 | Install dewatering and draw down | 12.2026 | m | 8 | 10 | UG-21-S01-A040 | 1 | 2 |  | 2026-12-04 | 2026-12-14
UG-21-S01-A060 | AW.PIPE.F8.UG-21.UG-21-S01 | F8 | UG-21 | UG-21-S01 | A060 | Excavate and strut to formation | 289.0006 | m3 | 1 | 2 | UG-21-S01-A050 | 10 | 2 |  | 2026-12-14 | 2026-12-16 | 2026-12-16
UG-21-S01-A070 | AW.PIPE.F8.UG-21.UG-21-S01 | F8 | UG-21 | UG-21-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 12.2026 | m | 4 | 5 | UG-21-S01-A060 | 1 | 2 |  | 2026-12-15 | 2026-12-20 | 2026-12-20
UG-21-S01-A080 | AW.PIPE.F8.UG-21.UG-21-S01 | F8 | UG-21 | UG-21-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 12.2026 | m | 4 | 5 | UG-21-S01-A070 | 2 | 2 |  | 2026-12-17 | 2026-12-22 | 2026-12-22
UG-21-S01-A090 | AW.PIPE.F8.UG-21.UG-21-S01 | F8 | UG-21 | UG-21-S01 | A090 | Surround, joint test and line test | 12.2026 | m | 3 | 4 | UG-21-S01-A080 | 2 | 2 |  | 2026-12-19 | 2026-12-24
UG-21-S01-A100 | AW.PIPE.F8.UG-21.UG-21-S01 | F8 | UG-21 | UG-21-S01 | A100 | Backfill to NG and remove struts | 219.3467 | m3 | 1 | 2 | UG-21-S01-A090 | 2 | 2 | UG-22-S01-A080 (FS, shared trench laid); UG-28-S02-A080 (FS, shared trench laid) | 2026-12-24 | 2026-12-26 | 2026-12-26
UG-21-S01-A110 | AW.PIPE.F8.UG-21.UG-21-S01 | F8 | UG-21 | UG-21-S01 | A110 | Dewatering off, extract sheets, reinstate | 24.4052 | m wall | 2 | 3 | UG-21-S01-A100 | 1 | 2 |  | 2026-12-25 | 2026-12-28
UG-22-S01-A010 | AW.PIPE.F8.UG-22.UG-22-S01 | F8 | UG-22 | UG-22-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-22-S01-A020 | AW.PIPE.F8.UG-22.UG-22-S01 | F8 | UG-22 | UG-22-S01 | A020 | Set-out, crossing survey and working platform | 12.2104 | m | 1 | 2 | UG-22-S01-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-22-S01-A030 | AW.PIPE.F8.UG-22.UG-22-S01 | F8 | UG-22 | UG-22-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 12 | piles | 2 | 3 | UG-22-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-05 | 2026-12-05
UG-22-S01-A040 | AW.PIPE.F8.UG-22.UG-22-S01 | F8 | UG-22 | UG-22-S01 | A040 | Install sheet piles (shored lengths) | 24.4208 | m wall | 1 | 2 | UG-22-S01-A030 | 1 | 2 |  | 2026-12-03 | 2026-12-07 | 2026-12-07
UG-22-S01-A050 | AW.PIPE.F8.UG-22.UG-22-S01 | F8 | UG-22 | UG-22-S01 | A050 | Install dewatering and draw down | 12.2104 | m | 8 | 10 | UG-22-S01-A040 | 1 | 2 |  | 2026-12-04 | 2026-12-14
UG-22-S01-A060 | AW.PIPE.F8.UG-22.UG-22-S01 | F8 | UG-22 | UG-22-S01 | A060 | Excavate and strut to formation | 289.1853 | m3 | 1 | 2 | UG-22-S01-A050 | 10 | 2 | UG-21-S01-A060 (SS, shared trench) | 2026-12-14 | 2026-12-16 | 2026-12-16
UG-22-S01-A070 | AW.PIPE.F8.UG-22.UG-22-S01 | F8 | UG-22 | UG-22-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 12.2104 | m | 4 | 5 | UG-22-S01-A060 | 1 | 2 |  | 2026-12-15 | 2026-12-20 | 2026-12-20
UG-22-S01-A080 | AW.PIPE.F8.UG-22.UG-22-S01 | F8 | UG-22 | UG-22-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 12.2104 | m | 4 | 5 | UG-22-S01-A070 | 2 | 2 |  | 2026-12-17 | 2026-12-22 | 2026-12-22
UG-22-S01-A090 | AW.PIPE.F8.UG-22.UG-22-S01 | F8 | UG-22 | UG-22-S01 | A090 | Surround, joint test and line test | 12.2104 | m | 3 | 4 | UG-22-S01-A080 | 2 | 2 |  | 2026-12-19 | 2026-12-24
UG-22-S01-A100 | AW.PIPE.F8.UG-22.UG-22-S01 | F8 | UG-22 | UG-22-S01 | A100 | Backfill to NG and remove struts | 219.4869 | m3 | 1 | 2 | UG-22-S01-A090 | 2 | 2 | UG-21-S01-A080 (FS, shared trench laid); UG-28-S02-A080 (FS, shared trench laid) | 2026-12-24 | 2026-12-26 | 2026-12-26
UG-22-S01-A110 | AW.PIPE.F8.UG-22.UG-22-S01 | F8 | UG-22 | UG-22-S01 | A110 | Dewatering off, extract sheets, reinstate | 24.4208 | m wall | 2 | 3 | UG-22-S01-A100 | 1 | 2 |  | 2026-12-25 | 2026-12-28
UG-28-S02-A010 | AW.PIPE.F8.UG-28.UG-28-S02 | F8 | UG-28 | UG-28-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-28-S02-A020 | AW.PIPE.F8.UG-28.UG-28-S02 | F8 | UG-28 | UG-28-S02 | A020 | Set-out, crossing survey and working platform | 12.4454 | m | 1 | 2 | UG-28-S02-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-28-S02-A030 | AW.PIPE.F8.UG-28.UG-28-S02 | F8 | UG-28 | UG-28-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 6 | piles | 1 | 2 | UG-28-S02-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-05 | 2026-12-05
UG-28-S02-A040 | AW.PIPE.F8.UG-28.UG-28-S02 | F8 | UG-28 | UG-28-S02 | A040 | Install sheet piles (shored lengths) | 24.8909 | m wall | 1 | 2 | UG-28-S02-A030 | 1 | 2 |  | 2026-12-03 | 2026-12-07 | 2026-12-07
UG-28-S02-A050 | AW.PIPE.F8.UG-28.UG-28-S02 | F8 | UG-28 | UG-28-S02 | A050 | Install dewatering and draw down | 12.4454 | m | 8 | 10 | UG-28-S02-A040 | 1 | 2 |  | 2026-12-04 | 2026-12-14
UG-28-S02-A060 | AW.PIPE.F8.UG-28.UG-28-S02 | F8 | UG-28 | UG-28-S02 | A060 | Excavate and strut to formation | 152.4565 | m3 | 1 | 2 | UG-28-S02-A050 | 10 | 2 | UG-21-S01-A060 (SS, shared trench); UG-22-S01-A060 (SS, shared trench) | 2026-12-14 | 2026-12-16 | 2026-12-16
UG-28-S02-A070 | AW.PIPE.F8.UG-28.UG-28-S02 | F8 | UG-28 | UG-28-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 12.4454 | m | 4 | 5 | UG-28-S02-A060 | 1 | 2 |  | 2026-12-15 | 2026-12-20 | 2026-12-20
UG-28-S02-A080 | AW.PIPE.F8.UG-28.UG-28-S02 | F8 | UG-28 | UG-28-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 12.4454 | m | 6 | 7 | UG-28-S02-A070 | 2 | 2 |  | 2026-12-17 | 2026-12-24 | 2026-12-24
UG-28-S02-A090 | AW.PIPE.F8.UG-28.UG-28-S02 | F8 | UG-28 | UG-28-S02 | A090 | Surround, joint test and line test | 12.4454 | m | 3 | 4 | UG-28-S02-A080 | 3 | 2 |  | 2026-12-20 | 2026-12-26
UG-28-S02-A100 | AW.PIPE.F8.UG-28.UG-28-S02 | F8 | UG-28 | UG-28-S02 | A100 | Backfill to NG and remove struts | 140.6787 | m3 | 1 | 2 | UG-28-S02-A090 | 2 | 2 | UG-21-S01-A080 (FS, shared trench laid); UG-22-S01-A080 (FS, shared trench laid) | 2026-12-22 | 2026-12-28 | 2026-12-28
UG-28-S02-A110 | AW.PIPE.F8.UG-28.UG-28-S02 | F8 | UG-28 | UG-28-S02 | A110 | Dewatering off, extract sheets, reinstate | 24.8909 | m wall | 2 | 3 | UG-28-S02-A100 | 1 | 2 |  | 2026-12-23 | 2026-12-30
UG-15-S01-A010 | AW.PIPE.F8.UG-15.UG-15-S01 | F8 | UG-15 | UG-15-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-15-S01-A020 | AW.PIPE.F8.UG-15.UG-15-S01 | F8 | UG-15 | UG-15-S01 | A020 | Set-out, crossing survey and working platform | 49.3 | m | 1 | 2 | UG-15-S01-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-15-S01-A030 | AW.PIPE.F8.UG-15.UG-15-S01 | F8 | UG-15 | UG-15-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 36 | piles | 4 | 5 | UG-15-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-07 | 2026-12-07
UG-15-S01-A040 | AW.PIPE.F8.UG-15.UG-15-S01 | F8 | UG-15 | UG-15-S01 | A040 | Install sheet piles (shored lengths) | 98.6 | m wall | 2 | 3 | UG-15-S01-A030 | 2 | 2 |  | 2026-12-04 | 2026-12-09 | 2026-12-09
UG-15-S01-A050 | AW.PIPE.F8.UG-15.UG-15-S01 | F8 | UG-15 | UG-15-S01 | A050 | Install dewatering and draw down | 49.3 | m | 9 | 11 | UG-15-S01-A040 | 1 | 2 |  | 2026-12-05 | 2026-12-16
UG-15-S01-A060 | AW.PIPE.F8.UG-15.UG-15-S01 | F8 | UG-15 | UG-15-S01 | A060 | Excavate and strut to formation | 920.8634 | m3 | 2 | 3 | UG-15-S01-A050 | 10 | 2 |  | 2026-12-15 | 2026-12-18 | 2026-12-18
UG-15-S01-A070 | AW.PIPE.F8.UG-15.UG-15-S01 | F8 | UG-15 | UG-15-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 49.3 | m | 6 | 7 | UG-15-S01-A060 | 1 | 2 |  | 2026-12-16 | 2026-12-23 | 2026-12-23
UG-15-S01-A080 | AW.PIPE.F8.UG-15.UG-15-S01 | F8 | UG-15 | UG-15-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 49.3 | m | 3 | 4 | UG-15-S01-A070 | 3 | 2 |  | 2026-12-19 | 2026-12-25 | 2026-12-25
UG-15-S01-A090 | AW.PIPE.F8.UG-15.UG-15-S01 | F8 | UG-15 | UG-15-S01 | A090 | Surround, joint test and line test | 49.3 | m | 3 | 4 | UG-15-S01-A080 | 2 | 2 |  | 2026-12-21 | 2026-12-27
UG-15-S01-A100 | AW.PIPE.F8.UG-15.UG-15-S01 | F8 | UG-15 | UG-15-S01 | A100 | Backfill to NG and remove struts | 683.9628 | m3 | 1 | 2 | UG-15-S01-A090 | 2 | 2 | UG-15A-S06-A080 (FS, shared trench laid); UG-15A-S09-A080 (FS, shared trench laid); UG-15A-S10-A080 (FS, shared trench laid) | 2027-01-06 | 2027-01-08 | 2027-01-08
UG-15-S01-A110 | AW.PIPE.F8.UG-15.UG-15-S01 | F8 | UG-15 | UG-15-S01 | A110 | Dewatering off, extract sheets, reinstate | 98.6 | m wall | 3 | 4 | UG-15-S01-A100 | 1 | 2 |  | 2027-01-07 | 2027-01-11
UG-15A-S10-A010 | AW.PIPE.F8.UG-15A.UG-15A-S10 | F8 | UG-15A | UG-15A-S10 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-15A-S10-A020 | AW.PIPE.F8.UG-15A.UG-15A-S10 | F8 | UG-15A | UG-15A-S10 | A020 | Set-out, crossing survey and working platform | 6.3125 | m | 1 | 2 | UG-15A-S10-A010 |  |  | FS from A010; UG-15-S01-A030 (SS, set-out one package ahead of piling) | 2026-12-02 | 2026-12-04
UG-15A-S10-A030 | AW.PIPE.F8.UG-15A.UG-15A-S10 | F8 | UG-15A | UG-15A-S10 | A030 | Pipe-support piling from platform (incl. integrity tests) | 8 | piles | 1 | 2 | UG-15A-S10-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-07 | 2026-12-09 | 2026-12-09 | UG-15-S01-A030
UG-15A-S10-A040 | AW.PIPE.F8.UG-15A.UG-15A-S10 | F8 | UG-15A | UG-15A-S10 | A040 | Install sheet piles (shored lengths) | 12.6249 | m wall | 1 | 2 | UG-15A-S10-A030 | 1 | 2 |  | 2026-12-09 | 2026-12-11 | 2026-12-11 | UG-15-S01-A040
UG-15A-S10-A050 | AW.PIPE.F8.UG-15A.UG-15A-S10 | F8 | UG-15A | UG-15A-S10 | A050 | Install dewatering and draw down | 6.3125 | m | 8 | 10 | UG-15A-S10-A040 | 1 | 2 | UG-15-S01-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2026-12-10 | 2026-12-20
UG-15A-S10-A060 | AW.PIPE.F8.UG-15A.UG-15A-S10 | F8 | UG-15A | UG-15A-S10 | A060 | Excavate and strut to formation | 83.7718 | m3 | 1 | 2 | UG-15A-S10-A050 | 10 | 2 | UG-15-S01-A060 (SS, shared trench) | 2026-12-20 | 2026-12-22 | 2026-12-22 | UG-15-S01-A060
UG-15A-S10-A070 | AW.PIPE.F8.UG-15A.UG-15A-S10 | F8 | UG-15A | UG-15A-S10 | A070 | Trim piles, blinding and piled slab (incl. cure) | 6.3125 | m | 4 | 5 | UG-15A-S10-A060 | 1 | 2 |  | 2026-12-23 | 2026-12-28 | 2026-12-28 | UG-15-S01-A070
UG-15A-S10-A080 | AW.PIPE.F8.UG-15A.UG-15A-S10 | F8 | UG-15A | UG-15A-S10 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 6.3125 | m | 1 | 2 | UG-15A-S10-A070 | 2 | 2 |  | 2026-12-25 | 2026-12-30 | 2026-12-30 | UG-15-S01-A080
UG-15A-S10-A090 | AW.PIPE.F8.UG-15A.UG-15A-S10 | F8 | UG-15A | UG-15A-S10 | A090 | Surround, joint test and line test | 6.3125 | m | 3 | 4 | UG-15A-S10-A080 | 1 | 2 |  | 2026-12-26 | 2027-01-01
UG-15A-S10-A100 | AW.PIPE.F8.UG-15A.UG-15A-S10 | F8 | UG-15A | UG-15A-S10 | A100 | Backfill to NG and remove struts | 69.5013 | m3 | 1 | 2 | UG-15A-S10-A090 | 2 | 2 | UG-15-S01-A080 (FS, shared trench laid); UG-17-S02-A080 (FS, shared trench laid) | 2027-01-17 | 2027-01-19 | 2027-01-19 | UG-15-S01-A100
UG-15A-S10-A110 | AW.PIPE.F8.UG-15A.UG-15A-S10 | F8 | UG-15A | UG-15A-S10 | A110 | Dewatering off, extract sheets, reinstate | 12.6249 | m wall | 2 | 3 | UG-15A-S10-A100 | 1 | 2 |  | 2027-01-18 | 2027-01-21
UG-15A-S09-A010 | AW.PIPE.F8.UG-15A.UG-15A-S09 | F8 | UG-15A | UG-15A-S09 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-15A-S09-A020 | AW.PIPE.F8.UG-15A.UG-15A-S09 | F8 | UG-15A | UG-15A-S09 | A020 | Set-out, crossing survey and working platform | 0.88082 | m | 1 | 2 | UG-15A-S09-A010 |  |  | FS from A010; UG-15A-S10-A030 (SS, tie-in team follows the adjacent run) | 2026-12-07 | 2026-12-09
UG-15A-S09-A030 | AW.PIPE.F8.UG-15A.UG-15A-S09 | F8 | UG-15A | UG-15A-S09 | A030 | Pipe-support piling from platform (incl. integrity tests) | 4 | piles | 1 | 2 | UG-15A-S09-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-08 | 2026-12-11 | 2026-12-11
UG-15A-S09-A040 | AW.PIPE.F8.UG-15A.UG-15A-S09 | F8 | UG-15A | UG-15A-S09 | A040 | Install sheet piles (shored lengths) | 1.7616 | m wall | 1 | 2 | UG-15A-S09-A030 | 1 | 2 |  | 2026-12-09 | 2026-12-13 | 2026-12-13
UG-15A-S09-A050 | AW.PIPE.F8.UG-15A.UG-15A-S09 | F8 | UG-15A | UG-15A-S09 | A050 | Install dewatering and draw down | 0.88082 | m | 8 | 10 | UG-15A-S09-A040 | 1 | 2 |  | 2026-12-10 | 2026-12-20
UG-15A-S09-A060 | AW.PIPE.F8.UG-15A.UG-15A-S09 | F8 | UG-15A | UG-15A-S09 | A060 | Excavate and strut to formation | 11.595 | m3 | 1 | 2 | UG-15A-S09-A050 | 10 | 2 | UG-15-S01-A060 (SS, shared trench) | 2026-12-20 | 2026-12-22 | 2026-12-22
UG-15A-S09-A070 | AW.PIPE.F8.UG-15A.UG-15A-S09 | F8 | UG-15A | UG-15A-S09 | A070 | Trim piles, blinding and piled slab (incl. cure) | 0.88082 | m | 4 | 5 | UG-15A-S09-A060 | 1 | 2 |  | 2026-12-21 | 2026-12-26 | 2026-12-26
UG-15A-S09-A080 | AW.PIPE.F8.UG-15A.UG-15A-S09 | F8 | UG-15A | UG-15A-S09 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 0.88082 | m | 4 | 5 | UG-15A-S09-A070 | 2 | 2 | UG-15A-S10-A080 (FS, closure) | 2026-12-30 | 2027-01-04 | 2027-01-04
UG-15A-S09-A090 | AW.PIPE.F8.UG-15A.UG-15A-S09 | F8 | UG-15A | UG-15A-S09 | A090 | Surround, joint test and line test | 0.88082 | m | 3 | 4 | UG-15A-S09-A080 | 2 | 2 |  | 2027-01-01 | 2027-01-06
UG-15A-S09-A100 | AW.PIPE.F8.UG-15A.UG-15A-S09 | F8 | UG-15A | UG-15A-S09 | A100 | Backfill to NG and remove struts | 9.6431 | m3 | 1 | 2 | UG-15A-S09-A090 | 2 | 2 | UG-15-S01-A080 (FS, shared trench laid) | 2027-01-03 | 2027-01-08 | 2027-01-08
UG-15A-S09-A110 | AW.PIPE.F8.UG-15A.UG-15A-S09 | F8 | UG-15A | UG-15A-S09 | A110 | Dewatering off, extract sheets, reinstate | 1.7616 | m wall | 2 | 3 | UG-15A-S09-A100 | 1 | 2 |  | 2027-01-04 | 2027-01-10
UG-15A-S06-A010 | AW.PIPE.F8.UG-15A.UG-15A-S06 | F8 | UG-15A | UG-15A-S06 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-15A-S06-A020 | AW.PIPE.F8.UG-15A.UG-15A-S06 | F8 | UG-15A | UG-15A-S06 | A020 | Set-out, crossing survey and working platform | 62.5267 | m | 1 | 2 | UG-15A-S06-A010 |  |  | FS from A010; UG-15A-S10-A030 (SS, set-out one package ahead of piling) | 2026-12-07 | 2026-12-09
UG-15A-S06-A030 | AW.PIPE.F8.UG-15A.UG-15A-S06 | F8 | UG-15A | UG-15A-S06 | A030 | Pipe-support piling from platform (incl. integrity tests) | 44 | piles | 5 | 6 | UG-15A-S06-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-09 | 2026-12-15 | 2026-12-15 | UG-15A-S10-A030
UG-15A-S06-A040 | AW.PIPE.F8.UG-15A.UG-15A-S06 | F8 | UG-15A | UG-15A-S06 | A040 | Install sheet piles (shored lengths) | 125.0534 | m wall | 3 | 4 | UG-15A-S06-A030 | 2 | 2 |  | 2026-12-11 | 2026-12-17 | 2026-12-17 | UG-15A-S10-A040
UG-15A-S06-A050 | AW.PIPE.F8.UG-15A.UG-15A-S06 | F8 | UG-15A | UG-15A-S06 | A050 | Install dewatering and draw down | 62.5267 | m | 9 | 11 | UG-15A-S06-A040 | 2 | 2 | UG-15A-S10-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2026-12-13 | 2026-12-24
UG-15A-S06-A060 | AW.PIPE.F8.UG-15A.UG-15A-S06 | F8 | UG-15A | UG-15A-S06 | A060 | Excavate and strut to formation | 949.8489 | m3 | 2 | 3 | UG-15A-S06-A050 | 10 | 2 | UG-15-S01-A060 (SS, shared trench) | 2026-12-23 | 2026-12-26 | 2026-12-26 | UG-15A-S10-A060
UG-15A-S06-A070 | AW.PIPE.F8.UG-15A.UG-15A-S06 | F8 | UG-15A | UG-15A-S06 | A070 | Trim piles, blinding and piled slab (incl. cure) | 62.5267 | m | 6 | 7 | UG-15A-S06-A060 | 1 | 2 |  | 2026-12-28 | 2027-01-04 | 2027-01-04 | UG-15A-S10-A070
UG-15A-S06-A080 | AW.PIPE.F8.UG-15A.UG-15A-S06 | F8 | UG-15A | UG-15A-S06 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 62.5267 | m | 3 | 4 | UG-15A-S06-A070 | 3 | 2 |  | 2026-12-31 | 2027-01-06 | 2027-01-06 | UG-15A-S10-A080
UG-15A-S06-A090 | AW.PIPE.F8.UG-15A.UG-15A-S06 | F8 | UG-15A | UG-15A-S06 | A090 | Surround, joint test and line test | 62.5267 | m | 3 | 4 | UG-15A-S06-A080 | 2 | 2 |  | 2027-01-02 | 2027-01-08
UG-15A-S06-A100 | AW.PIPE.F8.UG-15A.UG-15A-S06 | F8 | UG-15A | UG-15A-S06 | A100 | Backfill to NG and remove struts | 741.7514 | m3 | 2 | 3 | UG-15A-S06-A090 | 2 | 2 | UG-15-S01-A080 (FS, shared trench laid); UG-17-S02-A080 (FS, shared trench laid); UG-17-S03-A080 (FS, shared trench laid) | 2027-04-06 | 2027-04-09 | 2027-04-09 | UG-15A-S10-A100
UG-15A-S06-A110 | AW.PIPE.F8.UG-15A.UG-15A-S06 | F8 | UG-15A | UG-15A-S06 | A110 | Dewatering off, extract sheets, reinstate | 125.0534 | m wall | 4 | 5 | UG-15A-S06-A100 | 1 | 2 |  | 2027-04-07 | 2027-04-12
UG-17-S02-A010 | AW.PIPE.F8.UG-17.UG-17-S02 | F8 | UG-17 | UG-17-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-17-S02-A020 | AW.PIPE.F8.UG-17.UG-17-S02 | F8 | UG-17 | UG-17-S02 | A020 | Set-out, crossing survey and working platform | 45.2674 | m | 1 | 2 | UG-17-S02-A010 |  |  | FS from A010; UG-15A-S06-A030 (SS, set-out one package ahead of piling) | 2026-12-09 | 2026-12-11
UG-17-S02-A030 | AW.PIPE.F8.UG-17.UG-17-S02 | F8 | UG-17 | UG-17-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 34 | piles | 4 | 5 | UG-17-S02-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-15 | 2026-12-20 | 2026-12-20 | UG-15A-S06-A030
UG-17-S02-A040 | AW.PIPE.F8.UG-17.UG-17-S02 | F8 | UG-17 | UG-17-S02 | A040 | Install sheet piles (shored lengths) | 80 | m wall | 2 | 3 | UG-17-S02-A030 | 2 | 2 |  | 2026-12-17 | 2026-12-22 | 2026-12-22 | UG-15A-S06-A040
UG-17-S02-A050 | AW.PIPE.F8.UG-17.UG-17-S02 | F8 | UG-17 | UG-17-S02 | A050 | Install dewatering and draw down | 45.2674 | m | 9 | 11 | UG-17-S02-A040 | 1 | 2 | UG-15A-S06-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2026-12-18 | 2026-12-29
UG-17-S02-A060 | AW.PIPE.F8.UG-17.UG-17-S02 | F8 | UG-17 | UG-17-S02 | A060 | Excavate and strut to formation | 782.365 | m3 | 2 | 3 | UG-17-S02-A050 | 10 | 2 | UG-15-S01-A100 (FS, deeper first); UG-15A-S06-A060 (SS, shared trench); UG-15A-S10-A060 (SS, shared trench) | 2027-01-08 | 2027-01-11 | 2027-01-11 | UG-15A-S06-A060
UG-17-S02-A070 | AW.PIPE.F8.UG-17.UG-17-S02 | F8 | UG-17 | UG-17-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 45.2674 | m | 5 | 6 | UG-17-S02-A060 | 1 | 2 |  | 2027-01-09 | 2027-01-15 | 2027-01-15 | UG-15A-S06-A070
UG-17-S02-A080 | AW.PIPE.F8.UG-17.UG-17-S02 | F8 | UG-17 | UG-17-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 45.2674 | m | 3 | 4 | UG-17-S02-A070 | 2 | 2 |  | 2027-01-11 | 2027-01-17 | 2027-01-17 | UG-15A-S06-A080
UG-17-S02-A090 | AW.PIPE.F8.UG-17.UG-17-S02 | F8 | UG-17 | UG-17-S02 | A090 | Surround, joint test and line test | 45.2674 | m | 3 | 4 | UG-17-S02-A080 | 2 | 2 |  | 2027-01-13 | 2027-01-19
UG-17-S02-A100 | AW.PIPE.F8.UG-17.UG-17-S02 | F8 | UG-17 | UG-17-S02 | A100 | Backfill to NG and remove struts | 523.9731 | m3 | 1 | 2 | UG-17-S02-A090 | 2 | 2 | UG-15A-S06-A080 (FS, shared trench laid); UG-15A-S10-A080 (FS, shared trench laid); UG-18-S01-A080 (FS, shared trench laid); UG-18-S02-A080 (FS, shared trench laid) | 2027-05-08 | 2027-05-10 | 2027-05-10 | UG-15A-S06-A100
UG-17-S02-A110 | AW.PIPE.F8.UG-17.UG-17-S02 | F8 | UG-17 | UG-17-S02 | A110 | Dewatering off, extract sheets, reinstate | 80 | m wall | 3 | 4 | UG-17-S02-A100 | 1 | 2 |  | 2027-05-09 | 2027-05-13
UG-19-S03-A010 | AW.PIPE.F8.UG-19.UG-19-S03 | F8 | UG-19 | UG-19-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-19-S03-A020 | AW.PIPE.F8.UG-19.UG-19-S03 | F8 | UG-19 | UG-19-S03 | A020 | Set-out, crossing survey and working platform | 82.2204 | m | 2 | 3 | UG-19-S03-A010 |  |  | FS from A010; UG-17-S02-A030 (SS, set-out one package ahead of piling) | 2026-12-15 | 2026-12-18
UG-19-S03-A030 | AW.PIPE.F8.UG-19.UG-19-S03 | F8 | UG-19 | UG-19-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 58 | piles | 6 | 7 | UG-19-S03-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-20 | 2026-12-27 | 2026-12-27 | UG-17-S02-A030
UG-19-S03-A040 | AW.PIPE.F8.UG-19.UG-19-S03 | F8 | UG-19 | UG-19-S03 | A040 | Install sheet piles (shored lengths) | 164.4409 | m wall | 4 | 5 | UG-19-S03-A030 | 3 | 2 |  | 2026-12-23 | 2026-12-29 | 2026-12-29 | UG-17-S02-A040
UG-19-S03-A050 | AW.PIPE.F8.UG-19.UG-19-S03 | F8 | UG-19 | UG-19-S03 | A050 | Install dewatering and draw down | 82.2204 | m | 10 | 12 | UG-19-S03-A040 | 2 | 2 | UG-17-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2026-12-30 | 2027-01-11
UG-19-S03-A060 | AW.PIPE.F8.UG-19.UG-19-S03 | F8 | UG-19 | UG-19-S03 | A060 | Excavate and strut to formation | 1202.9904 | m3 | 3 | 4 | UG-19-S03-A050 | 10 | 2 |  | 2027-01-11 | 2027-01-15 | 2027-01-15 | UG-17-S02-A060
UG-19-S03-A070 | AW.PIPE.F8.UG-19.UG-19-S03 | F8 | UG-19 | UG-19-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 82.2204 | m | 7 | 9 | UG-19-S03-A060 | 2 | 2 |  | 2027-01-15 | 2027-01-24 | 2027-01-24 | UG-17-S02-A070
UG-19-S03-A080 | AW.PIPE.F8.UG-19.UG-19-S03 | F8 | UG-19 | UG-19-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 82.2204 | m | 5 | 6 | UG-19-S03-A070 | 3 | 2 |  | 2027-01-18 | 2027-01-26 | 2027-01-26 | UG-17-S02-A080
UG-19-S03-A090 | AW.PIPE.F8.UG-19.UG-19-S03 | F8 | UG-19 | UG-19-S03 | A090 | Surround, joint test and line test | 82.2204 | m | 3 | 4 | UG-19-S03-A080 | 2 | 2 |  | 2027-01-20 | 2027-01-28
UG-19-S03-A100 | AW.PIPE.F8.UG-19.UG-19-S03 | F8 | UG-19 | UG-19-S03 | A100 | Backfill to NG and remove struts | 862.5244 | m3 | 2 | 3 | UG-19-S03-A090 | 2 | 2 | UG-20-S02-A080 (FS, shared trench laid) | 2027-05-10 | 2027-05-13 | 2027-05-13 | UG-17-S02-A100
UG-19-S03-A110 | AW.PIPE.F8.UG-19.UG-19-S03 | F8 | UG-19 | UG-19-S03 | A110 | Dewatering off, extract sheets, reinstate | 164.4409 | m wall | 5 | 6 | UG-19-S03-A100 | 1 | 2 |  | 2027-05-11 | 2027-05-17
UG-20-S02-A010 | AW.PIPE.F8.UG-20.UG-20-S02 | F8 | UG-20 | UG-20-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-20-S02-A020 | AW.PIPE.F8.UG-20.UG-20-S02 | F8 | UG-20 | UG-20-S02 | A020 | Set-out, crossing survey and working platform | 107.0069 | m | 2 | 3 | UG-20-S02-A010 |  |  | FS from A010; UG-19-S03-A030 (SS, set-out one package ahead of piling) | 2026-12-20 | 2026-12-23
UG-20-S02-A030 | AW.PIPE.F8.UG-20.UG-20-S02 | F8 | UG-20 | UG-20-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 74 | piles | 8 | 10 | UG-20-S02-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-27 | 2027-01-06 | 2027-01-06 | UG-19-S03-A030
UG-20-S02-A040 | AW.PIPE.F8.UG-20.UG-20-S02 | F8 | UG-20 | UG-20-S02 | A040 | Install sheet piles (shored lengths) | 214.0138 | m wall | 5 | 6 | UG-20-S02-A030 | 3 | 2 |  | 2026-12-30 | 2027-01-08 | 2027-01-08 | UG-19-S03-A040
UG-20-S02-A050 | AW.PIPE.F8.UG-20.UG-20-S02 | F8 | UG-20 | UG-20-S02 | A050 | Install dewatering and draw down | 107.0069 | m | 10 | 12 | UG-20-S02-A040 | 2 | 2 | UG-19-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-03 | 2027-01-15
UG-20-S02-A060 | AW.PIPE.F8.UG-20.UG-20-S02 | F8 | UG-20 | UG-20-S02 | A060 | Excavate and strut to formation | 1532.138 | m3 | 4 | 5 | UG-20-S02-A050 | 10 | 2 | UG-19-S03-A060 (SS, shared trench) | 2027-01-15 | 2027-01-20 | 2027-01-20 | UG-19-S03-A060
UG-20-S02-A070 | AW.PIPE.F8.UG-20.UG-20-S02 | F8 | UG-20 | UG-20-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 107.0069 | m | 8 | 10 | UG-20-S02-A060 | 2 | 2 |  | 2027-01-24 | 2027-02-03 | 2027-02-03 | UG-19-S03-A070
UG-20-S02-A080 | AW.PIPE.F8.UG-20.UG-20-S02 | F8 | UG-20 | UG-20-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 107.0069 | m | 6 | 7 | UG-20-S02-A070 | 3 | 2 |  | 2027-01-27 | 2027-02-05 | 2027-02-05 | UG-19-S03-A080
UG-20-S02-A090 | AW.PIPE.F8.UG-20.UG-20-S02 | F8 | UG-20 | UG-20-S02 | A090 | Surround, joint test and line test | 107.0069 | m | 3 | 4 | UG-20-S02-A080 | 3 | 2 |  | 2027-01-30 | 2027-02-07
UG-20-S02-A100 | AW.PIPE.F8.UG-20.UG-20-S02 | F8 | UG-20 | UG-20-S02 | A100 | Backfill to NG and remove struts | 1088.8425 | m3 | 2 | 3 | UG-20-S02-A090 | 2 | 2 | UG-18-S02-A080 (FS, shared trench laid); UG-19-S01-A080 (FS, shared trench laid); UG-19-S02-A080 (FS, shared trench laid); UG-19-S03-A080 (FS, shared trench laid) | 2027-05-13 | 2027-05-16 | 2027-05-16 | UG-19-S03-A100
UG-20-S02-A110 | AW.PIPE.F8.UG-20.UG-20-S02 | F8 | UG-20 | UG-20-S02 | A110 | Dewatering off, extract sheets, reinstate | 214.0138 | m wall | 6 | 7 | UG-20-S02-A100 | 1 | 2 |  | 2027-05-14 | 2027-05-21
UG-20-S01-A010 | AW.PIPE.F8.UG-20.UG-20-S01 | F8 | UG-20 | UG-20-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-20-S01-A020 | AW.PIPE.F8.UG-20.UG-20-S01 | F8 | UG-20 | UG-20-S01 | A020 | Set-out, crossing survey and working platform | 2.7185 | m | 1 | 2 | UG-20-S01-A010 |  |  | FS from A010; UG-20-S02-A030 (SS, tie-in team follows the adjacent run) | 2026-12-27 | 2026-12-29
UG-20-S01-A030 | AW.PIPE.F8.UG-20.UG-20-S01 | F8 | UG-20 | UG-20-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 4 | piles | 1 | 2 | UG-20-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-28 | 2026-12-31 | 2026-12-31
UG-20-S01-A040 | AW.PIPE.F8.UG-20.UG-20-S01 | F8 | UG-20 | UG-20-S01 | A040 | Install sheet piles (shored lengths) | 5.4369 | m wall | 1 | 2 | UG-20-S01-A030 | 1 | 2 |  | 2026-12-29 | 2027-01-02 | 2027-01-02
UG-20-S01-A050 | AW.PIPE.F8.UG-20.UG-20-S01 | F8 | UG-20 | UG-20-S01 | A050 | Install dewatering and draw down | 2.7185 | m | 8 | 10 | UG-20-S01-A040 | 1 | 2 |  | 2026-12-30 | 2027-01-09
UG-20-S01-A060 | AW.PIPE.F8.UG-20.UG-20-S01 | F8 | UG-20 | UG-20-S01 | A060 | Excavate and strut to formation | 37.9197 | m3 | 1 | 2 | UG-20-S01-A050 | 10 | 2 |  | 2027-01-09 | 2027-01-11 | 2027-01-11
UG-20-S01-A070 | AW.PIPE.F8.UG-20.UG-20-S01 | F8 | UG-20 | UG-20-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 2.7185 | m | 4 | 5 | UG-20-S01-A060 | 1 | 2 |  | 2027-01-10 | 2027-01-15 | 2027-01-15
UG-20-S01-A080 | AW.PIPE.F8.UG-20.UG-20-S01 | F8 | UG-20 | UG-20-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 2.7185 | m | 5 | 6 | UG-20-S01-A070 | 2 | 2 | UG-20-S02-A080 (FS, closure) | 2027-02-05 | 2027-02-11 | 2027-02-11
UG-20-S01-A090 | AW.PIPE.F8.UG-20.UG-20-S01 | F8 | UG-20 | UG-20-S01 | A090 | Surround, joint test and line test | 2.7185 | m | 3 | 4 | UG-20-S01-A080 | 2 | 2 |  | 2027-02-07 | 2027-02-13
UG-20-S01-A100 | AW.PIPE.F8.UG-20.UG-20-S01 | F8 | UG-20 | UG-20-S01 | A100 | Backfill to NG and remove struts | 26.6217 | m3 | 1 | 2 | UG-20-S01-A090 | 2 | 2 | UG-19-S01-A080 (FS, shared trench laid); UG-19-S02-A080 (FS, shared trench laid) | 2027-02-17 | 2027-02-19 | 2027-02-19
UG-20-S01-A110 | AW.PIPE.F8.UG-20.UG-20-S01 | F8 | UG-20 | UG-20-S01 | A110 | Dewatering off, extract sheets, reinstate | 5.4369 | m wall | 2 | 3 | UG-20-S01-A100 | 1 | 2 |  | 2027-02-18 | 2027-02-21
UG-19-S02-A010 | AW.PIPE.F8.UG-19.UG-19-S02 | F8 | UG-19 | UG-19-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-19-S02-A020 | AW.PIPE.F8.UG-19.UG-19-S02 | F8 | UG-19 | UG-19-S02 | A020 | Set-out, crossing survey and working platform | 30.5156 | m | 1 | 2 | UG-19-S02-A010 |  |  | FS from A010; UG-20-S02-A030 (SS, set-out one package ahead of piling) | 2026-12-27 | 2026-12-29
UG-19-S02-A030 | AW.PIPE.F8.UG-19.UG-19-S02 | F8 | UG-19 | UG-19-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 24 | piles | 3 | 4 | UG-19-S02-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-06 | 2027-01-10 | 2027-01-10 | UG-20-S02-A030
UG-19-S02-A040 | AW.PIPE.F8.UG-19.UG-19-S02 | F8 | UG-19 | UG-19-S02 | A040 | Install sheet piles (shored lengths) | 61.0312 | m wall | 2 | 3 | UG-19-S02-A030 | 2 | 2 |  | 2027-01-08 | 2027-01-12 | 2027-01-12 | UG-20-S02-A040
UG-19-S02-A050 | AW.PIPE.F8.UG-19.UG-19-S02 | F8 | UG-19 | UG-19-S02 | A050 | Install dewatering and draw down | 30.5156 | m | 8 | 10 | UG-19-S02-A040 | 1 | 2 | UG-20-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-10 | 2027-01-20
UG-19-S02-A060 | AW.PIPE.F8.UG-19.UG-19-S02 | F8 | UG-19 | UG-19-S02 | A060 | Excavate and strut to formation | 407.6953 | m3 | 1 | 2 | UG-19-S02-A050 | 10 | 2 | UG-20-S01-A060 (SS, shared trench); UG-20-S02-A060 (SS, shared trench) | 2027-01-20 | 2027-01-22 | 2027-01-22 | UG-20-S02-A060
UG-19-S02-A070 | AW.PIPE.F8.UG-19.UG-19-S02 | F8 | UG-19 | UG-19-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 30.5156 | m | 5 | 6 | UG-19-S02-A060 | 1 | 2 |  | 2027-02-03 | 2027-02-09 | 2027-02-09 | UG-20-S02-A070
UG-19-S02-A080 | AW.PIPE.F8.UG-19.UG-19-S02 | F8 | UG-19 | UG-19-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 30.5156 | m | 4 | 5 | UG-19-S02-A070 | 2 | 2 |  | 2027-02-05 | 2027-02-11 | 2027-02-11 | UG-20-S02-A080
UG-19-S02-A090 | AW.PIPE.F8.UG-19.UG-19-S02 | F8 | UG-19 | UG-19-S02 | A090 | Surround, joint test and line test | 30.5156 | m | 3 | 4 | UG-19-S02-A080 | 2 | 2 |  | 2027-02-07 | 2027-02-13
UG-19-S02-A100 | AW.PIPE.F8.UG-19.UG-19-S02 | F8 | UG-19 | UG-19-S02 | A100 | Backfill to NG and remove struts | 281.0555 | m3 | 1 | 2 | UG-19-S02-A090 | 2 | 2 | UG-20-S01-A080 (FS, shared trench laid); UG-20-S02-A080 (FS, shared trench laid) | 2027-05-16 | 2027-05-18 | 2027-05-18 | UG-20-S02-A100
UG-19-S02-A110 | AW.PIPE.F8.UG-19.UG-19-S02 | F8 | UG-19 | UG-19-S02 | A110 | Dewatering off, extract sheets, reinstate | 61.0312 | m wall | 3 | 4 | UG-19-S02-A100 | 1 | 2 |  | 2027-05-17 | 2027-05-21
UG-19-S01-A010 | AW.PIPE.F8.UG-19.UG-19-S01 | F8 | UG-19 | UG-19-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-19-S01-A020 | AW.PIPE.F8.UG-19.UG-19-S01 | F8 | UG-19 | UG-19-S01 | A020 | Set-out, crossing survey and working platform | 2.5061 | m | 1 | 2 | UG-19-S01-A010 |  |  | FS from A010; UG-19-S02-A030 (SS, tie-in team follows the adjacent run) | 2027-01-06 | 2027-01-08
UG-19-S01-A030 | AW.PIPE.F8.UG-19.UG-19-S01 | F8 | UG-19 | UG-19-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 4 | piles | 1 | 2 | UG-19-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-07 | 2027-01-10 | 2027-01-10
UG-19-S01-A040 | AW.PIPE.F8.UG-19.UG-19-S01 | F8 | UG-19 | UG-19-S01 | A040 | Install sheet piles (shored lengths) | 5.0122 | m wall | 1 | 2 | UG-19-S01-A030 | 1 | 2 |  | 2027-01-08 | 2027-01-12 | 2027-01-12
UG-19-S01-A050 | AW.PIPE.F8.UG-19.UG-19-S01 | F8 | UG-19 | UG-19-S01 | A050 | Install dewatering and draw down | 2.5061 | m | 8 | 10 | UG-19-S01-A040 | 1 | 2 |  | 2027-01-09 | 2027-01-19
UG-19-S01-A060 | AW.PIPE.F8.UG-19.UG-19-S01 | F8 | UG-19 | UG-19-S01 | A060 | Excavate and strut to formation | 32.2471 | m3 | 1 | 2 | UG-19-S01-A050 | 10 | 2 | UG-20-S01-A060 (SS, shared trench); UG-20-S02-A060 (SS, shared trench) | 2027-01-19 | 2027-01-21 | 2027-01-21
UG-19-S01-A070 | AW.PIPE.F8.UG-19.UG-19-S01 | F8 | UG-19 | UG-19-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 2.5061 | m | 4 | 5 | UG-19-S01-A060 | 1 | 2 |  | 2027-01-20 | 2027-01-25 | 2027-01-25
UG-19-S01-A080 | AW.PIPE.F8.UG-19.UG-19-S01 | F8 | UG-19 | UG-19-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 2.5061 | m | 5 | 6 | UG-19-S01-A070 | 2 | 2 | UG-19-S02-A080 (FS, closure) | 2027-02-11 | 2027-02-17 | 2027-02-17
UG-19-S01-A090 | AW.PIPE.F8.UG-19.UG-19-S01 | F8 | UG-19 | UG-19-S01 | A090 | Surround, joint test and line test | 2.5061 | m | 3 | 4 | UG-19-S01-A080 | 2 | 2 |  | 2027-02-13 | 2027-02-19
UG-19-S01-A100 | AW.PIPE.F8.UG-19.UG-19-S01 | F8 | UG-19 | UG-19-S01 | A100 | Backfill to NG and remove struts | 21.8316 | m3 | 1 | 2 | UG-19-S01-A090 | 2 | 2 | UG-20-S01-A080 (FS, shared trench laid); UG-20-S02-A080 (FS, shared trench laid) | 2027-02-15 | 2027-02-21 | 2027-02-21
UG-19-S01-A110 | AW.PIPE.F8.UG-19.UG-19-S01 | F8 | UG-19 | UG-19-S01 | A110 | Dewatering off, extract sheets, reinstate | 5.0122 | m wall | 2 | 3 | UG-19-S01-A100 | 1 | 2 |  | 2027-02-16 | 2027-02-23
UG-15A-S08-A010 | AW.PIPE.F8.UG-15A.UG-15A-S08 | F8 | UG-15A | UG-15A-S08 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-15A-S08-A020 | AW.PIPE.F8.UG-15A.UG-15A-S08 | F8 | UG-15A | UG-15A-S08 | A020 | Set-out, crossing survey and working platform | 10.9818 | m | 1 | 2 | UG-15A-S08-A010 |  |  | FS from A010; UG-19-S02-A030 (SS, set-out one package ahead of piling) | 2027-01-06 | 2027-01-08
UG-15A-S08-A030 | AW.PIPE.F8.UG-15A.UG-15A-S08 | F8 | UG-15A | UG-15A-S08 | A030 | Pipe-support piling from platform (incl. integrity tests) | 10 | piles | 1 | 2 | UG-15A-S08-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-10 | 2027-01-12 | 2027-01-12 | UG-19-S02-A030
UG-15A-S08-A040 | AW.PIPE.F8.UG-15A.UG-15A-S08 | F8 | UG-15A | UG-15A-S08 | A040 | Install sheet piles (shored lengths) | 21.9636 | m wall | 1 | 2 | UG-15A-S08-A030 | 1 | 2 |  | 2027-01-12 | 2027-01-14 | 2027-01-14 | UG-19-S02-A040
UG-15A-S08-A050 | AW.PIPE.F8.UG-15A.UG-15A-S08 | F8 | UG-15A | UG-15A-S08 | A050 | Install dewatering and draw down | 10.9818 | m | 8 | 10 | UG-15A-S08-A040 | 1 | 2 | UG-19-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-13 | 2027-01-23
UG-15A-S08-A060 | AW.PIPE.F8.UG-15A.UG-15A-S08 | F8 | UG-15A | UG-15A-S08 | A060 | Excavate and strut to formation | 140.5672 | m3 | 1 | 2 | UG-15A-S08-A050 | 10 | 2 |  | 2027-01-23 | 2027-01-25 | 2027-01-25 | UG-19-S02-A060
UG-15A-S08-A070 | AW.PIPE.F8.UG-15A.UG-15A-S08 | F8 | UG-15A | UG-15A-S08 | A070 | Trim piles, blinding and piled slab (incl. cure) | 10.9818 | m | 4 | 5 | UG-15A-S08-A060 | 1 | 2 |  | 2027-02-09 | 2027-02-14 | 2027-02-14 | UG-19-S02-A070
UG-15A-S08-A080 | AW.PIPE.F8.UG-15A.UG-15A-S08 | F8 | UG-15A | UG-15A-S08 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 10.9818 | m | 1 | 2 | UG-15A-S08-A070 | 2 | 2 |  | 2027-02-11 | 2027-02-16 | 2027-02-16 | UG-19-S02-A080
UG-15A-S08-A090 | AW.PIPE.F8.UG-15A.UG-15A-S08 | F8 | UG-15A | UG-15A-S08 | A090 | Surround, joint test and line test | 10.9818 | m | 3 | 4 | UG-15A-S08-A080 | 1 | 2 |  | 2027-02-12 | 2027-02-18
UG-15A-S08-A100 | AW.PIPE.F8.UG-15A.UG-15A-S08 | F8 | UG-15A | UG-15A-S08 | A100 | Backfill to NG and remove struts | 116.067 | m3 | 1 | 2 | UG-15A-S08-A090 | 2 | 2 | UG-17-S03-A080 (FS, shared trench laid) | 2027-05-18 | 2027-05-20 | 2027-05-20 | UG-19-S02-A100
UG-15A-S08-A110 | AW.PIPE.F8.UG-15A.UG-15A-S08 | F8 | UG-15A | UG-15A-S08 | A110 | Dewatering off, extract sheets, reinstate | 21.9636 | m wall | 2 | 3 | UG-15A-S08-A100 | 1 | 2 |  | 2027-05-19 | 2027-05-22
UG-15A-S05-A010 | AW.PIPE.F8.UG-15A.UG-15A-S05 | F8 | UG-15A | UG-15A-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-15A-S05-A020 | AW.PIPE.F8.UG-15A.UG-15A-S05 | F8 | UG-15A | UG-15A-S05 | A020 | Set-out, crossing survey and working platform | 122.1198 | m | 2 | 3 | UG-15A-S05-A010 |  |  | FS from A010; UG-15A-S08-A030 (SS, set-out one package ahead of piling) | 2027-01-10 | 2027-01-13
UG-15A-S05-A030 | AW.PIPE.F8.UG-15A.UG-15A-S05 | F8 | UG-15A | UG-15A-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 84 | piles | 9 | 11 | UG-15A-S05-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-12 | 2027-01-23 | 2027-01-23 | UG-15A-S08-A030
UG-15A-S05-A040 | AW.PIPE.F8.UG-15A.UG-15A-S05 | F8 | UG-15A | UG-15A-S05 | A040 | Install sheet piles (shored lengths) | 244.2397 | m wall | 5 | 6 | UG-15A-S05-A030 | 4 | 2 |  | 2027-01-16 | 2027-01-25 | 2027-01-25 | UG-15A-S08-A040
UG-15A-S05-A050 | AW.PIPE.F8.UG-15A.UG-15A-S05 | F8 | UG-15A | UG-15A-S05 | A050 | Install dewatering and draw down | 122.1198 | m | 11 | 13 | UG-15A-S05-A040 | 2 | 2 | UG-15A-S08-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-18 | 2027-01-31
UG-15A-S05-A060 | AW.PIPE.F8.UG-15A.UG-15A-S05 | F8 | UG-15A | UG-15A-S05 | A060 | Excavate and strut to formation | 1568.8756 | m3 | 4 | 5 | UG-15A-S05-A050 | 11 | 2 |  | 2027-01-29 | 2027-02-03 | 2027-02-03 | UG-15A-S08-A060
UG-15A-S05-A070 | AW.PIPE.F8.UG-15A.UG-15A-S05 | F8 | UG-15A | UG-15A-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 122.1198 | m | 9 | 11 | UG-15A-S05-A060 | 2 | 2 |  | 2027-02-14 | 2027-02-25 | 2027-02-25 | UG-15A-S08-A070
UG-15A-S05-A080 | AW.PIPE.F8.UG-15A.UG-15A-S05 | F8 | UG-15A | UG-15A-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 122.1198 | m | 6 | 7 | UG-15A-S05-A070 | 4 | 2 |  | 2027-02-18 | 2027-02-27 | 2027-02-27 | UG-15A-S08-A080
UG-15A-S05-A090 | AW.PIPE.F8.UG-15A.UG-15A-S05 | F8 | UG-15A | UG-15A-S05 | A090 | Surround, joint test and line test | 122.1198 | m | 3 | 4 | UG-15A-S05-A080 | 3 | 2 |  | 2027-02-21 | 2027-03-01
UG-15A-S05-A100 | AW.PIPE.F8.UG-15A.UG-15A-S05 | F8 | UG-15A | UG-15A-S05 | A100 | Backfill to NG and remove struts | 1291.7077 | m3 | 2 | 3 | UG-15A-S05-A090 | 2 | 2 | UG-11B-S06-A080 (FS, shared trench laid); UG-17-S03-A080 (FS, shared trench laid); UG-18-S02-A080 (FS, shared trench laid) | 2027-05-20 | 2027-05-23 | 2027-05-23 | UG-15A-S08-A100
UG-15A-S05-A110 | AW.PIPE.F8.UG-15A.UG-15A-S05 | F8 | UG-15A | UG-15A-S05 | A110 | Dewatering off, extract sheets, reinstate | 244.2397 | m wall | 6 | 7 | UG-15A-S05-A100 | 1 | 2 |  | 2027-05-21 | 2027-05-28
UG-17-S04-A010 | AW.PIPE.F8.UG-17.UG-17-S04 | F8 | UG-17 | UG-17-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-17-S04-A020 | AW.PIPE.F8.UG-17.UG-17-S04 | F8 | UG-17 | UG-17-S04 | A020 | Set-out, crossing survey and working platform | 76 | m | 1 | 2 | UG-17-S04-A010 |  |  | FS from A010; UG-15A-S05-A030 (SS, set-out one package ahead of piling) | 2027-01-12 | 2027-01-14
UG-17-S04-A030 | AW.PIPE.F8.UG-17.UG-17-S04 | F8 | UG-17 | UG-17-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 54 | piles | 6 | 7 | UG-17-S04-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-23 | 2027-01-30 | 2027-01-30 | UG-15A-S05-A030
UG-17-S04-A040 | AW.PIPE.F8.UG-17.UG-17-S04 | F8 | UG-17 | UG-17-S04 | A040 | Install sheet piles (shored lengths) | 152 | m wall | 4 | 5 | UG-17-S04-A030 | 3 | 2 |  | 2027-01-26 | 2027-02-01 | 2027-02-01 | UG-15A-S05-A040
UG-17-S04-A050 | AW.PIPE.F8.UG-17.UG-17-S04 | F8 | UG-17 | UG-17-S04 | A050 | Install dewatering and draw down | 76 | m | 9 | 11 | UG-17-S04-A040 | 2 | 2 | UG-15A-S05-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-01-28 | 2027-02-08
UG-17-S04-A060 | AW.PIPE.F8.UG-17.UG-17-S04 | F8 | UG-17 | UG-17-S04 | A060 | Excavate and strut to formation | 1163.9819 | m3 | 3 | 4 | UG-17-S04-A050 | 10 | 2 |  | 2027-02-07 | 2027-02-11 | 2027-02-11 | UG-15A-S05-A060
UG-17-S04-A070 | AW.PIPE.F8.UG-17.UG-17-S04 | F8 | UG-17 | UG-17-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 76 | m | 7 | 9 | UG-17-S04-A060 | 2 | 2 |  | 2027-02-25 | 2027-03-06 | 2027-03-06 | UG-15A-S05-A070
UG-17-S04-A080 | AW.PIPE.F8.UG-17.UG-17-S04 | F8 | UG-17 | UG-17-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 76 | m | 2 | 3 | UG-17-S04-A070 | 3 | 2 |  | 2027-02-28 | 2027-03-08 | 2027-03-08 | UG-15A-S05-A080
UG-17-S04-A090 | AW.PIPE.F8.UG-17.UG-17-S04 | F8 | UG-17 | UG-17-S04 | A090 | Surround, joint test and line test | 76 | m | 3 | 4 | UG-17-S04-A080 | 1 | 2 |  | 2027-03-01 | 2027-03-10
UG-17-S04-A100 | AW.PIPE.F8.UG-17.UG-17-S04 | F8 | UG-17 | UG-17-S04 | A100 | Backfill to NG and remove struts | 738.6049 | m3 | 2 | 3 | UG-17-S04-A090 | 2 | 2 | UG-11B-S05-A080 (FS, shared trench laid); UG-11B-S06-A080 (FS, shared trench laid); UG-18-S02-A080 (FS, shared trench laid) | 2027-05-23 | 2027-05-26 | 2027-05-26 | UG-15A-S05-A100
UG-17-S04-A110 | AW.PIPE.F8.UG-17.UG-17-S04 | F8 | UG-17 | UG-17-S04 | A110 | Dewatering off, extract sheets, reinstate | 152 | m wall | 5 | 6 | UG-17-S04-A100 | 1 | 2 |  | 2027-05-24 | 2027-05-30
UG-17-S05-A010 | AW.PIPE.F8.UG-17.UG-17-S05 | F8 | UG-17 | UG-17-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-17-S05-A020 | AW.PIPE.F8.UG-17.UG-17-S05 | F8 | UG-17 | UG-17-S05 | A020 | Set-out, crossing survey and working platform | 24.9735 | m | 1 | 2 | UG-17-S05-A010 |  |  | FS from A010; UG-17-S04-A030 (SS, set-out one package ahead of piling) | 2027-01-23 | 2027-01-25
UG-17-S05-A030 | AW.PIPE.F8.UG-17.UG-17-S05 | F8 | UG-17 | UG-17-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 20 | piles | 2 | 3 | UG-17-S05-A020 | 1 | 2 | gate: D_PILEDES | 2027-01-30 | 2027-02-02 | 2027-02-02 | UG-17-S04-A030
UG-17-S05-A040 | AW.PIPE.F8.UG-17.UG-17-S05 | F8 | UG-17 | UG-17-S05 | A040 | Install sheet piles (shored lengths) | 49.9469 | m wall | 1 | 2 | UG-17-S05-A030 | 1 | 2 |  | 2027-02-01 | 2027-02-04 | 2027-02-04 | UG-17-S04-A040
UG-17-S05-A050 | AW.PIPE.F8.UG-17.UG-17-S05 | F8 | UG-17 | UG-17-S05 | A050 | Install dewatering and draw down | 24.9735 | m | 8 | 10 | UG-17-S05-A040 | 1 | 2 | UG-17-S04-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-02-02 | 2027-02-12
UG-17-S05-A060 | AW.PIPE.F8.UG-17.UG-17-S05 | F8 | UG-17 | UG-17-S05 | A060 | Excavate and strut to formation | 382.4824 | m3 | 1 | 2 | UG-17-S05-A050 | 10 | 2 |  | 2027-02-12 | 2027-02-14 | 2027-02-14 | UG-17-S04-A060
UG-17-S05-A070 | AW.PIPE.F8.UG-17.UG-17-S05 | F8 | UG-17 | UG-17-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 24.9735 | m | 5 | 6 | UG-17-S05-A060 | 1 | 2 |  | 2027-03-06 | 2027-03-12 | 2027-03-12 | UG-17-S04-A070
UG-17-S05-A080 | AW.PIPE.F8.UG-17.UG-17-S05 | F8 | UG-17 | UG-17-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 24.9735 | m | 1 | 2 | UG-17-S05-A070 | 2 | 2 |  | 2027-03-08 | 2027-03-14 | 2027-03-14 | UG-17-S04-A080
UG-17-S05-A090 | AW.PIPE.F8.UG-17.UG-17-S05 | F8 | UG-17 | UG-17-S05 | A090 | Surround, joint test and line test | 24.9735 | m | 3 | 4 | UG-17-S05-A080 | 1 | 2 |  | 2027-03-09 | 2027-03-16
UG-17-S05-A100 | AW.PIPE.F8.UG-17.UG-17-S05 | F8 | UG-17 | UG-17-S05 | A100 | Backfill to NG and remove struts | 242.7042 | m3 | 1 | 2 | UG-17-S05-A090 | 2 | 2 | UG-11B-S05-A080 (FS, shared trench laid); UG-18-S02-A080 (FS, shared trench laid) | 2027-05-26 | 2027-05-28 | 2027-05-28 | UG-17-S04-A100
UG-17-S05-A110 | AW.PIPE.F8.UG-17.UG-17-S05 | F8 | UG-17 | UG-17-S05 | A110 | Dewatering off, extract sheets, reinstate | 49.9469 | m wall | 2 | 3 | UG-17-S05-A100 | 1 | 2 |  | 2027-05-27 | 2027-05-30
UG-11B-S05-A010 | AW.PIPE.F8.UG-11B.UG-11B-S05 | F8 | UG-11B | UG-11B-S05 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11B-S05-A020 | AW.PIPE.F8.UG-11B.UG-11B-S05 | F8 | UG-11B | UG-11B-S05 | A020 | Set-out, crossing survey and working platform | 75.1 | m | 1 | 2 | UG-11B-S05-A010 |  |  | FS from A010; UG-17-S05-A030 (SS, set-out one package ahead of piling) | 2027-01-30 | 2027-02-01
UG-11B-S05-A030 | AW.PIPE.F8.UG-11B.UG-11B-S05 | F8 | UG-11B | UG-11B-S05 | A030 | Pipe-support piling from platform (incl. integrity tests) | 54 | piles | 6 | 7 | UG-11B-S05-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-02 | 2027-02-09 | 2027-02-09 | UG-17-S05-A030
UG-11B-S05-A040 | AW.PIPE.F8.UG-11B.UG-11B-S05 | F8 | UG-11B | UG-11B-S05 | A040 | Install sheet piles (shored lengths) | 150.2 | m wall | 4 | 5 | UG-11B-S05-A030 | 3 | 2 |  | 2027-02-05 | 2027-02-11 | 2027-02-11 | UG-17-S05-A040
UG-11B-S05-A050 | AW.PIPE.F8.UG-11B.UG-11B-S05 | F8 | UG-11B | UG-11B-S05 | A050 | Install dewatering and draw down | 75.1 | m | 9 | 11 | UG-11B-S05-A040 | 2 | 2 | UG-17-S05-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-02-07 | 2027-02-18
UG-11B-S05-A060 | AW.PIPE.F8.UG-11B.UG-11B-S05 | F8 | UG-11B | UG-11B-S05 | A060 | Excavate and strut to formation | 919.4929 | m3 | 2 | 3 | UG-11B-S05-A050 | 10 | 2 | UG-17-S04-A060 (SS, shared trench); UG-17-S05-A060 (SS, shared trench) | 2027-02-17 | 2027-02-20 | 2027-02-20 | UG-17-S05-A060
UG-11B-S05-A070 | AW.PIPE.F8.UG-11B.UG-11B-S05 | F8 | UG-11B | UG-11B-S05 | A070 | Trim piles, blinding and piled slab (incl. cure) | 75.1 | m | 7 | 9 | UG-11B-S05-A060 | 1 | 2 |  | 2027-03-12 | 2027-03-21 | 2027-03-21 | UG-17-S05-A070
UG-11B-S05-A080 | AW.PIPE.F8.UG-11B.UG-11B-S05 | F8 | UG-11B | UG-11B-S05 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 75.1 | m | 4 | 5 | UG-11B-S05-A070 | 3 | 2 |  | 2027-03-15 | 2027-03-23 | 2027-03-23 | UG-17-S05-A080
UG-11B-S05-A090 | AW.PIPE.F8.UG-11B.UG-11B-S05 | F8 | UG-11B | UG-11B-S05 | A090 | Surround, joint test and line test | 75.1 | m | 3 | 4 | UG-11B-S05-A080 | 2 | 2 |  | 2027-03-17 | 2027-03-25
UG-11B-S05-A100 | AW.PIPE.F8.UG-11B.UG-11B-S05 | F8 | UG-11B | UG-11B-S05 | A100 | Backfill to NG and remove struts | 713.6278 | m3 | 2 | 3 | UG-11B-S05-A090 | 2 | 2 | UG-17-S03-A080 (FS, shared trench laid); UG-17-S04-A080 (FS, shared trench laid); UG-17-S05-A080 (FS, shared trench laid) | 2027-05-28 | 2027-05-31 | 2027-05-31 | UG-17-S05-A100
UG-11B-S05-A110 | AW.PIPE.F8.UG-11B.UG-11B-S05 | F8 | UG-11B | UG-11B-S05 | A110 | Dewatering off, extract sheets, reinstate | 150.2 | m wall | 5 | 6 | UG-11B-S05-A100 | 1 | 2 |  | 2027-05-29 | 2027-06-04
UG-17-S03-A010 | AW.PIPE.F8.UG-17.UG-17-S03 | F8 | UG-17 | UG-17-S03 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-17-S03-A020 | AW.PIPE.F8.UG-17.UG-17-S03 | F8 | UG-17 | UG-17-S03 | A020 | Set-out, crossing survey and working platform | 207.1 | m | 3 | 4 | UG-17-S03-A010 |  |  | FS from A010; UG-11B-S05-A030 (SS, set-out one package ahead of piling) | 2027-02-02 | 2027-02-06
UG-17-S03-A030 | AW.PIPE.F8.UG-17.UG-17-S03 | F8 | UG-17 | UG-17-S03 | A030 | Pipe-support piling from platform (incl. integrity tests) | 142 | piles | 15 | 18 | UG-17-S03-A020 | 2 | 2 | gate: D_PILEDES | 2027-02-09 | 2027-02-27 | 2027-02-27 | UG-11B-S05-A030
UG-17-S03-A040 | AW.PIPE.F8.UG-17.UG-17-S03 | F8 | UG-17 | UG-17-S03 | A040 | Install sheet piles (shored lengths) | 414.2 | m wall | 9 | 11 | UG-17-S03-A030 | 6 | 2 |  | 2027-02-15 | 2027-03-01 | 2027-03-01 | UG-11B-S05-A040
UG-17-S03-A050 | AW.PIPE.F8.UG-17.UG-17-S03 | F8 | UG-17 | UG-17-S03 | A050 | Install dewatering and draw down | 207.1 | m | 13 | 16 | UG-17-S03-A040 | 4 | 2 | UG-11B-S05-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-02-19 | 2027-03-07
UG-17-S03-A060 | AW.PIPE.F8.UG-17.UG-17-S03 | F8 | UG-17 | UG-17-S03 | A060 | Excavate and strut to formation | 3176.5415 | m3 | 7 | 9 | UG-17-S03-A050 | 12 | 2 | UG-11B-S05-A060 (SS, shared trench); UG-15-S01-A060 (SS, shared trench); UG-15A-S05-A060 (SS, shared trench); UG-15A-S06-A060 (SS, shared trench); UG-15A-S08-A060 (SS, shared trench) | 2027-03-03 | 2027-03-12 | 2027-03-12 | UG-11B-S05-A060
UG-17-S03-A070 | AW.PIPE.F8.UG-17.UG-17-S03 | F8 | UG-17 | UG-17-S03 | A070 | Trim piles, blinding and piled slab (incl. cure) | 207.1 | m | 12 | 14 | UG-17-S03-A060 | 3 | 2 |  | 2027-03-21 | 2027-04-04 | 2027-04-04 | UG-11B-S05-A070
UG-17-S03-A080 | AW.PIPE.F8.UG-17.UG-17-S03 | F8 | UG-17 | UG-17-S03 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 207.1 | m | 9 | 11 | UG-17-S03-A070 | 5 | 2 |  | 2027-03-26 | 2027-04-06 | 2027-04-06 | UG-11B-S05-A080
UG-17-S03-A090 | AW.PIPE.F8.UG-17.UG-17-S03 | F8 | UG-17 | UG-17-S03 | A090 | Surround, joint test and line test | 207.1 | m | 4 | 5 | UG-17-S03-A080 | 4 | 2 |  | 2027-03-30 | 2027-04-08
UG-17-S03-A100 | AW.PIPE.F8.UG-17.UG-17-S03 | F8 | UG-17 | UG-17-S03 | A100 | Backfill to NG and remove struts | 2014.0774 | m3 | 3 | 4 | UG-17-S03-A090 | 2 | 2 | UG-11B-S05-A080 (FS, shared trench laid); UG-11B-S06-A080 (FS, shared trench laid); UG-15-S01-A080 (FS, shared trench laid); UG-15A-S04-A080 (FS, shared trench laid); UG-15A-S05-A080 (FS, shared trench laid); UG-15A-S06-A080 (FS, shared trench laid); UG-15A-S08-A080 (FS, shared trench laid); UG-18-S02-A080 (FS, shared trench laid) | 2027-06-08 | 2027-06-12 | 2027-06-12 | UG-11B-S05-A100
UG-17-S03-A110 | AW.PIPE.F8.UG-17.UG-17-S03 | F8 | UG-17 | UG-17-S03 | A110 | Dewatering off, extract sheets, reinstate | 414.2 | m wall | 10 | 12 | UG-17-S03-A100 | 2 | 2 |  | 2027-06-10 | 2027-06-22
UG-18-S02-A010 | AW.PIPE.F8.UG-18.UG-18-S02 | F8 | UG-18 | UG-18-S02 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-18-S02-A020 | AW.PIPE.F8.UG-18.UG-18-S02 | F8 | UG-18 | UG-18-S02 | A020 | Set-out, crossing survey and working platform | 364.5418 | m | 5 | 6 | UG-18-S02-A010 |  |  | FS from A010; UG-17-S03-A030 (SS, set-out one package ahead of piling) | 2027-02-09 | 2027-02-15
UG-18-S02-A030 | AW.PIPE.F8.UG-18.UG-18-S02 | F8 | UG-18 | UG-18-S02 | A030 | Pipe-support piling from platform (incl. integrity tests) | 246 | piles | 25 | 30 | UG-18-S02-A020 | 2 | 2 | gate: D_PILEDES | 2027-02-27 | 2027-03-29 | 2027-03-29 | UG-17-S03-A030
UG-18-S02-A040 | AW.PIPE.F8.UG-18.UG-18-S02 | F8 | UG-18 | UG-18-S02 | A040 | Install sheet piles (shored lengths) | 729.0836 | m wall | 15 | 18 | UG-18-S02-A030 | 9 | 2 |  | 2027-03-08 | 2027-03-31 | 2027-03-31 | UG-17-S03-A040
UG-18-S02-A050 | AW.PIPE.F8.UG-18.UG-18-S02 | F8 | UG-18 | UG-18-S02 | A050 | Install dewatering and draw down | 364.5418 | m | 17 | 20 | UG-18-S02-A040 | 6 | 2 | UG-17-S03-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-03-14 | 2027-04-03
UG-18-S02-A060 | AW.PIPE.F8.UG-18.UG-18-S02 | F8 | UG-18 | UG-18-S02 | A060 | Excavate and strut to formation | 5579.2448 | m3 | 12 | 14 | UG-18-S02-A050 | 13 | 2 | UG-15A-S05-A060 (SS, shared trench); UG-17-S02-A060 (SS, shared trench); UG-17-S03-A060 (SS, shared trench); UG-17-S04-A060 (SS, shared trench); UG-17-S05-A060 (SS, shared trench); UG-20-S02-A060 (SS, shared trench) | 2027-03-27 | 2027-04-10 | 2027-04-10 | UG-17-S03-A060
UG-18-S02-A070 | AW.PIPE.F8.UG-18.UG-18-S02 | F8 | UG-18 | UG-18-S02 | A070 | Trim piles, blinding and piled slab (incl. cure) | 364.5418 | m | 19 | 23 | UG-18-S02-A060 | 5 | 2 |  | 2027-04-04 | 2027-04-27 | 2027-04-27 | UG-17-S03-A070
UG-18-S02-A080 | AW.PIPE.F8.UG-18.UG-18-S02 | F8 | UG-18 | UG-18-S02 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 364.5418 | m | 14 | 17 | UG-18-S02-A070 | 7 | 2 |  | 2027-04-11 | 2027-04-29 | 2027-04-29 | UG-17-S03-A080
UG-18-S02-A090 | AW.PIPE.F8.UG-18.UG-18-S02 | F8 | UG-18 | UG-18-S02 | A090 | Surround, joint test and line test | 364.5418 | m | 5 | 6 | UG-18-S02-A080 | 6 | 2 |  | 2027-04-17 | 2027-05-01
UG-18-S02-A100 | AW.PIPE.F8.UG-18.UG-18-S02 | F8 | UG-18 | UG-18-S02 | A100 | Backfill to NG and remove struts | 3518.1207 | m3 | 6 | 7 | UG-18-S02-A090 | 2 | 2 | UG-15A-S05-A080 (FS, shared trench laid); UG-17-S01-A080 (FS, shared trench laid); UG-17-S02-A080 (FS, shared trench laid); UG-17-S03-A080 (FS, shared trench laid); UG-17-S04-A080 (FS, shared trench laid); UG-17-S05-A080 (FS, shared trench laid); UG-20-S02-A080 (FS, shared trench laid) | 2027-06-12 | 2027-06-19 | 2027-06-19 | UG-17-S03-A100
UG-18-S02-A110 | AW.PIPE.F8.UG-18.UG-18-S02 | F8 | UG-18 | UG-18-S02 | A110 | Dewatering off, extract sheets, reinstate | 729.0836 | m wall | 16 | 19 | UG-18-S02-A100 | 3 | 2 |  | 2027-06-15 | 2027-07-04
UG-11B-S06-A010 | AW.PIPE.F8.UG-11B.UG-11B-S06 | F8 | UG-11B | UG-11B-S06 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-11B-S06-A020 | AW.PIPE.F8.UG-11B.UG-11B-S06 | F8 | UG-11B | UG-11B-S06 | A020 | Set-out, crossing survey and working platform | 17.6867 | m | 1 | 2 | UG-11B-S06-A010 |  |  | FS from A010; UG-18-S02-A030 (SS, set-out one package ahead of piling) | 2027-02-27 | 2027-03-01
UG-11B-S06-A030 | AW.PIPE.F8.UG-11B.UG-11B-S06 | F8 | UG-11B | UG-11B-S06 | A030 | Pipe-support piling from platform (incl. integrity tests) | 14 | piles | 2 | 3 | UG-11B-S06-A020 | 1 | 2 | gate: D_PILEDES | 2027-03-29 | 2027-04-01 | 2027-04-01 | UG-18-S02-A030
UG-11B-S06-A040 | AW.PIPE.F8.UG-11B.UG-11B-S06 | F8 | UG-11B | UG-11B-S06 | A040 | Install sheet piles (shored lengths) | 35.3735 | m wall | 1 | 2 | UG-11B-S06-A030 | 1 | 2 |  | 2027-03-31 | 2027-04-03 | 2027-04-03 | UG-18-S02-A040
UG-11B-S06-A050 | AW.PIPE.F8.UG-11B.UG-11B-S06 | F8 | UG-11B | UG-11B-S06 | A050 | Install dewatering and draw down | 17.6867 | m | 8 | 10 | UG-11B-S06-A040 | 1 | 2 | UG-18-S02-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-01 | 2027-04-11
UG-11B-S06-A060 | AW.PIPE.F8.UG-11B.UG-11B-S06 | F8 | UG-11B | UG-11B-S06 | A060 | Excavate and strut to formation | 216.7524 | m3 | 1 | 2 | UG-11B-S06-A050 | 10 | 2 | UG-15A-S05-A060 (SS, shared trench); UG-17-S03-A060 (SS, shared trench); UG-17-S04-A060 (SS, shared trench) | 2027-04-11 | 2027-04-13 | 2027-04-13 | UG-18-S02-A060
UG-11B-S06-A070 | AW.PIPE.F8.UG-11B.UG-11B-S06 | F8 | UG-11B | UG-11B-S06 | A070 | Trim piles, blinding and piled slab (incl. cure) | 17.6867 | m | 4 | 5 | UG-11B-S06-A060 | 1 | 2 |  | 2027-04-27 | 2027-05-02 | 2027-05-02 | UG-18-S02-A070
UG-11B-S06-A080 | AW.PIPE.F8.UG-11B.UG-11B-S06 | F8 | UG-11B | UG-11B-S06 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 17.6867 | m | 2 | 3 | UG-11B-S06-A070 | 2 | 2 |  | 2027-04-29 | 2027-05-04 | 2027-05-04 | UG-18-S02-A080
UG-11B-S06-A090 | AW.PIPE.F8.UG-11B.UG-11B-S06 | F8 | UG-11B | UG-11B-S06 | A090 | Surround, joint test and line test | 17.6867 | m | 3 | 4 | UG-11B-S06-A080 | 1 | 2 |  | 2027-04-30 | 2027-05-06
UG-11B-S06-A100 | AW.PIPE.F8.UG-11B.UG-11B-S06 | F8 | UG-11B | UG-11B-S06 | A100 | Backfill to NG and remove struts | 168.1652 | m3 | 1 | 2 | UG-11B-S06-A090 | 2 | 2 | UG-15A-S04-A080 (FS, shared trench laid); UG-15A-S05-A080 (FS, shared trench laid); UG-17-S03-A080 (FS, shared trench laid); UG-17-S04-A080 (FS, shared trench laid) | 2027-06-19 | 2027-06-21 | 2027-06-21 | UG-18-S02-A100
UG-11B-S06-A110 | AW.PIPE.F8.UG-11B.UG-11B-S06 | F8 | UG-11B | UG-11B-S06 | A110 | Dewatering off, extract sheets, reinstate | 35.3735 | m wall | 2 | 3 | UG-11B-S06-A100 | 1 | 2 |  | 2027-06-20 | 2027-06-23
UG-15A-S04-A010 | AW.PIPE.F8.UG-15A.UG-15A-S04 | F8 | UG-15A | UG-15A-S04 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU | 2026-12-01 | 2026-12-01
UG-15A-S04-A020 | AW.PIPE.F8.UG-15A.UG-15A-S04 | F8 | UG-15A | UG-15A-S04 | A020 | Set-out, crossing survey and working platform | 9.6496 | m | 1 | 2 | UG-15A-S04-A010 |  |  | FS from A010; UG-11B-S06-A030 (SS, set-out one package ahead of piling) | 2027-03-29 | 2027-03-31
UG-15A-S04-A030 | AW.PIPE.F8.UG-15A.UG-15A-S04 | F8 | UG-15A | UG-15A-S04 | A030 | Pipe-support piling from platform (incl. integrity tests) | 10 | piles | 1 | 2 | UG-15A-S04-A020 | 1 | 2 | gate: D_PILEDES | 2027-04-01 | 2027-04-03 | 2027-04-03 | UG-11B-S06-A030
UG-15A-S04-A040 | AW.PIPE.F8.UG-15A.UG-15A-S04 | F8 | UG-15A | UG-15A-S04 | A040 | Install sheet piles (shored lengths) | 14.2 | m wall | 1 | 2 | UG-15A-S04-A030 | 1 | 2 |  | 2027-04-03 | 2027-04-05 | 2027-04-05 | UG-11B-S06-A040
UG-15A-S04-A050 | AW.PIPE.F8.UG-15A.UG-15A-S04 | F8 | UG-15A | UG-15A-S04 | A050 | Install dewatering and draw down | 9.6496 | m | 8 | 10 | UG-15A-S04-A040 | 1 | 2 | UG-11B-S06-A060 (FS, negative lag = own duration: drawdown complete when the excavation crew is free) | 2027-04-04 | 2027-04-14
UG-15A-S04-A060 | AW.PIPE.F8.UG-15A.UG-15A-S04 | F8 | UG-15A | UG-15A-S04 | A060 | Excavate and strut to formation | 125.907 | m3 | 1 | 2 | UG-15A-S04-A050 | 10 | 2 | UG-11B-S05-A100 (FS, deeper first); UG-17-S04-A100 (FS, deeper first); UG-11B-S06-A060 (SS, shared trench); UG-17-S03-A060 (SS, shared trench) | 2027-05-31 | 2027-06-02 | 2027-06-02 | UG-11B-S06-A060
UG-15A-S04-A070 | AW.PIPE.F8.UG-15A.UG-15A-S04 | F8 | UG-15A | UG-15A-S04 | A070 | Trim piles, blinding and piled slab (incl. cure) | 9.6496 | m | 4 | 5 | UG-15A-S04-A060 | 1 | 2 |  | 2027-06-01 | 2027-06-06 | 2027-06-06 | UG-11B-S06-A070
UG-15A-S04-A080 | AW.PIPE.F8.UG-15A.UG-15A-S04 | F8 | UG-15A | UG-15A-S04 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 9.6496 | m | 2 | 3 | UG-15A-S04-A070 | 2 | 2 |  | 2027-06-03 | 2027-06-08 | 2027-06-08 | UG-11B-S06-A080
UG-15A-S04-A090 | AW.PIPE.F8.UG-15A.UG-15A-S04 | F8 | UG-15A | UG-15A-S04 | A090 | Surround, joint test and line test | 9.6496 | m | 3 | 4 | UG-15A-S04-A080 | 1 | 2 |  | 2027-06-04 | 2027-06-10
UG-15A-S04-A100 | AW.PIPE.F8.UG-15A.UG-15A-S04 | F8 | UG-15A | UG-15A-S04 | A100 | Backfill to NG and remove struts | 104.4252 | m3 | 1 | 2 | UG-15A-S04-A090 | 2 | 2 | UG-11B-S06-A080 (FS, shared trench laid); UG-17-S03-A080 (FS, shared trench laid) | 2027-06-21 | 2027-06-23 | 2027-06-23 | UG-11B-S06-A100
UG-15A-S04-A110 | AW.PIPE.F8.UG-15A.UG-15A-S04 | F8 | UG-15A | UG-15A-S04 | A110 | Dewatering off, extract sheets, reinstate | 14.2 | m wall | 2 | 3 | UG-15A-S04-A100 | 1 | 2 |  | 2027-06-22 | 2027-06-25
UG-17-S01-A010 | AW.PIPE.F8.UG-17.UG-17-S01 | F8 | UG-17 | UG-17-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-17-S01-A020 | AW.PIPE.F8.UG-17.UG-17-S01 | F8 | UG-17 | UG-17-S01 | A020 | Set-out, crossing survey and working platform | 14.7326 | m | 1 | 2 | UG-17-S01-A010 |  |  | FS from A010; UG-17-S02-A030 (SS, tie-in team follows the adjacent run) | 2026-12-15 | 2026-12-17
UG-17-S01-A030 | AW.PIPE.F8.UG-17.UG-17-S01 | F8 | UG-17 | UG-17-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 12 | piles | 2 | 3 | UG-17-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-16 | 2026-12-19 | 2026-12-19
UG-17-S01-A040 | AW.PIPE.F8.UG-17.UG-17-S01 | F8 | UG-17 | UG-17-S01 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-17-S01-A030 | 1 | 0 |  | 2026-12-17 | 2026-12-19 | 0
UG-17-S01-A050 | AW.PIPE.F8.UG-17.UG-17-S01 | F8 | UG-17 | UG-17-S01 | A050 | Install dewatering and draw down | 14.7326 | m | 8 | 10 | UG-17-S01-A040 | 0 | 2 |  | 2026-12-17 | 2026-12-27
UG-17-S01-A060 | AW.PIPE.F8.UG-17.UG-17-S01 | F8 | UG-17 | UG-17-S01 | A060 | Excavate and strut to formation | 502.9318 | m3 | 1 | 2 | UG-17-S01-A050 | 10 | 2 | UG-15-S01-A100 (FS, deeper first); UG-22-S01-A100 (FS, deeper first); UG-18-S02-A060 (SS, shared trench) | 2027-03-27 | 2027-03-29 | 2027-03-29
UG-17-S01-A070 | AW.PIPE.F8.UG-17.UG-17-S01 | F8 | UG-17 | UG-17-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 14.7326 | m | 4 | 5 | UG-17-S01-A060 | 1 | 2 |  | 2027-03-28 | 2027-04-02 | 2027-04-02
UG-17-S01-A080 | AW.PIPE.F8.UG-17.UG-17-S01 | F8 | UG-17 | UG-17-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 14.7326 | m | 7 | 9 | UG-17-S01-A070 | 2 | 2 | UG-17-S02-A080 (FS, closure) | 2027-03-30 | 2027-04-08 | 2027-04-08
UG-17-S01-A090 | AW.PIPE.F8.UG-17.UG-17-S01 | F8 | UG-17 | UG-17-S01 | A090 | Surround, joint test and line test | 14.7326 | m | 3 | 4 | UG-17-S01-A080 | 3 | 2 |  | 2027-04-02 | 2027-04-10
UG-17-S01-A100 | AW.PIPE.F8.UG-17.UG-17-S01 | F8 | UG-17 | UG-17-S01 | A100 | Backfill to NG and remove struts | 419.7976 | m3 | 1 | 2 | UG-17-S01-A090 | 2 | 2 | UG-18-S01-A080 (FS, shared trench laid); UG-18-S02-A080 (FS, shared trench laid) | 2027-05-08 | 2027-05-10 | 2027-05-10
UG-17-S01-A110 | AW.PIPE.F8.UG-17.UG-17-S01 | F8 | UG-17 | UG-17-S01 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-17-S01-A100 | 1 | 2 |  | 2027-05-09 | 2027-05-12
UG-18-S01-A010 | AW.PIPE.F8.UG-18.UG-18-S01 | F8 | UG-18 | UG-18-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-18-S01-A020 | AW.PIPE.F8.UG-18.UG-18-S01 | F8 | UG-18 | UG-18-S01 | A020 | Set-out, crossing survey and working platform | 10.5191 | m | 1 | 2 | UG-18-S01-A010 |  |  | FS from A010; UG-18-S02-A030 (SS, tie-in team follows the adjacent run) | 2027-02-27 | 2027-03-01
UG-18-S01-A030 | AW.PIPE.F8.UG-18.UG-18-S01 | F8 | UG-18 | UG-18-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 10 | piles | 1 | 2 | UG-18-S01-A020 | 1 | 2 | gate: D_PILEDES | 2027-02-28 | 2027-03-03 | 2027-03-03
UG-18-S01-A040 | AW.PIPE.F8.UG-18.UG-18-S01 | F8 | UG-18 | UG-18-S01 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-18-S01-A030 | 1 | 0 |  | 2027-03-01 | 2027-03-03 | 0
UG-18-S01-A050 | AW.PIPE.F8.UG-18.UG-18-S01 | F8 | UG-18 | UG-18-S01 | A050 | Install dewatering and draw down | 10.5191 | m | 8 | 10 | UG-18-S01-A040 | 0 | 2 |  | 2027-03-01 | 2027-03-11
UG-18-S01-A060 | AW.PIPE.F8.UG-18.UG-18-S01 | F8 | UG-18 | UG-18-S01 | A060 | Excavate and strut to formation | 358.2952 | m3 | 1 | 2 | UG-18-S01-A050 | 10 | 2 | UG-17-S01-A060 (SS, shared trench); UG-17-S02-A060 (SS, shared trench) | 2027-03-27 | 2027-03-29 | 2027-03-29
UG-18-S01-A070 | AW.PIPE.F8.UG-18.UG-18-S01 | F8 | UG-18 | UG-18-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 10.5191 | m | 4 | 5 | UG-18-S01-A060 | 1 | 2 |  | 2027-03-28 | 2027-04-02 | 2027-04-02
UG-18-S01-A080 | AW.PIPE.F8.UG-18.UG-18-S01 | F8 | UG-18 | UG-18-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 10.5191 | m | 7 | 9 | UG-18-S01-A070 | 2 | 2 | UG-18-S02-A080 (FS, closure) | 2027-04-29 | 2027-05-08 | 2027-05-08
UG-18-S01-A090 | AW.PIPE.F8.UG-18.UG-18-S01 | F8 | UG-18 | UG-18-S01 | A090 | Surround, joint test and line test | 10.5191 | m | 3 | 4 | UG-18-S01-A080 | 3 | 2 |  | 2027-05-02 | 2027-05-10
UG-18-S01-A100 | AW.PIPE.F8.UG-18.UG-18-S01 | F8 | UG-18 | UG-18-S01 | A100 | Backfill to NG and remove struts | 299.2118 | m3 | 1 | 2 | UG-18-S01-A090 | 2 | 2 | UG-17-S01-A080 (FS, shared trench laid); UG-17-S02-A080 (FS, shared trench laid) | 2027-05-04 | 2027-05-12 | 2027-05-12
UG-18-S01-A110 | AW.PIPE.F8.UG-18.UG-18-S01 | F8 | UG-18 | UG-18-S01 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 1 | 2 | UG-18-S01-A100 | 1 | 2 |  | 2027-05-05 | 2027-05-14
UG-28-S01-A010 | AW.PIPE.F8.UG-28.UG-28-S01 | F8 | UG-28 | UG-28-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-28-S01-A020 | AW.PIPE.F8.UG-28.UG-28-S01 | F8 | UG-28 | UG-28-S01 | A020 | Set-out, crossing survey and working platform | 1.1 | m | 1 | 2 | UG-28-S01-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-28-S01-A030 | AW.PIPE.F8.UG-28.UG-28-S01 | F8 | UG-28 | UG-28-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 2 | piles | 1 | 2 | UG-28-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-05 | 2026-12-05
UG-28-S01-A040 | AW.PIPE.F8.UG-28.UG-28-S01 | F8 | UG-28 | UG-28-S01 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-28-S01-A030 | 1 | 0 |  | 2026-12-03 | 2026-12-05 | 0
UG-28-S01-A050 | AW.PIPE.F8.UG-28.UG-28-S01 | F8 | UG-28 | UG-28-S01 | A050 | Install dewatering and draw down | 1.1 | m | 0 | 0 | UG-28-S01-A040 | 0 | 0 |  | 2026-12-03 | 2026-12-05
UG-28-S01-A060 | AW.PIPE.F8.UG-28.UG-28-S01 | F8 | UG-28 | UG-28-S01 | A060 | Excavate and strut to formation | 0 | m3 | 1 | 2 | UG-28-S01-A050 | 0 | 2 | UG-10-S02-A100 (FS, deeper first); UG-10-S03-A100 (FS, deeper first); UG-21-S01-A100 (FS, deeper first); UG-22-S01-A100 (FS, deeper first) | 2027-03-05 | 2027-03-07 | 2027-03-07
UG-28-S01-A070 | AW.PIPE.F8.UG-28.UG-28-S01 | F8 | UG-28 | UG-28-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 1.1 | m | 4 | 5 | UG-28-S01-A060 | 1 | 2 |  | 2027-03-06 | 2027-03-11 | 2027-03-11
UG-28-S01-A080 | AW.PIPE.F8.UG-28.UG-28-S01 | F8 | UG-28 | UG-28-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 1.1 | m | 4 | 5 | UG-28-S01-A070 | 2 | 2 |  | 2027-03-08 | 2027-03-13 | 2027-03-13
UG-28-S01-A090 | AW.PIPE.F8.UG-28.UG-28-S01 | F8 | UG-28 | UG-28-S01 | A090 | Surround, joint test and line test | 1.1 | m | 3 | 4 | UG-28-S01-A080 | 2 | 2 |  | 2027-03-10 | 2027-03-15
UG-28-S01-A100 | AW.PIPE.F8.UG-28.UG-28-S01 | F8 | UG-28 | UG-28-S01 | A100 | Backfill to NG and remove struts | 0 | m3 | 1 | 2 | UG-28-S01-A090 | 2 | 2 | UG-28A-S01-A080 (FS, shared trench laid) | 2027-03-17 | 2027-03-19 | 2027-03-19
UG-28-S01-A110 | AW.PIPE.F8.UG-28.UG-28-S01 | F8 | UG-28 | UG-28-S01 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 0 | 0 | UG-28-S01-A100 | 1 | 0 |  | 2027-03-18 | 2027-03-19
UG-28A-S01-A010 | AW.PIPE.F8.UG-28A.UG-28A-S01 | F8 | UG-28A | UG-28A-S01 | A010 | Release: drawings, holds, access and gates |  |  | 0 | 0 |  |  |  | gates: START, D_DLU, structure ready | 2026-12-01 | 2026-12-01
UG-28A-S01-A020 | AW.PIPE.F8.UG-28A.UG-28A-S01 | F8 | UG-28A | UG-28A-S01 | A020 | Set-out, crossing survey and working platform | 17.8374 | m | 1 | 2 | UG-28A-S01-A010 |  |  | FS from A010 | 2026-12-01 | 2026-12-03
UG-28A-S01-A030 | AW.PIPE.F8.UG-28A.UG-28A-S01 | F8 | UG-28A | UG-28A-S01 | A030 | Pipe-support piling from platform (incl. integrity tests) | 7 | piles | 1 | 2 | UG-28A-S01-A020 | 1 | 2 | gate: D_PILEDES | 2026-12-02 | 2026-12-05 | 2026-12-05
UG-28A-S01-A040 | AW.PIPE.F8.UG-28A.UG-28A-S01 | F8 | UG-28A | UG-28A-S01 | A040 | Install sheet piles (shored lengths) | 0 | m wall | 0 | 0 | UG-28A-S01-A030 | 1 | 0 |  | 2026-12-03 | 2026-12-05 | 0
UG-28A-S01-A050 | AW.PIPE.F8.UG-28A.UG-28A-S01 | F8 | UG-28A | UG-28A-S01 | A050 | Install dewatering and draw down | 17.8374 | m | 0 | 0 | UG-28A-S01-A040 | 0 | 0 |  | 2026-12-03 | 2026-12-05
UG-28A-S01-A060 | AW.PIPE.F8.UG-28A.UG-28A-S01 | F8 | UG-28A | UG-28A-S01 | A060 | Excavate and strut to formation | 0 | m3 | 1 | 2 | UG-28A-S01-A050 | 0 | 2 | UG-10-S02-A100 (FS, deeper first); UG-10-S03-A100 (FS, deeper first); UG-21-S01-A100 (FS, deeper first); UG-22-S01-A100 (FS, deeper first); UG-28-S02-A100 (FS, deeper first); UG-28-S01-A060 (SS, shared trench) | 2027-03-05 | 2027-03-07 | 2027-03-07
UG-28A-S01-A070 | AW.PIPE.F8.UG-28A.UG-28A-S01 | F8 | UG-28A | UG-28A-S01 | A070 | Trim piles, blinding and piled slab (incl. cure) | 17.8374 | m | 4 | 5 | UG-28A-S01-A060 | 1 | 2 |  | 2027-03-06 | 2027-03-11 | 2027-03-11
UG-28A-S01-A080 | AW.PIPE.F8.UG-28A.UG-28A-S01 | F8 | UG-28A | UG-28A-S01 | A080 | Lay and joint pipe (incl. fittings, tie-in) | 17.8374 | m | 7 | 9 | UG-28A-S01-A070 | 2 | 2 |  | 2027-03-08 | 2027-03-17 | 2027-03-17
UG-28A-S01-A090 | AW.PIPE.F8.UG-28A.UG-28A-S01 | F8 | UG-28A | UG-28A-S01 | A090 | Surround, joint test and line test | 17.8374 | m | 3 | 4 | UG-28A-S01-A080 | 3 | 2 |  | 2027-03-11 | 2027-03-19
UG-28A-S01-A100 | AW.PIPE.F8.UG-28A.UG-28A-S01 | F8 | UG-28A | UG-28A-S01 | A100 | Backfill to NG and remove struts | 0 | m3 | 1 | 2 | UG-28A-S01-A090 | 2 | 2 | UG-28-S01-A080 (FS, shared trench laid) | 2027-03-13 | 2027-03-21 | 2027-03-21
UG-28A-S01-A110 | AW.PIPE.F8.UG-28A.UG-28A-S01 | F8 | UG-28A | UG-28A-S01 | A110 | Dewatering off, extract sheets, reinstate | 0 | m wall | 0 | 0 | UG-28A-S01-A100 | 1 | 0 |  | 2027-03-14 | 2027-03-21
Formulas:
Start = MAX([Finish, row above])
Start = MAX([Start, row above]+[SS lag (cal. days)],D_PILEDES)
Finish = [Start]+[Duration (cal. days)]
Finish = MAX([Start]+[Duration (cal. days)],[Finish, row above]+[FF lag (cal. days)])
Crew released = IF([Duration (cal. days)]>0,[Finish],0)
Crew released = IF([Duration (cal. days)]>0,[Finish],R8)

## Relationships
Relationships (for P6 / MS Project import)
Lags in calendar days, linked to the Activities sheet. Gates (dates) are start constraints on A010 / A030 / A060, listed on the Activities sheet.
Predecessor | Successor | Type | Lag (cal. days) | Reason
UG-01-S02-A010 | UG-01-S02-A020 | FS | 0 | Within package
UG-01-S02-A020 | UG-01-S02-A030 | SS | 2 | Within package (ladder)
UG-01-S02-A020 | UG-01-S02-A030 | FF | 2 | Within package (ladder)
UG-01-S02-A030 | UG-01-S02-A040 | SS | 14 | Within package (ladder)
UG-01-S02-A030 | UG-01-S02-A040 | FF | 2 | Within package (ladder)
UG-01-S02-A040 | UG-01-S02-A050 | SS | 9 | Within package (ladder)
UG-01-S02-A040 | UG-01-S02-A050 | FF | 2 | Within package (ladder)
UG-01-S02-A050 | UG-01-S02-A060 | SS | 12 | Within package (ladder)
UG-01-S02-A050 | UG-01-S02-A060 | FF | 2 | Within package (ladder)
UG-01-S02-A060 | UG-01-S02-A070 | SS | 11 | Within package (ladder)
UG-01-S02-A060 | UG-01-S02-A070 | FF | 2 | Within package (ladder)
UG-01-S02-A070 | UG-01-S02-A080 | SS | 10 | Within package (ladder)
UG-01-S02-A070 | UG-01-S02-A080 | FF | 2 | Within package (ladder)
UG-01-S02-A080 | UG-01-S02-A090 | SS | 8 | Within package (ladder)
UG-01-S02-A080 | UG-01-S02-A090 | FF | 2 | Within package (ladder)
UG-01-S02-A090 | UG-01-S02-A100 | SS | 2 | Within package (ladder)
UG-01-S02-A090 | UG-01-S02-A100 | FF | 2 | Within package (ladder)
UG-01-S02-A100 | UG-01-S02-A110 | SS | 6 | Within package (ladder)
UG-01-S02-A100 | UG-01-S02-A110 | FF | 2 | Within package (ladder)
UG-01-S03-A010 | UG-01-S03-A020 | FS | 0 | Within package
UG-01-S02-A030 | UG-01-S03-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-01-S03-A020 | UG-01-S03-A030 | SS | 1 | Within package (ladder)
UG-01-S03-A020 | UG-01-S03-A030 | FF | 2 | Within package (ladder)
UG-01-S03-A030 | UG-01-S03-A040 | SS | 2 | Within package (ladder)
UG-01-S03-A030 | UG-01-S03-A040 | FF | 2 | Within package (ladder)
UG-01-S03-A040 | UG-01-S03-A050 | SS | 2 | Within package (ladder)
UG-01-S03-A040 | UG-01-S03-A050 | FF | 2 | Within package (ladder)
UG-01-S03-A050 | UG-01-S03-A060 | SS | 10 | Within package (ladder)
UG-01-S03-A050 | UG-01-S03-A060 | FF | 2 | Within package (ladder)
UG-01-S03-A060 | UG-01-S03-A070 | SS | 1 | Within package (ladder)
UG-01-S03-A060 | UG-01-S03-A070 | FF | 2 | Within package (ladder)
UG-01-S03-A070 | UG-01-S03-A080 | SS | 3 | Within package (ladder)
UG-01-S03-A070 | UG-01-S03-A080 | FF | 2 | Within package (ladder)
UG-01-S02-A080 | UG-01-S03-A080 | FS | 0 | Tie-in laid as closure
UG-01-S03-A080 | UG-01-S03-A090 | SS | 2 | Within package (ladder)
UG-01-S03-A080 | UG-01-S03-A090 | FF | 2 | Within package (ladder)
UG-01-S03-A090 | UG-01-S03-A100 | SS | 2 | Within package (ladder)
UG-01-S03-A090 | UG-01-S03-A100 | FF | 2 | Within package (ladder)
UG-01-S03-A100 | UG-01-S03-A110 | SS | 1 | Within package (ladder)
UG-01-S03-A100 | UG-01-S03-A110 | FF | 2 | Within package (ladder)
UG-01-S01-A010 | UG-01-S01-A020 | FS | 0 | Within package
UG-01-S02-A030 | UG-01-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-01-S01-A020 | UG-01-S01-A030 | SS | 1 | Within package (ladder)
UG-01-S01-A020 | UG-01-S01-A030 | FF | 2 | Within package (ladder)
UG-01-S01-A030 | UG-01-S01-A040 | SS | 2 | Within package (ladder)
UG-01-S01-A030 | UG-01-S01-A040 | FF | 2 | Within package (ladder)
UG-01-S01-A040 | UG-01-S01-A050 | SS | 1 | Within package (ladder)
UG-01-S01-A040 | UG-01-S01-A050 | FF | 2 | Within package (ladder)
UG-01-S01-A050 | UG-01-S01-A060 | SS | 10 | Within package (ladder)
UG-01-S01-A050 | UG-01-S01-A060 | FF | 2 | Within package (ladder)
UG-01-S01-A060 | UG-01-S01-A070 | SS | 1 | Within package (ladder)
UG-01-S01-A060 | UG-01-S01-A070 | FF | 2 | Within package (ladder)
UG-01-S01-A070 | UG-01-S01-A080 | SS | 2 | Within package (ladder)
UG-01-S01-A070 | UG-01-S01-A080 | FF | 2 | Within package (ladder)
UG-01-S02-A080 | UG-01-S01-A080 | FS | 0 | Tie-in laid as closure
UG-01-S01-A080 | UG-01-S01-A090 | SS | 2 | Within package (ladder)
UG-01-S01-A080 | UG-01-S01-A090 | FF | 2 | Within package (ladder)
UG-01-S01-A090 | UG-01-S01-A100 | SS | 2 | Within package (ladder)
UG-01-S01-A090 | UG-01-S01-A100 | FF | 2 | Within package (ladder)
UG-01-S01-A100 | UG-01-S01-A110 | SS | 1 | Within package (ladder)
UG-01-S01-A100 | UG-01-S01-A110 | FF | 2 | Within package (ladder)
UG-02-S03-A010 | UG-02-S03-A020 | FS | 0 | Within package
UG-01-S02-A030 | UG-02-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-02-S03-A020 | UG-02-S03-A030 | SS | 1 | Within package (ladder)
UG-02-S03-A020 | UG-02-S03-A030 | FF | 2 | Within package (ladder)
UG-01-S02-A030 | UG-02-S03-A030 | FS | 0 | Crew continuity, front F1
UG-02-S03-A030 | UG-02-S03-A040 | SS | 4 | Within package (ladder)
UG-02-S03-A030 | UG-02-S03-A040 | FF | 2 | Within package (ladder)
UG-01-S02-A040 | UG-02-S03-A040 | FS | 0 | Crew continuity, front F1
UG-02-S03-A040 | UG-02-S03-A050 | SS | 3 | Within package (ladder)
UG-02-S03-A040 | UG-02-S03-A050 | FF | 2 | Within package (ladder)
UG-01-S02-A060 | UG-02-S03-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-02-S03-A050 | UG-02-S03-A060 | SS | 10 | Within package (ladder)
UG-02-S03-A050 | UG-02-S03-A060 | FF | 2 | Within package (ladder)
UG-01-S02-A060 | UG-02-S03-A060 | FS | 0 | Crew continuity, front F1
UG-02-S03-A060 | UG-02-S03-A070 | SS | 3 | Within package (ladder)
UG-02-S03-A060 | UG-02-S03-A070 | FF | 2 | Within package (ladder)
UG-01-S02-A070 | UG-02-S03-A070 | FS | 0 | Crew continuity, front F1
UG-02-S03-A070 | UG-02-S03-A080 | SS | 4 | Within package (ladder)
UG-02-S03-A070 | UG-02-S03-A080 | FF | 2 | Within package (ladder)
UG-01-S02-A080 | UG-02-S03-A080 | FS | 0 | Crew continuity, front F1
UG-02-S03-A080 | UG-02-S03-A090 | SS | 2 | Within package (ladder)
UG-02-S03-A080 | UG-02-S03-A090 | FF | 2 | Within package (ladder)
UG-02-S03-A090 | UG-02-S03-A100 | SS | 2 | Within package (ladder)
UG-02-S03-A090 | UG-02-S03-A100 | FF | 2 | Within package (ladder)
UG-01-S02-A100 | UG-02-S03-A100 | FS | 0 | Crew continuity, front F1
UG-03-S01-A080 | UG-02-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-03-S02-A080 | UG-02-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-02-S03-A100 | UG-02-S03-A110 | SS | 2 | Within package (ladder)
UG-02-S03-A100 | UG-02-S03-A110 | FF | 2 | Within package (ladder)
UG-02-S02-A010 | UG-02-S02-A020 | FS | 0 | Within package
UG-02-S03-A030 | UG-02-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-02-S02-A020 | UG-02-S02-A030 | SS | 1 | Within package (ladder)
UG-02-S02-A020 | UG-02-S02-A030 | FF | 2 | Within package (ladder)
UG-02-S03-A030 | UG-02-S02-A030 | FS | 0 | Crew continuity, front F1
UG-02-S02-A030 | UG-02-S02-A040 | SS | 5 | Within package (ladder)
UG-02-S02-A030 | UG-02-S02-A040 | FF | 2 | Within package (ladder)
UG-02-S03-A040 | UG-02-S02-A040 | FS | 0 | Crew continuity, front F1
UG-02-S02-A040 | UG-02-S02-A050 | SS | 3 | Within package (ladder)
UG-02-S02-A040 | UG-02-S02-A050 | FF | 2 | Within package (ladder)
UG-02-S03-A060 | UG-02-S02-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-02-S02-A050 | UG-02-S02-A060 | SS | 10 | Within package (ladder)
UG-02-S02-A050 | UG-02-S02-A060 | FF | 2 | Within package (ladder)
UG-02-S03-A060 | UG-02-S02-A060 | FS | 0 | Crew continuity, front F1
UG-02-S02-A060 | UG-02-S02-A070 | SS | 3 | Within package (ladder)
UG-02-S02-A060 | UG-02-S02-A070 | FF | 2 | Within package (ladder)
UG-02-S03-A070 | UG-02-S02-A070 | FS | 0 | Crew continuity, front F1
UG-02-S02-A070 | UG-02-S02-A080 | SS | 4 | Within package (ladder)
UG-02-S02-A070 | UG-02-S02-A080 | FF | 2 | Within package (ladder)
UG-02-S03-A080 | UG-02-S02-A080 | FS | 0 | Crew continuity, front F1
UG-02-S02-A080 | UG-02-S02-A090 | SS | 2 | Within package (ladder)
UG-02-S02-A080 | UG-02-S02-A090 | FF | 2 | Within package (ladder)
UG-02-S02-A090 | UG-02-S02-A100 | SS | 2 | Within package (ladder)
UG-02-S02-A090 | UG-02-S02-A100 | FF | 2 | Within package (ladder)
UG-02-S03-A100 | UG-02-S02-A100 | FS | 0 | Crew continuity, front F1
UG-03-S01-A080 | UG-02-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-02-S02-A100 | UG-02-S02-A110 | SS | 2 | Within package (ladder)
UG-02-S02-A100 | UG-02-S02-A110 | FF | 2 | Within package (ladder)
UG-02-S05-A010 | UG-02-S05-A020 | FS | 0 | Within package
UG-02-S04-A030 | UG-02-S05-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-02-S05-A020 | UG-02-S05-A030 | SS | 1 | Within package (ladder)
UG-02-S05-A020 | UG-02-S05-A030 | FF | 2 | Within package (ladder)
UG-02-S05-A030 | UG-02-S05-A040 | SS | 1 | Within package (ladder)
UG-02-S05-A030 | UG-02-S05-A040 | FF | 2 | Within package (ladder)
UG-02-S05-A040 | UG-02-S05-A050 | SS | 1 | Within package (ladder)
UG-02-S05-A040 | UG-02-S05-A050 | FF | 2 | Within package (ladder)
UG-02-S05-A050 | UG-02-S05-A060 | SS | 10 | Within package (ladder)
UG-02-S05-A050 | UG-02-S05-A060 | FF | 2 | Within package (ladder)
UG-03-S04-A060 | UG-02-S05-A060 | SS | 0 | Shared excavation / dewatering front
UG-03-S05-A060 | UG-02-S05-A060 | SS | 0 | Shared excavation / dewatering front
UG-02-S05-A060 | UG-02-S05-A070 | SS | 1 | Within package (ladder)
UG-02-S05-A060 | UG-02-S05-A070 | FF | 2 | Within package (ladder)
UG-02-S05-A070 | UG-02-S05-A080 | SS | 2 | Within package (ladder)
UG-02-S05-A070 | UG-02-S05-A080 | FF | 2 | Within package (ladder)
UG-02-S04-A080 | UG-02-S05-A080 | FS | 0 | Tie-in laid as closure
UG-02-S05-A080 | UG-02-S05-A090 | SS | 2 | Within package (ladder)
UG-02-S05-A080 | UG-02-S05-A090 | FF | 2 | Within package (ladder)
UG-02-S05-A090 | UG-02-S05-A100 | SS | 2 | Within package (ladder)
UG-02-S05-A090 | UG-02-S05-A100 | FF | 2 | Within package (ladder)
UG-03-S04-A080 | UG-02-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-03-S05-A080 | UG-02-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-02-S05-A100 | UG-02-S05-A110 | SS | 1 | Within package (ladder)
UG-02-S05-A100 | UG-02-S05-A110 | FF | 2 | Within package (ladder)
UG-02-S04-A010 | UG-02-S04-A020 | FS | 0 | Within package
UG-02-S02-A030 | UG-02-S04-A020 | SS | 0 | Set-out one package ahead of piling
UG-02-S04-A020 | UG-02-S04-A030 | SS | 1 | Within package (ladder)
UG-02-S04-A020 | UG-02-S04-A030 | FF | 2 | Within package (ladder)
UG-02-S02-A030 | UG-02-S04-A030 | FS | 0 | Crew continuity, front F1
UG-02-S04-A030 | UG-02-S04-A040 | SS | 6 | Within package (ladder)
UG-02-S04-A030 | UG-02-S04-A040 | FF | 2 | Within package (ladder)
UG-02-S02-A040 | UG-02-S04-A040 | FS | 0 | Crew continuity, front F1
UG-02-S04-A040 | UG-02-S04-A050 | SS | 4 | Within package (ladder)
UG-02-S04-A040 | UG-02-S04-A050 | FF | 2 | Within package (ladder)
UG-02-S02-A060 | UG-02-S04-A050 | FS | -12 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-02-S04-A050 | UG-02-S04-A060 | SS | 10 | Within package (ladder)
UG-02-S04-A050 | UG-02-S04-A060 | FF | 2 | Within package (ladder)
UG-02-S02-A060 | UG-02-S04-A060 | FS | 0 | Crew continuity, front F1
UG-03-S05-A060 | UG-02-S04-A060 | SS | 0 | Shared excavation / dewatering front
UG-02-S04-A060 | UG-02-S04-A070 | SS | 4 | Within package (ladder)
UG-02-S04-A060 | UG-02-S04-A070 | FF | 2 | Within package (ladder)
UG-02-S02-A070 | UG-02-S04-A070 | FS | 0 | Crew continuity, front F1
UG-02-S04-A070 | UG-02-S04-A080 | SS | 5 | Within package (ladder)
UG-02-S04-A070 | UG-02-S04-A080 | FF | 2 | Within package (ladder)
UG-02-S02-A080 | UG-02-S04-A080 | FS | 0 | Crew continuity, front F1
UG-02-S04-A080 | UG-02-S04-A090 | SS | 3 | Within package (ladder)
UG-02-S04-A080 | UG-02-S04-A090 | FF | 2 | Within package (ladder)
UG-02-S04-A090 | UG-02-S04-A100 | SS | 2 | Within package (ladder)
UG-02-S04-A090 | UG-02-S04-A100 | FF | 2 | Within package (ladder)
UG-02-S02-A100 | UG-02-S04-A100 | FS | 0 | Crew continuity, front F1
UG-03-S01-A080 | UG-02-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-03-S02-A080 | UG-02-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-03-S03-A080 | UG-02-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-03-S04-A080 | UG-02-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-03-S05-A080 | UG-02-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-02-S04-A100 | UG-02-S04-A110 | SS | 3 | Within package (ladder)
UG-02-S04-A100 | UG-02-S04-A110 | FF | 2 | Within package (ladder)
UG-03-S01-A010 | UG-03-S01-A020 | FS | 0 | Within package
UG-02-S04-A030 | UG-03-S01-A020 | SS | 0 | Set-out one package ahead of piling
UG-03-S01-A020 | UG-03-S01-A030 | SS | 1 | Within package (ladder)
UG-03-S01-A020 | UG-03-S01-A030 | FF | 2 | Within package (ladder)
UG-02-S04-A030 | UG-03-S01-A030 | FS | 0 | Crew continuity, front F1
UG-03-S01-A030 | UG-03-S01-A040 | SS | 4 | Within package (ladder)
UG-03-S01-A030 | UG-03-S01-A040 | FF | 2 | Within package (ladder)
UG-02-S04-A040 | UG-03-S01-A040 | FS | 0 | Crew continuity, front F1
UG-03-S01-A040 | UG-03-S01-A050 | SS | 3 | Within package (ladder)
UG-03-S01-A040 | UG-03-S01-A050 | FF | 2 | Within package (ladder)
UG-02-S04-A060 | UG-03-S01-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-03-S01-A050 | UG-03-S01-A060 | SS | 10 | Within package (ladder)
UG-03-S01-A050 | UG-03-S01-A060 | FF | 2 | Within package (ladder)
UG-02-S04-A060 | UG-03-S01-A060 | FS | 0 | Crew continuity, front F1
UG-02-S02-A060 | UG-03-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-02-S03-A060 | UG-03-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-02-S04-A060 | UG-03-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-03-S01-A060 | UG-03-S01-A070 | SS | 3 | Within package (ladder)
UG-03-S01-A060 | UG-03-S01-A070 | FF | 2 | Within package (ladder)
UG-02-S04-A070 | UG-03-S01-A070 | FS | 0 | Crew continuity, front F1
UG-03-S01-A070 | UG-03-S01-A080 | SS | 4 | Within package (ladder)
UG-03-S01-A070 | UG-03-S01-A080 | FF | 2 | Within package (ladder)
UG-02-S04-A080 | UG-03-S01-A080 | FS | 0 | Crew continuity, front F1
UG-03-S01-A080 | UG-03-S01-A090 | SS | 2 | Within package (ladder)
UG-03-S01-A080 | UG-03-S01-A090 | FF | 2 | Within package (ladder)
UG-03-S01-A090 | UG-03-S01-A100 | SS | 2 | Within package (ladder)
UG-03-S01-A090 | UG-03-S01-A100 | FF | 2 | Within package (ladder)
UG-02-S04-A100 | UG-03-S01-A100 | FS | 0 | Crew continuity, front F1
UG-02-S02-A080 | UG-03-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-02-S03-A080 | UG-03-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-02-S04-A080 | UG-03-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-03-S01-A100 | UG-03-S01-A110 | SS | 2 | Within package (ladder)
UG-03-S01-A100 | UG-03-S01-A110 | FF | 2 | Within package (ladder)
UG-03-S02-A010 | UG-03-S02-A020 | FS | 0 | Within package
UG-03-S01-A030 | UG-03-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-03-S02-A020 | UG-03-S02-A030 | SS | 1 | Within package (ladder)
UG-03-S02-A020 | UG-03-S02-A030 | FF | 2 | Within package (ladder)
UG-03-S01-A030 | UG-03-S02-A030 | FS | 0 | Crew continuity, front F1
UG-03-S02-A030 | UG-03-S02-A040 | SS | 2 | Within package (ladder)
UG-03-S02-A030 | UG-03-S02-A040 | FF | 2 | Within package (ladder)
UG-03-S01-A040 | UG-03-S02-A040 | FS | 0 | Crew continuity, front F1
UG-03-S02-A040 | UG-03-S02-A050 | SS | 1 | Within package (ladder)
UG-03-S02-A040 | UG-03-S02-A050 | FF | 2 | Within package (ladder)
UG-03-S01-A060 | UG-03-S02-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-03-S02-A050 | UG-03-S02-A060 | SS | 10 | Within package (ladder)
UG-03-S02-A050 | UG-03-S02-A060 | FF | 2 | Within package (ladder)
UG-03-S01-A060 | UG-03-S02-A060 | FS | 0 | Crew continuity, front F1
UG-02-S03-A060 | UG-03-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-02-S04-A060 | UG-03-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-03-S02-A060 | UG-03-S02-A070 | SS | 1 | Within package (ladder)
UG-03-S02-A060 | UG-03-S02-A070 | FF | 2 | Within package (ladder)
UG-03-S01-A070 | UG-03-S02-A070 | FS | 0 | Crew continuity, front F1
UG-03-S02-A070 | UG-03-S02-A080 | SS | 2 | Within package (ladder)
UG-03-S02-A070 | UG-03-S02-A080 | FF | 2 | Within package (ladder)
UG-03-S01-A080 | UG-03-S02-A080 | FS | 0 | Crew continuity, front F1
UG-03-S02-A080 | UG-03-S02-A090 | SS | 1 | Within package (ladder)
UG-03-S02-A080 | UG-03-S02-A090 | FF | 2 | Within package (ladder)
UG-03-S02-A090 | UG-03-S02-A100 | SS | 2 | Within package (ladder)
UG-03-S02-A090 | UG-03-S02-A100 | FF | 2 | Within package (ladder)
UG-03-S01-A100 | UG-03-S02-A100 | FS | 0 | Crew continuity, front F1
UG-02-S03-A080 | UG-03-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-02-S04-A080 | UG-03-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-03-S02-A100 | UG-03-S02-A110 | SS | 1 | Within package (ladder)
UG-03-S02-A100 | UG-03-S02-A110 | FF | 2 | Within package (ladder)
UG-03-S04-A010 | UG-03-S04-A020 | FS | 0 | Within package
UG-03-S02-A030 | UG-03-S04-A020 | SS | 0 | Set-out one package ahead of piling
UG-03-S04-A020 | UG-03-S04-A030 | SS | 1 | Within package (ladder)
UG-03-S04-A020 | UG-03-S04-A030 | FF | 2 | Within package (ladder)
UG-03-S02-A030 | UG-03-S04-A030 | FS | 0 | Crew continuity, front F1
UG-03-S04-A030 | UG-03-S04-A040 | SS | 1 | Within package (ladder)
UG-03-S04-A030 | UG-03-S04-A040 | FF | 2 | Within package (ladder)
UG-03-S02-A040 | UG-03-S04-A040 | FS | 0 | Crew continuity, front F1
UG-03-S04-A040 | UG-03-S04-A050 | SS | 1 | Within package (ladder)
UG-03-S04-A040 | UG-03-S04-A050 | FF | 2 | Within package (ladder)
UG-03-S02-A060 | UG-03-S04-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-03-S04-A050 | UG-03-S04-A060 | SS | 10 | Within package (ladder)
UG-03-S04-A050 | UG-03-S04-A060 | FF | 2 | Within package (ladder)
UG-03-S02-A060 | UG-03-S04-A060 | FS | 0 | Crew continuity, front F1
UG-02-S04-A060 | UG-03-S04-A060 | SS | 0 | Shared excavation / dewatering front
UG-03-S04-A060 | UG-03-S04-A070 | SS | 1 | Within package (ladder)
UG-03-S04-A060 | UG-03-S04-A070 | FF | 2 | Within package (ladder)
UG-03-S02-A070 | UG-03-S04-A070 | FS | 0 | Crew continuity, front F1
UG-03-S04-A070 | UG-03-S04-A080 | SS | 2 | Within package (ladder)
UG-03-S04-A070 | UG-03-S04-A080 | FF | 2 | Within package (ladder)
UG-03-S02-A080 | UG-03-S04-A080 | FS | 0 | Crew continuity, front F1
UG-03-S04-A080 | UG-03-S04-A090 | SS | 1 | Within package (ladder)
UG-03-S04-A080 | UG-03-S04-A090 | FF | 2 | Within package (ladder)
UG-03-S04-A090 | UG-03-S04-A100 | SS | 2 | Within package (ladder)
UG-03-S04-A090 | UG-03-S04-A100 | FF | 2 | Within package (ladder)
UG-03-S02-A100 | UG-03-S04-A100 | FS | 0 | Crew continuity, front F1
UG-02-S04-A080 | UG-03-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-02-S05-A080 | UG-03-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-04-S01-A080 | UG-03-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-04-S02-A080 | UG-03-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-03-S04-A100 | UG-03-S04-A110 | SS | 1 | Within package (ladder)
UG-03-S04-A100 | UG-03-S04-A110 | FF | 2 | Within package (ladder)
UG-03-S05-A010 | UG-03-S05-A020 | FS | 0 | Within package
UG-03-S04-A030 | UG-03-S05-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-03-S05-A020 | UG-03-S05-A030 | SS | 1 | Within package (ladder)
UG-03-S05-A020 | UG-03-S05-A030 | FF | 2 | Within package (ladder)
UG-03-S05-A030 | UG-03-S05-A040 | SS | 1 | Within package (ladder)
UG-03-S05-A030 | UG-03-S05-A040 | FF | 2 | Within package (ladder)
UG-03-S05-A040 | UG-03-S05-A050 | SS | 1 | Within package (ladder)
UG-03-S05-A040 | UG-03-S05-A050 | FF | 2 | Within package (ladder)
UG-03-S05-A050 | UG-03-S05-A060 | SS | 10 | Within package (ladder)
UG-03-S05-A050 | UG-03-S05-A060 | FF | 2 | Within package (ladder)
UG-03-S05-A060 | UG-03-S05-A070 | SS | 1 | Within package (ladder)
UG-03-S05-A060 | UG-03-S05-A070 | FF | 2 | Within package (ladder)
UG-03-S05-A070 | UG-03-S05-A080 | SS | 2 | Within package (ladder)
UG-03-S05-A070 | UG-03-S05-A080 | FF | 2 | Within package (ladder)
UG-03-S04-A080 | UG-03-S05-A080 | FS | 0 | Tie-in laid as closure
UG-03-S05-A080 | UG-03-S05-A090 | SS | 2 | Within package (ladder)
UG-03-S05-A080 | UG-03-S05-A090 | FF | 2 | Within package (ladder)
UG-03-S05-A090 | UG-03-S05-A100 | SS | 2 | Within package (ladder)
UG-03-S05-A090 | UG-03-S05-A100 | FF | 2 | Within package (ladder)
UG-02-S04-A080 | UG-03-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-02-S05-A080 | UG-03-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-04-S01-A080 | UG-03-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-04-S02-A080 | UG-03-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-03-S05-A100 | UG-03-S05-A110 | SS | 1 | Within package (ladder)
UG-03-S05-A100 | UG-03-S05-A110 | FF | 2 | Within package (ladder)
UG-04-S01-A010 | UG-04-S01-A020 | FS | 0 | Within package
UG-03-S04-A030 | UG-04-S01-A020 | SS | 0 | Set-out one package ahead of piling
UG-04-S01-A020 | UG-04-S01-A030 | SS | 1 | Within package (ladder)
UG-04-S01-A020 | UG-04-S01-A030 | FF | 2 | Within package (ladder)
UG-03-S04-A030 | UG-04-S01-A030 | FS | 0 | Crew continuity, front F1
UG-04-S01-A030 | UG-04-S01-A040 | SS | 1 | Within package (ladder)
UG-04-S01-A030 | UG-04-S01-A040 | FF | 2 | Within package (ladder)
UG-03-S04-A040 | UG-04-S01-A040 | FS | 0 | Crew continuity, front F1
UG-04-S01-A040 | UG-04-S01-A050 | SS | 1 | Within package (ladder)
UG-04-S01-A040 | UG-04-S01-A050 | FF | 2 | Within package (ladder)
UG-03-S04-A060 | UG-04-S01-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-04-S01-A050 | UG-04-S01-A060 | SS | 10 | Within package (ladder)
UG-04-S01-A050 | UG-04-S01-A060 | FF | 2 | Within package (ladder)
UG-03-S04-A060 | UG-04-S01-A060 | FS | 0 | Crew continuity, front F1
UG-03-S04-A060 | UG-04-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-03-S05-A060 | UG-04-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-04-S01-A060 | UG-04-S01-A070 | SS | 1 | Within package (ladder)
UG-04-S01-A060 | UG-04-S01-A070 | FF | 2 | Within package (ladder)
UG-03-S04-A070 | UG-04-S01-A070 | FS | 0 | Crew continuity, front F1
UG-04-S01-A070 | UG-04-S01-A080 | SS | 2 | Within package (ladder)
UG-04-S01-A070 | UG-04-S01-A080 | FF | 2 | Within package (ladder)
UG-03-S04-A080 | UG-04-S01-A080 | FS | 0 | Crew continuity, front F1
UG-04-S01-A080 | UG-04-S01-A090 | SS | 2 | Within package (ladder)
UG-04-S01-A080 | UG-04-S01-A090 | FF | 2 | Within package (ladder)
UG-04-S01-A090 | UG-04-S01-A100 | SS | 2 | Within package (ladder)
UG-04-S01-A090 | UG-04-S01-A100 | FF | 2 | Within package (ladder)
UG-03-S04-A100 | UG-04-S01-A100 | FS | 0 | Crew continuity, front F1
UG-03-S04-A080 | UG-04-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-03-S05-A080 | UG-04-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-04-S01-A100 | UG-04-S01-A110 | SS | 1 | Within package (ladder)
UG-04-S01-A100 | UG-04-S01-A110 | FF | 2 | Within package (ladder)
UG-04-S02-A010 | UG-04-S02-A020 | FS | 0 | Within package
UG-04-S01-A030 | UG-04-S02-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-04-S02-A020 | UG-04-S02-A030 | SS | 1 | Within package (ladder)
UG-04-S02-A020 | UG-04-S02-A030 | FF | 2 | Within package (ladder)
UG-04-S02-A030 | UG-04-S02-A040 | SS | 2 | Within package (ladder)
UG-04-S02-A030 | UG-04-S02-A040 | FF | 2 | Within package (ladder)
UG-04-S02-A040 | UG-04-S02-A050 | SS | 1 | Within package (ladder)
UG-04-S02-A040 | UG-04-S02-A050 | FF | 2 | Within package (ladder)
UG-04-S02-A050 | UG-04-S02-A060 | SS | 10 | Within package (ladder)
UG-04-S02-A050 | UG-04-S02-A060 | FF | 2 | Within package (ladder)
UG-03-S04-A060 | UG-04-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-03-S05-A060 | UG-04-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-04-S02-A060 | UG-04-S02-A070 | SS | 1 | Within package (ladder)
UG-04-S02-A060 | UG-04-S02-A070 | FF | 2 | Within package (ladder)
UG-04-S02-A070 | UG-04-S02-A080 | SS | 2 | Within package (ladder)
UG-04-S02-A070 | UG-04-S02-A080 | FF | 2 | Within package (ladder)
UG-04-S01-A080 | UG-04-S02-A080 | FS | 0 | Tie-in laid as closure
UG-04-S02-A080 | UG-04-S02-A090 | SS | 2 | Within package (ladder)
UG-04-S02-A080 | UG-04-S02-A090 | FF | 2 | Within package (ladder)
UG-04-S02-A090 | UG-04-S02-A100 | SS | 2 | Within package (ladder)
UG-04-S02-A090 | UG-04-S02-A100 | FF | 2 | Within package (ladder)
UG-03-S04-A080 | UG-04-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-03-S05-A080 | UG-04-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-04-S02-A100 | UG-04-S02-A110 | SS | 1 | Within package (ladder)
UG-04-S02-A100 | UG-04-S02-A110 | FF | 2 | Within package (ladder)
UG-03-S03-A010 | UG-03-S03-A020 | FS | 0 | Within package
UG-04-S01-A030 | UG-03-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-03-S03-A020 | UG-03-S03-A030 | SS | 1 | Within package (ladder)
UG-03-S03-A020 | UG-03-S03-A030 | FF | 2 | Within package (ladder)
UG-04-S01-A030 | UG-03-S03-A030 | FS | 0 | Crew continuity, front F1
UG-03-S03-A030 | UG-03-S03-A040 | SS | 5 | Within package (ladder)
UG-03-S03-A030 | UG-03-S03-A040 | FF | 2 | Within package (ladder)
UG-04-S01-A040 | UG-03-S03-A040 | FS | 0 | Crew continuity, front F1
UG-03-S03-A040 | UG-03-S03-A050 | SS | 3 | Within package (ladder)
UG-03-S03-A040 | UG-03-S03-A050 | FF | 2 | Within package (ladder)
UG-04-S01-A060 | UG-03-S03-A050 | FS | -12 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-03-S03-A050 | UG-03-S03-A060 | SS | 10 | Within package (ladder)
UG-03-S03-A050 | UG-03-S03-A060 | FF | 2 | Within package (ladder)
UG-04-S01-A060 | UG-03-S03-A060 | FS | 0 | Crew continuity, front F1
UG-02-S04-A060 | UG-03-S03-A060 | SS | 0 | Shared excavation / dewatering front
UG-03-S03-A060 | UG-03-S03-A070 | SS | 3 | Within package (ladder)
UG-03-S03-A060 | UG-03-S03-A070 | FF | 2 | Within package (ladder)
UG-04-S01-A070 | UG-03-S03-A070 | FS | 0 | Crew continuity, front F1
UG-03-S03-A070 | UG-03-S03-A080 | SS | 4 | Within package (ladder)
UG-03-S03-A070 | UG-03-S03-A080 | FF | 2 | Within package (ladder)
UG-04-S01-A080 | UG-03-S03-A080 | FS | 0 | Crew continuity, front F1
UG-03-S03-A080 | UG-03-S03-A090 | SS | 2 | Within package (ladder)
UG-03-S03-A080 | UG-03-S03-A090 | FF | 2 | Within package (ladder)
UG-03-S03-A090 | UG-03-S03-A100 | SS | 2 | Within package (ladder)
UG-03-S03-A090 | UG-03-S03-A100 | FF | 2 | Within package (ladder)
UG-04-S01-A100 | UG-03-S03-A100 | FS | 0 | Crew continuity, front F1
UG-02-S04-A080 | UG-03-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-03-S03-A100 | UG-03-S03-A110 | SS | 2 | Within package (ladder)
UG-03-S03-A100 | UG-03-S03-A110 | FF | 2 | Within package (ladder)
UG-02-S01-A010 | UG-02-S01-A020 | FS | 0 | Within package
UG-02-S02-A030 | UG-02-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-02-S01-A020 | UG-02-S01-A030 | SS | 1 | Within package (ladder)
UG-02-S01-A020 | UG-02-S01-A030 | FF | 2 | Within package (ladder)
UG-02-S01-A030 | UG-02-S01-A040 | SS | 2 | Within package (ladder)
UG-02-S01-A030 | UG-02-S01-A040 | FF | 2 | Within package (ladder)
UG-02-S01-A040 | UG-02-S01-A050 | SS | 1 | Within package (ladder)
UG-02-S01-A040 | UG-02-S01-A050 | FF | 2 | Within package (ladder)
UG-02-S01-A050 | UG-02-S01-A060 | SS | 10 | Within package (ladder)
UG-02-S01-A050 | UG-02-S01-A060 | FF | 2 | Within package (ladder)
UG-02-S01-A060 | UG-02-S01-A070 | SS | 1 | Within package (ladder)
UG-02-S01-A060 | UG-02-S01-A070 | FF | 2 | Within package (ladder)
UG-02-S01-A070 | UG-02-S01-A080 | SS | 2 | Within package (ladder)
UG-02-S01-A070 | UG-02-S01-A080 | FF | 2 | Within package (ladder)
UG-02-S02-A080 | UG-02-S01-A080 | FS | 0 | Tie-in laid as closure
UG-02-S01-A080 | UG-02-S01-A090 | SS | 3 | Within package (ladder)
UG-02-S01-A080 | UG-02-S01-A090 | FF | 2 | Within package (ladder)
UG-02-S01-A090 | UG-02-S01-A100 | SS | 2 | Within package (ladder)
UG-02-S01-A090 | UG-02-S01-A100 | FF | 2 | Within package (ladder)
UG-02-S01-A100 | UG-02-S01-A110 | SS | 1 | Within package (ladder)
UG-02-S01-A100 | UG-02-S01-A110 | FF | 2 | Within package (ladder)
UG-06-S02-A010 | UG-06-S02-A020 | FS | 0 | Within package
UG-06-S02-A020 | UG-06-S02-A030 | SS | 1 | Within package (ladder)
UG-06-S02-A020 | UG-06-S02-A030 | FF | 2 | Within package (ladder)
UG-06-S02-A030 | UG-06-S02-A040 | SS | 2 | Within package (ladder)
UG-06-S02-A030 | UG-06-S02-A040 | FF | 2 | Within package (ladder)
UG-06-S02-A040 | UG-06-S02-A050 | SS | 1 | Within package (ladder)
UG-06-S02-A040 | UG-06-S02-A050 | FF | 2 | Within package (ladder)
UG-06-S02-A050 | UG-06-S02-A060 | SS | 10 | Within package (ladder)
UG-06-S02-A050 | UG-06-S02-A060 | FF | 2 | Within package (ladder)
UG-06-S02-A060 | UG-06-S02-A070 | SS | 1 | Within package (ladder)
UG-06-S02-A060 | UG-06-S02-A070 | FF | 2 | Within package (ladder)
UG-06-S02-A070 | UG-06-S02-A080 | SS | 2 | Within package (ladder)
UG-06-S02-A070 | UG-06-S02-A080 | FF | 2 | Within package (ladder)
UG-06-S02-A080 | UG-06-S02-A090 | SS | 1 | Within package (ladder)
UG-06-S02-A080 | UG-06-S02-A090 | FF | 2 | Within package (ladder)
UG-06-S02-A090 | UG-06-S02-A100 | SS | 2 | Within package (ladder)
UG-06-S02-A090 | UG-06-S02-A100 | FF | 2 | Within package (ladder)
UG-06-S02-A100 | UG-06-S02-A110 | SS | 1 | Within package (ladder)
UG-06-S02-A100 | UG-06-S02-A110 | FF | 2 | Within package (ladder)
UG-25-S01-A010 | UG-25-S01-A020 | FS | 0 | Within package
UG-06-S02-A030 | UG-25-S01-A020 | SS | 0 | Set-out one package ahead of piling
UG-25-S01-A020 | UG-25-S01-A030 | SS | 3 | Within package (ladder)
UG-25-S01-A020 | UG-25-S01-A030 | FF | 2 | Within package (ladder)
UG-06-S02-A030 | UG-25-S01-A030 | FS | 0 | Crew continuity, front F2
UG-25-S01-A030 | UG-25-S01-A040 | SS | 12 | Within package (ladder)
UG-25-S01-A030 | UG-25-S01-A040 | FF | 2 | Within package (ladder)
UG-06-S02-A040 | UG-25-S01-A040 | FS | 0 | Crew continuity, front F2
UG-25-S01-A040 | UG-25-S01-A050 | SS | 8 | Within package (ladder)
UG-25-S01-A040 | UG-25-S01-A050 | FF | 2 | Within package (ladder)
UG-06-S02-A060 | UG-25-S01-A050 | FS | -24 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-25-S01-A050 | UG-25-S01-A060 | SS | 14 | Within package (ladder)
UG-25-S01-A050 | UG-25-S01-A060 | FF | 2 | Within package (ladder)
UG-06-S02-A060 | UG-25-S01-A060 | FS | 0 | Crew continuity, front F2
UG-25-S01-A060 | UG-25-S01-A070 | SS | 7 | Within package (ladder)
UG-25-S01-A060 | UG-25-S01-A070 | FF | 2 | Within package (ladder)
UG-06-S02-A070 | UG-25-S01-A070 | FS | 0 | Crew continuity, front F2
UG-25-S01-A070 | UG-25-S01-A080 | SS | 9 | Within package (ladder)
UG-25-S01-A070 | UG-25-S01-A080 | FF | 2 | Within package (ladder)
UG-06-S02-A080 | UG-25-S01-A080 | FS | 0 | Crew continuity, front F2
UG-25-S01-A080 | UG-25-S01-A090 | SS | 7 | Within package (ladder)
UG-25-S01-A080 | UG-25-S01-A090 | FF | 2 | Within package (ladder)
UG-25-S01-A090 | UG-25-S01-A100 | SS | 3 | Within package (ladder)
UG-25-S01-A090 | UG-25-S01-A100 | FF | 2 | Within package (ladder)
UG-06-S02-A100 | UG-25-S01-A100 | FS | 0 | Crew continuity, front F2
UG-05-S05-A080 | UG-25-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-06-S05-A080 | UG-25-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-26-S01-A080 | UG-25-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-25-S01-A100 | UG-25-S01-A110 | SS | 3 | Within package (ladder)
UG-25-S01-A100 | UG-25-S01-A110 | FF | 2 | Within package (ladder)
UG-26-S01-A010 | UG-26-S01-A020 | FS | 0 | Within package
UG-25-S01-A030 | UG-26-S01-A020 | SS | 0 | Set-out one package ahead of piling
UG-26-S01-A020 | UG-26-S01-A030 | SS | 3 | Within package (ladder)
UG-26-S01-A020 | UG-26-S01-A030 | FF | 2 | Within package (ladder)
UG-25-S01-A030 | UG-26-S01-A030 | FS | 0 | Crew continuity, front F2
UG-26-S01-A030 | UG-26-S01-A040 | SS | 12 | Within package (ladder)
UG-26-S01-A030 | UG-26-S01-A040 | FF | 2 | Within package (ladder)
UG-25-S01-A040 | UG-26-S01-A040 | FS | 0 | Crew continuity, front F2
UG-26-S01-A040 | UG-26-S01-A050 | SS | 8 | Within package (ladder)
UG-26-S01-A040 | UG-26-S01-A050 | FF | 2 | Within package (ladder)
UG-25-S01-A060 | UG-26-S01-A050 | FS | -24 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-26-S01-A050 | UG-26-S01-A060 | SS | 14 | Within package (ladder)
UG-26-S01-A050 | UG-26-S01-A060 | FF | 2 | Within package (ladder)
UG-25-S01-A060 | UG-26-S01-A060 | FS | 0 | Crew continuity, front F2
UG-25-S01-A060 | UG-26-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-26-S01-A060 | UG-26-S01-A070 | SS | 6 | Within package (ladder)
UG-26-S01-A060 | UG-26-S01-A070 | FF | 2 | Within package (ladder)
UG-25-S01-A070 | UG-26-S01-A070 | FS | 0 | Crew continuity, front F2
UG-26-S01-A070 | UG-26-S01-A080 | SS | 9 | Within package (ladder)
UG-26-S01-A070 | UG-26-S01-A080 | FF | 2 | Within package (ladder)
UG-25-S01-A080 | UG-26-S01-A080 | FS | 0 | Crew continuity, front F2
UG-26-S01-A080 | UG-26-S01-A090 | SS | 6 | Within package (ladder)
UG-26-S01-A080 | UG-26-S01-A090 | FF | 2 | Within package (ladder)
UG-26-S01-A090 | UG-26-S01-A100 | SS | 3 | Within package (ladder)
UG-26-S01-A090 | UG-26-S01-A100 | FF | 2 | Within package (ladder)
UG-25-S01-A100 | UG-26-S01-A100 | FS | 0 | Crew continuity, front F2
UG-05-S05-A080 | UG-26-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-06-S05-A080 | UG-26-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-25-S01-A080 | UG-26-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-26-S01-A100 | UG-26-S01-A110 | SS | 3 | Within package (ladder)
UG-26-S01-A100 | UG-26-S01-A110 | FF | 2 | Within package (ladder)
UG-06-S05-A010 | UG-06-S05-A020 | FS | 0 | Within package
UG-26-S01-A030 | UG-06-S05-A020 | SS | 0 | Set-out one package ahead of piling
UG-06-S05-A020 | UG-06-S05-A030 | SS | 1 | Within package (ladder)
UG-06-S05-A020 | UG-06-S05-A030 | FF | 2 | Within package (ladder)
UG-26-S01-A030 | UG-06-S05-A030 | FS | 0 | Crew continuity, front F2
UG-06-S05-A030 | UG-06-S05-A040 | SS | 1 | Within package (ladder)
UG-06-S05-A030 | UG-06-S05-A040 | FF | 2 | Within package (ladder)
UG-26-S01-A040 | UG-06-S05-A040 | FS | 0 | Crew continuity, front F2
UG-06-S05-A040 | UG-06-S05-A050 | SS | 1 | Within package (ladder)
UG-06-S05-A040 | UG-06-S05-A050 | FF | 2 | Within package (ladder)
UG-26-S01-A060 | UG-06-S05-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-06-S05-A050 | UG-06-S05-A060 | SS | 10 | Within package (ladder)
UG-06-S05-A050 | UG-06-S05-A060 | FF | 2 | Within package (ladder)
UG-26-S01-A060 | UG-06-S05-A060 | FS | 0 | Crew continuity, front F2
UG-25-S01-A060 | UG-06-S05-A060 | SS | 0 | Shared excavation / dewatering front
UG-26-S01-A060 | UG-06-S05-A060 | SS | 0 | Shared excavation / dewatering front
UG-06-S05-A060 | UG-06-S05-A070 | SS | 1 | Within package (ladder)
UG-06-S05-A060 | UG-06-S05-A070 | FF | 2 | Within package (ladder)
UG-26-S01-A070 | UG-06-S05-A070 | FS | 0 | Crew continuity, front F2
UG-06-S05-A070 | UG-06-S05-A080 | SS | 2 | Within package (ladder)
UG-06-S05-A070 | UG-06-S05-A080 | FF | 2 | Within package (ladder)
UG-26-S01-A080 | UG-06-S05-A080 | FS | 0 | Crew continuity, front F2
UG-06-S05-A080 | UG-06-S05-A090 | SS | 1 | Within package (ladder)
UG-06-S05-A080 | UG-06-S05-A090 | FF | 2 | Within package (ladder)
UG-06-S05-A090 | UG-06-S05-A100 | SS | 2 | Within package (ladder)
UG-06-S05-A090 | UG-06-S05-A100 | FF | 2 | Within package (ladder)
UG-26-S01-A100 | UG-06-S05-A100 | FS | 0 | Crew continuity, front F2
UG-05-S04-A080 | UG-06-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-05-S05-A080 | UG-06-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-25-S01-A080 | UG-06-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-26-S01-A080 | UG-06-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-06-S05-A100 | UG-06-S05-A110 | SS | 1 | Within package (ladder)
UG-06-S05-A100 | UG-06-S05-A110 | FF | 2 | Within package (ladder)
UG-06-S04-A010 | UG-06-S04-A020 | FS | 0 | Within package
UG-06-S05-A030 | UG-06-S04-A020 | SS | 0 | Set-out one package ahead of piling
UG-06-S04-A020 | UG-06-S04-A030 | SS | 1 | Within package (ladder)
UG-06-S04-A020 | UG-06-S04-A030 | FF | 2 | Within package (ladder)
UG-06-S05-A030 | UG-06-S04-A030 | FS | 0 | Crew continuity, front F2
UG-06-S04-A030 | UG-06-S04-A040 | SS | 4 | Within package (ladder)
UG-06-S04-A030 | UG-06-S04-A040 | FF | 2 | Within package (ladder)
UG-06-S05-A040 | UG-06-S04-A040 | FS | 0 | Crew continuity, front F2
UG-06-S04-A040 | UG-06-S04-A050 | SS | 3 | Within package (ladder)
UG-06-S04-A040 | UG-06-S04-A050 | FF | 2 | Within package (ladder)
UG-06-S05-A060 | UG-06-S04-A050 | FS | -13 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-06-S04-A050 | UG-06-S04-A060 | SS | 11 | Within package (ladder)
UG-06-S04-A050 | UG-06-S04-A060 | FF | 2 | Within package (ladder)
UG-06-S05-A060 | UG-06-S04-A060 | FS | 0 | Crew continuity, front F2
UG-06-S04-A060 | UG-06-S04-A070 | SS | 2 | Within package (ladder)
UG-06-S04-A060 | UG-06-S04-A070 | FF | 2 | Within package (ladder)
UG-06-S05-A070 | UG-06-S04-A070 | FS | 0 | Crew continuity, front F2
UG-06-S04-A070 | UG-06-S04-A080 | SS | 4 | Within package (ladder)
UG-06-S04-A070 | UG-06-S04-A080 | FF | 2 | Within package (ladder)
UG-06-S05-A080 | UG-06-S04-A080 | FS | 0 | Crew continuity, front F2
UG-06-S04-A080 | UG-06-S04-A090 | SS | 2 | Within package (ladder)
UG-06-S04-A080 | UG-06-S04-A090 | FF | 2 | Within package (ladder)
UG-06-S04-A090 | UG-06-S04-A100 | SS | 2 | Within package (ladder)
UG-06-S04-A090 | UG-06-S04-A100 | FF | 2 | Within package (ladder)
UG-06-S05-A100 | UG-06-S04-A100 | FS | 0 | Crew continuity, front F2
UG-05-S03-A080 | UG-06-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-05-S04-A080 | UG-06-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-05-S05-A080 | UG-06-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-06-S04-A100 | UG-06-S04-A110 | SS | 1 | Within package (ladder)
UG-06-S04-A100 | UG-06-S04-A110 | FF | 2 | Within package (ladder)
UG-05-S05-A010 | UG-05-S05-A020 | FS | 0 | Within package
UG-06-S04-A030 | UG-05-S05-A020 | SS | 0 | Set-out one package ahead of piling
UG-05-S05-A020 | UG-05-S05-A030 | SS | 1 | Within package (ladder)
UG-05-S05-A020 | UG-05-S05-A030 | FF | 2 | Within package (ladder)
UG-06-S04-A030 | UG-05-S05-A030 | FS | 0 | Crew continuity, front F2
UG-05-S05-A030 | UG-05-S05-A040 | SS | 1 | Within package (ladder)
UG-05-S05-A030 | UG-05-S05-A040 | FF | 2 | Within package (ladder)
UG-06-S04-A040 | UG-05-S05-A040 | FS | 0 | Crew continuity, front F2
UG-05-S05-A040 | UG-05-S05-A050 | SS | 1 | Within package (ladder)
UG-05-S05-A040 | UG-05-S05-A050 | FF | 2 | Within package (ladder)
UG-06-S04-A060 | UG-05-S05-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-05-S05-A050 | UG-05-S05-A060 | SS | 10 | Within package (ladder)
UG-05-S05-A050 | UG-05-S05-A060 | FF | 2 | Within package (ladder)
UG-06-S04-A060 | UG-05-S05-A060 | FS | 0 | Crew continuity, front F2
UG-06-S04-A060 | UG-05-S05-A060 | SS | 0 | Shared excavation / dewatering front
UG-06-S05-A060 | UG-05-S05-A060 | SS | 0 | Shared excavation / dewatering front
UG-25-S01-A060 | UG-05-S05-A060 | SS | 0 | Shared excavation / dewatering front
UG-26-S01-A060 | UG-05-S05-A060 | SS | 0 | Shared excavation / dewatering front
UG-05-S05-A060 | UG-05-S05-A070 | SS | 1 | Within package (ladder)
UG-05-S05-A060 | UG-05-S05-A070 | FF | 2 | Within package (ladder)
UG-06-S04-A070 | UG-05-S05-A070 | FS | 0 | Crew continuity, front F2
UG-05-S05-A070 | UG-05-S05-A080 | SS | 2 | Within package (ladder)
UG-05-S05-A070 | UG-05-S05-A080 | FF | 2 | Within package (ladder)
UG-06-S04-A080 | UG-05-S05-A080 | FS | 0 | Crew continuity, front F2
UG-05-S05-A080 | UG-05-S05-A090 | SS | 1 | Within package (ladder)
UG-05-S05-A080 | UG-05-S05-A090 | FF | 2 | Within package (ladder)
UG-05-S05-A090 | UG-05-S05-A100 | SS | 2 | Within package (ladder)
UG-05-S05-A090 | UG-05-S05-A100 | FF | 2 | Within package (ladder)
UG-06-S04-A100 | UG-05-S05-A100 | FS | 0 | Crew continuity, front F2
UG-06-S04-A080 | UG-05-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-06-S05-A080 | UG-05-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-25-S01-A080 | UG-05-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-26-S01-A080 | UG-05-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-05-S05-A100 | UG-05-S05-A110 | SS | 1 | Within package (ladder)
UG-05-S05-A100 | UG-05-S05-A110 | FF | 2 | Within package (ladder)
UG-06-S03-A010 | UG-06-S03-A020 | FS | 0 | Within package
UG-05-S05-A030 | UG-06-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-06-S03-A020 | UG-06-S03-A030 | SS | 1 | Within package (ladder)
UG-06-S03-A020 | UG-06-S03-A030 | FF | 2 | Within package (ladder)
UG-05-S05-A030 | UG-06-S03-A030 | FS | 0 | Crew continuity, front F2
UG-06-S03-A030 | UG-06-S03-A040 | SS | 3 | Within package (ladder)
UG-06-S03-A030 | UG-06-S03-A040 | FF | 2 | Within package (ladder)
UG-05-S05-A040 | UG-06-S03-A040 | FS | 0 | Crew continuity, front F2
UG-06-S03-A040 | UG-06-S03-A050 | SS | 2 | Within package (ladder)
UG-06-S03-A040 | UG-06-S03-A050 | FF | 2 | Within package (ladder)
UG-05-S05-A060 | UG-06-S03-A050 | FS | -12 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-06-S03-A050 | UG-06-S03-A060 | SS | 10 | Within package (ladder)
UG-06-S03-A050 | UG-06-S03-A060 | FF | 2 | Within package (ladder)
UG-05-S05-A060 | UG-06-S03-A060 | FS | 0 | Crew continuity, front F2
UG-06-S03-A060 | UG-06-S03-A070 | SS | 2 | Within package (ladder)
UG-06-S03-A060 | UG-06-S03-A070 | FF | 2 | Within package (ladder)
UG-05-S05-A070 | UG-06-S03-A070 | FS | 0 | Crew continuity, front F2
UG-06-S03-A070 | UG-06-S03-A080 | SS | 3 | Within package (ladder)
UG-06-S03-A070 | UG-06-S03-A080 | FF | 2 | Within package (ladder)
UG-05-S05-A080 | UG-06-S03-A080 | FS | 0 | Crew continuity, front F2
UG-06-S03-A080 | UG-06-S03-A090 | SS | 3 | Within package (ladder)
UG-06-S03-A080 | UG-06-S03-A090 | FF | 2 | Within package (ladder)
UG-06-S03-A090 | UG-06-S03-A100 | SS | 2 | Within package (ladder)
UG-06-S03-A090 | UG-06-S03-A100 | FF | 2 | Within package (ladder)
UG-05-S05-A100 | UG-06-S03-A100 | FS | 0 | Crew continuity, front F2
UG-05-S02-A080 | UG-06-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-05-S03-A080 | UG-06-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-05-S04-A080 | UG-06-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-06-S03-A100 | UG-06-S03-A110 | SS | 1 | Within package (ladder)
UG-06-S03-A100 | UG-06-S03-A110 | FF | 2 | Within package (ladder)
UG-05-S04-A010 | UG-05-S04-A020 | FS | 0 | Within package
UG-06-S03-A030 | UG-05-S04-A020 | SS | 0 | Set-out one package ahead of piling
UG-05-S04-A020 | UG-05-S04-A030 | SS | 1 | Within package (ladder)
UG-05-S04-A020 | UG-05-S04-A030 | FF | 2 | Within package (ladder)
UG-06-S03-A030 | UG-05-S04-A030 | FS | 0 | Crew continuity, front F2
UG-05-S04-A030 | UG-05-S04-A040 | SS | 4 | Within package (ladder)
UG-05-S04-A030 | UG-05-S04-A040 | FF | 2 | Within package (ladder)
UG-06-S03-A040 | UG-05-S04-A040 | FS | 0 | Crew continuity, front F2
UG-05-S04-A040 | UG-05-S04-A050 | SS | 2 | Within package (ladder)
UG-05-S04-A040 | UG-05-S04-A050 | FF | 2 | Within package (ladder)
UG-06-S03-A060 | UG-05-S04-A050 | FS | -13 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-05-S04-A050 | UG-05-S04-A060 | SS | 11 | Within package (ladder)
UG-05-S04-A050 | UG-05-S04-A060 | FF | 2 | Within package (ladder)
UG-06-S03-A060 | UG-05-S04-A060 | FS | 0 | Crew continuity, front F2
UG-06-S03-A060 | UG-05-S04-A060 | SS | 0 | Shared excavation / dewatering front
UG-06-S04-A060 | UG-05-S04-A060 | SS | 0 | Shared excavation / dewatering front
UG-06-S05-A060 | UG-05-S04-A060 | SS | 0 | Shared excavation / dewatering front
UG-05-S04-A060 | UG-05-S04-A070 | SS | 2 | Within package (ladder)
UG-05-S04-A060 | UG-05-S04-A070 | FF | 2 | Within package (ladder)
UG-06-S03-A070 | UG-05-S04-A070 | FS | 0 | Crew continuity, front F2
UG-05-S04-A070 | UG-05-S04-A080 | SS | 4 | Within package (ladder)
UG-05-S04-A070 | UG-05-S04-A080 | FF | 2 | Within package (ladder)
UG-06-S03-A080 | UG-05-S04-A080 | FS | 0 | Crew continuity, front F2
UG-05-S04-A080 | UG-05-S04-A090 | SS | 2 | Within package (ladder)
UG-05-S04-A080 | UG-05-S04-A090 | FF | 2 | Within package (ladder)
UG-05-S04-A090 | UG-05-S04-A100 | SS | 2 | Within package (ladder)
UG-05-S04-A090 | UG-05-S04-A100 | FF | 2 | Within package (ladder)
UG-06-S03-A100 | UG-05-S04-A100 | FS | 0 | Crew continuity, front F2
UG-06-S03-A080 | UG-05-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-06-S04-A080 | UG-05-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-06-S05-A080 | UG-05-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-05-S04-A100 | UG-05-S04-A110 | SS | 1 | Within package (ladder)
UG-05-S04-A100 | UG-05-S04-A110 | FF | 2 | Within package (ladder)
UG-05-S03-A010 | UG-05-S03-A020 | FS | 0 | Within package
UG-05-S04-A030 | UG-05-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-05-S03-A020 | UG-05-S03-A030 | SS | 1 | Within package (ladder)
UG-05-S03-A020 | UG-05-S03-A030 | FF | 2 | Within package (ladder)
UG-05-S04-A030 | UG-05-S03-A030 | FS | 0 | Crew continuity, front F2
UG-05-S03-A030 | UG-05-S03-A040 | SS | 3 | Within package (ladder)
UG-05-S03-A030 | UG-05-S03-A040 | FF | 2 | Within package (ladder)
UG-05-S04-A040 | UG-05-S03-A040 | FS | 0 | Crew continuity, front F2
UG-05-S03-A040 | UG-05-S03-A050 | SS | 2 | Within package (ladder)
UG-05-S03-A040 | UG-05-S03-A050 | FF | 2 | Within package (ladder)
UG-05-S04-A060 | UG-05-S03-A050 | FS | -12 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-05-S03-A050 | UG-05-S03-A060 | SS | 10 | Within package (ladder)
UG-05-S03-A050 | UG-05-S03-A060 | FF | 2 | Within package (ladder)
UG-05-S04-A060 | UG-05-S03-A060 | FS | 0 | Crew continuity, front F2
UG-06-S03-A060 | UG-05-S03-A060 | SS | 0 | Shared excavation / dewatering front
UG-06-S04-A060 | UG-05-S03-A060 | SS | 0 | Shared excavation / dewatering front
UG-05-S03-A060 | UG-05-S03-A070 | SS | 2 | Within package (ladder)
UG-05-S03-A060 | UG-05-S03-A070 | FF | 2 | Within package (ladder)
UG-05-S04-A070 | UG-05-S03-A070 | FS | 0 | Crew continuity, front F2
UG-05-S03-A070 | UG-05-S03-A080 | SS | 3 | Within package (ladder)
UG-05-S03-A070 | UG-05-S03-A080 | FF | 2 | Within package (ladder)
UG-05-S04-A080 | UG-05-S03-A080 | FS | 0 | Crew continuity, front F2
UG-05-S03-A080 | UG-05-S03-A090 | SS | 2 | Within package (ladder)
UG-05-S03-A080 | UG-05-S03-A090 | FF | 2 | Within package (ladder)
UG-05-S03-A090 | UG-05-S03-A100 | SS | 2 | Within package (ladder)
UG-05-S03-A090 | UG-05-S03-A100 | FF | 2 | Within package (ladder)
UG-05-S04-A100 | UG-05-S03-A100 | FS | 0 | Crew continuity, front F2
UG-06-S03-A080 | UG-05-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-06-S04-A080 | UG-05-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-05-S03-A100 | UG-05-S03-A110 | SS | 2 | Within package (ladder)
UG-05-S03-A100 | UG-05-S03-A110 | FF | 2 | Within package (ladder)
UG-05-S02-A010 | UG-05-S02-A020 | FS | 0 | Within package
UG-05-S03-A030 | UG-05-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-05-S02-A020 | UG-05-S02-A030 | SS | 1 | Within package (ladder)
UG-05-S02-A020 | UG-05-S02-A030 | FF | 2 | Within package (ladder)
UG-05-S03-A030 | UG-05-S02-A030 | FS | 0 | Crew continuity, front F2
UG-05-S02-A030 | UG-05-S02-A040 | SS | 2 | Within package (ladder)
UG-05-S02-A030 | UG-05-S02-A040 | FF | 0 | Within package (ladder)
UG-05-S03-A040 | UG-05-S02-A040 | FS | 0 | Crew continuity, front F2
UG-05-S02-A040 | UG-05-S02-A050 | SS | 0 | Within package (ladder)
UG-05-S02-A040 | UG-05-S02-A050 | FF | 2 | Within package (ladder)
UG-05-S03-A060 | UG-05-S02-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-05-S02-A050 | UG-05-S02-A060 | SS | 10 | Within package (ladder)
UG-05-S02-A050 | UG-05-S02-A060 | FF | 2 | Within package (ladder)
UG-05-S03-A060 | UG-05-S02-A060 | FS | 0 | Crew continuity, front F2
UG-06-S03-A060 | UG-05-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-05-S02-A060 | UG-05-S02-A070 | SS | 1 | Within package (ladder)
UG-05-S02-A060 | UG-05-S02-A070 | FF | 2 | Within package (ladder)
UG-05-S03-A070 | UG-05-S02-A070 | FS | 0 | Crew continuity, front F2
UG-05-S02-A070 | UG-05-S02-A080 | SS | 3 | Within package (ladder)
UG-05-S02-A070 | UG-05-S02-A080 | FF | 2 | Within package (ladder)
UG-05-S03-A080 | UG-05-S02-A080 | FS | 0 | Crew continuity, front F2
UG-05-S02-A080 | UG-05-S02-A090 | SS | 2 | Within package (ladder)
UG-05-S02-A080 | UG-05-S02-A090 | FF | 2 | Within package (ladder)
UG-05-S02-A090 | UG-05-S02-A100 | SS | 2 | Within package (ladder)
UG-05-S02-A090 | UG-05-S02-A100 | FF | 2 | Within package (ladder)
UG-05-S03-A100 | UG-05-S02-A100 | FS | 0 | Crew continuity, front F2
UG-06-S03-A080 | UG-05-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-24-S01-A080 | UG-05-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-24-S02-A080 | UG-05-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-05-S02-A100 | UG-05-S02-A110 | SS | 1 | Within package (ladder)
UG-05-S02-A100 | UG-05-S02-A110 | FF | 2 | Within package (ladder)
UG-06-S01-A010 | UG-06-S01-A020 | FS | 0 | Within package
UG-06-S02-A030 | UG-06-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-06-S01-A020 | UG-06-S01-A030 | SS | 1 | Within package (ladder)
UG-06-S01-A020 | UG-06-S01-A030 | FF | 2 | Within package (ladder)
UG-06-S01-A030 | UG-06-S01-A040 | SS | 1 | Within package (ladder)
UG-06-S01-A030 | UG-06-S01-A040 | FF | 2 | Within package (ladder)
UG-06-S01-A040 | UG-06-S01-A050 | SS | 1 | Within package (ladder)
UG-06-S01-A040 | UG-06-S01-A050 | FF | 2 | Within package (ladder)
UG-06-S01-A050 | UG-06-S01-A060 | SS | 10 | Within package (ladder)
UG-06-S01-A050 | UG-06-S01-A060 | FF | 2 | Within package (ladder)
UG-06-S01-A060 | UG-06-S01-A070 | SS | 1 | Within package (ladder)
UG-06-S01-A060 | UG-06-S01-A070 | FF | 2 | Within package (ladder)
UG-06-S01-A070 | UG-06-S01-A080 | SS | 2 | Within package (ladder)
UG-06-S01-A070 | UG-06-S01-A080 | FF | 2 | Within package (ladder)
UG-06-S02-A080 | UG-06-S01-A080 | FS | 0 | Tie-in laid as closure
UG-06-S01-A080 | UG-06-S01-A090 | SS | 3 | Within package (ladder)
UG-06-S01-A080 | UG-06-S01-A090 | FF | 2 | Within package (ladder)
UG-06-S01-A090 | UG-06-S01-A100 | SS | 2 | Within package (ladder)
UG-06-S01-A090 | UG-06-S01-A100 | FF | 2 | Within package (ladder)
UG-05-S01-A080 | UG-06-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-06-S01-A100 | UG-06-S01-A110 | SS | 1 | Within package (ladder)
UG-06-S01-A100 | UG-06-S01-A110 | FF | 2 | Within package (ladder)
UG-05-S01-A010 | UG-05-S01-A020 | FS | 0 | Within package
UG-05-S02-A030 | UG-05-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-05-S01-A020 | UG-05-S01-A030 | SS | 1 | Within package (ladder)
UG-05-S01-A020 | UG-05-S01-A030 | FF | 2 | Within package (ladder)
UG-05-S01-A030 | UG-05-S01-A040 | SS | 1 | Within package (ladder)
UG-05-S01-A030 | UG-05-S01-A040 | FF | 0 | Within package (ladder)
UG-05-S01-A040 | UG-05-S01-A050 | SS | 0 | Within package (ladder)
UG-05-S01-A040 | UG-05-S01-A050 | FF | 2 | Within package (ladder)
UG-05-S01-A050 | UG-05-S01-A060 | SS | 10 | Within package (ladder)
UG-05-S01-A050 | UG-05-S01-A060 | FF | 2 | Within package (ladder)
UG-06-S01-A060 | UG-05-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-05-S01-A060 | UG-05-S01-A070 | SS | 1 | Within package (ladder)
UG-05-S01-A060 | UG-05-S01-A070 | FF | 2 | Within package (ladder)
UG-05-S01-A070 | UG-05-S01-A080 | SS | 2 | Within package (ladder)
UG-05-S01-A070 | UG-05-S01-A080 | FF | 2 | Within package (ladder)
UG-05-S02-A080 | UG-05-S01-A080 | FS | 0 | Tie-in laid as closure
UG-05-S01-A080 | UG-05-S01-A090 | SS | 2 | Within package (ladder)
UG-05-S01-A080 | UG-05-S01-A090 | FF | 2 | Within package (ladder)
UG-05-S01-A090 | UG-05-S01-A100 | SS | 2 | Within package (ladder)
UG-05-S01-A090 | UG-05-S01-A100 | FF | 2 | Within package (ladder)
UG-06-S01-A080 | UG-05-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-24-S01-A080 | UG-05-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-24-S02-A080 | UG-05-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-05-S01-A100 | UG-05-S01-A110 | SS | 1 | Within package (ladder)
UG-05-S01-A100 | UG-05-S01-A110 | FF | 2 | Within package (ladder)
UG-24-S01-A010 | UG-24-S01-A020 | FS | 0 | Within package
UG-05-S02-A030 | UG-24-S01-A020 | SS | 0 | Set-out one package ahead of piling
UG-24-S01-A020 | UG-24-S01-A030 | SS | 1 | Within package (ladder)
UG-24-S01-A020 | UG-24-S01-A030 | FF | 2 | Within package (ladder)
UG-05-S02-A030 | UG-24-S01-A030 | FS | 0 | Crew continuity, front F2
UG-24-S01-A030 | UG-24-S01-A040 | SS | 4 | Within package (ladder)
UG-24-S01-A030 | UG-24-S01-A040 | FF | 2 | Within package (ladder)
UG-05-S02-A040 | UG-24-S01-A040 | FS | 0 | Crew continuity, front F2
UG-24-S01-A040 | UG-24-S01-A050 | SS | 2 | Within package (ladder)
UG-24-S01-A040 | UG-24-S01-A050 | FF | 2 | Within package (ladder)
UG-05-S02-A060 | UG-24-S01-A050 | FS | -13 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-24-S01-A050 | UG-24-S01-A060 | SS | 11 | Within package (ladder)
UG-24-S01-A050 | UG-24-S01-A060 | FF | 2 | Within package (ladder)
UG-05-S02-A060 | UG-24-S01-A060 | FS | 0 | Crew continuity, front F2
UG-02-S04-A100 | UG-24-S01-A060 | FS | 0 | Deeper line first
UG-02-S05-A100 | UG-24-S01-A060 | FS | 0 | Deeper line first
UG-03-S01-A100 | UG-24-S01-A060 | FS | 0 | Deeper line first
UG-03-S02-A100 | UG-24-S01-A060 | FS | 0 | Deeper line first
UG-03-S03-A100 | UG-24-S01-A060 | FS | 0 | Deeper line first
UG-03-S04-A100 | UG-24-S01-A060 | FS | 0 | Deeper line first
UG-03-S05-A100 | UG-24-S01-A060 | FS | 0 | Deeper line first
UG-04-S01-A100 | UG-24-S01-A060 | FS | 0 | Deeper line first
UG-04-S02-A100 | UG-24-S01-A060 | FS | 0 | Deeper line first
UG-05-S01-A060 | UG-24-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-05-S02-A060 | UG-24-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-24-S01-A060 | UG-24-S01-A070 | SS | 2 | Within package (ladder)
UG-24-S01-A060 | UG-24-S01-A070 | FF | 2 | Within package (ladder)
UG-05-S02-A070 | UG-24-S01-A070 | FS | 0 | Crew continuity, front F2
UG-24-S01-A070 | UG-24-S01-A080 | SS | 4 | Within package (ladder)
UG-24-S01-A070 | UG-24-S01-A080 | FF | 2 | Within package (ladder)
UG-05-S02-A080 | UG-24-S01-A080 | FS | 0 | Crew continuity, front F2
UG-24-S01-A080 | UG-24-S01-A090 | SS | 3 | Within package (ladder)
UG-24-S01-A080 | UG-24-S01-A090 | FF | 2 | Within package (ladder)
UG-24-S01-A090 | UG-24-S01-A100 | SS | 2 | Within package (ladder)
UG-24-S01-A090 | UG-24-S01-A100 | FF | 2 | Within package (ladder)
UG-05-S02-A100 | UG-24-S01-A100 | FS | 0 | Crew continuity, front F2
UG-05-S01-A080 | UG-24-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-05-S02-A080 | UG-24-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-24-S01-A100 | UG-24-S01-A110 | SS | 1 | Within package (ladder)
UG-24-S01-A100 | UG-24-S01-A110 | FF | 2 | Within package (ladder)
UG-24-S02-A010 | UG-24-S02-A020 | FS | 0 | Within package
UG-24-S01-A030 | UG-24-S02-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-24-S02-A020 | UG-24-S02-A030 | SS | 1 | Within package (ladder)
UG-24-S02-A020 | UG-24-S02-A030 | FF | 2 | Within package (ladder)
UG-24-S02-A030 | UG-24-S02-A040 | SS | 1 | Within package (ladder)
UG-24-S02-A030 | UG-24-S02-A040 | FF | 0 | Within package (ladder)
UG-24-S02-A040 | UG-24-S02-A050 | SS | 0 | Within package (ladder)
UG-24-S02-A040 | UG-24-S02-A050 | FF | 2 | Within package (ladder)
UG-24-S02-A050 | UG-24-S02-A060 | SS | 10 | Within package (ladder)
UG-24-S02-A050 | UG-24-S02-A060 | FF | 2 | Within package (ladder)
UG-04-S02-A100 | UG-24-S02-A060 | FS | 0 | Deeper line first
UG-05-S01-A060 | UG-24-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-05-S02-A060 | UG-24-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-24-S02-A060 | UG-24-S02-A070 | SS | 1 | Within package (ladder)
UG-24-S02-A060 | UG-24-S02-A070 | FF | 2 | Within package (ladder)
UG-24-S02-A070 | UG-24-S02-A080 | SS | 2 | Within package (ladder)
UG-24-S02-A070 | UG-24-S02-A080 | FF | 2 | Within package (ladder)
UG-24-S01-A080 | UG-24-S02-A080 | FS | 0 | Tie-in laid as closure
UG-24-S02-A080 | UG-24-S02-A090 | SS | 2 | Within package (ladder)
UG-24-S02-A080 | UG-24-S02-A090 | FF | 2 | Within package (ladder)
UG-24-S02-A090 | UG-24-S02-A100 | SS | 2 | Within package (ladder)
UG-24-S02-A090 | UG-24-S02-A100 | FF | 2 | Within package (ladder)
UG-05-S01-A080 | UG-24-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-05-S02-A080 | UG-24-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-24-S02-A100 | UG-24-S02-A110 | SS | 1 | Within package (ladder)
UG-24-S02-A100 | UG-24-S02-A110 | FF | 2 | Within package (ladder)
UG-10-S04-A010 | UG-10-S04-A020 | FS | 0 | Within package
UG-10-S04-A020 | UG-10-S04-A030 | SS | 1 | Within package (ladder)
UG-10-S04-A020 | UG-10-S04-A030 | FF | 2 | Within package (ladder)
UG-10-S04-A030 | UG-10-S04-A040 | SS | 3 | Within package (ladder)
UG-10-S04-A030 | UG-10-S04-A040 | FF | 2 | Within package (ladder)
UG-10-S04-A040 | UG-10-S04-A050 | SS | 2 | Within package (ladder)
UG-10-S04-A040 | UG-10-S04-A050 | FF | 2 | Within package (ladder)
UG-10-S04-A050 | UG-10-S04-A060 | SS | 10 | Within package (ladder)
UG-10-S04-A050 | UG-10-S04-A060 | FF | 2 | Within package (ladder)
UG-15-S02-A100 | UG-10-S04-A060 | FS | 0 | Deeper line first
UG-10-S04-A060 | UG-10-S04-A070 | SS | 2 | Within package (ladder)
UG-10-S04-A060 | UG-10-S04-A070 | FF | 2 | Within package (ladder)
UG-10-S04-A070 | UG-10-S04-A080 | SS | 3 | Within package (ladder)
UG-10-S04-A070 | UG-10-S04-A080 | FF | 2 | Within package (ladder)
UG-10-S04-A080 | UG-10-S04-A090 | SS | 2 | Within package (ladder)
UG-10-S04-A080 | UG-10-S04-A090 | FF | 2 | Within package (ladder)
UG-10-S04-A090 | UG-10-S04-A100 | SS | 2 | Within package (ladder)
UG-10-S04-A090 | UG-10-S04-A100 | FF | 2 | Within package (ladder)
UG-10-S04-A100 | UG-10-S04-A110 | SS | 1 | Within package (ladder)
UG-10-S04-A100 | UG-10-S04-A110 | FF | 2 | Within package (ladder)
UG-10-S05-A010 | UG-10-S05-A020 | FS | 0 | Within package
UG-10-S04-A030 | UG-10-S05-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-10-S05-A020 | UG-10-S05-A030 | SS | 1 | Within package (ladder)
UG-10-S05-A020 | UG-10-S05-A030 | FF | 2 | Within package (ladder)
UG-10-S05-A030 | UG-10-S05-A040 | SS | 1 | Within package (ladder)
UG-10-S05-A030 | UG-10-S05-A040 | FF | 2 | Within package (ladder)
UG-10-S05-A040 | UG-10-S05-A050 | SS | 1 | Within package (ladder)
UG-10-S05-A040 | UG-10-S05-A050 | FF | 2 | Within package (ladder)
UG-10-S05-A050 | UG-10-S05-A060 | SS | 10 | Within package (ladder)
UG-10-S05-A050 | UG-10-S05-A060 | FF | 2 | Within package (ladder)
UG-10-S05-A060 | UG-10-S05-A070 | SS | 1 | Within package (ladder)
UG-10-S05-A060 | UG-10-S05-A070 | FF | 2 | Within package (ladder)
UG-10-S05-A070 | UG-10-S05-A080 | SS | 2 | Within package (ladder)
UG-10-S05-A070 | UG-10-S05-A080 | FF | 2 | Within package (ladder)
UG-10-S04-A080 | UG-10-S05-A080 | FS | 0 | Tie-in laid as closure
UG-10-S05-A080 | UG-10-S05-A090 | SS | 2 | Within package (ladder)
UG-10-S05-A080 | UG-10-S05-A090 | FF | 2 | Within package (ladder)
UG-10-S05-A090 | UG-10-S05-A100 | SS | 2 | Within package (ladder)
UG-10-S05-A090 | UG-10-S05-A100 | FF | 2 | Within package (ladder)
UG-10-S05-A100 | UG-10-S05-A110 | SS | 1 | Within package (ladder)
UG-10-S05-A100 | UG-10-S05-A110 | FF | 2 | Within package (ladder)
UG-10-S03-A010 | UG-10-S03-A020 | FS | 0 | Within package
UG-10-S04-A030 | UG-10-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-10-S03-A020 | UG-10-S03-A030 | SS | 1 | Within package (ladder)
UG-10-S03-A020 | UG-10-S03-A030 | FF | 2 | Within package (ladder)
UG-10-S04-A030 | UG-10-S03-A030 | FS | 0 | Crew continuity, front F3
UG-10-S03-A030 | UG-10-S03-A040 | SS | 2 | Within package (ladder)
UG-10-S03-A030 | UG-10-S03-A040 | FF | 2 | Within package (ladder)
UG-10-S04-A040 | UG-10-S03-A040 | FS | 0 | Crew continuity, front F3
UG-10-S03-A040 | UG-10-S03-A050 | SS | 1 | Within package (ladder)
UG-10-S03-A040 | UG-10-S03-A050 | FF | 2 | Within package (ladder)
UG-10-S04-A060 | UG-10-S03-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-10-S03-A050 | UG-10-S03-A060 | SS | 10 | Within package (ladder)
UG-10-S03-A050 | UG-10-S03-A060 | FF | 2 | Within package (ladder)
UG-10-S04-A060 | UG-10-S03-A060 | FS | 0 | Crew continuity, front F3
UG-15-S02-A100 | UG-10-S03-A060 | FS | 0 | Deeper line first
UG-15-S03-A100 | UG-10-S03-A060 | FS | 0 | Deeper line first
UG-21-S01-A100 | UG-10-S03-A060 | FS | 0 | Deeper line first
UG-22-S01-A100 | UG-10-S03-A060 | FS | 0 | Deeper line first
UG-28-S02-A100 | UG-10-S03-A060 | FS | 0 | Deeper line first
UG-10-S03-A060 | UG-10-S03-A070 | SS | 1 | Within package (ladder)
UG-10-S03-A060 | UG-10-S03-A070 | FF | 2 | Within package (ladder)
UG-10-S04-A070 | UG-10-S03-A070 | FS | 0 | Crew continuity, front F3
UG-10-S03-A070 | UG-10-S03-A080 | SS | 3 | Within package (ladder)
UG-10-S03-A070 | UG-10-S03-A080 | FF | 2 | Within package (ladder)
UG-10-S04-A080 | UG-10-S03-A080 | FS | 0 | Crew continuity, front F3
UG-10-S03-A080 | UG-10-S03-A090 | SS | 2 | Within package (ladder)
UG-10-S03-A080 | UG-10-S03-A090 | FF | 2 | Within package (ladder)
UG-10-S03-A090 | UG-10-S03-A100 | SS | 2 | Within package (ladder)
UG-10-S03-A090 | UG-10-S03-A100 | FF | 2 | Within package (ladder)
UG-10-S04-A100 | UG-10-S03-A100 | FS | 0 | Crew continuity, front F3
UG-10-S03-A100 | UG-10-S03-A110 | SS | 1 | Within package (ladder)
UG-10-S03-A100 | UG-10-S03-A110 | FF | 2 | Within package (ladder)
UG-10-S02-A010 | UG-10-S02-A020 | FS | 0 | Within package
UG-10-S03-A030 | UG-10-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-10-S02-A020 | UG-10-S02-A030 | SS | 1 | Within package (ladder)
UG-10-S02-A020 | UG-10-S02-A030 | FF | 2 | Within package (ladder)
UG-10-S03-A030 | UG-10-S02-A030 | FS | 0 | Crew continuity, front F3
UG-10-S02-A030 | UG-10-S02-A040 | SS | 6 | Within package (ladder)
UG-10-S02-A030 | UG-10-S02-A040 | FF | 2 | Within package (ladder)
UG-10-S03-A040 | UG-10-S02-A040 | FS | 0 | Crew continuity, front F3
UG-10-S02-A040 | UG-10-S02-A050 | SS | 4 | Within package (ladder)
UG-10-S02-A040 | UG-10-S02-A050 | FF | 2 | Within package (ladder)
UG-10-S03-A060 | UG-10-S02-A050 | FS | -12 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-10-S02-A050 | UG-10-S02-A060 | SS | 10 | Within package (ladder)
UG-10-S02-A050 | UG-10-S02-A060 | FF | 2 | Within package (ladder)
UG-10-S03-A060 | UG-10-S02-A060 | FS | 0 | Crew continuity, front F3
UG-21-S01-A100 | UG-10-S02-A060 | FS | 0 | Deeper line first
UG-22-S01-A100 | UG-10-S02-A060 | FS | 0 | Deeper line first
UG-28-S02-A100 | UG-10-S02-A060 | FS | 0 | Deeper line first
UG-10-S02-A060 | UG-10-S02-A070 | SS | 3 | Within package (ladder)
UG-10-S02-A060 | UG-10-S02-A070 | FF | 2 | Within package (ladder)
UG-10-S03-A070 | UG-10-S02-A070 | FS | 0 | Crew continuity, front F3
UG-10-S02-A070 | UG-10-S02-A080 | SS | 5 | Within package (ladder)
UG-10-S02-A070 | UG-10-S02-A080 | FF | 2 | Within package (ladder)
UG-10-S03-A080 | UG-10-S02-A080 | FS | 0 | Crew continuity, front F3
UG-10-S02-A080 | UG-10-S02-A090 | SS | 3 | Within package (ladder)
UG-10-S02-A080 | UG-10-S02-A090 | FF | 2 | Within package (ladder)
UG-10-S02-A090 | UG-10-S02-A100 | SS | 2 | Within package (ladder)
UG-10-S02-A090 | UG-10-S02-A100 | FF | 2 | Within package (ladder)
UG-10-S03-A100 | UG-10-S02-A100 | FS | 0 | Crew continuity, front F3
UG-10-S02-A100 | UG-10-S02-A110 | SS | 1 | Within package (ladder)
UG-10-S02-A100 | UG-10-S02-A110 | FF | 2 | Within package (ladder)
UG-10-S01-A010 | UG-10-S01-A020 | FS | 0 | Within package
UG-10-S02-A030 | UG-10-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-10-S01-A020 | UG-10-S01-A030 | SS | 1 | Within package (ladder)
UG-10-S01-A020 | UG-10-S01-A030 | FF | 2 | Within package (ladder)
UG-10-S01-A030 | UG-10-S01-A040 | SS | 1 | Within package (ladder)
UG-10-S01-A030 | UG-10-S01-A040 | FF | 2 | Within package (ladder)
UG-10-S01-A040 | UG-10-S01-A050 | SS | 1 | Within package (ladder)
UG-10-S01-A040 | UG-10-S01-A050 | FF | 2 | Within package (ladder)
UG-10-S01-A050 | UG-10-S01-A060 | SS | 10 | Within package (ladder)
UG-10-S01-A050 | UG-10-S01-A060 | FF | 2 | Within package (ladder)
UG-10-S01-A060 | UG-10-S01-A070 | SS | 1 | Within package (ladder)
UG-10-S01-A060 | UG-10-S01-A070 | FF | 2 | Within package (ladder)
UG-10-S01-A070 | UG-10-S01-A080 | SS | 2 | Within package (ladder)
UG-10-S01-A070 | UG-10-S01-A080 | FF | 2 | Within package (ladder)
UG-10-S02-A080 | UG-10-S01-A080 | FS | 0 | Tie-in laid as closure
UG-10-S01-A080 | UG-10-S01-A090 | SS | 2 | Within package (ladder)
UG-10-S01-A080 | UG-10-S01-A090 | FF | 2 | Within package (ladder)
UG-10-S01-A090 | UG-10-S01-A100 | SS | 2 | Within package (ladder)
UG-10-S01-A090 | UG-10-S01-A100 | FF | 2 | Within package (ladder)
UG-10-S01-A100 | UG-10-S01-A110 | SS | 1 | Within package (ladder)
UG-10-S01-A100 | UG-10-S01-A110 | FF | 2 | Within package (ladder)
UG-08-S06-A010 | UG-08-S06-A020 | FS | 0 | Within package
UG-10-S02-A030 | UG-08-S06-A020 | SS | 0 | Set-out one package ahead of piling
UG-08-S06-A020 | UG-08-S06-A030 | SS | 1 | Within package (ladder)
UG-08-S06-A020 | UG-08-S06-A030 | FF | 2 | Within package (ladder)
UG-10-S02-A030 | UG-08-S06-A030 | FS | 0 | Crew continuity, front F3
UG-08-S06-A030 | UG-08-S06-A040 | SS | 3 | Within package (ladder)
UG-08-S06-A030 | UG-08-S06-A040 | FF | 2 | Within package (ladder)
UG-10-S02-A040 | UG-08-S06-A040 | FS | 0 | Crew continuity, front F3
UG-08-S06-A040 | UG-08-S06-A050 | SS | 2 | Within package (ladder)
UG-08-S06-A040 | UG-08-S06-A050 | FF | 2 | Within package (ladder)
UG-10-S02-A060 | UG-08-S06-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-08-S06-A050 | UG-08-S06-A060 | SS | 10 | Within package (ladder)
UG-08-S06-A050 | UG-08-S06-A060 | FF | 2 | Within package (ladder)
UG-10-S02-A060 | UG-08-S06-A060 | FS | 0 | Crew continuity, front F3
UG-08-S06-A060 | UG-08-S06-A070 | SS | 2 | Within package (ladder)
UG-08-S06-A060 | UG-08-S06-A070 | FF | 2 | Within package (ladder)
UG-10-S02-A070 | UG-08-S06-A070 | FS | 0 | Crew continuity, front F3
UG-08-S06-A070 | UG-08-S06-A080 | SS | 3 | Within package (ladder)
UG-08-S06-A070 | UG-08-S06-A080 | FF | 2 | Within package (ladder)
UG-10-S02-A080 | UG-08-S06-A080 | FS | 0 | Crew continuity, front F3
UG-08-S06-A080 | UG-08-S06-A090 | SS | 2 | Within package (ladder)
UG-08-S06-A080 | UG-08-S06-A090 | FF | 2 | Within package (ladder)
UG-08-S06-A090 | UG-08-S06-A100 | SS | 2 | Within package (ladder)
UG-08-S06-A090 | UG-08-S06-A100 | FF | 2 | Within package (ladder)
UG-10-S02-A100 | UG-08-S06-A100 | FS | 0 | Crew continuity, front F3
UG-09-S06-A080 | UG-08-S06-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-08-S06-A100 | UG-08-S06-A110 | SS | 1 | Within package (ladder)
UG-08-S06-A100 | UG-08-S06-A110 | FF | 2 | Within package (ladder)
UG-09-S07-A010 | UG-09-S07-A020 | FS | 0 | Within package
UG-08-S06-A030 | UG-09-S07-A020 | SS | 0 | Set-out one package ahead of piling
UG-09-S07-A020 | UG-09-S07-A030 | SS | 1 | Within package (ladder)
UG-09-S07-A020 | UG-09-S07-A030 | FF | 2 | Within package (ladder)
UG-08-S06-A030 | UG-09-S07-A030 | FS | 0 | Crew continuity, front F3
UG-09-S07-A030 | UG-09-S07-A040 | SS | 3 | Within package (ladder)
UG-09-S07-A030 | UG-09-S07-A040 | FF | 2 | Within package (ladder)
UG-08-S06-A040 | UG-09-S07-A040 | FS | 0 | Crew continuity, front F3
UG-09-S07-A040 | UG-09-S07-A050 | SS | 2 | Within package (ladder)
UG-09-S07-A040 | UG-09-S07-A050 | FF | 2 | Within package (ladder)
UG-08-S06-A060 | UG-09-S07-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-09-S07-A050 | UG-09-S07-A060 | SS | 10 | Within package (ladder)
UG-09-S07-A050 | UG-09-S07-A060 | FF | 2 | Within package (ladder)
UG-08-S06-A060 | UG-09-S07-A060 | FS | 0 | Crew continuity, front F3
UG-09-S07-A060 | UG-09-S07-A070 | SS | 2 | Within package (ladder)
UG-09-S07-A060 | UG-09-S07-A070 | FF | 2 | Within package (ladder)
UG-08-S06-A070 | UG-09-S07-A070 | FS | 0 | Crew continuity, front F3
UG-09-S07-A070 | UG-09-S07-A080 | SS | 3 | Within package (ladder)
UG-09-S07-A070 | UG-09-S07-A080 | FF | 2 | Within package (ladder)
UG-08-S06-A080 | UG-09-S07-A080 | FS | 0 | Crew continuity, front F3
UG-09-S07-A080 | UG-09-S07-A090 | SS | 2 | Within package (ladder)
UG-09-S07-A080 | UG-09-S07-A090 | FF | 2 | Within package (ladder)
UG-09-S07-A090 | UG-09-S07-A100 | SS | 2 | Within package (ladder)
UG-09-S07-A090 | UG-09-S07-A100 | FF | 2 | Within package (ladder)
UG-08-S06-A100 | UG-09-S07-A100 | FS | 0 | Crew continuity, front F3
UG-08-S05-A080 | UG-09-S07-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-09-S07-A100 | UG-09-S07-A110 | SS | 1 | Within package (ladder)
UG-09-S07-A100 | UG-09-S07-A110 | FF | 2 | Within package (ladder)
UG-08-S05-A010 | UG-08-S05-A020 | FS | 0 | Within package
UG-09-S07-A030 | UG-08-S05-A020 | SS | 0 | Set-out one package ahead of piling
UG-08-S05-A020 | UG-08-S05-A030 | SS | 1 | Within package (ladder)
UG-08-S05-A020 | UG-08-S05-A030 | FF | 2 | Within package (ladder)
UG-09-S07-A030 | UG-08-S05-A030 | FS | 0 | Crew continuity, front F3
UG-08-S05-A030 | UG-08-S05-A040 | SS | 6 | Within package (ladder)
UG-08-S05-A030 | UG-08-S05-A040 | FF | 2 | Within package (ladder)
UG-09-S07-A040 | UG-08-S05-A040 | FS | 0 | Crew continuity, front F3
UG-08-S05-A040 | UG-08-S05-A050 | SS | 2 | Within package (ladder)
UG-08-S05-A040 | UG-08-S05-A050 | FF | 2 | Within package (ladder)
UG-09-S07-A060 | UG-08-S05-A050 | FS | -12 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-08-S05-A050 | UG-08-S05-A060 | SS | 10 | Within package (ladder)
UG-08-S05-A050 | UG-08-S05-A060 | FF | 2 | Within package (ladder)
UG-09-S07-A060 | UG-08-S05-A060 | FS | 0 | Crew continuity, front F3
UG-12-S03-A100 | UG-08-S05-A060 | FS | 0 | Deeper line first
UG-13-S03-A100 | UG-08-S05-A060 | FS | 0 | Deeper line first
UG-13B-S11-A100 | UG-08-S05-A060 | FS | 0 | Deeper line first
UG-09-S07-A060 | UG-08-S05-A060 | SS | 0 | Shared excavation / dewatering front
UG-08-S05-A060 | UG-08-S05-A070 | SS | 3 | Within package (ladder)
UG-08-S05-A060 | UG-08-S05-A070 | FF | 2 | Within package (ladder)
UG-09-S07-A070 | UG-08-S05-A070 | FS | 0 | Crew continuity, front F3
UG-08-S05-A070 | UG-08-S05-A080 | SS | 5 | Within package (ladder)
UG-08-S05-A070 | UG-08-S05-A080 | FF | 2 | Within package (ladder)
UG-09-S07-A080 | UG-08-S05-A080 | FS | 0 | Crew continuity, front F3
UG-08-S05-A080 | UG-08-S05-A090 | SS | 4 | Within package (ladder)
UG-08-S05-A080 | UG-08-S05-A090 | FF | 2 | Within package (ladder)
UG-08-S05-A090 | UG-08-S05-A100 | SS | 2 | Within package (ladder)
UG-08-S05-A090 | UG-08-S05-A100 | FF | 2 | Within package (ladder)
UG-09-S07-A100 | UG-08-S05-A100 | FS | 0 | Crew continuity, front F3
UG-09-S04-A080 | UG-08-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-09-S05-A080 | UG-08-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-09-S06-A080 | UG-08-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-09-S07-A080 | UG-08-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-08-S05-A100 | UG-08-S05-A110 | SS | 2 | Within package (ladder)
UG-08-S05-A100 | UG-08-S05-A110 | FF | 2 | Within package (ladder)
UG-09-S06-A010 | UG-09-S06-A020 | FS | 0 | Within package
UG-08-S05-A030 | UG-09-S06-A020 | SS | 0 | Set-out one package ahead of piling
UG-09-S06-A020 | UG-09-S06-A030 | SS | 1 | Within package (ladder)
UG-09-S06-A020 | UG-09-S06-A030 | FF | 2 | Within package (ladder)
UG-08-S05-A030 | UG-09-S06-A030 | FS | 0 | Crew continuity, front F3
UG-09-S06-A030 | UG-09-S06-A040 | SS | 4 | Within package (ladder)
UG-09-S06-A030 | UG-09-S06-A040 | FF | 2 | Within package (ladder)
UG-08-S05-A040 | UG-09-S06-A040 | FS | 0 | Crew continuity, front F3
UG-09-S06-A040 | UG-09-S06-A050 | SS | 2 | Within package (ladder)
UG-09-S06-A040 | UG-09-S06-A050 | FF | 2 | Within package (ladder)
UG-08-S05-A060 | UG-09-S06-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-09-S06-A050 | UG-09-S06-A060 | SS | 10 | Within package (ladder)
UG-09-S06-A050 | UG-09-S06-A060 | FF | 2 | Within package (ladder)
UG-08-S05-A060 | UG-09-S06-A060 | FS | 0 | Crew continuity, front F3
UG-13B-S08-A100 | UG-09-S06-A060 | FS | 0 | Deeper line first
UG-08-S05-A060 | UG-09-S06-A060 | SS | 0 | Shared excavation / dewatering front
UG-08-S06-A060 | UG-09-S06-A060 | SS | 0 | Shared excavation / dewatering front
UG-09-S06-A060 | UG-09-S06-A070 | SS | 2 | Within package (ladder)
UG-09-S06-A060 | UG-09-S06-A070 | FF | 2 | Within package (ladder)
UG-08-S05-A070 | UG-09-S06-A070 | FS | 0 | Crew continuity, front F3
UG-09-S06-A070 | UG-09-S06-A080 | SS | 4 | Within package (ladder)
UG-09-S06-A070 | UG-09-S06-A080 | FF | 2 | Within package (ladder)
UG-08-S05-A080 | UG-09-S06-A080 | FS | 0 | Crew continuity, front F3
UG-09-S06-A080 | UG-09-S06-A090 | SS | 2 | Within package (ladder)
UG-09-S06-A080 | UG-09-S06-A090 | FF | 2 | Within package (ladder)
UG-09-S06-A090 | UG-09-S06-A100 | SS | 2 | Within package (ladder)
UG-09-S06-A090 | UG-09-S06-A100 | FF | 2 | Within package (ladder)
UG-08-S05-A100 | UG-09-S06-A100 | FS | 0 | Crew continuity, front F3
UG-08-S05-A080 | UG-09-S06-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-08-S06-A080 | UG-09-S06-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-09-S06-A100 | UG-09-S06-A110 | SS | 1 | Within package (ladder)
UG-09-S06-A100 | UG-09-S06-A110 | FF | 2 | Within package (ladder)
UG-09-S05-A010 | UG-09-S05-A020 | FS | 0 | Within package
UG-09-S06-A030 | UG-09-S05-A020 | SS | 0 | Set-out one package ahead of piling
UG-09-S05-A020 | UG-09-S05-A030 | SS | 1 | Within package (ladder)
UG-09-S05-A020 | UG-09-S05-A030 | FF | 2 | Within package (ladder)
UG-09-S06-A030 | UG-09-S05-A030 | FS | 0 | Crew continuity, front F3
UG-09-S05-A030 | UG-09-S05-A040 | SS | 2 | Within package (ladder)
UG-09-S05-A030 | UG-09-S05-A040 | FF | 0 | Within package (ladder)
UG-09-S06-A040 | UG-09-S05-A040 | FS | 0 | Crew continuity, front F3
UG-09-S05-A040 | UG-09-S05-A050 | SS | 0 | Within package (ladder)
UG-09-S05-A040 | UG-09-S05-A050 | FF | 2 | Within package (ladder)
UG-09-S06-A060 | UG-09-S05-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-09-S05-A050 | UG-09-S05-A060 | SS | 10 | Within package (ladder)
UG-09-S05-A050 | UG-09-S05-A060 | FF | 2 | Within package (ladder)
UG-09-S06-A060 | UG-09-S05-A060 | FS | 0 | Crew continuity, front F3
UG-12-S03-A100 | UG-09-S05-A060 | FS | 0 | Deeper line first
UG-13B-S07-A100 | UG-09-S05-A060 | FS | 0 | Deeper line first
UG-13B-S08-A100 | UG-09-S05-A060 | FS | 0 | Deeper line first
UG-13B-S09-A100 | UG-09-S05-A060 | FS | 0 | Deeper line first
UG-13B-S11-A100 | UG-09-S05-A060 | FS | 0 | Deeper line first
UG-08-S05-A060 | UG-09-S05-A060 | SS | 0 | Shared excavation / dewatering front
UG-09-S05-A060 | UG-09-S05-A070 | SS | 1 | Within package (ladder)
UG-09-S05-A060 | UG-09-S05-A070 | FF | 2 | Within package (ladder)
UG-09-S06-A070 | UG-09-S05-A070 | FS | 0 | Crew continuity, front F3
UG-09-S05-A070 | UG-09-S05-A080 | SS | 2 | Within package (ladder)
UG-09-S05-A070 | UG-09-S05-A080 | FF | 2 | Within package (ladder)
UG-09-S06-A080 | UG-09-S05-A080 | FS | 0 | Crew continuity, front F3
UG-09-S05-A080 | UG-09-S05-A090 | SS | 2 | Within package (ladder)
UG-09-S05-A080 | UG-09-S05-A090 | FF | 2 | Within package (ladder)
UG-09-S05-A090 | UG-09-S05-A100 | SS | 2 | Within package (ladder)
UG-09-S05-A090 | UG-09-S05-A100 | FF | 2 | Within package (ladder)
UG-09-S06-A100 | UG-09-S05-A100 | FS | 0 | Crew continuity, front F3
UG-08-S05-A080 | UG-09-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-09-S05-A100 | UG-09-S05-A110 | SS | 1 | Within package (ladder)
UG-09-S05-A100 | UG-09-S05-A110 | FF | 2 | Within package (ladder)
UG-08-S04-A010 | UG-08-S04-A020 | FS | 0 | Within package
UG-09-S05-A030 | UG-08-S04-A020 | SS | 0 | Set-out one package ahead of piling
UG-08-S04-A020 | UG-08-S04-A030 | SS | 1 | Within package (ladder)
UG-08-S04-A020 | UG-08-S04-A030 | FF | 2 | Within package (ladder)
UG-09-S05-A030 | UG-08-S04-A030 | FS | 0 | Crew continuity, front F3
UG-08-S04-A030 | UG-08-S04-A040 | SS | 3 | Within package (ladder)
UG-08-S04-A030 | UG-08-S04-A040 | FF | 0 | Within package (ladder)
UG-09-S05-A040 | UG-08-S04-A040 | FS | 0 | Crew continuity, front F3
UG-08-S04-A040 | UG-08-S04-A050 | SS | 0 | Within package (ladder)
UG-08-S04-A040 | UG-08-S04-A050 | FF | 2 | Within package (ladder)
UG-09-S05-A060 | UG-08-S04-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-08-S04-A050 | UG-08-S04-A060 | SS | 10 | Within package (ladder)
UG-08-S04-A050 | UG-08-S04-A060 | FF | 2 | Within package (ladder)
UG-09-S05-A060 | UG-08-S04-A060 | FS | 0 | Crew continuity, front F3
UG-11-S03-A100 | UG-08-S04-A060 | FS | 0 | Deeper line first
UG-11-S04-A100 | UG-08-S04-A060 | FS | 0 | Deeper line first
UG-13-S05-A100 | UG-08-S04-A060 | FS | 0 | Deeper line first
UG-23-S02-A100 | UG-08-S04-A060 | FS | 0 | Deeper line first
UG-23-S03-A100 | UG-08-S04-A060 | FS | 0 | Deeper line first
UG-23-S04-A100 | UG-08-S04-A060 | FS | 0 | Deeper line first
UG-08-S04-A060 | UG-08-S04-A070 | SS | 2 | Within package (ladder)
UG-08-S04-A060 | UG-08-S04-A070 | FF | 2 | Within package (ladder)
UG-09-S05-A070 | UG-08-S04-A070 | FS | 0 | Crew continuity, front F3
UG-08-S04-A070 | UG-08-S04-A080 | SS | 3 | Within package (ladder)
UG-08-S04-A070 | UG-08-S04-A080 | FF | 2 | Within package (ladder)
UG-09-S05-A080 | UG-08-S04-A080 | FS | 0 | Crew continuity, front F3
UG-08-S04-A080 | UG-08-S04-A090 | SS | 2 | Within package (ladder)
UG-08-S04-A080 | UG-08-S04-A090 | FF | 2 | Within package (ladder)
UG-08-S04-A090 | UG-08-S04-A100 | SS | 2 | Within package (ladder)
UG-08-S04-A090 | UG-08-S04-A100 | FF | 2 | Within package (ladder)
UG-09-S05-A100 | UG-08-S04-A100 | FS | 0 | Crew continuity, front F3
UG-09-S03-A080 | UG-08-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-09-S04-A080 | UG-08-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-08-S04-A100 | UG-08-S04-A110 | SS | 2 | Within package (ladder)
UG-08-S04-A100 | UG-08-S04-A110 | FF | 2 | Within package (ladder)
UG-09-S04-A010 | UG-09-S04-A020 | FS | 0 | Within package
UG-08-S04-A030 | UG-09-S04-A020 | SS | 0 | Set-out one package ahead of piling
UG-09-S04-A020 | UG-09-S04-A030 | SS | 1 | Within package (ladder)
UG-09-S04-A020 | UG-09-S04-A030 | FF | 2 | Within package (ladder)
UG-08-S04-A030 | UG-09-S04-A030 | FS | 0 | Crew continuity, front F3
UG-09-S04-A030 | UG-09-S04-A040 | SS | 5 | Within package (ladder)
UG-09-S04-A030 | UG-09-S04-A040 | FF | 0 | Within package (ladder)
UG-08-S04-A040 | UG-09-S04-A040 | FS | 0 | Crew continuity, front F3
UG-09-S04-A040 | UG-09-S04-A050 | SS | 0 | Within package (ladder)
UG-09-S04-A040 | UG-09-S04-A050 | FF | 2 | Within package (ladder)
UG-08-S04-A060 | UG-09-S04-A050 | FS | -12 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-09-S04-A050 | UG-09-S04-A060 | SS | 10 | Within package (ladder)
UG-09-S04-A050 | UG-09-S04-A060 | FF | 2 | Within package (ladder)
UG-08-S04-A060 | UG-09-S04-A060 | FS | 0 | Crew continuity, front F3
UG-12-S03-A100 | UG-09-S04-A060 | FS | 0 | Deeper line first
UG-13B-S07-A100 | UG-09-S04-A060 | FS | 0 | Deeper line first
UG-13B-S08-A100 | UG-09-S04-A060 | FS | 0 | Deeper line first
UG-13B-S11-A100 | UG-09-S04-A060 | FS | 0 | Deeper line first
UG-23-S03-A100 | UG-09-S04-A060 | FS | 0 | Deeper line first
UG-23-S04-A100 | UG-09-S04-A060 | FS | 0 | Deeper line first
UG-08-S04-A060 | UG-09-S04-A060 | SS | 0 | Shared excavation / dewatering front
UG-08-S05-A060 | UG-09-S04-A060 | SS | 0 | Shared excavation / dewatering front
UG-09-S04-A060 | UG-09-S04-A070 | SS | 2 | Within package (ladder)
UG-09-S04-A060 | UG-09-S04-A070 | FF | 2 | Within package (ladder)
UG-08-S04-A070 | UG-09-S04-A070 | FS | 0 | Crew continuity, front F3
UG-09-S04-A070 | UG-09-S04-A080 | SS | 4 | Within package (ladder)
UG-09-S04-A070 | UG-09-S04-A080 | FF | 2 | Within package (ladder)
UG-08-S04-A080 | UG-09-S04-A080 | FS | 0 | Crew continuity, front F3
UG-09-S04-A080 | UG-09-S04-A090 | SS | 3 | Within package (ladder)
UG-09-S04-A080 | UG-09-S04-A090 | FF | 2 | Within package (ladder)
UG-09-S04-A090 | UG-09-S04-A100 | SS | 2 | Within package (ladder)
UG-09-S04-A090 | UG-09-S04-A100 | FF | 2 | Within package (ladder)
UG-08-S04-A100 | UG-09-S04-A100 | FS | 0 | Crew continuity, front F3
UG-08-S03-A080 | UG-09-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-08-S04-A080 | UG-09-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-08-S05-A080 | UG-09-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-09-S04-A100 | UG-09-S04-A110 | SS | 2 | Within package (ladder)
UG-09-S04-A100 | UG-09-S04-A110 | FF | 2 | Within package (ladder)
UG-08-S03-A010 | UG-08-S03-A020 | FS | 0 | Within package
UG-09-S04-A030 | UG-08-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-08-S03-A020 | UG-08-S03-A030 | SS | 1 | Within package (ladder)
UG-08-S03-A020 | UG-08-S03-A030 | FF | 2 | Within package (ladder)
UG-09-S04-A030 | UG-08-S03-A030 | FS | 0 | Crew continuity, front F3
UG-08-S03-A030 | UG-08-S03-A040 | SS | 2 | Within package (ladder)
UG-08-S03-A030 | UG-08-S03-A040 | FF | 2 | Within package (ladder)
UG-09-S04-A040 | UG-08-S03-A040 | FS | 0 | Crew continuity, front F3
UG-08-S03-A040 | UG-08-S03-A050 | SS | 1 | Within package (ladder)
UG-08-S03-A040 | UG-08-S03-A050 | FF | 2 | Within package (ladder)
UG-09-S04-A060 | UG-08-S03-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-08-S03-A050 | UG-08-S03-A060 | SS | 10 | Within package (ladder)
UG-08-S03-A050 | UG-08-S03-A060 | FF | 2 | Within package (ladder)
UG-09-S04-A060 | UG-08-S03-A060 | FS | 0 | Crew continuity, front F3
UG-11-S03-A100 | UG-08-S03-A060 | FS | 0 | Deeper line first
UG-11-S04-A100 | UG-08-S03-A060 | FS | 0 | Deeper line first
UG-23-S03-A100 | UG-08-S03-A060 | FS | 0 | Deeper line first
UG-23-S04-A100 | UG-08-S03-A060 | FS | 0 | Deeper line first
UG-23-S05-A100 | UG-08-S03-A060 | FS | 0 | Deeper line first
UG-09-S04-A060 | UG-08-S03-A060 | SS | 0 | Shared excavation / dewatering front
UG-08-S03-A060 | UG-08-S03-A070 | SS | 1 | Within package (ladder)
UG-08-S03-A060 | UG-08-S03-A070 | FF | 2 | Within package (ladder)
UG-09-S04-A070 | UG-08-S03-A070 | FS | 0 | Crew continuity, front F3
UG-08-S03-A070 | UG-08-S03-A080 | SS | 2 | Within package (ladder)
UG-08-S03-A070 | UG-08-S03-A080 | FF | 2 | Within package (ladder)
UG-09-S04-A080 | UG-08-S03-A080 | FS | 0 | Crew continuity, front F3
UG-08-S03-A080 | UG-08-S03-A090 | SS | 2 | Within package (ladder)
UG-08-S03-A080 | UG-08-S03-A090 | FF | 2 | Within package (ladder)
UG-08-S03-A090 | UG-08-S03-A100 | SS | 2 | Within package (ladder)
UG-08-S03-A090 | UG-08-S03-A100 | FF | 2 | Within package (ladder)
UG-09-S04-A100 | UG-08-S03-A100 | FS | 0 | Crew continuity, front F3
UG-09-S02-A080 | UG-08-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-09-S03-A080 | UG-08-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-09-S04-A080 | UG-08-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-08-S03-A100 | UG-08-S03-A110 | SS | 1 | Within package (ladder)
UG-08-S03-A100 | UG-08-S03-A110 | FF | 2 | Within package (ladder)
UG-08-S02-A010 | UG-08-S02-A020 | FS | 0 | Within package
UG-08-S03-A030 | UG-08-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-08-S02-A020 | UG-08-S02-A030 | SS | 1 | Within package (ladder)
UG-08-S02-A020 | UG-08-S02-A030 | FF | 2 | Within package (ladder)
UG-08-S03-A030 | UG-08-S02-A030 | FS | 0 | Crew continuity, front F3
UG-08-S02-A030 | UG-08-S02-A040 | SS | 2 | Within package (ladder)
UG-08-S02-A030 | UG-08-S02-A040 | FF | 2 | Within package (ladder)
UG-08-S03-A040 | UG-08-S02-A040 | FS | 0 | Crew continuity, front F3
UG-08-S02-A040 | UG-08-S02-A050 | SS | 1 | Within package (ladder)
UG-08-S02-A040 | UG-08-S02-A050 | FF | 2 | Within package (ladder)
UG-08-S03-A060 | UG-08-S02-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-08-S02-A050 | UG-08-S02-A060 | SS | 10 | Within package (ladder)
UG-08-S02-A050 | UG-08-S02-A060 | FF | 2 | Within package (ladder)
UG-08-S03-A060 | UG-08-S02-A060 | FS | 0 | Crew continuity, front F3
UG-11-S04-A100 | UG-08-S02-A060 | FS | 0 | Deeper line first
UG-23-S04-A100 | UG-08-S02-A060 | FS | 0 | Deeper line first
UG-23-S05-A100 | UG-08-S02-A060 | FS | 0 | Deeper line first
UG-08-S02-A060 | UG-08-S02-A070 | SS | 1 | Within package (ladder)
UG-08-S02-A060 | UG-08-S02-A070 | FF | 2 | Within package (ladder)
UG-08-S03-A070 | UG-08-S02-A070 | FS | 0 | Crew continuity, front F3
UG-08-S02-A070 | UG-08-S02-A080 | SS | 2 | Within package (ladder)
UG-08-S02-A070 | UG-08-S02-A080 | FF | 2 | Within package (ladder)
UG-08-S03-A080 | UG-08-S02-A080 | FS | 0 | Crew continuity, front F3
UG-08-S02-A080 | UG-08-S02-A090 | SS | 1 | Within package (ladder)
UG-08-S02-A080 | UG-08-S02-A090 | FF | 2 | Within package (ladder)
UG-08-S02-A090 | UG-08-S02-A100 | SS | 2 | Within package (ladder)
UG-08-S02-A090 | UG-08-S02-A100 | FF | 2 | Within package (ladder)
UG-08-S03-A100 | UG-08-S02-A100 | FS | 0 | Crew continuity, front F3
UG-09-S01-A080 | UG-08-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-09-S02-A080 | UG-08-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-09-S03-A080 | UG-08-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-08-S02-A100 | UG-08-S02-A110 | SS | 1 | Within package (ladder)
UG-08-S02-A100 | UG-08-S02-A110 | FF | 2 | Within package (ladder)
UG-09-S03-A010 | UG-09-S03-A020 | FS | 0 | Within package
UG-08-S02-A030 | UG-09-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-09-S03-A020 | UG-09-S03-A030 | SS | 1 | Within package (ladder)
UG-09-S03-A020 | UG-09-S03-A030 | FF | 2 | Within package (ladder)
UG-08-S02-A030 | UG-09-S03-A030 | FS | 0 | Crew continuity, front F3
UG-09-S03-A030 | UG-09-S03-A040 | SS | 2 | Within package (ladder)
UG-09-S03-A030 | UG-09-S03-A040 | FF | 2 | Within package (ladder)
UG-08-S02-A040 | UG-09-S03-A040 | FS | 0 | Crew continuity, front F3
UG-09-S03-A040 | UG-09-S03-A050 | SS | 1 | Within package (ladder)
UG-09-S03-A040 | UG-09-S03-A050 | FF | 2 | Within package (ladder)
UG-08-S02-A060 | UG-09-S03-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-09-S03-A050 | UG-09-S03-A060 | SS | 10 | Within package (ladder)
UG-09-S03-A050 | UG-09-S03-A060 | FF | 2 | Within package (ladder)
UG-08-S02-A060 | UG-09-S03-A060 | FS | 0 | Crew continuity, front F3
UG-11-S04-A100 | UG-09-S03-A060 | FS | 0 | Deeper line first
UG-11-S05-A100 | UG-09-S03-A060 | FS | 0 | Deeper line first
UG-23-S03-A100 | UG-09-S03-A060 | FS | 0 | Deeper line first
UG-23-S04-A100 | UG-09-S03-A060 | FS | 0 | Deeper line first
UG-23-S05-A100 | UG-09-S03-A060 | FS | 0 | Deeper line first
UG-08-S02-A060 | UG-09-S03-A060 | SS | 0 | Shared excavation / dewatering front
UG-08-S03-A060 | UG-09-S03-A060 | SS | 0 | Shared excavation / dewatering front
UG-08-S04-A060 | UG-09-S03-A060 | SS | 0 | Shared excavation / dewatering front
UG-09-S03-A060 | UG-09-S03-A070 | SS | 1 | Within package (ladder)
UG-09-S03-A060 | UG-09-S03-A070 | FF | 2 | Within package (ladder)
UG-08-S02-A070 | UG-09-S03-A070 | FS | 0 | Crew continuity, front F3
UG-09-S03-A070 | UG-09-S03-A080 | SS | 2 | Within package (ladder)
UG-09-S03-A070 | UG-09-S03-A080 | FF | 2 | Within package (ladder)
UG-08-S02-A080 | UG-09-S03-A080 | FS | 0 | Crew continuity, front F3
UG-09-S03-A080 | UG-09-S03-A090 | SS | 1 | Within package (ladder)
UG-09-S03-A080 | UG-09-S03-A090 | FF | 2 | Within package (ladder)
UG-09-S03-A090 | UG-09-S03-A100 | SS | 2 | Within package (ladder)
UG-09-S03-A090 | UG-09-S03-A100 | FF | 2 | Within package (ladder)
UG-08-S02-A100 | UG-09-S03-A100 | FS | 0 | Crew continuity, front F3
UG-08-S02-A080 | UG-09-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-08-S03-A080 | UG-09-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-08-S04-A080 | UG-09-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-09-S03-A100 | UG-09-S03-A110 | SS | 1 | Within package (ladder)
UG-09-S03-A100 | UG-09-S03-A110 | FF | 2 | Within package (ladder)
UG-08-S01-A010 | UG-08-S01-A020 | FS | 0 | Within package
UG-08-S02-A030 | UG-08-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-08-S01-A020 | UG-08-S01-A030 | SS | 1 | Within package (ladder)
UG-08-S01-A020 | UG-08-S01-A030 | FF | 2 | Within package (ladder)
UG-08-S01-A030 | UG-08-S01-A040 | SS | 2 | Within package (ladder)
UG-08-S01-A030 | UG-08-S01-A040 | FF | 0 | Within package (ladder)
UG-08-S01-A040 | UG-08-S01-A050 | SS | 0 | Within package (ladder)
UG-08-S01-A040 | UG-08-S01-A050 | FF | 2 | Within package (ladder)
UG-08-S01-A050 | UG-08-S01-A060 | SS | 10 | Within package (ladder)
UG-08-S01-A050 | UG-08-S01-A060 | FF | 2 | Within package (ladder)
UG-23-S05-A100 | UG-08-S01-A060 | FS | 0 | Deeper line first
UG-09-S01-A060 | UG-08-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-08-S01-A060 | UG-08-S01-A070 | SS | 1 | Within package (ladder)
UG-08-S01-A060 | UG-08-S01-A070 | FF | 2 | Within package (ladder)
UG-08-S01-A070 | UG-08-S01-A080 | SS | 2 | Within package (ladder)
UG-08-S01-A070 | UG-08-S01-A080 | FF | 2 | Within package (ladder)
UG-08-S02-A080 | UG-08-S01-A080 | FS | 0 | Tie-in laid as closure
UG-08-S01-A080 | UG-08-S01-A090 | SS | 3 | Within package (ladder)
UG-08-S01-A080 | UG-08-S01-A090 | FF | 2 | Within package (ladder)
UG-08-S01-A090 | UG-08-S01-A100 | SS | 2 | Within package (ladder)
UG-08-S01-A090 | UG-08-S01-A100 | FF | 2 | Within package (ladder)
UG-09-S01-A080 | UG-08-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-09-S02-A080 | UG-08-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-08-S01-A100 | UG-08-S01-A110 | SS | 1 | Within package (ladder)
UG-08-S01-A100 | UG-08-S01-A110 | FF | 2 | Within package (ladder)
UG-09-S02-A010 | UG-09-S02-A020 | FS | 0 | Within package
UG-09-S03-A030 | UG-09-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-09-S02-A020 | UG-09-S02-A030 | SS | 1 | Within package (ladder)
UG-09-S02-A020 | UG-09-S02-A030 | FF | 2 | Within package (ladder)
UG-09-S03-A030 | UG-09-S02-A030 | FS | 0 | Crew continuity, front F3
UG-09-S02-A030 | UG-09-S02-A040 | SS | 2 | Within package (ladder)
UG-09-S02-A030 | UG-09-S02-A040 | FF | 2 | Within package (ladder)
UG-09-S03-A040 | UG-09-S02-A040 | FS | 0 | Crew continuity, front F3
UG-09-S02-A040 | UG-09-S02-A050 | SS | 1 | Within package (ladder)
UG-09-S02-A040 | UG-09-S02-A050 | FF | 2 | Within package (ladder)
UG-09-S03-A060 | UG-09-S02-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-09-S02-A050 | UG-09-S02-A060 | SS | 10 | Within package (ladder)
UG-09-S02-A050 | UG-09-S02-A060 | FF | 2 | Within package (ladder)
UG-09-S03-A060 | UG-09-S02-A060 | FS | 0 | Crew continuity, front F3
UG-23-S04-A100 | UG-09-S02-A060 | FS | 0 | Deeper line first
UG-23-S05-A100 | UG-09-S02-A060 | FS | 0 | Deeper line first
UG-08-S01-A060 | UG-09-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-08-S02-A060 | UG-09-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-08-S03-A060 | UG-09-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-09-S02-A060 | UG-09-S02-A070 | SS | 1 | Within package (ladder)
UG-09-S02-A060 | UG-09-S02-A070 | FF | 2 | Within package (ladder)
UG-09-S03-A070 | UG-09-S02-A070 | FS | 0 | Crew continuity, front F3
UG-09-S02-A070 | UG-09-S02-A080 | SS | 2 | Within package (ladder)
UG-09-S02-A070 | UG-09-S02-A080 | FF | 2 | Within package (ladder)
UG-09-S03-A080 | UG-09-S02-A080 | FS | 0 | Crew continuity, front F3
UG-09-S02-A080 | UG-09-S02-A090 | SS | 1 | Within package (ladder)
UG-09-S02-A080 | UG-09-S02-A090 | FF | 2 | Within package (ladder)
UG-09-S02-A090 | UG-09-S02-A100 | SS | 2 | Within package (ladder)
UG-09-S02-A090 | UG-09-S02-A100 | FF | 2 | Within package (ladder)
UG-09-S03-A100 | UG-09-S02-A100 | FS | 0 | Crew continuity, front F3
UG-08-S01-A080 | UG-09-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-08-S02-A080 | UG-09-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-08-S03-A080 | UG-09-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-09-S02-A100 | UG-09-S02-A110 | SS | 1 | Within package (ladder)
UG-09-S02-A100 | UG-09-S02-A110 | FF | 2 | Within package (ladder)
UG-09-S01-A010 | UG-09-S01-A020 | FS | 0 | Within package
UG-09-S02-A030 | UG-09-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-09-S01-A020 | UG-09-S01-A030 | SS | 1 | Within package (ladder)
UG-09-S01-A020 | UG-09-S01-A030 | FF | 2 | Within package (ladder)
UG-09-S01-A030 | UG-09-S01-A040 | SS | 2 | Within package (ladder)
UG-09-S01-A030 | UG-09-S01-A040 | FF | 0 | Within package (ladder)
UG-09-S01-A040 | UG-09-S01-A050 | SS | 0 | Within package (ladder)
UG-09-S01-A040 | UG-09-S01-A050 | FF | 2 | Within package (ladder)
UG-09-S01-A050 | UG-09-S01-A060 | SS | 10 | Within package (ladder)
UG-09-S01-A050 | UG-09-S01-A060 | FF | 2 | Within package (ladder)
UG-23-S05-A100 | UG-09-S01-A060 | FS | 0 | Deeper line first
UG-08-S02-A060 | UG-09-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-09-S01-A060 | UG-09-S01-A070 | SS | 1 | Within package (ladder)
UG-09-S01-A060 | UG-09-S01-A070 | FF | 2 | Within package (ladder)
UG-09-S01-A070 | UG-09-S01-A080 | SS | 2 | Within package (ladder)
UG-09-S01-A070 | UG-09-S01-A080 | FF | 2 | Within package (ladder)
UG-09-S02-A080 | UG-09-S01-A080 | FS | 0 | Tie-in laid as closure
UG-09-S01-A080 | UG-09-S01-A090 | SS | 3 | Within package (ladder)
UG-09-S01-A080 | UG-09-S01-A090 | FF | 2 | Within package (ladder)
UG-09-S01-A090 | UG-09-S01-A100 | SS | 2 | Within package (ladder)
UG-09-S01-A090 | UG-09-S01-A100 | FF | 2 | Within package (ladder)
UG-08-S01-A080 | UG-09-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-08-S02-A080 | UG-09-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-09-S01-A100 | UG-09-S01-A110 | SS | 1 | Within package (ladder)
UG-09-S01-A100 | UG-09-S01-A110 | FF | 2 | Within package (ladder)
UG-08-S07-A010 | UG-08-S07-A020 | FS | 0 | Within package
UG-08-S06-A030 | UG-08-S07-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-08-S07-A020 | UG-08-S07-A030 | SS | 1 | Within package (ladder)
UG-08-S07-A020 | UG-08-S07-A030 | FF | 2 | Within package (ladder)
UG-08-S07-A030 | UG-08-S07-A040 | SS | 1 | Within package (ladder)
UG-08-S07-A030 | UG-08-S07-A040 | FF | 2 | Within package (ladder)
UG-08-S07-A040 | UG-08-S07-A050 | SS | 1 | Within package (ladder)
UG-08-S07-A040 | UG-08-S07-A050 | FF | 2 | Within package (ladder)
UG-08-S07-A050 | UG-08-S07-A060 | SS | 10 | Within package (ladder)
UG-08-S07-A050 | UG-08-S07-A060 | FF | 2 | Within package (ladder)
UG-08-S07-A060 | UG-08-S07-A070 | SS | 1 | Within package (ladder)
UG-08-S07-A060 | UG-08-S07-A070 | FF | 2 | Within package (ladder)
UG-08-S07-A070 | UG-08-S07-A080 | SS | 2 | Within package (ladder)
UG-08-S07-A070 | UG-08-S07-A080 | FF | 2 | Within package (ladder)
UG-08-S06-A080 | UG-08-S07-A080 | FS | 0 | Tie-in laid as closure
UG-08-S07-A080 | UG-08-S07-A090 | SS | 2 | Within package (ladder)
UG-08-S07-A080 | UG-08-S07-A090 | FF | 2 | Within package (ladder)
UG-08-S07-A090 | UG-08-S07-A100 | SS | 2 | Within package (ladder)
UG-08-S07-A090 | UG-08-S07-A100 | FF | 2 | Within package (ladder)
UG-08-S07-A100 | UG-08-S07-A110 | SS | 1 | Within package (ladder)
UG-08-S07-A100 | UG-08-S07-A110 | FF | 2 | Within package (ladder)
UG-13A-S13-A010 | UG-13A-S13-A020 | FS | 0 | Within package
UG-13A-S14-A030 | UG-13A-S13-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-13A-S13-A020 | UG-13A-S13-A030 | SS | 1 | Within package (ladder)
UG-13A-S13-A020 | UG-13A-S13-A030 | FF | 2 | Within package (ladder)
UG-13A-S13-A030 | UG-13A-S13-A040 | SS | 2 | Within package (ladder)
UG-13A-S13-A030 | UG-13A-S13-A040 | FF | 2 | Within package (ladder)
UG-13A-S13-A040 | UG-13A-S13-A050 | SS | 2 | Within package (ladder)
UG-13A-S13-A040 | UG-13A-S13-A050 | FF | 2 | Within package (ladder)
UG-13A-S13-A050 | UG-13A-S13-A060 | SS | 10 | Within package (ladder)
UG-13A-S13-A050 | UG-13A-S13-A060 | FF | 2 | Within package (ladder)
UG-13A-S13-A060 | UG-13A-S13-A070 | SS | 1 | Within package (ladder)
UG-13A-S13-A060 | UG-13A-S13-A070 | FF | 2 | Within package (ladder)
UG-13A-S13-A070 | UG-13A-S13-A080 | SS | 3 | Within package (ladder)
UG-13A-S13-A070 | UG-13A-S13-A080 | FF | 2 | Within package (ladder)
UG-13A-S14-A080 | UG-13A-S13-A080 | FS | 0 | Tie-in laid as closure
UG-13A-S13-A080 | UG-13A-S13-A090 | SS | 2 | Within package (ladder)
UG-13A-S13-A080 | UG-13A-S13-A090 | FF | 2 | Within package (ladder)
UG-13A-S13-A090 | UG-13A-S13-A100 | SS | 2 | Within package (ladder)
UG-13A-S13-A090 | UG-13A-S13-A100 | FF | 2 | Within package (ladder)
UG-27K-S01-A080 | UG-13A-S13-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13A-S13-A100 | UG-13A-S13-A110 | SS | 1 | Within package (ladder)
UG-13A-S13-A100 | UG-13A-S13-A110 | FF | 2 | Within package (ladder)
UG-27K-S01-A010 | UG-27K-S01-A020 | FS | 0 | Within package
UG-27K-S01-A020 | UG-27K-S01-A030 | SS | 1 | Within package (ladder)
UG-27K-S01-A020 | UG-27K-S01-A030 | FF | 2 | Within package (ladder)
UG-27K-S01-A030 | UG-27K-S01-A040 | SS | 3 | Within package (ladder)
UG-27K-S01-A030 | UG-27K-S01-A040 | FF | 2 | Within package (ladder)
UG-27K-S01-A040 | UG-27K-S01-A050 | SS | 2 | Within package (ladder)
UG-27K-S01-A040 | UG-27K-S01-A050 | FF | 2 | Within package (ladder)
UG-27K-S01-A050 | UG-27K-S01-A060 | SS | 10 | Within package (ladder)
UG-27K-S01-A050 | UG-27K-S01-A060 | FF | 2 | Within package (ladder)
UG-08-S07-A100 | UG-27K-S01-A060 | FS | 0 | Deeper line first
UG-13A-S13-A060 | UG-27K-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-27K-S01-A060 | UG-27K-S01-A070 | SS | 1 | Within package (ladder)
UG-27K-S01-A060 | UG-27K-S01-A070 | FF | 2 | Within package (ladder)
UG-27K-S01-A070 | UG-27K-S01-A080 | SS | 3 | Within package (ladder)
UG-27K-S01-A070 | UG-27K-S01-A080 | FF | 2 | Within package (ladder)
UG-27K-S01-A080 | UG-27K-S01-A090 | SS | 4 | Within package (ladder)
UG-27K-S01-A080 | UG-27K-S01-A090 | FF | 2 | Within package (ladder)
UG-27K-S01-A090 | UG-27K-S01-A100 | SS | 2 | Within package (ladder)
UG-27K-S01-A090 | UG-27K-S01-A100 | FF | 2 | Within package (ladder)
UG-13A-S13-A080 | UG-27K-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-27K-S01-A100 | UG-27K-S01-A110 | SS | 1 | Within package (ladder)
UG-27K-S01-A100 | UG-27K-S01-A110 | FF | 2 | Within package (ladder)
UG-09-S08-A010 | UG-09-S08-A020 | FS | 0 | Within package
UG-09-S07-A030 | UG-09-S08-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-09-S08-A020 | UG-09-S08-A030 | SS | 1 | Within package (ladder)
UG-09-S08-A020 | UG-09-S08-A030 | FF | 2 | Within package (ladder)
UG-09-S08-A030 | UG-09-S08-A040 | SS | 1 | Within package (ladder)
UG-09-S08-A030 | UG-09-S08-A040 | FF | 2 | Within package (ladder)
UG-09-S08-A040 | UG-09-S08-A050 | SS | 1 | Within package (ladder)
UG-09-S08-A040 | UG-09-S08-A050 | FF | 2 | Within package (ladder)
UG-09-S08-A050 | UG-09-S08-A060 | SS | 10 | Within package (ladder)
UG-09-S08-A050 | UG-09-S08-A060 | FF | 2 | Within package (ladder)
UG-09-S08-A060 | UG-09-S08-A070 | SS | 1 | Within package (ladder)
UG-09-S08-A060 | UG-09-S08-A070 | FF | 2 | Within package (ladder)
UG-09-S08-A070 | UG-09-S08-A080 | SS | 2 | Within package (ladder)
UG-09-S08-A070 | UG-09-S08-A080 | FF | 2 | Within package (ladder)
UG-09-S07-A080 | UG-09-S08-A080 | FS | 0 | Tie-in laid as closure
UG-09-S08-A080 | UG-09-S08-A090 | SS | 2 | Within package (ladder)
UG-09-S08-A080 | UG-09-S08-A090 | FF | 2 | Within package (ladder)
UG-09-S08-A090 | UG-09-S08-A100 | SS | 2 | Within package (ladder)
UG-09-S08-A090 | UG-09-S08-A100 | FF | 2 | Within package (ladder)
UG-09-S08-A100 | UG-09-S08-A110 | SS | 1 | Within package (ladder)
UG-09-S08-A100 | UG-09-S08-A110 | FF | 2 | Within package (ladder)
UG-13B-S01-A010 | UG-13B-S01-A020 | FS | 0 | Within package
UG-13B-S02-A030 | UG-13B-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-13B-S01-A020 | UG-13B-S01-A030 | SS | 1 | Within package (ladder)
UG-13B-S01-A020 | UG-13B-S01-A030 | FF | 2 | Within package (ladder)
UG-13B-S01-A030 | UG-13B-S01-A040 | SS | 2 | Within package (ladder)
UG-13B-S01-A030 | UG-13B-S01-A040 | FF | 2 | Within package (ladder)
UG-13B-S01-A040 | UG-13B-S01-A050 | SS | 2 | Within package (ladder)
UG-13B-S01-A040 | UG-13B-S01-A050 | FF | 2 | Within package (ladder)
UG-13B-S01-A050 | UG-13B-S01-A060 | SS | 10 | Within package (ladder)
UG-13B-S01-A050 | UG-13B-S01-A060 | FF | 2 | Within package (ladder)
UG-13B-S01-A060 | UG-13B-S01-A070 | SS | 1 | Within package (ladder)
UG-13B-S01-A060 | UG-13B-S01-A070 | FF | 2 | Within package (ladder)
UG-13B-S01-A070 | UG-13B-S01-A080 | SS | 3 | Within package (ladder)
UG-13B-S01-A070 | UG-13B-S01-A080 | FF | 2 | Within package (ladder)
UG-13B-S02-A080 | UG-13B-S01-A080 | FS | 0 | Tie-in laid as closure
UG-13B-S01-A080 | UG-13B-S01-A090 | SS | 2 | Within package (ladder)
UG-13B-S01-A080 | UG-13B-S01-A090 | FF | 2 | Within package (ladder)
UG-13B-S01-A090 | UG-13B-S01-A100 | SS | 2 | Within package (ladder)
UG-13B-S01-A090 | UG-13B-S01-A100 | FF | 2 | Within package (ladder)
UG-14E-S01-A080 | UG-13B-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13B-S01-A100 | UG-13B-S01-A110 | SS | 1 | Within package (ladder)
UG-13B-S01-A100 | UG-13B-S01-A110 | FF | 2 | Within package (ladder)
UG-14E-S01-A010 | UG-14E-S01-A020 | FS | 0 | Within package
UG-14E-S01-A020 | UG-14E-S01-A030 | SS | 1 | Within package (ladder)
UG-14E-S01-A020 | UG-14E-S01-A030 | FF | 2 | Within package (ladder)
UG-14E-S01-A030 | UG-14E-S01-A040 | SS | 3 | Within package (ladder)
UG-14E-S01-A030 | UG-14E-S01-A040 | FF | 0 | Within package (ladder)
UG-14E-S01-A040 | UG-14E-S01-A050 | SS | 0 | Within package (ladder)
UG-14E-S01-A040 | UG-14E-S01-A050 | FF | 2 | Within package (ladder)
UG-14E-S01-A050 | UG-14E-S01-A060 | SS | 10 | Within package (ladder)
UG-14E-S01-A050 | UG-14E-S01-A060 | FF | 2 | Within package (ladder)
UG-09-S08-A100 | UG-14E-S01-A060 | FS | 0 | Deeper line first
UG-13B-S01-A060 | UG-14E-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-14E-S01-A060 | UG-14E-S01-A070 | SS | 2 | Within package (ladder)
UG-14E-S01-A060 | UG-14E-S01-A070 | FF | 2 | Within package (ladder)
UG-14E-S01-A070 | UG-14E-S01-A080 | SS | 3 | Within package (ladder)
UG-14E-S01-A070 | UG-14E-S01-A080 | FF | 2 | Within package (ladder)
UG-14E-S01-A080 | UG-14E-S01-A090 | SS | 4 | Within package (ladder)
UG-14E-S01-A080 | UG-14E-S01-A090 | FF | 2 | Within package (ladder)
UG-14E-S01-A090 | UG-14E-S01-A100 | SS | 2 | Within package (ladder)
UG-14E-S01-A090 | UG-14E-S01-A100 | FF | 2 | Within package (ladder)
UG-13B-S01-A080 | UG-14E-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-14E-S01-A100 | UG-14E-S01-A110 | SS | 2 | Within package (ladder)
UG-14E-S01-A100 | UG-14E-S01-A110 | FF | 2 | Within package (ladder)
UG-11B-S08-A010 | UG-11B-S08-A020 | FS | 0 | Within package
UG-11B-S07-A030 | UG-11B-S08-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-11B-S08-A020 | UG-11B-S08-A030 | SS | 1 | Within package (ladder)
UG-11B-S08-A020 | UG-11B-S08-A030 | FF | 2 | Within package (ladder)
UG-11B-S08-A030 | UG-11B-S08-A040 | SS | 2 | Within package (ladder)
UG-11B-S08-A030 | UG-11B-S08-A040 | FF | 2 | Within package (ladder)
UG-11B-S08-A040 | UG-11B-S08-A050 | SS | 2 | Within package (ladder)
UG-11B-S08-A040 | UG-11B-S08-A050 | FF | 2 | Within package (ladder)
UG-11B-S08-A050 | UG-11B-S08-A060 | SS | 10 | Within package (ladder)
UG-11B-S08-A050 | UG-11B-S08-A060 | FF | 2 | Within package (ladder)
UG-11B-S08-A060 | UG-11B-S08-A070 | SS | 1 | Within package (ladder)
UG-11B-S08-A060 | UG-11B-S08-A070 | FF | 2 | Within package (ladder)
UG-11B-S08-A070 | UG-11B-S08-A080 | SS | 3 | Within package (ladder)
UG-11B-S08-A070 | UG-11B-S08-A080 | FF | 2 | Within package (ladder)
UG-11B-S07-A080 | UG-11B-S08-A080 | FS | 0 | Tie-in laid as closure
UG-11B-S08-A080 | UG-11B-S08-A090 | SS | 2 | Within package (ladder)
UG-11B-S08-A080 | UG-11B-S08-A090 | FF | 2 | Within package (ladder)
UG-11B-S08-A090 | UG-11B-S08-A100 | SS | 2 | Within package (ladder)
UG-11B-S08-A090 | UG-11B-S08-A100 | FF | 2 | Within package (ladder)
UG-16B-S01-A080 | UG-11B-S08-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11B-S08-A100 | UG-11B-S08-A110 | SS | 1 | Within package (ladder)
UG-11B-S08-A100 | UG-11B-S08-A110 | FF | 2 | Within package (ladder)
UG-16B-S01-A010 | UG-16B-S01-A020 | FS | 0 | Within package
UG-16B-S01-A020 | UG-16B-S01-A030 | SS | 1 | Within package (ladder)
UG-16B-S01-A020 | UG-16B-S01-A030 | FF | 2 | Within package (ladder)
UG-16B-S01-A030 | UG-16B-S01-A040 | SS | 3 | Within package (ladder)
UG-16B-S01-A030 | UG-16B-S01-A040 | FF | 2 | Within package (ladder)
UG-16B-S01-A040 | UG-16B-S01-A050 | SS | 2 | Within package (ladder)
UG-16B-S01-A040 | UG-16B-S01-A050 | FF | 2 | Within package (ladder)
UG-16B-S01-A050 | UG-16B-S01-A060 | SS | 10 | Within package (ladder)
UG-16B-S01-A050 | UG-16B-S01-A060 | FF | 2 | Within package (ladder)
UG-10-S05-A100 | UG-16B-S01-A060 | FS | 0 | Deeper line first
UG-11B-S08-A060 | UG-16B-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-16B-S01-A060 | UG-16B-S01-A070 | SS | 1 | Within package (ladder)
UG-16B-S01-A060 | UG-16B-S01-A070 | FF | 2 | Within package (ladder)
UG-16B-S01-A070 | UG-16B-S01-A080 | SS | 3 | Within package (ladder)
UG-16B-S01-A070 | UG-16B-S01-A080 | FF | 2 | Within package (ladder)
UG-16B-S01-A080 | UG-16B-S01-A090 | SS | 4 | Within package (ladder)
UG-16B-S01-A080 | UG-16B-S01-A090 | FF | 2 | Within package (ladder)
UG-16B-S01-A090 | UG-16B-S01-A100 | SS | 2 | Within package (ladder)
UG-16B-S01-A090 | UG-16B-S01-A100 | FF | 2 | Within package (ladder)
UG-11B-S08-A080 | UG-16B-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-16B-S01-A100 | UG-16B-S01-A110 | SS | 1 | Within package (ladder)
UG-16B-S01-A100 | UG-16B-S01-A110 | FF | 2 | Within package (ladder)
UG-14F-S01-A010 | UG-14F-S01-A020 | FS | 0 | Within package
UG-14F-S01-A020 | UG-14F-S01-A030 | SS | 1 | Within package (ladder)
UG-14F-S01-A020 | UG-14F-S01-A030 | FF | 2 | Within package (ladder)
UG-14F-S01-A030 | UG-14F-S01-A040 | SS | 3 | Within package (ladder)
UG-14F-S01-A030 | UG-14F-S01-A040 | FF | 2 | Within package (ladder)
UG-14F-S01-A040 | UG-14F-S01-A050 | SS | 2 | Within package (ladder)
UG-14F-S01-A040 | UG-14F-S01-A050 | FF | 2 | Within package (ladder)
UG-14F-S01-A050 | UG-14F-S01-A060 | SS | 10 | Within package (ladder)
UG-14F-S01-A050 | UG-14F-S01-A060 | FF | 2 | Within package (ladder)
UG-09-S08-A100 | UG-14F-S01-A060 | FS | 0 | Deeper line first
UG-13B-S09-A100 | UG-14F-S01-A060 | FS | 0 | Deeper line first
UG-13B-S10-A100 | UG-14F-S01-A060 | FS | 0 | Deeper line first
UG-14F-S01-A060 | UG-14F-S01-A070 | SS | 1 | Within package (ladder)
UG-14F-S01-A060 | UG-14F-S01-A070 | FF | 2 | Within package (ladder)
UG-14F-S01-A070 | UG-14F-S01-A080 | SS | 3 | Within package (ladder)
UG-14F-S01-A070 | UG-14F-S01-A080 | FF | 2 | Within package (ladder)
UG-14F-S01-A080 | UG-14F-S01-A090 | SS | 4 | Within package (ladder)
UG-14F-S01-A080 | UG-14F-S01-A090 | FF | 2 | Within package (ladder)
UG-14F-S01-A090 | UG-14F-S01-A100 | SS | 2 | Within package (ladder)
UG-14F-S01-A090 | UG-14F-S01-A100 | FF | 2 | Within package (ladder)
UG-14F-S01-A100 | UG-14F-S01-A110 | SS | 1 | Within package (ladder)
UG-14F-S01-A100 | UG-14F-S01-A110 | FF | 2 | Within package (ladder)
UG-27J-S02-A010 | UG-27J-S02-A020 | FS | 0 | Within package
UG-27J-S02-A020 | UG-27J-S02-A030 | SS | 1 | Within package (ladder)
UG-27J-S02-A020 | UG-27J-S02-A030 | FF | 2 | Within package (ladder)
UG-27J-S02-A030 | UG-27J-S02-A040 | SS | 2 | Within package (ladder)
UG-27J-S02-A030 | UG-27J-S02-A040 | FF | 0 | Within package (ladder)
UG-27J-S02-A040 | UG-27J-S02-A050 | SS | 0 | Within package (ladder)
UG-27J-S02-A040 | UG-27J-S02-A050 | FF | 2 | Within package (ladder)
UG-27J-S02-A050 | UG-27J-S02-A060 | SS | 10 | Within package (ladder)
UG-27J-S02-A050 | UG-27J-S02-A060 | FF | 2 | Within package (ladder)
UG-13A-S15-A100 | UG-27J-S02-A060 | FS | 0 | Deeper line first
UG-27J-S02-A060 | UG-27J-S02-A070 | SS | 1 | Within package (ladder)
UG-27J-S02-A060 | UG-27J-S02-A070 | FF | 2 | Within package (ladder)
UG-27J-S02-A070 | UG-27J-S02-A080 | SS | 2 | Within package (ladder)
UG-27J-S02-A070 | UG-27J-S02-A080 | FF | 2 | Within package (ladder)
UG-27J-S02-A080 | UG-27J-S02-A090 | SS | 2 | Within package (ladder)
UG-27J-S02-A080 | UG-27J-S02-A090 | FF | 2 | Within package (ladder)
UG-27J-S02-A090 | UG-27J-S02-A100 | SS | 2 | Within package (ladder)
UG-27J-S02-A090 | UG-27J-S02-A100 | FF | 2 | Within package (ladder)
UG-27J-S02-A100 | UG-27J-S02-A110 | SS | 1 | Within package (ladder)
UG-27J-S02-A100 | UG-27J-S02-A110 | FF | 2 | Within package (ladder)
UG-27J-S01-A010 | UG-27J-S01-A020 | FS | 0 | Within package
UG-27J-S01-A020 | UG-27J-S01-A030 | SS | 1 | Within package (ladder)
UG-27J-S01-A020 | UG-27J-S01-A030 | FF | 2 | Within package (ladder)
UG-27J-S01-A030 | UG-27J-S01-A040 | SS | 2 | Within package (ladder)
UG-27J-S01-A030 | UG-27J-S01-A040 | FF | 2 | Within package (ladder)
UG-27J-S01-A040 | UG-27J-S01-A050 | SS | 1 | Within package (ladder)
UG-27J-S01-A040 | UG-27J-S01-A050 | FF | 2 | Within package (ladder)
UG-27J-S01-A050 | UG-27J-S01-A060 | SS | 10 | Within package (ladder)
UG-27J-S01-A050 | UG-27J-S01-A060 | FF | 2 | Within package (ladder)
UG-13A-S06-A100 | UG-27J-S01-A060 | FS | 0 | Deeper line first
UG-13A-S07-A100 | UG-27J-S01-A060 | FS | 0 | Deeper line first
UG-27J-S01-A060 | UG-27J-S01-A070 | SS | 1 | Within package (ladder)
UG-27J-S01-A060 | UG-27J-S01-A070 | FF | 2 | Within package (ladder)
UG-27J-S01-A070 | UG-27J-S01-A080 | SS | 2 | Within package (ladder)
UG-27J-S01-A070 | UG-27J-S01-A080 | FF | 2 | Within package (ladder)
UG-27J-S01-A080 | UG-27J-S01-A090 | SS | 3 | Within package (ladder)
UG-27J-S01-A080 | UG-27J-S01-A090 | FF | 2 | Within package (ladder)
UG-27J-S01-A090 | UG-27J-S01-A100 | SS | 2 | Within package (ladder)
UG-27J-S01-A090 | UG-27J-S01-A100 | FF | 2 | Within package (ladder)
UG-27J-S01-A100 | UG-27J-S01-A110 | SS | 1 | Within package (ladder)
UG-27J-S01-A100 | UG-27J-S01-A110 | FF | 2 | Within package (ladder)
UG-27L-S01-A010 | UG-27L-S01-A020 | FS | 0 | Within package
UG-27L-S01-A020 | UG-27L-S01-A030 | SS | 1 | Within package (ladder)
UG-27L-S01-A020 | UG-27L-S01-A030 | FF | 2 | Within package (ladder)
UG-27L-S01-A030 | UG-27L-S01-A040 | SS | 3 | Within package (ladder)
UG-27L-S01-A030 | UG-27L-S01-A040 | FF | 0 | Within package (ladder)
UG-27L-S01-A040 | UG-27L-S01-A050 | SS | 0 | Within package (ladder)
UG-27L-S01-A040 | UG-27L-S01-A050 | FF | 2 | Within package (ladder)
UG-27L-S01-A050 | UG-27L-S01-A060 | SS | 10 | Within package (ladder)
UG-27L-S01-A050 | UG-27L-S01-A060 | FF | 2 | Within package (ladder)
UG-08-S07-A100 | UG-27L-S01-A060 | FS | 0 | Deeper line first
UG-13A-S01-A100 | UG-27L-S01-A060 | FS | 0 | Deeper line first
UG-13A-S02-A100 | UG-27L-S01-A060 | FS | 0 | Deeper line first
UG-27L-S01-A060 | UG-27L-S01-A070 | SS | 2 | Within package (ladder)
UG-27L-S01-A060 | UG-27L-S01-A070 | FF | 2 | Within package (ladder)
UG-27L-S01-A070 | UG-27L-S01-A080 | SS | 3 | Within package (ladder)
UG-27L-S01-A070 | UG-27L-S01-A080 | FF | 2 | Within package (ladder)
UG-27L-S01-A080 | UG-27L-S01-A090 | SS | 4 | Within package (ladder)
UG-27L-S01-A080 | UG-27L-S01-A090 | FF | 2 | Within package (ladder)
UG-27L-S01-A090 | UG-27L-S01-A100 | SS | 2 | Within package (ladder)
UG-27L-S01-A090 | UG-27L-S01-A100 | FF | 2 | Within package (ladder)
UG-27L-S01-A100 | UG-27L-S01-A110 | SS | 2 | Within package (ladder)
UG-27L-S01-A100 | UG-27L-S01-A110 | FF | 2 | Within package (ladder)
UG-15-S05-A010 | UG-15-S05-A020 | FS | 0 | Within package
UG-15-S05-A020 | UG-15-S05-A030 | SS | 1 | Within package (ladder)
UG-15-S05-A020 | UG-15-S05-A030 | FF | 2 | Within package (ladder)
UG-15-S05-A030 | UG-15-S05-A040 | SS | 2 | Within package (ladder)
UG-15-S05-A030 | UG-15-S05-A040 | FF | 2 | Within package (ladder)
UG-15-S05-A040 | UG-15-S05-A050 | SS | 1 | Within package (ladder)
UG-15-S05-A040 | UG-15-S05-A050 | FF | 2 | Within package (ladder)
UG-15-S05-A050 | UG-15-S05-A060 | SS | 10 | Within package (ladder)
UG-15-S05-A050 | UG-15-S05-A060 | FF | 2 | Within package (ladder)
UG-15-S05-A060 | UG-15-S05-A070 | SS | 1 | Within package (ladder)
UG-15-S05-A060 | UG-15-S05-A070 | FF | 2 | Within package (ladder)
UG-15-S05-A070 | UG-15-S05-A080 | SS | 2 | Within package (ladder)
UG-15-S05-A070 | UG-15-S05-A080 | FF | 2 | Within package (ladder)
UG-15-S05-A080 | UG-15-S05-A090 | SS | 1 | Within package (ladder)
UG-15-S05-A080 | UG-15-S05-A090 | FF | 2 | Within package (ladder)
UG-15-S05-A090 | UG-15-S05-A100 | SS | 2 | Within package (ladder)
UG-15-S05-A090 | UG-15-S05-A100 | FF | 2 | Within package (ladder)
UG-15A-S02-A080 | UG-15-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15-S05-A100 | UG-15-S05-A110 | SS | 1 | Within package (ladder)
UG-15-S05-A100 | UG-15-S05-A110 | FF | 2 | Within package (ladder)
UG-15-S04-A010 | UG-15-S04-A020 | FS | 0 | Within package
UG-15-S05-A030 | UG-15-S04-A020 | SS | 0 | Set-out one package ahead of piling
UG-15-S04-A020 | UG-15-S04-A030 | SS | 1 | Within package (ladder)
UG-15-S04-A020 | UG-15-S04-A030 | FF | 2 | Within package (ladder)
UG-15-S05-A030 | UG-15-S04-A030 | FS | 0 | Crew continuity, front F4
UG-15-S04-A030 | UG-15-S04-A040 | SS | 2 | Within package (ladder)
UG-15-S04-A030 | UG-15-S04-A040 | FF | 2 | Within package (ladder)
UG-15-S05-A040 | UG-15-S04-A040 | FS | 0 | Crew continuity, front F4
UG-15-S04-A040 | UG-15-S04-A050 | SS | 1 | Within package (ladder)
UG-15-S04-A040 | UG-15-S04-A050 | FF | 2 | Within package (ladder)
UG-15-S05-A060 | UG-15-S04-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-15-S04-A050 | UG-15-S04-A060 | SS | 10 | Within package (ladder)
UG-15-S04-A050 | UG-15-S04-A060 | FF | 2 | Within package (ladder)
UG-15-S05-A060 | UG-15-S04-A060 | FS | 0 | Crew continuity, front F4
UG-15-S04-A060 | UG-15-S04-A070 | SS | 1 | Within package (ladder)
UG-15-S04-A060 | UG-15-S04-A070 | FF | 2 | Within package (ladder)
UG-15-S05-A070 | UG-15-S04-A070 | FS | 0 | Crew continuity, front F4
UG-15-S04-A070 | UG-15-S04-A080 | SS | 2 | Within package (ladder)
UG-15-S04-A070 | UG-15-S04-A080 | FF | 2 | Within package (ladder)
UG-15-S05-A080 | UG-15-S04-A080 | FS | 0 | Crew continuity, front F4
UG-15-S04-A080 | UG-15-S04-A090 | SS | 1 | Within package (ladder)
UG-15-S04-A080 | UG-15-S04-A090 | FF | 2 | Within package (ladder)
UG-15-S04-A090 | UG-15-S04-A100 | SS | 2 | Within package (ladder)
UG-15-S04-A090 | UG-15-S04-A100 | FF | 2 | Within package (ladder)
UG-15-S05-A100 | UG-15-S04-A100 | FS | 0 | Crew continuity, front F4
UG-15A-S02-A080 | UG-15-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15-S04-A100 | UG-15-S04-A110 | SS | 1 | Within package (ladder)
UG-15-S04-A100 | UG-15-S04-A110 | FF | 2 | Within package (ladder)
UG-15A-S02-A010 | UG-15A-S02-A020 | FS | 0 | Within package
UG-15-S04-A030 | UG-15A-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-15A-S02-A020 | UG-15A-S02-A030 | SS | 1 | Within package (ladder)
UG-15A-S02-A020 | UG-15A-S02-A030 | FF | 2 | Within package (ladder)
UG-15-S04-A030 | UG-15A-S02-A030 | FS | 0 | Crew continuity, front F4
UG-15A-S02-A030 | UG-15A-S02-A040 | SS | 2 | Within package (ladder)
UG-15A-S02-A030 | UG-15A-S02-A040 | FF | 2 | Within package (ladder)
UG-15-S04-A040 | UG-15A-S02-A040 | FS | 0 | Crew continuity, front F4
UG-15A-S02-A040 | UG-15A-S02-A050 | SS | 1 | Within package (ladder)
UG-15A-S02-A040 | UG-15A-S02-A050 | FF | 2 | Within package (ladder)
UG-15-S04-A060 | UG-15A-S02-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-15A-S02-A050 | UG-15A-S02-A060 | SS | 10 | Within package (ladder)
UG-15A-S02-A050 | UG-15A-S02-A060 | FF | 2 | Within package (ladder)
UG-15-S04-A060 | UG-15A-S02-A060 | FS | 0 | Crew continuity, front F4
UG-15-S04-A060 | UG-15A-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-15-S05-A060 | UG-15A-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-15A-S02-A060 | UG-15A-S02-A070 | SS | 1 | Within package (ladder)
UG-15A-S02-A060 | UG-15A-S02-A070 | FF | 2 | Within package (ladder)
UG-15-S04-A070 | UG-15A-S02-A070 | FS | 0 | Crew continuity, front F4
UG-15A-S02-A070 | UG-15A-S02-A080 | SS | 2 | Within package (ladder)
UG-15A-S02-A070 | UG-15A-S02-A080 | FF | 2 | Within package (ladder)
UG-15-S04-A080 | UG-15A-S02-A080 | FS | 0 | Crew continuity, front F4
UG-15A-S02-A080 | UG-15A-S02-A090 | SS | 2 | Within package (ladder)
UG-15A-S02-A080 | UG-15A-S02-A090 | FF | 2 | Within package (ladder)
UG-15A-S02-A090 | UG-15A-S02-A100 | SS | 2 | Within package (ladder)
UG-15A-S02-A090 | UG-15A-S02-A100 | FF | 2 | Within package (ladder)
UG-15-S04-A100 | UG-15A-S02-A100 | FS | 0 | Crew continuity, front F4
UG-15-S04-A080 | UG-15A-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15-S05-A080 | UG-15A-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15A-S02-A100 | UG-15A-S02-A110 | SS | 1 | Within package (ladder)
UG-15A-S02-A100 | UG-15A-S02-A110 | FF | 2 | Within package (ladder)
UG-15-S06-A010 | UG-15-S06-A020 | FS | 0 | Within package
UG-15-S05-A030 | UG-15-S06-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-15-S06-A020 | UG-15-S06-A030 | SS | 1 | Within package (ladder)
UG-15-S06-A020 | UG-15-S06-A030 | FF | 2 | Within package (ladder)
UG-15-S06-A030 | UG-15-S06-A040 | SS | 2 | Within package (ladder)
UG-15-S06-A030 | UG-15-S06-A040 | FF | 2 | Within package (ladder)
UG-15-S06-A040 | UG-15-S06-A050 | SS | 1 | Within package (ladder)
UG-15-S06-A040 | UG-15-S06-A050 | FF | 2 | Within package (ladder)
UG-15-S06-A050 | UG-15-S06-A060 | SS | 10 | Within package (ladder)
UG-15-S06-A050 | UG-15-S06-A060 | FF | 2 | Within package (ladder)
UG-15-S06-A060 | UG-15-S06-A070 | SS | 1 | Within package (ladder)
UG-15-S06-A060 | UG-15-S06-A070 | FF | 2 | Within package (ladder)
UG-15-S06-A070 | UG-15-S06-A080 | SS | 2 | Within package (ladder)
UG-15-S06-A070 | UG-15-S06-A080 | FF | 2 | Within package (ladder)
UG-15-S05-A080 | UG-15-S06-A080 | FS | 0 | Tie-in laid as closure
UG-15-S06-A080 | UG-15-S06-A090 | SS | 2 | Within package (ladder)
UG-15-S06-A080 | UG-15-S06-A090 | FF | 2 | Within package (ladder)
UG-15-S06-A090 | UG-15-S06-A100 | SS | 2 | Within package (ladder)
UG-15-S06-A090 | UG-15-S06-A100 | FF | 2 | Within package (ladder)
UG-15-S06-A100 | UG-15-S06-A110 | SS | 1 | Within package (ladder)
UG-15-S06-A100 | UG-15-S06-A110 | FF | 2 | Within package (ladder)
UG-15-S03-A010 | UG-15-S03-A020 | FS | 0 | Within package
UG-15A-S02-A030 | UG-15-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-15-S03-A020 | UG-15-S03-A030 | SS | 1 | Within package (ladder)
UG-15-S03-A020 | UG-15-S03-A030 | FF | 2 | Within package (ladder)
UG-15A-S02-A030 | UG-15-S03-A030 | FS | 0 | Crew continuity, front F4
UG-15-S03-A030 | UG-15-S03-A040 | SS | 4 | Within package (ladder)
UG-15-S03-A030 | UG-15-S03-A040 | FF | 2 | Within package (ladder)
UG-15A-S02-A040 | UG-15-S03-A040 | FS | 0 | Crew continuity, front F4
UG-15-S03-A040 | UG-15-S03-A050 | SS | 2 | Within package (ladder)
UG-15-S03-A040 | UG-15-S03-A050 | FF | 2 | Within package (ladder)
UG-15A-S02-A060 | UG-15-S03-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-15-S03-A050 | UG-15-S03-A060 | SS | 10 | Within package (ladder)
UG-15-S03-A050 | UG-15-S03-A060 | FF | 2 | Within package (ladder)
UG-15A-S02-A060 | UG-15-S03-A060 | FS | 0 | Crew continuity, front F4
UG-15-S03-A060 | UG-15-S03-A070 | SS | 2 | Within package (ladder)
UG-15-S03-A060 | UG-15-S03-A070 | FF | 2 | Within package (ladder)
UG-15A-S02-A070 | UG-15-S03-A070 | FS | 0 | Crew continuity, front F4
UG-15-S03-A070 | UG-15-S03-A080 | SS | 3 | Within package (ladder)
UG-15-S03-A070 | UG-15-S03-A080 | FF | 2 | Within package (ladder)
UG-15A-S02-A080 | UG-15-S03-A080 | FS | 0 | Crew continuity, front F4
UG-15-S03-A080 | UG-15-S03-A090 | SS | 2 | Within package (ladder)
UG-15-S03-A080 | UG-15-S03-A090 | FF | 2 | Within package (ladder)
UG-15-S03-A090 | UG-15-S03-A100 | SS | 2 | Within package (ladder)
UG-15-S03-A090 | UG-15-S03-A100 | FF | 2 | Within package (ladder)
UG-15A-S02-A100 | UG-15-S03-A100 | FS | 0 | Crew continuity, front F4
UG-15-S03-A100 | UG-15-S03-A110 | SS | 2 | Within package (ladder)
UG-15-S03-A100 | UG-15-S03-A110 | FF | 2 | Within package (ladder)
UG-15-S02-A010 | UG-15-S02-A020 | FS | 0 | Within package
UG-15-S03-A030 | UG-15-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-15-S02-A020 | UG-15-S02-A030 | SS | 1 | Within package (ladder)
UG-15-S02-A020 | UG-15-S02-A030 | FF | 2 | Within package (ladder)
UG-15-S03-A030 | UG-15-S02-A030 | FS | 0 | Crew continuity, front F4
UG-15-S02-A030 | UG-15-S02-A040 | SS | 2 | Within package (ladder)
UG-15-S02-A030 | UG-15-S02-A040 | FF | 2 | Within package (ladder)
UG-15-S03-A040 | UG-15-S02-A040 | FS | 0 | Crew continuity, front F4
UG-15-S02-A040 | UG-15-S02-A050 | SS | 1 | Within package (ladder)
UG-15-S02-A040 | UG-15-S02-A050 | FF | 2 | Within package (ladder)
UG-15-S03-A060 | UG-15-S02-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-15-S02-A050 | UG-15-S02-A060 | SS | 10 | Within package (ladder)
UG-15-S02-A050 | UG-15-S02-A060 | FF | 2 | Within package (ladder)
UG-15-S03-A060 | UG-15-S02-A060 | FS | 0 | Crew continuity, front F4
UG-15-S02-A060 | UG-15-S02-A070 | SS | 1 | Within package (ladder)
UG-15-S02-A060 | UG-15-S02-A070 | FF | 2 | Within package (ladder)
UG-15-S03-A070 | UG-15-S02-A070 | FS | 0 | Crew continuity, front F4
UG-15-S02-A070 | UG-15-S02-A080 | SS | 2 | Within package (ladder)
UG-15-S02-A070 | UG-15-S02-A080 | FF | 2 | Within package (ladder)
UG-15-S03-A080 | UG-15-S02-A080 | FS | 0 | Crew continuity, front F4
UG-15-S02-A080 | UG-15-S02-A090 | SS | 1 | Within package (ladder)
UG-15-S02-A080 | UG-15-S02-A090 | FF | 2 | Within package (ladder)
UG-15-S02-A090 | UG-15-S02-A100 | SS | 2 | Within package (ladder)
UG-15-S02-A090 | UG-15-S02-A100 | FF | 2 | Within package (ladder)
UG-15-S03-A100 | UG-15-S02-A100 | FS | 0 | Crew continuity, front F4
UG-15-S02-A100 | UG-15-S02-A110 | SS | 1 | Within package (ladder)
UG-15-S02-A100 | UG-15-S02-A110 | FF | 2 | Within package (ladder)
UG-07-S02-A010 | UG-07-S02-A020 | FS | 0 | Within package
UG-15-S02-A030 | UG-07-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-07-S02-A020 | UG-07-S02-A030 | SS | 1 | Within package (ladder)
UG-07-S02-A020 | UG-07-S02-A030 | FF | 2 | Within package (ladder)
UG-15-S02-A030 | UG-07-S02-A030 | FS | 0 | Crew continuity, front F4
UG-07-S02-A030 | UG-07-S02-A040 | SS | 3 | Within package (ladder)
UG-07-S02-A030 | UG-07-S02-A040 | FF | 2 | Within package (ladder)
UG-15-S02-A040 | UG-07-S02-A040 | FS | 0 | Crew continuity, front F4
UG-07-S02-A040 | UG-07-S02-A050 | SS | 2 | Within package (ladder)
UG-07-S02-A040 | UG-07-S02-A050 | FF | 2 | Within package (ladder)
UG-15-S02-A060 | UG-07-S02-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-07-S02-A050 | UG-07-S02-A060 | SS | 10 | Within package (ladder)
UG-07-S02-A050 | UG-07-S02-A060 | FF | 2 | Within package (ladder)
UG-15-S02-A060 | UG-07-S02-A060 | FS | 0 | Crew continuity, front F4
UG-12-S05-A100 | UG-07-S02-A060 | FS | 0 | Deeper line first
UG-12-S06-A100 | UG-07-S02-A060 | FS | 0 | Deeper line first
UG-07-S02-A060 | UG-07-S02-A070 | SS | 2 | Within package (ladder)
UG-07-S02-A060 | UG-07-S02-A070 | FF | 2 | Within package (ladder)
UG-15-S02-A070 | UG-07-S02-A070 | FS | 0 | Crew continuity, front F4
UG-07-S02-A070 | UG-07-S02-A080 | SS | 3 | Within package (ladder)
UG-07-S02-A070 | UG-07-S02-A080 | FF | 2 | Within package (ladder)
UG-15-S02-A080 | UG-07-S02-A080 | FS | 0 | Crew continuity, front F4
UG-07-S02-A080 | UG-07-S02-A090 | SS | 2 | Within package (ladder)
UG-07-S02-A080 | UG-07-S02-A090 | FF | 2 | Within package (ladder)
UG-07-S02-A090 | UG-07-S02-A100 | SS | 2 | Within package (ladder)
UG-07-S02-A090 | UG-07-S02-A100 | FF | 2 | Within package (ladder)
UG-15-S02-A100 | UG-07-S02-A100 | FS | 0 | Crew continuity, front F4
UG-07A-S09-A080 | UG-07-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-07A-S12-A080 | UG-07-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-07-S02-A100 | UG-07-S02-A110 | SS | 1 | Within package (ladder)
UG-07-S02-A100 | UG-07-S02-A110 | FF | 2 | Within package (ladder)
UG-07A-S12-A010 | UG-07A-S12-A020 | FS | 0 | Within package
UG-07-S02-A030 | UG-07A-S12-A020 | SS | 0 | Set-out one package ahead of piling
UG-07A-S12-A020 | UG-07A-S12-A030 | SS | 1 | Within package (ladder)
UG-07A-S12-A020 | UG-07A-S12-A030 | FF | 2 | Within package (ladder)
UG-07-S02-A030 | UG-07A-S12-A030 | FS | 0 | Crew continuity, front F4
UG-07A-S12-A030 | UG-07A-S12-A040 | SS | 2 | Within package (ladder)
UG-07A-S12-A030 | UG-07A-S12-A040 | FF | 2 | Within package (ladder)
UG-07-S02-A040 | UG-07A-S12-A040 | FS | 0 | Crew continuity, front F4
UG-07A-S12-A040 | UG-07A-S12-A050 | SS | 2 | Within package (ladder)
UG-07A-S12-A040 | UG-07A-S12-A050 | FF | 2 | Within package (ladder)
UG-07-S02-A060 | UG-07A-S12-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-07A-S12-A050 | UG-07A-S12-A060 | SS | 10 | Within package (ladder)
UG-07A-S12-A050 | UG-07A-S12-A060 | FF | 2 | Within package (ladder)
UG-07-S02-A060 | UG-07A-S12-A060 | FS | 0 | Crew continuity, front F4
UG-12-S04-A100 | UG-07A-S12-A060 | FS | 0 | Deeper line first
UG-12-S05-A100 | UG-07A-S12-A060 | FS | 0 | Deeper line first
UG-12-S06-A100 | UG-07A-S12-A060 | FS | 0 | Deeper line first
UG-07-S02-A060 | UG-07A-S12-A060 | SS | 0 | Shared excavation / dewatering front
UG-07A-S12-A060 | UG-07A-S12-A070 | SS | 1 | Within package (ladder)
UG-07A-S12-A060 | UG-07A-S12-A070 | FF | 2 | Within package (ladder)
UG-07-S02-A070 | UG-07A-S12-A070 | FS | 0 | Crew continuity, front F4
UG-07A-S12-A070 | UG-07A-S12-A080 | SS | 3 | Within package (ladder)
UG-07A-S12-A070 | UG-07A-S12-A080 | FF | 2 | Within package (ladder)
UG-07-S02-A080 | UG-07A-S12-A080 | FS | 0 | Crew continuity, front F4
UG-07A-S12-A080 | UG-07A-S12-A090 | SS | 2 | Within package (ladder)
UG-07A-S12-A080 | UG-07A-S12-A090 | FF | 2 | Within package (ladder)
UG-07A-S12-A090 | UG-07A-S12-A100 | SS | 2 | Within package (ladder)
UG-07A-S12-A090 | UG-07A-S12-A100 | FF | 2 | Within package (ladder)
UG-07-S02-A100 | UG-07A-S12-A100 | FS | 0 | Crew continuity, front F4
UG-07-S01-A080 | UG-07A-S12-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-07-S02-A080 | UG-07A-S12-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-07A-S12-A100 | UG-07A-S12-A110 | SS | 1 | Within package (ladder)
UG-07A-S12-A100 | UG-07A-S12-A110 | FF | 2 | Within package (ladder)
UG-07-S01-A010 | UG-07-S01-A020 | FS | 0 | Within package
UG-07A-S12-A030 | UG-07-S01-A020 | SS | 0 | Set-out one package ahead of piling
UG-07-S01-A020 | UG-07-S01-A030 | SS | 1 | Within package (ladder)
UG-07-S01-A020 | UG-07-S01-A030 | FF | 2 | Within package (ladder)
UG-07A-S12-A030 | UG-07-S01-A030 | FS | 0 | Crew continuity, front F4
UG-07-S01-A030 | UG-07-S01-A040 | SS | 2 | Within package (ladder)
UG-07-S01-A030 | UG-07-S01-A040 | FF | 0 | Within package (ladder)
UG-07A-S12-A040 | UG-07-S01-A040 | FS | 0 | Crew continuity, front F4
UG-07-S01-A040 | UG-07-S01-A050 | SS | 0 | Within package (ladder)
UG-07-S01-A040 | UG-07-S01-A050 | FF | 2 | Within package (ladder)
UG-07A-S12-A060 | UG-07-S01-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-07-S01-A050 | UG-07-S01-A060 | SS | 10 | Within package (ladder)
UG-07-S01-A050 | UG-07-S01-A060 | FF | 2 | Within package (ladder)
UG-07A-S12-A060 | UG-07-S01-A060 | FS | 0 | Crew continuity, front F4
UG-12-S06-A100 | UG-07-S01-A060 | FS | 0 | Deeper line first
UG-07A-S12-A060 | UG-07-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-07-S01-A060 | UG-07-S01-A070 | SS | 1 | Within package (ladder)
UG-07-S01-A060 | UG-07-S01-A070 | FF | 2 | Within package (ladder)
UG-07A-S12-A070 | UG-07-S01-A070 | FS | 0 | Crew continuity, front F4
UG-07-S01-A070 | UG-07-S01-A080 | SS | 2 | Within package (ladder)
UG-07-S01-A070 | UG-07-S01-A080 | FF | 2 | Within package (ladder)
UG-07A-S12-A080 | UG-07-S01-A080 | FS | 0 | Crew continuity, front F4
UG-07-S01-A080 | UG-07-S01-A090 | SS | 2 | Within package (ladder)
UG-07-S01-A080 | UG-07-S01-A090 | FF | 2 | Within package (ladder)
UG-07-S01-A090 | UG-07-S01-A100 | SS | 2 | Within package (ladder)
UG-07-S01-A090 | UG-07-S01-A100 | FF | 2 | Within package (ladder)
UG-07A-S12-A100 | UG-07-S01-A100 | FS | 0 | Crew continuity, front F4
UG-07A-S05-A080 | UG-07-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-07A-S09-A080 | UG-07-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-07A-S12-A080 | UG-07-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-07-S01-A100 | UG-07-S01-A110 | SS | 1 | Within package (ladder)
UG-07-S01-A100 | UG-07-S01-A110 | FF | 2 | Within package (ladder)
UG-07A-S09-A010 | UG-07A-S09-A020 | FS | 0 | Within package
UG-07-S01-A030 | UG-07A-S09-A020 | SS | 0 | Set-out one package ahead of piling
UG-07A-S09-A020 | UG-07A-S09-A030 | SS | 1 | Within package (ladder)
UG-07A-S09-A020 | UG-07A-S09-A030 | FF | 2 | Within package (ladder)
UG-07-S01-A030 | UG-07A-S09-A030 | FS | 0 | Crew continuity, front F4
UG-07A-S09-A030 | UG-07A-S09-A040 | SS | 2 | Within package (ladder)
UG-07A-S09-A030 | UG-07A-S09-A040 | FF | 0 | Within package (ladder)
UG-07-S01-A040 | UG-07A-S09-A040 | FS | 0 | Crew continuity, front F4
UG-07A-S09-A040 | UG-07A-S09-A050 | SS | 0 | Within package (ladder)
UG-07A-S09-A040 | UG-07A-S09-A050 | FF | 2 | Within package (ladder)
UG-07-S01-A060 | UG-07A-S09-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-07A-S09-A050 | UG-07A-S09-A060 | SS | 10 | Within package (ladder)
UG-07A-S09-A050 | UG-07A-S09-A060 | FF | 2 | Within package (ladder)
UG-07-S01-A060 | UG-07A-S09-A060 | FS | 0 | Crew continuity, front F4
UG-07-S01-A060 | UG-07A-S09-A060 | SS | 0 | Shared excavation / dewatering front
UG-07-S02-A060 | UG-07A-S09-A060 | SS | 0 | Shared excavation / dewatering front
UG-07A-S09-A060 | UG-07A-S09-A070 | SS | 1 | Within package (ladder)
UG-07A-S09-A060 | UG-07A-S09-A070 | FF | 2 | Within package (ladder)
UG-07-S01-A070 | UG-07A-S09-A070 | FS | 0 | Crew continuity, front F4
UG-07A-S09-A070 | UG-07A-S09-A080 | SS | 2 | Within package (ladder)
UG-07A-S09-A070 | UG-07A-S09-A080 | FF | 2 | Within package (ladder)
UG-07-S01-A080 | UG-07A-S09-A080 | FS | 0 | Crew continuity, front F4
UG-07A-S09-A080 | UG-07A-S09-A090 | SS | 1 | Within package (ladder)
UG-07A-S09-A080 | UG-07A-S09-A090 | FF | 2 | Within package (ladder)
UG-07A-S09-A090 | UG-07A-S09-A100 | SS | 2 | Within package (ladder)
UG-07A-S09-A090 | UG-07A-S09-A100 | FF | 2 | Within package (ladder)
UG-07-S01-A100 | UG-07A-S09-A100 | FS | 0 | Crew continuity, front F4
UG-07-S01-A080 | UG-07A-S09-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-07-S02-A080 | UG-07A-S09-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-07A-S09-A100 | UG-07A-S09-A110 | SS | 1 | Within package (ladder)
UG-07A-S09-A100 | UG-07A-S09-A110 | FF | 2 | Within package (ladder)
UG-07A-S05-A010 | UG-07A-S05-A020 | FS | 0 | Within package
UG-07A-S09-A030 | UG-07A-S05-A020 | SS | 0 | Set-out one package ahead of piling
UG-07A-S05-A020 | UG-07A-S05-A030 | SS | 1 | Within package (ladder)
UG-07A-S05-A020 | UG-07A-S05-A030 | FF | 2 | Within package (ladder)
UG-07A-S09-A030 | UG-07A-S05-A030 | FS | 0 | Crew continuity, front F4
UG-07A-S05-A030 | UG-07A-S05-A040 | SS | 2 | Within package (ladder)
UG-07A-S05-A030 | UG-07A-S05-A040 | FF | 0 | Within package (ladder)
UG-07A-S09-A040 | UG-07A-S05-A040 | FS | 0 | Crew continuity, front F4
UG-07A-S05-A040 | UG-07A-S05-A050 | SS | 0 | Within package (ladder)
UG-07A-S05-A040 | UG-07A-S05-A050 | FF | 2 | Within package (ladder)
UG-07A-S09-A060 | UG-07A-S05-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-07A-S05-A050 | UG-07A-S05-A060 | SS | 10 | Within package (ladder)
UG-07A-S05-A050 | UG-07A-S05-A060 | FF | 2 | Within package (ladder)
UG-07A-S09-A060 | UG-07A-S05-A060 | FS | 0 | Crew continuity, front F4
UG-07-S01-A060 | UG-07A-S05-A060 | SS | 0 | Shared excavation / dewatering front
UG-07A-S05-A060 | UG-07A-S05-A070 | SS | 1 | Within package (ladder)
UG-07A-S05-A060 | UG-07A-S05-A070 | FF | 2 | Within package (ladder)
UG-07A-S09-A070 | UG-07A-S05-A070 | FS | 0 | Crew continuity, front F4
UG-07A-S05-A070 | UG-07A-S05-A080 | SS | 2 | Within package (ladder)
UG-07A-S05-A070 | UG-07A-S05-A080 | FF | 2 | Within package (ladder)
UG-07A-S09-A080 | UG-07A-S05-A080 | FS | 0 | Crew continuity, front F4
UG-07A-S05-A080 | UG-07A-S05-A090 | SS | 1 | Within package (ladder)
UG-07A-S05-A080 | UG-07A-S05-A090 | FF | 2 | Within package (ladder)
UG-07A-S05-A090 | UG-07A-S05-A100 | SS | 2 | Within package (ladder)
UG-07A-S05-A090 | UG-07A-S05-A100 | FF | 2 | Within package (ladder)
UG-07A-S09-A100 | UG-07A-S05-A100 | FS | 0 | Crew continuity, front F4
UG-07-S01-A080 | UG-07A-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-07A-S05-A100 | UG-07A-S05-A110 | SS | 1 | Within package (ladder)
UG-07A-S05-A100 | UG-07A-S05-A110 | FF | 2 | Within package (ladder)
UG-15A-S01-A010 | UG-15A-S01-A020 | FS | 0 | Within package
UG-15A-S02-A030 | UG-15A-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-15A-S01-A020 | UG-15A-S01-A030 | SS | 1 | Within package (ladder)
UG-15A-S01-A020 | UG-15A-S01-A030 | FF | 2 | Within package (ladder)
UG-15A-S01-A030 | UG-15A-S01-A040 | SS | 1 | Within package (ladder)
UG-15A-S01-A030 | UG-15A-S01-A040 | FF | 2 | Within package (ladder)
UG-15A-S01-A040 | UG-15A-S01-A050 | SS | 1 | Within package (ladder)
UG-15A-S01-A040 | UG-15A-S01-A050 | FF | 2 | Within package (ladder)
UG-15A-S01-A050 | UG-15A-S01-A060 | SS | 10 | Within package (ladder)
UG-15A-S01-A050 | UG-15A-S01-A060 | FF | 2 | Within package (ladder)
UG-15A-S01-A060 | UG-15A-S01-A070 | SS | 1 | Within package (ladder)
UG-15A-S01-A060 | UG-15A-S01-A070 | FF | 2 | Within package (ladder)
UG-15A-S01-A070 | UG-15A-S01-A080 | SS | 2 | Within package (ladder)
UG-15A-S01-A070 | UG-15A-S01-A080 | FF | 2 | Within package (ladder)
UG-15A-S02-A080 | UG-15A-S01-A080 | FS | 0 | Tie-in laid as closure
UG-15A-S01-A080 | UG-15A-S01-A090 | SS | 2 | Within package (ladder)
UG-15A-S01-A080 | UG-15A-S01-A090 | FF | 2 | Within package (ladder)
UG-15A-S01-A090 | UG-15A-S01-A100 | SS | 2 | Within package (ladder)
UG-15A-S01-A090 | UG-15A-S01-A100 | FF | 2 | Within package (ladder)
UG-15A-S01-A100 | UG-15A-S01-A110 | SS | 1 | Within package (ladder)
UG-15A-S01-A100 | UG-15A-S01-A110 | FF | 2 | Within package (ladder)
UG-15A-S03-A010 | UG-15A-S03-A020 | FS | 0 | Within package
UG-15A-S04-A030 | UG-15A-S03-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-15A-S03-A020 | UG-15A-S03-A030 | SS | 1 | Within package (ladder)
UG-15A-S03-A020 | UG-15A-S03-A030 | FF | 2 | Within package (ladder)
UG-15A-S03-A030 | UG-15A-S03-A040 | SS | 2 | Within package (ladder)
UG-15A-S03-A030 | UG-15A-S03-A040 | FF | 0 | Within package (ladder)
UG-15A-S03-A040 | UG-15A-S03-A050 | SS | 0 | Within package (ladder)
UG-15A-S03-A040 | UG-15A-S03-A050 | FF | 2 | Within package (ladder)
UG-15A-S03-A050 | UG-15A-S03-A060 | SS | 10 | Within package (ladder)
UG-15A-S03-A050 | UG-15A-S03-A060 | FF | 2 | Within package (ladder)
UG-11B-S05-A100 | UG-15A-S03-A060 | FS | 0 | Deeper line first
UG-11B-S06-A100 | UG-15A-S03-A060 | FS | 0 | Deeper line first
UG-17-S03-A100 | UG-15A-S03-A060 | FS | 0 | Deeper line first
UG-17-S04-A100 | UG-15A-S03-A060 | FS | 0 | Deeper line first
UG-15A-S03-A060 | UG-15A-S03-A070 | SS | 1 | Within package (ladder)
UG-15A-S03-A060 | UG-15A-S03-A070 | FF | 2 | Within package (ladder)
UG-15A-S03-A070 | UG-15A-S03-A080 | SS | 2 | Within package (ladder)
UG-15A-S03-A070 | UG-15A-S03-A080 | FF | 2 | Within package (ladder)
UG-15A-S04-A080 | UG-15A-S03-A080 | FS | 0 | Tie-in laid as closure
UG-15A-S03-A080 | UG-15A-S03-A090 | SS | 2 | Within package (ladder)
UG-15A-S03-A080 | UG-15A-S03-A090 | FF | 2 | Within package (ladder)
UG-15A-S03-A090 | UG-15A-S03-A100 | SS | 2 | Within package (ladder)
UG-15A-S03-A090 | UG-15A-S03-A100 | FF | 2 | Within package (ladder)
UG-15A-S03-A100 | UG-15A-S03-A110 | SS | 1 | Within package (ladder)
UG-15A-S03-A100 | UG-15A-S03-A110 | FF | 2 | Within package (ladder)
UG-15A-S07-A010 | UG-15A-S07-A020 | FS | 0 | Within package
UG-15A-S08-A030 | UG-15A-S07-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-15A-S07-A020 | UG-15A-S07-A030 | SS | 1 | Within package (ladder)
UG-15A-S07-A020 | UG-15A-S07-A030 | FF | 2 | Within package (ladder)
UG-15A-S07-A030 | UG-15A-S07-A040 | SS | 1 | Within package (ladder)
UG-15A-S07-A030 | UG-15A-S07-A040 | FF | 2 | Within package (ladder)
UG-15A-S07-A040 | UG-15A-S07-A050 | SS | 1 | Within package (ladder)
UG-15A-S07-A040 | UG-15A-S07-A050 | FF | 2 | Within package (ladder)
UG-15A-S07-A050 | UG-15A-S07-A060 | SS | 10 | Within package (ladder)
UG-15A-S07-A050 | UG-15A-S07-A060 | FF | 2 | Within package (ladder)
UG-15A-S07-A060 | UG-15A-S07-A070 | SS | 1 | Within package (ladder)
UG-15A-S07-A060 | UG-15A-S07-A070 | FF | 2 | Within package (ladder)
UG-15A-S07-A070 | UG-15A-S07-A080 | SS | 2 | Within package (ladder)
UG-15A-S07-A070 | UG-15A-S07-A080 | FF | 2 | Within package (ladder)
UG-15A-S08-A080 | UG-15A-S07-A080 | FS | 0 | Tie-in laid as closure
UG-15A-S07-A080 | UG-15A-S07-A090 | SS | 2 | Within package (ladder)
UG-15A-S07-A080 | UG-15A-S07-A090 | FF | 2 | Within package (ladder)
UG-15A-S07-A090 | UG-15A-S07-A100 | SS | 2 | Within package (ladder)
UG-15A-S07-A090 | UG-15A-S07-A100 | FF | 2 | Within package (ladder)
UG-15A-S07-A100 | UG-15A-S07-A110 | SS | 1 | Within package (ladder)
UG-15A-S07-A100 | UG-15A-S07-A110 | FF | 2 | Within package (ladder)
UG-07A-S03-A010 | UG-07A-S03-A020 | FS | 0 | Within package
UG-07A-S05-A030 | UG-07A-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-07A-S03-A020 | UG-07A-S03-A030 | SS | 1 | Within package (ladder)
UG-07A-S03-A020 | UG-07A-S03-A030 | FF | 2 | Within package (ladder)
UG-07A-S05-A030 | UG-07A-S03-A030 | FS | 0 | Crew continuity, front F4
UG-07A-S03-A030 | UG-07A-S03-A040 | SS | 1 | Within package (ladder)
UG-07A-S03-A030 | UG-07A-S03-A040 | FF | 0 | Within package (ladder)
UG-07A-S05-A040 | UG-07A-S03-A040 | FS | 0 | Crew continuity, front F4
UG-07A-S03-A040 | UG-07A-S03-A050 | SS | 0 | Within package (ladder)
UG-07A-S03-A040 | UG-07A-S03-A050 | FF | 2 | Within package (ladder)
UG-07A-S05-A060 | UG-07A-S03-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-07A-S03-A050 | UG-07A-S03-A060 | SS | 10 | Within package (ladder)
UG-07A-S03-A050 | UG-07A-S03-A060 | FF | 2 | Within package (ladder)
UG-07A-S05-A060 | UG-07A-S03-A060 | FS | 0 | Crew continuity, front F4
UG-07A-S03-A060 | UG-07A-S03-A070 | SS | 1 | Within package (ladder)
UG-07A-S03-A060 | UG-07A-S03-A070 | FF | 2 | Within package (ladder)
UG-07A-S05-A070 | UG-07A-S03-A070 | FS | 0 | Crew continuity, front F4
UG-07A-S03-A070 | UG-07A-S03-A080 | SS | 2 | Within package (ladder)
UG-07A-S03-A070 | UG-07A-S03-A080 | FF | 2 | Within package (ladder)
UG-07A-S05-A080 | UG-07A-S03-A080 | FS | 0 | Crew continuity, front F4
UG-07A-S03-A080 | UG-07A-S03-A090 | SS | 1 | Within package (ladder)
UG-07A-S03-A080 | UG-07A-S03-A090 | FF | 2 | Within package (ladder)
UG-07A-S03-A090 | UG-07A-S03-A100 | SS | 2 | Within package (ladder)
UG-07A-S03-A090 | UG-07A-S03-A100 | FF | 2 | Within package (ladder)
UG-07A-S05-A100 | UG-07A-S03-A100 | FS | 0 | Crew continuity, front F4
UG-07A-S03-A100 | UG-07A-S03-A110 | SS | 1 | Within package (ladder)
UG-07A-S03-A100 | UG-07A-S03-A110 | FF | 2 | Within package (ladder)
UG-07A-S02-A010 | UG-07A-S02-A020 | FS | 0 | Within package
UG-07A-S03-A030 | UG-07A-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-07A-S02-A020 | UG-07A-S02-A030 | SS | 1 | Within package (ladder)
UG-07A-S02-A020 | UG-07A-S02-A030 | FF | 2 | Within package (ladder)
UG-07A-S03-A030 | UG-07A-S02-A030 | FS | 0 | Crew continuity, front F4
UG-07A-S02-A030 | UG-07A-S02-A040 | SS | 7 | Within package (ladder)
UG-07A-S02-A030 | UG-07A-S02-A040 | FF | 2 | Within package (ladder)
UG-07A-S03-A040 | UG-07A-S02-A040 | FS | 0 | Crew continuity, front F4
UG-07A-S02-A040 | UG-07A-S02-A050 | SS | 3 | Within package (ladder)
UG-07A-S02-A040 | UG-07A-S02-A050 | FF | 2 | Within package (ladder)
UG-07A-S03-A060 | UG-07A-S02-A050 | FS | -13 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-07A-S02-A050 | UG-07A-S02-A060 | SS | 11 | Within package (ladder)
UG-07A-S02-A050 | UG-07A-S02-A060 | FF | 2 | Within package (ladder)
UG-07A-S03-A060 | UG-07A-S02-A060 | FS | 0 | Crew continuity, front F4
UG-07A-S02-A060 | UG-07A-S02-A070 | SS | 2 | Within package (ladder)
UG-07A-S02-A060 | UG-07A-S02-A070 | FF | 2 | Within package (ladder)
UG-07A-S03-A070 | UG-07A-S02-A070 | FS | 0 | Crew continuity, front F4
UG-07A-S02-A070 | UG-07A-S02-A080 | SS | 6 | Within package (ladder)
UG-07A-S02-A070 | UG-07A-S02-A080 | FF | 2 | Within package (ladder)
UG-07A-S03-A080 | UG-07A-S02-A080 | FS | 0 | Crew continuity, front F4
UG-07A-S02-A080 | UG-07A-S02-A090 | SS | 4 | Within package (ladder)
UG-07A-S02-A080 | UG-07A-S02-A090 | FF | 2 | Within package (ladder)
UG-07A-S02-A090 | UG-07A-S02-A100 | SS | 2 | Within package (ladder)
UG-07A-S02-A090 | UG-07A-S02-A100 | FF | 2 | Within package (ladder)
UG-07A-S03-A100 | UG-07A-S02-A100 | FS | 0 | Crew continuity, front F4
UG-07A-S02-A100 | UG-07A-S02-A110 | SS | 2 | Within package (ladder)
UG-07A-S02-A100 | UG-07A-S02-A110 | FF | 2 | Within package (ladder)
UG-07A-S01-A010 | UG-07A-S01-A020 | FS | 0 | Within package
UG-07A-S02-A030 | UG-07A-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-07A-S01-A020 | UG-07A-S01-A030 | SS | 1 | Within package (ladder)
UG-07A-S01-A020 | UG-07A-S01-A030 | FF | 2 | Within package (ladder)
UG-07A-S01-A030 | UG-07A-S01-A040 | SS | 2 | Within package (ladder)
UG-07A-S01-A030 | UG-07A-S01-A040 | FF | 0 | Within package (ladder)
UG-07A-S01-A040 | UG-07A-S01-A050 | SS | 0 | Within package (ladder)
UG-07A-S01-A040 | UG-07A-S01-A050 | FF | 2 | Within package (ladder)
UG-07A-S01-A050 | UG-07A-S01-A060 | SS | 10 | Within package (ladder)
UG-07A-S01-A050 | UG-07A-S01-A060 | FF | 2 | Within package (ladder)
UG-07A-S01-A060 | UG-07A-S01-A070 | SS | 1 | Within package (ladder)
UG-07A-S01-A060 | UG-07A-S01-A070 | FF | 2 | Within package (ladder)
UG-07A-S01-A070 | UG-07A-S01-A080 | SS | 2 | Within package (ladder)
UG-07A-S01-A070 | UG-07A-S01-A080 | FF | 2 | Within package (ladder)
UG-07A-S02-A080 | UG-07A-S01-A080 | FS | 0 | Tie-in laid as closure
UG-07A-S01-A080 | UG-07A-S01-A090 | SS | 2 | Within package (ladder)
UG-07A-S01-A080 | UG-07A-S01-A090 | FF | 2 | Within package (ladder)
UG-07A-S01-A090 | UG-07A-S01-A100 | SS | 2 | Within package (ladder)
UG-07A-S01-A090 | UG-07A-S01-A100 | FF | 2 | Within package (ladder)
UG-07A-S01-A100 | UG-07A-S01-A110 | SS | 1 | Within package (ladder)
UG-07A-S01-A100 | UG-07A-S01-A110 | FF | 2 | Within package (ladder)
UG-07A-S07-A010 | UG-07A-S07-A020 | FS | 0 | Within package
UG-07A-S02-A030 | UG-07A-S07-A020 | SS | 0 | Set-out one package ahead of piling
UG-07A-S07-A020 | UG-07A-S07-A030 | SS | 1 | Within package (ladder)
UG-07A-S07-A020 | UG-07A-S07-A030 | FF | 2 | Within package (ladder)
UG-07A-S02-A030 | UG-07A-S07-A030 | FS | 0 | Crew continuity, front F4
UG-07A-S07-A030 | UG-07A-S07-A040 | SS | 2 | Within package (ladder)
UG-07A-S07-A030 | UG-07A-S07-A040 | FF | 0 | Within package (ladder)
UG-07A-S02-A040 | UG-07A-S07-A040 | FS | 0 | Crew continuity, front F4
UG-07A-S07-A040 | UG-07A-S07-A050 | SS | 0 | Within package (ladder)
UG-07A-S07-A040 | UG-07A-S07-A050 | FF | 2 | Within package (ladder)
UG-07A-S02-A060 | UG-07A-S07-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-07A-S07-A050 | UG-07A-S07-A060 | SS | 10 | Within package (ladder)
UG-07A-S07-A050 | UG-07A-S07-A060 | FF | 2 | Within package (ladder)
UG-07A-S02-A060 | UG-07A-S07-A060 | FS | 0 | Crew continuity, front F4
UG-07A-S07-A060 | UG-07A-S07-A070 | SS | 1 | Within package (ladder)
UG-07A-S07-A060 | UG-07A-S07-A070 | FF | 2 | Within package (ladder)
UG-07A-S02-A070 | UG-07A-S07-A070 | FS | 0 | Crew continuity, front F4
UG-07A-S07-A070 | UG-07A-S07-A080 | SS | 2 | Within package (ladder)
UG-07A-S07-A070 | UG-07A-S07-A080 | FF | 2 | Within package (ladder)
UG-07A-S02-A080 | UG-07A-S07-A080 | FS | 0 | Crew continuity, front F4
UG-07A-S07-A080 | UG-07A-S07-A090 | SS | 1 | Within package (ladder)
UG-07A-S07-A080 | UG-07A-S07-A090 | FF | 2 | Within package (ladder)
UG-07A-S07-A090 | UG-07A-S07-A100 | SS | 2 | Within package (ladder)
UG-07A-S07-A090 | UG-07A-S07-A100 | FF | 2 | Within package (ladder)
UG-07A-S02-A100 | UG-07A-S07-A100 | FS | 0 | Crew continuity, front F4
UG-07A-S07-A100 | UG-07A-S07-A110 | SS | 1 | Within package (ladder)
UG-07A-S07-A100 | UG-07A-S07-A110 | FF | 2 | Within package (ladder)
UG-07A-S08-A010 | UG-07A-S08-A020 | FS | 0 | Within package
UG-07A-S09-A030 | UG-07A-S08-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-07A-S08-A020 | UG-07A-S08-A030 | SS | 1 | Within package (ladder)
UG-07A-S08-A020 | UG-07A-S08-A030 | FF | 2 | Within package (ladder)
UG-07A-S08-A030 | UG-07A-S08-A040 | SS | 1 | Within package (ladder)
UG-07A-S08-A030 | UG-07A-S08-A040 | FF | 0 | Within package (ladder)
UG-07A-S08-A040 | UG-07A-S08-A050 | SS | 0 | Within package (ladder)
UG-07A-S08-A040 | UG-07A-S08-A050 | FF | 2 | Within package (ladder)
UG-07A-S08-A050 | UG-07A-S08-A060 | SS | 10 | Within package (ladder)
UG-07A-S08-A050 | UG-07A-S08-A060 | FF | 2 | Within package (ladder)
UG-07A-S08-A060 | UG-07A-S08-A070 | SS | 1 | Within package (ladder)
UG-07A-S08-A060 | UG-07A-S08-A070 | FF | 2 | Within package (ladder)
UG-07A-S08-A070 | UG-07A-S08-A080 | SS | 2 | Within package (ladder)
UG-07A-S08-A070 | UG-07A-S08-A080 | FF | 2 | Within package (ladder)
UG-07A-S09-A080 | UG-07A-S08-A080 | FS | 0 | Tie-in laid as closure
UG-07A-S08-A080 | UG-07A-S08-A090 | SS | 2 | Within package (ladder)
UG-07A-S08-A080 | UG-07A-S08-A090 | FF | 2 | Within package (ladder)
UG-07A-S08-A090 | UG-07A-S08-A100 | SS | 2 | Within package (ladder)
UG-07A-S08-A090 | UG-07A-S08-A100 | FF | 2 | Within package (ladder)
UG-07A-S08-A100 | UG-07A-S08-A110 | SS | 1 | Within package (ladder)
UG-07A-S08-A100 | UG-07A-S08-A110 | FF | 2 | Within package (ladder)
UG-07A-S10-A010 | UG-07A-S10-A020 | FS | 0 | Within package
UG-07A-S11-A030 | UG-07A-S10-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-07A-S10-A020 | UG-07A-S10-A030 | SS | 1 | Within package (ladder)
UG-07A-S10-A020 | UG-07A-S10-A030 | FF | 2 | Within package (ladder)
UG-07A-S10-A030 | UG-07A-S10-A040 | SS | 1 | Within package (ladder)
UG-07A-S10-A030 | UG-07A-S10-A040 | FF | 0 | Within package (ladder)
UG-07A-S10-A040 | UG-07A-S10-A050 | SS | 0 | Within package (ladder)
UG-07A-S10-A040 | UG-07A-S10-A050 | FF | 2 | Within package (ladder)
UG-07A-S10-A050 | UG-07A-S10-A060 | SS | 10 | Within package (ladder)
UG-07A-S10-A050 | UG-07A-S10-A060 | FF | 2 | Within package (ladder)
UG-12-S04-A100 | UG-07A-S10-A060 | FS | 0 | Deeper line first
UG-13B-S06-A100 | UG-07A-S10-A060 | FS | 0 | Deeper line first
UG-13B-S07-A100 | UG-07A-S10-A060 | FS | 0 | Deeper line first
UG-07A-S10-A060 | UG-07A-S10-A070 | SS | 1 | Within package (ladder)
UG-07A-S10-A060 | UG-07A-S10-A070 | FF | 2 | Within package (ladder)
UG-07A-S10-A070 | UG-07A-S10-A080 | SS | 2 | Within package (ladder)
UG-07A-S10-A070 | UG-07A-S10-A080 | FF | 2 | Within package (ladder)
UG-07A-S11-A080 | UG-07A-S10-A080 | FS | 0 | Tie-in laid as closure
UG-07A-S10-A080 | UG-07A-S10-A090 | SS | 2 | Within package (ladder)
UG-07A-S10-A080 | UG-07A-S10-A090 | FF | 2 | Within package (ladder)
UG-07A-S10-A090 | UG-07A-S10-A100 | SS | 2 | Within package (ladder)
UG-07A-S10-A090 | UG-07A-S10-A100 | FF | 2 | Within package (ladder)
UG-07A-S10-A100 | UG-07A-S10-A110 | SS | 1 | Within package (ladder)
UG-07A-S10-A100 | UG-07A-S10-A110 | FF | 2 | Within package (ladder)
UG-07A-S06-A010 | UG-07A-S06-A020 | FS | 0 | Within package
UG-07A-S07-A030 | UG-07A-S06-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-07A-S06-A020 | UG-07A-S06-A030 | SS | 1 | Within package (ladder)
UG-07A-S06-A020 | UG-07A-S06-A030 | FF | 2 | Within package (ladder)
UG-07A-S06-A030 | UG-07A-S06-A040 | SS | 1 | Within package (ladder)
UG-07A-S06-A030 | UG-07A-S06-A040 | FF | 0 | Within package (ladder)
UG-07A-S06-A040 | UG-07A-S06-A050 | SS | 0 | Within package (ladder)
UG-07A-S06-A040 | UG-07A-S06-A050 | FF | 2 | Within package (ladder)
UG-07A-S06-A050 | UG-07A-S06-A060 | SS | 10 | Within package (ladder)
UG-07A-S06-A050 | UG-07A-S06-A060 | FF | 2 | Within package (ladder)
UG-11A-S02-A100 | UG-07A-S06-A060 | FS | 0 | Deeper line first
UG-07A-S06-A060 | UG-07A-S06-A070 | SS | 1 | Within package (ladder)
UG-07A-S06-A060 | UG-07A-S06-A070 | FF | 2 | Within package (ladder)
UG-07A-S06-A070 | UG-07A-S06-A080 | SS | 2 | Within package (ladder)
UG-07A-S06-A070 | UG-07A-S06-A080 | FF | 2 | Within package (ladder)
UG-07A-S07-A080 | UG-07A-S06-A080 | FS | 0 | Tie-in laid as closure
UG-07A-S06-A080 | UG-07A-S06-A090 | SS | 2 | Within package (ladder)
UG-07A-S06-A080 | UG-07A-S06-A090 | FF | 2 | Within package (ladder)
UG-07A-S06-A090 | UG-07A-S06-A100 | SS | 2 | Within package (ladder)
UG-07A-S06-A090 | UG-07A-S06-A100 | FF | 2 | Within package (ladder)
UG-07A-S06-A100 | UG-07A-S06-A110 | SS | 1 | Within package (ladder)
UG-07A-S06-A100 | UG-07A-S06-A110 | FF | 2 | Within package (ladder)
UG-07A-S04-A010 | UG-07A-S04-A020 | FS | 0 | Within package
UG-07A-S07-A030 | UG-07A-S04-A020 | SS | 0 | Set-out one package ahead of piling
UG-07A-S04-A020 | UG-07A-S04-A030 | SS | 1 | Within package (ladder)
UG-07A-S04-A020 | UG-07A-S04-A030 | FF | 2 | Within package (ladder)
UG-07A-S07-A030 | UG-07A-S04-A030 | FS | 0 | Crew continuity, front F4
UG-07A-S04-A030 | UG-07A-S04-A040 | SS | 4 | Within package (ladder)
UG-07A-S04-A030 | UG-07A-S04-A040 | FF | 2 | Within package (ladder)
UG-07A-S07-A040 | UG-07A-S04-A040 | FS | 0 | Crew continuity, front F4
UG-07A-S04-A040 | UG-07A-S04-A050 | SS | 2 | Within package (ladder)
UG-07A-S04-A040 | UG-07A-S04-A050 | FF | 2 | Within package (ladder)
UG-07A-S07-A060 | UG-07A-S04-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-07A-S04-A050 | UG-07A-S04-A060 | SS | 10 | Within package (ladder)
UG-07A-S04-A050 | UG-07A-S04-A060 | FF | 2 | Within package (ladder)
UG-07A-S07-A060 | UG-07A-S04-A060 | FS | 0 | Crew continuity, front F4
UG-11A-S03-A100 | UG-07A-S04-A060 | FS | 0 | Deeper line first
UG-11A-S04-A100 | UG-07A-S04-A060 | FS | 0 | Deeper line first
UG-11A-S05-A100 | UG-07A-S04-A060 | FS | 0 | Deeper line first
UG-11A-S07-A100 | UG-07A-S04-A060 | FS | 0 | Deeper line first
UG-07A-S04-A060 | UG-07A-S04-A070 | SS | 2 | Within package (ladder)
UG-07A-S04-A060 | UG-07A-S04-A070 | FF | 2 | Within package (ladder)
UG-07A-S07-A070 | UG-07A-S04-A070 | FS | 0 | Crew continuity, front F4
UG-07A-S04-A070 | UG-07A-S04-A080 | SS | 4 | Within package (ladder)
UG-07A-S04-A070 | UG-07A-S04-A080 | FF | 2 | Within package (ladder)
UG-07A-S07-A080 | UG-07A-S04-A080 | FS | 0 | Crew continuity, front F4
UG-07A-S04-A080 | UG-07A-S04-A090 | SS | 2 | Within package (ladder)
UG-07A-S04-A080 | UG-07A-S04-A090 | FF | 2 | Within package (ladder)
UG-07A-S04-A090 | UG-07A-S04-A100 | SS | 2 | Within package (ladder)
UG-07A-S04-A090 | UG-07A-S04-A100 | FF | 2 | Within package (ladder)
UG-07A-S07-A100 | UG-07A-S04-A100 | FS | 0 | Crew continuity, front F4
UG-07A-S04-A100 | UG-07A-S04-A110 | SS | 1 | Within package (ladder)
UG-07A-S04-A100 | UG-07A-S04-A110 | FF | 2 | Within package (ladder)
UG-12-S07-A010 | UG-12-S07-A020 | FS | 0 | Within package
UG-12-S07-A020 | UG-12-S07-A030 | SS | 1 | Within package (ladder)
UG-12-S07-A020 | UG-12-S07-A030 | FF | 2 | Within package (ladder)
UG-12-S07-A030 | UG-12-S07-A040 | SS | 2 | Within package (ladder)
UG-12-S07-A030 | UG-12-S07-A040 | FF | 2 | Within package (ladder)
UG-12-S07-A040 | UG-12-S07-A050 | SS | 1 | Within package (ladder)
UG-12-S07-A040 | UG-12-S07-A050 | FF | 2 | Within package (ladder)
UG-12-S07-A050 | UG-12-S07-A060 | SS | 10 | Within package (ladder)
UG-12-S07-A050 | UG-12-S07-A060 | FF | 2 | Within package (ladder)
UG-11-S06-A100 | UG-12-S07-A060 | FS | 0 | Deeper line first
UG-12-S07-A060 | UG-12-S07-A070 | SS | 1 | Within package (ladder)
UG-12-S07-A060 | UG-12-S07-A070 | FF | 2 | Within package (ladder)
UG-12-S07-A070 | UG-12-S07-A080 | SS | 2 | Within package (ladder)
UG-12-S07-A070 | UG-12-S07-A080 | FF | 2 | Within package (ladder)
UG-12-S07-A080 | UG-12-S07-A090 | SS | 1 | Within package (ladder)
UG-12-S07-A080 | UG-12-S07-A090 | FF | 2 | Within package (ladder)
UG-12-S07-A090 | UG-12-S07-A100 | SS | 2 | Within package (ladder)
UG-12-S07-A090 | UG-12-S07-A100 | FF | 2 | Within package (ladder)
UG-07-S03-A080 | UG-12-S07-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-07-S04-A080 | UG-12-S07-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11-S01-A080 | UG-12-S07-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12-S07-A100 | UG-12-S07-A110 | SS | 1 | Within package (ladder)
UG-12-S07-A100 | UG-12-S07-A110 | FF | 2 | Within package (ladder)
UG-12-S08-A010 | UG-12-S08-A020 | FS | 0 | Within package
UG-12-S07-A030 | UG-12-S08-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-12-S08-A020 | UG-12-S08-A030 | SS | 1 | Within package (ladder)
UG-12-S08-A020 | UG-12-S08-A030 | FF | 2 | Within package (ladder)
UG-12-S08-A030 | UG-12-S08-A040 | SS | 1 | Within package (ladder)
UG-12-S08-A030 | UG-12-S08-A040 | FF | 2 | Within package (ladder)
UG-12-S08-A040 | UG-12-S08-A050 | SS | 1 | Within package (ladder)
UG-12-S08-A040 | UG-12-S08-A050 | FF | 2 | Within package (ladder)
UG-12-S08-A050 | UG-12-S08-A060 | SS | 10 | Within package (ladder)
UG-12-S08-A050 | UG-12-S08-A060 | FF | 2 | Within package (ladder)
UG-11-S06-A100 | UG-12-S08-A060 | FS | 0 | Deeper line first
UG-12-S08-A060 | UG-12-S08-A070 | SS | 1 | Within package (ladder)
UG-12-S08-A060 | UG-12-S08-A070 | FF | 2 | Within package (ladder)
UG-12-S08-A070 | UG-12-S08-A080 | SS | 2 | Within package (ladder)
UG-12-S08-A070 | UG-12-S08-A080 | FF | 2 | Within package (ladder)
UG-12-S07-A080 | UG-12-S08-A080 | FS | 0 | Tie-in laid as closure
UG-12-S08-A080 | UG-12-S08-A090 | SS | 2 | Within package (ladder)
UG-12-S08-A080 | UG-12-S08-A090 | FF | 2 | Within package (ladder)
UG-12-S08-A090 | UG-12-S08-A100 | SS | 2 | Within package (ladder)
UG-12-S08-A090 | UG-12-S08-A100 | FF | 2 | Within package (ladder)
UG-07-S03-A080 | UG-12-S08-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-07-S04-A080 | UG-12-S08-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11-S01-A080 | UG-12-S08-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12-S08-A100 | UG-12-S08-A110 | SS | 1 | Within package (ladder)
UG-12-S08-A100 | UG-12-S08-A110 | FF | 2 | Within package (ladder)
UG-11B-S14-A010 | UG-11B-S14-A020 | FS | 0 | Within package
UG-12-S07-A030 | UG-11B-S14-A020 | SS | 0 | Set-out one package ahead of piling
UG-11B-S14-A020 | UG-11B-S14-A030 | SS | 1 | Within package (ladder)
UG-11B-S14-A020 | UG-11B-S14-A030 | FF | 2 | Within package (ladder)
UG-12-S07-A030 | UG-11B-S14-A030 | FS | 0 | Crew continuity, front F5
UG-11B-S14-A030 | UG-11B-S14-A040 | SS | 2 | Within package (ladder)
UG-11B-S14-A030 | UG-11B-S14-A040 | FF | 2 | Within package (ladder)
UG-12-S07-A040 | UG-11B-S14-A040 | FS | 0 | Crew continuity, front F5
UG-11B-S14-A040 | UG-11B-S14-A050 | SS | 1 | Within package (ladder)
UG-11B-S14-A040 | UG-11B-S14-A050 | FF | 2 | Within package (ladder)
UG-12-S07-A060 | UG-11B-S14-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11B-S14-A050 | UG-11B-S14-A060 | SS | 10 | Within package (ladder)
UG-11B-S14-A050 | UG-11B-S14-A060 | FF | 2 | Within package (ladder)
UG-12-S07-A060 | UG-11B-S14-A060 | FS | 0 | Crew continuity, front F5
UG-11B-S14-A060 | UG-11B-S14-A070 | SS | 1 | Within package (ladder)
UG-11B-S14-A060 | UG-11B-S14-A070 | FF | 2 | Within package (ladder)
UG-12-S07-A070 | UG-11B-S14-A070 | FS | 0 | Crew continuity, front F5
UG-11B-S14-A070 | UG-11B-S14-A080 | SS | 2 | Within package (ladder)
UG-11B-S14-A070 | UG-11B-S14-A080 | FF | 2 | Within package (ladder)
UG-12-S07-A080 | UG-11B-S14-A080 | FS | 0 | Crew continuity, front F5
UG-11B-S14-A080 | UG-11B-S14-A090 | SS | 2 | Within package (ladder)
UG-11B-S14-A080 | UG-11B-S14-A090 | FF | 2 | Within package (ladder)
UG-11B-S14-A090 | UG-11B-S14-A100 | SS | 2 | Within package (ladder)
UG-11B-S14-A090 | UG-11B-S14-A100 | FF | 2 | Within package (ladder)
UG-12-S07-A100 | UG-11B-S14-A100 | FS | 0 | Crew continuity, front F5
UG-11-S01-A080 | UG-11B-S14-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11B-S14-A100 | UG-11B-S14-A110 | SS | 1 | Within package (ladder)
UG-11B-S14-A100 | UG-11B-S14-A110 | FF | 2 | Within package (ladder)
UG-12-S06-A010 | UG-12-S06-A020 | FS | 0 | Within package
UG-11B-S14-A030 | UG-12-S06-A020 | SS | 0 | Set-out one package ahead of piling
UG-12-S06-A020 | UG-12-S06-A030 | SS | 1 | Within package (ladder)
UG-12-S06-A020 | UG-12-S06-A030 | FF | 2 | Within package (ladder)
UG-11B-S14-A030 | UG-12-S06-A030 | FS | 0 | Crew continuity, front F5
UG-12-S06-A030 | UG-12-S06-A040 | SS | 3 | Within package (ladder)
UG-12-S06-A030 | UG-12-S06-A040 | FF | 2 | Within package (ladder)
UG-11B-S14-A040 | UG-12-S06-A040 | FS | 0 | Crew continuity, front F5
UG-12-S06-A040 | UG-12-S06-A050 | SS | 2 | Within package (ladder)
UG-12-S06-A040 | UG-12-S06-A050 | FF | 2 | Within package (ladder)
UG-11B-S14-A060 | UG-12-S06-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-12-S06-A050 | UG-12-S06-A060 | SS | 10 | Within package (ladder)
UG-12-S06-A050 | UG-12-S06-A060 | FF | 2 | Within package (ladder)
UG-11B-S14-A060 | UG-12-S06-A060 | FS | 0 | Crew continuity, front F5
UG-12-S06-A060 | UG-12-S06-A070 | SS | 2 | Within package (ladder)
UG-12-S06-A060 | UG-12-S06-A070 | FF | 2 | Within package (ladder)
UG-11B-S14-A070 | UG-12-S06-A070 | FS | 0 | Crew continuity, front F5
UG-12-S06-A070 | UG-12-S06-A080 | SS | 3 | Within package (ladder)
UG-12-S06-A070 | UG-12-S06-A080 | FF | 2 | Within package (ladder)
UG-11B-S14-A080 | UG-12-S06-A080 | FS | 0 | Crew continuity, front F5
UG-12-S06-A080 | UG-12-S06-A090 | SS | 2 | Within package (ladder)
UG-12-S06-A080 | UG-12-S06-A090 | FF | 2 | Within package (ladder)
UG-12-S06-A090 | UG-12-S06-A100 | SS | 2 | Within package (ladder)
UG-12-S06-A090 | UG-12-S06-A100 | FF | 2 | Within package (ladder)
UG-11B-S14-A100 | UG-12-S06-A100 | FS | 0 | Crew continuity, front F5
UG-07-S03-A080 | UG-12-S06-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12-S06-A100 | UG-12-S06-A110 | SS | 1 | Within package (ladder)
UG-12-S06-A100 | UG-12-S06-A110 | FF | 2 | Within package (ladder)
UG-07-S03-A010 | UG-07-S03-A020 | FS | 0 | Within package
UG-12-S06-A030 | UG-07-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-07-S03-A020 | UG-07-S03-A030 | SS | 1 | Within package (ladder)
UG-07-S03-A020 | UG-07-S03-A030 | FF | 2 | Within package (ladder)
UG-12-S06-A030 | UG-07-S03-A030 | FS | 0 | Crew continuity, front F5
UG-07-S03-A030 | UG-07-S03-A040 | SS | 2 | Within package (ladder)
UG-07-S03-A030 | UG-07-S03-A040 | FF | 2 | Within package (ladder)
UG-12-S06-A040 | UG-07-S03-A040 | FS | 0 | Crew continuity, front F5
UG-07-S03-A040 | UG-07-S03-A050 | SS | 2 | Within package (ladder)
UG-07-S03-A040 | UG-07-S03-A050 | FF | 2 | Within package (ladder)
UG-12-S06-A060 | UG-07-S03-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-07-S03-A050 | UG-07-S03-A060 | SS | 10 | Within package (ladder)
UG-07-S03-A050 | UG-07-S03-A060 | FF | 2 | Within package (ladder)
UG-12-S06-A060 | UG-07-S03-A060 | FS | 0 | Crew continuity, front F5
UG-11-S06-A100 | UG-07-S03-A060 | FS | 0 | Deeper line first
UG-12-S06-A060 | UG-07-S03-A060 | SS | 0 | Shared excavation / dewatering front
UG-12-S07-A060 | UG-07-S03-A060 | SS | 0 | Shared excavation / dewatering front
UG-12-S08-A060 | UG-07-S03-A060 | SS | 0 | Shared excavation / dewatering front
UG-07-S03-A060 | UG-07-S03-A070 | SS | 1 | Within package (ladder)
UG-07-S03-A060 | UG-07-S03-A070 | FF | 2 | Within package (ladder)
UG-12-S06-A070 | UG-07-S03-A070 | FS | 0 | Crew continuity, front F5
UG-07-S03-A070 | UG-07-S03-A080 | SS | 3 | Within package (ladder)
UG-07-S03-A070 | UG-07-S03-A080 | FF | 2 | Within package (ladder)
UG-12-S06-A080 | UG-07-S03-A080 | FS | 0 | Crew continuity, front F5
UG-07-S03-A080 | UG-07-S03-A090 | SS | 1 | Within package (ladder)
UG-07-S03-A080 | UG-07-S03-A090 | FF | 2 | Within package (ladder)
UG-07-S03-A090 | UG-07-S03-A100 | SS | 2 | Within package (ladder)
UG-07-S03-A090 | UG-07-S03-A100 | FF | 2 | Within package (ladder)
UG-12-S06-A100 | UG-07-S03-A100 | FS | 0 | Crew continuity, front F5
UG-11-S01-A080 | UG-07-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12-S06-A080 | UG-07-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12-S07-A080 | UG-07-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12-S08-A080 | UG-07-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-07-S03-A100 | UG-07-S03-A110 | SS | 1 | Within package (ladder)
UG-07-S03-A100 | UG-07-S03-A110 | FF | 2 | Within package (ladder)
UG-07-S04-A010 | UG-07-S04-A020 | FS | 0 | Within package
UG-07-S03-A030 | UG-07-S04-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-07-S04-A020 | UG-07-S04-A030 | SS | 1 | Within package (ladder)
UG-07-S04-A020 | UG-07-S04-A030 | FF | 2 | Within package (ladder)
UG-07-S04-A030 | UG-07-S04-A040 | SS | 1 | Within package (ladder)
UG-07-S04-A030 | UG-07-S04-A040 | FF | 2 | Within package (ladder)
UG-07-S04-A040 | UG-07-S04-A050 | SS | 1 | Within package (ladder)
UG-07-S04-A040 | UG-07-S04-A050 | FF | 2 | Within package (ladder)
UG-07-S04-A050 | UG-07-S04-A060 | SS | 10 | Within package (ladder)
UG-07-S04-A050 | UG-07-S04-A060 | FF | 2 | Within package (ladder)
UG-11-S06-A100 | UG-07-S04-A060 | FS | 0 | Deeper line first
UG-12-S07-A060 | UG-07-S04-A060 | SS | 0 | Shared excavation / dewatering front
UG-12-S08-A060 | UG-07-S04-A060 | SS | 0 | Shared excavation / dewatering front
UG-07-S04-A060 | UG-07-S04-A070 | SS | 1 | Within package (ladder)
UG-07-S04-A060 | UG-07-S04-A070 | FF | 2 | Within package (ladder)
UG-07-S04-A070 | UG-07-S04-A080 | SS | 2 | Within package (ladder)
UG-07-S04-A070 | UG-07-S04-A080 | FF | 2 | Within package (ladder)
UG-07-S03-A080 | UG-07-S04-A080 | FS | 0 | Tie-in laid as closure
UG-07-S04-A080 | UG-07-S04-A090 | SS | 2 | Within package (ladder)
UG-07-S04-A080 | UG-07-S04-A090 | FF | 2 | Within package (ladder)
UG-07-S04-A090 | UG-07-S04-A100 | SS | 2 | Within package (ladder)
UG-07-S04-A090 | UG-07-S04-A100 | FF | 2 | Within package (ladder)
UG-11-S01-A080 | UG-07-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12-S07-A080 | UG-07-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12-S08-A080 | UG-07-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-07-S04-A100 | UG-07-S04-A110 | SS | 1 | Within package (ladder)
UG-07-S04-A100 | UG-07-S04-A110 | FF | 2 | Within package (ladder)
UG-11-S01-A010 | UG-11-S01-A020 | FS | 0 | Within package
UG-07-S03-A030 | UG-11-S01-A020 | SS | 0 | Set-out one package ahead of piling
UG-11-S01-A020 | UG-11-S01-A030 | SS | 1 | Within package (ladder)
UG-11-S01-A020 | UG-11-S01-A030 | FF | 2 | Within package (ladder)
UG-07-S03-A030 | UG-11-S01-A030 | FS | 0 | Crew continuity, front F5
UG-11-S01-A030 | UG-11-S01-A040 | SS | 3 | Within package (ladder)
UG-11-S01-A030 | UG-11-S01-A040 | FF | 2 | Within package (ladder)
UG-07-S03-A040 | UG-11-S01-A040 | FS | 0 | Crew continuity, front F5
UG-11-S01-A040 | UG-11-S01-A050 | SS | 2 | Within package (ladder)
UG-11-S01-A040 | UG-11-S01-A050 | FF | 2 | Within package (ladder)
UG-07-S03-A060 | UG-11-S01-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11-S01-A050 | UG-11-S01-A060 | SS | 10 | Within package (ladder)
UG-11-S01-A050 | UG-11-S01-A060 | FF | 2 | Within package (ladder)
UG-07-S03-A060 | UG-11-S01-A060 | FS | 0 | Crew continuity, front F5
UG-07-S03-A060 | UG-11-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-07-S04-A060 | UG-11-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-11B-S14-A060 | UG-11-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-12-S07-A060 | UG-11-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-12-S08-A060 | UG-11-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-11-S01-A060 | UG-11-S01-A070 | SS | 2 | Within package (ladder)
UG-11-S01-A060 | UG-11-S01-A070 | FF | 2 | Within package (ladder)
UG-07-S03-A070 | UG-11-S01-A070 | FS | 0 | Crew continuity, front F5
UG-11-S01-A070 | UG-11-S01-A080 | SS | 3 | Within package (ladder)
UG-11-S01-A070 | UG-11-S01-A080 | FF | 2 | Within package (ladder)
UG-07-S03-A080 | UG-11-S01-A080 | FS | 0 | Crew continuity, front F5
UG-11-S01-A080 | UG-11-S01-A090 | SS | 2 | Within package (ladder)
UG-11-S01-A080 | UG-11-S01-A090 | FF | 2 | Within package (ladder)
UG-11-S01-A090 | UG-11-S01-A100 | SS | 2 | Within package (ladder)
UG-11-S01-A090 | UG-11-S01-A100 | FF | 2 | Within package (ladder)
UG-07-S03-A100 | UG-11-S01-A100 | FS | 0 | Crew continuity, front F5
UG-07-S03-A080 | UG-11-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-07-S04-A080 | UG-11-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11B-S14-A080 | UG-11-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12-S07-A080 | UG-11-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12-S08-A080 | UG-11-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11-S01-A100 | UG-11-S01-A110 | SS | 1 | Within package (ladder)
UG-11-S01-A100 | UG-11-S01-A110 | FF | 2 | Within package (ladder)
UG-12-S05-A010 | UG-12-S05-A020 | FS | 0 | Within package
UG-11-S01-A030 | UG-12-S05-A020 | SS | 0 | Set-out one package ahead of piling
UG-12-S05-A020 | UG-12-S05-A030 | SS | 1 | Within package (ladder)
UG-12-S05-A020 | UG-12-S05-A030 | FF | 2 | Within package (ladder)
UG-11-S01-A030 | UG-12-S05-A030 | FS | 0 | Crew continuity, front F5
UG-12-S05-A030 | UG-12-S05-A040 | SS | 2 | Within package (ladder)
UG-12-S05-A030 | UG-12-S05-A040 | FF | 2 | Within package (ladder)
UG-11-S01-A040 | UG-12-S05-A040 | FS | 0 | Crew continuity, front F5
UG-12-S05-A040 | UG-12-S05-A050 | SS | 1 | Within package (ladder)
UG-12-S05-A040 | UG-12-S05-A050 | FF | 2 | Within package (ladder)
UG-11-S01-A060 | UG-12-S05-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-12-S05-A050 | UG-12-S05-A060 | SS | 10 | Within package (ladder)
UG-12-S05-A050 | UG-12-S05-A060 | FF | 2 | Within package (ladder)
UG-11-S01-A060 | UG-12-S05-A060 | FS | 0 | Crew continuity, front F5
UG-12-S05-A060 | UG-12-S05-A070 | SS | 2 | Within package (ladder)
UG-12-S05-A060 | UG-12-S05-A070 | FF | 2 | Within package (ladder)
UG-11-S01-A070 | UG-12-S05-A070 | FS | 0 | Crew continuity, front F5
UG-12-S05-A070 | UG-12-S05-A080 | SS | 3 | Within package (ladder)
UG-12-S05-A070 | UG-12-S05-A080 | FF | 2 | Within package (ladder)
UG-11-S01-A080 | UG-12-S05-A080 | FS | 0 | Crew continuity, front F5
UG-12-S05-A080 | UG-12-S05-A090 | SS | 2 | Within package (ladder)
UG-12-S05-A080 | UG-12-S05-A090 | FF | 2 | Within package (ladder)
UG-12-S05-A090 | UG-12-S05-A100 | SS | 2 | Within package (ladder)
UG-12-S05-A090 | UG-12-S05-A100 | FF | 2 | Within package (ladder)
UG-11-S01-A100 | UG-12-S05-A100 | FS | 0 | Crew continuity, front F5
UG-12-S05-A100 | UG-12-S05-A110 | SS | 1 | Within package (ladder)
UG-12-S05-A100 | UG-12-S05-A110 | FF | 2 | Within package (ladder)
UG-12-S02-A010 | UG-12-S02-A020 | FS | 0 | Within package
UG-12-S05-A030 | UG-12-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-12-S02-A020 | UG-12-S02-A030 | SS | 1 | Within package (ladder)
UG-12-S02-A020 | UG-12-S02-A030 | FF | 2 | Within package (ladder)
UG-12-S05-A030 | UG-12-S02-A030 | FS | 0 | Crew continuity, front F5
UG-12-S02-A030 | UG-12-S02-A040 | SS | 2 | Within package (ladder)
UG-12-S02-A030 | UG-12-S02-A040 | FF | 0 | Within package (ladder)
UG-12-S05-A040 | UG-12-S02-A040 | FS | 0 | Crew continuity, front F5
UG-12-S02-A040 | UG-12-S02-A050 | SS | 0 | Within package (ladder)
UG-12-S02-A040 | UG-12-S02-A050 | FF | 2 | Within package (ladder)
UG-12-S05-A060 | UG-12-S02-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-12-S02-A050 | UG-12-S02-A060 | SS | 10 | Within package (ladder)
UG-12-S02-A050 | UG-12-S02-A060 | FF | 2 | Within package (ladder)
UG-12-S05-A060 | UG-12-S02-A060 | FS | 0 | Crew continuity, front F5
UG-13-S02-A100 | UG-12-S02-A060 | FS | 0 | Deeper line first
UG-13-S03-A100 | UG-12-S02-A060 | FS | 0 | Deeper line first
UG-12-S02-A060 | UG-12-S02-A070 | SS | 1 | Within package (ladder)
UG-12-S02-A060 | UG-12-S02-A070 | FF | 2 | Within package (ladder)
UG-12-S05-A070 | UG-12-S02-A070 | FS | 0 | Crew continuity, front F5
UG-12-S02-A070 | UG-12-S02-A080 | SS | 2 | Within package (ladder)
UG-12-S02-A070 | UG-12-S02-A080 | FF | 2 | Within package (ladder)
UG-12-S05-A080 | UG-12-S02-A080 | FS | 0 | Crew continuity, front F5
UG-12-S02-A080 | UG-12-S02-A090 | SS | 1 | Within package (ladder)
UG-12-S02-A080 | UG-12-S02-A090 | FF | 2 | Within package (ladder)
UG-12-S02-A090 | UG-12-S02-A100 | SS | 2 | Within package (ladder)
UG-12-S02-A090 | UG-12-S02-A100 | FF | 2 | Within package (ladder)
UG-12-S05-A100 | UG-12-S02-A100 | FS | 0 | Crew continuity, front F5
UG-12A-S12-A080 | UG-12-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12-S02-A100 | UG-12-S02-A110 | SS | 1 | Within package (ladder)
UG-12-S02-A100 | UG-12-S02-A110 | FF | 2 | Within package (ladder)
UG-12-S01-A010 | UG-12-S01-A020 | FS | 0 | Within package
UG-12-S02-A030 | UG-12-S01-A020 | SS | 0 | Set-out one package ahead of piling
UG-12-S01-A020 | UG-12-S01-A030 | SS | 1 | Within package (ladder)
UG-12-S01-A020 | UG-12-S01-A030 | FF | 2 | Within package (ladder)
UG-12-S02-A030 | UG-12-S01-A030 | FS | 0 | Crew continuity, front F5
UG-12-S01-A030 | UG-12-S01-A040 | SS | 2 | Within package (ladder)
UG-12-S01-A030 | UG-12-S01-A040 | FF | 0 | Within package (ladder)
UG-12-S02-A040 | UG-12-S01-A040 | FS | 0 | Crew continuity, front F5
UG-12-S01-A040 | UG-12-S01-A050 | SS | 0 | Within package (ladder)
UG-12-S01-A040 | UG-12-S01-A050 | FF | 2 | Within package (ladder)
UG-12-S02-A060 | UG-12-S01-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-12-S01-A050 | UG-12-S01-A060 | SS | 10 | Within package (ladder)
UG-12-S01-A050 | UG-12-S01-A060 | FF | 2 | Within package (ladder)
UG-12-S02-A060 | UG-12-S01-A060 | FS | 0 | Crew continuity, front F5
UG-13-S02-A100 | UG-12-S01-A060 | FS | 0 | Deeper line first
UG-13-S03-A100 | UG-12-S01-A060 | FS | 0 | Deeper line first
UG-12-S01-A060 | UG-12-S01-A070 | SS | 1 | Within package (ladder)
UG-12-S01-A060 | UG-12-S01-A070 | FF | 2 | Within package (ladder)
UG-12-S02-A070 | UG-12-S01-A070 | FS | 0 | Crew continuity, front F5
UG-12-S01-A070 | UG-12-S01-A080 | SS | 3 | Within package (ladder)
UG-12-S01-A070 | UG-12-S01-A080 | FF | 2 | Within package (ladder)
UG-12-S02-A080 | UG-12-S01-A080 | FS | 0 | Crew continuity, front F5
UG-12-S01-A080 | UG-12-S01-A090 | SS | 2 | Within package (ladder)
UG-12-S01-A080 | UG-12-S01-A090 | FF | 2 | Within package (ladder)
UG-12-S01-A090 | UG-12-S01-A100 | SS | 2 | Within package (ladder)
UG-12-S01-A090 | UG-12-S01-A100 | FF | 2 | Within package (ladder)
UG-12-S02-A100 | UG-12-S01-A100 | FS | 0 | Crew continuity, front F5
UG-12A-S06-A080 | UG-12-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12A-S10-A080 | UG-12-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12A-S12-A080 | UG-12-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12-S01-A100 | UG-12-S01-A110 | SS | 1 | Within package (ladder)
UG-12-S01-A100 | UG-12-S01-A110 | FF | 2 | Within package (ladder)
UG-12A-S12-A010 | UG-12A-S12-A020 | FS | 0 | Within package
UG-12-S01-A030 | UG-12A-S12-A020 | SS | 0 | Set-out one package ahead of piling
UG-12A-S12-A020 | UG-12A-S12-A030 | SS | 1 | Within package (ladder)
UG-12A-S12-A020 | UG-12A-S12-A030 | FF | 2 | Within package (ladder)
UG-12-S01-A030 | UG-12A-S12-A030 | FS | 0 | Crew continuity, front F5
UG-12A-S12-A030 | UG-12A-S12-A040 | SS | 1 | Within package (ladder)
UG-12A-S12-A030 | UG-12A-S12-A040 | FF | 0 | Within package (ladder)
UG-12-S01-A040 | UG-12A-S12-A040 | FS | 0 | Crew continuity, front F5
UG-12A-S12-A040 | UG-12A-S12-A050 | SS | 0 | Within package (ladder)
UG-12A-S12-A040 | UG-12A-S12-A050 | FF | 2 | Within package (ladder)
UG-12-S01-A060 | UG-12A-S12-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-12A-S12-A050 | UG-12A-S12-A060 | SS | 10 | Within package (ladder)
UG-12A-S12-A050 | UG-12A-S12-A060 | FF | 2 | Within package (ladder)
UG-12-S01-A060 | UG-12A-S12-A060 | FS | 0 | Crew continuity, front F5
UG-13-S03-A100 | UG-12A-S12-A060 | FS | 0 | Deeper line first
UG-12-S01-A060 | UG-12A-S12-A060 | SS | 0 | Shared excavation / dewatering front
UG-12-S02-A060 | UG-12A-S12-A060 | SS | 0 | Shared excavation / dewatering front
UG-12A-S12-A060 | UG-12A-S12-A070 | SS | 1 | Within package (ladder)
UG-12A-S12-A060 | UG-12A-S12-A070 | FF | 2 | Within package (ladder)
UG-12-S01-A070 | UG-12A-S12-A070 | FS | 0 | Crew continuity, front F5
UG-12A-S12-A070 | UG-12A-S12-A080 | SS | 2 | Within package (ladder)
UG-12A-S12-A070 | UG-12A-S12-A080 | FF | 2 | Within package (ladder)
UG-12-S01-A080 | UG-12A-S12-A080 | FS | 0 | Crew continuity, front F5
UG-12A-S12-A080 | UG-12A-S12-A090 | SS | 1 | Within package (ladder)
UG-12A-S12-A080 | UG-12A-S12-A090 | FF | 2 | Within package (ladder)
UG-12A-S12-A090 | UG-12A-S12-A100 | SS | 2 | Within package (ladder)
UG-12A-S12-A090 | UG-12A-S12-A100 | FF | 2 | Within package (ladder)
UG-12-S01-A100 | UG-12A-S12-A100 | FS | 0 | Crew continuity, front F5
UG-12-S01-A080 | UG-12A-S12-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12-S02-A080 | UG-12A-S12-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12A-S12-A100 | UG-12A-S12-A110 | SS | 1 | Within package (ladder)
UG-12A-S12-A100 | UG-12A-S12-A110 | FF | 2 | Within package (ladder)
UG-12A-S10-A010 | UG-12A-S10-A020 | FS | 0 | Within package
UG-12A-S12-A030 | UG-12A-S10-A020 | SS | 0 | Set-out one package ahead of piling
UG-12A-S10-A020 | UG-12A-S10-A030 | SS | 1 | Within package (ladder)
UG-12A-S10-A020 | UG-12A-S10-A030 | FF | 2 | Within package (ladder)
UG-12A-S12-A030 | UG-12A-S10-A030 | FS | 0 | Crew continuity, front F5
UG-12A-S10-A030 | UG-12A-S10-A040 | SS | 2 | Within package (ladder)
UG-12A-S10-A030 | UG-12A-S10-A040 | FF | 0 | Within package (ladder)
UG-12A-S12-A040 | UG-12A-S10-A040 | FS | 0 | Crew continuity, front F5
UG-12A-S10-A040 | UG-12A-S10-A050 | SS | 0 | Within package (ladder)
UG-12A-S10-A040 | UG-12A-S10-A050 | FF | 2 | Within package (ladder)
UG-12A-S12-A060 | UG-12A-S10-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-12A-S10-A050 | UG-12A-S10-A060 | SS | 10 | Within package (ladder)
UG-12A-S10-A050 | UG-12A-S10-A060 | FF | 2 | Within package (ladder)
UG-12A-S12-A060 | UG-12A-S10-A060 | FS | 0 | Crew continuity, front F5
UG-12-S01-A060 | UG-12A-S10-A060 | SS | 0 | Shared excavation / dewatering front
UG-12A-S10-A060 | UG-12A-S10-A070 | SS | 1 | Within package (ladder)
UG-12A-S10-A060 | UG-12A-S10-A070 | FF | 2 | Within package (ladder)
UG-12A-S12-A070 | UG-12A-S10-A070 | FS | 0 | Crew continuity, front F5
UG-12A-S10-A070 | UG-12A-S10-A080 | SS | 3 | Within package (ladder)
UG-12A-S10-A070 | UG-12A-S10-A080 | FF | 2 | Within package (ladder)
UG-12A-S12-A080 | UG-12A-S10-A080 | FS | 0 | Crew continuity, front F5
UG-12A-S10-A080 | UG-12A-S10-A090 | SS | 1 | Within package (ladder)
UG-12A-S10-A080 | UG-12A-S10-A090 | FF | 2 | Within package (ladder)
UG-12A-S10-A090 | UG-12A-S10-A100 | SS | 2 | Within package (ladder)
UG-12A-S10-A090 | UG-12A-S10-A100 | FF | 2 | Within package (ladder)
UG-12A-S12-A100 | UG-12A-S10-A100 | FS | 0 | Crew continuity, front F5
UG-12-S01-A080 | UG-12A-S10-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12A-S10-A100 | UG-12A-S10-A110 | SS | 1 | Within package (ladder)
UG-12A-S10-A100 | UG-12A-S10-A110 | FF | 2 | Within package (ladder)
UG-12A-S06-A010 | UG-12A-S06-A020 | FS | 0 | Within package
UG-12A-S10-A030 | UG-12A-S06-A020 | SS | 0 | Set-out one package ahead of piling
UG-12A-S06-A020 | UG-12A-S06-A030 | SS | 1 | Within package (ladder)
UG-12A-S06-A020 | UG-12A-S06-A030 | FF | 2 | Within package (ladder)
UG-12A-S10-A030 | UG-12A-S06-A030 | FS | 0 | Crew continuity, front F5
UG-12A-S06-A030 | UG-12A-S06-A040 | SS | 3 | Within package (ladder)
UG-12A-S06-A030 | UG-12A-S06-A040 | FF | 0 | Within package (ladder)
UG-12A-S10-A040 | UG-12A-S06-A040 | FS | 0 | Crew continuity, front F5
UG-12A-S06-A040 | UG-12A-S06-A050 | SS | 0 | Within package (ladder)
UG-12A-S06-A040 | UG-12A-S06-A050 | FF | 2 | Within package (ladder)
UG-12A-S10-A060 | UG-12A-S06-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-12A-S06-A050 | UG-12A-S06-A060 | SS | 10 | Within package (ladder)
UG-12A-S06-A050 | UG-12A-S06-A060 | FF | 2 | Within package (ladder)
UG-12A-S10-A060 | UG-12A-S06-A060 | FS | 0 | Crew continuity, front F5
UG-12-S01-A060 | UG-12A-S06-A060 | SS | 0 | Shared excavation / dewatering front
UG-12A-S06-A060 | UG-12A-S06-A070 | SS | 1 | Within package (ladder)
UG-12A-S06-A060 | UG-12A-S06-A070 | FF | 2 | Within package (ladder)
UG-12A-S10-A070 | UG-12A-S06-A070 | FS | 0 | Crew continuity, front F5
UG-12A-S06-A070 | UG-12A-S06-A080 | SS | 3 | Within package (ladder)
UG-12A-S06-A070 | UG-12A-S06-A080 | FF | 2 | Within package (ladder)
UG-12A-S10-A080 | UG-12A-S06-A080 | FS | 0 | Crew continuity, front F5
UG-12A-S06-A080 | UG-12A-S06-A090 | SS | 1 | Within package (ladder)
UG-12A-S06-A080 | UG-12A-S06-A090 | FF | 2 | Within package (ladder)
UG-12A-S06-A090 | UG-12A-S06-A100 | SS | 2 | Within package (ladder)
UG-12A-S06-A090 | UG-12A-S06-A100 | FF | 2 | Within package (ladder)
UG-12A-S10-A100 | UG-12A-S06-A100 | FS | 0 | Crew continuity, front F5
UG-12-S01-A080 | UG-12A-S06-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12A-S06-A100 | UG-12A-S06-A110 | SS | 1 | Within package (ladder)
UG-12A-S06-A100 | UG-12A-S06-A110 | FF | 2 | Within package (ladder)
UG-12A-S05-A010 | UG-12A-S05-A020 | FS | 0 | Within package
UG-12A-S06-A030 | UG-12A-S05-A020 | SS | 0 | Set-out one package ahead of piling
UG-12A-S05-A020 | UG-12A-S05-A030 | SS | 1 | Within package (ladder)
UG-12A-S05-A020 | UG-12A-S05-A030 | FF | 2 | Within package (ladder)
UG-12A-S06-A030 | UG-12A-S05-A030 | FS | 0 | Crew continuity, front F5
UG-12A-S05-A030 | UG-12A-S05-A040 | SS | 2 | Within package (ladder)
UG-12A-S05-A030 | UG-12A-S05-A040 | FF | 0 | Within package (ladder)
UG-12A-S06-A040 | UG-12A-S05-A040 | FS | 0 | Crew continuity, front F5
UG-12A-S05-A040 | UG-12A-S05-A050 | SS | 0 | Within package (ladder)
UG-12A-S05-A040 | UG-12A-S05-A050 | FF | 2 | Within package (ladder)
UG-12A-S06-A060 | UG-12A-S05-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-12A-S05-A050 | UG-12A-S05-A060 | SS | 10 | Within package (ladder)
UG-12A-S05-A050 | UG-12A-S05-A060 | FF | 2 | Within package (ladder)
UG-12A-S06-A060 | UG-12A-S05-A060 | FS | 0 | Crew continuity, front F5
UG-06-S03-A100 | UG-12A-S05-A060 | FS | 0 | Deeper line first
UG-12A-S05-A060 | UG-12A-S05-A070 | SS | 1 | Within package (ladder)
UG-12A-S05-A060 | UG-12A-S05-A070 | FF | 2 | Within package (ladder)
UG-12A-S06-A070 | UG-12A-S05-A070 | FS | 0 | Crew continuity, front F5
UG-12A-S05-A070 | UG-12A-S05-A080 | SS | 2 | Within package (ladder)
UG-12A-S05-A070 | UG-12A-S05-A080 | FF | 2 | Within package (ladder)
UG-12A-S06-A080 | UG-12A-S05-A080 | FS | 0 | Crew continuity, front F5
UG-12A-S05-A080 | UG-12A-S05-A090 | SS | 1 | Within package (ladder)
UG-12A-S05-A080 | UG-12A-S05-A090 | FF | 2 | Within package (ladder)
UG-12A-S05-A090 | UG-12A-S05-A100 | SS | 2 | Within package (ladder)
UG-12A-S05-A090 | UG-12A-S05-A100 | FF | 2 | Within package (ladder)
UG-12A-S06-A100 | UG-12A-S05-A100 | FS | 0 | Crew continuity, front F5
UG-12A-S05-A100 | UG-12A-S05-A110 | SS | 1 | Within package (ladder)
UG-12A-S05-A100 | UG-12A-S05-A110 | FF | 2 | Within package (ladder)
UG-12A-S04-A010 | UG-12A-S04-A020 | FS | 0 | Within package
UG-12A-S05-A030 | UG-12A-S04-A020 | SS | 0 | Set-out one package ahead of piling
UG-12A-S04-A020 | UG-12A-S04-A030 | SS | 1 | Within package (ladder)
UG-12A-S04-A020 | UG-12A-S04-A030 | FF | 2 | Within package (ladder)
UG-12A-S05-A030 | UG-12A-S04-A030 | FS | 0 | Crew continuity, front F5
UG-12A-S04-A030 | UG-12A-S04-A040 | SS | 4 | Within package (ladder)
UG-12A-S04-A030 | UG-12A-S04-A040 | FF | 2 | Within package (ladder)
UG-12A-S05-A040 | UG-12A-S04-A040 | FS | 0 | Crew continuity, front F5
UG-12A-S04-A040 | UG-12A-S04-A050 | SS | 2 | Within package (ladder)
UG-12A-S04-A040 | UG-12A-S04-A050 | FF | 2 | Within package (ladder)
UG-12A-S05-A060 | UG-12A-S04-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-12A-S04-A050 | UG-12A-S04-A060 | SS | 10 | Within package (ladder)
UG-12A-S04-A050 | UG-12A-S04-A060 | FF | 2 | Within package (ladder)
UG-12A-S05-A060 | UG-12A-S04-A060 | FS | 0 | Crew continuity, front F5
UG-05-S04-A100 | UG-12A-S04-A060 | FS | 0 | Deeper line first
UG-06-S04-A100 | UG-12A-S04-A060 | FS | 0 | Deeper line first
UG-12A-S04-A060 | UG-12A-S04-A070 | SS | 2 | Within package (ladder)
UG-12A-S04-A060 | UG-12A-S04-A070 | FF | 2 | Within package (ladder)
UG-12A-S05-A070 | UG-12A-S04-A070 | FS | 0 | Crew continuity, front F5
UG-12A-S04-A070 | UG-12A-S04-A080 | SS | 4 | Within package (ladder)
UG-12A-S04-A070 | UG-12A-S04-A080 | FF | 2 | Within package (ladder)
UG-12A-S05-A080 | UG-12A-S04-A080 | FS | 0 | Crew continuity, front F5
UG-12A-S04-A080 | UG-12A-S04-A090 | SS | 2 | Within package (ladder)
UG-12A-S04-A080 | UG-12A-S04-A090 | FF | 2 | Within package (ladder)
UG-12A-S04-A090 | UG-12A-S04-A100 | SS | 2 | Within package (ladder)
UG-12A-S04-A090 | UG-12A-S04-A100 | FF | 2 | Within package (ladder)
UG-12A-S05-A100 | UG-12A-S04-A100 | FS | 0 | Crew continuity, front F5
UG-12A-S04-A100 | UG-12A-S04-A110 | SS | 2 | Within package (ladder)
UG-12A-S04-A100 | UG-12A-S04-A110 | FF | 2 | Within package (ladder)
UG-12A-S03-A010 | UG-12A-S03-A020 | FS | 0 | Within package
UG-12A-S04-A030 | UG-12A-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-12A-S03-A020 | UG-12A-S03-A030 | SS | 1 | Within package (ladder)
UG-12A-S03-A020 | UG-12A-S03-A030 | FF | 2 | Within package (ladder)
UG-12A-S04-A030 | UG-12A-S03-A030 | FS | 0 | Crew continuity, front F5
UG-12A-S03-A030 | UG-12A-S03-A040 | SS | 4 | Within package (ladder)
UG-12A-S03-A030 | UG-12A-S03-A040 | FF | 2 | Within package (ladder)
UG-12A-S04-A040 | UG-12A-S03-A040 | FS | 0 | Crew continuity, front F5
UG-12A-S03-A040 | UG-12A-S03-A050 | SS | 2 | Within package (ladder)
UG-12A-S03-A040 | UG-12A-S03-A050 | FF | 2 | Within package (ladder)
UG-12A-S04-A060 | UG-12A-S03-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-12A-S03-A050 | UG-12A-S03-A060 | SS | 10 | Within package (ladder)
UG-12A-S03-A050 | UG-12A-S03-A060 | FF | 2 | Within package (ladder)
UG-12A-S04-A060 | UG-12A-S03-A060 | FS | 0 | Crew continuity, front F5
UG-05-S04-A100 | UG-12A-S03-A060 | FS | 0 | Deeper line first
UG-06-S04-A100 | UG-12A-S03-A060 | FS | 0 | Deeper line first
UG-06-S05-A100 | UG-12A-S03-A060 | FS | 0 | Deeper line first
UG-12A-S03-A060 | UG-12A-S03-A070 | SS | 1 | Within package (ladder)
UG-12A-S03-A060 | UG-12A-S03-A070 | FF | 2 | Within package (ladder)
UG-12A-S04-A070 | UG-12A-S03-A070 | FS | 0 | Crew continuity, front F5
UG-12A-S03-A070 | UG-12A-S03-A080 | SS | 4 | Within package (ladder)
UG-12A-S03-A070 | UG-12A-S03-A080 | FF | 2 | Within package (ladder)
UG-12A-S04-A080 | UG-12A-S03-A080 | FS | 0 | Crew continuity, front F5
UG-12A-S03-A080 | UG-12A-S03-A090 | SS | 2 | Within package (ladder)
UG-12A-S03-A080 | UG-12A-S03-A090 | FF | 2 | Within package (ladder)
UG-12A-S03-A090 | UG-12A-S03-A100 | SS | 2 | Within package (ladder)
UG-12A-S03-A090 | UG-12A-S03-A100 | FF | 2 | Within package (ladder)
UG-12A-S04-A100 | UG-12A-S03-A100 | FS | 0 | Crew continuity, front F5
UG-12A-S03-A100 | UG-12A-S03-A110 | SS | 1 | Within package (ladder)
UG-12A-S03-A100 | UG-12A-S03-A110 | FF | 2 | Within package (ladder)
UG-12A-S02-A010 | UG-12A-S02-A020 | FS | 0 | Within package
UG-12A-S03-A030 | UG-12A-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-12A-S02-A020 | UG-12A-S02-A030 | SS | 1 | Within package (ladder)
UG-12A-S02-A020 | UG-12A-S02-A030 | FF | 2 | Within package (ladder)
UG-12A-S03-A030 | UG-12A-S02-A030 | FS | 0 | Crew continuity, front F5
UG-12A-S02-A030 | UG-12A-S02-A040 | SS | 4 | Within package (ladder)
UG-12A-S02-A030 | UG-12A-S02-A040 | FF | 0 | Within package (ladder)
UG-12A-S03-A040 | UG-12A-S02-A040 | FS | 0 | Crew continuity, front F5
UG-12A-S02-A040 | UG-12A-S02-A050 | SS | 0 | Within package (ladder)
UG-12A-S02-A040 | UG-12A-S02-A050 | FF | 2 | Within package (ladder)
UG-12A-S03-A060 | UG-12A-S02-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-12A-S02-A050 | UG-12A-S02-A060 | SS | 10 | Within package (ladder)
UG-12A-S02-A050 | UG-12A-S02-A060 | FF | 2 | Within package (ladder)
UG-12A-S03-A060 | UG-12A-S02-A060 | FS | 0 | Crew continuity, front F5
UG-12A-S02-A060 | UG-12A-S02-A070 | SS | 2 | Within package (ladder)
UG-12A-S02-A060 | UG-12A-S02-A070 | FF | 2 | Within package (ladder)
UG-12A-S03-A070 | UG-12A-S02-A070 | FS | 0 | Crew continuity, front F5
UG-12A-S02-A070 | UG-12A-S02-A080 | SS | 4 | Within package (ladder)
UG-12A-S02-A070 | UG-12A-S02-A080 | FF | 2 | Within package (ladder)
UG-12A-S03-A080 | UG-12A-S02-A080 | FS | 0 | Crew continuity, front F5
UG-12A-S02-A080 | UG-12A-S02-A090 | SS | 2 | Within package (ladder)
UG-12A-S02-A080 | UG-12A-S02-A090 | FF | 2 | Within package (ladder)
UG-12A-S02-A090 | UG-12A-S02-A100 | SS | 2 | Within package (ladder)
UG-12A-S02-A090 | UG-12A-S02-A100 | FF | 2 | Within package (ladder)
UG-12A-S03-A100 | UG-12A-S02-A100 | FS | 0 | Crew continuity, front F5
UG-12A-S02-A100 | UG-12A-S02-A110 | SS | 2 | Within package (ladder)
UG-12A-S02-A100 | UG-12A-S02-A110 | FF | 2 | Within package (ladder)
UG-12A-S01-A010 | UG-12A-S01-A020 | FS | 0 | Within package
UG-12A-S02-A030 | UG-12A-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-12A-S01-A020 | UG-12A-S01-A030 | SS | 1 | Within package (ladder)
UG-12A-S01-A020 | UG-12A-S01-A030 | FF | 2 | Within package (ladder)
UG-12A-S01-A030 | UG-12A-S01-A040 | SS | 2 | Within package (ladder)
UG-12A-S01-A030 | UG-12A-S01-A040 | FF | 0 | Within package (ladder)
UG-12A-S01-A040 | UG-12A-S01-A050 | SS | 0 | Within package (ladder)
UG-12A-S01-A040 | UG-12A-S01-A050 | FF | 2 | Within package (ladder)
UG-12A-S01-A050 | UG-12A-S01-A060 | SS | 10 | Within package (ladder)
UG-12A-S01-A050 | UG-12A-S01-A060 | FF | 2 | Within package (ladder)
UG-12A-S01-A060 | UG-12A-S01-A070 | SS | 1 | Within package (ladder)
UG-12A-S01-A060 | UG-12A-S01-A070 | FF | 2 | Within package (ladder)
UG-12A-S01-A070 | UG-12A-S01-A080 | SS | 2 | Within package (ladder)
UG-12A-S01-A070 | UG-12A-S01-A080 | FF | 2 | Within package (ladder)
UG-12A-S02-A080 | UG-12A-S01-A080 | FS | 0 | Tie-in laid as closure
UG-12A-S01-A080 | UG-12A-S01-A090 | SS | 2 | Within package (ladder)
UG-12A-S01-A080 | UG-12A-S01-A090 | FF | 2 | Within package (ladder)
UG-12A-S01-A090 | UG-12A-S01-A100 | SS | 2 | Within package (ladder)
UG-12A-S01-A090 | UG-12A-S01-A100 | FF | 2 | Within package (ladder)
UG-12A-S01-A100 | UG-12A-S01-A110 | SS | 1 | Within package (ladder)
UG-12A-S01-A100 | UG-12A-S01-A110 | FF | 2 | Within package (ladder)
UG-12A-S08-A010 | UG-12A-S08-A020 | FS | 0 | Within package
UG-12A-S02-A030 | UG-12A-S08-A020 | SS | 0 | Set-out one package ahead of piling
UG-12A-S08-A020 | UG-12A-S08-A030 | SS | 1 | Within package (ladder)
UG-12A-S08-A020 | UG-12A-S08-A030 | FF | 2 | Within package (ladder)
UG-12A-S02-A030 | UG-12A-S08-A030 | FS | 0 | Crew continuity, front F5
UG-12A-S08-A030 | UG-12A-S08-A040 | SS | 1 | Within package (ladder)
UG-12A-S08-A030 | UG-12A-S08-A040 | FF | 0 | Within package (ladder)
UG-12A-S02-A040 | UG-12A-S08-A040 | FS | 0 | Crew continuity, front F5
UG-12A-S08-A040 | UG-12A-S08-A050 | SS | 0 | Within package (ladder)
UG-12A-S08-A040 | UG-12A-S08-A050 | FF | 2 | Within package (ladder)
UG-12A-S02-A060 | UG-12A-S08-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-12A-S08-A050 | UG-12A-S08-A060 | SS | 10 | Within package (ladder)
UG-12A-S08-A050 | UG-12A-S08-A060 | FF | 2 | Within package (ladder)
UG-12A-S02-A060 | UG-12A-S08-A060 | FS | 0 | Crew continuity, front F5
UG-05-S04-A100 | UG-12A-S08-A060 | FS | 0 | Deeper line first
UG-06-S04-A100 | UG-12A-S08-A060 | FS | 0 | Deeper line first
UG-12A-S08-A060 | UG-12A-S08-A070 | SS | 1 | Within package (ladder)
UG-12A-S08-A060 | UG-12A-S08-A070 | FF | 2 | Within package (ladder)
UG-12A-S02-A070 | UG-12A-S08-A070 | FS | 0 | Crew continuity, front F5
UG-12A-S08-A070 | UG-12A-S08-A080 | SS | 2 | Within package (ladder)
UG-12A-S08-A070 | UG-12A-S08-A080 | FF | 2 | Within package (ladder)
UG-12A-S02-A080 | UG-12A-S08-A080 | FS | 0 | Crew continuity, front F5
UG-12A-S08-A080 | UG-12A-S08-A090 | SS | 1 | Within package (ladder)
UG-12A-S08-A080 | UG-12A-S08-A090 | FF | 2 | Within package (ladder)
UG-12A-S08-A090 | UG-12A-S08-A100 | SS | 2 | Within package (ladder)
UG-12A-S08-A090 | UG-12A-S08-A100 | FF | 2 | Within package (ladder)
UG-12A-S02-A100 | UG-12A-S08-A100 | FS | 0 | Crew continuity, front F5
UG-12A-S08-A100 | UG-12A-S08-A110 | SS | 1 | Within package (ladder)
UG-12A-S08-A100 | UG-12A-S08-A110 | FF | 2 | Within package (ladder)
UG-12A-S07-A010 | UG-12A-S07-A020 | FS | 0 | Within package
UG-12A-S08-A030 | UG-12A-S07-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-12A-S07-A020 | UG-12A-S07-A030 | SS | 1 | Within package (ladder)
UG-12A-S07-A020 | UG-12A-S07-A030 | FF | 2 | Within package (ladder)
UG-12A-S07-A030 | UG-12A-S07-A040 | SS | 1 | Within package (ladder)
UG-12A-S07-A030 | UG-12A-S07-A040 | FF | 0 | Within package (ladder)
UG-12A-S07-A040 | UG-12A-S07-A050 | SS | 0 | Within package (ladder)
UG-12A-S07-A040 | UG-12A-S07-A050 | FF | 2 | Within package (ladder)
UG-12A-S07-A050 | UG-12A-S07-A060 | SS | 10 | Within package (ladder)
UG-12A-S07-A050 | UG-12A-S07-A060 | FF | 2 | Within package (ladder)
UG-06-S04-A100 | UG-12A-S07-A060 | FS | 0 | Deeper line first
UG-12A-S07-A060 | UG-12A-S07-A070 | SS | 1 | Within package (ladder)
UG-12A-S07-A060 | UG-12A-S07-A070 | FF | 2 | Within package (ladder)
UG-12A-S07-A070 | UG-12A-S07-A080 | SS | 2 | Within package (ladder)
UG-12A-S07-A070 | UG-12A-S07-A080 | FF | 2 | Within package (ladder)
UG-12A-S08-A080 | UG-12A-S07-A080 | FS | 0 | Tie-in laid as closure
UG-12A-S07-A080 | UG-12A-S07-A090 | SS | 2 | Within package (ladder)
UG-12A-S07-A080 | UG-12A-S07-A090 | FF | 2 | Within package (ladder)
UG-12A-S07-A090 | UG-12A-S07-A100 | SS | 2 | Within package (ladder)
UG-12A-S07-A090 | UG-12A-S07-A100 | FF | 2 | Within package (ladder)
UG-12A-S07-A100 | UG-12A-S07-A110 | SS | 1 | Within package (ladder)
UG-12A-S07-A100 | UG-12A-S07-A110 | FF | 2 | Within package (ladder)
UG-12A-S09-A010 | UG-12A-S09-A020 | FS | 0 | Within package
UG-12A-S10-A030 | UG-12A-S09-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-12A-S09-A020 | UG-12A-S09-A030 | SS | 1 | Within package (ladder)
UG-12A-S09-A020 | UG-12A-S09-A030 | FF | 2 | Within package (ladder)
UG-12A-S09-A030 | UG-12A-S09-A040 | SS | 1 | Within package (ladder)
UG-12A-S09-A030 | UG-12A-S09-A040 | FF | 0 | Within package (ladder)
UG-12A-S09-A040 | UG-12A-S09-A050 | SS | 0 | Within package (ladder)
UG-12A-S09-A040 | UG-12A-S09-A050 | FF | 2 | Within package (ladder)
UG-12A-S09-A050 | UG-12A-S09-A060 | SS | 10 | Within package (ladder)
UG-12A-S09-A050 | UG-12A-S09-A060 | FF | 2 | Within package (ladder)
UG-13A-S15-A100 | UG-12A-S09-A060 | FS | 0 | Deeper line first
UG-12A-S09-A060 | UG-12A-S09-A070 | SS | 1 | Within package (ladder)
UG-12A-S09-A060 | UG-12A-S09-A070 | FF | 2 | Within package (ladder)
UG-12A-S09-A070 | UG-12A-S09-A080 | SS | 2 | Within package (ladder)
UG-12A-S09-A070 | UG-12A-S09-A080 | FF | 2 | Within package (ladder)
UG-12A-S10-A080 | UG-12A-S09-A080 | FS | 0 | Tie-in laid as closure
UG-12A-S09-A080 | UG-12A-S09-A090 | SS | 2 | Within package (ladder)
UG-12A-S09-A080 | UG-12A-S09-A090 | FF | 2 | Within package (ladder)
UG-12A-S09-A090 | UG-12A-S09-A100 | SS | 2 | Within package (ladder)
UG-12A-S09-A090 | UG-12A-S09-A100 | FF | 2 | Within package (ladder)
UG-12A-S09-A100 | UG-12A-S09-A110 | SS | 1 | Within package (ladder)
UG-12A-S09-A100 | UG-12A-S09-A110 | FF | 2 | Within package (ladder)
UG-12A-S11-A010 | UG-12A-S11-A020 | FS | 0 | Within package
UG-12A-S12-A030 | UG-12A-S11-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-12A-S11-A020 | UG-12A-S11-A030 | SS | 1 | Within package (ladder)
UG-12A-S11-A020 | UG-12A-S11-A030 | FF | 2 | Within package (ladder)
UG-12A-S11-A030 | UG-12A-S11-A040 | SS | 1 | Within package (ladder)
UG-12A-S11-A030 | UG-12A-S11-A040 | FF | 0 | Within package (ladder)
UG-12A-S11-A040 | UG-12A-S11-A050 | SS | 0 | Within package (ladder)
UG-12A-S11-A040 | UG-12A-S11-A050 | FF | 2 | Within package (ladder)
UG-12A-S11-A050 | UG-12A-S11-A060 | SS | 10 | Within package (ladder)
UG-12A-S11-A050 | UG-12A-S11-A060 | FF | 2 | Within package (ladder)
UG-13-S03-A100 | UG-12A-S11-A060 | FS | 0 | Deeper line first
UG-12A-S11-A060 | UG-12A-S11-A070 | SS | 1 | Within package (ladder)
UG-12A-S11-A060 | UG-12A-S11-A070 | FF | 2 | Within package (ladder)
UG-12A-S11-A070 | UG-12A-S11-A080 | SS | 2 | Within package (ladder)
UG-12A-S11-A070 | UG-12A-S11-A080 | FF | 2 | Within package (ladder)
UG-12A-S12-A080 | UG-12A-S11-A080 | FS | 0 | Tie-in laid as closure
UG-12A-S11-A080 | UG-12A-S11-A090 | SS | 2 | Within package (ladder)
UG-12A-S11-A080 | UG-12A-S11-A090 | FF | 2 | Within package (ladder)
UG-12A-S11-A090 | UG-12A-S11-A100 | SS | 2 | Within package (ladder)
UG-12A-S11-A090 | UG-12A-S11-A100 | FF | 2 | Within package (ladder)
UG-12A-S11-A100 | UG-12A-S11-A110 | SS | 1 | Within package (ladder)
UG-12A-S11-A100 | UG-12A-S11-A110 | FF | 2 | Within package (ladder)
UG-11-S02-A010 | UG-11-S02-A020 | FS | 0 | Within package
UG-11-S02-A020 | UG-11-S02-A030 | SS | 1 | Within package (ladder)
UG-11-S02-A020 | UG-11-S02-A030 | FF | 2 | Within package (ladder)
UG-11-S02-A030 | UG-11-S02-A040 | SS | 2 | Within package (ladder)
UG-11-S02-A030 | UG-11-S02-A040 | FF | 2 | Within package (ladder)
UG-11-S02-A040 | UG-11-S02-A050 | SS | 2 | Within package (ladder)
UG-11-S02-A040 | UG-11-S02-A050 | FF | 2 | Within package (ladder)
UG-11-S02-A050 | UG-11-S02-A060 | SS | 10 | Within package (ladder)
UG-11-S02-A050 | UG-11-S02-A060 | FF | 2 | Within package (ladder)
UG-11-S02-A060 | UG-11-S02-A070 | SS | 1 | Within package (ladder)
UG-11-S02-A060 | UG-11-S02-A070 | FF | 2 | Within package (ladder)
UG-11-S02-A070 | UG-11-S02-A080 | SS | 3 | Within package (ladder)
UG-11-S02-A070 | UG-11-S02-A080 | FF | 2 | Within package (ladder)
UG-11-S02-A080 | UG-11-S02-A090 | SS | 2 | Within package (ladder)
UG-11-S02-A080 | UG-11-S02-A090 | FF | 2 | Within package (ladder)
UG-11-S02-A090 | UG-11-S02-A100 | SS | 2 | Within package (ladder)
UG-11-S02-A090 | UG-11-S02-A100 | FF | 2 | Within package (ladder)
UG-11A-S05-A080 | UG-11-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11-S02-A100 | UG-11-S02-A110 | SS | 1 | Within package (ladder)
UG-11-S02-A100 | UG-11-S02-A110 | FF | 2 | Within package (ladder)
UG-11A-S05-A010 | UG-11A-S05-A020 | FS | 0 | Within package
UG-11-S02-A030 | UG-11A-S05-A020 | SS | 0 | Set-out one package ahead of piling
UG-11A-S05-A020 | UG-11A-S05-A030 | SS | 1 | Within package (ladder)
UG-11A-S05-A020 | UG-11A-S05-A030 | FF | 2 | Within package (ladder)
UG-11-S02-A030 | UG-11A-S05-A030 | FS | 0 | Crew continuity, front F6
UG-11A-S05-A030 | UG-11A-S05-A040 | SS | 3 | Within package (ladder)
UG-11A-S05-A030 | UG-11A-S05-A040 | FF | 2 | Within package (ladder)
UG-11-S02-A040 | UG-11A-S05-A040 | FS | 0 | Crew continuity, front F6
UG-11A-S05-A040 | UG-11A-S05-A050 | SS | 2 | Within package (ladder)
UG-11A-S05-A040 | UG-11A-S05-A050 | FF | 2 | Within package (ladder)
UG-11-S02-A060 | UG-11A-S05-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11A-S05-A050 | UG-11A-S05-A060 | SS | 10 | Within package (ladder)
UG-11A-S05-A050 | UG-11A-S05-A060 | FF | 2 | Within package (ladder)
UG-11-S02-A060 | UG-11A-S05-A060 | FS | 0 | Crew continuity, front F6
UG-11-S02-A060 | UG-11A-S05-A060 | SS | 0 | Shared excavation / dewatering front
UG-11A-S05-A060 | UG-11A-S05-A070 | SS | 1 | Within package (ladder)
UG-11A-S05-A060 | UG-11A-S05-A070 | FF | 2 | Within package (ladder)
UG-11-S02-A070 | UG-11A-S05-A070 | FS | 0 | Crew continuity, front F6
UG-11A-S05-A070 | UG-11A-S05-A080 | SS | 3 | Within package (ladder)
UG-11A-S05-A070 | UG-11A-S05-A080 | FF | 2 | Within package (ladder)
UG-11-S02-A080 | UG-11A-S05-A080 | FS | 0 | Crew continuity, front F6
UG-11A-S05-A080 | UG-11A-S05-A090 | SS | 1 | Within package (ladder)
UG-11A-S05-A080 | UG-11A-S05-A090 | FF | 2 | Within package (ladder)
UG-11A-S05-A090 | UG-11A-S05-A100 | SS | 2 | Within package (ladder)
UG-11A-S05-A090 | UG-11A-S05-A100 | FF | 2 | Within package (ladder)
UG-11-S02-A100 | UG-11A-S05-A100 | FS | 0 | Crew continuity, front F6
UG-11-S02-A080 | UG-11A-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11A-S05-A100 | UG-11A-S05-A110 | SS | 1 | Within package (ladder)
UG-11A-S05-A100 | UG-11A-S05-A110 | FF | 2 | Within package (ladder)
UG-11-S06-A010 | UG-11-S06-A020 | FS | 0 | Within package
UG-11A-S05-A030 | UG-11-S06-A020 | SS | 0 | Set-out one package ahead of piling
UG-11-S06-A020 | UG-11-S06-A030 | SS | 1 | Within package (ladder)
UG-11-S06-A020 | UG-11-S06-A030 | FF | 2 | Within package (ladder)
UG-11A-S05-A030 | UG-11-S06-A030 | FS | 0 | Crew continuity, front F6
UG-11-S06-A030 | UG-11-S06-A040 | SS | 3 | Within package (ladder)
UG-11-S06-A030 | UG-11-S06-A040 | FF | 2 | Within package (ladder)
UG-11A-S05-A040 | UG-11-S06-A040 | FS | 0 | Crew continuity, front F6
UG-11-S06-A040 | UG-11-S06-A050 | SS | 2 | Within package (ladder)
UG-11-S06-A040 | UG-11-S06-A050 | FF | 2 | Within package (ladder)
UG-11A-S05-A060 | UG-11-S06-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11-S06-A050 | UG-11-S06-A060 | SS | 10 | Within package (ladder)
UG-11-S06-A050 | UG-11-S06-A060 | FF | 2 | Within package (ladder)
UG-11A-S05-A060 | UG-11-S06-A060 | FS | 0 | Crew continuity, front F6
UG-11-S06-A060 | UG-11-S06-A070 | SS | 2 | Within package (ladder)
UG-11-S06-A060 | UG-11-S06-A070 | FF | 2 | Within package (ladder)
UG-11A-S05-A070 | UG-11-S06-A070 | FS | 0 | Crew continuity, front F6
UG-11-S06-A070 | UG-11-S06-A080 | SS | 3 | Within package (ladder)
UG-11-S06-A070 | UG-11-S06-A080 | FF | 2 | Within package (ladder)
UG-11A-S05-A080 | UG-11-S06-A080 | FS | 0 | Crew continuity, front F6
UG-11-S06-A080 | UG-11-S06-A090 | SS | 2 | Within package (ladder)
UG-11-S06-A080 | UG-11-S06-A090 | FF | 2 | Within package (ladder)
UG-11-S06-A090 | UG-11-S06-A100 | SS | 2 | Within package (ladder)
UG-11-S06-A090 | UG-11-S06-A100 | FF | 2 | Within package (ladder)
UG-11A-S05-A100 | UG-11-S06-A100 | FS | 0 | Crew continuity, front F6
UG-11-S06-A100 | UG-11-S06-A110 | SS | 2 | Within package (ladder)
UG-11-S06-A100 | UG-11-S06-A110 | FF | 2 | Within package (ladder)
UG-11-S05-A010 | UG-11-S05-A020 | FS | 0 | Within package
UG-11-S06-A030 | UG-11-S05-A020 | SS | 0 | Set-out one package ahead of piling
UG-11-S05-A020 | UG-11-S05-A030 | SS | 1 | Within package (ladder)
UG-11-S05-A020 | UG-11-S05-A030 | FF | 2 | Within package (ladder)
UG-11-S06-A030 | UG-11-S05-A030 | FS | 0 | Crew continuity, front F6
UG-11-S05-A030 | UG-11-S05-A040 | SS | 3 | Within package (ladder)
UG-11-S05-A030 | UG-11-S05-A040 | FF | 2 | Within package (ladder)
UG-11-S06-A040 | UG-11-S05-A040 | FS | 0 | Crew continuity, front F6
UG-11-S05-A040 | UG-11-S05-A050 | SS | 2 | Within package (ladder)
UG-11-S05-A040 | UG-11-S05-A050 | FF | 2 | Within package (ladder)
UG-11-S06-A060 | UG-11-S05-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11-S05-A050 | UG-11-S05-A060 | SS | 10 | Within package (ladder)
UG-11-S05-A050 | UG-11-S05-A060 | FF | 2 | Within package (ladder)
UG-11-S06-A060 | UG-11-S05-A060 | FS | 0 | Crew continuity, front F6
UG-11-S05-A060 | UG-11-S05-A070 | SS | 2 | Within package (ladder)
UG-11-S05-A060 | UG-11-S05-A070 | FF | 2 | Within package (ladder)
UG-11-S06-A070 | UG-11-S05-A070 | FS | 0 | Crew continuity, front F6
UG-11-S05-A070 | UG-11-S05-A080 | SS | 3 | Within package (ladder)
UG-11-S05-A070 | UG-11-S05-A080 | FF | 2 | Within package (ladder)
UG-11-S06-A080 | UG-11-S05-A080 | FS | 0 | Crew continuity, front F6
UG-11-S05-A080 | UG-11-S05-A090 | SS | 2 | Within package (ladder)
UG-11-S05-A080 | UG-11-S05-A090 | FF | 2 | Within package (ladder)
UG-11-S05-A090 | UG-11-S05-A100 | SS | 2 | Within package (ladder)
UG-11-S05-A090 | UG-11-S05-A100 | FF | 2 | Within package (ladder)
UG-11-S06-A100 | UG-11-S05-A100 | FS | 0 | Crew continuity, front F6
UG-11-S05-A100 | UG-11-S05-A110 | SS | 2 | Within package (ladder)
UG-11-S05-A100 | UG-11-S05-A110 | FF | 2 | Within package (ladder)
UG-11-S04-A010 | UG-11-S04-A020 | FS | 0 | Within package
UG-11-S05-A030 | UG-11-S04-A020 | SS | 0 | Set-out one package ahead of piling
UG-11-S04-A020 | UG-11-S04-A030 | SS | 1 | Within package (ladder)
UG-11-S04-A020 | UG-11-S04-A030 | FF | 2 | Within package (ladder)
UG-11-S05-A030 | UG-11-S04-A030 | FS | 0 | Crew continuity, front F6
UG-11-S04-A030 | UG-11-S04-A040 | SS | 2 | Within package (ladder)
UG-11-S04-A030 | UG-11-S04-A040 | FF | 2 | Within package (ladder)
UG-11-S05-A040 | UG-11-S04-A040 | FS | 0 | Crew continuity, front F6
UG-11-S04-A040 | UG-11-S04-A050 | SS | 1 | Within package (ladder)
UG-11-S04-A040 | UG-11-S04-A050 | FF | 2 | Within package (ladder)
UG-11-S05-A060 | UG-11-S04-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11-S04-A050 | UG-11-S04-A060 | SS | 10 | Within package (ladder)
UG-11-S04-A050 | UG-11-S04-A060 | FF | 2 | Within package (ladder)
UG-11-S05-A060 | UG-11-S04-A060 | FS | 0 | Crew continuity, front F6
UG-11-S04-A060 | UG-11-S04-A070 | SS | 2 | Within package (ladder)
UG-11-S04-A060 | UG-11-S04-A070 | FF | 2 | Within package (ladder)
UG-11-S05-A070 | UG-11-S04-A070 | FS | 0 | Crew continuity, front F6
UG-11-S04-A070 | UG-11-S04-A080 | SS | 2 | Within package (ladder)
UG-11-S04-A070 | UG-11-S04-A080 | FF | 2 | Within package (ladder)
UG-11-S05-A080 | UG-11-S04-A080 | FS | 0 | Crew continuity, front F6
UG-11-S04-A080 | UG-11-S04-A090 | SS | 1 | Within package (ladder)
UG-11-S04-A080 | UG-11-S04-A090 | FF | 2 | Within package (ladder)
UG-11-S04-A090 | UG-11-S04-A100 | SS | 2 | Within package (ladder)
UG-11-S04-A090 | UG-11-S04-A100 | FF | 2 | Within package (ladder)
UG-11-S05-A100 | UG-11-S04-A100 | FS | 0 | Crew continuity, front F6
UG-11-S04-A100 | UG-11-S04-A110 | SS | 1 | Within package (ladder)
UG-11-S04-A100 | UG-11-S04-A110 | FF | 2 | Within package (ladder)
UG-11-S03-A010 | UG-11-S03-A020 | FS | 0 | Within package
UG-11-S04-A030 | UG-11-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-11-S03-A020 | UG-11-S03-A030 | SS | 1 | Within package (ladder)
UG-11-S03-A020 | UG-11-S03-A030 | FF | 2 | Within package (ladder)
UG-11-S04-A030 | UG-11-S03-A030 | FS | 0 | Crew continuity, front F6
UG-11-S03-A030 | UG-11-S03-A040 | SS | 2 | Within package (ladder)
UG-11-S03-A030 | UG-11-S03-A040 | FF | 2 | Within package (ladder)
UG-11-S04-A040 | UG-11-S03-A040 | FS | 0 | Crew continuity, front F6
UG-11-S03-A040 | UG-11-S03-A050 | SS | 1 | Within package (ladder)
UG-11-S03-A040 | UG-11-S03-A050 | FF | 2 | Within package (ladder)
UG-11-S04-A060 | UG-11-S03-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11-S03-A050 | UG-11-S03-A060 | SS | 10 | Within package (ladder)
UG-11-S03-A050 | UG-11-S03-A060 | FF | 2 | Within package (ladder)
UG-11-S04-A060 | UG-11-S03-A060 | FS | 0 | Crew continuity, front F6
UG-11-S03-A060 | UG-11-S03-A070 | SS | 2 | Within package (ladder)
UG-11-S03-A060 | UG-11-S03-A070 | FF | 2 | Within package (ladder)
UG-11-S04-A070 | UG-11-S03-A070 | FS | 0 | Crew continuity, front F6
UG-11-S03-A070 | UG-11-S03-A080 | SS | 2 | Within package (ladder)
UG-11-S03-A070 | UG-11-S03-A080 | FF | 2 | Within package (ladder)
UG-11-S04-A080 | UG-11-S03-A080 | FS | 0 | Crew continuity, front F6
UG-11-S03-A080 | UG-11-S03-A090 | SS | 1 | Within package (ladder)
UG-11-S03-A080 | UG-11-S03-A090 | FF | 2 | Within package (ladder)
UG-11-S03-A090 | UG-11-S03-A100 | SS | 2 | Within package (ladder)
UG-11-S03-A090 | UG-11-S03-A100 | FF | 2 | Within package (ladder)
UG-11-S04-A100 | UG-11-S03-A100 | FS | 0 | Crew continuity, front F6
UG-11-S03-A100 | UG-11-S03-A110 | SS | 1 | Within package (ladder)
UG-11-S03-A100 | UG-11-S03-A110 | FF | 2 | Within package (ladder)
UG-23-S09-A010 | UG-23-S09-A020 | FS | 0 | Within package
UG-11-S03-A030 | UG-23-S09-A020 | SS | 0 | Set-out one package ahead of piling
UG-23-S09-A020 | UG-23-S09-A030 | SS | 1 | Within package (ladder)
UG-23-S09-A020 | UG-23-S09-A030 | FF | 2 | Within package (ladder)
UG-11-S03-A030 | UG-23-S09-A030 | FS | 0 | Crew continuity, front F6
UG-23-S09-A030 | UG-23-S09-A040 | SS | 3 | Within package (ladder)
UG-23-S09-A030 | UG-23-S09-A040 | FF | 0 | Within package (ladder)
UG-11-S03-A040 | UG-23-S09-A040 | FS | 0 | Crew continuity, front F6
UG-23-S09-A040 | UG-23-S09-A050 | SS | 0 | Within package (ladder)
UG-23-S09-A040 | UG-23-S09-A050 | FF | 2 | Within package (ladder)
UG-11-S03-A060 | UG-23-S09-A050 | FS | -12 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-23-S09-A050 | UG-23-S09-A060 | SS | 10 | Within package (ladder)
UG-23-S09-A050 | UG-23-S09-A060 | FF | 2 | Within package (ladder)
UG-11-S03-A060 | UG-23-S09-A060 | FS | 0 | Crew continuity, front F6
UG-23-S09-A060 | UG-23-S09-A070 | SS | 1 | Within package (ladder)
UG-23-S09-A060 | UG-23-S09-A070 | FF | 2 | Within package (ladder)
UG-11-S03-A070 | UG-23-S09-A070 | FS | 0 | Crew continuity, front F6
UG-23-S09-A070 | UG-23-S09-A080 | SS | 4 | Within package (ladder)
UG-23-S09-A070 | UG-23-S09-A080 | FF | 2 | Within package (ladder)
UG-11-S03-A080 | UG-23-S09-A080 | FS | 0 | Crew continuity, front F6
UG-23-S09-A080 | UG-23-S09-A090 | SS | 2 | Within package (ladder)
UG-23-S09-A080 | UG-23-S09-A090 | FF | 2 | Within package (ladder)
UG-23-S09-A090 | UG-23-S09-A100 | SS | 2 | Within package (ladder)
UG-23-S09-A090 | UG-23-S09-A100 | FF | 2 | Within package (ladder)
UG-11-S03-A100 | UG-23-S09-A100 | FS | 0 | Crew continuity, front F6
UG-23-S09-A100 | UG-23-S09-A110 | SS | 1 | Within package (ladder)
UG-23-S09-A100 | UG-23-S09-A110 | FF | 2 | Within package (ladder)
UG-23-S10-A010 | UG-23-S10-A020 | FS | 0 | Within package
UG-23-S09-A030 | UG-23-S10-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-23-S10-A020 | UG-23-S10-A030 | SS | 1 | Within package (ladder)
UG-23-S10-A020 | UG-23-S10-A030 | FF | 2 | Within package (ladder)
UG-23-S10-A030 | UG-23-S10-A040 | SS | 1 | Within package (ladder)
UG-23-S10-A030 | UG-23-S10-A040 | FF | 0 | Within package (ladder)
UG-23-S10-A040 | UG-23-S10-A050 | SS | 0 | Within package (ladder)
UG-23-S10-A040 | UG-23-S10-A050 | FF | 2 | Within package (ladder)
UG-23-S10-A050 | UG-23-S10-A060 | SS | 10 | Within package (ladder)
UG-23-S10-A050 | UG-23-S10-A060 | FF | 2 | Within package (ladder)
UG-23-S10-A060 | UG-23-S10-A070 | SS | 1 | Within package (ladder)
UG-23-S10-A060 | UG-23-S10-A070 | FF | 2 | Within package (ladder)
UG-23-S10-A070 | UG-23-S10-A080 | SS | 2 | Within package (ladder)
UG-23-S10-A070 | UG-23-S10-A080 | FF | 2 | Within package (ladder)
UG-23-S09-A080 | UG-23-S10-A080 | FS | 0 | Tie-in laid as closure
UG-23-S10-A080 | UG-23-S10-A090 | SS | 2 | Within package (ladder)
UG-23-S10-A080 | UG-23-S10-A090 | FF | 2 | Within package (ladder)
UG-23-S10-A090 | UG-23-S10-A100 | SS | 2 | Within package (ladder)
UG-23-S10-A090 | UG-23-S10-A100 | FF | 2 | Within package (ladder)
UG-23-S10-A100 | UG-23-S10-A110 | SS | 1 | Within package (ladder)
UG-23-S10-A100 | UG-23-S10-A110 | FF | 2 | Within package (ladder)
UG-23-S08-A010 | UG-23-S08-A020 | FS | 0 | Within package
UG-23-S09-A030 | UG-23-S08-A020 | SS | 0 | Set-out one package ahead of piling
UG-23-S08-A020 | UG-23-S08-A030 | SS | 1 | Within package (ladder)
UG-23-S08-A020 | UG-23-S08-A030 | FF | 2 | Within package (ladder)
UG-23-S09-A030 | UG-23-S08-A030 | FS | 0 | Crew continuity, front F6
UG-23-S08-A030 | UG-23-S08-A040 | SS | 2 | Within package (ladder)
UG-23-S08-A030 | UG-23-S08-A040 | FF | 0 | Within package (ladder)
UG-23-S09-A040 | UG-23-S08-A040 | FS | 0 | Crew continuity, front F6
UG-23-S08-A040 | UG-23-S08-A050 | SS | 0 | Within package (ladder)
UG-23-S08-A040 | UG-23-S08-A050 | FF | 2 | Within package (ladder)
UG-23-S09-A060 | UG-23-S08-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-23-S08-A050 | UG-23-S08-A060 | SS | 10 | Within package (ladder)
UG-23-S08-A050 | UG-23-S08-A060 | FF | 2 | Within package (ladder)
UG-23-S09-A060 | UG-23-S08-A060 | FS | 0 | Crew continuity, front F6
UG-11-S01-A100 | UG-23-S08-A060 | FS | 0 | Deeper line first
UG-11-S02-A100 | UG-23-S08-A060 | FS | 0 | Deeper line first
UG-11B-S14-A100 | UG-23-S08-A060 | FS | 0 | Deeper line first
UG-23-S08-A060 | UG-23-S08-A070 | SS | 1 | Within package (ladder)
UG-23-S08-A060 | UG-23-S08-A070 | FF | 2 | Within package (ladder)
UG-23-S09-A070 | UG-23-S08-A070 | FS | 0 | Crew continuity, front F6
UG-23-S08-A070 | UG-23-S08-A080 | SS | 3 | Within package (ladder)
UG-23-S08-A070 | UG-23-S08-A080 | FF | 2 | Within package (ladder)
UG-23-S09-A080 | UG-23-S08-A080 | FS | 0 | Crew continuity, front F6
UG-23-S08-A080 | UG-23-S08-A090 | SS | 1 | Within package (ladder)
UG-23-S08-A080 | UG-23-S08-A090 | FF | 2 | Within package (ladder)
UG-23-S08-A090 | UG-23-S08-A100 | SS | 2 | Within package (ladder)
UG-23-S08-A090 | UG-23-S08-A100 | FF | 2 | Within package (ladder)
UG-23-S09-A100 | UG-23-S08-A100 | FS | 0 | Crew continuity, front F6
UG-23-S08-A100 | UG-23-S08-A110 | SS | 1 | Within package (ladder)
UG-23-S08-A100 | UG-23-S08-A110 | FF | 2 | Within package (ladder)
UG-23-S07-A010 | UG-23-S07-A020 | FS | 0 | Within package
UG-23-S08-A030 | UG-23-S07-A020 | SS | 0 | Set-out one package ahead of piling
UG-23-S07-A020 | UG-23-S07-A030 | SS | 1 | Within package (ladder)
UG-23-S07-A020 | UG-23-S07-A030 | FF | 2 | Within package (ladder)
UG-23-S08-A030 | UG-23-S07-A030 | FS | 0 | Crew continuity, front F6
UG-23-S07-A030 | UG-23-S07-A040 | SS | 1 | Within package (ladder)
UG-23-S07-A030 | UG-23-S07-A040 | FF | 0 | Within package (ladder)
UG-23-S08-A040 | UG-23-S07-A040 | FS | 0 | Crew continuity, front F6
UG-23-S07-A040 | UG-23-S07-A050 | SS | 0 | Within package (ladder)
UG-23-S07-A040 | UG-23-S07-A050 | FF | 2 | Within package (ladder)
UG-23-S08-A060 | UG-23-S07-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-23-S07-A050 | UG-23-S07-A060 | SS | 10 | Within package (ladder)
UG-23-S07-A050 | UG-23-S07-A060 | FF | 2 | Within package (ladder)
UG-23-S08-A060 | UG-23-S07-A060 | FS | 0 | Crew continuity, front F6
UG-07-S03-A100 | UG-23-S07-A060 | FS | 0 | Deeper line first
UG-11-S01-A100 | UG-23-S07-A060 | FS | 0 | Deeper line first
UG-11-S06-A100 | UG-23-S07-A060 | FS | 0 | Deeper line first
UG-12-S07-A100 | UG-23-S07-A060 | FS | 0 | Deeper line first
UG-23-S07-A060 | UG-23-S07-A070 | SS | 1 | Within package (ladder)
UG-23-S07-A060 | UG-23-S07-A070 | FF | 2 | Within package (ladder)
UG-23-S08-A070 | UG-23-S07-A070 | FS | 0 | Crew continuity, front F6
UG-23-S07-A070 | UG-23-S07-A080 | SS | 2 | Within package (ladder)
UG-23-S07-A070 | UG-23-S07-A080 | FF | 2 | Within package (ladder)
UG-23-S08-A080 | UG-23-S07-A080 | FS | 0 | Crew continuity, front F6
UG-23-S07-A080 | UG-23-S07-A090 | SS | 1 | Within package (ladder)
UG-23-S07-A080 | UG-23-S07-A090 | FF | 2 | Within package (ladder)
UG-23-S07-A090 | UG-23-S07-A100 | SS | 2 | Within package (ladder)
UG-23-S07-A090 | UG-23-S07-A100 | FF | 2 | Within package (ladder)
UG-23-S08-A100 | UG-23-S07-A100 | FS | 0 | Crew continuity, front F6
UG-23-S07-A100 | UG-23-S07-A110 | SS | 1 | Within package (ladder)
UG-23-S07-A100 | UG-23-S07-A110 | FF | 2 | Within package (ladder)
UG-23-S06-A010 | UG-23-S06-A020 | FS | 0 | Within package
UG-23-S07-A030 | UG-23-S06-A020 | SS | 0 | Set-out one package ahead of piling
UG-23-S06-A020 | UG-23-S06-A030 | SS | 1 | Within package (ladder)
UG-23-S06-A020 | UG-23-S06-A030 | FF | 2 | Within package (ladder)
UG-23-S07-A030 | UG-23-S06-A030 | FS | 0 | Crew continuity, front F6
UG-23-S06-A030 | UG-23-S06-A040 | SS | 2 | Within package (ladder)
UG-23-S06-A030 | UG-23-S06-A040 | FF | 2 | Within package (ladder)
UG-23-S07-A040 | UG-23-S06-A040 | FS | 0 | Crew continuity, front F6
UG-23-S06-A040 | UG-23-S06-A050 | SS | 1 | Within package (ladder)
UG-23-S06-A040 | UG-23-S06-A050 | FF | 2 | Within package (ladder)
UG-23-S07-A060 | UG-23-S06-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-23-S06-A050 | UG-23-S06-A060 | SS | 10 | Within package (ladder)
UG-23-S06-A050 | UG-23-S06-A060 | FF | 2 | Within package (ladder)
UG-23-S07-A060 | UG-23-S06-A060 | FS | 0 | Crew continuity, front F6
UG-07-S03-A100 | UG-23-S06-A060 | FS | 0 | Deeper line first
UG-11-S05-A100 | UG-23-S06-A060 | FS | 0 | Deeper line first
UG-11-S06-A100 | UG-23-S06-A060 | FS | 0 | Deeper line first
UG-12-S07-A100 | UG-23-S06-A060 | FS | 0 | Deeper line first
UG-23-S06-A060 | UG-23-S06-A070 | SS | 1 | Within package (ladder)
UG-23-S06-A060 | UG-23-S06-A070 | FF | 2 | Within package (ladder)
UG-23-S07-A070 | UG-23-S06-A070 | FS | 0 | Crew continuity, front F6
UG-23-S06-A070 | UG-23-S06-A080 | SS | 3 | Within package (ladder)
UG-23-S06-A070 | UG-23-S06-A080 | FF | 2 | Within package (ladder)
UG-23-S07-A080 | UG-23-S06-A080 | FS | 0 | Crew continuity, front F6
UG-23-S06-A080 | UG-23-S06-A090 | SS | 3 | Within package (ladder)
UG-23-S06-A080 | UG-23-S06-A090 | FF | 2 | Within package (ladder)
UG-23-S06-A090 | UG-23-S06-A100 | SS | 2 | Within package (ladder)
UG-23-S06-A090 | UG-23-S06-A100 | FF | 2 | Within package (ladder)
UG-23-S07-A100 | UG-23-S06-A100 | FS | 0 | Crew continuity, front F6
UG-23-S06-A100 | UG-23-S06-A110 | SS | 1 | Within package (ladder)
UG-23-S06-A100 | UG-23-S06-A110 | FF | 2 | Within package (ladder)
UG-23-S05-A010 | UG-23-S05-A020 | FS | 0 | Within package
UG-23-S06-A030 | UG-23-S05-A020 | SS | 0 | Set-out one package ahead of piling
UG-23-S05-A020 | UG-23-S05-A030 | SS | 1 | Within package (ladder)
UG-23-S05-A020 | UG-23-S05-A030 | FF | 2 | Within package (ladder)
UG-23-S06-A030 | UG-23-S05-A030 | FS | 0 | Crew continuity, front F6
UG-23-S05-A030 | UG-23-S05-A040 | SS | 2 | Within package (ladder)
UG-23-S05-A030 | UG-23-S05-A040 | FF | 2 | Within package (ladder)
UG-23-S06-A040 | UG-23-S05-A040 | FS | 0 | Crew continuity, front F6
UG-23-S05-A040 | UG-23-S05-A050 | SS | 2 | Within package (ladder)
UG-23-S05-A040 | UG-23-S05-A050 | FF | 2 | Within package (ladder)
UG-23-S06-A060 | UG-23-S05-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-23-S05-A050 | UG-23-S05-A060 | SS | 10 | Within package (ladder)
UG-23-S05-A050 | UG-23-S05-A060 | FF | 2 | Within package (ladder)
UG-23-S06-A060 | UG-23-S05-A060 | FS | 0 | Crew continuity, front F6
UG-23-S05-A060 | UG-23-S05-A070 | SS | 1 | Within package (ladder)
UG-23-S05-A060 | UG-23-S05-A070 | FF | 2 | Within package (ladder)
UG-23-S06-A070 | UG-23-S05-A070 | FS | 0 | Crew continuity, front F6
UG-23-S05-A070 | UG-23-S05-A080 | SS | 3 | Within package (ladder)
UG-23-S05-A070 | UG-23-S05-A080 | FF | 2 | Within package (ladder)
UG-23-S06-A080 | UG-23-S05-A080 | FS | 0 | Crew continuity, front F6
UG-23-S05-A080 | UG-23-S05-A090 | SS | 2 | Within package (ladder)
UG-23-S05-A080 | UG-23-S05-A090 | FF | 2 | Within package (ladder)
UG-23-S05-A090 | UG-23-S05-A100 | SS | 2 | Within package (ladder)
UG-23-S05-A090 | UG-23-S05-A100 | FF | 2 | Within package (ladder)
UG-23-S06-A100 | UG-23-S05-A100 | FS | 0 | Crew continuity, front F6
UG-23-S05-A100 | UG-23-S05-A110 | SS | 1 | Within package (ladder)
UG-23-S05-A100 | UG-23-S05-A110 | FF | 2 | Within package (ladder)
UG-23-S04-A010 | UG-23-S04-A020 | FS | 0 | Within package
UG-23-S05-A030 | UG-23-S04-A020 | SS | 0 | Set-out one package ahead of piling
UG-23-S04-A020 | UG-23-S04-A030 | SS | 1 | Within package (ladder)
UG-23-S04-A020 | UG-23-S04-A030 | FF | 2 | Within package (ladder)
UG-23-S05-A030 | UG-23-S04-A030 | FS | 0 | Crew continuity, front F6
UG-23-S04-A030 | UG-23-S04-A040 | SS | 1 | Within package (ladder)
UG-23-S04-A030 | UG-23-S04-A040 | FF | 2 | Within package (ladder)
UG-23-S05-A040 | UG-23-S04-A040 | FS | 0 | Crew continuity, front F6
UG-23-S04-A040 | UG-23-S04-A050 | SS | 1 | Within package (ladder)
UG-23-S04-A040 | UG-23-S04-A050 | FF | 2 | Within package (ladder)
UG-23-S05-A060 | UG-23-S04-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-23-S04-A050 | UG-23-S04-A060 | SS | 10 | Within package (ladder)
UG-23-S04-A050 | UG-23-S04-A060 | FF | 2 | Within package (ladder)
UG-23-S05-A060 | UG-23-S04-A060 | FS | 0 | Crew continuity, front F6
UG-11-S04-A100 | UG-23-S04-A060 | FS | 0 | Deeper line first
UG-11-S05-A100 | UG-23-S04-A060 | FS | 0 | Deeper line first
UG-23-S04-A060 | UG-23-S04-A070 | SS | 1 | Within package (ladder)
UG-23-S04-A060 | UG-23-S04-A070 | FF | 2 | Within package (ladder)
UG-23-S05-A070 | UG-23-S04-A070 | FS | 0 | Crew continuity, front F6
UG-23-S04-A070 | UG-23-S04-A080 | SS | 2 | Within package (ladder)
UG-23-S04-A070 | UG-23-S04-A080 | FF | 2 | Within package (ladder)
UG-23-S05-A080 | UG-23-S04-A080 | FS | 0 | Crew continuity, front F6
UG-23-S04-A080 | UG-23-S04-A090 | SS | 1 | Within package (ladder)
UG-23-S04-A080 | UG-23-S04-A090 | FF | 2 | Within package (ladder)
UG-23-S04-A090 | UG-23-S04-A100 | SS | 2 | Within package (ladder)
UG-23-S04-A090 | UG-23-S04-A100 | FF | 2 | Within package (ladder)
UG-23-S05-A100 | UG-23-S04-A100 | FS | 0 | Crew continuity, front F6
UG-23-S04-A100 | UG-23-S04-A110 | SS | 1 | Within package (ladder)
UG-23-S04-A100 | UG-23-S04-A110 | FF | 2 | Within package (ladder)
UG-11B-S07-A010 | UG-11B-S07-A020 | FS | 0 | Within package
UG-23-S04-A030 | UG-11B-S07-A020 | SS | 0 | Set-out one package ahead of piling
UG-11B-S07-A020 | UG-11B-S07-A030 | SS | 1 | Within package (ladder)
UG-11B-S07-A020 | UG-11B-S07-A030 | FF | 2 | Within package (ladder)
UG-23-S04-A030 | UG-11B-S07-A030 | FS | 0 | Crew continuity, front F6
UG-11B-S07-A030 | UG-11B-S07-A040 | SS | 5 | Within package (ladder)
UG-11B-S07-A030 | UG-11B-S07-A040 | FF | 2 | Within package (ladder)
UG-23-S04-A040 | UG-11B-S07-A040 | FS | 0 | Crew continuity, front F6
UG-11B-S07-A040 | UG-11B-S07-A050 | SS | 3 | Within package (ladder)
UG-11B-S07-A040 | UG-11B-S07-A050 | FF | 2 | Within package (ladder)
UG-23-S04-A060 | UG-11B-S07-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11B-S07-A050 | UG-11B-S07-A060 | SS | 10 | Within package (ladder)
UG-11B-S07-A050 | UG-11B-S07-A060 | FF | 2 | Within package (ladder)
UG-23-S04-A060 | UG-11B-S07-A060 | FS | 0 | Crew continuity, front F6
UG-11B-S07-A060 | UG-11B-S07-A070 | SS | 2 | Within package (ladder)
UG-11B-S07-A060 | UG-11B-S07-A070 | FF | 2 | Within package (ladder)
UG-23-S04-A070 | UG-11B-S07-A070 | FS | 0 | Crew continuity, front F6
UG-11B-S07-A070 | UG-11B-S07-A080 | SS | 4 | Within package (ladder)
UG-11B-S07-A070 | UG-11B-S07-A080 | FF | 2 | Within package (ladder)
UG-23-S04-A080 | UG-11B-S07-A080 | FS | 0 | Crew continuity, front F6
UG-11B-S07-A080 | UG-11B-S07-A090 | SS | 3 | Within package (ladder)
UG-11B-S07-A080 | UG-11B-S07-A090 | FF | 2 | Within package (ladder)
UG-11B-S07-A090 | UG-11B-S07-A100 | SS | 2 | Within package (ladder)
UG-11B-S07-A090 | UG-11B-S07-A100 | FF | 2 | Within package (ladder)
UG-23-S04-A100 | UG-11B-S07-A100 | FS | 0 | Crew continuity, front F6
UG-11B-S07-A100 | UG-11B-S07-A110 | SS | 1 | Within package (ladder)
UG-11B-S07-A100 | UG-11B-S07-A110 | FF | 2 | Within package (ladder)
UG-11B-S04-A010 | UG-11B-S04-A020 | FS | 0 | Within package
UG-11B-S07-A030 | UG-11B-S04-A020 | SS | 0 | Set-out one package ahead of piling
UG-11B-S04-A020 | UG-11B-S04-A030 | SS | 1 | Within package (ladder)
UG-11B-S04-A020 | UG-11B-S04-A030 | FF | 2 | Within package (ladder)
UG-11B-S07-A030 | UG-11B-S04-A030 | FS | 0 | Crew continuity, front F6
UG-11B-S04-A030 | UG-11B-S04-A040 | SS | 3 | Within package (ladder)
UG-11B-S04-A030 | UG-11B-S04-A040 | FF | 2 | Within package (ladder)
UG-11B-S07-A040 | UG-11B-S04-A040 | FS | 0 | Crew continuity, front F6
UG-11B-S04-A040 | UG-11B-S04-A050 | SS | 2 | Within package (ladder)
UG-11B-S04-A040 | UG-11B-S04-A050 | FF | 2 | Within package (ladder)
UG-11B-S07-A060 | UG-11B-S04-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11B-S04-A050 | UG-11B-S04-A060 | SS | 10 | Within package (ladder)
UG-11B-S04-A050 | UG-11B-S04-A060 | FF | 2 | Within package (ladder)
UG-11B-S07-A060 | UG-11B-S04-A060 | FS | 0 | Crew continuity, front F6
UG-11B-S04-A060 | UG-11B-S04-A070 | SS | 2 | Within package (ladder)
UG-11B-S04-A060 | UG-11B-S04-A070 | FF | 2 | Within package (ladder)
UG-11B-S07-A070 | UG-11B-S04-A070 | FS | 0 | Crew continuity, front F6
UG-11B-S04-A070 | UG-11B-S04-A080 | SS | 3 | Within package (ladder)
UG-11B-S04-A070 | UG-11B-S04-A080 | FF | 2 | Within package (ladder)
UG-11B-S07-A080 | UG-11B-S04-A080 | FS | 0 | Crew continuity, front F6
UG-11B-S04-A080 | UG-11B-S04-A090 | SS | 2 | Within package (ladder)
UG-11B-S04-A080 | UG-11B-S04-A090 | FF | 2 | Within package (ladder)
UG-11B-S04-A090 | UG-11B-S04-A100 | SS | 2 | Within package (ladder)
UG-11B-S04-A090 | UG-11B-S04-A100 | FF | 2 | Within package (ladder)
UG-11B-S07-A100 | UG-11B-S04-A100 | FS | 0 | Crew continuity, front F6
UG-11B-S04-A100 | UG-11B-S04-A110 | SS | 1 | Within package (ladder)
UG-11B-S04-A100 | UG-11B-S04-A110 | FF | 2 | Within package (ladder)
UG-11B-S03-A010 | UG-11B-S03-A020 | FS | 0 | Within package
UG-11B-S04-A030 | UG-11B-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-11B-S03-A020 | UG-11B-S03-A030 | SS | 1 | Within package (ladder)
UG-11B-S03-A020 | UG-11B-S03-A030 | FF | 2 | Within package (ladder)
UG-11B-S04-A030 | UG-11B-S03-A030 | FS | 0 | Crew continuity, front F6
UG-11B-S03-A030 | UG-11B-S03-A040 | SS | 4 | Within package (ladder)
UG-11B-S03-A030 | UG-11B-S03-A040 | FF | 2 | Within package (ladder)
UG-11B-S04-A040 | UG-11B-S03-A040 | FS | 0 | Crew continuity, front F6
UG-11B-S03-A040 | UG-11B-S03-A050 | SS | 3 | Within package (ladder)
UG-11B-S03-A040 | UG-11B-S03-A050 | FF | 2 | Within package (ladder)
UG-11B-S04-A060 | UG-11B-S03-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11B-S03-A050 | UG-11B-S03-A060 | SS | 10 | Within package (ladder)
UG-11B-S03-A050 | UG-11B-S03-A060 | FF | 2 | Within package (ladder)
UG-11B-S04-A060 | UG-11B-S03-A060 | FS | 0 | Crew continuity, front F6
UG-11B-S03-A060 | UG-11B-S03-A070 | SS | 2 | Within package (ladder)
UG-11B-S03-A060 | UG-11B-S03-A070 | FF | 2 | Within package (ladder)
UG-11B-S04-A070 | UG-11B-S03-A070 | FS | 0 | Crew continuity, front F6
UG-11B-S03-A070 | UG-11B-S03-A080 | SS | 4 | Within package (ladder)
UG-11B-S03-A070 | UG-11B-S03-A080 | FF | 2 | Within package (ladder)
UG-11B-S04-A080 | UG-11B-S03-A080 | FS | 0 | Crew continuity, front F6
UG-11B-S03-A080 | UG-11B-S03-A090 | SS | 2 | Within package (ladder)
UG-11B-S03-A080 | UG-11B-S03-A090 | FF | 2 | Within package (ladder)
UG-11B-S03-A090 | UG-11B-S03-A100 | SS | 2 | Within package (ladder)
UG-11B-S03-A090 | UG-11B-S03-A100 | FF | 2 | Within package (ladder)
UG-11B-S04-A100 | UG-11B-S03-A100 | FS | 0 | Crew continuity, front F6
UG-11B-S03-A100 | UG-11B-S03-A110 | SS | 2 | Within package (ladder)
UG-11B-S03-A100 | UG-11B-S03-A110 | FF | 2 | Within package (ladder)
UG-11B-S02-A010 | UG-11B-S02-A020 | FS | 0 | Within package
UG-11B-S03-A030 | UG-11B-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-11B-S02-A020 | UG-11B-S02-A030 | SS | 1 | Within package (ladder)
UG-11B-S02-A020 | UG-11B-S02-A030 | FF | 2 | Within package (ladder)
UG-11B-S03-A030 | UG-11B-S02-A030 | FS | 0 | Crew continuity, front F6
UG-11B-S02-A030 | UG-11B-S02-A040 | SS | 3 | Within package (ladder)
UG-11B-S02-A030 | UG-11B-S02-A040 | FF | 2 | Within package (ladder)
UG-11B-S03-A040 | UG-11B-S02-A040 | FS | 0 | Crew continuity, front F6
UG-11B-S02-A040 | UG-11B-S02-A050 | SS | 2 | Within package (ladder)
UG-11B-S02-A040 | UG-11B-S02-A050 | FF | 2 | Within package (ladder)
UG-11B-S03-A060 | UG-11B-S02-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11B-S02-A050 | UG-11B-S02-A060 | SS | 10 | Within package (ladder)
UG-11B-S02-A050 | UG-11B-S02-A060 | FF | 2 | Within package (ladder)
UG-11B-S03-A060 | UG-11B-S02-A060 | FS | 0 | Crew continuity, front F6
UG-11B-S02-A060 | UG-11B-S02-A070 | SS | 2 | Within package (ladder)
UG-11B-S02-A060 | UG-11B-S02-A070 | FF | 2 | Within package (ladder)
UG-11B-S03-A070 | UG-11B-S02-A070 | FS | 0 | Crew continuity, front F6
UG-11B-S02-A070 | UG-11B-S02-A080 | SS | 3 | Within package (ladder)
UG-11B-S02-A070 | UG-11B-S02-A080 | FF | 2 | Within package (ladder)
UG-11B-S03-A080 | UG-11B-S02-A080 | FS | 0 | Crew continuity, front F6
UG-11B-S02-A080 | UG-11B-S02-A090 | SS | 1 | Within package (ladder)
UG-11B-S02-A080 | UG-11B-S02-A090 | FF | 2 | Within package (ladder)
UG-11B-S02-A090 | UG-11B-S02-A100 | SS | 2 | Within package (ladder)
UG-11B-S02-A090 | UG-11B-S02-A100 | FF | 2 | Within package (ladder)
UG-11B-S03-A100 | UG-11B-S02-A100 | FS | 0 | Crew continuity, front F6
UG-16A-S01-A080 | UG-11B-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11B-S02-A100 | UG-11B-S02-A110 | SS | 1 | Within package (ladder)
UG-11B-S02-A100 | UG-11B-S02-A110 | FF | 2 | Within package (ladder)
UG-11B-S01-A010 | UG-11B-S01-A020 | FS | 0 | Within package
UG-11B-S02-A030 | UG-11B-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-11B-S01-A020 | UG-11B-S01-A030 | SS | 1 | Within package (ladder)
UG-11B-S01-A020 | UG-11B-S01-A030 | FF | 2 | Within package (ladder)
UG-11B-S01-A030 | UG-11B-S01-A040 | SS | 1 | Within package (ladder)
UG-11B-S01-A030 | UG-11B-S01-A040 | FF | 2 | Within package (ladder)
UG-11B-S01-A040 | UG-11B-S01-A050 | SS | 1 | Within package (ladder)
UG-11B-S01-A040 | UG-11B-S01-A050 | FF | 2 | Within package (ladder)
UG-11B-S01-A050 | UG-11B-S01-A060 | SS | 10 | Within package (ladder)
UG-11B-S01-A050 | UG-11B-S01-A060 | FF | 2 | Within package (ladder)
UG-11B-S01-A060 | UG-11B-S01-A070 | SS | 1 | Within package (ladder)
UG-11B-S01-A060 | UG-11B-S01-A070 | FF | 2 | Within package (ladder)
UG-11B-S01-A070 | UG-11B-S01-A080 | SS | 2 | Within package (ladder)
UG-11B-S01-A070 | UG-11B-S01-A080 | FF | 2 | Within package (ladder)
UG-11B-S02-A080 | UG-11B-S01-A080 | FS | 0 | Tie-in laid as closure
UG-11B-S01-A080 | UG-11B-S01-A090 | SS | 2 | Within package (ladder)
UG-11B-S01-A080 | UG-11B-S01-A090 | FF | 2 | Within package (ladder)
UG-11B-S01-A090 | UG-11B-S01-A100 | SS | 2 | Within package (ladder)
UG-11B-S01-A090 | UG-11B-S01-A100 | FF | 2 | Within package (ladder)
UG-16A-S01-A080 | UG-11B-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11B-S01-A100 | UG-11B-S01-A110 | SS | 1 | Within package (ladder)
UG-11B-S01-A100 | UG-11B-S01-A110 | FF | 2 | Within package (ladder)
UG-16A-S01-A010 | UG-16A-S01-A020 | FS | 0 | Within package
UG-16A-S01-A020 | UG-16A-S01-A030 | SS | 1 | Within package (ladder)
UG-16A-S01-A020 | UG-16A-S01-A030 | FF | 2 | Within package (ladder)
UG-16A-S01-A030 | UG-16A-S01-A040 | SS | 3 | Within package (ladder)
UG-16A-S01-A030 | UG-16A-S01-A040 | FF | 2 | Within package (ladder)
UG-16A-S01-A040 | UG-16A-S01-A050 | SS | 2 | Within package (ladder)
UG-16A-S01-A040 | UG-16A-S01-A050 | FF | 2 | Within package (ladder)
UG-16A-S01-A050 | UG-16A-S01-A060 | SS | 10 | Within package (ladder)
UG-16A-S01-A050 | UG-16A-S01-A060 | FF | 2 | Within package (ladder)
UG-10-S05-A100 | UG-16A-S01-A060 | FS | 0 | Deeper line first
UG-11B-S01-A060 | UG-16A-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-11B-S02-A060 | UG-16A-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-16A-S01-A060 | UG-16A-S01-A070 | SS | 1 | Within package (ladder)
UG-16A-S01-A060 | UG-16A-S01-A070 | FF | 2 | Within package (ladder)
UG-16A-S01-A070 | UG-16A-S01-A080 | SS | 3 | Within package (ladder)
UG-16A-S01-A070 | UG-16A-S01-A080 | FF | 2 | Within package (ladder)
UG-16A-S01-A080 | UG-16A-S01-A090 | SS | 4 | Within package (ladder)
UG-16A-S01-A080 | UG-16A-S01-A090 | FF | 2 | Within package (ladder)
UG-16A-S01-A090 | UG-16A-S01-A100 | SS | 2 | Within package (ladder)
UG-16A-S01-A090 | UG-16A-S01-A100 | FF | 2 | Within package (ladder)
UG-11B-S01-A080 | UG-16A-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11B-S02-A080 | UG-16A-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-16A-S01-A100 | UG-16A-S01-A110 | SS | 1 | Within package (ladder)
UG-16A-S01-A100 | UG-16A-S01-A110 | FF | 2 | Within package (ladder)
UG-11B-S10-A010 | UG-11B-S10-A020 | FS | 0 | Within package
UG-11B-S02-A030 | UG-11B-S10-A020 | SS | 0 | Set-out one package ahead of piling
UG-11B-S10-A020 | UG-11B-S10-A030 | SS | 1 | Within package (ladder)
UG-11B-S10-A020 | UG-11B-S10-A030 | FF | 2 | Within package (ladder)
UG-11B-S02-A030 | UG-11B-S10-A030 | FS | 0 | Crew continuity, front F6
UG-11B-S10-A030 | UG-11B-S10-A040 | SS | 3 | Within package (ladder)
UG-11B-S10-A030 | UG-11B-S10-A040 | FF | 2 | Within package (ladder)
UG-11B-S02-A040 | UG-11B-S10-A040 | FS | 0 | Crew continuity, front F6
UG-11B-S10-A040 | UG-11B-S10-A050 | SS | 2 | Within package (ladder)
UG-11B-S10-A040 | UG-11B-S10-A050 | FF | 2 | Within package (ladder)
UG-11B-S02-A060 | UG-11B-S10-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11B-S10-A050 | UG-11B-S10-A060 | SS | 10 | Within package (ladder)
UG-11B-S10-A050 | UG-11B-S10-A060 | FF | 2 | Within package (ladder)
UG-11B-S02-A060 | UG-11B-S10-A060 | FS | 0 | Crew continuity, front F6
UG-11B-S10-A060 | UG-11B-S10-A070 | SS | 2 | Within package (ladder)
UG-11B-S10-A060 | UG-11B-S10-A070 | FF | 2 | Within package (ladder)
UG-11B-S02-A070 | UG-11B-S10-A070 | FS | 0 | Crew continuity, front F6
UG-11B-S10-A070 | UG-11B-S10-A080 | SS | 3 | Within package (ladder)
UG-11B-S10-A070 | UG-11B-S10-A080 | FF | 2 | Within package (ladder)
UG-11B-S02-A080 | UG-11B-S10-A080 | FS | 0 | Crew continuity, front F6
UG-11B-S10-A080 | UG-11B-S10-A090 | SS | 1 | Within package (ladder)
UG-11B-S10-A080 | UG-11B-S10-A090 | FF | 2 | Within package (ladder)
UG-11B-S10-A090 | UG-11B-S10-A100 | SS | 2 | Within package (ladder)
UG-11B-S10-A090 | UG-11B-S10-A100 | FF | 2 | Within package (ladder)
UG-11B-S02-A100 | UG-11B-S10-A100 | FS | 0 | Crew continuity, front F6
UG-16C-S01-A080 | UG-11B-S10-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11B-S10-A100 | UG-11B-S10-A110 | SS | 1 | Within package (ladder)
UG-11B-S10-A100 | UG-11B-S10-A110 | FF | 2 | Within package (ladder)
UG-11B-S09-A010 | UG-11B-S09-A020 | FS | 0 | Within package
UG-11B-S10-A030 | UG-11B-S09-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-11B-S09-A020 | UG-11B-S09-A030 | SS | 1 | Within package (ladder)
UG-11B-S09-A020 | UG-11B-S09-A030 | FF | 2 | Within package (ladder)
UG-11B-S09-A030 | UG-11B-S09-A040 | SS | 1 | Within package (ladder)
UG-11B-S09-A030 | UG-11B-S09-A040 | FF | 2 | Within package (ladder)
UG-11B-S09-A040 | UG-11B-S09-A050 | SS | 1 | Within package (ladder)
UG-11B-S09-A040 | UG-11B-S09-A050 | FF | 2 | Within package (ladder)
UG-11B-S09-A050 | UG-11B-S09-A060 | SS | 10 | Within package (ladder)
UG-11B-S09-A050 | UG-11B-S09-A060 | FF | 2 | Within package (ladder)
UG-11B-S09-A060 | UG-11B-S09-A070 | SS | 1 | Within package (ladder)
UG-11B-S09-A060 | UG-11B-S09-A070 | FF | 2 | Within package (ladder)
UG-11B-S09-A070 | UG-11B-S09-A080 | SS | 2 | Within package (ladder)
UG-11B-S09-A070 | UG-11B-S09-A080 | FF | 2 | Within package (ladder)
UG-11B-S10-A080 | UG-11B-S09-A080 | FS | 0 | Tie-in laid as closure
UG-11B-S09-A080 | UG-11B-S09-A090 | SS | 2 | Within package (ladder)
UG-11B-S09-A080 | UG-11B-S09-A090 | FF | 2 | Within package (ladder)
UG-11B-S09-A090 | UG-11B-S09-A100 | SS | 2 | Within package (ladder)
UG-11B-S09-A090 | UG-11B-S09-A100 | FF | 2 | Within package (ladder)
UG-16C-S01-A080 | UG-11B-S09-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11B-S09-A100 | UG-11B-S09-A110 | SS | 1 | Within package (ladder)
UG-11B-S09-A100 | UG-11B-S09-A110 | FF | 2 | Within package (ladder)
UG-16C-S01-A010 | UG-16C-S01-A020 | FS | 0 | Within package
UG-16C-S01-A020 | UG-16C-S01-A030 | SS | 1 | Within package (ladder)
UG-16C-S01-A020 | UG-16C-S01-A030 | FF | 2 | Within package (ladder)
UG-16C-S01-A030 | UG-16C-S01-A040 | SS | 3 | Within package (ladder)
UG-16C-S01-A030 | UG-16C-S01-A040 | FF | 0 | Within package (ladder)
UG-16C-S01-A040 | UG-16C-S01-A050 | SS | 0 | Within package (ladder)
UG-16C-S01-A040 | UG-16C-S01-A050 | FF | 2 | Within package (ladder)
UG-16C-S01-A050 | UG-16C-S01-A060 | SS | 10 | Within package (ladder)
UG-16C-S01-A050 | UG-16C-S01-A060 | FF | 2 | Within package (ladder)
UG-11B-S09-A060 | UG-16C-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-11B-S10-A060 | UG-16C-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-16C-S01-A060 | UG-16C-S01-A070 | SS | 2 | Within package (ladder)
UG-16C-S01-A060 | UG-16C-S01-A070 | FF | 2 | Within package (ladder)
UG-16C-S01-A070 | UG-16C-S01-A080 | SS | 3 | Within package (ladder)
UG-16C-S01-A070 | UG-16C-S01-A080 | FF | 2 | Within package (ladder)
UG-16C-S01-A080 | UG-16C-S01-A090 | SS | 3 | Within package (ladder)
UG-16C-S01-A080 | UG-16C-S01-A090 | FF | 2 | Within package (ladder)
UG-16C-S01-A090 | UG-16C-S01-A100 | SS | 2 | Within package (ladder)
UG-16C-S01-A090 | UG-16C-S01-A100 | FF | 2 | Within package (ladder)
UG-11B-S09-A080 | UG-16C-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11B-S10-A080 | UG-16C-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-16C-S01-A100 | UG-16C-S01-A110 | SS | 2 | Within package (ladder)
UG-16C-S01-A100 | UG-16C-S01-A110 | FF | 2 | Within package (ladder)
UG-11B-S12-A010 | UG-11B-S12-A020 | FS | 0 | Within package
UG-11B-S10-A030 | UG-11B-S12-A020 | SS | 0 | Set-out one package ahead of piling
UG-11B-S12-A020 | UG-11B-S12-A030 | SS | 1 | Within package (ladder)
UG-11B-S12-A020 | UG-11B-S12-A030 | FF | 2 | Within package (ladder)
UG-11B-S10-A030 | UG-11B-S12-A030 | FS | 0 | Crew continuity, front F6
UG-11B-S12-A030 | UG-11B-S12-A040 | SS | 2 | Within package (ladder)
UG-11B-S12-A030 | UG-11B-S12-A040 | FF | 2 | Within package (ladder)
UG-11B-S10-A040 | UG-11B-S12-A040 | FS | 0 | Crew continuity, front F6
UG-11B-S12-A040 | UG-11B-S12-A050 | SS | 2 | Within package (ladder)
UG-11B-S12-A040 | UG-11B-S12-A050 | FF | 2 | Within package (ladder)
UG-11B-S10-A060 | UG-11B-S12-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11B-S12-A050 | UG-11B-S12-A060 | SS | 10 | Within package (ladder)
UG-11B-S12-A050 | UG-11B-S12-A060 | FF | 2 | Within package (ladder)
UG-11B-S10-A060 | UG-11B-S12-A060 | FS | 0 | Crew continuity, front F6
UG-11B-S12-A060 | UG-11B-S12-A070 | SS | 1 | Within package (ladder)
UG-11B-S12-A060 | UG-11B-S12-A070 | FF | 2 | Within package (ladder)
UG-11B-S10-A070 | UG-11B-S12-A070 | FS | 0 | Crew continuity, front F6
UG-11B-S12-A070 | UG-11B-S12-A080 | SS | 3 | Within package (ladder)
UG-11B-S12-A070 | UG-11B-S12-A080 | FF | 2 | Within package (ladder)
UG-11B-S10-A080 | UG-11B-S12-A080 | FS | 0 | Crew continuity, front F6
UG-11B-S12-A080 | UG-11B-S12-A090 | SS | 1 | Within package (ladder)
UG-11B-S12-A080 | UG-11B-S12-A090 | FF | 2 | Within package (ladder)
UG-11B-S12-A090 | UG-11B-S12-A100 | SS | 2 | Within package (ladder)
UG-11B-S12-A090 | UG-11B-S12-A100 | FF | 2 | Within package (ladder)
UG-11B-S10-A100 | UG-11B-S12-A100 | FS | 0 | Crew continuity, front F6
UG-16D-S01-A080 | UG-11B-S12-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11B-S12-A100 | UG-11B-S12-A110 | SS | 1 | Within package (ladder)
UG-11B-S12-A100 | UG-11B-S12-A110 | FF | 2 | Within package (ladder)
UG-11B-S11-A010 | UG-11B-S11-A020 | FS | 0 | Within package
UG-11B-S12-A030 | UG-11B-S11-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-11B-S11-A020 | UG-11B-S11-A030 | SS | 1 | Within package (ladder)
UG-11B-S11-A020 | UG-11B-S11-A030 | FF | 2 | Within package (ladder)
UG-11B-S11-A030 | UG-11B-S11-A040 | SS | 1 | Within package (ladder)
UG-11B-S11-A030 | UG-11B-S11-A040 | FF | 2 | Within package (ladder)
UG-11B-S11-A040 | UG-11B-S11-A050 | SS | 1 | Within package (ladder)
UG-11B-S11-A040 | UG-11B-S11-A050 | FF | 2 | Within package (ladder)
UG-11B-S11-A050 | UG-11B-S11-A060 | SS | 10 | Within package (ladder)
UG-11B-S11-A050 | UG-11B-S11-A060 | FF | 2 | Within package (ladder)
UG-11B-S11-A060 | UG-11B-S11-A070 | SS | 1 | Within package (ladder)
UG-11B-S11-A060 | UG-11B-S11-A070 | FF | 2 | Within package (ladder)
UG-11B-S11-A070 | UG-11B-S11-A080 | SS | 2 | Within package (ladder)
UG-11B-S11-A070 | UG-11B-S11-A080 | FF | 2 | Within package (ladder)
UG-11B-S12-A080 | UG-11B-S11-A080 | FS | 0 | Tie-in laid as closure
UG-11B-S11-A080 | UG-11B-S11-A090 | SS | 2 | Within package (ladder)
UG-11B-S11-A080 | UG-11B-S11-A090 | FF | 2 | Within package (ladder)
UG-11B-S11-A090 | UG-11B-S11-A100 | SS | 2 | Within package (ladder)
UG-11B-S11-A090 | UG-11B-S11-A100 | FF | 2 | Within package (ladder)
UG-16D-S01-A080 | UG-11B-S11-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11B-S11-A100 | UG-11B-S11-A110 | SS | 1 | Within package (ladder)
UG-11B-S11-A100 | UG-11B-S11-A110 | FF | 2 | Within package (ladder)
UG-16D-S01-A010 | UG-16D-S01-A020 | FS | 0 | Within package
UG-16D-S01-A020 | UG-16D-S01-A030 | SS | 1 | Within package (ladder)
UG-16D-S01-A020 | UG-16D-S01-A030 | FF | 2 | Within package (ladder)
UG-16D-S01-A030 | UG-16D-S01-A040 | SS | 3 | Within package (ladder)
UG-16D-S01-A030 | UG-16D-S01-A040 | FF | 2 | Within package (ladder)
UG-16D-S01-A040 | UG-16D-S01-A050 | SS | 2 | Within package (ladder)
UG-16D-S01-A040 | UG-16D-S01-A050 | FF | 2 | Within package (ladder)
UG-16D-S01-A050 | UG-16D-S01-A060 | SS | 10 | Within package (ladder)
UG-16D-S01-A050 | UG-16D-S01-A060 | FF | 2 | Within package (ladder)
UG-11B-S07-A100 | UG-16D-S01-A060 | FS | 0 | Deeper line first
UG-11B-S11-A060 | UG-16D-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-11B-S12-A060 | UG-16D-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-16D-S01-A060 | UG-16D-S01-A070 | SS | 1 | Within package (ladder)
UG-16D-S01-A060 | UG-16D-S01-A070 | FF | 2 | Within package (ladder)
UG-16D-S01-A070 | UG-16D-S01-A080 | SS | 3 | Within package (ladder)
UG-16D-S01-A070 | UG-16D-S01-A080 | FF | 2 | Within package (ladder)
UG-16D-S01-A080 | UG-16D-S01-A090 | SS | 3 | Within package (ladder)
UG-16D-S01-A080 | UG-16D-S01-A090 | FF | 2 | Within package (ladder)
UG-16D-S01-A090 | UG-16D-S01-A100 | SS | 2 | Within package (ladder)
UG-16D-S01-A090 | UG-16D-S01-A100 | FF | 2 | Within package (ladder)
UG-11B-S11-A080 | UG-16D-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11B-S12-A080 | UG-16D-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-16D-S01-A100 | UG-16D-S01-A110 | SS | 1 | Within package (ladder)
UG-16D-S01-A100 | UG-16D-S01-A110 | FF | 2 | Within package (ladder)
UG-11B-S13-A010 | UG-11B-S13-A020 | FS | 0 | Within package
UG-11B-S12-A030 | UG-11B-S13-A020 | SS | 0 | Set-out one package ahead of piling
UG-11B-S13-A020 | UG-11B-S13-A030 | SS | 1 | Within package (ladder)
UG-11B-S13-A020 | UG-11B-S13-A030 | FF | 2 | Within package (ladder)
UG-11B-S12-A030 | UG-11B-S13-A030 | FS | 0 | Crew continuity, front F6
UG-11B-S13-A030 | UG-11B-S13-A040 | SS | 2 | Within package (ladder)
UG-11B-S13-A030 | UG-11B-S13-A040 | FF | 2 | Within package (ladder)
UG-11B-S12-A040 | UG-11B-S13-A040 | FS | 0 | Crew continuity, front F6
UG-11B-S13-A040 | UG-11B-S13-A050 | SS | 1 | Within package (ladder)
UG-11B-S13-A040 | UG-11B-S13-A050 | FF | 2 | Within package (ladder)
UG-11B-S12-A060 | UG-11B-S13-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11B-S13-A050 | UG-11B-S13-A060 | SS | 10 | Within package (ladder)
UG-11B-S13-A050 | UG-11B-S13-A060 | FF | 2 | Within package (ladder)
UG-11B-S12-A060 | UG-11B-S13-A060 | FS | 0 | Crew continuity, front F6
UG-11B-S13-A060 | UG-11B-S13-A070 | SS | 1 | Within package (ladder)
UG-11B-S13-A060 | UG-11B-S13-A070 | FF | 2 | Within package (ladder)
UG-11B-S12-A070 | UG-11B-S13-A070 | FS | 0 | Crew continuity, front F6
UG-11B-S13-A070 | UG-11B-S13-A080 | SS | 2 | Within package (ladder)
UG-11B-S13-A070 | UG-11B-S13-A080 | FF | 2 | Within package (ladder)
UG-11B-S12-A080 | UG-11B-S13-A080 | FS | 0 | Crew continuity, front F6
UG-11B-S13-A080 | UG-11B-S13-A090 | SS | 1 | Within package (ladder)
UG-11B-S13-A080 | UG-11B-S13-A090 | FF | 2 | Within package (ladder)
UG-11B-S13-A090 | UG-11B-S13-A100 | SS | 2 | Within package (ladder)
UG-11B-S13-A090 | UG-11B-S13-A100 | FF | 2 | Within package (ladder)
UG-11B-S12-A100 | UG-11B-S13-A100 | FS | 0 | Crew continuity, front F6
UG-11B-S13-A100 | UG-11B-S13-A110 | SS | 1 | Within package (ladder)
UG-11B-S13-A100 | UG-11B-S13-A110 | FF | 2 | Within package (ladder)
UG-11A-S04-A010 | UG-11A-S04-A020 | FS | 0 | Within package
UG-11B-S13-A030 | UG-11A-S04-A020 | SS | 0 | Set-out one package ahead of piling
UG-11A-S04-A020 | UG-11A-S04-A030 | SS | 1 | Within package (ladder)
UG-11A-S04-A020 | UG-11A-S04-A030 | FF | 2 | Within package (ladder)
UG-11B-S13-A030 | UG-11A-S04-A030 | FS | 0 | Crew continuity, front F6
UG-11A-S04-A030 | UG-11A-S04-A040 | SS | 3 | Within package (ladder)
UG-11A-S04-A030 | UG-11A-S04-A040 | FF | 2 | Within package (ladder)
UG-11B-S13-A040 | UG-11A-S04-A040 | FS | 0 | Crew continuity, front F6
UG-11A-S04-A040 | UG-11A-S04-A050 | SS | 2 | Within package (ladder)
UG-11A-S04-A040 | UG-11A-S04-A050 | FF | 2 | Within package (ladder)
UG-11B-S13-A060 | UG-11A-S04-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11A-S04-A050 | UG-11A-S04-A060 | SS | 10 | Within package (ladder)
UG-11A-S04-A050 | UG-11A-S04-A060 | FF | 2 | Within package (ladder)
UG-11B-S13-A060 | UG-11A-S04-A060 | FS | 0 | Crew continuity, front F6
UG-11A-S04-A060 | UG-11A-S04-A070 | SS | 1 | Within package (ladder)
UG-11A-S04-A060 | UG-11A-S04-A070 | FF | 2 | Within package (ladder)
UG-11B-S13-A070 | UG-11A-S04-A070 | FS | 0 | Crew continuity, front F6
UG-11A-S04-A070 | UG-11A-S04-A080 | SS | 3 | Within package (ladder)
UG-11A-S04-A070 | UG-11A-S04-A080 | FF | 2 | Within package (ladder)
UG-11B-S13-A080 | UG-11A-S04-A080 | FS | 0 | Crew continuity, front F6
UG-11A-S04-A080 | UG-11A-S04-A090 | SS | 1 | Within package (ladder)
UG-11A-S04-A080 | UG-11A-S04-A090 | FF | 2 | Within package (ladder)
UG-11A-S04-A090 | UG-11A-S04-A100 | SS | 2 | Within package (ladder)
UG-11A-S04-A090 | UG-11A-S04-A100 | FF | 2 | Within package (ladder)
UG-11B-S13-A100 | UG-11A-S04-A100 | FS | 0 | Crew continuity, front F6
UG-11A-S04-A100 | UG-11A-S04-A110 | SS | 1 | Within package (ladder)
UG-11A-S04-A100 | UG-11A-S04-A110 | FF | 2 | Within package (ladder)
UG-11A-S03-A010 | UG-11A-S03-A020 | FS | 0 | Within package
UG-11A-S04-A030 | UG-11A-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-11A-S03-A020 | UG-11A-S03-A030 | SS | 1 | Within package (ladder)
UG-11A-S03-A020 | UG-11A-S03-A030 | FF | 2 | Within package (ladder)
UG-11A-S04-A030 | UG-11A-S03-A030 | FS | 0 | Crew continuity, front F6
UG-11A-S03-A030 | UG-11A-S03-A040 | SS | 2 | Within package (ladder)
UG-11A-S03-A030 | UG-11A-S03-A040 | FF | 2 | Within package (ladder)
UG-11A-S04-A040 | UG-11A-S03-A040 | FS | 0 | Crew continuity, front F6
UG-11A-S03-A040 | UG-11A-S03-A050 | SS | 2 | Within package (ladder)
UG-11A-S03-A040 | UG-11A-S03-A050 | FF | 2 | Within package (ladder)
UG-11A-S04-A060 | UG-11A-S03-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11A-S03-A050 | UG-11A-S03-A060 | SS | 10 | Within package (ladder)
UG-11A-S03-A050 | UG-11A-S03-A060 | FF | 2 | Within package (ladder)
UG-11A-S04-A060 | UG-11A-S03-A060 | FS | 0 | Crew continuity, front F6
UG-11A-S03-A060 | UG-11A-S03-A070 | SS | 1 | Within package (ladder)
UG-11A-S03-A060 | UG-11A-S03-A070 | FF | 2 | Within package (ladder)
UG-11A-S04-A070 | UG-11A-S03-A070 | FS | 0 | Crew continuity, front F6
UG-11A-S03-A070 | UG-11A-S03-A080 | SS | 3 | Within package (ladder)
UG-11A-S03-A070 | UG-11A-S03-A080 | FF | 2 | Within package (ladder)
UG-11A-S04-A080 | UG-11A-S03-A080 | FS | 0 | Crew continuity, front F6
UG-11A-S03-A080 | UG-11A-S03-A090 | SS | 2 | Within package (ladder)
UG-11A-S03-A080 | UG-11A-S03-A090 | FF | 2 | Within package (ladder)
UG-11A-S03-A090 | UG-11A-S03-A100 | SS | 2 | Within package (ladder)
UG-11A-S03-A090 | UG-11A-S03-A100 | FF | 2 | Within package (ladder)
UG-11A-S04-A100 | UG-11A-S03-A100 | FS | 0 | Crew continuity, front F6
UG-11A-S03-A100 | UG-11A-S03-A110 | SS | 1 | Within package (ladder)
UG-11A-S03-A100 | UG-11A-S03-A110 | FF | 2 | Within package (ladder)
UG-11A-S02-A010 | UG-11A-S02-A020 | FS | 0 | Within package
UG-11A-S03-A030 | UG-11A-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-11A-S02-A020 | UG-11A-S02-A030 | SS | 1 | Within package (ladder)
UG-11A-S02-A020 | UG-11A-S02-A030 | FF | 2 | Within package (ladder)
UG-11A-S03-A030 | UG-11A-S02-A030 | FS | 0 | Crew continuity, front F6
UG-11A-S02-A030 | UG-11A-S02-A040 | SS | 3 | Within package (ladder)
UG-11A-S02-A030 | UG-11A-S02-A040 | FF | 2 | Within package (ladder)
UG-11A-S03-A040 | UG-11A-S02-A040 | FS | 0 | Crew continuity, front F6
UG-11A-S02-A040 | UG-11A-S02-A050 | SS | 2 | Within package (ladder)
UG-11A-S02-A040 | UG-11A-S02-A050 | FF | 2 | Within package (ladder)
UG-11A-S03-A060 | UG-11A-S02-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11A-S02-A050 | UG-11A-S02-A060 | SS | 10 | Within package (ladder)
UG-11A-S02-A050 | UG-11A-S02-A060 | FF | 2 | Within package (ladder)
UG-11A-S03-A060 | UG-11A-S02-A060 | FS | 0 | Crew continuity, front F6
UG-11A-S02-A060 | UG-11A-S02-A070 | SS | 2 | Within package (ladder)
UG-11A-S02-A060 | UG-11A-S02-A070 | FF | 2 | Within package (ladder)
UG-11A-S03-A070 | UG-11A-S02-A070 | FS | 0 | Crew continuity, front F6
UG-11A-S02-A070 | UG-11A-S02-A080 | SS | 3 | Within package (ladder)
UG-11A-S02-A070 | UG-11A-S02-A080 | FF | 2 | Within package (ladder)
UG-11A-S03-A080 | UG-11A-S02-A080 | FS | 0 | Crew continuity, front F6
UG-11A-S02-A080 | UG-11A-S02-A090 | SS | 2 | Within package (ladder)
UG-11A-S02-A080 | UG-11A-S02-A090 | FF | 2 | Within package (ladder)
UG-11A-S02-A090 | UG-11A-S02-A100 | SS | 2 | Within package (ladder)
UG-11A-S02-A090 | UG-11A-S02-A100 | FF | 2 | Within package (ladder)
UG-11A-S03-A100 | UG-11A-S02-A100 | FS | 0 | Crew continuity, front F6
UG-14G-S01-A080 | UG-11A-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11A-S02-A100 | UG-11A-S02-A110 | SS | 1 | Within package (ladder)
UG-11A-S02-A100 | UG-11A-S02-A110 | FF | 2 | Within package (ladder)
UG-11A-S01-A010 | UG-11A-S01-A020 | FS | 0 | Within package
UG-11A-S02-A030 | UG-11A-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-11A-S01-A020 | UG-11A-S01-A030 | SS | 1 | Within package (ladder)
UG-11A-S01-A020 | UG-11A-S01-A030 | FF | 2 | Within package (ladder)
UG-11A-S01-A030 | UG-11A-S01-A040 | SS | 1 | Within package (ladder)
UG-11A-S01-A030 | UG-11A-S01-A040 | FF | 2 | Within package (ladder)
UG-11A-S01-A040 | UG-11A-S01-A050 | SS | 1 | Within package (ladder)
UG-11A-S01-A040 | UG-11A-S01-A050 | FF | 2 | Within package (ladder)
UG-11A-S01-A050 | UG-11A-S01-A060 | SS | 10 | Within package (ladder)
UG-11A-S01-A050 | UG-11A-S01-A060 | FF | 2 | Within package (ladder)
UG-11A-S01-A060 | UG-11A-S01-A070 | SS | 1 | Within package (ladder)
UG-11A-S01-A060 | UG-11A-S01-A070 | FF | 2 | Within package (ladder)
UG-11A-S01-A070 | UG-11A-S01-A080 | SS | 2 | Within package (ladder)
UG-11A-S01-A070 | UG-11A-S01-A080 | FF | 2 | Within package (ladder)
UG-11A-S02-A080 | UG-11A-S01-A080 | FS | 0 | Tie-in laid as closure
UG-11A-S01-A080 | UG-11A-S01-A090 | SS | 2 | Within package (ladder)
UG-11A-S01-A080 | UG-11A-S01-A090 | FF | 2 | Within package (ladder)
UG-11A-S01-A090 | UG-11A-S01-A100 | SS | 2 | Within package (ladder)
UG-11A-S01-A090 | UG-11A-S01-A100 | FF | 2 | Within package (ladder)
UG-14G-S01-A080 | UG-11A-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11A-S01-A100 | UG-11A-S01-A110 | SS | 1 | Within package (ladder)
UG-11A-S01-A100 | UG-11A-S01-A110 | FF | 2 | Within package (ladder)
UG-14G-S01-A010 | UG-14G-S01-A020 | FS | 0 | Within package
UG-14G-S01-A020 | UG-14G-S01-A030 | SS | 1 | Within package (ladder)
UG-14G-S01-A020 | UG-14G-S01-A030 | FF | 2 | Within package (ladder)
UG-14G-S01-A030 | UG-14G-S01-A040 | SS | 3 | Within package (ladder)
UG-14G-S01-A030 | UG-14G-S01-A040 | FF | 0 | Within package (ladder)
UG-14G-S01-A040 | UG-14G-S01-A050 | SS | 0 | Within package (ladder)
UG-14G-S01-A040 | UG-14G-S01-A050 | FF | 2 | Within package (ladder)
UG-14G-S01-A050 | UG-14G-S01-A060 | SS | 10 | Within package (ladder)
UG-14G-S01-A050 | UG-14G-S01-A060 | FF | 2 | Within package (ladder)
UG-13B-S02-A100 | UG-14G-S01-A060 | FS | 0 | Deeper line first
UG-13B-S03-A100 | UG-14G-S01-A060 | FS | 0 | Deeper line first
UG-11A-S01-A060 | UG-14G-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-11A-S02-A060 | UG-14G-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-14G-S01-A060 | UG-14G-S01-A070 | SS | 2 | Within package (ladder)
UG-14G-S01-A060 | UG-14G-S01-A070 | FF | 2 | Within package (ladder)
UG-14G-S01-A070 | UG-14G-S01-A080 | SS | 3 | Within package (ladder)
UG-14G-S01-A070 | UG-14G-S01-A080 | FF | 2 | Within package (ladder)
UG-14G-S01-A080 | UG-14G-S01-A090 | SS | 4 | Within package (ladder)
UG-14G-S01-A080 | UG-14G-S01-A090 | FF | 2 | Within package (ladder)
UG-14G-S01-A090 | UG-14G-S01-A100 | SS | 2 | Within package (ladder)
UG-14G-S01-A090 | UG-14G-S01-A100 | FF | 2 | Within package (ladder)
UG-11A-S01-A080 | UG-14G-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11A-S02-A080 | UG-14G-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-14G-S01-A100 | UG-14G-S01-A110 | SS | 2 | Within package (ladder)
UG-14G-S01-A100 | UG-14G-S01-A110 | FF | 2 | Within package (ladder)
UG-11A-S07-A010 | UG-11A-S07-A020 | FS | 0 | Within package
UG-11A-S02-A030 | UG-11A-S07-A020 | SS | 0 | Set-out one package ahead of piling
UG-11A-S07-A020 | UG-11A-S07-A030 | SS | 1 | Within package (ladder)
UG-11A-S07-A020 | UG-11A-S07-A030 | FF | 2 | Within package (ladder)
UG-11A-S02-A030 | UG-11A-S07-A030 | FS | 0 | Crew continuity, front F6
UG-11A-S07-A030 | UG-11A-S07-A040 | SS | 3 | Within package (ladder)
UG-11A-S07-A030 | UG-11A-S07-A040 | FF | 2 | Within package (ladder)
UG-11A-S02-A040 | UG-11A-S07-A040 | FS | 0 | Crew continuity, front F6
UG-11A-S07-A040 | UG-11A-S07-A050 | SS | 2 | Within package (ladder)
UG-11A-S07-A040 | UG-11A-S07-A050 | FF | 2 | Within package (ladder)
UG-11A-S02-A060 | UG-11A-S07-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11A-S07-A050 | UG-11A-S07-A060 | SS | 10 | Within package (ladder)
UG-11A-S07-A050 | UG-11A-S07-A060 | FF | 2 | Within package (ladder)
UG-11A-S02-A060 | UG-11A-S07-A060 | FS | 0 | Crew continuity, front F6
UG-11A-S07-A060 | UG-11A-S07-A070 | SS | 1 | Within package (ladder)
UG-11A-S07-A060 | UG-11A-S07-A070 | FF | 2 | Within package (ladder)
UG-11A-S02-A070 | UG-11A-S07-A070 | FS | 0 | Crew continuity, front F6
UG-11A-S07-A070 | UG-11A-S07-A080 | SS | 3 | Within package (ladder)
UG-11A-S07-A070 | UG-11A-S07-A080 | FF | 2 | Within package (ladder)
UG-11A-S02-A080 | UG-11A-S07-A080 | FS | 0 | Crew continuity, front F6
UG-11A-S07-A080 | UG-11A-S07-A090 | SS | 2 | Within package (ladder)
UG-11A-S07-A080 | UG-11A-S07-A090 | FF | 2 | Within package (ladder)
UG-11A-S07-A090 | UG-11A-S07-A100 | SS | 2 | Within package (ladder)
UG-11A-S07-A090 | UG-11A-S07-A100 | FF | 2 | Within package (ladder)
UG-11A-S02-A100 | UG-11A-S07-A100 | FS | 0 | Crew continuity, front F6
UG-14H-S01-A080 | UG-11A-S07-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11A-S07-A100 | UG-11A-S07-A110 | SS | 1 | Within package (ladder)
UG-11A-S07-A100 | UG-11A-S07-A110 | FF | 2 | Within package (ladder)
UG-11A-S06-A010 | UG-11A-S06-A020 | FS | 0 | Within package
UG-11A-S07-A030 | UG-11A-S06-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-11A-S06-A020 | UG-11A-S06-A030 | SS | 1 | Within package (ladder)
UG-11A-S06-A020 | UG-11A-S06-A030 | FF | 2 | Within package (ladder)
UG-11A-S06-A030 | UG-11A-S06-A040 | SS | 1 | Within package (ladder)
UG-11A-S06-A030 | UG-11A-S06-A040 | FF | 2 | Within package (ladder)
UG-11A-S06-A040 | UG-11A-S06-A050 | SS | 1 | Within package (ladder)
UG-11A-S06-A040 | UG-11A-S06-A050 | FF | 2 | Within package (ladder)
UG-11A-S06-A050 | UG-11A-S06-A060 | SS | 10 | Within package (ladder)
UG-11A-S06-A050 | UG-11A-S06-A060 | FF | 2 | Within package (ladder)
UG-11A-S06-A060 | UG-11A-S06-A070 | SS | 1 | Within package (ladder)
UG-11A-S06-A060 | UG-11A-S06-A070 | FF | 2 | Within package (ladder)
UG-11A-S06-A070 | UG-11A-S06-A080 | SS | 2 | Within package (ladder)
UG-11A-S06-A070 | UG-11A-S06-A080 | FF | 2 | Within package (ladder)
UG-11A-S07-A080 | UG-11A-S06-A080 | FS | 0 | Tie-in laid as closure
UG-11A-S06-A080 | UG-11A-S06-A090 | SS | 2 | Within package (ladder)
UG-11A-S06-A080 | UG-11A-S06-A090 | FF | 2 | Within package (ladder)
UG-11A-S06-A090 | UG-11A-S06-A100 | SS | 2 | Within package (ladder)
UG-11A-S06-A090 | UG-11A-S06-A100 | FF | 2 | Within package (ladder)
UG-14H-S01-A080 | UG-11A-S06-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11A-S06-A100 | UG-11A-S06-A110 | SS | 1 | Within package (ladder)
UG-11A-S06-A100 | UG-11A-S06-A110 | FF | 2 | Within package (ladder)
UG-14H-S01-A010 | UG-14H-S01-A020 | FS | 0 | Within package
UG-14H-S01-A020 | UG-14H-S01-A030 | SS | 1 | Within package (ladder)
UG-14H-S01-A020 | UG-14H-S01-A030 | FF | 2 | Within package (ladder)
UG-14H-S01-A030 | UG-14H-S01-A040 | SS | 3 | Within package (ladder)
UG-14H-S01-A030 | UG-14H-S01-A040 | FF | 0 | Within package (ladder)
UG-14H-S01-A040 | UG-14H-S01-A050 | SS | 0 | Within package (ladder)
UG-14H-S01-A040 | UG-14H-S01-A050 | FF | 2 | Within package (ladder)
UG-14H-S01-A050 | UG-14H-S01-A060 | SS | 10 | Within package (ladder)
UG-14H-S01-A050 | UG-14H-S01-A060 | FF | 2 | Within package (ladder)
UG-13B-S04-A100 | UG-14H-S01-A060 | FS | 0 | Deeper line first
UG-11A-S06-A060 | UG-14H-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-11A-S07-A060 | UG-14H-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-14H-S01-A060 | UG-14H-S01-A070 | SS | 2 | Within package (ladder)
UG-14H-S01-A060 | UG-14H-S01-A070 | FF | 2 | Within package (ladder)
UG-14H-S01-A070 | UG-14H-S01-A080 | SS | 3 | Within package (ladder)
UG-14H-S01-A070 | UG-14H-S01-A080 | FF | 2 | Within package (ladder)
UG-14H-S01-A080 | UG-14H-S01-A090 | SS | 4 | Within package (ladder)
UG-14H-S01-A080 | UG-14H-S01-A090 | FF | 2 | Within package (ladder)
UG-14H-S01-A090 | UG-14H-S01-A100 | SS | 2 | Within package (ladder)
UG-14H-S01-A090 | UG-14H-S01-A100 | FF | 2 | Within package (ladder)
UG-11A-S06-A080 | UG-14H-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11A-S07-A080 | UG-14H-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-14H-S01-A100 | UG-14H-S01-A110 | SS | 2 | Within package (ladder)
UG-14H-S01-A100 | UG-14H-S01-A110 | FF | 2 | Within package (ladder)
UG-12-S04-A010 | UG-12-S04-A020 | FS | 0 | Within package
UG-12-S04-A020 | UG-12-S04-A030 | SS | 1 | Within package (ladder)
UG-12-S04-A020 | UG-12-S04-A030 | FF | 2 | Within package (ladder)
UG-12-S04-A030 | UG-12-S04-A040 | SS | 3 | Within package (ladder)
UG-12-S04-A030 | UG-12-S04-A040 | FF | 2 | Within package (ladder)
UG-12-S04-A040 | UG-12-S04-A050 | SS | 2 | Within package (ladder)
UG-12-S04-A040 | UG-12-S04-A050 | FF | 2 | Within package (ladder)
UG-12-S04-A050 | UG-12-S04-A060 | SS | 10 | Within package (ladder)
UG-12-S04-A050 | UG-12-S04-A060 | FF | 2 | Within package (ladder)
UG-12-S04-A060 | UG-12-S04-A070 | SS | 2 | Within package (ladder)
UG-12-S04-A060 | UG-12-S04-A070 | FF | 2 | Within package (ladder)
UG-12-S04-A070 | UG-12-S04-A080 | SS | 3 | Within package (ladder)
UG-12-S04-A070 | UG-12-S04-A080 | FF | 2 | Within package (ladder)
UG-12-S04-A080 | UG-12-S04-A090 | SS | 2 | Within package (ladder)
UG-12-S04-A080 | UG-12-S04-A090 | FF | 2 | Within package (ladder)
UG-12-S04-A090 | UG-12-S04-A100 | SS | 2 | Within package (ladder)
UG-12-S04-A090 | UG-12-S04-A100 | FF | 2 | Within package (ladder)
UG-13B-S05-A080 | UG-12-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12-S04-A100 | UG-12-S04-A110 | SS | 2 | Within package (ladder)
UG-12-S04-A100 | UG-12-S04-A110 | FF | 2 | Within package (ladder)
UG-13B-S05-A010 | UG-13B-S05-A020 | FS | 0 | Within package
UG-12-S04-A030 | UG-13B-S05-A020 | SS | 0 | Set-out one package ahead of piling
UG-13B-S05-A020 | UG-13B-S05-A030 | SS | 1 | Within package (ladder)
UG-13B-S05-A020 | UG-13B-S05-A030 | FF | 2 | Within package (ladder)
UG-12-S04-A030 | UG-13B-S05-A030 | FS | 0 | Crew continuity, front F7
UG-13B-S05-A030 | UG-13B-S05-A040 | SS | 2 | Within package (ladder)
UG-13B-S05-A030 | UG-13B-S05-A040 | FF | 2 | Within package (ladder)
UG-12-S04-A040 | UG-13B-S05-A040 | FS | 0 | Crew continuity, front F7
UG-13B-S05-A040 | UG-13B-S05-A050 | SS | 3 | Within package (ladder)
UG-13B-S05-A040 | UG-13B-S05-A050 | FF | 2 | Within package (ladder)
UG-12-S04-A060 | UG-13B-S05-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13B-S05-A050 | UG-13B-S05-A060 | SS | 10 | Within package (ladder)
UG-13B-S05-A050 | UG-13B-S05-A060 | FF | 2 | Within package (ladder)
UG-12-S04-A060 | UG-13B-S05-A060 | FS | 0 | Crew continuity, front F7
UG-12-S04-A060 | UG-13B-S05-A060 | SS | 0 | Shared excavation / dewatering front
UG-13B-S05-A060 | UG-13B-S05-A070 | SS | 2 | Within package (ladder)
UG-13B-S05-A060 | UG-13B-S05-A070 | FF | 2 | Within package (ladder)
UG-12-S04-A070 | UG-13B-S05-A070 | FS | 0 | Crew continuity, front F7
UG-13B-S05-A070 | UG-13B-S05-A080 | SS | 4 | Within package (ladder)
UG-13B-S05-A070 | UG-13B-S05-A080 | FF | 2 | Within package (ladder)
UG-12-S04-A080 | UG-13B-S05-A080 | FS | 0 | Crew continuity, front F7
UG-13B-S05-A080 | UG-13B-S05-A090 | SS | 2 | Within package (ladder)
UG-13B-S05-A080 | UG-13B-S05-A090 | FF | 2 | Within package (ladder)
UG-13B-S05-A090 | UG-13B-S05-A100 | SS | 2 | Within package (ladder)
UG-13B-S05-A090 | UG-13B-S05-A100 | FF | 2 | Within package (ladder)
UG-12-S04-A100 | UG-13B-S05-A100 | FS | 0 | Crew continuity, front F7
UG-12-S04-A080 | UG-13B-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13B-S05-A100 | UG-13B-S05-A110 | SS | 1 | Within package (ladder)
UG-13B-S05-A100 | UG-13B-S05-A110 | FF | 2 | Within package (ladder)
UG-13-S03-A010 | UG-13-S03-A020 | FS | 0 | Within package
UG-13B-S05-A030 | UG-13-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-13-S03-A020 | UG-13-S03-A030 | SS | 1 | Within package (ladder)
UG-13-S03-A020 | UG-13-S03-A030 | FF | 2 | Within package (ladder)
UG-13B-S05-A030 | UG-13-S03-A030 | FS | 0 | Crew continuity, front F7
UG-13-S03-A030 | UG-13-S03-A040 | SS | 2 | Within package (ladder)
UG-13-S03-A030 | UG-13-S03-A040 | FF | 2 | Within package (ladder)
UG-13B-S05-A040 | UG-13-S03-A040 | FS | 0 | Crew continuity, front F7
UG-13-S03-A040 | UG-13-S03-A050 | SS | 2 | Within package (ladder)
UG-13-S03-A040 | UG-13-S03-A050 | FF | 2 | Within package (ladder)
UG-13B-S05-A060 | UG-13-S03-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13-S03-A050 | UG-13-S03-A060 | SS | 10 | Within package (ladder)
UG-13-S03-A050 | UG-13-S03-A060 | FF | 2 | Within package (ladder)
UG-13B-S05-A060 | UG-13-S03-A060 | FS | 0 | Crew continuity, front F7
UG-13-S03-A060 | UG-13-S03-A070 | SS | 2 | Within package (ladder)
UG-13-S03-A060 | UG-13-S03-A070 | FF | 2 | Within package (ladder)
UG-13B-S05-A070 | UG-13-S03-A070 | FS | 0 | Crew continuity, front F7
UG-13-S03-A070 | UG-13-S03-A080 | SS | 3 | Within package (ladder)
UG-13-S03-A070 | UG-13-S03-A080 | FF | 2 | Within package (ladder)
UG-13B-S05-A080 | UG-13-S03-A080 | FS | 0 | Crew continuity, front F7
UG-13-S03-A080 | UG-13-S03-A090 | SS | 2 | Within package (ladder)
UG-13-S03-A080 | UG-13-S03-A090 | FF | 2 | Within package (ladder)
UG-13-S03-A090 | UG-13-S03-A100 | SS | 2 | Within package (ladder)
UG-13-S03-A090 | UG-13-S03-A100 | FF | 2 | Within package (ladder)
UG-13B-S05-A100 | UG-13-S03-A100 | FS | 0 | Crew continuity, front F7
UG-13-S03-A100 | UG-13-S03-A110 | SS | 1 | Within package (ladder)
UG-13-S03-A100 | UG-13-S03-A110 | FF | 2 | Within package (ladder)
UG-13-S04-A010 | UG-13-S04-A020 | FS | 0 | Within package
UG-13-S03-A030 | UG-13-S04-A020 | SS | 0 | Set-out one package ahead of piling
UG-13-S04-A020 | UG-13-S04-A030 | SS | 1 | Within package (ladder)
UG-13-S04-A020 | UG-13-S04-A030 | FF | 2 | Within package (ladder)
UG-13-S03-A030 | UG-13-S04-A030 | FS | 0 | Crew continuity, front F7
UG-13-S04-A030 | UG-13-S04-A040 | SS | 3 | Within package (ladder)
UG-13-S04-A030 | UG-13-S04-A040 | FF | 2 | Within package (ladder)
UG-13-S03-A040 | UG-13-S04-A040 | FS | 0 | Crew continuity, front F7
UG-13-S04-A040 | UG-13-S04-A050 | SS | 2 | Within package (ladder)
UG-13-S04-A040 | UG-13-S04-A050 | FF | 2 | Within package (ladder)
UG-13-S03-A060 | UG-13-S04-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13-S04-A050 | UG-13-S04-A060 | SS | 10 | Within package (ladder)
UG-13-S04-A050 | UG-13-S04-A060 | FF | 2 | Within package (ladder)
UG-13-S03-A060 | UG-13-S04-A060 | FS | 0 | Crew continuity, front F7
UG-13-S04-A060 | UG-13-S04-A070 | SS | 2 | Within package (ladder)
UG-13-S04-A060 | UG-13-S04-A070 | FF | 2 | Within package (ladder)
UG-13-S03-A070 | UG-13-S04-A070 | FS | 0 | Crew continuity, front F7
UG-13-S04-A070 | UG-13-S04-A080 | SS | 3 | Within package (ladder)
UG-13-S04-A070 | UG-13-S04-A080 | FF | 2 | Within package (ladder)
UG-13-S03-A080 | UG-13-S04-A080 | FS | 0 | Crew continuity, front F7
UG-13-S04-A080 | UG-13-S04-A090 | SS | 1 | Within package (ladder)
UG-13-S04-A080 | UG-13-S04-A090 | FF | 2 | Within package (ladder)
UG-13-S04-A090 | UG-13-S04-A100 | SS | 2 | Within package (ladder)
UG-13-S04-A090 | UG-13-S04-A100 | FF | 2 | Within package (ladder)
UG-13-S03-A100 | UG-13-S04-A100 | FS | 0 | Crew continuity, front F7
UG-13-S04-A100 | UG-13-S04-A110 | SS | 1 | Within package (ladder)
UG-13-S04-A100 | UG-13-S04-A110 | FF | 2 | Within package (ladder)
UG-12-S03-A010 | UG-12-S03-A020 | FS | 0 | Within package
UG-13-S04-A030 | UG-12-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-12-S03-A020 | UG-12-S03-A030 | SS | 1 | Within package (ladder)
UG-12-S03-A020 | UG-12-S03-A030 | FF | 2 | Within package (ladder)
UG-13-S04-A030 | UG-12-S03-A030 | FS | 0 | Crew continuity, front F7
UG-12-S03-A030 | UG-12-S03-A040 | SS | 3 | Within package (ladder)
UG-12-S03-A030 | UG-12-S03-A040 | FF | 2 | Within package (ladder)
UG-13-S04-A040 | UG-12-S03-A040 | FS | 0 | Crew continuity, front F7
UG-12-S03-A040 | UG-12-S03-A050 | SS | 2 | Within package (ladder)
UG-12-S03-A040 | UG-12-S03-A050 | FF | 2 | Within package (ladder)
UG-13-S04-A060 | UG-12-S03-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-12-S03-A050 | UG-12-S03-A060 | SS | 10 | Within package (ladder)
UG-12-S03-A050 | UG-12-S03-A060 | FF | 2 | Within package (ladder)
UG-13-S04-A060 | UG-12-S03-A060 | FS | 0 | Crew continuity, front F7
UG-13-S03-A100 | UG-12-S03-A060 | FS | 0 | Deeper line first
UG-13-S04-A100 | UG-12-S03-A060 | FS | 0 | Deeper line first
UG-12-S03-A060 | UG-12-S03-A070 | SS | 2 | Within package (ladder)
UG-12-S03-A060 | UG-12-S03-A070 | FF | 2 | Within package (ladder)
UG-13-S04-A070 | UG-12-S03-A070 | FS | 0 | Crew continuity, front F7
UG-12-S03-A070 | UG-12-S03-A080 | SS | 3 | Within package (ladder)
UG-12-S03-A070 | UG-12-S03-A080 | FF | 2 | Within package (ladder)
UG-13-S04-A080 | UG-12-S03-A080 | FS | 0 | Crew continuity, front F7
UG-12-S03-A080 | UG-12-S03-A090 | SS | 2 | Within package (ladder)
UG-12-S03-A080 | UG-12-S03-A090 | FF | 2 | Within package (ladder)
UG-12-S03-A090 | UG-12-S03-A100 | SS | 2 | Within package (ladder)
UG-12-S03-A090 | UG-12-S03-A100 | FF | 2 | Within package (ladder)
UG-13-S04-A100 | UG-12-S03-A100 | FS | 0 | Crew continuity, front F7
UG-13B-S06-A080 | UG-12-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13B-S07-A080 | UG-12-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13B-S11-A080 | UG-12-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12-S03-A100 | UG-12-S03-A110 | SS | 2 | Within package (ladder)
UG-12-S03-A100 | UG-12-S03-A110 | FF | 2 | Within package (ladder)
UG-13B-S11-A010 | UG-13B-S11-A020 | FS | 0 | Within package
UG-12-S03-A030 | UG-13B-S11-A020 | SS | 0 | Set-out one package ahead of piling
UG-13B-S11-A020 | UG-13B-S11-A030 | SS | 1 | Within package (ladder)
UG-13B-S11-A020 | UG-13B-S11-A030 | FF | 2 | Within package (ladder)
UG-12-S03-A030 | UG-13B-S11-A030 | FS | 0 | Crew continuity, front F7
UG-13B-S11-A030 | UG-13B-S11-A040 | SS | 2 | Within package (ladder)
UG-13B-S11-A030 | UG-13B-S11-A040 | FF | 2 | Within package (ladder)
UG-12-S03-A040 | UG-13B-S11-A040 | FS | 0 | Crew continuity, front F7
UG-13B-S11-A040 | UG-13B-S11-A050 | SS | 1 | Within package (ladder)
UG-13B-S11-A040 | UG-13B-S11-A050 | FF | 2 | Within package (ladder)
UG-12-S03-A060 | UG-13B-S11-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13B-S11-A050 | UG-13B-S11-A060 | SS | 10 | Within package (ladder)
UG-13B-S11-A050 | UG-13B-S11-A060 | FF | 2 | Within package (ladder)
UG-12-S03-A060 | UG-13B-S11-A060 | FS | 0 | Crew continuity, front F7
UG-12-S03-A060 | UG-13B-S11-A060 | SS | 0 | Shared excavation / dewatering front
UG-13-S03-A060 | UG-13B-S11-A060 | SS | 0 | Shared excavation / dewatering front
UG-13-S04-A060 | UG-13B-S11-A060 | SS | 0 | Shared excavation / dewatering front
UG-13B-S11-A060 | UG-13B-S11-A070 | SS | 1 | Within package (ladder)
UG-13B-S11-A060 | UG-13B-S11-A070 | FF | 2 | Within package (ladder)
UG-12-S03-A070 | UG-13B-S11-A070 | FS | 0 | Crew continuity, front F7
UG-13B-S11-A070 | UG-13B-S11-A080 | SS | 2 | Within package (ladder)
UG-13B-S11-A070 | UG-13B-S11-A080 | FF | 2 | Within package (ladder)
UG-12-S03-A080 | UG-13B-S11-A080 | FS | 0 | Crew continuity, front F7
UG-13B-S11-A080 | UG-13B-S11-A090 | SS | 1 | Within package (ladder)
UG-13B-S11-A080 | UG-13B-S11-A090 | FF | 2 | Within package (ladder)
UG-13B-S11-A090 | UG-13B-S11-A100 | SS | 2 | Within package (ladder)
UG-13B-S11-A090 | UG-13B-S11-A100 | FF | 2 | Within package (ladder)
UG-12-S03-A100 | UG-13B-S11-A100 | FS | 0 | Crew continuity, front F7
UG-12-S03-A080 | UG-13B-S11-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13-S03-A080 | UG-13B-S11-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13-S04-A080 | UG-13B-S11-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13B-S11-A100 | UG-13B-S11-A110 | SS | 1 | Within package (ladder)
UG-13B-S11-A100 | UG-13B-S11-A110 | FF | 2 | Within package (ladder)
UG-13B-S07-A010 | UG-13B-S07-A020 | FS | 0 | Within package
UG-13B-S11-A030 | UG-13B-S07-A020 | SS | 0 | Set-out one package ahead of piling
UG-13B-S07-A020 | UG-13B-S07-A030 | SS | 1 | Within package (ladder)
UG-13B-S07-A020 | UG-13B-S07-A030 | FF | 2 | Within package (ladder)
UG-13B-S11-A030 | UG-13B-S07-A030 | FS | 0 | Crew continuity, front F7
UG-13B-S07-A030 | UG-13B-S07-A040 | SS | 2 | Within package (ladder)
UG-13B-S07-A030 | UG-13B-S07-A040 | FF | 2 | Within package (ladder)
UG-13B-S11-A040 | UG-13B-S07-A040 | FS | 0 | Crew continuity, front F7
UG-13B-S07-A040 | UG-13B-S07-A050 | SS | 2 | Within package (ladder)
UG-13B-S07-A040 | UG-13B-S07-A050 | FF | 2 | Within package (ladder)
UG-13B-S11-A060 | UG-13B-S07-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13B-S07-A050 | UG-13B-S07-A060 | SS | 10 | Within package (ladder)
UG-13B-S07-A050 | UG-13B-S07-A060 | FF | 2 | Within package (ladder)
UG-13B-S11-A060 | UG-13B-S07-A060 | FS | 0 | Crew continuity, front F7
UG-12-S03-A060 | UG-13B-S07-A060 | SS | 0 | Shared excavation / dewatering front
UG-12-S04-A060 | UG-13B-S07-A060 | SS | 0 | Shared excavation / dewatering front
UG-13B-S07-A060 | UG-13B-S07-A070 | SS | 1 | Within package (ladder)
UG-13B-S07-A060 | UG-13B-S07-A070 | FF | 2 | Within package (ladder)
UG-13B-S11-A070 | UG-13B-S07-A070 | FS | 0 | Crew continuity, front F7
UG-13B-S07-A070 | UG-13B-S07-A080 | SS | 3 | Within package (ladder)
UG-13B-S07-A070 | UG-13B-S07-A080 | FF | 2 | Within package (ladder)
UG-13B-S11-A080 | UG-13B-S07-A080 | FS | 0 | Crew continuity, front F7
UG-13B-S07-A080 | UG-13B-S07-A090 | SS | 2 | Within package (ladder)
UG-13B-S07-A080 | UG-13B-S07-A090 | FF | 2 | Within package (ladder)
UG-13B-S07-A090 | UG-13B-S07-A100 | SS | 2 | Within package (ladder)
UG-13B-S07-A090 | UG-13B-S07-A100 | FF | 2 | Within package (ladder)
UG-13B-S11-A100 | UG-13B-S07-A100 | FS | 0 | Crew continuity, front F7
UG-12-S03-A080 | UG-13B-S07-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12-S04-A080 | UG-13B-S07-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13B-S07-A100 | UG-13B-S07-A110 | SS | 1 | Within package (ladder)
UG-13B-S07-A100 | UG-13B-S07-A110 | FF | 2 | Within package (ladder)
UG-13B-S06-A010 | UG-13B-S06-A020 | FS | 0 | Within package
UG-13B-S07-A030 | UG-13B-S06-A020 | SS | 0 | Set-out one package ahead of piling
UG-13B-S06-A020 | UG-13B-S06-A030 | SS | 1 | Within package (ladder)
UG-13B-S06-A020 | UG-13B-S06-A030 | FF | 2 | Within package (ladder)
UG-13B-S07-A030 | UG-13B-S06-A030 | FS | 0 | Crew continuity, front F7
UG-13B-S06-A030 | UG-13B-S06-A040 | SS | 2 | Within package (ladder)
UG-13B-S06-A030 | UG-13B-S06-A040 | FF | 2 | Within package (ladder)
UG-13B-S07-A040 | UG-13B-S06-A040 | FS | 0 | Crew continuity, front F7
UG-13B-S06-A040 | UG-13B-S06-A050 | SS | 2 | Within package (ladder)
UG-13B-S06-A040 | UG-13B-S06-A050 | FF | 2 | Within package (ladder)
UG-13B-S07-A060 | UG-13B-S06-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13B-S06-A050 | UG-13B-S06-A060 | SS | 10 | Within package (ladder)
UG-13B-S06-A050 | UG-13B-S06-A060 | FF | 2 | Within package (ladder)
UG-13B-S07-A060 | UG-13B-S06-A060 | FS | 0 | Crew continuity, front F7
UG-12-S03-A060 | UG-13B-S06-A060 | SS | 0 | Shared excavation / dewatering front
UG-12-S04-A060 | UG-13B-S06-A060 | SS | 0 | Shared excavation / dewatering front
UG-13B-S06-A060 | UG-13B-S06-A070 | SS | 2 | Within package (ladder)
UG-13B-S06-A060 | UG-13B-S06-A070 | FF | 2 | Within package (ladder)
UG-13B-S07-A070 | UG-13B-S06-A070 | FS | 0 | Crew continuity, front F7
UG-13B-S06-A070 | UG-13B-S06-A080 | SS | 3 | Within package (ladder)
UG-13B-S06-A070 | UG-13B-S06-A080 | FF | 2 | Within package (ladder)
UG-13B-S07-A080 | UG-13B-S06-A080 | FS | 0 | Crew continuity, front F7
UG-13B-S06-A080 | UG-13B-S06-A090 | SS | 1 | Within package (ladder)
UG-13B-S06-A080 | UG-13B-S06-A090 | FF | 2 | Within package (ladder)
UG-13B-S06-A090 | UG-13B-S06-A100 | SS | 2 | Within package (ladder)
UG-13B-S06-A090 | UG-13B-S06-A100 | FF | 2 | Within package (ladder)
UG-13B-S07-A100 | UG-13B-S06-A100 | FS | 0 | Crew continuity, front F7
UG-07A-S11-A080 | UG-13B-S06-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12-S03-A080 | UG-13B-S06-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-12-S04-A080 | UG-13B-S06-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13B-S06-A100 | UG-13B-S06-A110 | SS | 1 | Within package (ladder)
UG-13B-S06-A100 | UG-13B-S06-A110 | FF | 2 | Within package (ladder)
UG-07A-S11-A010 | UG-07A-S11-A020 | FS | 0 | Within package
UG-13B-S06-A030 | UG-07A-S11-A020 | SS | 0 | Set-out one package ahead of piling
UG-07A-S11-A020 | UG-07A-S11-A030 | SS | 1 | Within package (ladder)
UG-07A-S11-A020 | UG-07A-S11-A030 | FF | 2 | Within package (ladder)
UG-13B-S06-A030 | UG-07A-S11-A030 | FS | 0 | Crew continuity, front F7
UG-07A-S11-A030 | UG-07A-S11-A040 | SS | 3 | Within package (ladder)
UG-07A-S11-A030 | UG-07A-S11-A040 | FF | 2 | Within package (ladder)
UG-13B-S06-A040 | UG-07A-S11-A040 | FS | 0 | Crew continuity, front F7
UG-07A-S11-A040 | UG-07A-S11-A050 | SS | 2 | Within package (ladder)
UG-07A-S11-A040 | UG-07A-S11-A050 | FF | 2 | Within package (ladder)
UG-13B-S06-A060 | UG-07A-S11-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-07A-S11-A050 | UG-07A-S11-A060 | SS | 10 | Within package (ladder)
UG-07A-S11-A050 | UG-07A-S11-A060 | FF | 2 | Within package (ladder)
UG-13B-S06-A060 | UG-07A-S11-A060 | FS | 0 | Crew continuity, front F7
UG-12-S04-A100 | UG-07A-S11-A060 | FS | 0 | Deeper line first
UG-12-S05-A100 | UG-07A-S11-A060 | FS | 0 | Deeper line first
UG-13B-S07-A100 | UG-07A-S11-A060 | FS | 0 | Deeper line first
UG-13B-S05-A060 | UG-07A-S11-A060 | SS | 0 | Shared excavation / dewatering front
UG-13B-S06-A060 | UG-07A-S11-A060 | SS | 0 | Shared excavation / dewatering front
UG-07A-S11-A060 | UG-07A-S11-A070 | SS | 2 | Within package (ladder)
UG-07A-S11-A060 | UG-07A-S11-A070 | FF | 2 | Within package (ladder)
UG-13B-S06-A070 | UG-07A-S11-A070 | FS | 0 | Crew continuity, front F7
UG-07A-S11-A070 | UG-07A-S11-A080 | SS | 3 | Within package (ladder)
UG-07A-S11-A070 | UG-07A-S11-A080 | FF | 2 | Within package (ladder)
UG-13B-S06-A080 | UG-07A-S11-A080 | FS | 0 | Crew continuity, front F7
UG-07A-S11-A080 | UG-07A-S11-A090 | SS | 2 | Within package (ladder)
UG-07A-S11-A080 | UG-07A-S11-A090 | FF | 2 | Within package (ladder)
UG-07A-S11-A090 | UG-07A-S11-A100 | SS | 2 | Within package (ladder)
UG-07A-S11-A090 | UG-07A-S11-A100 | FF | 2 | Within package (ladder)
UG-13B-S06-A100 | UG-07A-S11-A100 | FS | 0 | Crew continuity, front F7
UG-13B-S05-A080 | UG-07A-S11-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13B-S06-A080 | UG-07A-S11-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-07A-S11-A100 | UG-07A-S11-A110 | SS | 1 | Within package (ladder)
UG-07A-S11-A100 | UG-07A-S11-A110 | FF | 2 | Within package (ladder)
UG-13B-S12-A010 | UG-13B-S12-A020 | FS | 0 | Within package
UG-13B-S12-A020 | UG-13B-S12-A030 | SS | 1 | Within package (ladder)
UG-13B-S12-A020 | UG-13B-S12-A030 | FF | 2 | Within package (ladder)
UG-13B-S12-A030 | UG-13B-S12-A040 | SS | 1 | Within package (ladder)
UG-13B-S12-A030 | UG-13B-S12-A040 | FF | 2 | Within package (ladder)
UG-13B-S12-A040 | UG-13B-S12-A050 | SS | 1 | Within package (ladder)
UG-13B-S12-A040 | UG-13B-S12-A050 | FF | 2 | Within package (ladder)
UG-13B-S12-A050 | UG-13B-S12-A060 | SS | 10 | Within package (ladder)
UG-13B-S12-A050 | UG-13B-S12-A060 | FF | 2 | Within package (ladder)
UG-13B-S12-A060 | UG-13B-S12-A070 | SS | 1 | Within package (ladder)
UG-13B-S12-A060 | UG-13B-S12-A070 | FF | 2 | Within package (ladder)
UG-13B-S12-A070 | UG-13B-S12-A080 | SS | 2 | Within package (ladder)
UG-13B-S12-A070 | UG-13B-S12-A080 | FF | 2 | Within package (ladder)
UG-13B-S12-A080 | UG-13B-S12-A090 | SS | 2 | Within package (ladder)
UG-13B-S12-A080 | UG-13B-S12-A090 | FF | 2 | Within package (ladder)
UG-13B-S12-A090 | UG-13B-S12-A100 | SS | 2 | Within package (ladder)
UG-13B-S12-A090 | UG-13B-S12-A100 | FF | 2 | Within package (ladder)
UG-13-S05-A080 | UG-13B-S12-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-23-S01-A080 | UG-13B-S12-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-23-S02-A080 | UG-13B-S12-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-23-S03-A080 | UG-13B-S12-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13B-S12-A100 | UG-13B-S12-A110 | SS | 1 | Within package (ladder)
UG-13B-S12-A100 | UG-13B-S12-A110 | FF | 2 | Within package (ladder)
UG-13-S05-A010 | UG-13-S05-A020 | FS | 0 | Within package
UG-07A-S11-A030 | UG-13-S05-A020 | SS | 0 | Set-out one package ahead of piling
UG-13-S05-A020 | UG-13-S05-A030 | SS | 1 | Within package (ladder)
UG-13-S05-A020 | UG-13-S05-A030 | FF | 2 | Within package (ladder)
UG-07A-S11-A030 | UG-13-S05-A030 | FS | 0 | Crew continuity, front F7
UG-13-S05-A030 | UG-13-S05-A040 | SS | 3 | Within package (ladder)
UG-13-S05-A030 | UG-13-S05-A040 | FF | 2 | Within package (ladder)
UG-07A-S11-A040 | UG-13-S05-A040 | FS | 0 | Crew continuity, front F7
UG-13-S05-A040 | UG-13-S05-A050 | SS | 2 | Within package (ladder)
UG-13-S05-A040 | UG-13-S05-A050 | FF | 2 | Within package (ladder)
UG-07A-S11-A060 | UG-13-S05-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13-S05-A050 | UG-13-S05-A060 | SS | 10 | Within package (ladder)
UG-13-S05-A050 | UG-13-S05-A060 | FF | 2 | Within package (ladder)
UG-07A-S11-A060 | UG-13-S05-A060 | FS | 0 | Crew continuity, front F7
UG-13B-S12-A060 | UG-13-S05-A060 | SS | 0 | Shared excavation / dewatering front
UG-13-S05-A060 | UG-13-S05-A070 | SS | 2 | Within package (ladder)
UG-13-S05-A060 | UG-13-S05-A070 | FF | 2 | Within package (ladder)
UG-07A-S11-A070 | UG-13-S05-A070 | FS | 0 | Crew continuity, front F7
UG-13-S05-A070 | UG-13-S05-A080 | SS | 3 | Within package (ladder)
UG-13-S05-A070 | UG-13-S05-A080 | FF | 2 | Within package (ladder)
UG-07A-S11-A080 | UG-13-S05-A080 | FS | 0 | Crew continuity, front F7
UG-13-S05-A080 | UG-13-S05-A090 | SS | 2 | Within package (ladder)
UG-13-S05-A080 | UG-13-S05-A090 | FF | 2 | Within package (ladder)
UG-13-S05-A090 | UG-13-S05-A100 | SS | 2 | Within package (ladder)
UG-13-S05-A090 | UG-13-S05-A100 | FF | 2 | Within package (ladder)
UG-07A-S11-A100 | UG-13-S05-A100 | FS | 0 | Crew continuity, front F7
UG-13B-S12-A080 | UG-13-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-23-S01-A080 | UG-13-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-23-S02-A080 | UG-13-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-23-S03-A080 | UG-13-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13-S05-A100 | UG-13-S05-A110 | SS | 2 | Within package (ladder)
UG-13-S05-A100 | UG-13-S05-A110 | FF | 2 | Within package (ladder)
UG-23-S03-A010 | UG-23-S03-A020 | FS | 0 | Within package
UG-13-S05-A030 | UG-23-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-23-S03-A020 | UG-23-S03-A030 | SS | 1 | Within package (ladder)
UG-23-S03-A020 | UG-23-S03-A030 | FF | 2 | Within package (ladder)
UG-13-S05-A030 | UG-23-S03-A030 | FS | 0 | Crew continuity, front F7
UG-23-S03-A030 | UG-23-S03-A040 | SS | 1 | Within package (ladder)
UG-23-S03-A030 | UG-23-S03-A040 | FF | 2 | Within package (ladder)
UG-13-S05-A040 | UG-23-S03-A040 | FS | 0 | Crew continuity, front F7
UG-23-S03-A040 | UG-23-S03-A050 | SS | 1 | Within package (ladder)
UG-23-S03-A040 | UG-23-S03-A050 | FF | 2 | Within package (ladder)
UG-13-S05-A060 | UG-23-S03-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-23-S03-A050 | UG-23-S03-A060 | SS | 10 | Within package (ladder)
UG-23-S03-A050 | UG-23-S03-A060 | FF | 2 | Within package (ladder)
UG-13-S05-A060 | UG-23-S03-A060 | FS | 0 | Crew continuity, front F7
UG-13-S05-A060 | UG-23-S03-A060 | SS | 0 | Shared excavation / dewatering front
UG-13B-S12-A060 | UG-23-S03-A060 | SS | 0 | Shared excavation / dewatering front
UG-23-S03-A060 | UG-23-S03-A070 | SS | 1 | Within package (ladder)
UG-23-S03-A060 | UG-23-S03-A070 | FF | 2 | Within package (ladder)
UG-13-S05-A070 | UG-23-S03-A070 | FS | 0 | Crew continuity, front F7
UG-23-S03-A070 | UG-23-S03-A080 | SS | 2 | Within package (ladder)
UG-23-S03-A070 | UG-23-S03-A080 | FF | 2 | Within package (ladder)
UG-13-S05-A080 | UG-23-S03-A080 | FS | 0 | Crew continuity, front F7
UG-23-S03-A080 | UG-23-S03-A090 | SS | 1 | Within package (ladder)
UG-23-S03-A080 | UG-23-S03-A090 | FF | 2 | Within package (ladder)
UG-23-S03-A090 | UG-23-S03-A100 | SS | 2 | Within package (ladder)
UG-23-S03-A090 | UG-23-S03-A100 | FF | 2 | Within package (ladder)
UG-13-S05-A100 | UG-23-S03-A100 | FS | 0 | Crew continuity, front F7
UG-13-S05-A080 | UG-23-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13B-S12-A080 | UG-23-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-23-S03-A100 | UG-23-S03-A110 | SS | 1 | Within package (ladder)
UG-23-S03-A100 | UG-23-S03-A110 | FF | 2 | Within package (ladder)
UG-23-S02-A010 | UG-23-S02-A020 | FS | 0 | Within package
UG-23-S03-A030 | UG-23-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-23-S02-A020 | UG-23-S02-A030 | SS | 1 | Within package (ladder)
UG-23-S02-A020 | UG-23-S02-A030 | FF | 2 | Within package (ladder)
UG-23-S03-A030 | UG-23-S02-A030 | FS | 0 | Crew continuity, front F7
UG-23-S02-A030 | UG-23-S02-A040 | SS | 1 | Within package (ladder)
UG-23-S02-A030 | UG-23-S02-A040 | FF | 2 | Within package (ladder)
UG-23-S03-A040 | UG-23-S02-A040 | FS | 0 | Crew continuity, front F7
UG-23-S02-A040 | UG-23-S02-A050 | SS | 1 | Within package (ladder)
UG-23-S02-A040 | UG-23-S02-A050 | FF | 2 | Within package (ladder)
UG-23-S03-A060 | UG-23-S02-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-23-S02-A050 | UG-23-S02-A060 | SS | 10 | Within package (ladder)
UG-23-S02-A050 | UG-23-S02-A060 | FF | 2 | Within package (ladder)
UG-23-S03-A060 | UG-23-S02-A060 | FS | 0 | Crew continuity, front F7
UG-13-S05-A060 | UG-23-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-13B-S12-A060 | UG-23-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-23-S02-A060 | UG-23-S02-A070 | SS | 1 | Within package (ladder)
UG-23-S02-A060 | UG-23-S02-A070 | FF | 2 | Within package (ladder)
UG-23-S03-A070 | UG-23-S02-A070 | FS | 0 | Crew continuity, front F7
UG-23-S02-A070 | UG-23-S02-A080 | SS | 2 | Within package (ladder)
UG-23-S02-A070 | UG-23-S02-A080 | FF | 2 | Within package (ladder)
UG-23-S03-A080 | UG-23-S02-A080 | FS | 0 | Crew continuity, front F7
UG-23-S02-A080 | UG-23-S02-A090 | SS | 1 | Within package (ladder)
UG-23-S02-A080 | UG-23-S02-A090 | FF | 2 | Within package (ladder)
UG-23-S02-A090 | UG-23-S02-A100 | SS | 2 | Within package (ladder)
UG-23-S02-A090 | UG-23-S02-A100 | FF | 2 | Within package (ladder)
UG-23-S03-A100 | UG-23-S02-A100 | FS | 0 | Crew continuity, front F7
UG-13-S05-A080 | UG-23-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13B-S12-A080 | UG-23-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-23-S02-A100 | UG-23-S02-A110 | SS | 1 | Within package (ladder)
UG-23-S02-A100 | UG-23-S02-A110 | FF | 2 | Within package (ladder)
UG-23-S01-A010 | UG-23-S01-A020 | FS | 0 | Within package
UG-23-S02-A030 | UG-23-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-23-S01-A020 | UG-23-S01-A030 | SS | 1 | Within package (ladder)
UG-23-S01-A020 | UG-23-S01-A030 | FF | 2 | Within package (ladder)
UG-23-S01-A030 | UG-23-S01-A040 | SS | 1 | Within package (ladder)
UG-23-S01-A030 | UG-23-S01-A040 | FF | 2 | Within package (ladder)
UG-23-S01-A040 | UG-23-S01-A050 | SS | 1 | Within package (ladder)
UG-23-S01-A040 | UG-23-S01-A050 | FF | 2 | Within package (ladder)
UG-23-S01-A050 | UG-23-S01-A060 | SS | 10 | Within package (ladder)
UG-23-S01-A050 | UG-23-S01-A060 | FF | 2 | Within package (ladder)
UG-13-S05-A060 | UG-23-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-13B-S12-A060 | UG-23-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-23-S01-A060 | UG-23-S01-A070 | SS | 1 | Within package (ladder)
UG-23-S01-A060 | UG-23-S01-A070 | FF | 2 | Within package (ladder)
UG-23-S01-A070 | UG-23-S01-A080 | SS | 2 | Within package (ladder)
UG-23-S01-A070 | UG-23-S01-A080 | FF | 2 | Within package (ladder)
UG-23-S02-A080 | UG-23-S01-A080 | FS | 0 | Tie-in laid as closure
UG-23-S01-A080 | UG-23-S01-A090 | SS | 2 | Within package (ladder)
UG-23-S01-A080 | UG-23-S01-A090 | FF | 2 | Within package (ladder)
UG-23-S01-A090 | UG-23-S01-A100 | SS | 2 | Within package (ladder)
UG-23-S01-A090 | UG-23-S01-A100 | FF | 2 | Within package (ladder)
UG-13-S05-A080 | UG-23-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13B-S12-A080 | UG-23-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-23-S01-A100 | UG-23-S01-A110 | SS | 1 | Within package (ladder)
UG-23-S01-A100 | UG-23-S01-A110 | FF | 2 | Within package (ladder)
UG-13B-S09-A010 | UG-13B-S09-A020 | FS | 0 | Within package
UG-23-S02-A030 | UG-13B-S09-A020 | SS | 0 | Set-out one package ahead of piling
UG-13B-S09-A020 | UG-13B-S09-A030 | SS | 1 | Within package (ladder)
UG-13B-S09-A020 | UG-13B-S09-A030 | FF | 2 | Within package (ladder)
UG-23-S02-A030 | UG-13B-S09-A030 | FS | 0 | Crew continuity, front F7
UG-13B-S09-A030 | UG-13B-S09-A040 | SS | 2 | Within package (ladder)
UG-13B-S09-A030 | UG-13B-S09-A040 | FF | 2 | Within package (ladder)
UG-23-S02-A040 | UG-13B-S09-A040 | FS | 0 | Crew continuity, front F7
UG-13B-S09-A040 | UG-13B-S09-A050 | SS | 2 | Within package (ladder)
UG-13B-S09-A040 | UG-13B-S09-A050 | FF | 2 | Within package (ladder)
UG-23-S02-A060 | UG-13B-S09-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13B-S09-A050 | UG-13B-S09-A060 | SS | 10 | Within package (ladder)
UG-13B-S09-A050 | UG-13B-S09-A060 | FF | 2 | Within package (ladder)
UG-23-S02-A060 | UG-13B-S09-A060 | FS | 0 | Crew continuity, front F7
UG-13B-S09-A060 | UG-13B-S09-A070 | SS | 1 | Within package (ladder)
UG-13B-S09-A060 | UG-13B-S09-A070 | FF | 2 | Within package (ladder)
UG-23-S02-A070 | UG-13B-S09-A070 | FS | 0 | Crew continuity, front F7
UG-13B-S09-A070 | UG-13B-S09-A080 | SS | 3 | Within package (ladder)
UG-13B-S09-A070 | UG-13B-S09-A080 | FF | 2 | Within package (ladder)
UG-23-S02-A080 | UG-13B-S09-A080 | FS | 0 | Crew continuity, front F7
UG-13B-S09-A080 | UG-13B-S09-A090 | SS | 1 | Within package (ladder)
UG-13B-S09-A080 | UG-13B-S09-A090 | FF | 2 | Within package (ladder)
UG-13B-S09-A090 | UG-13B-S09-A100 | SS | 2 | Within package (ladder)
UG-13B-S09-A090 | UG-13B-S09-A100 | FF | 2 | Within package (ladder)
UG-23-S02-A100 | UG-13B-S09-A100 | FS | 0 | Crew continuity, front F7
UG-13B-S09-A100 | UG-13B-S09-A110 | SS | 1 | Within package (ladder)
UG-13B-S09-A100 | UG-13B-S09-A110 | FF | 2 | Within package (ladder)
UG-13B-S10-A010 | UG-13B-S10-A020 | FS | 0 | Within package
UG-13B-S09-A030 | UG-13B-S10-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-13B-S10-A020 | UG-13B-S10-A030 | SS | 1 | Within package (ladder)
UG-13B-S10-A020 | UG-13B-S10-A030 | FF | 2 | Within package (ladder)
UG-13B-S10-A030 | UG-13B-S10-A040 | SS | 1 | Within package (ladder)
UG-13B-S10-A030 | UG-13B-S10-A040 | FF | 2 | Within package (ladder)
UG-13B-S10-A040 | UG-13B-S10-A050 | SS | 1 | Within package (ladder)
UG-13B-S10-A040 | UG-13B-S10-A050 | FF | 2 | Within package (ladder)
UG-13B-S10-A050 | UG-13B-S10-A060 | SS | 10 | Within package (ladder)
UG-13B-S10-A050 | UG-13B-S10-A060 | FF | 2 | Within package (ladder)
UG-13B-S10-A060 | UG-13B-S10-A070 | SS | 1 | Within package (ladder)
UG-13B-S10-A060 | UG-13B-S10-A070 | FF | 2 | Within package (ladder)
UG-13B-S10-A070 | UG-13B-S10-A080 | SS | 2 | Within package (ladder)
UG-13B-S10-A070 | UG-13B-S10-A080 | FF | 2 | Within package (ladder)
UG-13B-S09-A080 | UG-13B-S10-A080 | FS | 0 | Tie-in laid as closure
UG-13B-S10-A080 | UG-13B-S10-A090 | SS | 2 | Within package (ladder)
UG-13B-S10-A080 | UG-13B-S10-A090 | FF | 2 | Within package (ladder)
UG-13B-S10-A090 | UG-13B-S10-A100 | SS | 2 | Within package (ladder)
UG-13B-S10-A090 | UG-13B-S10-A100 | FF | 2 | Within package (ladder)
UG-13B-S10-A100 | UG-13B-S10-A110 | SS | 1 | Within package (ladder)
UG-13B-S10-A100 | UG-13B-S10-A110 | FF | 2 | Within package (ladder)
UG-13B-S08-A010 | UG-13B-S08-A020 | FS | 0 | Within package
UG-13B-S09-A030 | UG-13B-S08-A020 | SS | 0 | Set-out one package ahead of piling
UG-13B-S08-A020 | UG-13B-S08-A030 | SS | 1 | Within package (ladder)
UG-13B-S08-A020 | UG-13B-S08-A030 | FF | 2 | Within package (ladder)
UG-13B-S09-A030 | UG-13B-S08-A030 | FS | 0 | Crew continuity, front F7
UG-13B-S08-A030 | UG-13B-S08-A040 | SS | 1 | Within package (ladder)
UG-13B-S08-A030 | UG-13B-S08-A040 | FF | 2 | Within package (ladder)
UG-13B-S09-A040 | UG-13B-S08-A040 | FS | 0 | Crew continuity, front F7
UG-13B-S08-A040 | UG-13B-S08-A050 | SS | 1 | Within package (ladder)
UG-13B-S08-A040 | UG-13B-S08-A050 | FF | 2 | Within package (ladder)
UG-13B-S09-A060 | UG-13B-S08-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13B-S08-A050 | UG-13B-S08-A060 | SS | 10 | Within package (ladder)
UG-13B-S08-A050 | UG-13B-S08-A060 | FF | 2 | Within package (ladder)
UG-13B-S09-A060 | UG-13B-S08-A060 | FS | 0 | Crew continuity, front F7
UG-12-S03-A100 | UG-13B-S08-A060 | FS | 0 | Deeper line first
UG-13B-S08-A060 | UG-13B-S08-A070 | SS | 1 | Within package (ladder)
UG-13B-S08-A060 | UG-13B-S08-A070 | FF | 2 | Within package (ladder)
UG-13B-S09-A070 | UG-13B-S08-A070 | FS | 0 | Crew continuity, front F7
UG-13B-S08-A070 | UG-13B-S08-A080 | SS | 2 | Within package (ladder)
UG-13B-S08-A070 | UG-13B-S08-A080 | FF | 2 | Within package (ladder)
UG-13B-S09-A080 | UG-13B-S08-A080 | FS | 0 | Crew continuity, front F7
UG-13B-S08-A080 | UG-13B-S08-A090 | SS | 1 | Within package (ladder)
UG-13B-S08-A080 | UG-13B-S08-A090 | FF | 2 | Within package (ladder)
UG-13B-S08-A090 | UG-13B-S08-A100 | SS | 2 | Within package (ladder)
UG-13B-S08-A090 | UG-13B-S08-A100 | FF | 2 | Within package (ladder)
UG-13B-S09-A100 | UG-13B-S08-A100 | FS | 0 | Crew continuity, front F7
UG-13B-S08-A100 | UG-13B-S08-A110 | SS | 1 | Within package (ladder)
UG-13B-S08-A100 | UG-13B-S08-A110 | FF | 2 | Within package (ladder)
UG-13B-S04-A010 | UG-13B-S04-A020 | FS | 0 | Within package
UG-13B-S08-A030 | UG-13B-S04-A020 | SS | 0 | Set-out one package ahead of piling
UG-13B-S04-A020 | UG-13B-S04-A030 | SS | 1 | Within package (ladder)
UG-13B-S04-A020 | UG-13B-S04-A030 | FF | 2 | Within package (ladder)
UG-13B-S08-A030 | UG-13B-S04-A030 | FS | 0 | Crew continuity, front F7
UG-13B-S04-A030 | UG-13B-S04-A040 | SS | 2 | Within package (ladder)
UG-13B-S04-A030 | UG-13B-S04-A040 | FF | 2 | Within package (ladder)
UG-13B-S08-A040 | UG-13B-S04-A040 | FS | 0 | Crew continuity, front F7
UG-13B-S04-A040 | UG-13B-S04-A050 | SS | 1 | Within package (ladder)
UG-13B-S04-A040 | UG-13B-S04-A050 | FF | 2 | Within package (ladder)
UG-13B-S08-A060 | UG-13B-S04-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13B-S04-A050 | UG-13B-S04-A060 | SS | 10 | Within package (ladder)
UG-13B-S04-A050 | UG-13B-S04-A060 | FF | 2 | Within package (ladder)
UG-13B-S08-A060 | UG-13B-S04-A060 | FS | 0 | Crew continuity, front F7
UG-13B-S04-A060 | UG-13B-S04-A070 | SS | 1 | Within package (ladder)
UG-13B-S04-A060 | UG-13B-S04-A070 | FF | 2 | Within package (ladder)
UG-13B-S08-A070 | UG-13B-S04-A070 | FS | 0 | Crew continuity, front F7
UG-13B-S04-A070 | UG-13B-S04-A080 | SS | 3 | Within package (ladder)
UG-13B-S04-A070 | UG-13B-S04-A080 | FF | 2 | Within package (ladder)
UG-13B-S08-A080 | UG-13B-S04-A080 | FS | 0 | Crew continuity, front F7
UG-13B-S04-A080 | UG-13B-S04-A090 | SS | 2 | Within package (ladder)
UG-13B-S04-A080 | UG-13B-S04-A090 | FF | 2 | Within package (ladder)
UG-13B-S04-A090 | UG-13B-S04-A100 | SS | 2 | Within package (ladder)
UG-13B-S04-A090 | UG-13B-S04-A100 | FF | 2 | Within package (ladder)
UG-13B-S08-A100 | UG-13B-S04-A100 | FS | 0 | Crew continuity, front F7
UG-13B-S04-A100 | UG-13B-S04-A110 | SS | 1 | Within package (ladder)
UG-13B-S04-A100 | UG-13B-S04-A110 | FF | 2 | Within package (ladder)
UG-13B-S03-A010 | UG-13B-S03-A020 | FS | 0 | Within package
UG-13B-S04-A030 | UG-13B-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-13B-S03-A020 | UG-13B-S03-A030 | SS | 1 | Within package (ladder)
UG-13B-S03-A020 | UG-13B-S03-A030 | FF | 2 | Within package (ladder)
UG-13B-S04-A030 | UG-13B-S03-A030 | FS | 0 | Crew continuity, front F7
UG-13B-S03-A030 | UG-13B-S03-A040 | SS | 2 | Within package (ladder)
UG-13B-S03-A030 | UG-13B-S03-A040 | FF | 2 | Within package (ladder)
UG-13B-S04-A040 | UG-13B-S03-A040 | FS | 0 | Crew continuity, front F7
UG-13B-S03-A040 | UG-13B-S03-A050 | SS | 1 | Within package (ladder)
UG-13B-S03-A040 | UG-13B-S03-A050 | FF | 2 | Within package (ladder)
UG-13B-S04-A060 | UG-13B-S03-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13B-S03-A050 | UG-13B-S03-A060 | SS | 10 | Within package (ladder)
UG-13B-S03-A050 | UG-13B-S03-A060 | FF | 2 | Within package (ladder)
UG-13B-S04-A060 | UG-13B-S03-A060 | FS | 0 | Crew continuity, front F7
UG-13B-S03-A060 | UG-13B-S03-A070 | SS | 1 | Within package (ladder)
UG-13B-S03-A060 | UG-13B-S03-A070 | FF | 2 | Within package (ladder)
UG-13B-S04-A070 | UG-13B-S03-A070 | FS | 0 | Crew continuity, front F7
UG-13B-S03-A070 | UG-13B-S03-A080 | SS | 2 | Within package (ladder)
UG-13B-S03-A070 | UG-13B-S03-A080 | FF | 2 | Within package (ladder)
UG-13B-S04-A080 | UG-13B-S03-A080 | FS | 0 | Crew continuity, front F7
UG-13B-S03-A080 | UG-13B-S03-A090 | SS | 1 | Within package (ladder)
UG-13B-S03-A080 | UG-13B-S03-A090 | FF | 2 | Within package (ladder)
UG-13B-S03-A090 | UG-13B-S03-A100 | SS | 2 | Within package (ladder)
UG-13B-S03-A090 | UG-13B-S03-A100 | FF | 2 | Within package (ladder)
UG-13B-S04-A100 | UG-13B-S03-A100 | FS | 0 | Crew continuity, front F7
UG-13B-S03-A100 | UG-13B-S03-A110 | SS | 1 | Within package (ladder)
UG-13B-S03-A100 | UG-13B-S03-A110 | FF | 2 | Within package (ladder)
UG-13B-S02-A010 | UG-13B-S02-A020 | FS | 0 | Within package
UG-13B-S03-A030 | UG-13B-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-13B-S02-A020 | UG-13B-S02-A030 | SS | 1 | Within package (ladder)
UG-13B-S02-A020 | UG-13B-S02-A030 | FF | 2 | Within package (ladder)
UG-13B-S03-A030 | UG-13B-S02-A030 | FS | 0 | Crew continuity, front F7
UG-13B-S02-A030 | UG-13B-S02-A040 | SS | 2 | Within package (ladder)
UG-13B-S02-A030 | UG-13B-S02-A040 | FF | 2 | Within package (ladder)
UG-13B-S03-A040 | UG-13B-S02-A040 | FS | 0 | Crew continuity, front F7
UG-13B-S02-A040 | UG-13B-S02-A050 | SS | 2 | Within package (ladder)
UG-13B-S02-A040 | UG-13B-S02-A050 | FF | 2 | Within package (ladder)
UG-13B-S03-A060 | UG-13B-S02-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13B-S02-A050 | UG-13B-S02-A060 | SS | 10 | Within package (ladder)
UG-13B-S02-A050 | UG-13B-S02-A060 | FF | 2 | Within package (ladder)
UG-13B-S03-A060 | UG-13B-S02-A060 | FS | 0 | Crew continuity, front F7
UG-13B-S02-A060 | UG-13B-S02-A070 | SS | 1 | Within package (ladder)
UG-13B-S02-A060 | UG-13B-S02-A070 | FF | 2 | Within package (ladder)
UG-13B-S03-A070 | UG-13B-S02-A070 | FS | 0 | Crew continuity, front F7
UG-13B-S02-A070 | UG-13B-S02-A080 | SS | 3 | Within package (ladder)
UG-13B-S02-A070 | UG-13B-S02-A080 | FF | 2 | Within package (ladder)
UG-13B-S03-A080 | UG-13B-S02-A080 | FS | 0 | Crew continuity, front F7
UG-13B-S02-A080 | UG-13B-S02-A090 | SS | 2 | Within package (ladder)
UG-13B-S02-A080 | UG-13B-S02-A090 | FF | 2 | Within package (ladder)
UG-13B-S02-A090 | UG-13B-S02-A100 | SS | 2 | Within package (ladder)
UG-13B-S02-A090 | UG-13B-S02-A100 | FF | 2 | Within package (ladder)
UG-13B-S03-A100 | UG-13B-S02-A100 | FS | 0 | Crew continuity, front F7
UG-13B-S02-A100 | UG-13B-S02-A110 | SS | 1 | Within package (ladder)
UG-13B-S02-A100 | UG-13B-S02-A110 | FF | 2 | Within package (ladder)
UG-13A-S07-A010 | UG-13A-S07-A020 | FS | 0 | Within package
UG-13B-S02-A030 | UG-13A-S07-A020 | SS | 0 | Set-out one package ahead of piling
UG-13A-S07-A020 | UG-13A-S07-A030 | SS | 1 | Within package (ladder)
UG-13A-S07-A020 | UG-13A-S07-A030 | FF | 2 | Within package (ladder)
UG-13B-S02-A030 | UG-13A-S07-A030 | FS | 0 | Crew continuity, front F7
UG-13A-S07-A030 | UG-13A-S07-A040 | SS | 1 | Within package (ladder)
UG-13A-S07-A030 | UG-13A-S07-A040 | FF | 2 | Within package (ladder)
UG-13B-S02-A040 | UG-13A-S07-A040 | FS | 0 | Crew continuity, front F7
UG-13A-S07-A040 | UG-13A-S07-A050 | SS | 1 | Within package (ladder)
UG-13A-S07-A040 | UG-13A-S07-A050 | FF | 2 | Within package (ladder)
UG-13B-S02-A060 | UG-13A-S07-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13A-S07-A050 | UG-13A-S07-A060 | SS | 10 | Within package (ladder)
UG-13A-S07-A050 | UG-13A-S07-A060 | FF | 2 | Within package (ladder)
UG-13B-S02-A060 | UG-13A-S07-A060 | FS | 0 | Crew continuity, front F7
UG-13A-S07-A060 | UG-13A-S07-A070 | SS | 1 | Within package (ladder)
UG-13A-S07-A060 | UG-13A-S07-A070 | FF | 2 | Within package (ladder)
UG-13B-S02-A070 | UG-13A-S07-A070 | FS | 0 | Crew continuity, front F7
UG-13A-S07-A070 | UG-13A-S07-A080 | SS | 2 | Within package (ladder)
UG-13A-S07-A070 | UG-13A-S07-A080 | FF | 2 | Within package (ladder)
UG-13B-S02-A080 | UG-13A-S07-A080 | FS | 0 | Crew continuity, front F7
UG-13A-S07-A080 | UG-13A-S07-A090 | SS | 1 | Within package (ladder)
UG-13A-S07-A080 | UG-13A-S07-A090 | FF | 2 | Within package (ladder)
UG-13A-S07-A090 | UG-13A-S07-A100 | SS | 2 | Within package (ladder)
UG-13A-S07-A090 | UG-13A-S07-A100 | FF | 2 | Within package (ladder)
UG-13B-S02-A100 | UG-13A-S07-A100 | FS | 0 | Crew continuity, front F7
UG-13A-S07-A100 | UG-13A-S07-A110 | SS | 1 | Within package (ladder)
UG-13A-S07-A100 | UG-13A-S07-A110 | FF | 2 | Within package (ladder)
UG-13-S02-A010 | UG-13-S02-A020 | FS | 0 | Within package
UG-13A-S07-A030 | UG-13-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-13-S02-A020 | UG-13-S02-A030 | SS | 1 | Within package (ladder)
UG-13-S02-A020 | UG-13-S02-A030 | FF | 2 | Within package (ladder)
UG-13A-S07-A030 | UG-13-S02-A030 | FS | 0 | Crew continuity, front F7
UG-13-S02-A030 | UG-13-S02-A040 | SS | 2 | Within package (ladder)
UG-13-S02-A030 | UG-13-S02-A040 | FF | 2 | Within package (ladder)
UG-13A-S07-A040 | UG-13-S02-A040 | FS | 0 | Crew continuity, front F7
UG-13-S02-A040 | UG-13-S02-A050 | SS | 2 | Within package (ladder)
UG-13-S02-A040 | UG-13-S02-A050 | FF | 2 | Within package (ladder)
UG-13A-S07-A060 | UG-13-S02-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13-S02-A050 | UG-13-S02-A060 | SS | 10 | Within package (ladder)
UG-13-S02-A050 | UG-13-S02-A060 | FF | 2 | Within package (ladder)
UG-13A-S07-A060 | UG-13-S02-A060 | FS | 0 | Crew continuity, front F7
UG-13-S02-A060 | UG-13-S02-A070 | SS | 2 | Within package (ladder)
UG-13-S02-A060 | UG-13-S02-A070 | FF | 2 | Within package (ladder)
UG-13A-S07-A070 | UG-13-S02-A070 | FS | 0 | Crew continuity, front F7
UG-13-S02-A070 | UG-13-S02-A080 | SS | 3 | Within package (ladder)
UG-13-S02-A070 | UG-13-S02-A080 | FF | 2 | Within package (ladder)
UG-13A-S07-A080 | UG-13-S02-A080 | FS | 0 | Crew continuity, front F7
UG-13-S02-A080 | UG-13-S02-A090 | SS | 2 | Within package (ladder)
UG-13-S02-A080 | UG-13-S02-A090 | FF | 2 | Within package (ladder)
UG-13-S02-A090 | UG-13-S02-A100 | SS | 2 | Within package (ladder)
UG-13-S02-A090 | UG-13-S02-A100 | FF | 2 | Within package (ladder)
UG-13A-S07-A100 | UG-13-S02-A100 | FS | 0 | Crew continuity, front F7
UG-13A-S02-A080 | UG-13-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13A-S16-A080 | UG-13-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13-S02-A100 | UG-13-S02-A110 | SS | 1 | Within package (ladder)
UG-13-S02-A100 | UG-13-S02-A110 | FF | 2 | Within package (ladder)
UG-13A-S02-A010 | UG-13A-S02-A020 | FS | 0 | Within package
UG-13-S02-A030 | UG-13A-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-13A-S02-A020 | UG-13A-S02-A030 | SS | 1 | Within package (ladder)
UG-13A-S02-A020 | UG-13A-S02-A030 | FF | 2 | Within package (ladder)
UG-13-S02-A030 | UG-13A-S02-A030 | FS | 0 | Crew continuity, front F7
UG-13A-S02-A030 | UG-13A-S02-A040 | SS | 2 | Within package (ladder)
UG-13A-S02-A030 | UG-13A-S02-A040 | FF | 2 | Within package (ladder)
UG-13-S02-A040 | UG-13A-S02-A040 | FS | 0 | Crew continuity, front F7
UG-13A-S02-A040 | UG-13A-S02-A050 | SS | 2 | Within package (ladder)
UG-13A-S02-A040 | UG-13A-S02-A050 | FF | 2 | Within package (ladder)
UG-13-S02-A060 | UG-13A-S02-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13A-S02-A050 | UG-13A-S02-A060 | SS | 10 | Within package (ladder)
UG-13A-S02-A050 | UG-13A-S02-A060 | FF | 2 | Within package (ladder)
UG-13-S02-A060 | UG-13A-S02-A060 | FS | 0 | Crew continuity, front F7
UG-13-S02-A060 | UG-13A-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-13A-S02-A060 | UG-13A-S02-A070 | SS | 1 | Within package (ladder)
UG-13A-S02-A060 | UG-13A-S02-A070 | FF | 2 | Within package (ladder)
UG-13-S02-A070 | UG-13A-S02-A070 | FS | 0 | Crew continuity, front F7
UG-13A-S02-A070 | UG-13A-S02-A080 | SS | 3 | Within package (ladder)
UG-13A-S02-A070 | UG-13A-S02-A080 | FF | 2 | Within package (ladder)
UG-13-S02-A080 | UG-13A-S02-A080 | FS | 0 | Crew continuity, front F7
UG-13A-S02-A080 | UG-13A-S02-A090 | SS | 2 | Within package (ladder)
UG-13A-S02-A080 | UG-13A-S02-A090 | FF | 2 | Within package (ladder)
UG-13A-S02-A090 | UG-13A-S02-A100 | SS | 2 | Within package (ladder)
UG-13A-S02-A090 | UG-13A-S02-A100 | FF | 2 | Within package (ladder)
UG-13-S02-A100 | UG-13A-S02-A100 | FS | 0 | Crew continuity, front F7
UG-13-S02-A080 | UG-13A-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13A-S02-A100 | UG-13A-S02-A110 | SS | 1 | Within package (ladder)
UG-13A-S02-A100 | UG-13A-S02-A110 | FF | 2 | Within package (ladder)
UG-13-S01-A010 | UG-13-S01-A020 | FS | 0 | Within package
UG-13-S02-A030 | UG-13-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-13-S01-A020 | UG-13-S01-A030 | SS | 1 | Within package (ladder)
UG-13-S01-A020 | UG-13-S01-A030 | FF | 2 | Within package (ladder)
UG-13-S01-A030 | UG-13-S01-A040 | SS | 2 | Within package (ladder)
UG-13-S01-A030 | UG-13-S01-A040 | FF | 2 | Within package (ladder)
UG-13-S01-A040 | UG-13-S01-A050 | SS | 1 | Within package (ladder)
UG-13-S01-A040 | UG-13-S01-A050 | FF | 2 | Within package (ladder)
UG-13-S01-A050 | UG-13-S01-A060 | SS | 10 | Within package (ladder)
UG-13-S01-A050 | UG-13-S01-A060 | FF | 2 | Within package (ladder)
UG-13-S01-A060 | UG-13-S01-A070 | SS | 1 | Within package (ladder)
UG-13-S01-A060 | UG-13-S01-A070 | FF | 2 | Within package (ladder)
UG-13-S01-A070 | UG-13-S01-A080 | SS | 2 | Within package (ladder)
UG-13-S01-A070 | UG-13-S01-A080 | FF | 2 | Within package (ladder)
UG-13-S02-A080 | UG-13-S01-A080 | FS | 0 | Tie-in laid as closure
UG-13-S01-A080 | UG-13-S01-A090 | SS | 3 | Within package (ladder)
UG-13-S01-A080 | UG-13-S01-A090 | FF | 2 | Within package (ladder)
UG-13-S01-A090 | UG-13-S01-A100 | SS | 2 | Within package (ladder)
UG-13-S01-A090 | UG-13-S01-A100 | FF | 2 | Within package (ladder)
UG-13A-S08-A080 | UG-13-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13A-S11-A080 | UG-13-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13A-S12-A080 | UG-13-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13A-S16-A080 | UG-13-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13-S01-A100 | UG-13-S01-A110 | SS | 1 | Within package (ladder)
UG-13-S01-A100 | UG-13-S01-A110 | FF | 2 | Within package (ladder)
UG-13A-S16-A010 | UG-13A-S16-A020 | FS | 0 | Within package
UG-13A-S02-A030 | UG-13A-S16-A020 | SS | 0 | Set-out one package ahead of piling
UG-13A-S16-A020 | UG-13A-S16-A030 | SS | 1 | Within package (ladder)
UG-13A-S16-A020 | UG-13A-S16-A030 | FF | 2 | Within package (ladder)
UG-13A-S02-A030 | UG-13A-S16-A030 | FS | 0 | Crew continuity, front F7
UG-13A-S16-A030 | UG-13A-S16-A040 | SS | 1 | Within package (ladder)
UG-13A-S16-A030 | UG-13A-S16-A040 | FF | 2 | Within package (ladder)
UG-13A-S02-A040 | UG-13A-S16-A040 | FS | 0 | Crew continuity, front F7
UG-13A-S16-A040 | UG-13A-S16-A050 | SS | 1 | Within package (ladder)
UG-13A-S16-A040 | UG-13A-S16-A050 | FF | 2 | Within package (ladder)
UG-13A-S02-A060 | UG-13A-S16-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13A-S16-A050 | UG-13A-S16-A060 | SS | 10 | Within package (ladder)
UG-13A-S16-A050 | UG-13A-S16-A060 | FF | 2 | Within package (ladder)
UG-13A-S02-A060 | UG-13A-S16-A060 | FS | 0 | Crew continuity, front F7
UG-13-S01-A060 | UG-13A-S16-A060 | SS | 0 | Shared excavation / dewatering front
UG-13-S02-A060 | UG-13A-S16-A060 | SS | 0 | Shared excavation / dewatering front
UG-13A-S16-A060 | UG-13A-S16-A070 | SS | 1 | Within package (ladder)
UG-13A-S16-A060 | UG-13A-S16-A070 | FF | 2 | Within package (ladder)
UG-13A-S02-A070 | UG-13A-S16-A070 | FS | 0 | Crew continuity, front F7
UG-13A-S16-A070 | UG-13A-S16-A080 | SS | 2 | Within package (ladder)
UG-13A-S16-A070 | UG-13A-S16-A080 | FF | 2 | Within package (ladder)
UG-13A-S02-A080 | UG-13A-S16-A080 | FS | 0 | Crew continuity, front F7
UG-13A-S16-A080 | UG-13A-S16-A090 | SS | 1 | Within package (ladder)
UG-13A-S16-A080 | UG-13A-S16-A090 | FF | 2 | Within package (ladder)
UG-13A-S16-A090 | UG-13A-S16-A100 | SS | 2 | Within package (ladder)
UG-13A-S16-A090 | UG-13A-S16-A100 | FF | 2 | Within package (ladder)
UG-13A-S02-A100 | UG-13A-S16-A100 | FS | 0 | Crew continuity, front F7
UG-13-S01-A080 | UG-13A-S16-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13-S02-A080 | UG-13A-S16-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13A-S16-A100 | UG-13A-S16-A110 | SS | 1 | Within package (ladder)
UG-13A-S16-A100 | UG-13A-S16-A110 | FF | 2 | Within package (ladder)
UG-13A-S08-A010 | UG-13A-S08-A020 | FS | 0 | Within package
UG-13A-S07-A030 | UG-13A-S08-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-13A-S08-A020 | UG-13A-S08-A030 | SS | 1 | Within package (ladder)
UG-13A-S08-A020 | UG-13A-S08-A030 | FF | 2 | Within package (ladder)
UG-13A-S08-A030 | UG-13A-S08-A040 | SS | 1 | Within package (ladder)
UG-13A-S08-A030 | UG-13A-S08-A040 | FF | 2 | Within package (ladder)
UG-13A-S08-A040 | UG-13A-S08-A050 | SS | 1 | Within package (ladder)
UG-13A-S08-A040 | UG-13A-S08-A050 | FF | 2 | Within package (ladder)
UG-13A-S08-A050 | UG-13A-S08-A060 | SS | 10 | Within package (ladder)
UG-13A-S08-A050 | UG-13A-S08-A060 | FF | 2 | Within package (ladder)
UG-13-S01-A060 | UG-13A-S08-A060 | SS | 0 | Shared excavation / dewatering front
UG-13A-S08-A060 | UG-13A-S08-A070 | SS | 1 | Within package (ladder)
UG-13A-S08-A060 | UG-13A-S08-A070 | FF | 2 | Within package (ladder)
UG-13A-S08-A070 | UG-13A-S08-A080 | SS | 2 | Within package (ladder)
UG-13A-S08-A070 | UG-13A-S08-A080 | FF | 2 | Within package (ladder)
UG-13A-S07-A080 | UG-13A-S08-A080 | FS | 0 | Tie-in laid as closure
UG-13A-S08-A080 | UG-13A-S08-A090 | SS | 2 | Within package (ladder)
UG-13A-S08-A080 | UG-13A-S08-A090 | FF | 2 | Within package (ladder)
UG-13A-S08-A090 | UG-13A-S08-A100 | SS | 2 | Within package (ladder)
UG-13A-S08-A090 | UG-13A-S08-A100 | FF | 2 | Within package (ladder)
UG-13-S01-A080 | UG-13A-S08-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13A-S08-A100 | UG-13A-S08-A110 | SS | 1 | Within package (ladder)
UG-13A-S08-A100 | UG-13A-S08-A110 | FF | 2 | Within package (ladder)
UG-13A-S12-A010 | UG-13A-S12-A020 | FS | 0 | Within package
UG-13A-S16-A030 | UG-13A-S12-A020 | SS | 0 | Set-out one package ahead of piling
UG-13A-S12-A020 | UG-13A-S12-A030 | SS | 1 | Within package (ladder)
UG-13A-S12-A020 | UG-13A-S12-A030 | FF | 2 | Within package (ladder)
UG-13A-S16-A030 | UG-13A-S12-A030 | FS | 0 | Crew continuity, front F7
UG-13A-S12-A030 | UG-13A-S12-A040 | SS | 1 | Within package (ladder)
UG-13A-S12-A030 | UG-13A-S12-A040 | FF | 2 | Within package (ladder)
UG-13A-S16-A040 | UG-13A-S12-A040 | FS | 0 | Crew continuity, front F7
UG-13A-S12-A040 | UG-13A-S12-A050 | SS | 1 | Within package (ladder)
UG-13A-S12-A040 | UG-13A-S12-A050 | FF | 2 | Within package (ladder)
UG-13A-S16-A060 | UG-13A-S12-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13A-S12-A050 | UG-13A-S12-A060 | SS | 10 | Within package (ladder)
UG-13A-S12-A050 | UG-13A-S12-A060 | FF | 2 | Within package (ladder)
UG-13A-S16-A060 | UG-13A-S12-A060 | FS | 0 | Crew continuity, front F7
UG-13-S01-A060 | UG-13A-S12-A060 | SS | 0 | Shared excavation / dewatering front
UG-13A-S12-A060 | UG-13A-S12-A070 | SS | 1 | Within package (ladder)
UG-13A-S12-A060 | UG-13A-S12-A070 | FF | 2 | Within package (ladder)
UG-13A-S16-A070 | UG-13A-S12-A070 | FS | 0 | Crew continuity, front F7
UG-13A-S12-A070 | UG-13A-S12-A080 | SS | 2 | Within package (ladder)
UG-13A-S12-A070 | UG-13A-S12-A080 | FF | 2 | Within package (ladder)
UG-13A-S16-A080 | UG-13A-S12-A080 | FS | 0 | Crew continuity, front F7
UG-13A-S12-A080 | UG-13A-S12-A090 | SS | 1 | Within package (ladder)
UG-13A-S12-A080 | UG-13A-S12-A090 | FF | 2 | Within package (ladder)
UG-13A-S12-A090 | UG-13A-S12-A100 | SS | 2 | Within package (ladder)
UG-13A-S12-A090 | UG-13A-S12-A100 | FF | 2 | Within package (ladder)
UG-13A-S16-A100 | UG-13A-S12-A100 | FS | 0 | Crew continuity, front F7
UG-13-S01-A080 | UG-13A-S12-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13A-S12-A100 | UG-13A-S12-A110 | SS | 1 | Within package (ladder)
UG-13A-S12-A100 | UG-13A-S12-A110 | FF | 2 | Within package (ladder)
UG-13A-S11-A010 | UG-13A-S11-A020 | FS | 0 | Within package
UG-13A-S12-A030 | UG-13A-S11-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-13A-S11-A020 | UG-13A-S11-A030 | SS | 1 | Within package (ladder)
UG-13A-S11-A020 | UG-13A-S11-A030 | FF | 2 | Within package (ladder)
UG-13A-S11-A030 | UG-13A-S11-A040 | SS | 1 | Within package (ladder)
UG-13A-S11-A030 | UG-13A-S11-A040 | FF | 2 | Within package (ladder)
UG-13A-S11-A040 | UG-13A-S11-A050 | SS | 1 | Within package (ladder)
UG-13A-S11-A040 | UG-13A-S11-A050 | FF | 2 | Within package (ladder)
UG-13A-S11-A050 | UG-13A-S11-A060 | SS | 10 | Within package (ladder)
UG-13A-S11-A050 | UG-13A-S11-A060 | FF | 2 | Within package (ladder)
UG-13-S01-A060 | UG-13A-S11-A060 | SS | 0 | Shared excavation / dewatering front
UG-13A-S11-A060 | UG-13A-S11-A070 | SS | 1 | Within package (ladder)
UG-13A-S11-A060 | UG-13A-S11-A070 | FF | 2 | Within package (ladder)
UG-13A-S11-A070 | UG-13A-S11-A080 | SS | 2 | Within package (ladder)
UG-13A-S11-A070 | UG-13A-S11-A080 | FF | 2 | Within package (ladder)
UG-13A-S12-A080 | UG-13A-S11-A080 | FS | 0 | Tie-in laid as closure
UG-13A-S11-A080 | UG-13A-S11-A090 | SS | 2 | Within package (ladder)
UG-13A-S11-A080 | UG-13A-S11-A090 | FF | 2 | Within package (ladder)
UG-13A-S11-A090 | UG-13A-S11-A100 | SS | 2 | Within package (ladder)
UG-13A-S11-A090 | UG-13A-S11-A100 | FF | 2 | Within package (ladder)
UG-13-S01-A080 | UG-13A-S11-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13A-S11-A100 | UG-13A-S11-A110 | SS | 1 | Within package (ladder)
UG-13A-S11-A100 | UG-13A-S11-A110 | FF | 2 | Within package (ladder)
UG-13A-S01-A010 | UG-13A-S01-A020 | FS | 0 | Within package
UG-13A-S02-A030 | UG-13A-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-13A-S01-A020 | UG-13A-S01-A030 | SS | 1 | Within package (ladder)
UG-13A-S01-A020 | UG-13A-S01-A030 | FF | 2 | Within package (ladder)
UG-13A-S01-A030 | UG-13A-S01-A040 | SS | 1 | Within package (ladder)
UG-13A-S01-A030 | UG-13A-S01-A040 | FF | 2 | Within package (ladder)
UG-13A-S01-A040 | UG-13A-S01-A050 | SS | 1 | Within package (ladder)
UG-13A-S01-A040 | UG-13A-S01-A050 | FF | 2 | Within package (ladder)
UG-13A-S01-A050 | UG-13A-S01-A060 | SS | 10 | Within package (ladder)
UG-13A-S01-A050 | UG-13A-S01-A060 | FF | 2 | Within package (ladder)
UG-13A-S01-A060 | UG-13A-S01-A070 | SS | 1 | Within package (ladder)
UG-13A-S01-A060 | UG-13A-S01-A070 | FF | 2 | Within package (ladder)
UG-13A-S01-A070 | UG-13A-S01-A080 | SS | 2 | Within package (ladder)
UG-13A-S01-A070 | UG-13A-S01-A080 | FF | 2 | Within package (ladder)
UG-13A-S02-A080 | UG-13A-S01-A080 | FS | 0 | Tie-in laid as closure
UG-13A-S01-A080 | UG-13A-S01-A090 | SS | 2 | Within package (ladder)
UG-13A-S01-A080 | UG-13A-S01-A090 | FF | 2 | Within package (ladder)
UG-13A-S01-A090 | UG-13A-S01-A100 | SS | 2 | Within package (ladder)
UG-13A-S01-A090 | UG-13A-S01-A100 | FF | 2 | Within package (ladder)
UG-13A-S01-A100 | UG-13A-S01-A110 | SS | 1 | Within package (ladder)
UG-13A-S01-A100 | UG-13A-S01-A110 | FF | 2 | Within package (ladder)
UG-13A-S06-A010 | UG-13A-S06-A020 | FS | 0 | Within package
UG-13A-S12-A030 | UG-13A-S06-A020 | SS | 0 | Set-out one package ahead of piling
UG-13A-S06-A020 | UG-13A-S06-A030 | SS | 1 | Within package (ladder)
UG-13A-S06-A020 | UG-13A-S06-A030 | FF | 2 | Within package (ladder)
UG-13A-S12-A030 | UG-13A-S06-A030 | FS | 0 | Crew continuity, front F7
UG-13A-S06-A030 | UG-13A-S06-A040 | SS | 2 | Within package (ladder)
UG-13A-S06-A030 | UG-13A-S06-A040 | FF | 2 | Within package (ladder)
UG-13A-S12-A040 | UG-13A-S06-A040 | FS | 0 | Crew continuity, front F7
UG-13A-S06-A040 | UG-13A-S06-A050 | SS | 1 | Within package (ladder)
UG-13A-S06-A040 | UG-13A-S06-A050 | FF | 2 | Within package (ladder)
UG-13A-S12-A060 | UG-13A-S06-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13A-S06-A050 | UG-13A-S06-A060 | SS | 10 | Within package (ladder)
UG-13A-S06-A050 | UG-13A-S06-A060 | FF | 2 | Within package (ladder)
UG-13A-S12-A060 | UG-13A-S06-A060 | FS | 0 | Crew continuity, front F7
UG-13A-S06-A060 | UG-13A-S06-A070 | SS | 1 | Within package (ladder)
UG-13A-S06-A060 | UG-13A-S06-A070 | FF | 2 | Within package (ladder)
UG-13A-S12-A070 | UG-13A-S06-A070 | FS | 0 | Crew continuity, front F7
UG-13A-S06-A070 | UG-13A-S06-A080 | SS | 2 | Within package (ladder)
UG-13A-S06-A070 | UG-13A-S06-A080 | FF | 2 | Within package (ladder)
UG-13A-S12-A080 | UG-13A-S06-A080 | FS | 0 | Crew continuity, front F7
UG-13A-S06-A080 | UG-13A-S06-A090 | SS | 1 | Within package (ladder)
UG-13A-S06-A080 | UG-13A-S06-A090 | FF | 2 | Within package (ladder)
UG-13A-S06-A090 | UG-13A-S06-A100 | SS | 2 | Within package (ladder)
UG-13A-S06-A090 | UG-13A-S06-A100 | FF | 2 | Within package (ladder)
UG-13A-S12-A100 | UG-13A-S06-A100 | FS | 0 | Crew continuity, front F7
UG-13A-S06-A100 | UG-13A-S06-A110 | SS | 1 | Within package (ladder)
UG-13A-S06-A100 | UG-13A-S06-A110 | FF | 2 | Within package (ladder)
UG-13A-S05-A010 | UG-13A-S05-A020 | FS | 0 | Within package
UG-13A-S06-A030 | UG-13A-S05-A020 | SS | 0 | Set-out one package ahead of piling
UG-13A-S05-A020 | UG-13A-S05-A030 | SS | 1 | Within package (ladder)
UG-13A-S05-A020 | UG-13A-S05-A030 | FF | 2 | Within package (ladder)
UG-13A-S06-A030 | UG-13A-S05-A030 | FS | 0 | Crew continuity, front F7
UG-13A-S05-A030 | UG-13A-S05-A040 | SS | 1 | Within package (ladder)
UG-13A-S05-A030 | UG-13A-S05-A040 | FF | 2 | Within package (ladder)
UG-13A-S06-A040 | UG-13A-S05-A040 | FS | 0 | Crew continuity, front F7
UG-13A-S05-A040 | UG-13A-S05-A050 | SS | 1 | Within package (ladder)
UG-13A-S05-A040 | UG-13A-S05-A050 | FF | 2 | Within package (ladder)
UG-13A-S06-A060 | UG-13A-S05-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13A-S05-A050 | UG-13A-S05-A060 | SS | 10 | Within package (ladder)
UG-13A-S05-A050 | UG-13A-S05-A060 | FF | 2 | Within package (ladder)
UG-13A-S06-A060 | UG-13A-S05-A060 | FS | 0 | Crew continuity, front F7
UG-13A-S05-A060 | UG-13A-S05-A070 | SS | 1 | Within package (ladder)
UG-13A-S05-A060 | UG-13A-S05-A070 | FF | 2 | Within package (ladder)
UG-13A-S06-A070 | UG-13A-S05-A070 | FS | 0 | Crew continuity, front F7
UG-13A-S05-A070 | UG-13A-S05-A080 | SS | 2 | Within package (ladder)
UG-13A-S05-A070 | UG-13A-S05-A080 | FF | 2 | Within package (ladder)
UG-13A-S06-A080 | UG-13A-S05-A080 | FS | 0 | Crew continuity, front F7
UG-13A-S05-A080 | UG-13A-S05-A090 | SS | 1 | Within package (ladder)
UG-13A-S05-A080 | UG-13A-S05-A090 | FF | 2 | Within package (ladder)
UG-13A-S05-A090 | UG-13A-S05-A100 | SS | 2 | Within package (ladder)
UG-13A-S05-A090 | UG-13A-S05-A100 | FF | 2 | Within package (ladder)
UG-13A-S06-A100 | UG-13A-S05-A100 | FS | 0 | Crew continuity, front F7
UG-13A-S05-A100 | UG-13A-S05-A110 | SS | 1 | Within package (ladder)
UG-13A-S05-A100 | UG-13A-S05-A110 | FF | 2 | Within package (ladder)
UG-13A-S10-A010 | UG-13A-S10-A020 | FS | 0 | Within package
UG-13A-S05-A030 | UG-13A-S10-A020 | SS | 0 | Set-out one package ahead of piling
UG-13A-S10-A020 | UG-13A-S10-A030 | SS | 1 | Within package (ladder)
UG-13A-S10-A020 | UG-13A-S10-A030 | FF | 2 | Within package (ladder)
UG-13A-S05-A030 | UG-13A-S10-A030 | FS | 0 | Crew continuity, front F7
UG-13A-S10-A030 | UG-13A-S10-A040 | SS | 2 | Within package (ladder)
UG-13A-S10-A030 | UG-13A-S10-A040 | FF | 2 | Within package (ladder)
UG-13A-S05-A040 | UG-13A-S10-A040 | FS | 0 | Crew continuity, front F7
UG-13A-S10-A040 | UG-13A-S10-A050 | SS | 1 | Within package (ladder)
UG-13A-S10-A040 | UG-13A-S10-A050 | FF | 2 | Within package (ladder)
UG-13A-S05-A060 | UG-13A-S10-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13A-S10-A050 | UG-13A-S10-A060 | SS | 10 | Within package (ladder)
UG-13A-S10-A050 | UG-13A-S10-A060 | FF | 2 | Within package (ladder)
UG-13A-S05-A060 | UG-13A-S10-A060 | FS | 0 | Crew continuity, front F7
UG-13A-S10-A060 | UG-13A-S10-A070 | SS | 1 | Within package (ladder)
UG-13A-S10-A060 | UG-13A-S10-A070 | FF | 2 | Within package (ladder)
UG-13A-S05-A070 | UG-13A-S10-A070 | FS | 0 | Crew continuity, front F7
UG-13A-S10-A070 | UG-13A-S10-A080 | SS | 2 | Within package (ladder)
UG-13A-S10-A070 | UG-13A-S10-A080 | FF | 2 | Within package (ladder)
UG-13A-S05-A080 | UG-13A-S10-A080 | FS | 0 | Crew continuity, front F7
UG-13A-S10-A080 | UG-13A-S10-A090 | SS | 1 | Within package (ladder)
UG-13A-S10-A080 | UG-13A-S10-A090 | FF | 2 | Within package (ladder)
UG-13A-S10-A090 | UG-13A-S10-A100 | SS | 2 | Within package (ladder)
UG-13A-S10-A090 | UG-13A-S10-A100 | FF | 2 | Within package (ladder)
UG-13A-S05-A100 | UG-13A-S10-A100 | FS | 0 | Crew continuity, front F7
UG-13A-S10-A100 | UG-13A-S10-A110 | SS | 1 | Within package (ladder)
UG-13A-S10-A100 | UG-13A-S10-A110 | FF | 2 | Within package (ladder)
UG-13A-S09-A010 | UG-13A-S09-A020 | FS | 0 | Within package
UG-13A-S10-A030 | UG-13A-S09-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-13A-S09-A020 | UG-13A-S09-A030 | SS | 1 | Within package (ladder)
UG-13A-S09-A020 | UG-13A-S09-A030 | FF | 2 | Within package (ladder)
UG-13A-S09-A030 | UG-13A-S09-A040 | SS | 1 | Within package (ladder)
UG-13A-S09-A030 | UG-13A-S09-A040 | FF | 2 | Within package (ladder)
UG-13A-S09-A040 | UG-13A-S09-A050 | SS | 1 | Within package (ladder)
UG-13A-S09-A040 | UG-13A-S09-A050 | FF | 2 | Within package (ladder)
UG-13A-S09-A050 | UG-13A-S09-A060 | SS | 10 | Within package (ladder)
UG-13A-S09-A050 | UG-13A-S09-A060 | FF | 2 | Within package (ladder)
UG-13A-S09-A060 | UG-13A-S09-A070 | SS | 1 | Within package (ladder)
UG-13A-S09-A060 | UG-13A-S09-A070 | FF | 2 | Within package (ladder)
UG-13A-S09-A070 | UG-13A-S09-A080 | SS | 2 | Within package (ladder)
UG-13A-S09-A070 | UG-13A-S09-A080 | FF | 2 | Within package (ladder)
UG-13A-S10-A080 | UG-13A-S09-A080 | FS | 0 | Tie-in laid as closure
UG-13A-S09-A080 | UG-13A-S09-A090 | SS | 2 | Within package (ladder)
UG-13A-S09-A080 | UG-13A-S09-A090 | FF | 2 | Within package (ladder)
UG-13A-S09-A090 | UG-13A-S09-A100 | SS | 2 | Within package (ladder)
UG-13A-S09-A090 | UG-13A-S09-A100 | FF | 2 | Within package (ladder)
UG-13A-S09-A100 | UG-13A-S09-A110 | SS | 1 | Within package (ladder)
UG-13A-S09-A100 | UG-13A-S09-A110 | FF | 2 | Within package (ladder)
UG-13A-S14-A010 | UG-13A-S14-A020 | FS | 0 | Within package
UG-13A-S10-A030 | UG-13A-S14-A020 | SS | 0 | Set-out one package ahead of piling
UG-13A-S14-A020 | UG-13A-S14-A030 | SS | 1 | Within package (ladder)
UG-13A-S14-A020 | UG-13A-S14-A030 | FF | 2 | Within package (ladder)
UG-13A-S10-A030 | UG-13A-S14-A030 | FS | 0 | Crew continuity, front F7
UG-13A-S14-A030 | UG-13A-S14-A040 | SS | 2 | Within package (ladder)
UG-13A-S14-A030 | UG-13A-S14-A040 | FF | 2 | Within package (ladder)
UG-13A-S10-A040 | UG-13A-S14-A040 | FS | 0 | Crew continuity, front F7
UG-13A-S14-A040 | UG-13A-S14-A050 | SS | 2 | Within package (ladder)
UG-13A-S14-A040 | UG-13A-S14-A050 | FF | 2 | Within package (ladder)
UG-13A-S10-A060 | UG-13A-S14-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13A-S14-A050 | UG-13A-S14-A060 | SS | 10 | Within package (ladder)
UG-13A-S14-A050 | UG-13A-S14-A060 | FF | 2 | Within package (ladder)
UG-13A-S10-A060 | UG-13A-S14-A060 | FS | 0 | Crew continuity, front F7
UG-13A-S14-A060 | UG-13A-S14-A070 | SS | 1 | Within package (ladder)
UG-13A-S14-A060 | UG-13A-S14-A070 | FF | 2 | Within package (ladder)
UG-13A-S10-A070 | UG-13A-S14-A070 | FS | 0 | Crew continuity, front F7
UG-13A-S14-A070 | UG-13A-S14-A080 | SS | 3 | Within package (ladder)
UG-13A-S14-A070 | UG-13A-S14-A080 | FF | 2 | Within package (ladder)
UG-13A-S10-A080 | UG-13A-S14-A080 | FS | 0 | Crew continuity, front F7
UG-13A-S14-A080 | UG-13A-S14-A090 | SS | 2 | Within package (ladder)
UG-13A-S14-A080 | UG-13A-S14-A090 | FF | 2 | Within package (ladder)
UG-13A-S14-A090 | UG-13A-S14-A100 | SS | 2 | Within package (ladder)
UG-13A-S14-A090 | UG-13A-S14-A100 | FF | 2 | Within package (ladder)
UG-13A-S10-A100 | UG-13A-S14-A100 | FS | 0 | Crew continuity, front F7
UG-13A-S14-A100 | UG-13A-S14-A110 | SS | 1 | Within package (ladder)
UG-13A-S14-A100 | UG-13A-S14-A110 | FF | 2 | Within package (ladder)
UG-13A-S04-A010 | UG-13A-S04-A020 | FS | 0 | Within package
UG-13A-S14-A030 | UG-13A-S04-A020 | SS | 0 | Set-out one package ahead of piling
UG-13A-S04-A020 | UG-13A-S04-A030 | SS | 1 | Within package (ladder)
UG-13A-S04-A020 | UG-13A-S04-A030 | FF | 2 | Within package (ladder)
UG-13A-S14-A030 | UG-13A-S04-A030 | FS | 0 | Crew continuity, front F7
UG-13A-S04-A030 | UG-13A-S04-A040 | SS | 3 | Within package (ladder)
UG-13A-S04-A030 | UG-13A-S04-A040 | FF | 2 | Within package (ladder)
UG-13A-S14-A040 | UG-13A-S04-A040 | FS | 0 | Crew continuity, front F7
UG-13A-S04-A040 | UG-13A-S04-A050 | SS | 2 | Within package (ladder)
UG-13A-S04-A040 | UG-13A-S04-A050 | FF | 2 | Within package (ladder)
UG-13A-S14-A060 | UG-13A-S04-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-13A-S04-A050 | UG-13A-S04-A060 | SS | 10 | Within package (ladder)
UG-13A-S04-A050 | UG-13A-S04-A060 | FF | 2 | Within package (ladder)
UG-13A-S14-A060 | UG-13A-S04-A060 | FS | 0 | Crew continuity, front F7
UG-13A-S04-A060 | UG-13A-S04-A070 | SS | 1 | Within package (ladder)
UG-13A-S04-A060 | UG-13A-S04-A070 | FF | 2 | Within package (ladder)
UG-13A-S14-A070 | UG-13A-S04-A070 | FS | 0 | Crew continuity, front F7
UG-13A-S04-A070 | UG-13A-S04-A080 | SS | 3 | Within package (ladder)
UG-13A-S04-A070 | UG-13A-S04-A080 | FF | 2 | Within package (ladder)
UG-13A-S14-A080 | UG-13A-S04-A080 | FS | 0 | Crew continuity, front F7
UG-13A-S04-A080 | UG-13A-S04-A090 | SS | 3 | Within package (ladder)
UG-13A-S04-A080 | UG-13A-S04-A090 | FF | 2 | Within package (ladder)
UG-13A-S04-A090 | UG-13A-S04-A100 | SS | 2 | Within package (ladder)
UG-13A-S04-A090 | UG-13A-S04-A100 | FF | 2 | Within package (ladder)
UG-13A-S14-A100 | UG-13A-S04-A100 | FS | 0 | Crew continuity, front F7
UG-27I-S01-A080 | UG-13A-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13A-S04-A100 | UG-13A-S04-A110 | SS | 1 | Within package (ladder)
UG-13A-S04-A100 | UG-13A-S04-A110 | FF | 2 | Within package (ladder)
UG-13A-S03-A010 | UG-13A-S03-A020 | FS | 0 | Within package
UG-13A-S04-A030 | UG-13A-S03-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-13A-S03-A020 | UG-13A-S03-A030 | SS | 1 | Within package (ladder)
UG-13A-S03-A020 | UG-13A-S03-A030 | FF | 2 | Within package (ladder)
UG-13A-S03-A030 | UG-13A-S03-A040 | SS | 1 | Within package (ladder)
UG-13A-S03-A030 | UG-13A-S03-A040 | FF | 2 | Within package (ladder)
UG-13A-S03-A040 | UG-13A-S03-A050 | SS | 1 | Within package (ladder)
UG-13A-S03-A040 | UG-13A-S03-A050 | FF | 2 | Within package (ladder)
UG-13A-S03-A050 | UG-13A-S03-A060 | SS | 10 | Within package (ladder)
UG-13A-S03-A050 | UG-13A-S03-A060 | FF | 2 | Within package (ladder)
UG-13A-S03-A060 | UG-13A-S03-A070 | SS | 1 | Within package (ladder)
UG-13A-S03-A060 | UG-13A-S03-A070 | FF | 2 | Within package (ladder)
UG-13A-S03-A070 | UG-13A-S03-A080 | SS | 2 | Within package (ladder)
UG-13A-S03-A070 | UG-13A-S03-A080 | FF | 2 | Within package (ladder)
UG-13A-S04-A080 | UG-13A-S03-A080 | FS | 0 | Tie-in laid as closure
UG-13A-S03-A080 | UG-13A-S03-A090 | SS | 2 | Within package (ladder)
UG-13A-S03-A080 | UG-13A-S03-A090 | FF | 2 | Within package (ladder)
UG-13A-S03-A090 | UG-13A-S03-A100 | SS | 2 | Within package (ladder)
UG-13A-S03-A090 | UG-13A-S03-A100 | FF | 2 | Within package (ladder)
UG-27I-S01-A080 | UG-13A-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13A-S03-A100 | UG-13A-S03-A110 | SS | 1 | Within package (ladder)
UG-13A-S03-A100 | UG-13A-S03-A110 | FF | 2 | Within package (ladder)
UG-27I-S01-A010 | UG-27I-S01-A020 | FS | 0 | Within package
UG-27I-S01-A020 | UG-27I-S01-A030 | SS | 1 | Within package (ladder)
UG-27I-S01-A020 | UG-27I-S01-A030 | FF | 2 | Within package (ladder)
UG-27I-S01-A030 | UG-27I-S01-A040 | SS | 3 | Within package (ladder)
UG-27I-S01-A030 | UG-27I-S01-A040 | FF | 2 | Within package (ladder)
UG-27I-S01-A040 | UG-27I-S01-A050 | SS | 1 | Within package (ladder)
UG-27I-S01-A040 | UG-27I-S01-A050 | FF | 2 | Within package (ladder)
UG-27I-S01-A050 | UG-27I-S01-A060 | SS | 10 | Within package (ladder)
UG-27I-S01-A050 | UG-27I-S01-A060 | FF | 2 | Within package (ladder)
UG-13A-S09-A100 | UG-27I-S01-A060 | FS | 0 | Deeper line first
UG-13A-S10-A100 | UG-27I-S01-A060 | FS | 0 | Deeper line first
UG-13A-S14-A100 | UG-27I-S01-A060 | FS | 0 | Deeper line first
UG-13A-S03-A060 | UG-27I-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-13A-S04-A060 | UG-27I-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-27I-S01-A060 | UG-27I-S01-A070 | SS | 2 | Within package (ladder)
UG-27I-S01-A060 | UG-27I-S01-A070 | FF | 2 | Within package (ladder)
UG-27I-S01-A070 | UG-27I-S01-A080 | SS | 3 | Within package (ladder)
UG-27I-S01-A070 | UG-27I-S01-A080 | FF | 2 | Within package (ladder)
UG-27I-S01-A080 | UG-27I-S01-A090 | SS | 4 | Within package (ladder)
UG-27I-S01-A080 | UG-27I-S01-A090 | FF | 2 | Within package (ladder)
UG-27I-S01-A090 | UG-27I-S01-A100 | SS | 2 | Within package (ladder)
UG-27I-S01-A090 | UG-27I-S01-A100 | FF | 2 | Within package (ladder)
UG-13A-S03-A080 | UG-27I-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-13A-S04-A080 | UG-27I-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-27I-S01-A100 | UG-27I-S01-A110 | SS | 2 | Within package (ladder)
UG-27I-S01-A100 | UG-27I-S01-A110 | FF | 2 | Within package (ladder)
UG-13A-S15-A010 | UG-13A-S15-A020 | FS | 0 | Within package
UG-13A-S16-A030 | UG-13A-S15-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-13A-S15-A020 | UG-13A-S15-A030 | SS | 1 | Within package (ladder)
UG-13A-S15-A020 | UG-13A-S15-A030 | FF | 2 | Within package (ladder)
UG-13A-S15-A030 | UG-13A-S15-A040 | SS | 2 | Within package (ladder)
UG-13A-S15-A030 | UG-13A-S15-A040 | FF | 2 | Within package (ladder)
UG-13A-S15-A040 | UG-13A-S15-A050 | SS | 2 | Within package (ladder)
UG-13A-S15-A040 | UG-13A-S15-A050 | FF | 2 | Within package (ladder)
UG-13A-S15-A050 | UG-13A-S15-A060 | SS | 10 | Within package (ladder)
UG-13A-S15-A050 | UG-13A-S15-A060 | FF | 2 | Within package (ladder)
UG-13A-S15-A060 | UG-13A-S15-A070 | SS | 1 | Within package (ladder)
UG-13A-S15-A060 | UG-13A-S15-A070 | FF | 2 | Within package (ladder)
UG-13A-S15-A070 | UG-13A-S15-A080 | SS | 3 | Within package (ladder)
UG-13A-S15-A070 | UG-13A-S15-A080 | FF | 2 | Within package (ladder)
UG-13A-S16-A080 | UG-13A-S15-A080 | FS | 0 | Tie-in laid as closure
UG-13A-S15-A080 | UG-13A-S15-A090 | SS | 2 | Within package (ladder)
UG-13A-S15-A080 | UG-13A-S15-A090 | FF | 2 | Within package (ladder)
UG-13A-S15-A090 | UG-13A-S15-A100 | SS | 2 | Within package (ladder)
UG-13A-S15-A090 | UG-13A-S15-A100 | FF | 2 | Within package (ladder)
UG-13A-S15-A100 | UG-13A-S15-A110 | SS | 1 | Within package (ladder)
UG-13A-S15-A100 | UG-13A-S15-A110 | FF | 2 | Within package (ladder)
UG-21-S01-A010 | UG-21-S01-A020 | FS | 0 | Within package
UG-21-S01-A020 | UG-21-S01-A030 | SS | 1 | Within package (ladder)
UG-21-S01-A020 | UG-21-S01-A030 | FF | 2 | Within package (ladder)
UG-21-S01-A030 | UG-21-S01-A040 | SS | 1 | Within package (ladder)
UG-21-S01-A030 | UG-21-S01-A040 | FF | 2 | Within package (ladder)
UG-21-S01-A040 | UG-21-S01-A050 | SS | 1 | Within package (ladder)
UG-21-S01-A040 | UG-21-S01-A050 | FF | 2 | Within package (ladder)
UG-21-S01-A050 | UG-21-S01-A060 | SS | 10 | Within package (ladder)
UG-21-S01-A050 | UG-21-S01-A060 | FF | 2 | Within package (ladder)
UG-21-S01-A060 | UG-21-S01-A070 | SS | 1 | Within package (ladder)
UG-21-S01-A060 | UG-21-S01-A070 | FF | 2 | Within package (ladder)
UG-21-S01-A070 | UG-21-S01-A080 | SS | 2 | Within package (ladder)
UG-21-S01-A070 | UG-21-S01-A080 | FF | 2 | Within package (ladder)
UG-21-S01-A080 | UG-21-S01-A090 | SS | 2 | Within package (ladder)
UG-21-S01-A080 | UG-21-S01-A090 | FF | 2 | Within package (ladder)
UG-21-S01-A090 | UG-21-S01-A100 | SS | 2 | Within package (ladder)
UG-21-S01-A090 | UG-21-S01-A100 | FF | 2 | Within package (ladder)
UG-22-S01-A080 | UG-21-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-28-S02-A080 | UG-21-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-21-S01-A100 | UG-21-S01-A110 | SS | 1 | Within package (ladder)
UG-21-S01-A100 | UG-21-S01-A110 | FF | 2 | Within package (ladder)
UG-22-S01-A010 | UG-22-S01-A020 | FS | 0 | Within package
UG-22-S01-A020 | UG-22-S01-A030 | SS | 1 | Within package (ladder)
UG-22-S01-A020 | UG-22-S01-A030 | FF | 2 | Within package (ladder)
UG-22-S01-A030 | UG-22-S01-A040 | SS | 1 | Within package (ladder)
UG-22-S01-A030 | UG-22-S01-A040 | FF | 2 | Within package (ladder)
UG-22-S01-A040 | UG-22-S01-A050 | SS | 1 | Within package (ladder)
UG-22-S01-A040 | UG-22-S01-A050 | FF | 2 | Within package (ladder)
UG-22-S01-A050 | UG-22-S01-A060 | SS | 10 | Within package (ladder)
UG-22-S01-A050 | UG-22-S01-A060 | FF | 2 | Within package (ladder)
UG-21-S01-A060 | UG-22-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-22-S01-A060 | UG-22-S01-A070 | SS | 1 | Within package (ladder)
UG-22-S01-A060 | UG-22-S01-A070 | FF | 2 | Within package (ladder)
UG-22-S01-A070 | UG-22-S01-A080 | SS | 2 | Within package (ladder)
UG-22-S01-A070 | UG-22-S01-A080 | FF | 2 | Within package (ladder)
UG-22-S01-A080 | UG-22-S01-A090 | SS | 2 | Within package (ladder)
UG-22-S01-A080 | UG-22-S01-A090 | FF | 2 | Within package (ladder)
UG-22-S01-A090 | UG-22-S01-A100 | SS | 2 | Within package (ladder)
UG-22-S01-A090 | UG-22-S01-A100 | FF | 2 | Within package (ladder)
UG-21-S01-A080 | UG-22-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-28-S02-A080 | UG-22-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-22-S01-A100 | UG-22-S01-A110 | SS | 1 | Within package (ladder)
UG-22-S01-A100 | UG-22-S01-A110 | FF | 2 | Within package (ladder)
UG-28-S02-A010 | UG-28-S02-A020 | FS | 0 | Within package
UG-28-S02-A020 | UG-28-S02-A030 | SS | 1 | Within package (ladder)
UG-28-S02-A020 | UG-28-S02-A030 | FF | 2 | Within package (ladder)
UG-28-S02-A030 | UG-28-S02-A040 | SS | 1 | Within package (ladder)
UG-28-S02-A030 | UG-28-S02-A040 | FF | 2 | Within package (ladder)
UG-28-S02-A040 | UG-28-S02-A050 | SS | 1 | Within package (ladder)
UG-28-S02-A040 | UG-28-S02-A050 | FF | 2 | Within package (ladder)
UG-28-S02-A050 | UG-28-S02-A060 | SS | 10 | Within package (ladder)
UG-28-S02-A050 | UG-28-S02-A060 | FF | 2 | Within package (ladder)
UG-21-S01-A060 | UG-28-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-22-S01-A060 | UG-28-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-28-S02-A060 | UG-28-S02-A070 | SS | 1 | Within package (ladder)
UG-28-S02-A060 | UG-28-S02-A070 | FF | 2 | Within package (ladder)
UG-28-S02-A070 | UG-28-S02-A080 | SS | 2 | Within package (ladder)
UG-28-S02-A070 | UG-28-S02-A080 | FF | 2 | Within package (ladder)
UG-28-S02-A080 | UG-28-S02-A090 | SS | 3 | Within package (ladder)
UG-28-S02-A080 | UG-28-S02-A090 | FF | 2 | Within package (ladder)
UG-28-S02-A090 | UG-28-S02-A100 | SS | 2 | Within package (ladder)
UG-28-S02-A090 | UG-28-S02-A100 | FF | 2 | Within package (ladder)
UG-21-S01-A080 | UG-28-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-22-S01-A080 | UG-28-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-28-S02-A100 | UG-28-S02-A110 | SS | 1 | Within package (ladder)
UG-28-S02-A100 | UG-28-S02-A110 | FF | 2 | Within package (ladder)
UG-15-S01-A010 | UG-15-S01-A020 | FS | 0 | Within package
UG-15-S01-A020 | UG-15-S01-A030 | SS | 1 | Within package (ladder)
UG-15-S01-A020 | UG-15-S01-A030 | FF | 2 | Within package (ladder)
UG-15-S01-A030 | UG-15-S01-A040 | SS | 2 | Within package (ladder)
UG-15-S01-A030 | UG-15-S01-A040 | FF | 2 | Within package (ladder)
UG-15-S01-A040 | UG-15-S01-A050 | SS | 1 | Within package (ladder)
UG-15-S01-A040 | UG-15-S01-A050 | FF | 2 | Within package (ladder)
UG-15-S01-A050 | UG-15-S01-A060 | SS | 10 | Within package (ladder)
UG-15-S01-A050 | UG-15-S01-A060 | FF | 2 | Within package (ladder)
UG-15-S01-A060 | UG-15-S01-A070 | SS | 1 | Within package (ladder)
UG-15-S01-A060 | UG-15-S01-A070 | FF | 2 | Within package (ladder)
UG-15-S01-A070 | UG-15-S01-A080 | SS | 3 | Within package (ladder)
UG-15-S01-A070 | UG-15-S01-A080 | FF | 2 | Within package (ladder)
UG-15-S01-A080 | UG-15-S01-A090 | SS | 2 | Within package (ladder)
UG-15-S01-A080 | UG-15-S01-A090 | FF | 2 | Within package (ladder)
UG-15-S01-A090 | UG-15-S01-A100 | SS | 2 | Within package (ladder)
UG-15-S01-A090 | UG-15-S01-A100 | FF | 2 | Within package (ladder)
UG-15A-S06-A080 | UG-15-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15A-S09-A080 | UG-15-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15A-S10-A080 | UG-15-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15-S01-A100 | UG-15-S01-A110 | SS | 1 | Within package (ladder)
UG-15-S01-A100 | UG-15-S01-A110 | FF | 2 | Within package (ladder)
UG-15A-S10-A010 | UG-15A-S10-A020 | FS | 0 | Within package
UG-15-S01-A030 | UG-15A-S10-A020 | SS | 0 | Set-out one package ahead of piling
UG-15A-S10-A020 | UG-15A-S10-A030 | SS | 1 | Within package (ladder)
UG-15A-S10-A020 | UG-15A-S10-A030 | FF | 2 | Within package (ladder)
UG-15-S01-A030 | UG-15A-S10-A030 | FS | 0 | Crew continuity, front F8
UG-15A-S10-A030 | UG-15A-S10-A040 | SS | 1 | Within package (ladder)
UG-15A-S10-A030 | UG-15A-S10-A040 | FF | 2 | Within package (ladder)
UG-15-S01-A040 | UG-15A-S10-A040 | FS | 0 | Crew continuity, front F8
UG-15A-S10-A040 | UG-15A-S10-A050 | SS | 1 | Within package (ladder)
UG-15A-S10-A040 | UG-15A-S10-A050 | FF | 2 | Within package (ladder)
UG-15-S01-A060 | UG-15A-S10-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-15A-S10-A050 | UG-15A-S10-A060 | SS | 10 | Within package (ladder)
UG-15A-S10-A050 | UG-15A-S10-A060 | FF | 2 | Within package (ladder)
UG-15-S01-A060 | UG-15A-S10-A060 | FS | 0 | Crew continuity, front F8
UG-15-S01-A060 | UG-15A-S10-A060 | SS | 0 | Shared excavation / dewatering front
UG-15A-S10-A060 | UG-15A-S10-A070 | SS | 1 | Within package (ladder)
UG-15A-S10-A060 | UG-15A-S10-A070 | FF | 2 | Within package (ladder)
UG-15-S01-A070 | UG-15A-S10-A070 | FS | 0 | Crew continuity, front F8
UG-15A-S10-A070 | UG-15A-S10-A080 | SS | 2 | Within package (ladder)
UG-15A-S10-A070 | UG-15A-S10-A080 | FF | 2 | Within package (ladder)
UG-15-S01-A080 | UG-15A-S10-A080 | FS | 0 | Crew continuity, front F8
UG-15A-S10-A080 | UG-15A-S10-A090 | SS | 1 | Within package (ladder)
UG-15A-S10-A080 | UG-15A-S10-A090 | FF | 2 | Within package (ladder)
UG-15A-S10-A090 | UG-15A-S10-A100 | SS | 2 | Within package (ladder)
UG-15A-S10-A090 | UG-15A-S10-A100 | FF | 2 | Within package (ladder)
UG-15-S01-A100 | UG-15A-S10-A100 | FS | 0 | Crew continuity, front F8
UG-15-S01-A080 | UG-15A-S10-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S02-A080 | UG-15A-S10-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15A-S10-A100 | UG-15A-S10-A110 | SS | 1 | Within package (ladder)
UG-15A-S10-A100 | UG-15A-S10-A110 | FF | 2 | Within package (ladder)
UG-15A-S09-A010 | UG-15A-S09-A020 | FS | 0 | Within package
UG-15A-S10-A030 | UG-15A-S09-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-15A-S09-A020 | UG-15A-S09-A030 | SS | 1 | Within package (ladder)
UG-15A-S09-A020 | UG-15A-S09-A030 | FF | 2 | Within package (ladder)
UG-15A-S09-A030 | UG-15A-S09-A040 | SS | 1 | Within package (ladder)
UG-15A-S09-A030 | UG-15A-S09-A040 | FF | 2 | Within package (ladder)
UG-15A-S09-A040 | UG-15A-S09-A050 | SS | 1 | Within package (ladder)
UG-15A-S09-A040 | UG-15A-S09-A050 | FF | 2 | Within package (ladder)
UG-15A-S09-A050 | UG-15A-S09-A060 | SS | 10 | Within package (ladder)
UG-15A-S09-A050 | UG-15A-S09-A060 | FF | 2 | Within package (ladder)
UG-15-S01-A060 | UG-15A-S09-A060 | SS | 0 | Shared excavation / dewatering front
UG-15A-S09-A060 | UG-15A-S09-A070 | SS | 1 | Within package (ladder)
UG-15A-S09-A060 | UG-15A-S09-A070 | FF | 2 | Within package (ladder)
UG-15A-S09-A070 | UG-15A-S09-A080 | SS | 2 | Within package (ladder)
UG-15A-S09-A070 | UG-15A-S09-A080 | FF | 2 | Within package (ladder)
UG-15A-S10-A080 | UG-15A-S09-A080 | FS | 0 | Tie-in laid as closure
UG-15A-S09-A080 | UG-15A-S09-A090 | SS | 2 | Within package (ladder)
UG-15A-S09-A080 | UG-15A-S09-A090 | FF | 2 | Within package (ladder)
UG-15A-S09-A090 | UG-15A-S09-A100 | SS | 2 | Within package (ladder)
UG-15A-S09-A090 | UG-15A-S09-A100 | FF | 2 | Within package (ladder)
UG-15-S01-A080 | UG-15A-S09-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15A-S09-A100 | UG-15A-S09-A110 | SS | 1 | Within package (ladder)
UG-15A-S09-A100 | UG-15A-S09-A110 | FF | 2 | Within package (ladder)
UG-15A-S06-A010 | UG-15A-S06-A020 | FS | 0 | Within package
UG-15A-S10-A030 | UG-15A-S06-A020 | SS | 0 | Set-out one package ahead of piling
UG-15A-S06-A020 | UG-15A-S06-A030 | SS | 1 | Within package (ladder)
UG-15A-S06-A020 | UG-15A-S06-A030 | FF | 2 | Within package (ladder)
UG-15A-S10-A030 | UG-15A-S06-A030 | FS | 0 | Crew continuity, front F8
UG-15A-S06-A030 | UG-15A-S06-A040 | SS | 2 | Within package (ladder)
UG-15A-S06-A030 | UG-15A-S06-A040 | FF | 2 | Within package (ladder)
UG-15A-S10-A040 | UG-15A-S06-A040 | FS | 0 | Crew continuity, front F8
UG-15A-S06-A040 | UG-15A-S06-A050 | SS | 2 | Within package (ladder)
UG-15A-S06-A040 | UG-15A-S06-A050 | FF | 2 | Within package (ladder)
UG-15A-S10-A060 | UG-15A-S06-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-15A-S06-A050 | UG-15A-S06-A060 | SS | 10 | Within package (ladder)
UG-15A-S06-A050 | UG-15A-S06-A060 | FF | 2 | Within package (ladder)
UG-15A-S10-A060 | UG-15A-S06-A060 | FS | 0 | Crew continuity, front F8
UG-15-S01-A060 | UG-15A-S06-A060 | SS | 0 | Shared excavation / dewatering front
UG-15A-S06-A060 | UG-15A-S06-A070 | SS | 1 | Within package (ladder)
UG-15A-S06-A060 | UG-15A-S06-A070 | FF | 2 | Within package (ladder)
UG-15A-S10-A070 | UG-15A-S06-A070 | FS | 0 | Crew continuity, front F8
UG-15A-S06-A070 | UG-15A-S06-A080 | SS | 3 | Within package (ladder)
UG-15A-S06-A070 | UG-15A-S06-A080 | FF | 2 | Within package (ladder)
UG-15A-S10-A080 | UG-15A-S06-A080 | FS | 0 | Crew continuity, front F8
UG-15A-S06-A080 | UG-15A-S06-A090 | SS | 2 | Within package (ladder)
UG-15A-S06-A080 | UG-15A-S06-A090 | FF | 2 | Within package (ladder)
UG-15A-S06-A090 | UG-15A-S06-A100 | SS | 2 | Within package (ladder)
UG-15A-S06-A090 | UG-15A-S06-A100 | FF | 2 | Within package (ladder)
UG-15A-S10-A100 | UG-15A-S06-A100 | FS | 0 | Crew continuity, front F8
UG-15-S01-A080 | UG-15A-S06-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S02-A080 | UG-15A-S06-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S03-A080 | UG-15A-S06-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15A-S06-A100 | UG-15A-S06-A110 | SS | 1 | Within package (ladder)
UG-15A-S06-A100 | UG-15A-S06-A110 | FF | 2 | Within package (ladder)
UG-17-S02-A010 | UG-17-S02-A020 | FS | 0 | Within package
UG-15A-S06-A030 | UG-17-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-17-S02-A020 | UG-17-S02-A030 | SS | 1 | Within package (ladder)
UG-17-S02-A020 | UG-17-S02-A030 | FF | 2 | Within package (ladder)
UG-15A-S06-A030 | UG-17-S02-A030 | FS | 0 | Crew continuity, front F8
UG-17-S02-A030 | UG-17-S02-A040 | SS | 2 | Within package (ladder)
UG-17-S02-A030 | UG-17-S02-A040 | FF | 2 | Within package (ladder)
UG-15A-S06-A040 | UG-17-S02-A040 | FS | 0 | Crew continuity, front F8
UG-17-S02-A040 | UG-17-S02-A050 | SS | 1 | Within package (ladder)
UG-17-S02-A040 | UG-17-S02-A050 | FF | 2 | Within package (ladder)
UG-15A-S06-A060 | UG-17-S02-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-17-S02-A050 | UG-17-S02-A060 | SS | 10 | Within package (ladder)
UG-17-S02-A050 | UG-17-S02-A060 | FF | 2 | Within package (ladder)
UG-15A-S06-A060 | UG-17-S02-A060 | FS | 0 | Crew continuity, front F8
UG-15-S01-A100 | UG-17-S02-A060 | FS | 0 | Deeper line first
UG-15A-S06-A060 | UG-17-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-15A-S10-A060 | UG-17-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-17-S02-A060 | UG-17-S02-A070 | SS | 1 | Within package (ladder)
UG-17-S02-A060 | UG-17-S02-A070 | FF | 2 | Within package (ladder)
UG-15A-S06-A070 | UG-17-S02-A070 | FS | 0 | Crew continuity, front F8
UG-17-S02-A070 | UG-17-S02-A080 | SS | 2 | Within package (ladder)
UG-17-S02-A070 | UG-17-S02-A080 | FF | 2 | Within package (ladder)
UG-15A-S06-A080 | UG-17-S02-A080 | FS | 0 | Crew continuity, front F8
UG-17-S02-A080 | UG-17-S02-A090 | SS | 2 | Within package (ladder)
UG-17-S02-A080 | UG-17-S02-A090 | FF | 2 | Within package (ladder)
UG-17-S02-A090 | UG-17-S02-A100 | SS | 2 | Within package (ladder)
UG-17-S02-A090 | UG-17-S02-A100 | FF | 2 | Within package (ladder)
UG-15A-S06-A100 | UG-17-S02-A100 | FS | 0 | Crew continuity, front F8
UG-15A-S06-A080 | UG-17-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15A-S10-A080 | UG-17-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-18-S01-A080 | UG-17-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-18-S02-A080 | UG-17-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S02-A100 | UG-17-S02-A110 | SS | 1 | Within package (ladder)
UG-17-S02-A100 | UG-17-S02-A110 | FF | 2 | Within package (ladder)
UG-19-S03-A010 | UG-19-S03-A020 | FS | 0 | Within package
UG-17-S02-A030 | UG-19-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-19-S03-A020 | UG-19-S03-A030 | SS | 1 | Within package (ladder)
UG-19-S03-A020 | UG-19-S03-A030 | FF | 2 | Within package (ladder)
UG-17-S02-A030 | UG-19-S03-A030 | FS | 0 | Crew continuity, front F8
UG-19-S03-A030 | UG-19-S03-A040 | SS | 3 | Within package (ladder)
UG-19-S03-A030 | UG-19-S03-A040 | FF | 2 | Within package (ladder)
UG-17-S02-A040 | UG-19-S03-A040 | FS | 0 | Crew continuity, front F8
UG-19-S03-A040 | UG-19-S03-A050 | SS | 2 | Within package (ladder)
UG-19-S03-A040 | UG-19-S03-A050 | FF | 2 | Within package (ladder)
UG-17-S02-A060 | UG-19-S03-A050 | FS | -12 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-19-S03-A050 | UG-19-S03-A060 | SS | 10 | Within package (ladder)
UG-19-S03-A050 | UG-19-S03-A060 | FF | 2 | Within package (ladder)
UG-17-S02-A060 | UG-19-S03-A060 | FS | 0 | Crew continuity, front F8
UG-19-S03-A060 | UG-19-S03-A070 | SS | 2 | Within package (ladder)
UG-19-S03-A060 | UG-19-S03-A070 | FF | 2 | Within package (ladder)
UG-17-S02-A070 | UG-19-S03-A070 | FS | 0 | Crew continuity, front F8
UG-19-S03-A070 | UG-19-S03-A080 | SS | 3 | Within package (ladder)
UG-19-S03-A070 | UG-19-S03-A080 | FF | 2 | Within package (ladder)
UG-17-S02-A080 | UG-19-S03-A080 | FS | 0 | Crew continuity, front F8
UG-19-S03-A080 | UG-19-S03-A090 | SS | 2 | Within package (ladder)
UG-19-S03-A080 | UG-19-S03-A090 | FF | 2 | Within package (ladder)
UG-19-S03-A090 | UG-19-S03-A100 | SS | 2 | Within package (ladder)
UG-19-S03-A090 | UG-19-S03-A100 | FF | 2 | Within package (ladder)
UG-17-S02-A100 | UG-19-S03-A100 | FS | 0 | Crew continuity, front F8
UG-20-S02-A080 | UG-19-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-19-S03-A100 | UG-19-S03-A110 | SS | 1 | Within package (ladder)
UG-19-S03-A100 | UG-19-S03-A110 | FF | 2 | Within package (ladder)
UG-20-S02-A010 | UG-20-S02-A020 | FS | 0 | Within package
UG-19-S03-A030 | UG-20-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-20-S02-A020 | UG-20-S02-A030 | SS | 1 | Within package (ladder)
UG-20-S02-A020 | UG-20-S02-A030 | FF | 2 | Within package (ladder)
UG-19-S03-A030 | UG-20-S02-A030 | FS | 0 | Crew continuity, front F8
UG-20-S02-A030 | UG-20-S02-A040 | SS | 3 | Within package (ladder)
UG-20-S02-A030 | UG-20-S02-A040 | FF | 2 | Within package (ladder)
UG-19-S03-A040 | UG-20-S02-A040 | FS | 0 | Crew continuity, front F8
UG-20-S02-A040 | UG-20-S02-A050 | SS | 2 | Within package (ladder)
UG-20-S02-A040 | UG-20-S02-A050 | FF | 2 | Within package (ladder)
UG-19-S03-A060 | UG-20-S02-A050 | FS | -12 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-20-S02-A050 | UG-20-S02-A060 | SS | 10 | Within package (ladder)
UG-20-S02-A050 | UG-20-S02-A060 | FF | 2 | Within package (ladder)
UG-19-S03-A060 | UG-20-S02-A060 | FS | 0 | Crew continuity, front F8
UG-19-S03-A060 | UG-20-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-20-S02-A060 | UG-20-S02-A070 | SS | 2 | Within package (ladder)
UG-20-S02-A060 | UG-20-S02-A070 | FF | 2 | Within package (ladder)
UG-19-S03-A070 | UG-20-S02-A070 | FS | 0 | Crew continuity, front F8
UG-20-S02-A070 | UG-20-S02-A080 | SS | 3 | Within package (ladder)
UG-20-S02-A070 | UG-20-S02-A080 | FF | 2 | Within package (ladder)
UG-19-S03-A080 | UG-20-S02-A080 | FS | 0 | Crew continuity, front F8
UG-20-S02-A080 | UG-20-S02-A090 | SS | 3 | Within package (ladder)
UG-20-S02-A080 | UG-20-S02-A090 | FF | 2 | Within package (ladder)
UG-20-S02-A090 | UG-20-S02-A100 | SS | 2 | Within package (ladder)
UG-20-S02-A090 | UG-20-S02-A100 | FF | 2 | Within package (ladder)
UG-19-S03-A100 | UG-20-S02-A100 | FS | 0 | Crew continuity, front F8
UG-18-S02-A080 | UG-20-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-19-S01-A080 | UG-20-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-19-S02-A080 | UG-20-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-19-S03-A080 | UG-20-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-20-S02-A100 | UG-20-S02-A110 | SS | 1 | Within package (ladder)
UG-20-S02-A100 | UG-20-S02-A110 | FF | 2 | Within package (ladder)
UG-20-S01-A010 | UG-20-S01-A020 | FS | 0 | Within package
UG-20-S02-A030 | UG-20-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-20-S01-A020 | UG-20-S01-A030 | SS | 1 | Within package (ladder)
UG-20-S01-A020 | UG-20-S01-A030 | FF | 2 | Within package (ladder)
UG-20-S01-A030 | UG-20-S01-A040 | SS | 1 | Within package (ladder)
UG-20-S01-A030 | UG-20-S01-A040 | FF | 2 | Within package (ladder)
UG-20-S01-A040 | UG-20-S01-A050 | SS | 1 | Within package (ladder)
UG-20-S01-A040 | UG-20-S01-A050 | FF | 2 | Within package (ladder)
UG-20-S01-A050 | UG-20-S01-A060 | SS | 10 | Within package (ladder)
UG-20-S01-A050 | UG-20-S01-A060 | FF | 2 | Within package (ladder)
UG-20-S01-A060 | UG-20-S01-A070 | SS | 1 | Within package (ladder)
UG-20-S01-A060 | UG-20-S01-A070 | FF | 2 | Within package (ladder)
UG-20-S01-A070 | UG-20-S01-A080 | SS | 2 | Within package (ladder)
UG-20-S01-A070 | UG-20-S01-A080 | FF | 2 | Within package (ladder)
UG-20-S02-A080 | UG-20-S01-A080 | FS | 0 | Tie-in laid as closure
UG-20-S01-A080 | UG-20-S01-A090 | SS | 2 | Within package (ladder)
UG-20-S01-A080 | UG-20-S01-A090 | FF | 2 | Within package (ladder)
UG-20-S01-A090 | UG-20-S01-A100 | SS | 2 | Within package (ladder)
UG-20-S01-A090 | UG-20-S01-A100 | FF | 2 | Within package (ladder)
UG-19-S01-A080 | UG-20-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-19-S02-A080 | UG-20-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-20-S01-A100 | UG-20-S01-A110 | SS | 1 | Within package (ladder)
UG-20-S01-A100 | UG-20-S01-A110 | FF | 2 | Within package (ladder)
UG-19-S02-A010 | UG-19-S02-A020 | FS | 0 | Within package
UG-20-S02-A030 | UG-19-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-19-S02-A020 | UG-19-S02-A030 | SS | 1 | Within package (ladder)
UG-19-S02-A020 | UG-19-S02-A030 | FF | 2 | Within package (ladder)
UG-20-S02-A030 | UG-19-S02-A030 | FS | 0 | Crew continuity, front F8
UG-19-S02-A030 | UG-19-S02-A040 | SS | 2 | Within package (ladder)
UG-19-S02-A030 | UG-19-S02-A040 | FF | 2 | Within package (ladder)
UG-20-S02-A040 | UG-19-S02-A040 | FS | 0 | Crew continuity, front F8
UG-19-S02-A040 | UG-19-S02-A050 | SS | 1 | Within package (ladder)
UG-19-S02-A040 | UG-19-S02-A050 | FF | 2 | Within package (ladder)
UG-20-S02-A060 | UG-19-S02-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-19-S02-A050 | UG-19-S02-A060 | SS | 10 | Within package (ladder)
UG-19-S02-A050 | UG-19-S02-A060 | FF | 2 | Within package (ladder)
UG-20-S02-A060 | UG-19-S02-A060 | FS | 0 | Crew continuity, front F8
UG-20-S01-A060 | UG-19-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-20-S02-A060 | UG-19-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-19-S02-A060 | UG-19-S02-A070 | SS | 1 | Within package (ladder)
UG-19-S02-A060 | UG-19-S02-A070 | FF | 2 | Within package (ladder)
UG-20-S02-A070 | UG-19-S02-A070 | FS | 0 | Crew continuity, front F8
UG-19-S02-A070 | UG-19-S02-A080 | SS | 2 | Within package (ladder)
UG-19-S02-A070 | UG-19-S02-A080 | FF | 2 | Within package (ladder)
UG-20-S02-A080 | UG-19-S02-A080 | FS | 0 | Crew continuity, front F8
UG-19-S02-A080 | UG-19-S02-A090 | SS | 2 | Within package (ladder)
UG-19-S02-A080 | UG-19-S02-A090 | FF | 2 | Within package (ladder)
UG-19-S02-A090 | UG-19-S02-A100 | SS | 2 | Within package (ladder)
UG-19-S02-A090 | UG-19-S02-A100 | FF | 2 | Within package (ladder)
UG-20-S02-A100 | UG-19-S02-A100 | FS | 0 | Crew continuity, front F8
UG-20-S01-A080 | UG-19-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-20-S02-A080 | UG-19-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-19-S02-A100 | UG-19-S02-A110 | SS | 1 | Within package (ladder)
UG-19-S02-A100 | UG-19-S02-A110 | FF | 2 | Within package (ladder)
UG-19-S01-A010 | UG-19-S01-A020 | FS | 0 | Within package
UG-19-S02-A030 | UG-19-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-19-S01-A020 | UG-19-S01-A030 | SS | 1 | Within package (ladder)
UG-19-S01-A020 | UG-19-S01-A030 | FF | 2 | Within package (ladder)
UG-19-S01-A030 | UG-19-S01-A040 | SS | 1 | Within package (ladder)
UG-19-S01-A030 | UG-19-S01-A040 | FF | 2 | Within package (ladder)
UG-19-S01-A040 | UG-19-S01-A050 | SS | 1 | Within package (ladder)
UG-19-S01-A040 | UG-19-S01-A050 | FF | 2 | Within package (ladder)
UG-19-S01-A050 | UG-19-S01-A060 | SS | 10 | Within package (ladder)
UG-19-S01-A050 | UG-19-S01-A060 | FF | 2 | Within package (ladder)
UG-20-S01-A060 | UG-19-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-20-S02-A060 | UG-19-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-19-S01-A060 | UG-19-S01-A070 | SS | 1 | Within package (ladder)
UG-19-S01-A060 | UG-19-S01-A070 | FF | 2 | Within package (ladder)
UG-19-S01-A070 | UG-19-S01-A080 | SS | 2 | Within package (ladder)
UG-19-S01-A070 | UG-19-S01-A080 | FF | 2 | Within package (ladder)
UG-19-S02-A080 | UG-19-S01-A080 | FS | 0 | Tie-in laid as closure
UG-19-S01-A080 | UG-19-S01-A090 | SS | 2 | Within package (ladder)
UG-19-S01-A080 | UG-19-S01-A090 | FF | 2 | Within package (ladder)
UG-19-S01-A090 | UG-19-S01-A100 | SS | 2 | Within package (ladder)
UG-19-S01-A090 | UG-19-S01-A100 | FF | 2 | Within package (ladder)
UG-20-S01-A080 | UG-19-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-20-S02-A080 | UG-19-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-19-S01-A100 | UG-19-S01-A110 | SS | 1 | Within package (ladder)
UG-19-S01-A100 | UG-19-S01-A110 | FF | 2 | Within package (ladder)
UG-15A-S08-A010 | UG-15A-S08-A020 | FS | 0 | Within package
UG-19-S02-A030 | UG-15A-S08-A020 | SS | 0 | Set-out one package ahead of piling
UG-15A-S08-A020 | UG-15A-S08-A030 | SS | 1 | Within package (ladder)
UG-15A-S08-A020 | UG-15A-S08-A030 | FF | 2 | Within package (ladder)
UG-19-S02-A030 | UG-15A-S08-A030 | FS | 0 | Crew continuity, front F8
UG-15A-S08-A030 | UG-15A-S08-A040 | SS | 1 | Within package (ladder)
UG-15A-S08-A030 | UG-15A-S08-A040 | FF | 2 | Within package (ladder)
UG-19-S02-A040 | UG-15A-S08-A040 | FS | 0 | Crew continuity, front F8
UG-15A-S08-A040 | UG-15A-S08-A050 | SS | 1 | Within package (ladder)
UG-15A-S08-A040 | UG-15A-S08-A050 | FF | 2 | Within package (ladder)
UG-19-S02-A060 | UG-15A-S08-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-15A-S08-A050 | UG-15A-S08-A060 | SS | 10 | Within package (ladder)
UG-15A-S08-A050 | UG-15A-S08-A060 | FF | 2 | Within package (ladder)
UG-19-S02-A060 | UG-15A-S08-A060 | FS | 0 | Crew continuity, front F8
UG-15A-S08-A060 | UG-15A-S08-A070 | SS | 1 | Within package (ladder)
UG-15A-S08-A060 | UG-15A-S08-A070 | FF | 2 | Within package (ladder)
UG-19-S02-A070 | UG-15A-S08-A070 | FS | 0 | Crew continuity, front F8
UG-15A-S08-A070 | UG-15A-S08-A080 | SS | 2 | Within package (ladder)
UG-15A-S08-A070 | UG-15A-S08-A080 | FF | 2 | Within package (ladder)
UG-19-S02-A080 | UG-15A-S08-A080 | FS | 0 | Crew continuity, front F8
UG-15A-S08-A080 | UG-15A-S08-A090 | SS | 1 | Within package (ladder)
UG-15A-S08-A080 | UG-15A-S08-A090 | FF | 2 | Within package (ladder)
UG-15A-S08-A090 | UG-15A-S08-A100 | SS | 2 | Within package (ladder)
UG-15A-S08-A090 | UG-15A-S08-A100 | FF | 2 | Within package (ladder)
UG-19-S02-A100 | UG-15A-S08-A100 | FS | 0 | Crew continuity, front F8
UG-17-S03-A080 | UG-15A-S08-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15A-S08-A100 | UG-15A-S08-A110 | SS | 1 | Within package (ladder)
UG-15A-S08-A100 | UG-15A-S08-A110 | FF | 2 | Within package (ladder)
UG-15A-S05-A010 | UG-15A-S05-A020 | FS | 0 | Within package
UG-15A-S08-A030 | UG-15A-S05-A020 | SS | 0 | Set-out one package ahead of piling
UG-15A-S05-A020 | UG-15A-S05-A030 | SS | 1 | Within package (ladder)
UG-15A-S05-A020 | UG-15A-S05-A030 | FF | 2 | Within package (ladder)
UG-15A-S08-A030 | UG-15A-S05-A030 | FS | 0 | Crew continuity, front F8
UG-15A-S05-A030 | UG-15A-S05-A040 | SS | 4 | Within package (ladder)
UG-15A-S05-A030 | UG-15A-S05-A040 | FF | 2 | Within package (ladder)
UG-15A-S08-A040 | UG-15A-S05-A040 | FS | 0 | Crew continuity, front F8
UG-15A-S05-A040 | UG-15A-S05-A050 | SS | 2 | Within package (ladder)
UG-15A-S05-A040 | UG-15A-S05-A050 | FF | 2 | Within package (ladder)
UG-15A-S08-A060 | UG-15A-S05-A050 | FS | -13 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-15A-S05-A050 | UG-15A-S05-A060 | SS | 11 | Within package (ladder)
UG-15A-S05-A050 | UG-15A-S05-A060 | FF | 2 | Within package (ladder)
UG-15A-S08-A060 | UG-15A-S05-A060 | FS | 0 | Crew continuity, front F8
UG-15A-S05-A060 | UG-15A-S05-A070 | SS | 2 | Within package (ladder)
UG-15A-S05-A060 | UG-15A-S05-A070 | FF | 2 | Within package (ladder)
UG-15A-S08-A070 | UG-15A-S05-A070 | FS | 0 | Crew continuity, front F8
UG-15A-S05-A070 | UG-15A-S05-A080 | SS | 4 | Within package (ladder)
UG-15A-S05-A070 | UG-15A-S05-A080 | FF | 2 | Within package (ladder)
UG-15A-S08-A080 | UG-15A-S05-A080 | FS | 0 | Crew continuity, front F8
UG-15A-S05-A080 | UG-15A-S05-A090 | SS | 3 | Within package (ladder)
UG-15A-S05-A080 | UG-15A-S05-A090 | FF | 2 | Within package (ladder)
UG-15A-S05-A090 | UG-15A-S05-A100 | SS | 2 | Within package (ladder)
UG-15A-S05-A090 | UG-15A-S05-A100 | FF | 2 | Within package (ladder)
UG-15A-S08-A100 | UG-15A-S05-A100 | FS | 0 | Crew continuity, front F8
UG-11B-S06-A080 | UG-15A-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S03-A080 | UG-15A-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-18-S02-A080 | UG-15A-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15A-S05-A100 | UG-15A-S05-A110 | SS | 1 | Within package (ladder)
UG-15A-S05-A100 | UG-15A-S05-A110 | FF | 2 | Within package (ladder)
UG-17-S04-A010 | UG-17-S04-A020 | FS | 0 | Within package
UG-15A-S05-A030 | UG-17-S04-A020 | SS | 0 | Set-out one package ahead of piling
UG-17-S04-A020 | UG-17-S04-A030 | SS | 1 | Within package (ladder)
UG-17-S04-A020 | UG-17-S04-A030 | FF | 2 | Within package (ladder)
UG-15A-S05-A030 | UG-17-S04-A030 | FS | 0 | Crew continuity, front F8
UG-17-S04-A030 | UG-17-S04-A040 | SS | 3 | Within package (ladder)
UG-17-S04-A030 | UG-17-S04-A040 | FF | 2 | Within package (ladder)
UG-15A-S05-A040 | UG-17-S04-A040 | FS | 0 | Crew continuity, front F8
UG-17-S04-A040 | UG-17-S04-A050 | SS | 2 | Within package (ladder)
UG-17-S04-A040 | UG-17-S04-A050 | FF | 2 | Within package (ladder)
UG-15A-S05-A060 | UG-17-S04-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-17-S04-A050 | UG-17-S04-A060 | SS | 10 | Within package (ladder)
UG-17-S04-A050 | UG-17-S04-A060 | FF | 2 | Within package (ladder)
UG-15A-S05-A060 | UG-17-S04-A060 | FS | 0 | Crew continuity, front F8
UG-17-S04-A060 | UG-17-S04-A070 | SS | 2 | Within package (ladder)
UG-17-S04-A060 | UG-17-S04-A070 | FF | 2 | Within package (ladder)
UG-15A-S05-A070 | UG-17-S04-A070 | FS | 0 | Crew continuity, front F8
UG-17-S04-A070 | UG-17-S04-A080 | SS | 3 | Within package (ladder)
UG-17-S04-A070 | UG-17-S04-A080 | FF | 2 | Within package (ladder)
UG-15A-S05-A080 | UG-17-S04-A080 | FS | 0 | Crew continuity, front F8
UG-17-S04-A080 | UG-17-S04-A090 | SS | 1 | Within package (ladder)
UG-17-S04-A080 | UG-17-S04-A090 | FF | 2 | Within package (ladder)
UG-17-S04-A090 | UG-17-S04-A100 | SS | 2 | Within package (ladder)
UG-17-S04-A090 | UG-17-S04-A100 | FF | 2 | Within package (ladder)
UG-15A-S05-A100 | UG-17-S04-A100 | FS | 0 | Crew continuity, front F8
UG-11B-S05-A080 | UG-17-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11B-S06-A080 | UG-17-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-18-S02-A080 | UG-17-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S04-A100 | UG-17-S04-A110 | SS | 1 | Within package (ladder)
UG-17-S04-A100 | UG-17-S04-A110 | FF | 2 | Within package (ladder)
UG-17-S05-A010 | UG-17-S05-A020 | FS | 0 | Within package
UG-17-S04-A030 | UG-17-S05-A020 | SS | 0 | Set-out one package ahead of piling
UG-17-S05-A020 | UG-17-S05-A030 | SS | 1 | Within package (ladder)
UG-17-S05-A020 | UG-17-S05-A030 | FF | 2 | Within package (ladder)
UG-17-S04-A030 | UG-17-S05-A030 | FS | 0 | Crew continuity, front F8
UG-17-S05-A030 | UG-17-S05-A040 | SS | 1 | Within package (ladder)
UG-17-S05-A030 | UG-17-S05-A040 | FF | 2 | Within package (ladder)
UG-17-S04-A040 | UG-17-S05-A040 | FS | 0 | Crew continuity, front F8
UG-17-S05-A040 | UG-17-S05-A050 | SS | 1 | Within package (ladder)
UG-17-S05-A040 | UG-17-S05-A050 | FF | 2 | Within package (ladder)
UG-17-S04-A060 | UG-17-S05-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-17-S05-A050 | UG-17-S05-A060 | SS | 10 | Within package (ladder)
UG-17-S05-A050 | UG-17-S05-A060 | FF | 2 | Within package (ladder)
UG-17-S04-A060 | UG-17-S05-A060 | FS | 0 | Crew continuity, front F8
UG-17-S05-A060 | UG-17-S05-A070 | SS | 1 | Within package (ladder)
UG-17-S05-A060 | UG-17-S05-A070 | FF | 2 | Within package (ladder)
UG-17-S04-A070 | UG-17-S05-A070 | FS | 0 | Crew continuity, front F8
UG-17-S05-A070 | UG-17-S05-A080 | SS | 2 | Within package (ladder)
UG-17-S05-A070 | UG-17-S05-A080 | FF | 2 | Within package (ladder)
UG-17-S04-A080 | UG-17-S05-A080 | FS | 0 | Crew continuity, front F8
UG-17-S05-A080 | UG-17-S05-A090 | SS | 1 | Within package (ladder)
UG-17-S05-A080 | UG-17-S05-A090 | FF | 2 | Within package (ladder)
UG-17-S05-A090 | UG-17-S05-A100 | SS | 2 | Within package (ladder)
UG-17-S05-A090 | UG-17-S05-A100 | FF | 2 | Within package (ladder)
UG-17-S04-A100 | UG-17-S05-A100 | FS | 0 | Crew continuity, front F8
UG-11B-S05-A080 | UG-17-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-18-S02-A080 | UG-17-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S05-A100 | UG-17-S05-A110 | SS | 1 | Within package (ladder)
UG-17-S05-A100 | UG-17-S05-A110 | FF | 2 | Within package (ladder)
UG-11B-S05-A010 | UG-11B-S05-A020 | FS | 0 | Within package
UG-17-S05-A030 | UG-11B-S05-A020 | SS | 0 | Set-out one package ahead of piling
UG-11B-S05-A020 | UG-11B-S05-A030 | SS | 1 | Within package (ladder)
UG-11B-S05-A020 | UG-11B-S05-A030 | FF | 2 | Within package (ladder)
UG-17-S05-A030 | UG-11B-S05-A030 | FS | 0 | Crew continuity, front F8
UG-11B-S05-A030 | UG-11B-S05-A040 | SS | 3 | Within package (ladder)
UG-11B-S05-A030 | UG-11B-S05-A040 | FF | 2 | Within package (ladder)
UG-17-S05-A040 | UG-11B-S05-A040 | FS | 0 | Crew continuity, front F8
UG-11B-S05-A040 | UG-11B-S05-A050 | SS | 2 | Within package (ladder)
UG-11B-S05-A040 | UG-11B-S05-A050 | FF | 2 | Within package (ladder)
UG-17-S05-A060 | UG-11B-S05-A050 | FS | -11 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11B-S05-A050 | UG-11B-S05-A060 | SS | 10 | Within package (ladder)
UG-11B-S05-A050 | UG-11B-S05-A060 | FF | 2 | Within package (ladder)
UG-17-S05-A060 | UG-11B-S05-A060 | FS | 0 | Crew continuity, front F8
UG-17-S04-A060 | UG-11B-S05-A060 | SS | 0 | Shared excavation / dewatering front
UG-17-S05-A060 | UG-11B-S05-A060 | SS | 0 | Shared excavation / dewatering front
UG-11B-S05-A060 | UG-11B-S05-A070 | SS | 1 | Within package (ladder)
UG-11B-S05-A060 | UG-11B-S05-A070 | FF | 2 | Within package (ladder)
UG-17-S05-A070 | UG-11B-S05-A070 | FS | 0 | Crew continuity, front F8
UG-11B-S05-A070 | UG-11B-S05-A080 | SS | 3 | Within package (ladder)
UG-11B-S05-A070 | UG-11B-S05-A080 | FF | 2 | Within package (ladder)
UG-17-S05-A080 | UG-11B-S05-A080 | FS | 0 | Crew continuity, front F8
UG-11B-S05-A080 | UG-11B-S05-A090 | SS | 2 | Within package (ladder)
UG-11B-S05-A080 | UG-11B-S05-A090 | FF | 2 | Within package (ladder)
UG-11B-S05-A090 | UG-11B-S05-A100 | SS | 2 | Within package (ladder)
UG-11B-S05-A090 | UG-11B-S05-A100 | FF | 2 | Within package (ladder)
UG-17-S05-A100 | UG-11B-S05-A100 | FS | 0 | Crew continuity, front F8
UG-17-S03-A080 | UG-11B-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S04-A080 | UG-11B-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S05-A080 | UG-11B-S05-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11B-S05-A100 | UG-11B-S05-A110 | SS | 1 | Within package (ladder)
UG-11B-S05-A100 | UG-11B-S05-A110 | FF | 2 | Within package (ladder)
UG-17-S03-A010 | UG-17-S03-A020 | FS | 0 | Within package
UG-11B-S05-A030 | UG-17-S03-A020 | SS | 0 | Set-out one package ahead of piling
UG-17-S03-A020 | UG-17-S03-A030 | SS | 2 | Within package (ladder)
UG-17-S03-A020 | UG-17-S03-A030 | FF | 2 | Within package (ladder)
UG-11B-S05-A030 | UG-17-S03-A030 | FS | 0 | Crew continuity, front F8
UG-17-S03-A030 | UG-17-S03-A040 | SS | 6 | Within package (ladder)
UG-17-S03-A030 | UG-17-S03-A040 | FF | 2 | Within package (ladder)
UG-11B-S05-A040 | UG-17-S03-A040 | FS | 0 | Crew continuity, front F8
UG-17-S03-A040 | UG-17-S03-A050 | SS | 4 | Within package (ladder)
UG-17-S03-A040 | UG-17-S03-A050 | FF | 2 | Within package (ladder)
UG-11B-S05-A060 | UG-17-S03-A050 | FS | -16 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-17-S03-A050 | UG-17-S03-A060 | SS | 12 | Within package (ladder)
UG-17-S03-A050 | UG-17-S03-A060 | FF | 2 | Within package (ladder)
UG-11B-S05-A060 | UG-17-S03-A060 | FS | 0 | Crew continuity, front F8
UG-11B-S05-A060 | UG-17-S03-A060 | SS | 0 | Shared excavation / dewatering front
UG-15-S01-A060 | UG-17-S03-A060 | SS | 0 | Shared excavation / dewatering front
UG-15A-S05-A060 | UG-17-S03-A060 | SS | 0 | Shared excavation / dewatering front
UG-15A-S06-A060 | UG-17-S03-A060 | SS | 0 | Shared excavation / dewatering front
UG-15A-S08-A060 | UG-17-S03-A060 | SS | 0 | Shared excavation / dewatering front
UG-17-S03-A060 | UG-17-S03-A070 | SS | 3 | Within package (ladder)
UG-17-S03-A060 | UG-17-S03-A070 | FF | 2 | Within package (ladder)
UG-11B-S05-A070 | UG-17-S03-A070 | FS | 0 | Crew continuity, front F8
UG-17-S03-A070 | UG-17-S03-A080 | SS | 5 | Within package (ladder)
UG-17-S03-A070 | UG-17-S03-A080 | FF | 2 | Within package (ladder)
UG-11B-S05-A080 | UG-17-S03-A080 | FS | 0 | Crew continuity, front F8
UG-17-S03-A080 | UG-17-S03-A090 | SS | 4 | Within package (ladder)
UG-17-S03-A080 | UG-17-S03-A090 | FF | 2 | Within package (ladder)
UG-17-S03-A090 | UG-17-S03-A100 | SS | 2 | Within package (ladder)
UG-17-S03-A090 | UG-17-S03-A100 | FF | 2 | Within package (ladder)
UG-11B-S05-A100 | UG-17-S03-A100 | FS | 0 | Crew continuity, front F8
UG-11B-S05-A080 | UG-17-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11B-S06-A080 | UG-17-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15-S01-A080 | UG-17-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15A-S04-A080 | UG-17-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15A-S05-A080 | UG-17-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15A-S06-A080 | UG-17-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15A-S08-A080 | UG-17-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-18-S02-A080 | UG-17-S03-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S03-A100 | UG-17-S03-A110 | SS | 2 | Within package (ladder)
UG-17-S03-A100 | UG-17-S03-A110 | FF | 2 | Within package (ladder)
UG-18-S02-A010 | UG-18-S02-A020 | FS | 0 | Within package
UG-17-S03-A030 | UG-18-S02-A020 | SS | 0 | Set-out one package ahead of piling
UG-18-S02-A020 | UG-18-S02-A030 | SS | 2 | Within package (ladder)
UG-18-S02-A020 | UG-18-S02-A030 | FF | 2 | Within package (ladder)
UG-17-S03-A030 | UG-18-S02-A030 | FS | 0 | Crew continuity, front F8
UG-18-S02-A030 | UG-18-S02-A040 | SS | 9 | Within package (ladder)
UG-18-S02-A030 | UG-18-S02-A040 | FF | 2 | Within package (ladder)
UG-17-S03-A040 | UG-18-S02-A040 | FS | 0 | Crew continuity, front F8
UG-18-S02-A040 | UG-18-S02-A050 | SS | 6 | Within package (ladder)
UG-18-S02-A040 | UG-18-S02-A050 | FF | 2 | Within package (ladder)
UG-17-S03-A060 | UG-18-S02-A050 | FS | -20 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-18-S02-A050 | UG-18-S02-A060 | SS | 13 | Within package (ladder)
UG-18-S02-A050 | UG-18-S02-A060 | FF | 2 | Within package (ladder)
UG-17-S03-A060 | UG-18-S02-A060 | FS | 0 | Crew continuity, front F8
UG-15A-S05-A060 | UG-18-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-17-S02-A060 | UG-18-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-17-S03-A060 | UG-18-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-17-S04-A060 | UG-18-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-17-S05-A060 | UG-18-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-20-S02-A060 | UG-18-S02-A060 | SS | 0 | Shared excavation / dewatering front
UG-18-S02-A060 | UG-18-S02-A070 | SS | 5 | Within package (ladder)
UG-18-S02-A060 | UG-18-S02-A070 | FF | 2 | Within package (ladder)
UG-17-S03-A070 | UG-18-S02-A070 | FS | 0 | Crew continuity, front F8
UG-18-S02-A070 | UG-18-S02-A080 | SS | 7 | Within package (ladder)
UG-18-S02-A070 | UG-18-S02-A080 | FF | 2 | Within package (ladder)
UG-17-S03-A080 | UG-18-S02-A080 | FS | 0 | Crew continuity, front F8
UG-18-S02-A080 | UG-18-S02-A090 | SS | 6 | Within package (ladder)
UG-18-S02-A080 | UG-18-S02-A090 | FF | 2 | Within package (ladder)
UG-18-S02-A090 | UG-18-S02-A100 | SS | 2 | Within package (ladder)
UG-18-S02-A090 | UG-18-S02-A100 | FF | 2 | Within package (ladder)
UG-17-S03-A100 | UG-18-S02-A100 | FS | 0 | Crew continuity, front F8
UG-15A-S05-A080 | UG-18-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S01-A080 | UG-18-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S02-A080 | UG-18-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S03-A080 | UG-18-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S04-A080 | UG-18-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S05-A080 | UG-18-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-20-S02-A080 | UG-18-S02-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-18-S02-A100 | UG-18-S02-A110 | SS | 3 | Within package (ladder)
UG-18-S02-A100 | UG-18-S02-A110 | FF | 2 | Within package (ladder)
UG-11B-S06-A010 | UG-11B-S06-A020 | FS | 0 | Within package
UG-18-S02-A030 | UG-11B-S06-A020 | SS | 0 | Set-out one package ahead of piling
UG-11B-S06-A020 | UG-11B-S06-A030 | SS | 1 | Within package (ladder)
UG-11B-S06-A020 | UG-11B-S06-A030 | FF | 2 | Within package (ladder)
UG-18-S02-A030 | UG-11B-S06-A030 | FS | 0 | Crew continuity, front F8
UG-11B-S06-A030 | UG-11B-S06-A040 | SS | 1 | Within package (ladder)
UG-11B-S06-A030 | UG-11B-S06-A040 | FF | 2 | Within package (ladder)
UG-18-S02-A040 | UG-11B-S06-A040 | FS | 0 | Crew continuity, front F8
UG-11B-S06-A040 | UG-11B-S06-A050 | SS | 1 | Within package (ladder)
UG-11B-S06-A040 | UG-11B-S06-A050 | FF | 2 | Within package (ladder)
UG-18-S02-A060 | UG-11B-S06-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-11B-S06-A050 | UG-11B-S06-A060 | SS | 10 | Within package (ladder)
UG-11B-S06-A050 | UG-11B-S06-A060 | FF | 2 | Within package (ladder)
UG-18-S02-A060 | UG-11B-S06-A060 | FS | 0 | Crew continuity, front F8
UG-15A-S05-A060 | UG-11B-S06-A060 | SS | 0 | Shared excavation / dewatering front
UG-17-S03-A060 | UG-11B-S06-A060 | SS | 0 | Shared excavation / dewatering front
UG-17-S04-A060 | UG-11B-S06-A060 | SS | 0 | Shared excavation / dewatering front
UG-11B-S06-A060 | UG-11B-S06-A070 | SS | 1 | Within package (ladder)
UG-11B-S06-A060 | UG-11B-S06-A070 | FF | 2 | Within package (ladder)
UG-18-S02-A070 | UG-11B-S06-A070 | FS | 0 | Crew continuity, front F8
UG-11B-S06-A070 | UG-11B-S06-A080 | SS | 2 | Within package (ladder)
UG-11B-S06-A070 | UG-11B-S06-A080 | FF | 2 | Within package (ladder)
UG-18-S02-A080 | UG-11B-S06-A080 | FS | 0 | Crew continuity, front F8
UG-11B-S06-A080 | UG-11B-S06-A090 | SS | 1 | Within package (ladder)
UG-11B-S06-A080 | UG-11B-S06-A090 | FF | 2 | Within package (ladder)
UG-11B-S06-A090 | UG-11B-S06-A100 | SS | 2 | Within package (ladder)
UG-11B-S06-A090 | UG-11B-S06-A100 | FF | 2 | Within package (ladder)
UG-18-S02-A100 | UG-11B-S06-A100 | FS | 0 | Crew continuity, front F8
UG-15A-S04-A080 | UG-11B-S06-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15A-S05-A080 | UG-11B-S06-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S03-A080 | UG-11B-S06-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S04-A080 | UG-11B-S06-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-11B-S06-A100 | UG-11B-S06-A110 | SS | 1 | Within package (ladder)
UG-11B-S06-A100 | UG-11B-S06-A110 | FF | 2 | Within package (ladder)
UG-15A-S04-A010 | UG-15A-S04-A020 | FS | 0 | Within package
UG-11B-S06-A030 | UG-15A-S04-A020 | SS | 0 | Set-out one package ahead of piling
UG-15A-S04-A020 | UG-15A-S04-A030 | SS | 1 | Within package (ladder)
UG-15A-S04-A020 | UG-15A-S04-A030 | FF | 2 | Within package (ladder)
UG-11B-S06-A030 | UG-15A-S04-A030 | FS | 0 | Crew continuity, front F8
UG-15A-S04-A030 | UG-15A-S04-A040 | SS | 1 | Within package (ladder)
UG-15A-S04-A030 | UG-15A-S04-A040 | FF | 2 | Within package (ladder)
UG-11B-S06-A040 | UG-15A-S04-A040 | FS | 0 | Crew continuity, front F8
UG-15A-S04-A040 | UG-15A-S04-A050 | SS | 1 | Within package (ladder)
UG-15A-S04-A040 | UG-15A-S04-A050 | FF | 2 | Within package (ladder)
UG-11B-S06-A060 | UG-15A-S04-A050 | FS | -10 | Just-in-time dewatering: drawdown complete when excavation crew is free
UG-15A-S04-A050 | UG-15A-S04-A060 | SS | 10 | Within package (ladder)
UG-15A-S04-A050 | UG-15A-S04-A060 | FF | 2 | Within package (ladder)
UG-11B-S06-A060 | UG-15A-S04-A060 | FS | 0 | Crew continuity, front F8
UG-11B-S05-A100 | UG-15A-S04-A060 | FS | 0 | Deeper line first
UG-17-S04-A100 | UG-15A-S04-A060 | FS | 0 | Deeper line first
UG-11B-S06-A060 | UG-15A-S04-A060 | SS | 0 | Shared excavation / dewatering front
UG-17-S03-A060 | UG-15A-S04-A060 | SS | 0 | Shared excavation / dewatering front
UG-15A-S04-A060 | UG-15A-S04-A070 | SS | 1 | Within package (ladder)
UG-15A-S04-A060 | UG-15A-S04-A070 | FF | 2 | Within package (ladder)
UG-11B-S06-A070 | UG-15A-S04-A070 | FS | 0 | Crew continuity, front F8
UG-15A-S04-A070 | UG-15A-S04-A080 | SS | 2 | Within package (ladder)
UG-15A-S04-A070 | UG-15A-S04-A080 | FF | 2 | Within package (ladder)
UG-11B-S06-A080 | UG-15A-S04-A080 | FS | 0 | Crew continuity, front F8
UG-15A-S04-A080 | UG-15A-S04-A090 | SS | 1 | Within package (ladder)
UG-15A-S04-A080 | UG-15A-S04-A090 | FF | 2 | Within package (ladder)
UG-15A-S04-A090 | UG-15A-S04-A100 | SS | 2 | Within package (ladder)
UG-15A-S04-A090 | UG-15A-S04-A100 | FF | 2 | Within package (ladder)
UG-11B-S06-A100 | UG-15A-S04-A100 | FS | 0 | Crew continuity, front F8
UG-11B-S06-A080 | UG-15A-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S03-A080 | UG-15A-S04-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-15A-S04-A100 | UG-15A-S04-A110 | SS | 1 | Within package (ladder)
UG-15A-S04-A100 | UG-15A-S04-A110 | FF | 2 | Within package (ladder)
UG-17-S01-A010 | UG-17-S01-A020 | FS | 0 | Within package
UG-17-S02-A030 | UG-17-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-17-S01-A020 | UG-17-S01-A030 | SS | 1 | Within package (ladder)
UG-17-S01-A020 | UG-17-S01-A030 | FF | 2 | Within package (ladder)
UG-17-S01-A030 | UG-17-S01-A040 | SS | 1 | Within package (ladder)
UG-17-S01-A030 | UG-17-S01-A040 | FF | 0 | Within package (ladder)
UG-17-S01-A040 | UG-17-S01-A050 | SS | 0 | Within package (ladder)
UG-17-S01-A040 | UG-17-S01-A050 | FF | 2 | Within package (ladder)
UG-17-S01-A050 | UG-17-S01-A060 | SS | 10 | Within package (ladder)
UG-17-S01-A050 | UG-17-S01-A060 | FF | 2 | Within package (ladder)
UG-15-S01-A100 | UG-17-S01-A060 | FS | 0 | Deeper line first
UG-22-S01-A100 | UG-17-S01-A060 | FS | 0 | Deeper line first
UG-18-S02-A060 | UG-17-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-17-S01-A060 | UG-17-S01-A070 | SS | 1 | Within package (ladder)
UG-17-S01-A060 | UG-17-S01-A070 | FF | 2 | Within package (ladder)
UG-17-S01-A070 | UG-17-S01-A080 | SS | 2 | Within package (ladder)
UG-17-S01-A070 | UG-17-S01-A080 | FF | 2 | Within package (ladder)
UG-17-S02-A080 | UG-17-S01-A080 | FS | 0 | Tie-in laid as closure
UG-17-S01-A080 | UG-17-S01-A090 | SS | 3 | Within package (ladder)
UG-17-S01-A080 | UG-17-S01-A090 | FF | 2 | Within package (ladder)
UG-17-S01-A090 | UG-17-S01-A100 | SS | 2 | Within package (ladder)
UG-17-S01-A090 | UG-17-S01-A100 | FF | 2 | Within package (ladder)
UG-18-S01-A080 | UG-17-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-18-S02-A080 | UG-17-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S01-A100 | UG-17-S01-A110 | SS | 1 | Within package (ladder)
UG-17-S01-A100 | UG-17-S01-A110 | FF | 2 | Within package (ladder)
UG-18-S01-A010 | UG-18-S01-A020 | FS | 0 | Within package
UG-18-S02-A030 | UG-18-S01-A020 | SS | 0 | Tie-in team follows the adjacent run
UG-18-S01-A020 | UG-18-S01-A030 | SS | 1 | Within package (ladder)
UG-18-S01-A020 | UG-18-S01-A030 | FF | 2 | Within package (ladder)
UG-18-S01-A030 | UG-18-S01-A040 | SS | 1 | Within package (ladder)
UG-18-S01-A030 | UG-18-S01-A040 | FF | 0 | Within package (ladder)
UG-18-S01-A040 | UG-18-S01-A050 | SS | 0 | Within package (ladder)
UG-18-S01-A040 | UG-18-S01-A050 | FF | 2 | Within package (ladder)
UG-18-S01-A050 | UG-18-S01-A060 | SS | 10 | Within package (ladder)
UG-18-S01-A050 | UG-18-S01-A060 | FF | 2 | Within package (ladder)
UG-17-S01-A060 | UG-18-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-17-S02-A060 | UG-18-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-18-S01-A060 | UG-18-S01-A070 | SS | 1 | Within package (ladder)
UG-18-S01-A060 | UG-18-S01-A070 | FF | 2 | Within package (ladder)
UG-18-S01-A070 | UG-18-S01-A080 | SS | 2 | Within package (ladder)
UG-18-S01-A070 | UG-18-S01-A080 | FF | 2 | Within package (ladder)
UG-18-S02-A080 | UG-18-S01-A080 | FS | 0 | Tie-in laid as closure
UG-18-S01-A080 | UG-18-S01-A090 | SS | 3 | Within package (ladder)
UG-18-S01-A080 | UG-18-S01-A090 | FF | 2 | Within package (ladder)
UG-18-S01-A090 | UG-18-S01-A100 | SS | 2 | Within package (ladder)
UG-18-S01-A090 | UG-18-S01-A100 | FF | 2 | Within package (ladder)
UG-17-S01-A080 | UG-18-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-17-S02-A080 | UG-18-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-18-S01-A100 | UG-18-S01-A110 | SS | 1 | Within package (ladder)
UG-18-S01-A100 | UG-18-S01-A110 | FF | 2 | Within package (ladder)
UG-28-S01-A010 | UG-28-S01-A020 | FS | 0 | Within package
UG-28-S01-A020 | UG-28-S01-A030 | SS | 1 | Within package (ladder)
UG-28-S01-A020 | UG-28-S01-A030 | FF | 2 | Within package (ladder)
UG-28-S01-A030 | UG-28-S01-A040 | SS | 1 | Within package (ladder)
UG-28-S01-A030 | UG-28-S01-A040 | FF | 0 | Within package (ladder)
UG-28-S01-A040 | UG-28-S01-A050 | SS | 0 | Within package (ladder)
UG-28-S01-A040 | UG-28-S01-A050 | FF | 0 | Within package (ladder)
UG-28-S01-A050 | UG-28-S01-A060 | SS | 0 | Within package (ladder)
UG-28-S01-A050 | UG-28-S01-A060 | FF | 2 | Within package (ladder)
UG-10-S02-A100 | UG-28-S01-A060 | FS | 0 | Deeper line first
UG-10-S03-A100 | UG-28-S01-A060 | FS | 0 | Deeper line first
UG-21-S01-A100 | UG-28-S01-A060 | FS | 0 | Deeper line first
UG-22-S01-A100 | UG-28-S01-A060 | FS | 0 | Deeper line first
UG-28-S01-A060 | UG-28-S01-A070 | SS | 1 | Within package (ladder)
UG-28-S01-A060 | UG-28-S01-A070 | FF | 2 | Within package (ladder)
UG-28-S01-A070 | UG-28-S01-A080 | SS | 2 | Within package (ladder)
UG-28-S01-A070 | UG-28-S01-A080 | FF | 2 | Within package (ladder)
UG-28-S01-A080 | UG-28-S01-A090 | SS | 2 | Within package (ladder)
UG-28-S01-A080 | UG-28-S01-A090 | FF | 2 | Within package (ladder)
UG-28-S01-A090 | UG-28-S01-A100 | SS | 2 | Within package (ladder)
UG-28-S01-A090 | UG-28-S01-A100 | FF | 2 | Within package (ladder)
UG-28A-S01-A080 | UG-28-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-28-S01-A100 | UG-28-S01-A110 | SS | 1 | Within package (ladder)
UG-28-S01-A100 | UG-28-S01-A110 | FF | 0 | Within package (ladder)
UG-28A-S01-A010 | UG-28A-S01-A020 | FS | 0 | Within package
UG-28A-S01-A020 | UG-28A-S01-A030 | SS | 1 | Within package (ladder)
UG-28A-S01-A020 | UG-28A-S01-A030 | FF | 2 | Within package (ladder)
UG-28A-S01-A030 | UG-28A-S01-A040 | SS | 1 | Within package (ladder)
UG-28A-S01-A030 | UG-28A-S01-A040 | FF | 0 | Within package (ladder)
UG-28A-S01-A040 | UG-28A-S01-A050 | SS | 0 | Within package (ladder)
UG-28A-S01-A040 | UG-28A-S01-A050 | FF | 0 | Within package (ladder)
UG-28A-S01-A050 | UG-28A-S01-A060 | SS | 0 | Within package (ladder)
UG-28A-S01-A050 | UG-28A-S01-A060 | FF | 2 | Within package (ladder)
UG-10-S02-A100 | UG-28A-S01-A060 | FS | 0 | Deeper line first
UG-10-S03-A100 | UG-28A-S01-A060 | FS | 0 | Deeper line first
UG-21-S01-A100 | UG-28A-S01-A060 | FS | 0 | Deeper line first
UG-22-S01-A100 | UG-28A-S01-A060 | FS | 0 | Deeper line first
UG-28-S02-A100 | UG-28A-S01-A060 | FS | 0 | Deeper line first
UG-28-S01-A060 | UG-28A-S01-A060 | SS | 0 | Shared excavation / dewatering front
UG-28A-S01-A060 | UG-28A-S01-A070 | SS | 1 | Within package (ladder)
UG-28A-S01-A060 | UG-28A-S01-A070 | FF | 2 | Within package (ladder)
UG-28A-S01-A070 | UG-28A-S01-A080 | SS | 2 | Within package (ladder)
UG-28A-S01-A070 | UG-28A-S01-A080 | FF | 2 | Within package (ladder)
UG-28A-S01-A080 | UG-28A-S01-A090 | SS | 3 | Within package (ladder)
UG-28A-S01-A080 | UG-28A-S01-A090 | FF | 2 | Within package (ladder)
UG-28A-S01-A090 | UG-28A-S01-A100 | SS | 2 | Within package (ladder)
UG-28A-S01-A090 | UG-28A-S01-A100 | FF | 2 | Within package (ladder)
UG-28-S01-A080 | UG-28A-S01-A100 | FS | 0 | Shared trench: all pipes laid before backfill
UG-28A-S01-A100 | UG-28A-S01-A110 | SS | 1 | Within package (ladder)
UG-28A-S01-A100 | UG-28A-S01-A110 | FF | 0 | Within package (ladder)

## Programme
Programme summary and monthly bar chart
Bars recalculate from the Activities sheet. Rows: fronts, then lines. Shaded month = package work active on that line or front.
Front / line | Description | Packages | Length (m) | Shored (m) | Piles (no.) | Excavation (m3) | Start | Finish | Months | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01
Fronts
F1 | Headworks & primary (GRT-PST-IPS) | 15 | 800.3519 | 800.3519 | 569 | 18194.4326 | 2026-12-01 | 2027-06-24 | 6.7434 | 1 | 1 | 1 | 1 | 1 | 1 | 1
F2 | Bypass corridor: IPS bypass and outfall twin | 14 | 1724.1875 | 1567.3564 | 1196 | 29084.0475 | 2026-12-01 | 2027-07-22 | 7.6645 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
F3 | Distribution & FCT risers | 30 | 1094.7783 | 648.7086 | 800 | 19831.8731 | 2026-12-01 | 2027-07-26 | 7.7961 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
F4 | FCT effluent A-H to CCT | 22 | 550.5855 | 308.432 | 436 | 7672.2141 | 2026-12-01 | 2027-08-22 | 8.6842 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
F5 | FCT effluent I-L to CCT | 22 | 570.5608 | 254.1972 | 452 | 8748.604 | 2026-12-01 | 2027-09-18 | 9.5724 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
F6 | Sludge A-D,G,H to RAS/WAS + UG-23 | 34 | 1164.3496 | 839.9423 | 765 | 16149.8614 | 2026-12-01 | 2027-08-08 | 8.2237 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
F7 | Sludge I-L,E,F to RAS/WAS | 38 | 868.0987 | 816.1554 | 585 | 14084.8614 | 2026-12-01 | 2027-08-07 | 8.1908 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
F8 | Effluent, outfall & CCT links | 26 | 1378.4556 | 1326.4495 | 985 | 20827.1497 | 2026-12-01 | 2027-07-04 | 7.0724 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Lines
UG-01 | F1 ¦ GRP DN2500 ¦ New grit removal and fine screens to New primary sedimentation tanks | 3 | 324.2759 | 324.2759 | 215 | 7889.5844 | 2026-12-01 | 2027-03-06 | 3.125 | 1 | 1 | 1 | 1
UG-02 | F1 ¦ GRP DN2000 ¦ New primary sedimentation tanks to Intermediate pumping station | 5 | 267.3619 | 267.3619 | 194 | 5798.4474 | 2026-12-03 | 2027-06-09 | 6.1842 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-03 | F1 ¦ GRP DN2000 ¦ Existing primary sedimentation tanks to Intermediate pumping station | 5 | 186.0592 | 186.0592 | 138 | 4033.5588 | 2027-02-12 | 2027-06-24 | 4.3421 |  |  | 1 | 1 | 1 | 1 | 1
UG-04 | F1 ¦ GRP DN2000 ¦ Existing primary sedimentation tanks to Intermediate pumping station | 2 | 22.6549 | 22.6549 | 22 | 472.8419 | 2027-03-18 | 2027-06-18 | 3.0263 |  |  |  | 1 | 1 | 1 | 1
UG-05 | F2 ¦ GRP DN2200 ¦ Intermediate station bypass to Chamber connecting UG25 | 5 | 306.5174 | 206.5174 | 220 | 6219.5817 | 2027-02-27 | 2027-07-18 | 4.6382 |  |  | 1 | 1 | 1 | 1 | 1 | 1
UG-06 | F2 ¦ GRP DN2200 ¦ Intermediate station bypass to Chamber connecting UG25 | 5 | 299.9072 | 299.9072 | 216 | 4331.4844 | 2026-12-01 | 2027-06-03 | 6.0526 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-07 | F4/F5 ¦ GRP DN2000 ¦ FCT E,F,G,H to Chlorine contact tank | 4 | 86.7273 | 64.466 | 70 | 1570.7605 | 2026-12-11 | 2027-04-23 | 4.375 | 1 | 1 | 1 | 1 | 1
UG-07A | F4/F7 ¦ HDPE OD1600 ¦ FCT E,F,G,H to Chlorine contact tank | 12 | 370.9254 | 167.1876 | 284 | 4311.4634 | 2026-12-29 | 2027-08-22 | 7.7632 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-12 | F5/F7 ¦ GRP DN2000 ¦ FCT I,J,K,L to Chlorine contact tank | 8 | 232.7084 | 172.7084 | 184 | 4957.3787 | 2026-12-01 | 2027-07-28 | 7.8618 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-12A | F5 ¦ HDPE DN1600 as printed ¦ FCT I,J,K,L to Chlorine contact tank | 12 | 346.3712 | 76.1076 | 268 | 4517.2467 | 2027-01-10 | 2027-09-18 | 8.2566 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-15 | F4/F8 ¦ GRP DN2000 ¦ FCT A,B,C,D to Chlorine contact tank | 6 | 167.9976 | 167.9976 | 132 | 3141.7809 | 2026-12-01 | 2027-01-27 | 1.875 | 1 | 1
UG-15A | F4/F8 ¦ HDPE OD1600 ¦ FCT A,B,C,D to Chlorine contact tank | 10 | 258.7338 | 238.7338 | 204 | 3511.1332 | 2026-12-02 | 2027-07-06 | 7.1053 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-08 | F3 ¦ GRP DN2600 ¦ Aeration / FCT main distribution chamber to Secondary distribution chamber I,J,K,L | 7 | 283.1139 | 149.5009 | 206 | 5640.3874 | 2026-12-18 | 2027-07-22 | 7.1053 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-09 | F3 ¦ GRP DN2600 ¦ Aeration / FCT main distribution chamber to Secondary distribution chamber E,F,G,H | 8 | 287.799 | 137.799 | 214 | 5874.4255 | 2027-01-05 | 2027-07-26 | 6.6447 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-10 | F3 ¦ GRP DN2600 ¦ Aeration / FCT main distribution chamber to Secondary distribution chamber A,B,C,D | 5 | 205.5987 | 186.9547 | 150 | 3188.7792 | 2026-12-01 | 2027-03-13 | 3.3553 | 1 | 1 | 1 | 1
UG-11 | F5/F6 ¦ GRP DN2000 ¦ FCT sludge A,B,C,D,G,H to RAS/WAS pumping station | 6 | 189.3502 | 189.3502 | 144 | 4448.5968 | 2026-12-01 | 2027-03-12 | 3.3224 | 1 | 1 | 1 | 1
UG-11A | F6 ¦ HDPE OD1400 ¦ FCT sludge A,B,C,D,G,H to RAS/WAS pumping station | 7 | 206.0309 | 206.0309 | 152 | 2358.3885 | 2026-12-02 | 2027-08-08 | 8.1908 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-11B | F3/F5/F6/F8 ¦ HDPE OD1400 ¦ FCT sludge A,B,C,D,G,H to RAS/WAS pumping station | 14 | 500.7365 | 500.7365 | 366 | 6077.9766 | 2026-12-02 | 2027-06-29 | 6.875 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-13 | F7 ¦ GRP DN2000 ¦ FCT sludge I,J,K,L,E,F to RAS/WAS pumping station | 5 | 166.2127 | 166.2127 | 124 | 3492.6808 | 2026-12-11 | 2027-06-27 | 6.5132 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-13A | F3/F7 ¦ HDPE OD1400 ¦ FCT sludge I,J,K,L,E,F to RAS/WAS pumping station | 16 | 257.9106 | 257.9106 | 177 | 3388.8037 | 2027-02-28 | 2027-08-06 | 5.2303 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-13B | F3/F7 ¦ HDPE OD1400 ¦ FCT sludge I,J,K,L,E,F to RAS/WAS pumping station | 12 | 294.3979 | 294.3979 | 174 | 3741.7125 | 2026-12-01 | 2027-06-01 | 5.9868 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-14E | F3 ¦ HDPE OD1600 ¦ Secondary distribution chamber E,F,G,H to FCT E | 1 | 37.5876 | 0 | 28 | 1001.0676 | 2026-12-01 | 2027-06-01 | 5.9868 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-14F | F3 ¦ HDPE OD1600 ¦ Secondary distribution chamber E,F,G,H to FCT F | 1 | 38.0885 | 28.0375 | 28 | 417.5864 | 2026-12-01 | 2027-05-25 | 5.7566 | 1 | 1 | 1 | 1 | 1 | 1
UG-14G | F6 ¦ HDPE OD1600 ¦ Secondary distribution chamber E,F,G,H to FCT G | 1 | 38.2988 | 0 | 28 | 988.5207 | 2026-12-01 | 2027-07-30 | 7.9276 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-14H | F6 ¦ HDPE OD1600 ¦ Secondary distribution chamber E,F,G,H to FCT H | 1 | 38.1766 | 0 | 28 | 988.3716 | 2026-12-01 | 2027-08-08 | 8.2237 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-16A | F6 ¦ HDPE OD1600 ¦ Secondary distribution chamber A,B,C,D to FCT A | 1 | 37.7775 | 27.7775 | 28 | 394.9017 | 2026-12-01 | 2027-06-10 | 6.2829 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-16B | F3 ¦ HDPE OD1600 ¦ Secondary distribution chamber A,B,C,D to FCT B | 1 | 38.1234 | 28.004 | 28 | 399.9639 | 2026-12-01 | 2027-05-11 | 5.2961 | 1 | 1 | 1 | 1 | 1 | 1
UG-16C | F6 ¦ HDPE OD1600 ¦ Secondary distribution chamber A,B,C,D to FCT C | 1 | 38.3838 | 0 | 28 | 1012.689 | 2026-12-01 | 2027-06-21 | 6.6447 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-16D | F6 ¦ HDPE OD1600 ¦ Secondary distribution chamber A,B,C,D to FCT D | 1 | 36.3001 | 26.3001 | 28 | 376.8448 | 2026-12-01 | 2027-06-27 | 6.8421 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-27I | F7 ¦ HDPE OD1600 ¦ Secondary distribution chamber I,J,K,L to FCT I | 1 | 37.5872 | 0.83997 | 28 | 974.9083 | 2026-12-01 | 2027-08-07 | 8.1908 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-27J | F3 ¦ HDPE OD1600 ¦ Secondary distribution chamber I,J,K,L to FCT J | 2 | 38.0646 | 0.12144 | 32 | 996.6937 | 2026-12-01 | 2027-07-17 | 7.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-27K | F3 ¦ HDPE OD1600 ¦ Secondary distribution chamber I,J,K,L to FCT K | 1 | 37.7244 | 27.7244 | 28 | 390.9293 | 2026-12-01 | 2027-07-23 | 7.6974 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-27L | F3 ¦ HDPE OD1600 ¦ Secondary distribution chamber I,J,K,L to FCT L | 1 | 38.1115 | 0 | 28 | 998.2598 | 2026-12-01 | 2027-07-11 | 7.3026 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-17 | F8 ¦ GRP DN2200 ¦ Effluent maneuvering overflow / bypass sump to Outfall chamber at lake | 5 | 368.0735 | 348.0735 | 262 | 6008.3026 | 2026-12-09 | 2027-06-22 | 6.4145 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UG-18 | F8 ¦ GRP DN2200 ¦ Effluent maneuvering overflow / bypass sump to Outfall chamber at lake | 2 | 375.0609 | 364.5418 | 256 | 5937.54 | 2027-02-09 | 2027-07-04 | 4.7697 |  |  | 1 | 1 | 1 | 1 | 1 | 1
UG-19 | F8 ¦ GRP DN1800 ¦ Effluent sump to Treated effluent pump | 3 | 115.2421 | 115.2421 | 86 | 1642.9328 | 2026-12-15 | 2027-05-21 | 5.1645 | 1 | 1 | 1 | 1 | 1 | 1
UG-20 | F8 ¦ GRP DN1800 ¦ Effluent sump to Treated effluent pump | 2 | 109.7253 | 109.7253 | 78 | 1570.0578 | 2026-12-20 | 2027-05-21 | 5 | 1 | 1 | 1 | 1 | 1 | 1
UG-21 | F8 ¦ GRP DN2200 ¦ Chlorine contact tank to Fire / service / cold water feed tanks | 1 | 12.2026 | 12.2026 | 12 | 289.0006 | 2026-12-01 | 2026-12-28 | 0.88816 | 1
UG-22 | F8 ¦ GRP DN2200 ¦ Chlorine contact tank to Fire / service / cold water feed tanks | 1 | 12.2104 | 12.2104 | 12 | 289.1853 | 2026-12-01 | 2026-12-28 | 0.88816 | 1
UG-23 | F6/F7 ¦ HDPE OD600 ¦ RAS/WAS pumping station to Pre-dewatering building | 10 | 294.0926 | 104.5445 | 113 | 2262.837 | 2027-01-04 | 2027-05-03 | 3.9145 |  | 1 | 1 | 1 | 1 | 1
UG-24 | F2 ¦ GRP DN2000 ¦ Existing primary sedimentation overflow to Intermediate bypass chamber | 2 | 126.8311 | 70 | 92 | 1734.3306 | 2027-04-12 | 2027-07-22 | 3.3224 |  |  |  |  | 1 | 1 | 1 | 1
UG-25 | F2 ¦ GRP DN2400 ¦ Overflow bypass chamber to Outfall chamber | 1 | 495.2172 | 495.2172 | 334 | 8609.0665 | 2026-12-02 | 2027-05-15 | 5.3947 | 1 | 1 | 1 | 1 | 1 | 1
UG-26 | F2 ¦ GRP DN2400 ¦ Overflow bypass chamber to Outfall chamber | 1 | 495.7146 | 495.7146 | 334 | 8189.5843 | 2026-12-06 | 2027-05-25 | 5.5921 | 1 | 1 | 1 | 1 | 1 | 1
UG-28 | F8 ¦ HDPE OD500 ¦ Chlorine contact tank to Service water channel | 2 | 13.5454 | 12.4454 | 8 | 152.4565 | 2026-12-01 | 2027-03-19 | 3.5526 | 1 | 1 | 1 | 1
UG-28A | F8 ¦ HDPE OD315 ¦ Chlorine contact tank to Service water channel | 1 | 17.8374 | 0 | 7 | 0 | 2026-12-01 | 2027-03-21 | 3.6184 | 1 | 1 | 1 | 1
Packages with this activity in the month (sequential packages in a front all count; not concurrent crews)
A030 | Piling | [8 empty] | 64 | 52 | 39 | 45 | 28 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A040 | Sheet piling | [8 empty] | 52 | 30 | 29 | 38 | 24 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A050 | Dewatering install/drawdown | [8 empty] | 52 | 42 | 27 | 49 | 48 | 14 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A060 | Excavation | [8 empty] | 25 | 36 | 23 | 44 | 48 | 25 | 15 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A070 | Piled slab | [8 empty] | 22 | 32 | 30 | 36 | 46 | 33 | 29 | 17 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A080 | Pipe laying | [8 empty] | 17 | 23 | 30 | 29 | 35 | 35 | 32 | 31 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A100 | Backfill | [8 empty] | 5 | 19 | 17 | 21 | 22 | 46 | 39 | 37 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Piles | Pipe-support piles per month (spread evenly over each piling activity) | [8 empty] | 1658.854 | 1255.1697 | 1149.7955 | 1181.0483 | 539.7325 | 46.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rigs | Equivalent piling rigs needed (piles per month / (R_PILE x WD x 52/12)) | [8 empty] | 12.7604 | 9.6552 | 8.8446 | 9.085 | 4.1518 | 0.36077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sensitivity
Sheet-pile length under different ground / groundwater rules
Yellow = edit any scenario. Uses the Piece check geometry; the live programme uses the Inputs values (row "Current inputs").
Scenario | Slope above GWL (H:V) | Slope below GWL (H:V) | Max open-cut depth below GWL (m) | Sheet-piled length (m) | Share of 8,151 m | Note
Package workbook basis (no groundwater) | 1.5 | 1.5 | 99 | 1971.6332 | 24.19% | Reproduces the 1,972 m shoring of the v3 package workbook.
Flatter slope below GWL only | 1.5 | 2 | 99 | 2635.1253 | 32.33% | Space check only; no depth limit.
Depth limit 3.0 m below GWL | 1.5 | 2 | 3 | 4543.4972 | 55.74%
Depth limit 2.5 m below GWL | 1.5 | 2 | 2.5 | 6561.5933 | 80.5% | Default in Inputs.
Depth limit 2.0 m below GWL | 1.5 | 2 | 2 | 6913.4222 | 84.81%
Everything below GWL sheet-piled | 1.5 | 2 | 0 | 8092.5249 | 99.28% | Open cut only where the excavation stays above GWL.
Current inputs | 1.5 | 2 | 2.5 | 6561.5933 | 80.5% | Linked to Inputs.